## Sheet1
Selected line | Plant | Created on | Change date for order master | Basic start date | Basic finish date | Notification | Order | Superior order | Description | Location | Equipment | User Status | System status | Planner group | WBS order header | Total planned costs | Total actual costs | Main work center | Purchase order number | Last changed by | Actual Order Finish Date | Actual release date | Order Type | Priority | Reservation/Purc.req | Reference date | Priority type | Maintenance Plan | MaintActivityType | Criticallity | Date Update
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 |  | 8202243778 | 8202243768 | Welder Pipe Fitter Tahap 19 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 54221000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 |  | 8202243777 | 8202243768 | Welder Pipe Fitter Tahap 18 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 128853000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 |  | 8202243775 | 8202243768 | Welder Pipe Fitter Tahap 17 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 54916000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 |  | 8202243774 | 8202243768 | Welder Pipe Fitter Tahap 16 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 53801000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 |  | 8202243773 | 8202243768 | Welder Pipe Fitter Tahap 15 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 54326000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 |  | 8202243772 | 8202243768 | Welder Pipe Fitter Tahap 14 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 54650000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 |  | 8202243770 | 8202243768 | Welder Pipe Fitter Tahap 13 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 60773000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-09-07 | 2102369843 | 8202243768 |  | Welder Pipe Fitter Tahap 12 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 53619000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K202 | 2026-06-08 | 2026-06-11 | 2026-05-18 | 2026-05-18 | 2102369151 | 8202243673 |  | Vibrasi tinggi Pompa 900-02P1-A WTP | RU2S-KIL | 900-02P-1A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 0 | 2933796 | MAS-ME1 |  | JUNAIDIT |  | 2026-06-09 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-03-03 | 2026-03-06 | 2026-03-04 | 2026-12-04 | 2102364963 | 8202239405 |  | Vibrasi tinggi pada pompa G-5-01A | RU5-E15111 | G-5-01A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 2309866 | 0 | MA2-ROT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K201 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-17 | 2102366911 | 8202242432 |  | Vibrasi Tinggi 212-P-18B | RU2-HCC | 212-P-18B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 1715354 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K201 | 2026-04-15 |  | 2026-06-16 | 2026-06-17 | 2102365892 | 8202242456 |  | Vibrasi Tinggi | RU2-HCC | 212-EF-22B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/RT-D2H | 431800 | 0 | MA2-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-16 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102360596 | 8202243971 |  | Vibrasi Tinggi | RU2-HCC | 211-P-9A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 2157695 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K601 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-10-14 | 2102368077 | 8202242494 |  | Verifikasi bejana ukur dan meter prover | RU6-ITP | MP-B40-02/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 300000001 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-06-04 | 2026-06-08 | 2026-06-03 | 2026-07-16 | 2102369528 | 8202243629 |  | Valve Unloading to Lorry passing | RU6-RCC | 15-V-104/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 26395273 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-04-09 | 2026-04-09 | 2026-02-24 | 2026-02-24 | 2102364769 | 8202242290 |  | VALVE K-19-01 PASSING (UNIT RATE) | RU5-E15112 | K-19-01B/00 | 01 | CLSD CSER NCMP NMAT PRC | 5RR | D15/10/B6/RT1-19NH | 0 | 0 | MA2-ROT |  | YONZHETG |  |  | PT02 | 3 | 2 | 2026-04-09 | PM |  | 003
| K501 | 2026-04-02 | 2026-05-08 | 2026-06-08 | 2026-06-08 | 2102367093 | 8202242020 |  | V BELT EA-1-21T RUSAK | RU5-E15111 | EA-1-21T/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1680504 | 0 | MA2-ROT |  | FAUZANR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-06-08 | PM |  | 003
| K501 | 2026-04-22 | 2026-05-12 | 2026-03-30 | 2026-06-09 | 2102366997 | 8202242661 |  | UR. TAG-4 PERB. BORDES MA2 | RU5-E15111 |  | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 134563000 | 134563000 | MA2-STA |  | DWIYUDAAM |  | 2026-04-27 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 045
| K601 | 2026-04-23 | 2026-05-04 | 2026-02-06 | 2026-07-03 | 2102362682 | 8202242682 |  | Unitprice OH & Rewinding Motor LV Thp 3 | RU6-HSC | 32-P-104A-M/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 112620750 | WS-LIS |  | DINDINS |  | 2026-04-23 | PT02 | 5 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-05-18 | 2026-05-18 | 2026-04-10 | 2026-12-31 |  | 8202243243 | 8202242538 | Unit Price Open Sewer DHC Thp 2 | RU6-DHC | 22-OS-901/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 117000000 | 99450000 | MA2-STA |  | DANDARWANI |  | 2026-05-18 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K301 | 2026-04-14 | 2026-04-14 | 2026-01-01 | 2026-12-31 | 2102353286 | 8202242406 |  | Underground Sewer & Open Sewer Area CDL |  |  | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-LIS |  | RRAMADHANI |  |  | PT02 | 6 | 2 | 2026-01-01 | PM |  | 045
| K501 | 2026-03-27 | 2026-04-27 | 2026-03-02 | 2026-12-31 | 2102365190 | 8202241903 |  | Turbine GT-3-08B Repetitive Failure | RU5-E15112 | GT-3-08B/00 | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 300000000 | 0 | MA3-ROT |  | MANKURNIAWAN |  | 2026-04-27 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-02-23 | 2026-03-05 | 2026-04-01 | 2026-07-06 | 2102358733 | 8202239029 |  | TSA PM PLC HIMA (2) | RU5-UTL | G-32-05A-INST/00 | 60 | CLSD NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 259682000 | 0 | MA1-INT |  | RUDIEKO |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-23 | 2026-04-06 | 2026-02-24 | 2026-03-31 | 2102359472 | 8202239014 |  | TSA PM BERTH AID SYS (1) | RU5-TBL | 22-XCV-113/00 | 01 | CLSD NCMP NMAT PRC | 5IR | D15/26/B6/RT-C2H | 236536000 | 0 | MA4-INT |  | RIANDAADI |  |  | PT02 | 3 | 2 | 2026-04-06 | PM |  | 045
| K201 | 2026-04-21 | 2026-04-21 | 2026-12-02 | 2026-12-02 |  | 8202242619 | 8202242593 | TSA PEMELIHARAAN/ PENGGANTIAN MECHANICAL | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 600000000 | 0 | MA2-STA |  | STEVANEKOPP |  | 2026-04-21 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-04-21 | 2026-06-09 | 2026-12-02 | 2026-12-02 |  | 8202242622 | 8202241699 | TSA PEMELIHARAAN/ PENGGANTIAN MECHANICAL | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-06-09 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K401 | 2026-04-06 | 2026-06-21 | 2026-04-02 | 2026-12-30 | 2102367314 | 8202242089 |  | TSA pemeliharaan sparing HB 66 | RU4-TRML | 66FT001/00 | 50 | CRTD NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 1200000000 | 0 | MA1-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-04-02 | PM |  | 045
| K201 | 2026-04-20 | 2026-04-21 | 2026-10-02 | 2026-10-02 |  | 8202242593 | 8202241699 | TSA MECHANICAL SEAL JOHN CRANE UNTUK POM | RU2-HCC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 411341000 | 411341000 | MA2-STA |  | ADEMULYADI |  | 2026-04-21 | PT02 | 3 | 3 | 2026-10-02 | PM |  | 045
| K201 | 2026-04-27 | 2026-04-27 | 2026-12-07 | 2026-12-07 |  | 8202242764 | 8202238699 | TSA LAMPU EMERGENCY AREA KILANG SP 3950 | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 127160000 | 0 | MA2-LIS |  | STEVANEKOPP |  | 2026-04-27 | PT02 |  | 3 | 2026-12-07 | PM |  | 045
| K201 | 2026-03-09 | 2026-03-13 | 2026-02-11 | 2026-02-11 | 2102364163 | 8202241480 |  | TSA Lampu Emergency Area HCC | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 300000000 | 0 | MA2-LIS |  | STEVANEKOPP |  | 2026-03-13 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 045
| K201 | 2026-05-08 | 2026-05-26 | 2026-12-11 | 2026-12-11 |  | 8202243098 | 8202241483 | TSA EMELIHARAAN MECHSEAL FLOW SERVE UNTU | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 3470742000 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-05-08 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K401 | 2026-05-25 | 2026-05-26 | 2026-05-19 | 2026-05-19 | 2102369172 | 8202243468 |  | Transmitter 120PIC015A rusak | RU4-GTO |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-26 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-21 | 2026-06-15 | 2026-12-30 | 2102369989 | 8202243898 |  | TKDN TGH1&2_24 UP Piping LOC II |  |  | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 80667000 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 045
| K401 | 2026-04-06 | 2026-04-07 | 2026-04-01 | 2026-12-30 | 2102367192 | 8202242063 |  | TKDN TGH1_24 UP Piping FOC II |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 120499800 | 120499800 | MA2-STA |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 045
| K401 | 2026-06-17 |  | 2026-06-09 | 2026-06-09 | 2102369810 | 8202243909 |  | TI pompa sundyne 240P015 rusak | RU4-LOC3 | 240P105/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 2 | 2 | 2026-06-09 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-09 | 2026-06-09 | 2102369811 | 8202243908 |  | TI pompa sundyne 041P303 rusak | RU4-TRML | 041P303/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 2 | 2 | 2026-06-09 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369791 | 8202243921 |  | TI pelumas 89P208B rusak | RU4-KPC | 89P208B/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369790 | 8202243920 |  | TI pelumas 89P208A rusak | RU4-KPC | 89P208A/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369777 | 8202243919 |  | TI pelumas 85P217B rusak | RU4-KPC | 85P217B/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369776 | 8202243918 |  | TI pelumas 85P217A rusak | RU4-KPC | 85P217A/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369775 | 8202243917 |  | TI pelumas 84P206B rusak | RU4-KPC | 84P206B/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369774 | 8202243916 |  | TI pelumas 84P206A rusak | RU4-KPC | 84P206A/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369779 | 8202243915 |  | TI pelumas 84P203B rusak | RU4-KPC | 84P203B/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369778 | 8202243914 |  | TI pelumas 84P203A rusak | RU4-KPC | 84P203A/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369773 | 8202243913 |  | TI pelumas 82P205 rusak | RU4-KPC | 82P205/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369772 | 8202243912 |  | TI pelumas 39P204B rusak | RU4-KPC | 39P204B/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369771 | 8202243911 |  | TI pelumas 39P204A rusak | RU4-KPC | 39P204A/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-08 | 2026-06-08 | 2102369770 | 8202243910 |  | TI pelumas 39P201 rusak | RU4-KPC | 39P201/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 003
| K601 | 2026-04-23 | 2026-04-23 | 2026-01-19 | 2026-06-11 |  | 8202242684 | 8202236568 | Thp 5 PM Mekanik MA 3 | RU6-HSC | 32-R-102/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 114226000 | 114226000 | MA3-STA |  | DANDARWANI |  | 2026-04-23 | PT02 | 5 | 3 | 2026-01-19 | PM |  | 004
| K601 | 2026-05-05 | 2026-05-05 | 2026-03-06 | 2026-07-29 |  | 8202242982 | 8202242227 | Thp 4 Volume Pemeliharaan Rutin MA2 | RU6-DHC | 12-R-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 69461000 | 69461000 | MA2-STA |  | DANDARWANI |  | 2026-05-05 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 004
| K601 | 2026-04-06 | 2026-04-06 | 2026-01-19 | 2026-04-22 |  | 8202242079 | 8202236568 | Thp 4 PM Mekanik MA 3 | RU6-HSC | 32-R-102/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 67105000 | 67105000 | MA3-STA |  | DANDARWANI |  | 2026-04-06 | PT02 |  | 3 | 2026-01-19 | PM |  | 004
| K601 | 2026-04-23 | 2026-04-23 | 2026-03-06 | 2026-07-29 |  | 8202242685 | 8202242227 | Thp 3 rutin volume MA 2 | RU6-DHC | 12-R-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 115915000 | 115915000 | MA2-STA |  | DANDARWANI |  | 2026-04-23 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 004
| K601 | 2026-04-08 | 2026-04-08 | 2026-03-06 | 2026-07-29 |  | 8202242229 | 8202242227 | Thp 2 Volume Pemeliharaan Rutin MA2 | RU6-DHC | 12-R-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 67062000 | 67062000 | MA2-STA |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-03-06 | 2026-07-29 | 2102366280 | 8202242227 |  | Thp 1 Volume Pemeliharaan Rutin MA2 | RU6-DHC | 12-R-101/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 100568000 | 100568000 | MA2-STA |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-06 | 2026-02-09 | 2026-07-06 | 2102363955 | 8202242077 |  | Thp 1 LTSA Cleaning HE 85% (12-E-522CD) | RU6-DHC | 12-E-522C/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 113874500 | 113874500 | MA2-STA |  | DANDARWANI |  | 2026-04-06 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 005
| K401 | 2026-02-26 | 2026-06-18 | 2026-02-20 | 2026-12-30 | 2102364882 | 8202239193 |  | Tghn trmn 1 UP cleaning tanki 60&NBM 25 | RU4-TRML | 31T101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 1585711000 | 1585711000 | MA3-STA |  | FARIZSETYANA |  | 2026-02-27 | PT02 | 5 | 3 | 2026-02-20 | PM |  | 045
| K401 | 2026-06-11 | 2026-06-19 | 2026-06-10 | 2026-12-30 | 2102369880 | 8202243810 |  | TGH9-12_Sewa Alat Berat Opt dan & Crew | RU4-WS | 037BD101-B5/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 1350104000 | 0 | WS-KAB |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-06-10 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-19 | 2026-03-05 | 2026-12-30 |  | 8202239678 | 8202239371 | TGH9_UP Rumput 2025 | RU4-TRML | 30P104A/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 741677000 | 741677000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-30 | 2026-04-21 | 2026-04-02 | 2026-12-30 |  | 8202241916 | 8202241591 | TGH9_24 Jasa LTSA Fire Truk | RU4-WS | FL50/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 80722194 | 80722194 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-05 | 2026-03-03 | 2026-12-30 | 2102365226 | 8202239371 |  | TGH8_UP Rumput 2025 | RU4-TRML | 30P104A/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 766698000 | 766698000 | MA3-STA |  | ALFIANRH |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-05-18 | 2026-05-18 | 2026-04-24 | 2026-12-30 | 2102368332 | 8202243237 |  | TGH8_24 TSA LIGHTNING PROT SYS | RU4-TRML | 30EE101A-50GS/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 339818000 | 339818000 | MA3-LIS |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 4 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-21 | 2026-06-04 | 2026-12-30 | 2102369673 | 8202243701 |  | TGH7_25 UP MON&INSP MOTOR LISTRIK | RU4-LOC1 | 21P17/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 74400000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-10 | 2026-02-11 | 2026-12-30 | 2102364400 | 8202239076 |  | TGH7_24 PM Field Instrument ME I | RU4-KPC | 80FT205/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 297783050 | 297783050 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 | 5 | 3 | 2026-02-11 | PM |  | 003
| K401 | 2026-05-25 | 2026-06-22 | 2026-05-25 | 2026-12-30 | 2102369248 | 8202243464 |  | TGH7_24 PM Field Instr ME II | RU4-RFCUTL | 105FT072/00 | 50 | CRTD CSER NMAT PRC | 4IR |  | 315207200 | 0 | MA6-INT |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-04-24 | 2026-04-24 | 2026-04-16 | 2026-12-30 | 2102368035 | 8202242709 |  | TGH6_25 UP MON&INSP MOTOR LISTRIK | RU4-LOC1 | 21P10AM/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 109000000 | 109000000 | MA1-LIS |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-15 | 2026-02-24 | 2026-12-30 |  | 8202242442 | 8202242440 | TGH6_24 Pemeliharaan dan Perbaikan Diese | RU4-RFCUTL | 152G501A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 339968550 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-15 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 045
| K401 | 2026-04-13 | 2026-04-13 | 2026-04-01 | 2026-12-30 | 2102367191 | 8202242352 |  | TGH6_23 PM ELEVATOR 011S104 | RU4-FOC2 | 011S104/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 272602000 | 272602000 | MA2-LIS |  | WAHYUCATUR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-15 | 2026-03-11 | 2026-12-30 |  | 8202242439 | 8202242438 | TGH5_Skylift General Maintenance | RU4-TRML | 30P108A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 238140000 | 0 | GEN-LIS |  | WAHYUCATUR |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K401 | 2026-03-30 | 2026-03-30 | 2026-03-25 | 2026-12-30 | 2102366939 | 8202241926 |  | TGH5_25 UP MON&INSP MOTOR LISTRIK | RU4-LOC2 | 021E130M06-CB/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 56500000 | 56500000 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-30 | PT02 | 4 | 3 | 2026-03-25 | PM |  | 045
| K401 | 2026-03-16 | 2026-03-16 | 2026-01-02 | 2026-12-30 |  | 8202241727 | 8202237808 | TGH5_24 TSA Online Analyzer Teledyne | RU4-RFCC | 102FT049/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 645016000 | 645016000 | MA6-INT |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-13 | 2026-04-01 | 2026-12-30 | 2102367190 | 8202242351 |  | TGH5_23 PM ELEVATOR 011S104 | RU4-FOC2 | 011S104/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 89775000 | 89775000 | MA2-LIS |  | WAHYUCATUR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-04-30 | 2026-04-30 | 2026-03-17 | 2026-12-30 | 2102366765 | 8202242894 |  | TGH4-5_Sewa Forklift Gudang Katalis RFCC | RU4-REL |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 164295000 | 164295000 | MA6-STA |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 8 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-06-10 | 2026-06-21 | 2026-03-03 | 2026-12-30 |  | 8202243735 | 8202242288 | TGH4_UP Tenaga Kerja MA 3 | RU4-TRML | 032PSV041/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 423178000 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-06-22 |  | 2026-06-19 | 2026-06-19 | 2102370108 | 8202244023 |  | TGH4_UP Scaffolding Rejuvenate MA 4 | RU4-KPC | LN39-DW8001MS24/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 308176000 | 0 | MA4-STA |  |  |  |  | PT02 | 5 | 2 | 2026-06-19 | PM |  | 045
| K401 | 2026-05-07 | 2026-05-07 | 2026-03-12 | 2026-12-30 | 2102366575 | 8202243053 |  | TGH4_UP Scaffolding Rejuvenate MA 3 | RU4-TRML | LN37-1014AA/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 1170497000 | 0 | MA3-STA |  | WAHYUCATUR |  |  | PT02 | 4 | 2 | 2026-03-12 | PM |  | 045
| K401 | 2026-04-15 | 2026-04-15 | 2026-03-11 | 2026-12-30 |  | 8202242438 | 8202242437 | TGH4_Skylift General Maintenance | RU4-TRML | 30P108A/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 238140000 | 238140000 | GEN-LIS |  | WAHYUCATUR |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-21 | 2026-04-09 | 2026-12-30 | 2102367659 | 8202243923 |  | TGH4_Rejuvenate Isolasi Tangki | RU4-TRML | 042FT301/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 1952555000 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 4 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-06 | 2026-12-30 | 2102366240 | 8202241361 |  | TGH4_25 UP MON&INSP MOTOR LISTRIK |  |  | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 68300000 | 68300000 | MA1-LIS |  | WAHYUCATUR |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-26 | 2026-02-27 | 2026-02-25 | 2026-12-30 | 2102365021 | 8202239207 |  | TGH4_25 Instalasi dan Konfi Dedicated Ap | RU4-FOC2 | DCS-FOC2/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 390000000 | 390000000 | MA2-INT |  | FARIZSETYANA |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 003
| K401 | 2026-02-09 | 2026-06-18 | 2026-02-09 | 2026-12-30 | 2102354953 | 8202238774 |  | TGH4_24 UP Scaff Rejuve MA-3 |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 1170497000 | 1170497000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 045
| K401 | 2026-04-27 | 2026-04-27 | 2026-04-21 | 2026-12-30 | 2102368128 | 8202242737 |  | TGH4_24 TSA 2 Unit Brand Thermo Scientif | RU4-FOC2 | 30BD12EE0012B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 73835000 | 73835000 | WS-INT |  | WAHYUCATUR |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-02-20 | 2026-02-26 | 2026-02-02 | 2026-12-30 | 2102355543 | 8202238984 |  | TGH4_24 PSA UPS & BATT CHGR AEG |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 220737000 | 220737000 | MA5-LIS |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-27 | 2026-06-18 | 2026-02-09 | 2026-12-30 | 2102363995 | 8202242771 |  | TGH4_23 UP Penyehatan HE MA 2 |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 840861000 | 840861000 | MA2-STA |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 045
| K401 | 2026-04-30 | 2026-04-30 | 2026-02-02 | 2026-12-30 | 2102353530 | 8202242872 |  | TGH4_23 UP Penyehatan HE MA 1 |  |  | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 194751000 | 194751000 | MA1-STA |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-12-14 |  | 8202242399 | 8202237735 | TGH39-40_22 Sewa CCTV Tanki 41, 47, GTO | RU4-RFCGTO | 47T511A/00 | 50 WAMA | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 116661000 | 116661000 | MA3-INT |  | WAHYUCATUR |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-12-30 |  | 8202242803 | 8202239025 | TGH34_Kontrak Peformance Mechanical Seal | RU4-LOC2 | 021P102A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 116573000 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 045
| K401 | 2026-06-15 | 2026-06-21 | 2026-06-12 | 2026-12-22 | 2102369947 | 8202243846 |  | TGH33_23 TSA AC Central Non PLC | RU4-UTL | TEMP-U50/00 | 50 | CRTD CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 50150000 | 0 | WS-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-06-12 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-21 | 2026-06-12 | 2026-12-22 | 2102369972 | 8202243847 |  | TGH32_23 TSA AC Central Non PLC | RU4-UTL | TEMP-U50/00 | 50 | CRTD CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 209613000 | 0 | WS-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-06-12 | PM |  | 003
| K401 | 2026-04-17 | 2026-04-17 | 2026-01-12 | 2026-12-30 |  | 8202242529 | 8202234903 | TGH31-33_23 TSA 11 Unit GC KPC | RU4-KPC | DCS-KPC/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 231021000 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 5 | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-12-30 | 2102368387 | 8202242788 |  | TGH31_23 TSA AC Central Non PLC | RU4-UTL | TEMP-U50/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 253514000 | 253514000 | WS-INT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-13 | 2026-04-08 | 2026-12-30 | 2102367651 | 8202242348 |  | TGH30_23 TSA AC Central Non PLC | RU4-UTL | TEMP-U50/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 189371000 | 189371000 | WS-INT |  | SAMSUDINH |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-03-03 | 2026-06-18 | 2026-02-02 | 2026-12-30 | 2102356650 | 8202239365 |  | TGH3_UP Water Proofing ME II 24/25 | RU4-UTL | 50SS1/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 984766000 | 984766000 | GEN-SIP |  | FARIZSETYANA |  | 2026-03-05 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-10 | 2026-03-03 | 2026-12-30 |  | 8202242288 | 8202239372 | TGH3_UP Tenaga Kerja MA 3 | RU4-TRML | 032PSV041/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 294767000 | 250552000 | MA3-STA |  | WAHYUCATUR |  | 2026-04-10 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-16 | 2026-02-02 | 2026-12-30 |  | 8202242482 | 8202237714 | TGH3_UP Scaffolding Rejuvenate MA 4 | RU4-KPC | 82E201A/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 358492000 | 358492000 | MA4-STA |  | WAHYUCATUR |  | 2026-04-16 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-06-22 |  | 2026-05-11 | 2026-05-11 | 2102368933 | 8202244037 |  | TGH3_UP Perbaikan Quick Release Hook | RU4-TRML | 71JL71/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 312473000 | 0 | MA3-STA |  |  |  |  | PT02 | 4 | 2 | 2026-05-11 | PM |  | 045
| K401 | 2026-04-06 | 2026-06-18 | 2026-03-31 | 2026-12-30 | 2102367160 | 8202242112 |  | TGH3_UP Pengecetan MA 3 Area 60/30 | RU4-TRML | LN30-0500N/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 778815000 | 778815000 | MA3-STA |  | FARIZSETYANA |  | 2026-04-06 | PT02 | 4 | 3 | 2026-03-31 | PM |  | 045
| K401 | 2026-04-14 | 2026-06-19 | 2026-04-07 | 2026-12-30 | 2102367540 | 8202242422 |  | TGH3_UP Pengecetan MA 1 | RU4-FOC1 | LN10-10A/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 690025000 | 690025000 | MA1-STA |  | FARIZSETYANA |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 045
| K401 | 2026-03-03 | 2026-06-18 | 2026-03-03 | 2026-12-30 | 2102365175 | 8202239366 |  | TGH3_UP Loading Arm 24/26 | RU4-TRML | 72X101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 1122123000 | 1122123000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-04 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-04-15 | 2026-04-15 | 2026-03-11 | 2026-12-30 |  | 8202242437 | 8202242414 | TGH3_Skylift General Maintenance | RU4-TRML | 30P108A/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 238140000 | 238140000 | GEN-LIS |  | WAHYUCATUR |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K401 | 2026-02-20 | 2026-02-26 | 2026-02-09 | 2026-12-30 | 2102363944 | 8202238986 |  | TGH3_25 UP MON&INSP MOTOR LISTRIK EIIE | RU4-LOC2 | 021P102A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 50700000 | 50700000 | MA2-LIS |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-12-30 | 2102366694 | 8202242120 |  | TGH3_25 UP Cleaning SWD Jet Press | RU4-RFCUTL | 154A501A-S3/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 499491000 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 045
| K401 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-12-30 | 2102366171 | 8202242027 |  | TGH3_25 UP Cleaning HE Cooler UTL | RU4-UTL | 054WS101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 373101000 | 317135850 | MA5-STA |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 005
| K401 | 2026-05-04 | 2026-06-19 | 2026-04-30 | 2026-12-30 | 2102368572 | 8202242946 |  | TGH3_25 TSA CEMS UTL II dan SRU | RU4-UTL | 052B101-1/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 235336100 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-05-22 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-14 | 2026-03-04 | 2026-12-30 | 2102365718 | 8202242359 |  | TGH3_24 UP Piping LOC II | RU4-LOC2 | LN21-1001C/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 328497000 | 328497000 | MA2-STA |  | WAHYUCATUR |  | 2026-04-14 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-18 | 2026-12-29 | 2102369075 | 8202243296 |  | TGH3_24 TSA Sulfur Analyzer Rigaku | RU4-FOC2 | 30BD12EE0012A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 25542000 | 25542000 | WS-INT |  | WAHYUCATUR |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-04-30 | 2026-04-30 | 2026-02-03 | 2026-12-29 |  | 8202242845 | 8202234978 | TGH3_24 TSA Sparing HB 66 | RU4-TRML | 66HB101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 43060000 | 36601000 | MA3-INT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 4 | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-13 | 2026-04-06 | 2026-12-30 | 2102367453 | 8202242166 |  | TGH3_24 TSA 2 Unit Brand Thermo Scientif | RU4-FOC2 | 30BD12EE0012B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 34560000 | 34560000 | WS-INT |  | SAMSUDINH |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-10 | 2026-12-30 | 2102367769 | 8202242557 |  | TGH3_24 PM RUTIN GROUNDING & BONDING SYS |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 992561646 | 992561646 | MA3-LIS |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 4 | 3 | 2026-04-10 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-04 | 2026-03-02 | 2026-12-30 | 2102365170 | 8202239355 |  | TGH29_23 TSA AC Central Non PLC | RU4-UTL | TEMP-U50/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 171501000 | 171501000 | MA5-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-19 | 2026-06-04 | 2026-12-30 | 2102369549 | 8202243635 |  | TGH28&29_Sewa Crane 50 Ton WS | RU4-WS | 037BD101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-15-C2H | 251790000 | 0 | WS-KAB |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 045
| K401 | 2026-05-20 | 2026-06-21 | 2026-05-20 | 2026-12-30 |  | 8202243337 | 8202240899 | TGH28_23 Kontrak Peformance MS FS | RU4-FOC1 | 11P22A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 264152000 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-04-30 | 2026-04-30 | 2026-02-03 | 2026-12-30 |  | 8202242892 | 8202239202 | TGH27_Sewa Crane 50 Ton WS | RU4-WS | 037BD101-B1B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-15-C2H | 365680000 | 365680000 | WS-KAB |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 5 | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-05 |  | 2026-01-02 | 2026-03-04 |  | 8202238621 | 8202231276 | TGH26_Sewa Crane 50 Ton WS | RU4-WS | 037BD101/00 | 50 | CRTD NMAT PRC | 4MR | D14/26/B6/RT-15-C2 | 125895000 | 0 | WS-KAB |  |  |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-26 | 2026-04-30 | 2026-02-03 | 2026-12-30 | 2102357200 | 8202239202 |  | TGH26_Sewa Crane 50 Ton WS | RU4-WS | 037BD101-B1B/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-15-C2H | 125895000 | 125895000 | WS-KAB |  | HERIOBM |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-05-20 | 2026-06-21 | 2026-05-20 | 2026-12-30 |  | 8202243335 | 8202241068 | TGH26_23 Kontrak Peformance Mech Sel FS | RU4-FOC2 | 014P107A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 170006000 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-03-13 | 2026-03-14 | 2026-01-02 | 2026-12-30 |  | 8202241717 | 8202237810 | TGH25_23 TSA ConMon Instrument | RU4-RFCC | 101FJB001/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 262512000 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-03-14 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-02 | 2026-01-02 | 2026-12-30 |  | 8202239279 | 8202237810 | TGH24_23 TSA ConMon Instrument | RU4-RFCC | 101FJB001/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 237622000 | 237622000 | MA6-INT |  | WAHYUCATUR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-09 | 2026-05-22 | 2026-05-22 | 2026-12-30 | 2102355911 | 8202241482 |  | TGH23-24_23 PSA Metering System | RU4-TRML | 004FT002/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1248172000 | 1248172000 | MA3-INT |  | WAHYUCATUR |  | 2026-05-22 | PT02 | 4 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-12-30 |  | 8202243016 | 8202242730 | TGH23_Building Management Service | RU4-UTL | 50COC1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 91345000 | 0 | GEN-SIP |  | FARIZSETYANA |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-04-27 | 2026-05-05 | 2026-03-09 | 2026-12-30 |  | 8202242730 | 8202241689 | TGH22_Building Management Service | RU4-UTL | 50COC1/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 456449000 | 456449000 | GEN-SIP |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-04-06 | 2026-06-15 | 2026-01-02 | 2026-01-02 |  | 8202242099 | 8202237733 | TGH22_23 PSA Metering System | RU4-TRML | 004FT002/00 | 50 | CRTD CSER NMAT PRC | 4IR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-INT |  | DWIHIZZKI |  |  | PT02 | 5 | 2 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-13 | 2026-03-13 | 2026-03-09 | 2026-12-30 |  | 8202241689 | 8202241687 | TGH21_Building Management Service | RU4-UTL | 50COC1/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 437752000 | 437752000 | GEN-SIP |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-03-13 | 2026-03-13 | 2026-03-09 | 2026-12-30 | 2102366403 | 8202241687 |  | TGH20_Building Management Service | RU4-UTL | 50COC1/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 440142000 | 440142000 | GEN-SIP |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-03-03 | 2026-04-09 | 2026-03-03 | 2026-12-30 | 2102365177 | 8202239372 |  | TGH2_UP Tenaga Kerja MA 3 | RU4-TRML | 032PSV041/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 449625000 | 449625000 | MA3-STA |  | ALFIANRH |  | 2026-03-04 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-12-30 | 2102367970 | 8202242483 |  | TGH2_UP Scaffolding Rejuvenate MA 7 | RU4-RFCUTL | 166AA-U166/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 537261000 | 537261000 | MA7-STA |  | WAHYUCATUR |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-16 | 2026-02-02 | 2026-12-30 |  | 8202242481 | 8202237714 | TGH2_UP Scaffolding Rejuvenate MA 4 | RU4-KPC | 82E201A/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 230792000 | 230792000 | MA4-STA |  | WAHYUCATUR |  | 2026-04-16 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-12 | 2026-03-12 | 2026-03-04 | 2026-12-30 | 2102365879 | 8202241649 |  | TGH2_UP Scaffolding Rejuvenate MA 2 | RU4-FOC2 | 011C101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 641117000 | 544949450 | MA2-STA |  | WAHYUCATUR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-09 | 2026-03-03 | 2026-12-30 | 2102365176 | 8202239370 |  | TGH2_UP Rejuvenate Tangki | RU4-TRML | 71T1/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 2118900000 | 1801065000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-05-12 | 2026-06-18 | 2026-05-05 | 2026-12-30 | 2102368685 | 8202243153 |  | TGH2_UP Rejuvenate Isolasi MA 3 | RU4-TRML | LN40-5146AA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 962688000 | 962688000 | MA3-STA |  | FARIZSETYANA |  | 2026-05-12 | PT02 | 4 | 3 | 2026-05-05 | PM |  | 045
| K401 | 2026-04-28 | 2026-04-28 | 2026-03-13 | 2026-12-30 | 2102366538 | 8202242799 |  | TGH2_UP Rejuvenate Isolasi MA 2 | RU4-LOC2 | LN21-1101N/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 846153000 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 045
| K401 | 2026-06-10 | 2026-06-21 | 2026-04-13 | 2026-12-30 | 2102367818 | 8202243737 |  | TGH2_UP Grouting ME II 2024/2025 | RU4-UTL | 500SS1FC2-CB/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 452728000 | 0 | MA5-STA |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-04-13 | PM |  | 045
| K401 | 2026-04-16 | 2026-06-18 | 2026-04-15 | 2026-12-30 | 2102368023 | 8202242484 |  | TGH2_UP Fire Proofing MA 4 | RU4-KPC | 80P403/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 1134781000 | 1134781000 | MA4-STA |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-04-14 | 2026-04-15 | 2026-03-11 | 2026-12-30 | 2102366568 | 8202242414 |  | TGH2_Skylift General Maintenance | RU4-TRML | 30P108A/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 238140000 | 238140000 | GEN-LIS |  | WAHYUCATUR |  | 2026-04-15 | PT02 | 5 | 3 | 2026-03-11 | PM |  | 045
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-05 | 2026-12-30 |  | 8202243670 | 8202237718 | TGH2_RT LOADING UNLOADING COLUMN | RU4-KPC | 84PV504B/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 293890000 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-05 | PM |  | 045
| K401 | 2026-04-30 | 2026-05-03 | 2026-04-30 | 2026-12-30 |  | 8202242896 | 8202237667 | TGH2_Perpipaan dan Aksesoris MA 4 | RU4-KPC | LN81LP8001MS11/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 871987000 | 871987000 | MA4-STA |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 045
| K401 | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-12-30 |  | 8202241711 | 8202236097 | TGH2_Pembersihan Dalam Tanki MA4 | RU4-TRML | 39T206/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 1331020000 | 1331020000 | MA4-STA |  | WAHYUCATUR |  | 2026-03-14 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 045
| K401 | 2026-03-13 | 2026-03-25 | 2026-03-13 | 2026-12-30 | 2102354339 | 8202241708 |  | TGH2_Composite Wrapping di Area PX |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 453559000 | 453559000 | MA4-STA |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 045
| K401 | 2026-06-03 | 2026-06-20 | 2026-06-03 | 2026-12-30 | 2102369536 | 8202243600 |  | TGH2_Bordes Handrail Structure & Plenum | RU4-KPC | 82K201A/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 1015057000 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 045
| K401 | 2026-06-03 | 2026-06-20 | 2026-06-03 | 2026-12-30 | 2102369537 | 8202243602 |  | TGH2_Bordes Handrail Structure & Pengeca | LOC3-UP4 | GMAT-STA-LOC3/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-9-C2H | 647090000 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-06-20 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 045
| K401 | 2026-02-26 | 2026-03-02 | 2026-02-02 | 2026-12-30 | 2102357312 | 8202239205 |  | TGH2_25_UP Cleaning Burner MA 1 |  |  | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 144168000 | 122542800 | MA1-STA |  | WAHYUCATUR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-06-08 | 2026-06-21 | 2026-04-27 | 2026-12-30 | 2102368372 | 8202243698 |  | TGH2_25 UP Plenum FOC II |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 917388000 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 045
| K401 | 2026-05-22 | 2026-06-22 | 2026-05-22 | 2026-05-22 | 2102368571 | 8202243422 |  | TGH2_25 UP Pipa UTL 50/05/500 |  |  | 50 | CRTD CSER NMAT PRC | 4MR |  | 282880000 | 0 | MA5-STA |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-05-22 | PM |  | 045
| K401 | 2026-02-23 | 2026-06-19 | 2026-02-23 | 2026-12-30 | 2102356063 | 8202239021 |  | TGH2_25 UP Perb RWI 63 063 | RU4-TRML | 63S101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 887552000 | 754419200 | MA5-STA |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 005
| K401 | 2026-03-06 | 2026-03-06 | 2026-03-05 | 2026-12-30 | 2102364880 | 8202241292 |  | TGH2_25 UP Cleaning SWD Jet Press | RU4-RFCUTL | 154A501A-E1/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 998982000 | 0 | MA5-STA |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-03-05 | PM |  | 005
| K401 | 2026-06-04 | 2026-06-20 | 2026-05-06 | 2026-12-30 | 2102368773 | 8202243637 |  | TGH2_25 UP Boardesk Aksesoris MA 2 |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 394903000 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-07 | 2026-05-07 | 2026-04-20 | 2026-12-30 | 2102368151 | 8202243057 |  | TGH2_25 TSA MCC & SWITCHGEAR FUJI ELECT | RU4-UTL | 05EE1102A-CB/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 441668000 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-03-03 | 2026-06-18 | 2026-03-02 | 2026-12-30 | 2102365172 | 8202239359 |  | TGH2_25 TSA CEMS UTL II dan SRU | RU4-UTL | 052B101-1/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1100590200 | 1100590200 | MA5-INT |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-22 | 2026-04-20 | 2026-04-20 |  | 8202243131 | 8202242785 | TGH2_25 Perbaikan Peralatan Kilang Area | RU4-UTL | 054P106A/00 | 50 | CRTD NMAT PRC | 4RR | D14/26/B6/RT-5-C2H | 129438850 | 0 | MA5-ROT |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-04-20 | PM |  | 045
| K401 | 2026-04-13 | 2026-04-13 | 2026-02-02 | 2026-12-30 | 2102353419 | 8202242358 |  | TGH2_24 UP Penyehatan SRU |  |  | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 612624000 | 520730400 | MA1-STA |  | WAHYUCATUR |  | 2026-04-13 | PT02 | 2 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-24 | 2026-06-18 | 2026-02-19 | 2026-12-30 | 2102364537 | 8202239090 |  | TGH2_24 PM RUTIN GROUNDING & BONDING SYS |  |  | 60 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 1816343979 | 1816343979 | MA3-LIS |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 4 | 3 | 2026-02-19 | PM |  | 045
| K401 | 2026-05-04 | 2026-05-19 | 2026-05-19 | 2026-12-30 |  | 8202242955 | 8202241300 | TGH16_23 Kontrak Peformance Mech Seal EA | RU4-LOC3 | 260P159A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 40235600 | 40235600 | WS-PMP |  | AGHANIAKBAR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-05-13 | 2026-05-18 | 2026-05-13 | 2026-12-29 |  | 8202243193 | 8202237828 | TGH15_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 275317000 | 275317000 | MA6-INT |  | FARIZSETYANA |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-15 | 2026-03-09 | 2026-12-30 |  | 8202241714 | 8202241713 | TGH15 Kontrak Peformance Mech Seal Asmus | RU4-KPC | 87P204A/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 40318900 | 40318900 | WS-PMP |  | YUNITAMR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-08 | 2026-01-02 | 2026-12-29 |  | 8202242213 | 8202237828 | TGH14_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 133066000 | 133066000 | MA6-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-08 | 2026-01-02 | 2026-12-29 |  | 8202242204 | 8202237828 | TGH13_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 485421000 | 485421000 | MA6-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-07 | 2026-04-06 | 2026-12-30 |  | 8202243051 | 8202242211 | TGH12_UP Rumput 2025 | RU4-TRML | 30P104A/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 218114000 | 218114000 | MA3-STA |  | WAHYUCATUR |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 045
| K401 | 2026-03-13 | 2026-03-16 | 2026-03-12 | 2026-12-30 | 2102366594 | 8202241695 |  | TGH12_25 UP MON&INSP PERALATN ELECTR EI | RU4-RFCGTO | 107P502A-MCC/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 249367135 | 249367135 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-04-08 | 2026-04-08 | 2026-01-02 | 2026-12-29 |  | 8202242198 | 8202237828 | TGH12_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 273575000 | 273575000 | MA6-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-31 | 2026-03-03 | 2026-12-30 | 2102365241 | 8202239460 |  | TGH11-12_22 TSA FGDS Gastron RFCC | RU4-RFCC | 102TG005/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 89861000 | 89861000 | MA6-INT |  | FARIZSETYANA |  | 2026-03-31 | PT02 | 8 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-04-08 | 2026-06-19 | 2026-04-06 | 2026-12-30 |  | 8202242211 | 8202242209 | TGH11_UP Rumput 2025 | RU4-TRML | 30P104A/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 664690000 | 664690000 | MA3-STA |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 045
| K401 | 2026-03-13 | 2026-03-16 | 2026-03-12 | 2026-12-30 | 2102366593 | 8202241694 |  | TGH11_25 UP MON&INSP PERALATN ELECTR EI | RU4-RFCGTO | 107P502A-MCC/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 137158906 | 137158906 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-03-30 | 2026-03-30 | 2026-01-02 | 2026-12-29 |  | 8202241922 | 8202237828 | TGH11_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 254333000 | 254333000 | MA6-INT |  | FARIZSETYANA |  | 2026-03-30 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-16 | 2026-04-02 | 2026-12-30 |  | 8202242495 | 8202242010 | TGH11_24 Jasa LTSA Fire Truck | RU4-K3LL | FT34/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 242839610 | 242839610 | WS-KAB |  | WAHYUCATUR |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 045
| K401 | 2026-05-25 | 2026-06-22 | 2026-05-21 | 2026-12-29 | 2102369225 | 8202243458 |  | TGH10-12_24 TSA AC Split di Area Kilang | RU4-RFCC | 30BD12EE0102A/00 | 50 | CRTD NMAT PRC | 4IR |  | 232123000 | 0 | GEN-INT |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-05-21 | PM |  | 003
| K401 | 2026-04-08 | 2026-06-18 | 2026-03-05 | 2026-12-30 |  | 8202242209 | 8202239678 | TGH10_UP Rumput 2025 | RU4-TRML | 30P104A/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 782823000 | 782823000 | MA3-STA |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-25 | 2026-03-30 | 2026-01-02 | 2026-12-30 |  | 8202239164 | 8202237828 | TGH10_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 334718000 | 334718000 | MA6-INT |  | FARIZSETYANA |  | 2026-03-02 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-30 | 2026-04-21 | 2026-04-02 | 2026-12-30 |  | 8202241919 | 8202241498 | TGH10_24 Jasa LTSA Fire Truk | RU4-K3LL | FT40/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 14922943 | 14922943 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 045
| K401 | 2026-06-02 | 2026-06-20 | 2026-05-25 | 2026-12-30 | 2102369311 | 8202243574 |  | TGH10_22 TSA ATG Endress Hauser | RU4-TRML | 31LT-U31/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1103020000 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 5 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-07 | 2026-06-18 | 2026-03-12 | 2026-12-30 | 2102366576 | 8202243054 |  | TGH1_UP Scaffolding Rejuvenate MA 3 2025 | RU4-TRML | LN41-1007AJ/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 1238071000 | 1238071000 | MA3-STA |  | FARIZSETYANA |  | 2026-05-07 | PT02 | 4 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-06 | 2026-03-11 | 2026-12-30 | 2102366572 | 8202243013 |  | TGH1_UP Pengecetan MA 6 Tahun 24/25 | RU4-RFCC | 102-WT0829-3-4/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 845000000 | 0 | MA6-STA |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-03-11 | PM |  | 045
| K401 | 2026-03-12 | 2026-06-18 | 2026-03-05 | 2026-12-30 | 2102366170 | 8202241596 |  | TGH1_UP Pengecetan MA 5 Tahun 2024 | RU4-UTL | LN05-1004N/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 946992000 | 804943000 | MA5-STA |  | FARIZSETYANA |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-12-30 | 2102367820 | 8202242964 |  | TGH1_UP Pengecetan MA 2 Tahun 25/26 | RU4-FOC2 | LN16-1036N/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 496736000 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 045
| K401 | 2026-06-22 |  | 2026-06-08 | 2026-06-08 | 2102369738 | 8202244033 |  | TGH1_UP Holding Basin 66 Barat Th 2025 | RU4-TRML | 66HB101/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 1684683000 | 0 | MA3-STA |  |  |  |  | PT02 | 4 | 2 | 2026-06-08 | PM |  | 045
| K401 | 2026-02-27 | 2026-06-19 | 2026-02-02 | 2026-12-30 | 2102356199 | 8202239256 |  | TGH1_UP Grouting ME II 2024/2025 | RU4-UTL | 050JL1/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 748553000 | 636270000 | MA5-STA |  | FARIZSETYANA |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-27 | 2026-06-18 | 2026-02-02 | 2026-12-30 | 2102356273 | 8202239253 |  | TGH1_UP CPI ME II Tahun 2024/2025 | RU4-UTL | 050JL1/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 1344858000 | 1143129000 | MA5-STA |  | FARIZSETYANA |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-06-10 | 2026-06-21 | 2026-06-08 | 2026-12-30 | 2102369767 | 8202243757 |  | TGH1_OLLS 2026 | RU4-KPC | 81PSV341/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 1185328000 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 5 | 3 | 2026-06-08 | PM |  | 045
| K401 | 2026-03-02 | 2026-06-19 | 2026-02-02 | 2026-12-30 | 2102353520 | 8202239321 |  | TGH1_Bordes Handrail Structure & Plenum | RU4-KPC | 82K201A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 767110550 | 767110550 | MA4-STA |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-02 | 2026-06-18 | 2026-02-02 | 2026-12-30 | 2102356511 | 8202239328 |  | TGH1_Bordes Handrail Structure & Pengeca | RU4-LOC3 | 240S101B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-9-C2H | 1137746250 | 1137746250 | MA4-STA |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-05-20 |  | 2026-05-20 | 2026-12-30 | 2102369108 | 8202243320 |  | TGH1_26 Kontrak UP Substandard Peneranga | RU4-TRML | 41FSL006/00 | 50 | CRTD NMAT PRC | 4ER |  | 3139000000 | 0 | MA3-INT |  |  |  |  | PT02 | 5 | 2 | 2026-05-20 | PM |  | 045
| K401 | 2026-04-30 | 2026-06-18 | 2026-04-29 | 2026-12-30 | 2102368022 | 8202242895 |  | TGH1_25 UPScaffold Tanki 47 |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 1436889000 | 1221355650 | MA7-STA |  | FARIZSETYANA |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K401 | 2026-02-26 | 2026-06-19 | 2026-02-02 | 2026-12-30 | 2102355562 | 8202239192 |  | TGH1_25 UP Plenum FOC II | RU4-FOC2 | 011C102/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 898982000 | 764134700 | MA2-STA |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-05-26 | 2026-06-22 | 2026-05-26 | 2026-05-26 | 2102367411 | 8202243519 |  | TGH1_25 UP PIPA UTL RFCC | RU4-RFCUTL |  | 50 | CRTD CSER NMAT PRC | 4MR |  | 598329000 | 0 | MA5-STA |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-05-26 | PM |  | 045
| K401 | 2026-02-23 | 2026-03-06 | 2026-02-23 | 2026-12-30 | 2102357807 | 8202239015 |  | TGH1_25 UP Pipa UTL 50 |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 436727000 | 371217950 | MA5-STA |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 045
| K401 | 2026-02-09 | 2026-06-18 | 2026-02-09 | 2026-12-30 | 2102357184 | 8202238769 |  | TGH1_25 UP Perb. Plenum MA-6 | RU4-RFCC | 101V521/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 929439000 | 790023150 | MA6-STA |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 8 | 3 | 2026-02-09 | PM |  | 045
| K401 | 2026-02-10 | 2026-02-26 | 2026-02-10 | 2026-12-30 | 2102358252 | 8202238807 |  | TGH1_25 UP Perb RWI 63 063 | RU4-TRML | 63S101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 530971000 | 451325350 | MA5-STA |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 045
| K401 | 2026-04-30 | 2026-04-30 | 2026-04-07 | 2026-12-30 | 2102367419 | 8202242873 |  | TGH1_25 UP Penyehatan HE MA 1 |  |  | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 553173000 | 553173000 | MA1-STA |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 045
| K401 | 2026-05-18 | 2026-05-18 | 2026-05-05 | 2026-12-30 | 2102367817 | 8202243241 |  | TGH1_25 UP Line Distribusi | RU4-UTL | LN50-2CC/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 250443000 | 0 | MA5-STA |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 045
| K401 | 2026-05-06 | 2026-06-19 | 2026-02-24 | 2026-12-30 | 2102364846 | 8202243023 |  | TGH1_25 UP Cleaning Tanki LOC I | RU4-LOC1 | 24T1/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 746305000 | 634359250 | MA1-STA |  | FARIZSETYANA |  | 2026-05-07 | PT02 | 6 | 3 | 2026-02-24 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-06 | 2026-03-26 | 2026-12-30 | 2102366909 | 8202243026 |  | TGH1_25 UP Boardesk Aksesoris MA 2 | RU4-FOC2 | 014K101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 616881000 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-05-06 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 045
| K401 | 2026-03-11 | 2026-03-11 | 2026-03-02 | 2026-12-30 | 2102365171 | 8202241581 |  | TGH1_25 PSA UPS & BATT CHGR GUTOR | RU4-UTL | 50EE109B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 150000000 | 127500000 | MA5-LIS |  | WAHYUCATUR |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-16 | 2026-03-02 | 2026-12-30 | 2102354125 | 8202239308 |  | TGH1_24 UP Line Distribusi UTL (Final) | RU4-UTL | LN50-4AA/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 992494000 | 843619900 | MA5-STA |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 005
| K401 | 2026-06-17 | 2026-06-21 | 2026-05-26 | 2026-12-30 | 2102369357 | 8202243874 |  | TGH1 - 25 TSA MCC & SWITCHGEAR TOSHIBA | RU4-UTL | 80EE2127A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 172000000 | 0 | MA4-LIS |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 5 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-25 | 2026-05-25 | 2026-12-30 |  | 8202243388 | 8202237716 | TGH_TKDN Pengecetan MA 2 | RU4-LOC2 | LN21-1001C/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 276825550 | 276825550 | MA2-STA |  | WAHYUCATUR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 045
| K401 | 2026-05-21 | 2026-05-25 | 2026-04-07 | 2026-12-30 |  | 8202243389 | 8202242422 | TGH_TKDN Pengecetan MA 1 | RU4-FOC1 | LN10-10A/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 192501000 | 192501000 | MA1-STA |  | WAHYUCATUR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 045
| K401 | 2026-04-30 | 2026-04-30 | 2026-02-02 | 2026-12-30 |  | 8202242880 | 8202237557 | TGH_TKDN OLLS 2025 | RU4-KPC | 82K201A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 297129600 | 297129600 | MA4-STA |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-29 | 2026-06-18 | 2026-04-15 | 2026-12-30 | 2102368017 | 8202242843 |  | TGH_TandemSeal, Burner & Level Glass | RU4-KPC | 82PV251/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 1008000000 | 806400000 | MA4-STA |  | FARIZSETYANA |  | 2026-04-30 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-18 | 2026-03-05 | 2026-12-30 | 2102366190 | 8202240061 |  | TGH_Relokasi Motor Kompresor 019K102ABCD | RU4-FOC2 | 011K101A-P2/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/NR-2-C2H | 1286890589 | 1286890589 | MA2-LIS |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-04-30 | 2026-06-05 | 2026-02-03 | 2026-12-30 |  | 8202242891 | 8202241461 | TGH_Penggantian Mechanical Seal Complete | RU4-UTL | 054P101A/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 341602000 | 0 | WS-PMP |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-12-31 |  | 8202242802 | 8202239056 | TGH_Kontrak Peformance Mech Seal Eagle | RU4-KPC | 86P202B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 50694000 | 50694000 | WS-PMP |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 045
| K401 | 2026-04-06 | 2026-05-03 | 2026-04-01 | 2026-12-30 | 2102367231 | 8202242094 |  | TGH_24 Integrasi CEMS 052B101/102 | RU4-UTL | 052B101/00 | 60 | CLSD CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 |  | 8202239451 | 8202237875 | TGH Perbaikan Pompa 011P127B | RU4-FOC2 | 011P127B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 66587300 | 66587300 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-06-02 |  | 2026-06-02 | 2026-07-15 |  | 8202243563 | 8202236582 | Tgh ke 9 volume stat MA 1 | RU6-RCC | 15-R-103/00 | 50 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 82591500 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-06-02 | PM |  | 003
| K601 | 2026-06-02 |  | 2026-06-02 | 2026-07-15 |  | 8202243562 | 8202236582 | Tgh ke 8 volume stat MA 1 | RU6-RCC | 15-R-103/00 | 50 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 80410300 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-06-02 | PM |  | 003
| K601 | 2026-06-04 | 2026-06-08 | 2026-03-06 | 2026-09-11 |  | 8202243621 | 8202242227 | Tgh ke 5 Pemeliharaan Rutin MA 2 | RU6-DHC | 12-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 66967000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-06-12 | 2102365236 | 8202239414 |  | Tgh ke 3 Mech MA 3 | RU6-HSC | 32-R-102/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 65536000 | 65536000 | MA1-STA |  | DANDARWANI |  | 2026-03-04 | PT02 | 5 | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-06-02 |  | 2026-06-02 | 2026-07-15 |  | 8202243565 | 8202236582 | Tgh ke 11volume stat MA 1 | RU6-RCC | 15-R-103/00 | 50 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 81500000 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-06-02 | PM |  | 003
| K601 | 2026-06-02 |  | 2026-06-02 | 2026-07-15 |  | 8202243564 | 8202236582 | Tgh ke 10volume stat MA 1 | RU6-RCC | 15-R-103/00 | 50 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 82418000 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-18 | 2026-06-05 | 2026-02-06 | 2026-03-10 | 2102362330 | 8202238950 |  | Temporary Repair Pompa 14-P-102B | RU6-DHC | 14-P-102B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 312164763 | 124984368 | MA2-ROT |  | PANDUA |  | 2026-02-18 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-07-31 | 2102370122 | 8202243962 |  | Temp bearing O/B 12-P-505B-T overheat | RU6-DHC | 12-P-505B-T/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 5691628 | 5691628 | MA2-ROT |  | ABDULAZIZ70 |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 003
| K201 | 2026-05-08 | 2026-05-21 | 2026-12-11 | 2026-12-11 |  | 8202243100 | 8202241483 | TECHNICAL SERVICE AGREEMENT PEMELIHARAAN | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-05-08 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-05-08 | 2026-05-26 | 2026-12-11 | 2026-12-11 |  | 8202243101 | 8202241483 | TECHNICAL SERVICE AGREEMENT PEMELIHARAAN | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1199880000 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-05-08 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-03-13 | 2026-05-29 | 2026-12-02 | 2026-12-02 |  | 8202241721 | 8202241701 | TECHNICAL SERVICE AGREEMENT (TSA) PEMELI | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K401 | 2026-04-09 |  | 2026-04-06 | 2026-04-06 | 2102367467 | 8202242298 |  | Tagihan Upgrade PLC BMS 520B401 | RU4-UTL | 520B401/00 | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-INT |  |  |  |  | PT02 | 3 | 2 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-15 | 2026-02-24 | 2026-12-30 | 2102364826 | 8202242440 |  | Tagihan Termin 5 Perb Diesel Engine | RU4-RFCUTL | 152G501A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 213249700 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-15 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 045
| K401 | 2026-03-11 | 2026-06-18 | 2026-03-11 | 2026-12-30 | 2102366172 | 8202241562 |  | Tagihan termin 2-Suplai Udara Bertekanan |  |  | 60 | REL CNF GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 1371489000 | 1371489000 | MA5-ROT |  | FARIZSETYANA | 2026-06-12 | 2026-03-11 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K401 | 2026-06-15 |  | 2026-06-10 | 2026-06-10 | 2102369807 | 8202243848 |  | Tagihan Termin 1 Pekerjaan TSA FGDS RFCC | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  |  |  |  | PT02 | 8 | 2 | 2026-06-10 | PM |  | 045
| K401 | 2026-06-15 |  | 2026-06-10 | 2026-06-10 | 2102369808 | 8202243849 |  | Tagihan Termin 1 Pekerjaan ConMon RFCC | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  |  |  |  | PT02 | 8 | 2 | 2026-06-10 | PM |  | 045
| K401 | 2026-06-22 |  | 2026-06-18 | 2026-06-18 | 2102370054 | 8202243990 |  | Tagihan PM Field Instrument termin 8 |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-18 | PM |  | 045
| K401 | 2026-02-26 | 2026-02-27 | 2026-02-20 | 2026-12-30 | 2102364900 | 8202239190 |  | Tagihan Pkerjaan UP Pipa Area 70 | RU4-TRML | LN71-1016AJ/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 501953000 | 426660050 | MA3-STA |  | FARIZSETYANA |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 045
| K301 | 2026-06-18 | 2026-06-18 | 2026-01-01 | 2026-12-31 |  | 8202243937 | 8202235505 | Tagihan Perbaikan Sarana Tambat Kapal Ar |  |  | 01 | CRTD NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 045
| K401 | 2026-03-11 | 2026-06-19 | 2026-03-09 | 2026-12-30 | 2102366313 | 8202241563 |  | Tagihan Penggantian FWL Tangki 2025 | RU4-TRML | 30P108A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 739927000 | 739927000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2102370092 | 8202243941 |  | Tagihan Pemeliharaan GC KPC 22-25 |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-06-18 | PM |  | 045
| K301 | 2026-06-18 | 2026-06-22 | 2026-01-02 | 2026-12-31 |  | 8202243957 | 8202235140 | Tagihan Ke- 7 Termin TKDN Pekerjaan Meka | RU3-CDGP | 24-PSL-001A/00 | 50 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 269992950 | 0 | MA1-STA |  | RRAMADHANI |  | 2026-06-22 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-06-03 | 2026-06-18 | 2026-01-01 | 2026-12-31 |  | 8202243611 | 8202235056 | Tagihan Ke- 7 Pekerjaan Kontrak Volume L | RU3-ITP | 34-RJ-MTR-KRM/00 | 60 | REL GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 68258400 | 68258400 | MA4-LIS |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-06-03 | 2026-06-18 | 2026-01-01 | 2026-12-30 |  | 8202243610 | 8202235056 | Tagihan Ke- 6 Pekerjaan Kontrak Volume L | RU3-ITP | 34-RJ-MTR-KRM/00 | 60 | REL GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 34407150 | 34407150 | MA4-LIS |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-06-09 | 2026-06-18 | 2026-06-09 | 2026-12-31 |  | 8202243714 | 8202234391 | Tagihan Ke- 4 Pekerjaan TSA-PM Peralatan | RU3-CDGP | ALK-MCC-PM-24/00 | 60 | REL NMAT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 54400000 | 0 | MA1-INT |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K301 | 2026-06-18 |  | 2026-01-02 | 2026-12-31 |  | 8202243951 | 8202241407 | Tagihan Ke- 24 Pekerjaan Penyediaan Jasa | RU3-WS | BEN-TOOL/00 | 50 | CRTD NMAT PRC | 3RR | D13/26/B6/RT-2-D2H | 93401000 | 0 | WS-SG |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K301 | 2026-06-18 | 2026-06-19 | 2026-01-01 | 2026-12-31 |  | 8202243950 | 8202243937 | Tagihan Ke- 2 Pekerjaan Perbaikan Sarana | RU3-ITP | ITP-JETTY-001/00 | 50 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 17932450 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-06-19 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-06-12 | 2026-06-18 | 2026-06-12 | 2026-12-31 |  | 8202243837 | 8202243826 | Tagihan Ke- 11 Pekerjaan Condition Monit | RU3-CDGP | ALK-MCC-PM-06A/00 | 60 | REL NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 165221300 | 0 | MA1-ROT |  | ALEPDALITAN |  | 2026-06-12 | PT02 | 4 | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-03-12 |  | 2026-03-11 | 2026-03-11 | 2102366571 | 8202241652 |  | Tagihan ke 11 - PM FGDS RFCC | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA6-INT |  |  |  |  | PT02 | 3 | 2 | 2026-03-11 | PM |  | 045
| K501 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-12-31 | 2102359082 | 8202243235 |  | Tagihan 8 UR Pengecatan Area UTL & BPP I | RU5-D&W |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 386896000 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 045
| K501 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-12-31 | 2102359081 | 8202243234 |  | Tagihan 7 UR Pengecatan Area UTL & BPP I | RU5-D&W |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 240000000 | 0 | MA1-STA |  | MANKURNIAWAN |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 045
| K501 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-31 | 2102370220 | 8202243991 |  | Tagihan 5 Pengelasan di Workshop |  |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 106148000 | 0 | WS-LAS |  | MANKURNIAWAN |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 045
| K501 | 2026-02-25 | 2026-03-06 | 2026-02-09 | 2026-12-31 | 2102364027 | 8202239138 |  | Tagihan 4, UR Perb. Bocoran Steam Trace | RU5-D&W | 231-LLS013-1-H/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 1 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K501 | 2026-06-11 | 2026-06-12 | 2026-06-11 | 2026-12-31 | 2102369868 | 8202243783 |  | Tagihan 4 Pengelasan di Workshop |  |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 108996000 | 0 | WS-LAS |  | RESTUANDRI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 045
| K401 | 2026-03-11 | 2026-06-18 | 2026-03-04 | 2026-12-30 | 2102365596 | 8202241568 |  | Tagihan 1 PERBAIKAN BORDES HANDRAIL |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 957607000 | 813965950 | MA3-STA |  | FARIZSETYANA |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 045
| K501 | 2026-04-09 | 2026-04-09 | 2026-03-04 | 2026-03-04 | 2102365812 | 8202242287 |  | Tag-8, U/R Perbaikan Sootblower Area HCC |  |  | 01 | CLSD CSER NCMP NMAT PRC | 5RR | D15/09/B6/RT1-03NH | 0 | 0 | MA3-ROT |  | YONZHETG |  |  | PT02 | 3 | 2 | 2026-04-09 | PM |  | 045
| K501 | 2026-03-05 | 2026-06-17 | 2026-02-23 | 2026-05-05 | 2102364729 | 8202239472 |  | Tag-7, U/R Cleaning Sump HCC | RU5-D&W | G-34-54/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 104948000 | 0 | MA3-STA |  | FAUZANR |  | 2026-06-17 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 045
| K501 | 2026-05-06 | 2026-05-19 | 2026-05-06 | 2026-07-15 | 2102368795 | 8202243042 |  | Tag-6 UR.Pemb. Sedmen&Soil under pipe OM | RU5-TBL | OC-JL-301/00 | 60 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C1H | 155394000 | 0 | MA4-STA |  | DWIYUDAAM |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K501 | 2026-03-04 | 2026-03-04 | 2026-02-23 | 2026-02-23 | 2102364781 | 8202239456 |  | Tag-19, U/R Perbaikan Mechanical Seal |  |  | 01 | CLSD CSER NCMP NMAT PRC | 5RR | D15/09/B6/RT1-03NH | 0 | 0 | MA3-ROT |  | YONZHETG |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 045
| K301 | 2026-05-20 | 2026-06-18 | 2026-01-01 | 2026-12-31 | 2102364236 | 8202243346 |  | Tag LTSA Catlys Convrtr | RU3-CDGP | STA-1-1A/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 900000000 | 106652131 | MA1-STA |  | ALEPDALITAN |  | 2026-05-25 | PT02 | 4 | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-12-31 | 2102353236 | 8202242782 |  | Tag KV Sipil Utara | RU3-CDGP |  | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI |  |  | PT02 | 3 | 2 | 2026-04-28 | PM |  | 045
| K301 | 2026-04-06 | 2026-05-15 | 2026-01-01 | 2026-12-31 |  | 8202242096 | 8202234942 | Tag KV PM Cleaning Pre Heater 2026 | RU3-CDGP |  | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 900000000 | 248952407 | MA1-STA |  | MULYONO701 | 2026-01-30 | 2026-04-06 | PT02 |  | 3 | 2026-05-15 | PM |  | 045
| K301 | 2026-04-20 |  | 2026-04-20 | 2026-04-20 |  | 8202242586 | 8202235068 | Tag KV Isolasi Area CDL UTL OM SG 26 | RU3-ITP | ITP-T-150/00 | 01 | CRTD NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-04-20 | PM |  | 003
| K301 | 2026-05-26 |  | 2026-01-01 | 2026-12-31 |  | 8202243522 | 8202235420 | Tag Kontr.Vol Steam Leak SG 26 | RU3-ITP | 35-PICA-140-J10/00 | 01 | CRTD NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 003
| K301 | 2026-05-26 |  | 2026-01-01 | 2026-12-31 |  | 8202243524 | 8202235420 | Tag Kontr.Vol Steam Leak PL 26 | RU3-ITP | 35-PICA-140-J10/00 | 01 | CRTD NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-26 | 2026-01-01 | 2026-12-31 |  | 8202235420 |  | Tag Kontr.Vol Steam Leak | RU3-ITP | 35-PICA-140-J10/00 | 01 | CRTD GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 003
| K301 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2102352829 | 8202243325 |  | Tag Fire Proofing | RU3-CDGP | SRM-4-1/00 | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI |  |  | PT02 | 4 | 2 | 2026-05-20 | PM |  | 003
| K301 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2102353178 | 8202243826 |  | Tag Conmon Peralatan Rotating RUIII | RU3-CDGP | ALK-MCC-PM-06A/00 | 01 | CRTD NMAT PRC | 3ER | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | RRAMADHANI |  |  | PT02 | 4 | 2 | 2026-06-12 | PM |  | 003
| K301 | 2026-04-23 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242690 | 8202234925 | Tag 9 RPA 1-5 & Teknik Bawah Air | RU3-UTL | 61-GDG-UTL-SG/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 60425643 | 64045886 | MA2-STA |  | ALEPDALITAN |  | 2026-04-23 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-03-09 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202241390 | 8202238248 | Tag 9 Pem IPAL Domestik RU III | RU3-LKKK | 33-SH-IPAL/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 47783600 | 47783600 | GEN-STA |  | ALEPDALITAN |  | 2026-03-09 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-11 | 2026-06-09 | 2026-01-01 | 2026-12-30 |  | 8202243129 | 8202235629 | Tag 9 Pek Hose Handling Area OM | RU3-ITP | 34-RJ-MUSI/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 223445046 | 223445046 | MA4-STA |  | ALEPDALITAN |  | 2026-05-11 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-04-06 | 2026-06-09 | 2026-01-01 | 2026-12-31 |  | 8202242088 | 8202235105 | Tag 9 Mekanik CDL, OM, UTL SG |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 132675000 | 132675000 | MA3-ROT |  | ALEPDALITAN |  | 2026-04-06 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-06-05 | 2026-06-18 | 2026-06-05 | 2026-12-31 |  | 8202243662 | 8202235126 | Tag 9 Mekanik Area Utara OM |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 42738000 | 42738000 | MA4-STA |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-06-05 | PM |  | 045
| K301 | 2026-06-12 | 2026-06-18 | 2026-06-12 | 2026-12-31 |  | 8202243828 | 8202243826 | Tag 9 Conmon Peralatan Rotating RUIII | RU3-CDGP | ALK-MCC-PM-06A/00 | 60 | REL NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 223625565 | 0 | MA1-ROT |  | ALEPDALITAN |  | 2026-06-12 | PT02 | 4 | 3 | 2026-06-12 | PM |  | 003
| K301 | 2026-02-25 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202239169 | 8202234582 | Tag 8 TKDN Korosi Atap Tangki |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 288416976 | 288416976 | MA4-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-04-06 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242097 | 8202234925 | Tag 8 Pemeliharaan RPA 1-5 & TBA |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 60425643 | 60425643 | MA2-STA |  | ALEPDALITAN |  | 2026-04-06 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-23 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239043 | 8202238248 | Tag 8 Pem IPAL Domestik RU III | RU3-LKKK | 33-SH-IPAL/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 32815100 | 32815100 | GEN-STA |  | ALEPDALITAN |  | 2026-02-23 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-23 | 2026-06-09 | 2026-01-01 | 2026-12-31 |  | 8202242691 | 8202235629 | Tag 8 Pek Hose Handling Area OM | RU3-ITP | 34-RJ-MUSI/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 223445046 | 223445046 | MA4-STA |  | ALEPDALITAN |  | 2026-04-23 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-06-12 | 2026-06-18 | 2026-06-12 | 2026-12-31 |  | 8202243816 | 8202235056 | Tag 8 Listrik Area Oil Movement |  |  | 60 | REL GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 72452300 | 72452300 | MA4-LIS |  | ALEPDALITAN |  | 2026-06-12 | PT02 |  | 3 | 2026-06-12 | PM |  | 045
| K301 | 2026-04-07 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202242177 | 8202235126 | Tag 8 KV Mekanik Area Utara OM |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 68109650 | 68109650 | MA4-STA |  | ALEPDALITAN |  | 2026-04-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-06-12 | 2026-06-18 | 2026-06-12 | 2026-12-31 |  | 8202243827 | 8202243826 | Tag 8 Conmon Peralatan Rotating RUIII | RU3-CDGP | ALK-MCC-PM-06A/00 | 60 | REL NMAT NTUP PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 228110930 | 0 | MA1-ROT |  | ALEPDALITAN |  | 2026-06-12 | PT02 | 4 | 3 | 2026-06-12 | PM |  | 003
| K301 | 2026-03-05 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239583 | 8202234925 | Tag 7 Pemeliharaan RPA 1-5 & TBA |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 98393994 | 98393994 | MA2-STA |  | ALEPDALITAN |  | 2026-03-05 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-06 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202242085 | 8202235629 | Tag 7 Pek Hose Handling Area OM |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 223445046 | 223445046 | MA4-STA |  | ALEPDALITAN |  | 2026-04-06 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-26 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202239237 | 8202234972 | Tag 7 KV Pembersihan Ceceran Minyak |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 71354000 | 71354000 | MA4-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-26 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202239234 | 8202235126 | Tag 7 KV Mekanik Area Utara OM |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 66300000 | 66300000 | MA4-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-25 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239151 | 8202235817 | Tag 7 ConMon Peralatan Rotating |  |  | 60 | REL GMPS NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 225353105 | 225353105 | MA2-ROT |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-23 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202239022 | 8202238062 | Tag 60 Sewa Beli 20 Unit ATG | RU3-ITP | LT-A-003/00 | 60 | REL GMPS NMAT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 131845314 | 131845314 | MA4-INT |  | ALEPDALITAN |  | 2026-02-23 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-25 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239154 | 8202234925 | Tag 6 Pemeliharaan RPA 1-5 & TBA |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 465174468 | 465174468 | MA2-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-06 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202242070 | 8202235629 | Tag 6 Pek Hose Handling Area OM |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 223445046 | 223445046 | MA4-STA |  | ALEPDALITAN |  | 2026-04-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-18 | 2026-04-29 | 2026-01-01 | 2026-12-31 |  | 8202238948 | 8202234749 | Tag 6 LTSA Online Partial Discharge |  |  | 60 | REL GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 127139600 | 127139600 | MA2-LIS |  | ALEPDALITAN |  | 2026-02-23 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-27 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202239244 | 8202234749 | Tag 6 LTSA Online Partial Discharge |  |  | 60 | REL NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 71978000 | 0 | MA2-LIS |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-06-05 | 2026-06-18 | 2026-06-05 | 2026-12-31 |  | 8202243661 | 8202235030 | Tag 6 KV Mekanik UTL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 72631174 | 72631174 | MA2-STA |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-06-05 | PM |  | 045
| K301 | 2026-02-26 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202239233 | 8202235126 | Tag 6 KV Mekanik Area Utara OM |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 85595000 | 85595000 | MA4-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-03-12 | 2026-05-18 | 2026-01-02 | 2026-12-31 |  | 8202241595 | 8202235140 | Tag 6 KV Mekanik Area CDGP | RU3-CDGP |  | 60 | TECO GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 124202000 | 124202000 | MA1-STA |  | MULYONO701 |  | 2026-03-12 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-20 | 2026-04-29 | 2026-01-01 | 2026-12-31 |  | 8202238991 | 8202235423 | Tag 6 KV Cleaning Tangki M. Ringan |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 34119000 | 34119000 | MA4-STA |  | ALEPDALITAN |  | 2026-02-23 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-04-14 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242421 | 8202242406 | Tag 5 Underground Sewer & Open Sewer CDL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-1-C2H | 23196990 | 23196990 | MA2-LIS |  | ALEPDALITAN |  | 2026-04-16 | PT02 | 6 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-25 | 2026-06-18 | 2026-01-02 | 2026-12-31 |  | 8202243451 | 8202235501 | Tag 5 Pengeruk Lumpur&Pasir Selatan | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 41846285 | 0 | MA1-STA |  | ALEPDALITAN |  | 2026-05-26 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-05 | 2026-06-09 | 2026-05-06 | 2026-12-31 |  | 8202243000 | 8202235152 | Tag 5 KV Sipil Selatan | RU3-ITP | 36-RJ-DER-10/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 31326750 | 31326750 | GEN-STA |  | ALEPDALITAN |  | 2026-05-05 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K301 | 2026-04-27 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242772 | 8202235030 | Tag 5 KV Mekanik UTL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 45743379 | 45743379 | MA2-STA |  | ALEPDALITAN |  | 2026-04-28 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-26 | 2026-05-18 | 2026-01-02 | 2026-12-31 |  | 8202239232 | 8202235140 | Tag 5 KV Mekanik Area CDGP | RU3-CDGP |  | 60 | TECO GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 109650000 | 109650000 | MA1-STA |  | MULYONO701 |  | 2026-02-27 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-03-09 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202241372 | 8202235056 | Tag 5 KV Listrik Area Oil Movement |  |  | 60 | REL GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 37889600 | 37889600 | MA4-LIS |  | ALEPDALITAN |  | 2026-03-09 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-04-14 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242420 | 8202242406 | Tag 4 Underground Sewer & Open Sewer CDL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-1-C2H | 23196990 | 23196990 | MA2-LIS |  | ALEPDALITAN |  | 2026-04-16 | PT02 | 6 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-16 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242493 | 8202241547 | Tag 4 Pengukuran Thermograp RU III | RU3-PP | 22-V-212/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 49237848 | 49237848 | MA4-STA |  | ALEPDALITAN |  | 2026-04-16 | PT02 | 4 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-18 | 2026-04-29 | 2026-01-01 | 2026-12-31 |  | 8202238935 | 8202235501 | Tag 4 Pek Pengerukan Lumpur dan pasir | RU3-CDGP |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 37227995 | 37227995 | MA1-STA |  | ALEPDALITAN |  | 2026-02-23 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-04-14 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242424 | 8202235563 | Tag 4 Pek Kontrak NDT, Radiography |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 92998500 | 92998500 | MA1-STA |  | ALEPDALITAN |  | 2026-04-16 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-05 | 2026-06-09 | 2026-05-06 | 2026-12-31 |  | 8202242999 | 8202235152 | Tag 4 KV Sipil Selatan | RU3-ITP | 36-RJ-DER-10/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 133288500 | 133288500 | GEN-STA |  | ALEPDALITAN |  | 2026-05-05 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K301 | 2026-04-07 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242176 | 8202235030 | Tag 4 KV Pekerjaan Mekanik Area UTL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 93716865 | 93716865 | MA2-STA |  | ALEPDALITAN |  | 2026-04-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-03-05 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202239521 | 8202235056 | Tag 4 KV Listrik Area Oil Movement |  |  | 60 | REL GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 31212000 | 31212000 | MA4-LIS |  | ALEPDALITAN |  | 2026-03-05 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  | 8202243884 | 8302404484 | Tag 34 TKDN TSA Fire Truck RU III Plaju | RU3-LKKK | 03-JLN-AKA/00 | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 777472372 | 0 | WS-PL |  | BUDIRAHARJO |  | 2026-06-17 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-04-14 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242419 | 8202242406 | Tag 3 Underground Sewer & Open Sewer CDL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-1-C2H | 127814963 | 127814963 | MA2-LIS |  | ALEPDALITAN |  | 2026-04-16 | PT02 | 6 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-07 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242171 | 8202241547 | Tag 3 Pengukuran Thermograp RU III | RU3-PP | 22-V-212/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 49887860 | 49887860 | MA4-STA |  | ALEPDALITAN |  | 2026-04-07 | PT02 | 4 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-06-11 | 2026-06-18 | 2026-06-11 | 2026-12-31 |  | 8202243771 | 8202239249 | Tag 3 Peng Lumpur&Pasir Sewer SG | RU3-ITP | 34-BLDG-OC1/00 | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 14743245 | 0 | MA4-STA |  | ALEPDALITAN |  | 2026-06-11 | PT02 | 5 | 3 | 2026-06-11 | PM |  | 003
| K301 | 2026-02-25 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239150 | 8202235563 | Tag 3 Pek Kontrak NDT, Radiography |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 103401225 | 103401225 | MA1-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-11 | 2026-06-18 | 2026-05-06 | 2026-12-31 |  | 8202243130 | 8202235152 | Tag 3 KV Sipil Selatan | RU3-ITP | 36-RJ-DER-10/00 | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 748182750 | 0 | GEN-STA |  | ALEPDALITAN |  | 2026-05-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K301 | 2026-03-09 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202241398 | 8202235341 | Tag 3 KV Sipil Area Laboratory | RU3-LAB |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 56345806 | 56345806 | GEN-STA |  | ALEPDALITAN |  | 2026-03-09 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-03-05 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239991 | 8202235030 | Tag 3 KV Pekerjaan Mekanik Area UTL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 74985289 | 74985289 | MA2-STA |  | ALEPDALITAN |  | 2026-03-05 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-03-12 | 2026-04-29 | 2026-01-01 | 2026-12-31 |  | 8202241594 | 8202235701 | Tag 3 KV Mekanik area Selatan OM PL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 80855256 | 80855256 | MA4-STA |  | ALEPDALITAN |  | 2026-03-12 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-26 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239235 | 8202235240 | Tag 3 Kontrak Volume Mekanik PP |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 59550150 | 59550150 | MA2-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 |  | 8202243821 | 8202238421 | Tag 24 PM&CM RU II |  |  | 50 | CRTD NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 385828977 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2026-06-12 | PM |  | 045
| K301 | 2026-05-20 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202243347 | 8202238421 | Tag 23 PM&CM RU III |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 138759048 | 0 | MA4-ROT |  | ALEPDALITAN |  | 2026-05-26 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-22 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242669 | 8202238421 | Tag 22 PM CM Rot & Elec. | RU3-ITP | 34-RJ-MUSI/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 146734948 | 146734948 | MA4-ROT |  | ALEPDALITAN |  | 2026-04-22 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-03-05 | 2026-05-26 | 2026-01-02 | 2026-12-31 |  | 8202239652 | 8202235565 | Tag 22 Jasa Operator& Pem. Ringan Alber | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 94813000 | 94813000 | WS-SG |  | SAPBATCH | 2026-05-26 | 2026-03-05 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K301 | 2026-03-09 | 2026-06-18 | 2026-01-02 | 2026-05-26 |  | 8202241407 | 8202235565 | Tag 22 Jasa Operator& Pem. Ringan Alber | RU3-WS | BEN-TOOL/00 | 60 | REL CNF GMPS NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 94045000 | 94045000 | WS-SG |  | RRAMADHANI | 2026-05-26 | 2026-03-09 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-06 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242081 | 8202238421 | Tag 21 PM CM Rot & Elec. |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 186201868 | 186201868 | MA4-ROT |  | ALEPDALITAN |  | 2026-04-06 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-25 | 2026-05-18 | 2026-01-02 | 2026-12-31 |  | 8202239166 | 8202235151 | Tag 20 TKDN KV Cleaning & Ganti Catalyst | RU3-CDGP |  | 60 | TECO GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 162057502 | 162057502 | MA1-STA |  | MULYONO701 |  | 2026-02-27 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-25 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239165 | 8202238421 | Tag 20 PM CM Rot & Elec. |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 149717410 | 149717410 | MA4-ROT |  | ALEPDALITAN |  | 2026-02-27 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-03-05 | 2026-05-26 | 2026-01-01 | 2026-12-31 |  | 8202239651 | 8202235565 | Tag 20 Jasa Operator& Pem. Ringan Alber | RU3-WS | BEN-TOOL/00 | 60 | CLSD GMPS NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 95663000 | 95663000 | WS-SG |  | YUDOALANSYAH |  | 2026-03-05 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K301 | 2026-04-14 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242418 | 8202242406 | Tag 2 Underground Sewer & Open Sewer CDL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-1-C2H | 23196990 | 23196990 | MA2-LIS |  | ALEPDALITAN |  | 2026-04-16 | PT02 | 6 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-03-10 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202241548 | 8202241547 | Tag 2 Pengukuran Thermograp RU III | RU3-PP | 22-V-212/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 103172949 | 103172949 | MA4-STA |  | ALEPDALITAN |  | 2026-03-10 | PT02 | 4 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-05 | 2026-06-09 | 2026-01-01 | 2026-12-31 |  | 8202242998 | 8202235152 | Tag 2 KV Sipil Selatan | RU3-ITP | 36-RJ-DER-10/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 56812300 | 56812300 | GEN-STA |  | ALEPDALITAN |  | 2026-05-05 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-02-20 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202238996 | 8202235341 | Tag 2 KV Sipil Area Laboratory | RU3-LAB |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 30417329 | 30417329 | GEN-STA |  | ALEPDALITAN |  | 2026-02-23 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-07 | 2026-04-29 | 2026-01-01 | 2026-12-30 |  | 8202242178 | 8202235364 | Tag 2 KV Perb.Bocoran Dinding Tangki |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-1-C2H | 114490000 | 114490000 | MA4-STA |  | ALEPDALITAN |  | 2026-04-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-23 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202239045 | 8202235240 | Tag 2 KV Mekanik PP |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 82248550 | 82248550 | MA2-STA |  | ALEPDALITAN |  | 2026-02-23 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-25 | 2026-06-09 | 2026-01-01 | 2026-12-31 |  | 8202243463 | 8202235102 | Tag 2 KV Isolasi Area CDGP OM Plaju | RU3-CDGP | ALK-MCC-PM-24/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 171816500 | 171816500 | MA1-STA |  | ALEPDALITAN |  | 2026-05-25 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-03-09 | 2026-04-29 | 2026-01-01 | 2026-12-31 |  | 8202241410 | 8202239249 | Tag 2 KV Cleaning dan Pngerukan Lmpr SG |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 17387929 | 17387929 | MA4-STA |  | ALEPDALITAN |  | 2026-03-09 | PT02 | 5 | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-03-05 | 2026-04-29 | 2026-01-01 | 2026-12-31 |  | 8202239482 | 8202235439 | Tag 2 Kontr.Vol Online leak Sealing |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 393295000 | 393295000 | MA1-STA |  | ALEPDALITAN |  | 2026-03-05 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-06-05 | 2026-06-18 | 2026-04-20 | 2026-12-31 |  | 8202243663 | 8202242586 | Tag 2 Isolasi Panas CDl,UTL&OM SG | RU3-ITP | ITP-T-150/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 330744300 | 330744300 | MA4-STA |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-04-20 | PM |  | 045
| K301 | 2026-02-23 | 2026-05-18 | 2026-01-02 | 2026-12-31 |  | 8202239034 | 8202235151 | Tag 19 KV Cleaning & Ganti Catalyst | RU3-CDGP |  | 60 | TECO GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 26637450 | 26637450 | MA1-STA |  | MULYONO701 |  | 2026-02-23 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-06-04 | 2026-06-18 | 2026-06-04 | 2026-12-31 |  | 8202243623 | 8202235092 | Tag 14 Sup Teknisi&Operator WS | RU3-WS | BEN-TOOL/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 154036357 | 154036357 | WS-SG |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 045
| K301 | 2026-04-30 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242853 | 8202235092 | Tag 13 Sup Teknisi&Operator WS | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 147807837 | 147807837 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-04-30 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K301 | 2026-04-27 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242780 | 8202235092 | Tag 12 Sup Teknisi&Operator WS | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 163621424 | 163621424 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-04-28 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K301 | 2026-05-25 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202243449 | 8202238248 | Tag 12 Pek IPAL Domestik | RU3-LKKK | 33-SH-IPAL/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 43769900 | 43769900 | GEN-STA |  | ALEPDALITAN |  | 2026-05-26 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-03-12 | 2026-05-19 | 2026-01-02 | 2026-12-31 |  | 8202241593 | 8202235092 | Tag 11 Sup Teknisi dan Oprtr | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 156624680 | 156624680 | WS-SG |  | SAPBATCH | 2026-05-19 | 2026-03-12 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K301 | 2026-06-11 | 2026-06-18 | 2026-06-11 | 2026-12-31 |  | 8202243769 | 8202234925 | Tag 11 RPA 1-5 & Teknik Bawah Air |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 71186732 | 71186732 | MA2-STA |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K301 | 2026-04-27 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242781 | 8202238248 | Tag 11 Pek IPAL Domestik | RU3-LKKK | 33-SH-IPAL/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 41168050 | 38788050 | GEN-STA |  | ALEPDALITAN |  | 2026-04-28 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-26 | 2026-05-19 | 2026-01-02 | 2026-12-31 |  | 8202239236 | 8202235092 | Tag 10 Sup Teknisi dan Oprtr | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 41437656 | 41437656 | WS-SG |  | SAPBATCH | 2026-05-19 | 2026-02-27 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K301 | 2026-05-20 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202243333 | 8202234925 | Tag 10 RPA 1-5 & Teknik Bawah Air |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 71386012 | 71386012 | MA2-STA |  | ALEPDALITAN |  | 2026-05-26 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-04-07 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242179 | 8202238248 | Tag 10 Pem IPAL Domestik RU III | RU3-LKKK | 33-SH-IPAL/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 32656150 | 32656150 | GEN-STA |  | ALEPDALITAN |  | 2026-04-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-05 | 2026-06-09 | 2026-01-02 | 2026-12-31 |  | 8202242996 | 8202235105 | Tag 10 Mekanik CDL,OM,UTL SG | RU3-UTL | 61-HEST-101/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 100745000 | 100745000 | MA3-ROT |  | ALEPDALITAN |  | 2026-05-05 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-06-09 | 2026-06-18 | 2026-06-09 | 2026-12-31 |  | 8202243713 | 8202235629 | Tag 10 Hose Handling Dermaga | RU3-ITP | 34-RJ-MUSI/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 223445046 | 223445046 | MA4-STA |  | ALEPDALITAN |  | 2026-06-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K301 | 2026-06-12 | 2026-06-18 | 2026-06-12 | 2026-12-31 |  | 8202243829 | 8202243826 | Tag 10 Conmon Peralatan Rotating RUIII | RU3-CDGP | ALK-MCC-PM-06A/00 | 60 | REL NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 174472700 | 0 | MA1-ROT |  | ALEPDALITAN |  | 2026-06-12 | PT02 | 4 | 3 | 2026-06-12 | PM |  | 003
| K301 | 2026-04-14 | 2026-04-29 | 2026-01-02 | 2026-12-31 |  | 8202242416 | 8202242406 | Tag 1 Underground Sewer & Open Sewer CDL |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-1-C2H | 36334563 | 36334563 | MA2-LIS |  | ALEPDALITAN |  | 2026-04-16 | PT02 | 6 | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-05-26 | 2026-06-18 | 2026-01-01 | 2026-12-31 |  | 8202243523 | 8202243522 | Tag 1 Steam Leak Non Trap Kilang SG | RU3-ITP | 35-PICA-140-J10/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 124658000 | 124658000 | MA1-STA |  | ALEPDALITAN |  | 2026-05-26 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-05-26 | 2026-06-18 | 2026-01-01 | 2026-12-31 |  | 8202243525 | 8202243524 | Tag 1 Steam Leak Non Trap Kilang PL | RU3-ITP | 35-PICA-140-J10/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 91290000 | 91290000 | MA1-STA |  | ALEPDALITAN |  | 2026-05-26 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-04-27 | 2026-06-09 | 2026-04-28 | 2026-12-31 |  | 8202242783 | 8202242782 | Tag 1 Sipil Utara Kil. Plaju | RU3-CDGP | ALK-MCC-PM-24/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 168461500 | 168461500 | MA1-STA |  | ALEPDALITAN |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K301 | 2026-04-30 | 2026-06-09 | 2026-04-30 | 2026-12-31 |  | 8202242852 | 8202235477 | Tag 1 KV Sarana Tambat Kapal SG | RU3-ITP | ITP-JETTY-001/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 507078550 | 507078550 | MA3-STA |  | ALEPDALITAN |  | 2026-04-30 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K301 | 2026-04-20 | 2026-06-09 | 2026-04-20 | 2026-12-31 |  | 8202242587 | 8202242586 | Tag 1 KV Isolasi Area CDL UTL OM SG 26 | RU3-ITP | ITP-T-150/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 199743000 | 199743000 | MA4-STA |  | ALEPDALITAN |  | 2026-04-20 | PT02 |  | 3 | 2026-04-20 | PM |  | 003
| K301 | 2026-04-30 | 2026-06-09 | 2026-01-01 | 2026-12-31 |  | 8202242848 | 8202235102 | Tag 1 KV Isolasi Area CDGP OM Plaju | RU3-CDGP | CD4-8-1/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 224952861 | 224952861 | MA1-STA |  | ALEPDALITAN |  | 2026-04-30 | PT02 |  | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-02-27 | 2026-04-29 | 2026-01-01 | 2026-12-31 |  | 8202239252 | 8202239249 | Tag 1 KV Cleaning dan Pngerukan Lmpr SG |  |  | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 159576800 | 159576800 | MA4-STA |  | ALEPDALITAN |  | 2026-02-27 | PT02 | 5 | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-05-20 | 2026-06-09 | 2026-05-20 | 2026-12-31 |  | 8202243327 | 8202243325 | Tag 1 Fire Proofing (Pemeliharaan) | RU3-CDGP | SRM-4-1/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 138551199 | 138551199 | MA1-STA |  | ALEPDALITAN |  | 2026-05-25 | PT02 | 4 | 3 | 2026-05-20 | PM |  | 003
| K301 | 2026-05-20 | 2026-06-09 | 2026-05-20 | 2026-12-31 |  | 8202243326 | 8202243325 | Tag 1 Fire Proofing | RU3-CDGP | SRM-4-1/00 | 60 | REL GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 2216819183 | 2216819183 | MA1-STA |  | ALEPDALITAN |  | 2026-05-25 | PT02 | 4 | 3 | 2026-05-20 | PM |  | 003
| K202 | 2026-05-05 | 2026-06-10 | 2026-02-02 | 2026-02-02 | 2102352149 | 8202242978 |  | TA 2027 .2102336697#Pemeriksaan TCV Atom | RU2S-KIL | 101-TCV-063/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 144001 | 0 | MAS-INT |  | JUNAIDIT |  | 2026-06-10 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-05-05 | 2026-06-10 | 2026-02-02 | 2026-02-02 | 2102352154 | 8202242977 |  | TA 2027 .2102336385#pengecekan Control V |  | 101-PCV-076/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 1 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-06-10 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-05-05 | 2026-06-10 | 2026-02-02 | 2026-02-02 | 2102352206 | 8202242980 |  | TA 2027 .2102334394#Pemeriksaan Control |  | 101-PCV-072/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 1 | 0 | MAS-INT |  | JUNAIDIT |  | 2026-06-10 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-04-28 | 2026-06-18 | 2026-04-23 | 2026-12-30 | 2102368328 | 8202242786 |  | T3 suplai udara bertekanan UPC | RU4-RFCUTL | 156K502A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 845971000 | 845971000 | MA5-ROT |  | FARIZSETYANA |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 045
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-08-07 |  | 8202241502 | 8202239394 | SWO Sarana dan Fasilitas UCO | RU6-DHC | 21-S-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 5 | 0 | MA2-INT |  | DANDARWANI |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-04-10 | 2026-04-15 | 2026-01-02 | 2026-05-26 |  | 8202242342 | 8202232733 | SWO Pigging SPL 17.500 DWT & 35.000 DWT | RU6-ITP | 42-T-503/00 | 50 | CLSD NCMP NMAT PRC | 6MR | D16/26/B6/RT-C2H | 2200000001 | 0 | MA4-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-06-09 | 2026-06-10 | 2026-04-01 | 2026-08-18 |  | 8202243723 | 8202242050 | SWO Pemb. LTSA Sparing Thp 5 (85%) | RU6-LK/KK | JALANKILANG/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 129353340 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K601 | 2026-04-02 | 2026-06-17 | 2026-04-01 | 2026-08-18 |  | 8202242051 | 8202242050 | SWO Pemb. LTSA Sparing Thp 4 (85%) | RU6-LK/KK | JALANKILANG/00 | 60 | TECO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 126803340 | 126803340 | MA4-STA |  | ZAMZAMKHALID |  | 2026-04-07 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-02 | 2026-04-01 | 2026-11-25 | 2102367194 | 8202242050 |  | SWO Pemb. LTSA Sparing | RU6-LK/KK | JALANKILANG/00 | 01 | CRTD GMCO NMAT PRC | 6MR | D16/26/B6/RT-C2H | 21120 | 0 | MA4-STA |  | ANDRIES |  |  | PT02 | 5 | 2 | 2026-04-01 | PM |  | 003
| K601 | 2026-05-18 | 2026-05-18 | 2026-05-04 | 2026-09-17 |  | 8202243247 | 8202243145 | SWO Pemb. LTSA O2 Ametek Termin 7 (85%) | RU6-RCC | 15-AT-002/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 257975000 | 257975000 | MA1-INT |  | DANDARWANI |  | 2026-05-18 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-05-29 | 2026-05-29 | 2026-03-03 | 2026-07-24 |  | 8202243541 | 8202242747 | SWO Pemb. LTSA Metering Thp 41 (15%) | RU6-ITP | 42-A-100/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 23678230 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-29 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-05-29 | 2026-05-29 | 2026-03-03 | 2026-07-24 |  | 8202243539 | 8202242747 | SWO Pemb. LTSA Metering Thp 40 (15%) | RU6-ITP | 42-A-100/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 14837961 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-29 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-05-29 | 2026-05-29 | 2026-03-03 | 2026-07-24 |  | 8202243538 | 8202242747 | SWO Pemb. LTSA Metering Thp 39 (15%) | RU6-ITP | 42-A-100/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 17308474 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-29 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-05-29 | 2026-05-29 | 2026-03-03 | 2026-07-24 |  | 8202243537 | 8202242747 | SWO Pemb. LTSA Metering Thp 38 (15%) | RU6-ITP | 42-A-100/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 17948426 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-29 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-05-29 | 2026-05-29 | 2026-03-03 | 2026-07-24 |  | 8202243536 | 8202242747 | SWO Pemb. LTSA Metering Thp 37 (15%) | RU6-ITP | 42-A-100/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 16683404 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-29 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-03-03 | 2026-07-24 |  | 8202242885 | 8202242747 | SWO Pemb. LTSA Metering Termin 41 (85%) | RU6-ITP | 42-A-100/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 134176637 | 134176637 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-03-03 | 2026-07-24 |  | 8202242883 | 8202242747 | SWO Pemb. LTSA Metering Termin 40 (85%) | RU6-ITP | 42-A-100/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 84081777 | 84081777 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-03-03 | 2026-07-24 |  | 8202242882 | 8202242747 | SWO Pemb. LTSA Metering Termin 39 (85%) | RU6-ITP | 42-A-100/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 98081351 | 98081351 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-03-03 | 2026-07-24 |  | 8202242881 | 8202242747 | SWO Pemb. LTSA Metering Termin 38 (85%) | RU6-ITP | 42-A-100/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 101707746 | 101707746 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-03-03 | 2026-07-24 |  | 8202242878 | 8202242747 | SWO Pemb. LTSA Metering Termin 37 (85%) | RU6-ITP | 42-A-100/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 94539290 | 94539290 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-03-03 | 2026-07-24 |  | 8202242877 | 8202242747 | SWO Pemb. LTSA Metering Termin 36 (85%) | RU6-ITP | 42-A-100/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 86786700 | 86768700 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-05-29 | 2026-05-29 | 2026-03-03 | 2026-07-24 |  | 8202243535 | 8202242747 | SWO Pemb. LTSA Metering Termin 36 (15%) | RU6-ITP | 42-A-100/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 15315300 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-29 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-23 | 2026-05-13 | 2026-04-16 | 2026-09-02 | 2102368042 | 8202242680 |  | SWO Pemb. LTSA CV Masoneila Thp 4 (100%) | RU6-RCC | 15-SLV-105/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 507082000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-04-23 | PT02 | 5 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-15 | 2026-03-11 | 2026-09-16 | 2102366541 | 8202242028 |  | SWO Pemb. LTSA ConMon PLC/MMS | RU6-RCC | OS-14/00 | 50 | REL CSER GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | DANDARWANI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-05-29 | 2026-05-29 | 2026-04-16 | 2026-09-02 |  | 8202243542 | 8202242941 | SWO Pemb. LTSA ATG Thp 11 (100%) | RU6-ITP | 42-T-403A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 272100000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-29 | PT02 | 5 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-05-04 | 2026-06-17 | 2026-04-16 | 2026-09-02 |  | 8202242942 | 8202242941 | SWO Pemb. LTSA ATG Termin 10 (100%) | RU6-ITP | 42-T-403A/00 | 60 | TECO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 204600000 | 204600000 | MA4-STA |  | ZAMZAMKHALID |  | 2026-05-04 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-05-13 | 2026-09-28 |  | 8202243366 | 8202243361 | SWO Pemb On Call Thp 5 LTSA CEMS | RU6-RCC | 15-B-101/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 69014050 | 69014050 | MA1-INT |  | DANDARWANI |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-05-13 | 2026-09-28 |  | 8202243365 | 8202243361 | SWO Pemb On Call Thp 4 LTSA CEMS | RU6-RCC | 15-B-101/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 12174932 | 12174932 | MA1-INT |  | DANDARWANI |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-05-13 | 2026-09-28 |  | 8202243364 | 8202243361 | SWO Pemb LTSA CEMS Thp 12 | RU6-RCC | 15-B-101/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 59458350 | 59458350 | MA1-INT |  | DANDARWANI |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-05-13 | 2026-09-28 |  | 8202243363 | 8202243361 | SWO Pemb LTSA CEMS Thp 11 | RU6-RCC | 15-B-101/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 18698725 | 18698725 | MA1-INT |  | DANDARWANI |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-05-13 | 2026-09-28 |  | 8202243362 | 8202243361 | SWO Pemb LTSA CEMS Thp 10 | RU6-RCC | 15-B-101/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 14247700 | 14247700 | MA1-INT |  | DANDARWANI |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-04-10 | 2026-06-08 | 2026-04-08 | 2026-08-24 |  | 8202242326 | 8202242320 | SWO Pemb LTSA CEMS 11-AT-401 Thp 3 (85%) | RU6-HSC | 11-F-101/00 | 60 | TECO GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 216658663 | 216658663 | MA1-INT |  | ZAMZAMKHALID |  | 2026-04-13 | PT02 | 5 | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-05-20 | 2026-05-29 | 2026-03-05 | 2026-07-28 |  | 8202243345 | 8202239479 | SWO LTSA Resertifikasi Boiler 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 103140000 | 0 | MA4-STA |  | HARSARIZANO |  | 2026-05-20 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-05-20 | 2026-05-20 | 2026-03-09 | 2026-07-30 |  | 8202243343 | 8202241440 | SWO LTSA Resertifikasi Boiler 52-B-101B | RU6-UTL | 52-B-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 93764000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-20 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-04-30 | 2026-09-16 |  | 8202243822 | 8202242981 | SWO LTSA Cleaning Mnyk Rngan Thp 8 | RU6-POC | 34-A-101-T-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 91510000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-09-30 |  | 8202243301 | 8202243298 | SWO LTSA Cleaning 2022 Thp 6 | RU6-ITP | 42-T-107B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 191941900 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-09-30 |  | 8202243300 | 8202243298 | SWO LTSA Cleaning 2022 Thp 4 | RU6-ITP | 42-T-107B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 77528000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-15 | 2026-02-03 | 2026-06-30 |  | 8202242474 | 8202237820 | SWO Coalescer 14-S-101 | RU6-DHC | 14-S-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-19 | 2026-03-13 | 2026-02-19 | 2026-12-30 | 2102364584 | 8202238968 |  | Suplai Daya dan Kontrol Motor Pompa | RU2-HSC | 301-ONP-3A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/NR-D2H | 800000000 | 0 | MA2-LIS |  | ADEMULYADI |  | 2026-02-23 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K501 | 2026-02-24 | 2026-06-17 | 2026-01-02 | 2026-01-09 |  | 8202239136 | 8202238855 | SUPERVISI API 936 F-2-01A/B | RU5-E15112 | 2-SPW05-3-B6/00 | 60 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 75000000 | 0 | ENG-STA |  | MANKURNIAWAN |  | 2026-02-24 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-23 | 2026-02-23 | 2026-02-20 | 2026-12-18 | 2102364648 | 8202239013 |  | Superior Order Pekerjaan EI MA1 2026 | RU6-RCC | 09-14B-PSW2-01A/00 | 01 | CRTD CSER GMCO NMAT PRC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DINDINS |  |  | PT02 | 3 | 2 | 2026-02-20 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-07-31 | 2102365598 | 8202241525 |  | Stock Filter & Mech Seal 14P-101 | RU6-DHC | 14-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 218907223 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-04 | 2026-04-23 | 2102365597 | 8202241523 |  | Stock Filter & Mech Seal 12-P-505A/B | RU6-DHC | 12-P-505A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-03-13 | 2026-03-30 | 2026-03-12 | 2026-08-04 | 2102366586 | 8202241715 |  | SPKR LTSA Piping Tahap 6 Salamdarma | RU6-UTL | 53-P-101A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 961954000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-03-11 | 2026-03-26 | 2026-03-09 | 2026-07-30 | 2102366401 | 8202241575 |  | SPKR LTSA Piping Tahap 5 SPKR No. 007/KP | RU6-ITP | 42-PIPE/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 289263000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-11 | PT02 | 6 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-03-11 | 2026-03-26 | 2026-03-09 | 2026-07-30 | 2102366400 | 8202241574 |  | SPKR LTSA Piping Tahap 4 SPKR No. 321/KP | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 371120000 | 315452000 | MA4-STA |  | DANDARWANI |  | 2026-03-12 | PT02 | 6 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-03-11 | 2026-03-26 | 2026-03-09 | 2026-07-30 | 2102366329 | 8202241566 |  | SPKR LTSA Piping Tahap 3 SPKR No. 320 | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 202896000 | 172461600 | MA4-STA |  | DANDARWANI |  | 2026-03-11 | PT02 | 6 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-03-11 | 2026-03-26 | 2026-03-09 | 2026-07-30 | 2102366328 | 8202241565 |  | SPKR LTSA Piping Tahap 2 SPKR No. 301 | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 277946000 | 236254100 | MA4-STA |  | DANDARWANI |  | 2026-03-11 | PT02 | 6 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-03-11 | 2026-03-26 | 2026-03-09 | 2026-07-30 | 2102366353 | 8202241576 |  | SPKR LTSA Piping tahap 1 OCU | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 50420000 | 42857000 | MA3-STA |  | DANDARWANI |  | 2026-03-11 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-08-20 |  | 8202242160 | 8202242158 | SPK Thp 2 15% | RU6-UTL | 58-K-101E/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 2268000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-08-20 |  | 8202242158 | 8202242153 | SPK Thp 1 15% | RU6-UTL | 58-K-101E/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 28645500 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-09-30 | 2102369171 | 8202243298 |  | SPK LTSA Cleaning 2022 Thp 3 | RU6-ITP | 42-T-107B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 5859150 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-19 | 2026-06-19 | 2026-12-08 |  | 8202243782 | 8202243781 | SPK 32 LTSA Transformator RU VI | RU6-UTL | 01-PTR1-01A/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 177789000 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-11 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 003
| K601 | 2026-04-09 | 2026-06-03 | 2026-02-27 | 2026-07-22 | 2102365143 | 8202242301 |  | SPK 31 LTSA Transformator RU VI | RU6-HSC | 11-V-101B-3/01 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 84098000 | 0 | MA1-LIS |  | DINDINS |  | 2026-04-10 | PT02 | 5 | 3 | 2026-02-27 | PM |  | 003
| K601 | 2026-03-12 | 2026-06-03 | 2026-06-03 | 2026-10-12 | 2102351032 | 8202241665 |  | SPK 30 LTSA Transformator RU VI | RU6-HSC | 17-PTR1-02A/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 467158000 | 0 | MA3-LIS |  | DINDINS |  | 2026-03-13 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-22 | 2026-06-19 | 2026-06-19 | 2102366760 | 8202243960 |  | Sight Glass Pecah | RU2-HCC | 701-P-4A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 10500000 | 0 | MA2-ROT |  | NURFADHILLA |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K501 | 2026-02-09 | 2026-05-09 | 2026-02-02 | 2026-02-02 | 2102358736 | 8202238775 |  | Sewa Forklift & Truck (3) | RU5-E15112 | F-3-01A/00 | 60 | CLSD CNF NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 268750000 | 0 | WS-KAB |  | SAPBATCH | 2026-02-06 | 2026-02-20 | PT02 | 5 | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-02-09 | 2026-02-20 | 2026-02-02 | 2026-04-30 | 2102358737 | 8202238773 |  | Sewa Forklift & Truck (2) | RU5-E15112 | F-3-01A/00 | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 251550000 | 0 | WS-KAB |  | MANKURNIAWAN |  | 2026-02-20 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-05-14 | 2026-05-14 | 2026-06-30 | 2026-06-30 |  | 8202243203 | 8202243201 | Sewa DEG Periode Maret-April 2026 | RU7-UTL | 4-KDE-03E/00 | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-5-D2H | 253820000 | 0 | MA-ROT |  | YAYANHER |  | 2026-05-14 | PT02 | 5 | 3 | 2026-06-30 | PM |  | 005
| K701 | 2026-05-14 | 2026-05-14 | 2026-06-30 | 2026-06-30 | 2102368368 | 8202243201 |  | Sewa DEG Periode Jan-Feb 2026 | RU7-UTL | 4-KDE-03E/00 | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-4-D2H | 436953000 | 0 | MA-ROT |  | RIZKAANDIKAP |  | 2026-05-14 | PT02 | 3 | 3 | 2026-06-30 | PM |  | 005
| K701 | 2026-05-14 | 2026-05-14 | 2026-06-30 | 2026-06-30 |  | 8202243202 | 8202243201 | Sewa DEG Periode Feb-Maret 2026 | RU7-UTL | 4-KDE-03E/00 | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-4-D2H | 229810000 | 0 | MA-ROT |  | YAYANHER |  | 2026-05-14 | PT02 | 6 | 3 | 2026-06-30 | PM |  | 005
| K701 | 2026-06-19 | 2026-06-19 | 2026-12-30 | 2026-12-30 | 2102369566 | 8202243976 |  | Sewa DEG Periode Apr-Mei 2026 | RU7-UTL | 4-KDE-03B/00 | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-4-D2H | 240105000 | 0 | MA-ROT |  | YAYANHER |  | 2026-06-19 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-15 | 2026-01-28 | 2026-06-23 |  | 8202242460 | 8202232147 | Sewa Barge Tahap 8 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 40000000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-15 | 2026-01-28 | 2026-06-23 |  | 8202242458 | 8202232147 | Sewa Barge Tahap 7 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 40000000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K201 | 2026-03-02 | 2026-05-29 | 2026-03-31 | 2026-03-31 | 2102365106 | 8202239285 |  | Services dan ganti bearing motor | RU2-ITP | P-202B-M/00 | 60 | REL CSER MSPT PRC SETC | 2ER | D12/26/B6/RT-D2H | 5754664 | 0 | MA4-LIS |  | NURFADHILLA |  | 2026-03-02 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K202 | 2026-03-11 | 2026-06-22 | 2026-03-04 | 2026-03-04 | 2102365878 | 8202241579 |  | Service Rutin Air Compressor Kilang SPK | RU2S-KIL | 946-AC-1-MCC-E/00 | 50 | REL CSER MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 45049000 | 0 | MAS-LIS |  | JUNIANTO |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K201 | 2026-04-07 | 2026-05-26 | 2026-03-06 | 2026-03-06 | 2102366218 | 8202242131 |  | Service Motor 100-PM-4 A | RU2-HSC | 100-PM-4A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/NR-D2H | 664500 | 664500 | MA2-LIS |  | ADEMULYADI |  | 2026-04-07 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K202 | 2026-04-07 | 2026-04-17 | 2026-03-17 | 2026-03-17 | 2102366796 | 8202242135 |  | Service 4000 RH 900-06GE-6 | RU2S-KIL | 900-06GE-6/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/RTZ-C2H | 53636499 | 30286499 | MAS-ME1 |  | JUNAIDIT |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K201 | 2026-04-30 | 2026-05-19 | 2026-04-30 | 2026-05-12 | 2102368293 | 8202242897 |  | Service 310-BV-9 A | RU2-HSC | 310-BV-9A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 882521 | 882521 | MA2-INT |  | ADEMULYADI |  | 2026-05-08 | PT02 | 5 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-09-21 |  | 8202243024 | 8202242240 | Service & Fire Water Thp 4 (85%) | RU6-UTL | 54SW0103MS0124N/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 204450500 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-06 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-06-17 |  | 2026-06-03 | 2026-06-03 | 2102369553 | 8202243922 |  | Sensor Tandem Seal 91K401B | RU4-SRU | 91K401BM/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 4 | 2 | 2026-06-03 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-05 | 2026-02-23 | 2026-02-23 | 2102364718 | 8202239216 |  | Selisih penunjukan level CPI 200LT051 | RU4-LOC3 | 200LT051/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | FARIZSETYANA |  |  | PT02 | 2 | 2 | 2026-03-05 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-07-07 |  | 8202241628 | 8202239394 | Sarana dan Fasilitas Instrument UCO Tamb | RU6-DHC | 21-S-101/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 4773637 | 1325030 | MA2-INT |  | DANDARWANI |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-09 | 2026-03-03 | 2026-06-26 | 2102365243 | 8202239394 |  | Sarana dan Fasilitas Instrument UCO | RU6-DHC | 21-S-101/00 | 50 | REL CSER GMCO MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 29714692 | 0 | MA2-INT |  | DINDINS |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 004
| K401 | 2026-05-26 | 2026-06-03 | 2026-05-25 | 2026-11-30 | 2102368211 | 8202243510 |  | Sample point S8409 bocor flex hose - gan |  |  | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 30 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 4 | 3 | 2026-05-25 | PM |  | 045
| K601 | 2026-05-05 | 2026-05-05 | 2026-04-28 | 2026-04-28 | 2102368533 | 8202243001 |  | Sample Box PENEX | RU6-HSC | 33-C-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 5662704 | 0 | MA3-STA |  | DANDARWANI |  | 2026-05-05 | PT02 | 5 | 3 | 2026-04-28 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-19 | 2026-04-02 | 2026-04-02 | 2102367333 | 8202243973 |  | Safety guard rail di area water pond | RU2-UTL | 520-PIPING/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 7579466 | 3789733 | MA3-STA |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-03-05 | 2026-05-26 | 2026-12-02 | 2026-12-02 | 2102352022 | 8202240008 |  | s102350121#TSA GROUNDING HOC | RU2-HOC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1000000000 | 573039000 | MA1-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-11 | 2026-05-11 | 2102368935 | 8202243169 |  | RKAP27_Upgrade AVR 051G103 | RU4-UTL | 051G103T/00 | 50 | CRTD NMAT PRC | 4ER |  | 2500000000 | 0 | MA5-LIS |  | DHANANGDH |  |  | PT02 | 3 | 2 | 2026-05-11 | PM |  | 045
| K401 | 2026-06-04 | 2026-06-20 | 2026-09-04 | 2026-12-28 | 2102369516 | 8202243617 |  | RKAP27_Penggantian Relay MV Incomer 30SS | RU4-TRML | 30SS1/00 | 50 | CRTD NMAT PRC | 4ER |  | 3100000000 | 0 | MA3-LIS |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-09-04 | PM |  | 001
| K401 | 2026-02-27 | 2026-03-09 | 2026-02-26 | 2026-12-30 | 2102364993 | 8202239240 |  | RKAP26_Penyehatan RSBV Area LNHT ISOM | RU4-GTO | 140E607C-A/00 | 50 | CLSD CSER NCMP NMAT PRC | 4IR |  | 8000000000 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-05-06 | 2026-05-07 | 2026-04-08 | 2026-04-08 | 2102367662 | 8202243035 |  | RKAP26_penggantian LCS FOCII Tahap 2 | RU4-FOC2 | 011E111M01/00 | 50 | CLSD NCMP NMAT PRC | 4ER |  | 2800000000 | 0 | MA2-LIS |  | TEGARPRAMUDY |  |  | PT02 | 3 | 2 | 2026-05-07 | PM |  | 004
| K401 | 2026-04-10 |  | 2026-04-10 | 2026-04-10 | 2102356523 | 8202242321 |  | RKA26_UP Plenum MA-6 | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 1 | 0 | MA6-STA |  |  |  |  | PT02 | 8 | 2 | 2026-04-10 | PM |  | 045
| K401 | 2026-04-10 |  | 2026-04-10 | 2026-04-10 | 2102356815 | 8202242330 |  | RKA26_UP Plenum MA-5 |  |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 1 | 0 | MA5-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 045
| K401 | 2026-04-10 |  | 2026-02-02 | 2026-02-02 | 2102356525 | 8202242322 |  | RKA26_UP Perbaikan Pipa OLLS | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 1 | 0 | MA6-STA |  |  |  |  | PT02 | 8 | 2 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-10 |  | 2026-04-10 | 2026-04-10 | 2102356851 | 8202242327 |  | RKA26_UP Perb Pipa & Dummy Support MA5 |  |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 1 | 0 | MA5-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 045
| K401 | 2026-03-02 |  | 2026-03-02 | 2026-03-02 | 2102356526 | 8202239305 |  | RKA26_UP Perb Pipa & Dummy Support MA-6 | RU4-RFCC | 101-CS0020-1/00 | 01 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 1 | 0 | MA6-STA |  |  |  |  | PT02 | 8 | 2 | 2026-03-02 | PM |  | 005
| K401 | 2026-04-10 |  | 2026-04-10 | 2026-04-10 | 2102356668 | 8202242325 |  | RKA26_UP Cleaning Water Jet SWD | RU4-RFCUTL |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 1 | 0 | MA5-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 045
| K401 | 2026-04-10 |  | 2026-04-10 | 2026-04-10 | 2102356811 | 8202242328 |  | RKA26_UP Cleaning HE Cooler UTL |  |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 1 | 0 | MA5-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 045
| K201 | 2026-03-05 | 2026-06-05 | 2026-12-02 | 2026-12-02 | 2102351270 | 8202239737 |  | RK0379 LTSA Reciprocating Pump | RU2-HCC | 211-P-5A/01 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-03-17 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K201 | 2026-03-09 | 2026-05-26 | 2026-02-11 | 2026-02-11 | 2102364161 | 8202241483 |  | RK0377 PM & Rutin Repair Rotating Equipm | RU2-HCC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 2850000000 | 1334153000 | MA2-ROT |  | ADEMULYADI |  | 2026-03-10 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 045
| K201 | 2026-03-11 | 2026-06-22 | 2026-12-09 | 2026-12-09 | 2102366246 | 8202241582 |  | RK0368 Refurbishment Steam Turbine Gen.P | RU2-UTL | 905-PT-58/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1000000 | 0 | MA3-ROT |  | ADEMULYADI |  | 2026-04-13 | PT02 | 3 | 3 | 2026-12-09 | PM |  | 003
| K201 | 2026-04-29 | 2026-05-26 | 2026-05-05 | 2026-05-05 |  | 8202242839 | 8202241318 | RK0145 Perbaikan Autotrafo 905-TRF-17B P | RU2-UTL | 905-TRF-17B/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 697512000 | 558009600 | MA2-INT |  | ADEMULYADI |  | 2026-05-04 | PT02 | 5 | 3 | 2026-05-05 | PM |  | 003
| K201 | 2026-03-09 | 2026-05-26 | 2026-12-11 | 2026-12-11 | 2102364146 | 8202241496 |  | RK0129 LTSA Cleaning Burner Heater Area | RU2-HCC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 453926000 | MA2-STA |  | DEDISUKMANA |  | 2026-03-10 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-03-10 | 2026-05-26 | 2026-02-25 | 2026-02-25 | 2102364971 | 8202241555 |  | RK0121 Perbaikan dan Penggantian Piping | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA3-STA |  | DEDISUKMANA |  | 2026-03-11 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 045
| K201 | 2026-03-10 | 2026-05-26 | 2026-10-12 | 2026-10-12 | 2102364144 | 8202241551 |  | RK0110 Pemeliharaan AC Area Dalam Kilang | RU2-HCC |  | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 300000000 | 168512746 | MA2-LIS |  | DEDISUKMANA |  | 2026-03-11 | PT02 | 3 | 3 | 2026-10-12 | PM |  | 045
| K201 | 2026-03-13 | 2026-05-26 | 2026-09-02 | 2026-09-02 |  | 8202241720 | 8202241701 | RK0105 TSA PEMELIHARAAN FIRE ALARM SYSTE | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 431733000 | MA1-STA |  | DEDISUKMANA |  | 2026-03-13 | PT02 | 3 | 3 | 2026-09-02 | PM |  | 045
| K201 | 2026-03-09 | 2026-05-26 | 2026-08-03 | 2026-08-03 | 2102364143 | 8202241441 |  | RK0097 Condition monitoring Rotating Ele | RU2-HCC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1700000000 | 1118108000 | MA2-ROT |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 045
| K201 | 2026-03-12 | 2026-05-26 | 2026-12-14 | 2026-12-14 |  | 8202241658 | 8202241614 | RK0054 LTSA PERBAIKAN RUTIN THERMAL INSU | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA3-STA |  | DEDISUKMANA |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-14 | PM |  | 045
| K201 | 2026-03-09 | 2026-05-26 | 2026-12-11 | 2026-12-11 | 2102364147 | 8202241492 |  | RK0041 LTSA Perbaikan Thermal Insulation | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 600000000 | 0 | MA2-STA |  | DEDISUKMANA |  | 2026-03-10 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-02-19 | 2026-05-25 | 2026-03-02 | 2026-12-30 | 2102363557 | 8202238960 |  | RK0037 LTSA Switchgear & MCC Brand Schne | RU2-UTL | 905-SWG-52D11/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 750000000 | 0 | MA3-LIS |  | DEDISUKMANA |  | 2026-02-25 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 045
| K201 | 2026-03-05 | 2026-05-26 | 2026-12-02 | 2026-12-02 | 2102352078 | 8202239923 |  | RK0035 2102350093#PSA Kontrak Transforma | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 800000000 | 0 | MA3-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-13 | 2026-05-26 | 2026-12-02 | 2026-12-02 |  | 8202241718 | 8202241701 | RK0034 TSA PEMELIHARAAN FIRE GAS DETECTO | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1700000000 | 354191000 | MA1-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-04-27 | 2026-05-26 | 2026-12-11 | 2026-12-11 |  | 8202242761 | 8202241554 | RK0031 LTSA Perawatan & Prwtn Line Fire | RU2-ITP |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 502129000 | MA2-STA |  | ADEMULYADI |  | 2026-04-27 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-03-09 | 2026-05-26 | 2026-03-31 | 2026-03-31 | 2102364148 | 8202241491 |  | RK0030 NDT Peralatan Kilang Area HCC | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 160970000 | 0 | MA2-STA |  | DEDISUKMANA |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 045
| K201 | 2026-03-10 | 2026-05-26 | 2026-08-03 | 2026-08-03 |  | 8202241552 | 8202241441 | RK0023 LTSA ONLINE ANALYZER DI REFINERY | RU2-HSC |  | 50 | REL GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 500000000 | 464675000 | MA2-ROT |  | DEDISUKMANA |  | 2026-03-11 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 045
| K401 | 2026-03-04 | 2026-06-08 | 2026-03-04 | 2026-03-04 | 2102365750 | 8202239418 |  | RK_26 UP Fire Proofing KPC dan LOC3 | RU4-KPC | 80S301/00 | 50 | CRTD NMAT PRC | 4MR |  | 1 | 0 | MA4-STA |  | AKHMADRIZAL |  |  | PT02 | 5 | 2 | 2026-03-04 | PM |  | 045
| K501 | 2026-05-31 | 2026-06-12 | 2026-05-29 | 2026-08-19 | 2102369395 | 8202243552 |  | Rintisan Rumput WTP (7) | RU5-UTL | W-18/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 1 | 0 | GM-SIP |  | BERNANDOP |  | 2026-06-12 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 045
| K601 | 2026-03-16 | 2026-03-30 | 2026-03-11 | 2026-09-16 | 2102366459 | 8202241748 |  | Rewinding trafo 11-V-101B-B3 | RU6-HSC | 11-V-101B-3/01 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DINDINS |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-28 | 2026-04-24 | 2026-09-21 | 2102368314 | 8202242735 |  | Rewinding Motor Soot Blower 52-B-101F2-K | RU6-UTL | 52-B-101F/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 349313 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-09-02 | 2102367460 | 8202242087 |  | Rewinding Motor 14-P-601A | RU6-DHC | 14-P-601A/00 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 368385 | 368385 | MA2-LIS |  | DINDINS |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-15 | 2026-03-03 | 2026-12-04 | 2102365300 | 8202242197 |  | Retrofit Auxiliary Trafo Stabilizer WIF | RU6-UTL | 53-LPB-WF/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 24157 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-15 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 004
| K601 | 2026-04-08 | 2026-04-15 | 2026-03-05 | 2027-04-05 | 2102366161 | 8202242194 |  | retrofit auxiliary trafo stabilizer SS13 | RU6-DHC | 12-LPB-SS13/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-04-15 | PT02 | 5 | 3 | 2026-03-05 | PM |  | 004
| K601 | 2026-04-08 | 2026-04-15 | 2026-03-05 | 2027-04-05 | 2102366160 | 8202242190 |  | retrofit auxiliary trafo stabilizer SS12 | RU6-DHC | 14-LPB-SS12/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-04-15 | PT02 | 4 | 3 | 2026-03-05 | PM |  | 004
| K601 | 2026-04-08 | 2026-04-15 | 2026-03-05 | 2027-04-05 | 2102365899 | 8202242186 |  | retrofit auxiliary trafo stabilizer SS11 | RU6-DHC | 22-LPB-SS11N/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-04-15 | PT02 | 4 | 3 | 2026-03-05 | PM |  | 004
| K201 | 2026-03-30 | 2026-06-15 | 2026-07-01 | 2026-07-01 | 2102367075 | 8202241952 |  | Resertifikasi Disnaker Peralatan Kilang | RU2-UTL | 940-B-1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/NR-D2H | 0 | 0 | MA2-STA |  | AHILMANSYAH |  | 2026-04-30 | PT02 | 5 | 3 | 2026-07-01 | PM |  | 003
| K201 | 2026-04-16 | 2026-04-19 | 2026-02-05 | 2026-02-05 | 2102360929 | 8202242496 |  | Reroute Pipa Treated Water 12 dan 8 inch | RU2-UTL | 6-PW-92512-MS1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 88962817 | 0 | MA3-STA |  | STEVANEKOPP |  | 2026-04-19 | PT02 | 3 | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-13 | 2026-03-04 | 2026-10-21 | 2102365713 | 8202241524 |  | Reposisi kabel area NPU periode 4 | RU6-HSC | 30-JBE-003/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-03-13 | PT02 | 5 | 3 | 2026-03-04 | PM |  | 003
| K701 | 2026-04-03 | 2026-04-04 | 2026-01-02 | 2026-01-02 | 2102367280 | 8202242052 |  | Repair Stop Unit CDU 1-E-31 | RU7-CDU | 1-E-31/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 4621328 | 0 | MA-STA |  | YAYANHER |  | 2026-04-03 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K701 | 2026-04-03 | 2026-04-04 | 2026-01-02 | 2026-01-02 | 2102367281 | 8202242053 |  | Repair Stop Unit CDU 1-C-03 | RU7-CDU | 1-C-03/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 2704534 | 0 | MA-STA |  | YAYANHER |  | 2026-04-03 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K701 | 2026-04-03 | 2026-04-04 | 2026-01-02 | 2026-01-02 | 2102367370 | 8202242055 |  | Repair Stop Unit CDU 1-C-02 | RU7-CDU | 1-C-02/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 4932802 | 0 | MA-STA |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 005
| K701 | 2026-04-03 | 2026-04-04 | 2026-04-02 | 2026-04-02 | 2102367282 | 8202242054 |  | Repair Stop Unit CDU 1-C-01 | RU7-CDU | 1-C-01/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/10/B6/RT1-CDUNH | 9125686 | 0 | MA-STA |  | YAYANHER |  | 2026-04-03 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 005
| K201 | 2026-05-21 | 2026-05-22 | 2026-06-01 | 2026-07-31 | 2102367805 | 8202243354 |  | Repair 580-P-302D | RU2-UTL | 580-P-302D/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-06-01 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-07 | 2026-02-02 | 2026-08-10 |  | 8202242080 | 8202233638 | Repair & Rewinding Motor 056-K-101A1 | RU6-UTL | 056-K-101-A1-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-05-20 | 2026-05-20 | 2026-04-10 | 2026-12-01 | 2102367757 | 8202243330 |  | Relokasi Panel heater Dryer 58-D-101A&B | RU6-UTL | 58-D-101A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 10957320 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-05-20 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K501 | 2026-05-25 | 2026-06-04 | 2026-07-21 | 2026-08-19 | 2102368555 | 8202243481 |  | Rekalibrasi Analyzer 05-AIT-355 | RU5-E15111 | 05-AIT-355/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 24802000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-06-04 | PT02 | 3 | 3 | 2026-07-21 | PM |  | 003
| K201 | 2026-06-11 | 2026-06-15 | 2026-06-10 | 2026-12-28 | 2102369852 | 8202243767 |  | Refurbishment Decoking Valve 140-PX-52 | RU2-HOC | 140-PX-52/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 1350000000 | 0 | MA1-ROT |  | MSADLI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K501 | 2026-04-21 | 2026-04-22 | 2026-07-01 | 2026-08-28 |  | 8202242625 |  | Refill Cylinder FM-200 SS-62 | RU5-TBL | FM-2/00 | 50 | CLSD NCMP NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | HSSE |  | RIANDAADI |  |  | PT02 | 5 | 2 | 2026-04-22 | PM |  | 004
| K202 | 2026-05-19 | 2026-06-22 | 2026-04-28 | 2026-04-28 | 2102368506 | 8202243286 |  | Rating MCCB tidak sesuai FLA motor | RU2S-KIL | 900-07P-1A-M/00 | 50 | REL CSER MSPT PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-LIS |  | JUNAIDIT |  | 2026-06-11 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K501 | 2026-05-04 | 2026-06-22 | 2026-09-29 | 2026-09-29 | 2102366915 | 8202242924 |  | PSA Transformator di RU V (T20) |  |  | 50 | REL NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 271666000 | 0 | MA1-LIS |  | AGUSHIDAYAT |  | 2026-05-12 | PT02 | 5 | 3 | 2026-09-29 | PM |  | 045
| K401 | 2026-03-12 |  | 2026-03-12 | 2026-03-12 | 2102366578 | 8202241651 |  | PSA Metering Sistem |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | MA3-INT |  |  |  |  | PT02 | 4 | 2 | 2026-03-12 | PM |  | 045
| K701 | 2026-02-10 | 2026-03-28 | 2026-03-02 | 2026-03-02 | 2102363940 | 8202238805 |  | Preventive Rutin Februari 2026 |  |  | 60 | CLSD CSER GMPS PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 1492600744 | 733392148 | MA-LINT |  | RYANMANGGASA |  | 2026-02-10 | PT02 | 3 | 3 | 2026-03-28 | PM |  | 005
| K201 | 2026-04-22 | 2026-05-26 | 2026-12-07 | 2026-12-07 |  | 8202242657 | 8202241318 | PREVENTIVE MAINTENANCE UPS & DC CHARGER | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA2-INT |  | ADEMULYADI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-12-07 | PM |  | 045
| K201 | 2026-04-27 | 2026-04-27 | 2026-12-02 | 2026-12-02 |  | 8202242762 | 8202240008 | PREVENTIVE MAINTENANCE MOTOR ALL AREA RU | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1000000000 | 258739655 | MA1-LIS |  | ADEMULYADI |  | 2026-04-27 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K701 | 2026-04-01 | 2026-04-02 | 2026-01-02 | 2026-01-02 | 2102367099 | 8202242007 |  | Preventive Maintenance 5-P-19 A/B |  |  | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-4-D4H | 43770848 | 43770848 | MA-STA |  | YAYANHER |  | 2026-04-01 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K701 | 2026-06-17 | 2026-06-18 | 2026-06-17 | 2026-06-17 | 2102370051 | 8202243901 |  | Preventive maintenance 4-P-01B | RU7-UTL | 4-P-01B/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-4-D4H | 154887468 | 0 | MA-ROT |  | YAYANHER |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 005
| K701 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2102369916 | 8202243861 |  | Preventive maintenance 1-PM-01 | RU7-CDU | 1-PM-01A/00 | 50 | CRTD CSER MACM PRC RELR | 7RT | D17/26/B6/RT-1-D1H | 760300000 | 0 | MA-LINT |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-06-15 | PM |  | 005
| K701 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2102369659 | 8202243671 |  | Preventive Maintenance | RU7-CDU | 1-P-04B/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 83642180 | 0 | MA-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-08 | PM |  | 005
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-10-23 | 2102369877 | 8202243879 |  | PrbikanBearing FDF 15-K-102B (Mat Pen TA | RU6-RCC | 15-K-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 25834939 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-10-23 | 2102369876 | 8202243878 |  | PrbikanBearing FDF 15-K-102A (Mat Pen TA | RU6-RCC | 15-K-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 25834939 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-02-23 | 2026-02-24 | 2026-02-20 | 2026-02-20 | 2102364632 | 8202239051 |  | Positioner Rusak 108PV642 | RU4-RFCGTO | 108A501V4/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-02-24 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-06 | 2026-04-27 | 2026-09-11 | 2102368422 | 8202243045 |  | Pompa tidak menghisap 34-A-104-P-101A | RU6-POC | 34-A-104-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3600000 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-06 | PT02 | 4 | 3 | 2026-04-27 | PM |  | 005
| K201 | 2026-03-31 | 2026-06-15 | 2026-03-17 | 2026-03-17 | 2102366820 | 8202241991 |  | Pompa Rusak | RU2-HCC | 212-P-9C/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 9552698 | 4339619 | MA2-ROT |  | NURFADHILLA |  | 2026-04-01 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 005
| K501 | 2026-02-17 | 2026-03-03 | 2026-03-09 | 2026-03-09 | 2102364013 | 8202238922 |  | Pompa P-16 WTP 1 Vibrasi | RU5-UTL | P-16-WTP/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 4 | 3 | 2026-02-17 | PM |  | 003
| K501 | 2026-03-03 | 2026-06-02 | 2026-08-04 | 2026-08-04 | 2102363954 | 8202239407 |  | POMPA G-5-12B MECHSEAL BOCOR | RU5-E15111 | G-5-12B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 7135681 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-08-04 | PM |  | 003
| K501 | 2026-03-03 | 2026-05-04 | 2026-03-04 | 2026-09-04 | 2102364245 | 8202239406 |  | POMPA G-34-111B MECH SEAL BOCOR | RU5-D&W | G-34-111B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 5816441 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 4 | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-03-05 | 2026-03-13 | 2026-06-08 | 2026-06-08 | 2102365283 | 8202240703 |  | POMPA G-202-07B SERING TRIP | RU5-D&W | G-202-07B/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-03-13 | 2026-06-02 | 2026-08-03 | 2026-08-03 | 2102365282 | 8202241724 |  | POMPA G-201-07A MS BOCOR | RU5-D&W | G-201-07A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 72708652 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-03-30 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 003
| K501 | 2026-02-18 | 2026-03-04 | 2026-05-18 | 2026-05-18 | 2102364482 | 8202238949 |  | POMPA G-1-14A DAN G-1-14B RUSAK | RU5-E15111 | G-1-14A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 1060914 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-25 | 2026-03-10 | 2026-06-26 | 2026-06-26 | 2102363573 | 8202239170 |  | pompa anti scale G-37-233 SWD 2 rusak |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 28000000 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 4 | 3 | 2026-06-26 | PM |  | 045
| K301 | 2026-05-18 | 2026-05-18 | 2026-01-01 | 2026-12-31 | 2102368622 | 8202243254 |  | Pompa 213 tidak Hisap | RU3-ITP | 41292-P-213/00 | 50 | REL CSER MSPT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 2 | 0 | MA4-ROT |  | RRAMADHANI |  | 2026-05-18 | PT02 | 4 | 3 | 2026-01-01 | PM |  | 045
| K601 | 2026-04-21 | 2026-04-21 | 2026-04-20 | 2026-05-05 | 2102368108 | 8202242629 |  | Pnggntian Valve Discharge 1st Stage (MIV | RU6-DHC | 22-K-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-06-05 | 2026-06-08 | 2026-06-05 | 2026-06-22 | 2102369655 | 8202243647 |  | Pnggntian Membrane Coupling 55-A-101B-P4 | RU6-UTL | 55-A-101B-P4/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 28153053 | 14075867 | MA4-ROT |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-05 | PM |  | 003
| K501 | 2026-06-02 | 2026-06-02 | 2026-04-07 | 2026-12-31 | 2102367524 | 8202243554 |  | Pnggntian Kaca Peep Hole Boiler HHP 4&5 | RU5-UTL | HHP-4/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 8 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-06-02 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-09 | 2026-04-07 | 2026-04-21 | 2102367492 | 8202242143 |  | Pnggntian Disc Coupling 056-P-101B (MIV) | RU6-UTL | 056-P-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 77201320 | 77200000 | MA4-ROT |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2027-03-30 | 2102364954 | 8202239184 |  | Pnggantian pping 18" Avtur area Jetty 70 | RU4-TRML | LN70-22A/00 | 50 | CRTD NMAT PRC | 4MR |  | 11200000000 | 0 | MA3-STA |  | FAJRIINDRAK |  |  | PT02 | 3 | 2 | 2026-02-26 | PM |  | 045
| K601 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-07-13 | 2102369430 | 8202243529 |  | Pnggantian Coupling MCO STG51-G-101E-P2A | RU6-UTL | 51-G-101E-P2A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 7262834 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-06-23 |  | 2026-06-22 | 2026-10-30 | 2102370210 | 8202244042 |  | PM trafo 11-PTR1-01 B | RU6-HSC | 11-PTR1-01B/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/26/B6/RT-C2H | 57074378 | 0 | MA1-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-06-22 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-09-01 |  | 8202242457 | 8202237751 | PM Tangki Tagihan Ke-5 | RU6-ITP | 42-T-101A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 200957000 | 200957000 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-04-10 | 2026-04-13 | 2026-01-05 | 2026-05-29 |  | 8202242337 | 8202232772 | PM PDM Elect Inst Area MA-2 DHC Thp 7 | RU6-DHC | 09-13-PSW2-01B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 52542000 | MA2-LIS |  | DANDARWANI |  | 2026-04-13 | PT02 | 3 | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-04-10 | 2026-04-13 | 2026-01-05 | 2026-05-29 |  | 8202242335 | 8202232772 | PM PDM Elect Inst Area MA-2 DHC Thp 6 | RU6-DHC | 09-13-PSW2-01B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 49127000 | MA2-LIS |  | DANDARWANI |  | 2026-04-13 | PT02 | 3 | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-09-03 |  | 8202243676 | 8202236813 | PM Mek MA 3 Thp 7 | RU6-HSC | 32-R-102/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 67105000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-06-08 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-09-03 |  | 8202243674 | 8202236813 | PM Mek MA 3 Thp 6 | RU6-HSC | 32-R-102/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 95022000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-06-08 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K201 | 2026-02-18 | 2026-03-25 | 2026-12-04 | 2026-12-04 |  | 8202238955 | 8202238141 | PM Cathocic Protection Sea water pipelin | RU2-ITP | BLP-PIPING/00 | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 2000000000 | 1636340000 | MA2-STA |  | ERLANGGA |  | 2026-02-19 | PT02 |  | 3 | 2026-12-04 | PM |  | 045
| K601 | 2026-05-04 | 2026-05-04 | 2026-03-11 | 2026-08-03 |  | 8202242937 | 8202242847 | PM 4 - LTSA Nitrogen Kjeldahl | RU6-LAB | LABORATORIUM/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 330400000 | 330400000 | MA3-STA |  | DANDARWANI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-05-08 | 2026-05-13 | 2026-02-06 | 2026-07-03 | 2102361863 | 8202243092 |  | PM 4 - LTSA Asphaltene Analyzer | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 159050800 | 0 | MA3-STA |  | DANDARWANI |  | 2026-05-08 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-05-08 | 2026-05-13 | 2026-02-06 | 2026-07-03 | 2102361861 | 8202243091 |  | PM 3 - LTSA Asphaltene Analyzer | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 458570000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-05-08 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-05-08 | 2026-05-13 | 2026-02-06 | 2026-07-03 | 2102361829 | 8202243090 |  | PM 1 - LTSA Asphaltene Analyzer | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 419269000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-05-08 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K701 | 2026-06-02 | 2026-06-02 | 2026-12-30 | 2026-12-30 | 2102364989 | 8202243581 |  | PM 02 Analyzer ke-10 |  |  | 50 | REL GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-2-D3H | 1659840000 | 1659840000 | MA-LINT |  | RIZKAANDIKAP |  | 2026-06-02 | PT02 | 4 | 3 | 2026-12-30 | PM |  | 005
| K601 | 2026-05-04 | 2026-05-11 | 2026-04-15 | 2026-09-01 | 2102368018 | 8202242944 |  | Piping Work Tahap 6 Area UTL (85%) | RU6-UTL | PIPAAIR/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 124332900 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-04 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-03-10 | 2026-06-08 | 2026-03-05 | 2026-03-05 | 2102366202 | 8202241515 |  | Permintaan Stock Material Rotating | RU6-RCC | 16-K-101/00 | 50 WAMA | REL CSER MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 1376172386 | 0 | MA2-ROT |  | ERWINSURYAG |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-05 | 2026-03-02 | 2026-04-21 | 2102365193 | 8202239397 |  | Permintaan Press Gauge Untk Press Survey | RU6-RCC | 15-C-101/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 10461050 | 4802025 | MA1-INT |  | MRBASUKI |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K201 | 2026-02-27 | 2026-03-06 | 2026-03-03 | 2026-07-28 | 2102365107 | 8202239274 |  | Permintaan Material Alat ICP-OES Lab | RU2-LAB | LAB-ANALIS-13/00 | 50 | REL MACM PRC SETC | 2IR | D12/26/B6/NR-D2H | 248098000 | 0 | WS-IN1 |  | STEVANEKOPP |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 005
| K601 | 2026-05-12 | 2026-05-20 | 2026-05-12 | 2026-07-01 | 2102367986 | 8202243147 |  | Permanent Repair Pump 53-P-301 | RU6-UTL | 53-P-301-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3961 | 0 | MA4-ROT |  | PANDUA |  | 2026-05-12 | PT02 | 6 | 3 | 2026-05-12 | PM |  | 004
| K601 | 2026-05-19 | 2026-05-20 | 2026-05-19 | 2026-06-05 | 2102369203 | 8202243307 |  | Pergantian Membran Kopling 51-G-101E-P1A | RU6-UTL | 51-G-101E-P1A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 16801320 | 16800000 | MA4-ROT |  | DANDARWANI |  | 2026-05-20 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-05-04 |  | 2026-10-29 | 2026-10-29 | 2102367435 | 8202242923 |  | PERGANTIAN KIPAS MOTOR GM-34-52 | RU5-E15111 | GM-34-52/00 | 01 | CRTD CSER NMAT PRC | 5ER | D15/10/B6/RT1-05NH | 0 | 0 | MA2-LIS |  |  |  |  | PT02 | 6 | 2 | 2026-10-29 | PM |  | 045
| K601 | 2026-03-06 | 2026-03-28 | 2026-03-06 | 2026-04-13 | 2102366270 | 8202241345 |  | Perbaikan Water Jacket EDG 51-G-102-P1A | RU6-UTL | 51-G-102-P1/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 16659744 | 958571 | MA4-ROT |  | HERDIANW |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-06-12 | 2026-06-22 | 2026-10-07 | 2026-10-28 | 2102366429 | 8202243811 |  | Perbaikan Vibration System G-3-01A | RU5-E15112 | G-3-01A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 212500015 | 0 | MA3-INT |  | MANKURNIAWAN |  | 2026-06-22 | PT02 | 3 | 3 | 2026-10-07 | PM |  | 004
| K601 | 2026-04-27 | 2026-05-21 | 2026-02-06 | 2026-07-03 | 2102361619 | 8202242770 |  | Perbaikan Vessel 42-V-317 | RU6-ITP | 42-V-601/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 200000001 | 0 | MA4-STA |  | ARYATHONI |  | 2026-04-27 | PT02 | 4 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-22 | 2026-06-17 | 2026-06-17 | 2102369984 | 8202243907 |  | Perbaikan valve comp 22K-1 | RU4-LOC1 | 22K1/00 | 50 | CRTD CSER MACM PRC | 4MR | D14/XX/B6/RT-C2NH | 997833809 | 0 | MA1-ROT |  | EDWINK |  |  | PT02 | 3 | 2 | 2026-06-17 | PM |  | 003
| K601 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-07-03 | 2102369261 | 8202243630 |  | Perbaikan V-belt Finfan 11-E-131A | RU6-HSC | 11-E-131A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 32400000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-04 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365184 | 8202241413 |  | Perbaikan V-belt EA-32-01J | RU5-E15112 | EA-32-01J/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-10 | 2026-05-18 | 2026-11-03 | 2026-12-30 | 2102365267 | 8202241501 |  | PERBAIKAN UPS WORKSTATION LDS BPP-LAWE2 | RU5-TBL | SP-MOORING-BUOY/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/26/B6/RT-C2H | 18468000 | 0 | MA4-INT |  | RIANDAADI |  | 2026-04-07 | PT02 | 5 | 3 | 2026-11-03 | PM |  | 004
| K201 | 2026-05-21 | 2026-05-22 | 2026-06-01 | 2026-07-31 | 2102367688 | 8202243355 |  | Perbaikan Unit Pompa 580-P-301B | RU2-UTL | 580-P-301B/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-06-01 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-05-29 | 2026-05-29 | 2102369461 | 8202243838 |  | Perbaikan Unit Polisher | RU6-DHC | 22-A-105/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 20500000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 6 | 3 | 2026-05-29 | PM |  | 003
| K501 | 2026-03-11 | 2026-05-04 | 2026-03-10 | 2026-12-31 | 2102366428 | 8202241560 |  | Perbaikan turbine GT-3-30A | RU5-E15112 | GT-3-30A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3422650 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K501 | 2026-03-16 | 2026-05-04 | 2026-03-09 | 2026-08-30 | 2102366290 | 8202241738 |  | Perbaikan Turbine GT-1-08B | RU5-E15111 | GT-1-08B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 15025105 | 0 | MA2-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-06 | 2026-05-05 | 2026-05-21 | 2102368695 | 8202243048 |  | Perbaikan Turbine 56-P-101D-T | RU6-UTL | 56-P-101D-T/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 18601145 | 18599825 | MA4-ROT |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365132 | 8202241475 |  | Perbaikan Turbin GT-8-01B | RU5-E15112 | GT-8-01B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 345212 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-02 | 2026-05-08 | 2026-02-23 | 2026-08-30 | 2102364757 | 8202239277 |  | Perbaikan Turbin GT-31-46B | RU5-E15112 | GT-31-46B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 122122997 | 0 | MA3-ROT |  | FAUZANR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-03-13 | 2026-05-04 | 2026-03-13 | 2026-08-30 | 2102366669 | 8202241697 |  | Perbaikan Turbin GT-31-39B | RU5-E15112 | GT-31-39B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 44577147 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K601 | 2026-02-13 | 2026-05-12 | 2026-02-13 | 2026-03-17 | 2102364043 | 8202238910 |  | Perbaikan Turbin 32-K-101-P1A-T | RU6-HSC | 32-K-101-P1-T/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 62768889 | 62579889 | MA3-ROT |  | PANDUA |  | 2026-02-13 | PT02 | 5 | 3 | 2026-02-13 | PM |  | 003
| K501 | 2026-03-31 | 2026-04-07 | 2026-05-11 | 2026-06-15 | 2102360069 | 8202241957 |  | Perbaikan Tubing XV-07 FG Boiler 5 | RU5-UTL | HHP-5-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 17993740 | 0 | MA1-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 2 | 3 | 2026-05-11 | PM |  | 003
| K601 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-03-12 | 2102364339 | 8202238909 |  | Perbaikan Tubing Analyzer 32-AT-010 | RU6-HSC | 32-F-107/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 3667554 | 2706284 | MA3-INT |  | DANDARWANI |  | 2026-02-13 | PT02 | 5 | 3 | 2026-02-13 | PM |  | 003
| K501 | 2026-02-19 | 2026-02-20 | 2026-02-18 | 2026-12-31 | 2102364572 | 8202238973 |  | Perbaikan Tube Saturated Steam HHP 3 | RU5-UTL | 3NV00-D001-SB-1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 17236925 | 0 | MA1-STA |  | MANKURNIAWAN |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K201 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-12-30 | 2102364114 | 8202241507 |  | Perbaikan Tube Sagging Pass 5 100-H-1 | RU2-HSC | 100-H-1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 900000000 | 0 | MA2-STA |  | CHANRARD |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K201 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2102365130 | 8202241588 |  | Perbaikan Tube | RU2-HCC | 211-E-19/00 | 50 | CRTD CSER MACM PRC | 2MR |  | 677698 | 0 | MA2-STA |  | STEVANEKOPP |  |  | PT02 | 3 | 2 | 2026-03-11 | PM |  | 003
| K501 | 2026-03-16 | 2026-05-04 | 2026-02-24 | 2026-08-30 | 2102364862 | 8202241740 |  | Perbaikan Trubine GT-5-12B | RU5-E15111 | GT-5-12B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K501 | 2026-02-18 | 2026-03-05 | 2026-02-13 | 2026-04-30 | 2102364458 | 8202238939 |  | Perbaikan Trubin GT-3-30C | RU5-E15112 | GT-3-30C/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3820334 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-05-26 | 2026-05-29 | 2026-09-09 | 2026-10-07 | 2102360706 | 8202243495 |  | Perbaikan Transmitter 234-LT-003 | RU5-D&W | 234-LT-003/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 12090397 | 0 | MA1-INT |  | BERNANDOP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-09-09 | PM |  | 004
| K401 | 2026-03-03 | 2026-03-17 | 2026-02-23 | 2026-02-23 | 2102364802 | 8202239373 |  | Perbaikan Transmitter 103LT034 | RU4-RFCC | 103LT-U103/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-17 | PM |  | 003
| K501 | 2026-02-11 | 2026-06-11 | 2026-02-11 | 2026-02-27 | 2102364113 | 8202238847 |  | PERBAIKAN TRANSMITTER 05-PSL-799 | RU5-E15111 | G-5-18B/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 9881699 | 0 | MA2-INT |  | BERNANDOP |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 004
| K501 | 2026-02-24 | 2026-03-04 | 2026-03-02 | 2026-03-05 | 2102364894 | 8202239107 |  | PERBAIKAN TRANSMITTER 01-PT-124A | RU5-E15111 | 01-PT-124A/00 | 60 | CLSD CSER PRC SETC | 5IR | D15/26/B6/RT-C2H | 9881699 | 0 | MA2-INT |  | RIANDAADI |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 004
| K501 | 2026-02-27 | 2026-03-04 | 2026-02-27 | 2026-03-27 | 2102364487 | 8202239266 |  | PERBAIKAN TRANSMITTER 01-LT-133 | RU5-E15111 | 01-LT-133/00 | 60 | CLSD CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 11786000 | 0 | MA2-INT |  | RIANDAADI |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 045
| K201 | 2026-04-22 | 2026-06-15 | 2026-04-22 | 2026-04-28 | 2102367449 | 8202242666 |  | Perbaikan Transmitter | RU2-HCC | 840-FT-3/00 | 50 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 9900000 | 9900000 | MA2-INT |  | NURFADHILLA |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 005
| K601 | 2026-05-07 | 2026-05-07 | 2026-05-06 | 2026-07-03 | 2102368770 | 8202243065 |  | Perbaikan trafo FO-PTR2-01/02 | RU6-UTL | FO-PTR2-01/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 28512791 | 28484000 | MA2-LIS |  | DANDARWANI |  | 2026-05-07 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-05-07 | 2026-05-07 | 2026-05-05 | 2026-07-02 | 2102368721 | 8202243064 |  | Perbaikan Trafo 12-PTR2-02B | RU6-DHC | 12-PTR2-02B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 28702791 | 28484000 | MA2-LIS |  | DANDARWANI |  | 2026-05-07 | PT02 | 6 | 3 | 2026-05-05 | PM |  | 003
| K601 | 2026-05-07 | 2026-05-07 | 2026-05-05 | 2026-07-02 | 2102368722 | 8202243063 |  | Perbaikan Trafo 11-PTR1-01A | RU6-HSC | 11-PTR1-01A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 57186791 | 56968000 | MA2-LIS |  | DANDARWANI |  | 2026-05-07 | PT02 | 6 | 3 | 2026-05-05 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-07-01 | 2102365766 | 8202241512 |  | Perbaikan torque tube gasket 15-LT-510 | RU6-RCC | 15-LT-510/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 6212925 | 0 | MA1-INT |  | DANDARWANI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K201 | 2026-04-30 | 2026-05-04 | 2026-04-30 | 2026-05-06 | 2102368381 | 8202242898 |  | Perbaikan Thermowell generator 905 TG 03 | UTL-UP2 | 905-TE-1128C/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 005
| K601 | 2026-04-09 | 2026-04-15 | 2026-04-09 | 2026-07-17 | 2102367415 | 8202242247 |  | Perbaikan Thermodial Out Cooler 15P107A | RU6-RCC | 15-P-107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K501 | 2026-02-19 | 2026-03-03 | 2026-02-19 | 2026-02-19 |  | 8202238974 | 8202238949 | Perbaikan temporary pompa G-1-14AB | RU5-E15111 | G-1-14A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-05-13 |  | 2026-05-12 | 2026-05-12 | 2102368948 | 8202243188 |  | Perbaikan temp transmitter 14TT548 |  |  | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-12 | PM |  | 045
| K201 | 2026-04-29 | 2026-05-19 | 2026-10-10 | 2026-10-12 | 2102366899 | 8202242812 |  | Perbaikan Stuffing Box 200-C-1B | RU2-HSC | 200-C-1B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 449956319 | 449956319 | MA2-ROT |  | ADEMULYADI |  | 2026-05-12 | PT02 | 5 | 3 | 2026-10-10 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-03-31 | 2026-04-29 | 2102367164 | 8202242193 |  | Perbaikan Steam Turbine 51-G-101E-P2A-T | RU6-UTL | 51-G-101E-P2A-T/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 8706130 | 735490 | MA4-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 004
| K601 | 2026-03-10 | 2026-03-26 | 2026-03-09 | 2026-07-30 | 2102366318 | 8202241527 |  | Perbaikan Steam Leak Area DHC-Tahap 1 | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 397443000 | 337826550 | MA2-STA |  | DANDARWANI |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-05-25 |  | 2026-05-18 | 2026-05-18 | 2102369153 | 8202243472 |  | Perbaikan SOV 154XV734A | RU4-RFCUTL | 154XV734A/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-18 | PM |  | 003
| K501 | 2026-03-30 | 2026-04-06 | 2026-03-30 | 2026-04-28 | 2102367024 | 8202241950 |  | PERBAIKAN SOLENOID 05-XCV-254A | RU5-E15111 | F-5-02/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 45780272 | 0 | MA2-INT |  | RUDIEKO |  | 2026-04-06 | PT02 | 4 | 3 | 2026-03-30 | PM |  | 004
| K501 | 2026-05-26 | 2026-05-26 | 2026-08-03 | 2026-09-30 |  | 8202243496 |  | PERBAIKAN SOLAR CHARGE CONTROLER LDS SPM | RU5-TBL | SP-MOORING-BUOY/00 | 50 | CLSD CSER NCMP NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  | RIANDAADI |  |  | PT02 | 3 | 2 | 2026-05-26 | PM |  | 004
| K401 | 2026-03-10 |  | 2026-03-04 | 2026-12-30 | 2102365770 | 8202241546 |  | Perbaikan sistem kontrol 93K401A/B-INS M | RU4-SRU | 93K401A/00 | 50 | CRTD NMAT PRC | 4IR |  | 1975000000 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-06 | 2026-04-20 | 2026-02-09 | 2026-02-09 | 2102363873 | 8202238731 |  | Perbaikan Sensor Temperatur RTD RFCC | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-04-20 | PM |  | 045
| K501 | 2026-05-22 | 2026-05-29 | 2026-08-13 | 2026-08-31 | 2102364467 | 8202243415 |  | Perbaikan Sensor Temp. 08B-TE-017/008 | RU5-E15112 | F-8-01B-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 18794000 | 0 | MA3-INT |  | BERNANDOP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-08-13 | PM |  | 004
| K501 | 2026-03-10 | 2026-04-07 | 2026-08-03 | 2026-09-30 | 2102365794 | 8202241500 |  | PERBAIKAN SENSOR ROD DROP K-19-01A | RU5-E15112 | K-19-01A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 38940005 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 004
| K601 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-06-08 | 2102369205 | 8202243336 |  | Perbaikan Seal LO Pompa 20-P-106A | RU6-RCC | 20-P-106A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 12560000 | 12560000 | MA1-ROT |  | DANDARWANI |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K201 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-12-30 | 2102367952 | 8202242409 |  | Perbaikan sarfas WPS Sei Rokan | RU2-UTL | 510-PIPING/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1330000000 | 988000000 | MA3-STA |  | CHANRARD |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K601 | 2026-03-02 | 2026-04-08 | 2026-03-02 | 2026-12-30 | 2102365139 | 8202239284 |  | Perbaikan Sarfas Feeder 20kV PLN BP-BLG | RU6-UTL | MSS-31/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-02-26 | 2026-04-07 | 2026-06-02 | 2026-08-28 | 2102364070 | 8202239173 |  | Perbaikan Safety Barrier VMS K-3-02A | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 30 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 004
| K501 | 2026-02-23 | 2026-03-06 | 2026-05-13 | 2026-08-13 | 2102363889 | 8202239024 |  | Perbaikan Safety Barrier VMS G-3-01A | RU5-E15112 | G-3-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 63000010 | 0 | MA3-INT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 004
| K701 | 2026-03-04 | 2026-03-11 | 2026-01-02 | 2026-01-02 |  | 8202239457 | 8202239341 | Perbaikan Rutin Maret 2026 | RU7-CRU | 3-K-01A/00 | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-3-D3H | 70967288 | 61934181 | MA-ROT |  | RYANMANGGASA |  | 2026-03-04 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K501 | 2026-04-02 | 2026-04-07 | 2026-08-03 | 2026-08-11 | 2102363990 | 8202242044 |  | PERBAIKAN ROTAMETER 05-AIT-133 | RU5-E15111 | E-5-12/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 3 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-07 | 2026-03-26 | 2026-08-13 | 2102366906 | 8202242083 |  | Perbaikan RGA tangki 42-T-101C | RU6-ITP | 42-T-101C/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 12144 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-07 | PT02 | 4 | 3 | 2026-03-26 | PM |  | 003
| K601 | 2026-03-09 | 2026-05-20 | 2026-03-09 | 2026-07-30 | 2102366229 | 8202241440 |  | Perbaikan Refractory Boiler 52-B-101B | RU6-UTL | 52-B-101B/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 139850000 | 118872500 | MA4-STA |  | HARSARIZANO |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K201 | 2026-05-12 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 2102368878 | 8202243164 |  | Perbaikan PTO Dominator Pump | RU2-PK | 970-P-2B/00 | 50 | REL GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 244319904 | 244319904 | WS-KAB |  | ERLANGGA |  | 2026-05-20 | PT02 | 8 | 3 | 2026-05-21 | PM |  | 003
| K201 | 2026-04-10 | 2026-05-19 | 2026-04-10 | 2026-04-16 | 2102365057 | 8202242314 |  | Perbaikan PSL-12 Pressure Switch 920 P2B | RU2-UTL | 920-PS-12/00 | 60 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 7334800 | 7334800 | MA3-INT |  | ADEMULYADI |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 004
| K401 | 2026-05-04 | 2026-05-06 | 2026-04-30 | 2026-12-14 | 2102368612 | 8202242954 |  | Perbaikan prob axial 14XE-006A/B | RU4-FOC1 | 14K1/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-05-04 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-04-09 | 2026-04-23 | 2026-07-14 | 2026-07-21 | 2102363985 | 8202242236 |  | Perbaikan Pressure Transmitter C-20-01A | RU5-TBL | C-20-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 15808492 | 0 | MA4-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 5 | 3 | 2026-07-14 | PM |  | 004
| K701 | 2026-04-29 | 2026-04-29 | 2026-12-01 | 2026-12-01 | 2102368408 | 8202242810 |  | Perbaikan Press Transmitter CDU CRU NHT | RU7-NHT | 2-PT-107/00 | 50 | REL MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 300000000 | 0 | MA-ROT |  | YAYANHER |  | 2026-04-29 | PT02 | 3 | 3 | 2026-12-01 | PM |  | 005
| K201 | 2026-05-04 | 2026-05-19 | 2026-06-02 | 2026-06-02 | 2102367646 | 8202242956 |  | Perbaikan Power Supply Motor Pompa | RU2-UTL | 940-PM-C-1C/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 973200 | 973200 | MA3-LIS |  | ADEMULYADI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-02-23 | 2026-02-24 | 2026-02-12 | 2026-02-12 | 2102364274 | 8202239074 |  | Perbaikan Power Supply 054 FV 501 | RU4-UTL | 054WS105/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-02-24 | PM |  | 003
| K601 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-04-07 | 2102366945 | 8202241886 |  | Perbaikan positioner control valve | RU6-DHC | 22-V-109B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 141000000 | 141000000 | MA2-INT |  | DANDARWANI |  | 2026-03-26 | PT02 | 5 | 3 | 2026-03-26 | PM |  | 003
| K501 | 2026-06-02 | 2026-06-08 | 2026-10-21 | 2026-11-04 | 2102363942 | 8202243553 |  | Perbaikan Positioner 37-LCV-210 | RU5-UTL | 37A-LCV-210-5/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | MA1-INT |  | MANKURNIAWAN |  | 2026-06-08 | PT02 | 3 | 3 | 2026-10-21 | PM |  | 004
| K401 | 2026-05-25 | 2026-05-26 | 2026-05-18 | 2026-05-18 | 2102369152 | 8202243471 |  | Perbaikan positioner 152PV062B | RU4-RFCUTL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-26 | PM |  | 045
| K601 | 2026-03-12 | 2026-05-21 | 2026-03-11 | 2026-06-05 | 2102366434 | 8202241600 |  | Perbaikan Positioner 15-FV-008 | RU6-RCC | 15-FV-008/00 | 60 | CLSD CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 79592004 | 79592004 | MA1-INT |  | SAPBATCH |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-03 | 2026-02-18 | 2026-04-09 | 2102364448 | 8202239356 |  | Perbaikan Pompa Spare Ex 53-P-102A | RU6-UTL | 53-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 6403984 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-18 | PM |  | 003
| K301 | 2026-03-31 | 2026-04-29 | 2026-03-30 | 2026-03-30 | 2102367072 | 8202241974 |  | Perbaikan Pompa P-2209 | RU3-PP | 23-P-2209A/00 | 50 WAMA | CRTD CSER MACM PRC | 3RR |  | 2058838326 | 0 | MA2-ROT |  | ALEPDALITAN |  |  | PT02 | 3 | 2 | 2026-03-30 | PM |  | 004
| K501 | 2026-03-16 | 2026-06-02 | 2026-02-06 | 2026-08-30 | 2102363572 | 8202241737 |  | Perbaikan pompa G-37-204 | RU5-UTL | G-37-204/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 11321879 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-03-03 | 2026-05-04 | 2026-06-02 | 2026-06-02 | 2102365225 | 8202239378 |  | Perbaikan Pompa G-34-58 | RU5-D&W | G-34-58A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-03-11 | 2026-03-13 | 2026-03-10 | 2026-12-31 | 2102366395 | 8202241561 |  | Perbaikan Pompa G-31-39A | RU5-E15112 | G-31-39A/00 | 50 | CLSD CSER NCMP PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | ANDREAYR |  |  | PT02 | 3 | 2 | 2026-03-13 | PM |  | 003
| K501 | 2026-02-19 | 2026-05-04 | 2026-02-02 | 2026-04-30 | 2102359917 | 8202238977 |  | Perbaikan Pompa G-3-15B | RU5-E15112 | G-3-15B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 409112 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-03-05 | 2026-06-02 | 2026-02-26 | 2026-08-30 | 2102365006 | 8202239471 |  | Perbaikan Pompa G-3-02B | RU5-E15112 | G-3-02B/01 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1570642 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K501 | 2026-02-09 | 2026-06-02 | 2026-05-07 | 2026-05-07 | 2102359889 | 8202238797 |  | Perbaikan Pompa G-3-02A | RU5-E15112 | G-3-02A/01 | 60 | TECO CNF CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 609099385 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-02 | 2026-04-20 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-09 | 2026-05-04 | 2026-02-09 | 2026-04-30 | 2102363845 | 8202238782 |  | Perbaikan Pompa G-3-01B | RU5-E15112 | G-3-01B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 155874287 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K501 | 2026-03-17 | 2026-05-04 | 2026-02-19 | 2026-12-31 | 2102364607 | 8202241795 |  | Perbaikan Pompa G-220-03B | RU5-TBL | G-220-03B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K501 | 2026-02-13 | 2026-06-18 | 2026-12-09 | 2026-12-09 | 2102363994 | 8202238919 |  | Perbaikan pompa G-220-01 D | RU5-TBL | G-220-01D/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 2309870 | 0 | MA4-ROT |  | FAUZANR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-12-09 | PM |  | 003
| K501 | 2026-03-30 | 2026-05-12 | 2026-02-19 | 2026-08-30 | 2102364609 | 8202241915 |  | Perbaikan Pompa G-20-06A | RU5-TBL | G-20-06A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 460209943 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K501 | 2026-03-17 | 2026-05-04 | 2026-02-19 | 2026-12-31 | 2102364608 | 8202241796 |  | Perbaikan Pompa G-20-02A | RU5-TBL | G-20-02A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1802388 | 0 | MA4-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K501 | 2026-02-09 | 2026-05-04 | 2026-02-02 | 2026-04-30 | 2102359015 | 8202238786 |  | Perbaikan Pompa G-2-05A | RU5-E15112 | G-2-05A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 2309866 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-03-03 | 2026-03-06 | 2026-02-19 | 2026-08-30 | 2102364574 | 8202239380 |  | Perbaikan Pompa G-2-03B | RU5-E15112 | G-2-03B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 56962766 | 0 | MA3-ROT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K501 | 2026-02-26 | 2026-03-05 | 2026-02-12 | 2026-08-30 | 2102364241 | 8202239186 |  | Perbaikan Pompa FOP 2 | RU5-UTL | OPE00D002/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K501 | 2026-03-27 | 2026-04-17 | 2026-03-25 | 2026-08-30 | 2102366922 | 8202241904 |  | Perbaikan Pompa BFW2 | RU5-UTL | 1RL-10-D001/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 67890000 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-03-31 | PT02 | 1 | 3 | 2026-03-25 | PM |  | 003
| K601 | 2026-04-14 | 2026-05-12 | 2026-04-08 | 2026-05-07 | 2102367650 | 8202242401 |  | Perbaikan Pompa 64-P-103B | RU6-HSC | 64-P-103B/00 | 50 | REL CSER MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 1438771 | 0 | MA1-ROT |  | PANDUA |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-06-03 | 2102368996 | 8202243177 |  | Perbaikan Pompa 63-P-303B | RU6-ITP | 63-P-303B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 151501320 | 151500000 | MA4-ROT |  | DANDARWANI |  | 2026-05-13 | PT02 | 4 | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-07 | 2026-03-26 | 2026-08-13 | 2102366926 | 8202242086 |  | Perbaikan pompa 63-P-303B | RU6-ITP | 63-P-303B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 8747756 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-07 | PT02 | 5 | 3 | 2026-03-26 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-05-06 | 2102368200 | 8202242627 |  | Perbaikan Pompa 53-P-305A | RU6-UTL | 53-P-305A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3594575 | 3593255 | MA4-ROT |  | DANDARWANI |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-02-26 | 2026-03-04 | 2026-02-26 | 2026-03-12 | 2102365022 | 8202239178 |  | Perbaikan Pompa 52-P-103A | RU6-UTL | 52-P-103A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 63139835 | 63138515 | MA4-ROT |  | DANDARWANI |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K701 | 2026-04-13 | 2026-04-16 | 2026-04-13 | 2026-04-13 | 2102367840 | 8202242345 |  | Perbaikan Pompa 5-PM-20A | RU7-OFF | 5-PM-20A/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-4-D4H | 46551030 | 0 | MA-LINT |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-04-13 | PM |  | 005
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-07-01 | 2102368307 | 8202243139 |  | Perbaikan Pompa 42-P-965A | RU6-ITP | 42-P-965A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 17003960 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-02-25 | 2026-03-05 | 2026-02-24 | 2026-07-17 | 2102364859 | 8202239147 |  | Perbaikan pompa 42-P-207B | RU6-ITP | 42-P-207B/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 901556130 | 1225544250 | MA4-ROT |  | DANDARWANI |  | 2026-02-25 | PT02 | 5 | 3 | 2026-02-24 | PM |  | 003
| K601 | 2026-02-25 | 2026-02-25 | 2026-02-24 | 2026-11-24 | 2102364857 | 8202239148 |  | Perbaikan pompa 42-P-207A | RU6-ITP | 42-P-207A/00 | 50 | REL CSER MANC PRC SETC | 6RR | D16/26/B6/RT-C2 | 901568010 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-02-25 | PT02 | 4 | 3 | 2026-02-24 | PM |  | 003
| K601 | 2026-06-15 | 2026-06-18 | 2026-06-15 | 2026-06-30 | 2102368715 | 8202243866 |  | Perbaikan Pompa 42-P-206B | RU6-ITP | 42-P-206B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 77742289 | 70559666 | MA4-ROT |  | DANDARWANI |  | 2026-06-15 | PT02 | 5 | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-29 | 2102367858 | 8202242462 |  | Perbaikan Pompa 42-P-104B | RU6-ITP | 42-P-104B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 140901520 | 140900200 | MA4-ROT |  | DANDARWANI |  | 2026-04-15 | PT02 | 1 | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-04-13 | 2026-04-13 | 2026-04-09 | 2026-05-26 | 2102367639 | 8202242354 |  | Perbaikan Pompa 32-P-107A | RU6-HSC | 32-P-107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-04-13 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 003
| K601 | 2026-03-06 | 2026-03-10 | 2026-03-05 | 2026-03-26 | 2102366138 | 8202241301 |  | Perbaikan Pompa 32-A-101-P1A | RU6-HSC | 32-A-101-P1A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 31279677 | 31279677 | MA3-ROT |  | DANDARWANI |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-06-01 | 2026-06-03 | 2102364621 | 8202243358 |  | Perbaikan Pompa 301-P-7B | RU2-HSC | 301-P-7B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 3754871 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 5 | 3 | 2026-06-01 | PM |  | 003
| K701 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  | 8202241499 | 8202239341 | PERBAIKAN POMPA 3-P-01A/00 | RU7-CRU | 3-P-01A/00 | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-3-D3H | 179092526 | 167849757 | MA-ROT |  | YAYANHER |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 045
| K601 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-07-31 | 2102369990 | 8202243983 |  | Perbaikan Pompa 24-P-304A | RU6-HSC | 24-P-304A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 512000000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 004
| K601 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-07-28 | 2102369949 | 8202243868 |  | Perbaikan Pompa 24-P-303A | RU6-HSC | 24-P-303A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 540000000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-15 | PT02 | 5 | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-30 | 2102369948 | 8202243867 |  | Perbaikan Pompa 24-P-302B | RU6-HSC | 24-P-302B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 669000000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-15 | PT02 | 5 | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-09 | 2026-06-03 | 2026-06-18 | 2102369398 | 8202243597 |  | Perbaikan Pompa 24-P-102B | RU6-HSC | 24-P-102B/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C1H | 110583458 | 107038844 | MA1-ROT |  | DANDARWANI |  | 2026-06-03 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-22 | 2026-06-08 | 2026-06-23 | 2102369718 | 8202243683 |  | Perbaikan Pompa 23-P-201A | RU6-HSC | 23-P-201A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 4604394 | 4604394 | MA1-ROT |  | ERWINSURYAG |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-09 | 2026-06-03 | 2026-06-18 | 2102369413 | 8202243609 |  | Perbaikan Pompa 23-P-102B | RU6-HSC | 23-P-102B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 56165730 | 56165730 | MA1-ROT |  | DANDARWANI |  | 2026-06-03 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-07-14 | 2102369902 | 8202243869 |  | Perbaikan Pompa 23-P-101B | RU6-HSC | 23-P-101B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 5888844 | 5888844 | MA1-ROT |  | DANDARWANI |  | 2026-06-15 | PT02 | 5 | 3 | 2026-06-15 | PM |  | 003
| K201 | 2026-04-01 | 2026-05-04 | 2026-03-25 | 2026-03-25 | 2102366902 | 8202242006 |  | Perbaikan Pompa 220-P-3A | RU2-HOC | 220-P-3A/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RR | D12/26/B6/RT-D2H | 330180023 | 3820022 | MA1-ROT |  | MDSYAHPUTRA |  | 2026-04-01 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K201 | 2026-03-17 | 2026-05-19 | 2026-03-17 | 2026-03-17 | 2102366770 | 8202241818 |  | Perbaikan Pompa 220 P-3A | RU2-HOC | 220-P-3A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6920333 | 6920333 | MA1-ROT |  | ADEMULYADI |  | 2026-04-10 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-04-23 | 2026-05-08 | 2102368277 | 8202243110 |  | Perbaikan Pompa 19-P-111B | RU6-RCC | 19-P-111B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 12560000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102364410 | 8202242205 |  | Perbaikan Pompa 16-P-111A | RU6-RCC | 16-P-111A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 23932662 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-04-08 | 2102365261 | 8202239354 |  | Perbaikan Pompa 16-P-101A | RU6-RCC | 16-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 34500000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-04-09 | 2102365780 | 8202239438 |  | Perbaikan Pompa 16-P-101A | RU6-RCC | 16-P-101A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 34500000 | 34500000 | MA1-ROT |  | DANDARWANI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-07-01 | 2102369694 | 8202243881 |  | Perbaikan Pompa 15-P-113A | RU6-RCC | 15-P-113A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 5491723 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-06-15 | 2026-06-18 | 2026-06-15 | 2026-06-30 | 2102370021 | 8202243865 |  | Perbaikan Pompa 15-P-111D | RU6-RCC | 15-P-111D/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 245151997 | 245151997 | MA1-ROT |  | DANDARWANI |  | 2026-06-15 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-06-15 | 2026-06-17 | 2026-06-12 | 2026-07-13 | 2102369941 | 8202243870 |  | Perbaikan Pompa 15-P-102A Body G | RU6-RCC | 15-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2363898 | 0 | MA1-ROT |  | ABDULAZIZ70 |  | 2026-06-15 | PT02 | 3 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-02-24 | 2026-04-16 | 2026-02-24 | 2026-03-31 |  | 8202239095 | 8202238877 | Perbaikan Pompa 15-P-102 Body F&D (MIV) | RU6-RCC | 15-P-102A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 424924000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K601 | 2026-04-14 | 2026-05-06 | 2026-04-14 | 2026-05-13 | 2102367859 | 8202242404 |  | Perbaikan Pompa 15-P-102 Body C | RU6-RCC | 15-P-102A/00 | 50 | REL CSER GMCO GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 215887491 | 225342184 | MA1-ROT |  | DANDARWANI |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K601 | 2026-04-14 | 2026-05-06 | 2026-04-14 | 2026-05-13 | 2102367940 | 8202242405 |  | Perbaikan Pompa 15-P-101 Body B | RU6-RCC | 15-P-101A/00 | 50 WAMA | REL CSER GMCO GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 243303996 | 243303996 | MA1-ROT |  | DANDARWANI |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K601 | 2026-06-04 | 2026-06-08 | 2026-06-02 | 2026-06-17 | 2102369469 | 8202243628 |  | Perbaikan Pompa 14-P-107B | RU6-DHC | 14-P-107B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 188892944 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-05-19 | 2026-06-02 | 2026-05-19 | 2026-06-05 | 2102369052 | 8202243293 |  | Perbaikan Pompa 12-P-505B | RU6-DHC | 12-P-505B/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 40518800 | 40518800 | MA2-ROT |  | ABDULAZIZ70 |  | 2026-05-19 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-18 | 2026-06-11 | 2026-06-26 | 2102369804 | 8202243794 |  | Perbaikan Pompa 12-P-504B | RU6-DHC | 12-P-504B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 225368604 | 0 | MA2-ROT |  | ABDULAZIZ70 |  | 2026-06-11 | PT02 | 5 | 3 | 2026-06-11 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-18 | 2102369353 | 8202243587 |  | Perbaikan Pompa 12-P-501A (MIV) | RU6-DHC | 12-P-501A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 1219234 | 1219234 | MA2-ROT |  | DANDARWANI |  | 2026-06-03 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-04-28 | 2026-05-29 | 2026-04-24 | 2026-05-11 | 2102368248 | 8202242794 |  | Perbaikan Pompa 12-P-501A | RU6-DHC | 12-P-501A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 18828763 | 18828763 | MA2-ROT |  | SAPBATCH | 2026-05-29 | 2026-04-28 | PT02 | 5 | 3 | 2026-05-29 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-07-01 | 2102364011 | 8202243152 |  | Perbaikan Pompa 12-A-501-P1B | RU6-DHC | 12-A-501-P1B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 1311000 | 874000 | MA2-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-18 | 2102369352 | 8202243586 |  | Perbaikan Pompa 12-A-501-P1A (MIV) | RU6-DHC | 12-A-501-P1A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3278000 | 3278000 | MA2-ROT |  | DANDARWANI |  | 2026-06-03 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-04-14 | 2026-04-14 | 2026-04-09 | 2026-05-08 | 2102367686 | 8202242403 |  | Perbaikan Pompa 11-P-103B | RU6-HSC | 11-P-103B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 35160446 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 003
| K701 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2102367759 | 8202242346 |  | Perbaikan Pompa 1-P-07B |  |  | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 92251118 | 0 | MA-ROT |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-04-13 | PM |  | 005
| K701 | 2026-03-04 | 2026-04-07 | 2026-01-02 | 2026-01-02 |  | 8202239462 | 8202239341 | PERBAIKAN POMPA 1 - P 07 B | RU7-CDU | 1-P-07A/00 | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 88931577 | 88652855 | MA-ROT |  | YAYANHER |  | 2026-03-04 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K501 | 2026-02-09 | 2026-02-26 | 2026-02-02 | 2026-04-30 | 2102359916 | 8202238788 |  | Perbaikan Pompa G-3-05A | RU5-E15112 | G-3-05A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 7782520 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-04 | 2026-02-09 | 2026-04-01 | 2102363839 | 8202239459 |  | Perbaikan Pit Pump 30-P-901B | RU6-HSC | 30-P-901B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 5389169 | 5389169 | MA3-ROT |  | DANDARWANI |  | 2026-03-04 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-19 | 2026-04-02 | 2026-04-02 | 2102367301 | 8202243970 |  | Perbaikan pipa supply raw water KM 12 | RU2-UTL | 510-PIPING/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 15951250 | 15951250 | MA3-STA |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-04-20 | 2026-04-27 | 2026-04-20 | 2026-12-30 | 2102364699 | 8202242595 |  | Perbaikan Pipa RWI Sei Rokan KM 8-10 | RU2-UTL |  | 01 | CRTD NMAT PRC | 2MR | D12/25/B6/RT-D2H | 5192500000 | 0 | MA3-STA |  | ADEMULYADI |  |  | PT02 | 3 | 2 | 2026-04-20 | PM |  | 045
| K601 | 2026-05-04 | 2026-05-21 | 2026-04-15 | 2026-09-01 | 2102368019 | 8202242945 |  | Perbaikan pipa 53-RW-0103-MS01-8" | RU6-UTL | 53-RW-0401-MS22/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 68794800 | 0 | MA4-STA |  | ARYATHONI |  | 2026-05-04 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-04-02 | 2026-04-07 | 2026-05-29 | 2026-06-30 | 2102360766 | 8202242030 |  | Perbaikan PI Loader K-302 | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 55487500 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 004
| K501 | 2026-04-09 | 2026-04-23 | 2026-07-14 | 2026-07-21 | 2102364000 | 8202242237 |  | Perbaikan PI Jetty 5 (Line 910 Naphtha) | RU5-TBL | DER-JT-05/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 3045000 | 0 | MA4-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-07-14 | PM |  | 004
| K401 | 2026-03-03 | 2026-03-04 | 2026-02-20 | 2026-02-20 | 2102364633 | 8202239388 |  | Perbaikan PG range 0-40 & 0-60 kg/cm2 | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 045
| K401 | 2026-06-15 |  | 2026-06-09 | 2026-06-09 | 2102369789 | 8202243854 |  | Perbaikan PG Kompressor 108 | RU4-RFCGTO | 108K501A/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-26 | 2026-03-06 | 2026-08-03 | 2026-09-02 | 2102359476 | 8202239180 |  | Perbaikan Peralatn Oil Spill Monitoring | RU5-TBL | 34-LT-170/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 6 | 0 | MA4-INT |  | RIANDAADI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 004
| K601 | 2026-02-12 | 2026-04-14 | 2026-02-11 | 2026-04-06 | 2102364131 | 8202238904 |  | Perbaikan penggantian element FWS | RU6-DHC | 21-S-104/00 | 60 | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 93512574 | 93512574 | MA2-STA |  | DANDARWANI |  | 2026-02-12 | PT02 | 4 | 3 | 2026-02-11 | PM |  | 003
| K701 | 2026-05-09 | 2026-05-21 | 2026-12-30 | 2026-12-30 |  | 8202243102 | 8202237964 | Perbaikan Panel Community |  |  | 50 | REL GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 699385000 | 594477250 | MA-STA |  | YAYANHER |  | 2026-05-09 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 005
| K301 | 2026-05-19 | 2026-05-21 | 2026-05-19 | 2026-05-19 | 2102367977 | 8202243290 |  | Perbaikan P-8 CDU VI Pasca Flash 2022 | RU3-CDL | CDU-6-P-8A/00 | 50 WAMA | REL MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 2 | 0 | MA3-ROT |  | ALEPDALITAN |  | 2026-05-19 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-12-29 | 2102361464 | 8202243329 |  | Perbaikan Overhead Crane 12-A-602 | RU6-DHC | 12-A-602/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 150 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-04-28 | 2026-06-17 | 2026-03-30 | 2026-12-30 | 2102367029 | 8202242809 |  | Perbaikan OrbisBV Stardist ASTM D850 | RU4-FOC1 | 10AOC1/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 100000 | 0 | WS-INT |  | WAHYUCATUR |  | 2026-04-29 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K401 | 2026-02-23 | 2026-06-22 | 2026-02-02 | 2026-12-30 | 2102355423 | 8202239070 |  | Perbaikan OHC Gudang Cataly | RU4-RFCGTO | 106P501AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 100000 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-11-04 | 2102368540 | 8202242960 |  | Perbaikan O-RING 16-XV-501/502 | RU6-RCC | 16-XV-501/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-19 | 2026-02-02 | 2026-02-02 | 2102355354 | 8202238703 |  | Perbaikan Natural Draft 105 | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-02-19 | PM |  | 045
| K201 | 2026-04-24 | 2026-04-24 | 2026-12-04 | 2026-12-04 |  | 8202242718 | 8202238141 | Perbaikan MOV Tank Farm Oil Movement PT | RU2-ITP | 945-T-35/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 201000000 | 0 | MA2-STA |  | STEVANEKOPP |  | 2026-04-24 | PT02 |  | 3 | 2026-12-04 | PM |  | 003
| K601 | 2026-06-05 | 2026-06-09 | 2026-06-02 | 2026-07-17 | 2102369439 | 8202243658 |  | Perbaikan motor Sootblower 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 584676 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-09 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-05-04 | 2102364039 | 8202238803 |  | Perbaikan motor SB No.6 052-B-101B-K6 | RU6-UTL | 052-B-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 496628 | 489896 | MA4-LIS |  | DANDARWANI |  | 2026-02-10 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K201 | 2026-04-07 | 2026-05-26 | 2026-03-12 | 2026-03-12 | 2102366595 | 8202242136 |  | Perbaikan Motor Pompa Ex RBDPO | RU2-HOC | 2-P-22045-A1A1/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/NR-D2H | 88000 | 88000 | MA1-STA |  | ADEMULYADI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-06-23 |  | 2026-06-19 | 2026-10-29 | 2102370160 | 8202244044 |  | Perbaikan motor pompa 42-P-403D | RU6-ITP | 42-P-403D-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/26/B6/RT-C2H | 2512144 | 0 | MA4-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-06-19 | PM |  | 003
| K601 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102369277 | 8202243480 |  | Perbaikan motor pompa 055-A-101-P1B | RU6-UTL | 055-A-101-P1B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 674457 | 356570 | MA4-LIS |  | DANDARWANI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K201 | 2026-03-06 | 2026-03-06 | 2026-02-27 | 2026-02-27 | 2102365075 | 8202241350 |  | Perbaikan motor P 202 A | RU2-ITP | 610-P-203A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/09/B6/RT1-JSRNH | 1448000 | 0 | MA4-LIS |  | STEVANEKOPP |  | 2026-03-06 | PT02 | 5 | 3 | 2026-02-27 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-04-28 | 2026-06-23 | 2102368434 | 8202243181 |  | Perbaikan Motor Noise 16E117C | RU6-RCC | 16-E-117C-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-13 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-03-05 | 2026-03-05 | 2026-02-06 | 2026-02-06 | 2102361593 | 8202239466 |  | Perbaikan Motor Mixer 15M101 | RU6-RCC | 15-M-101-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 167374 | 172932 | MA1-LIS |  | DANDARWANI |  | 2026-03-05 | PT02 | 2 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-08-31 | 2102364925 | 8202241353 |  | Perbaikan Motor MCC Finfan 101E531 | RU4-RFCC | 101E531/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 112064233 | 112064233 | MA6-LIS |  | YMOHAMMAD |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K201 | 2026-03-25 | 2026-04-06 | 2026-09-30 | 2026-09-30 | 2102364831 | 8202241875 |  | Perbaikan Motor Lube Oil 970P1C | RU2-ITP | 970-PM-1C/00 | 60 | REL MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 31200000 | 0 | MA3-LIS |  | STEVANEKOPP |  | 2026-04-01 | PT02 | 8 | 3 | 2026-09-30 | PM |  | 003
| K201 | 2026-04-06 | 2026-04-06 | 2026-07-01 | 2026-07-01 | 2102366727 | 8202242082 |  | Perbaikan motor 940 PM 4A | RU2-UTL | 940-PM-4A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  | AZIZFATONI |  | 2026-04-06 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K201 | 2026-02-24 | 2026-04-13 | 2026-02-09 | 2026-02-09 | 2102364023 | 8202239094 |  | Perbaikan Motor 925-PM-2A | RU2-UTL | 925-PM-2A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/NR-D2H | 890000 | 0 | MA3-LIS |  | SATRIAAGUNG |  | 2026-03-12 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K601 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-06-12 | 2102368161 | 8202242558 |  | Perbaikan motor 63K401AM | RU6-ITP | 63-K-401A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 400359 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-20 | PT02 | 6 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-04-17 | 2026-06-02 | 2026-04-17 | 2026-05-06 | 2102368036 | 8202242525 |  | Perbaikan motor 63-P-303B | RU6-ITP | 63-P-306A-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 29545339 | 29469680 | MA4-LIS |  | ANDRIN |  | 2026-04-17 | PT02 | 5 | 3 | 2026-04-17 | PM |  | 003
| K601 | 2026-02-19 | 2026-02-20 | 2026-02-10 | 2026-06-02 | 2102364086 | 8202238982 |  | Perbaikan motor 56-K-102F | RU6-UTL | 56-K-102F/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2 | 8712 | 0 | MA4-LIS |  | DINDINS |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 003
| K601 | 2026-02-19 | 2026-02-23 | 2026-02-19 | 2026-06-17 | 2102364600 | 8202238980 |  | Perbaikan motor 53-S-101A | RU6-UTL | 53-S-101A-M/00 | 60 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2 | 8251940 | 7666568 | MA4-LIS |  | AGUNGK79 |  | 2026-02-20 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-02-19 | 2026-03-17 | 2026-02-19 | 2026-06-09 | 2102364559 | 8202238979 |  | Perbaikan motor 53-P-303A | RU6-UTL | 53-P-303A-M/00 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 884254 | 875542 | MA4-LIS |  | DANDARWANI |  | 2026-02-20 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-05-08 | 2102368095 | 8202242526 |  | Perbaikan Motor 53-P-301 | RU6-UTL | 53-P-301-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 810561 | 1025694 | MA4-LIS |  | DANDARWANI |  | 2026-04-17 | PT02 | 5 | 3 | 2026-04-17 | PM |  | 003
| K601 | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-06-09 | 2102364558 | 8202238978 |  | Perbaikan motor 53-P-203B | RU6-UTL | 53-P-203B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2 | 482343 | 0 | MA4-LIS |  | DINDINS |  | 2026-02-20 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-17 | 2026-11-04 | 2102370067 | 8202243939 |  | Perbaikan motor 53-P-201C | RU6-UTL | 53-P-201C-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 6152497 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-06-19 | 2102368410 | 8202242777 |  | Perbaikan Motor 34-P-109 A | RU6-POC | 34-P-109A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 752387 | 2160482 | MA3-LIS |  | DANDARWANI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-05-20 | 2102366891 | 8202241876 |  | Perbaikan motor 34-A-103-P-101 B | RU6-POC | 34-A-103-P-101BM/0 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 8934159 | 8502152 | MA3-LIS |  | DANDARWANI |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-04-30 | 2026-09-24 | 2102368609 | 8202244040 |  | Perbaikan Motor 20E108B | RU6-RCC | 20-E-108B/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/26/B6/RT-C2H | 1532180 | 0 | MA1-LIS |  | DINDINS |  |  | PT02 | 3 | 2 | 2026-04-30 | PM |  | 003
| K201 | 2026-06-18 | 2026-06-18 | 2026-09-01 | 2026-09-01 | 2102369731 | 8202243948 |  | perbaikan motor 200-PM-8 | RU2-ITP | 200-PM-8/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 1257119 | 0 | MA4-LIS |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 5 | 3 | 2026-09-01 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-04 | 2026-06-26 | 2102368588 | 8202243182 |  | Perbaikan Motor 19-P-109B | RU6-RCC | 19-P-109B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 552101 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-03-16 | 2026-03-16 | 2026-03-05 | 2026-05-12 | 2102365897 | 8202241728 |  | Perbaikan Motor 16-E-120H | RU6-RCC | 16-E-120H/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1445999 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-04 | 2026-06-26 | 2102368678 | 8202243183 |  | Perbaikan Motor 16-E-119E | RU6-RCC | 16-E-119E/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-04 | 2026-06-26 | 2102368674 | 8202243186 |  | Perbaikan Motor 16-E-117C | RU6-RCC | 16-E-117C/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-04 | 2026-06-04 | 2102368672 | 8202243175 |  | Perbaikan Motor 16-E-117AB | RU6-RCC | 16-E-117AB/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-04-30 | 2026-06-25 | 2102368607 | 8202243178 |  | Perbaikan Motor 15E110 Y | RU6-RCC | 15-E-110Y/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-13 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-05-04 | 2026-08-12 | 2102368654 | 8202243763 |  | Perbaikan Motor 15-E-109C | RU6-RCC | 15-E-109C/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K201 | 2026-06-18 | 2026-06-18 | 2026-09-01 | 2026-09-01 | 2102370039 | 8202243944 |  | Perbaikan Motor 140 PM-3B | RU2-HOC | 140-PM-3B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 4955026 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K201 | 2026-04-21 | 2026-05-19 | 2026-07-01 | 2026-07-01 | 2102368232 | 8202242645 |  | Perbaikan Motor 140 PM-27B | RU2-HOC | 140-PM-27B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 112171 | 112171 | MA1-LIS |  | ADEMULYADI |  | 2026-04-21 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K201 | 2026-06-18 | 2026-06-18 | 2026-09-01 | 2026-09-01 | 2102369832 | 8202243947 |  | Perbaikan Motor 140 PM-16B | RU2-HOC | 140-PM-16B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 3110000 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K601 | 2026-06-15 | 2026-06-18 | 2026-06-15 | 2026-10-30 | 2102370031 | 8202243871 |  | Perbaikan motor 14-P-903B | RU6-DHC | 14-P-903B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 716565 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-03-02 | 2026-03-04 | 2026-02-27 | 2026-04-28 | 2102365103 | 8202239288 |  | Perbaikan Motor 14-E-102G | RU6-DHC | 14-E-102G/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 319400 | 319400 | MA2-LIS |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-27 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-17 | 2026-12-04 | 2102370026 | 8202243997 |  | Perbaikan Motor 12-K-501A | RU6-DHC | 12-K-501A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1607223 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-20 | 2026-04-15 | 2026-10-13 | 2102364811 | 8202242473 |  | Perbaikan motor 11P16CM | RU4-FOC1 | 11P16A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 149650 | 149650 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K601 | 2026-05-07 | 2026-05-07 | 2026-05-04 | 2026-06-26 | 2102368690 | 8202243056 |  | Perbaikan Motor 11-P-115 B | RU6-HSC | 11-P-115B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 693950 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-07 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-03-06 | 2026-03-06 | 2026-02-10 | 2026-04-14 | 2102364069 | 8202241316 |  | Perbaikan Motor 11-E-117 A | RU6-HSC | 11-E-117A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 693950 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-03-06 | PT02 | 5 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-08-31 | 2102364924 | 8202241334 |  | Perbaikan Motor 102E520AM2 | RU4-RFCC | 102E520AM2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 173062000 | 173062000 | MA6-LIS |  | YMOHAMMAD |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-08-31 | 2102364923 | 8202241333 |  | Perbaikan Motor 102E517AM2 | RU4-RFCC | 102E517AM2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 156526000 | 156526000 | MA6-LIS |  | YMOHAMMAD |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-26 | 2026-03-12 | 2026-07-29 | 2026-07-30 | 2102365001 | 8202239181 |  | PERBAIKAN MOTOR GM-1-14C | RU5-E15111 | GM-1-14C/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 1061933 | 0 | MA2-LIS |  | GHAGASP |  | 2026-03-12 | PT02 | 5 | 3 | 2026-07-29 | PM |  | 003
| K601 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-07-30 | 2102368125 | 8202242596 |  | Perbaikan Motor 30-P-201B | RU6-HSC | 30-P-201B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1040629 | 948724 | MA3-LIS |  | DANDARWANI |  | 2026-04-20 | PT02 | 5 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-12-08 | 2102361326 | 8202243819 |  | Perbaikan Mobile Lube Oil Purifier | RU6-UTL | 56-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 32738 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-12 | PM |  | 003
| K201 | 2026-06-18 | 2026-06-18 | 2026-09-18 | 2026-09-29 | 2102370091 | 8202243936 |  | Perbaikan mixer 945 T-29 | RU2-ITP | 945-T-29/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 10204000 | 0 | MA4-ROT |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 5 | 3 | 2026-09-18 | PM |  | 003
| K201 | 2026-02-25 | 2026-06-15 | 2026-02-26 | 2026-02-26 | 2102364945 | 8202239168 |  | Perbaikan mixer 610 TK-205 | RU2-ITP | M-205A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 7038444 | 7468833 | MA4-ROT |  | NURFADHILLA |  | 2026-02-25 | PT02 | 5 | 3 | 2026-02-26 | PM |  | 003
| K601 | 2026-06-19 | 2026-06-22 | 2026-06-18 | 2026-12-22 | 2102370106 | 8202243977 |  | Perbaikan mixer 42-T-101E | RU6-ITP | 42-M-101D1-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 17292 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-03-30 | 2026-04-06 | 2026-03-26 | 2026-07-08 | 2102366897 | 8202241929 |  | Perbaikan mixer 42-M-301A | RU6-ITP | 42-M-301A-M/00 | 50 | REL CSER MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 2891077 | 0 | MA4-LIS |  | DINDINS |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K601 | 2026-06-10 | 2026-06-10 | 2026-06-09 | 2026-12-03 | 2102369814 | 8202243732 |  | Perbaikan Membrane Actuator 33-FV-032 | RU6-HSC | 33-FV-032/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | WS-INT |  | DANDARWANI |  | 2026-06-10 | PT02 | 5 | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-06-09 | 2026-06-15 | 2026-06-04 | 2026-07-03 | 2102369663 | 8202243708 |  | Perbaikan Mechseal Pompa 24-P-204 | RU6-HSC | 24-P-204/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C1H | 159052624 | 54957194 | MA1-ROT |  | PANDUA |  | 2026-06-09 | PT02 | 5 | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-18 | 2026-06-17 | 2026-07-15 | 2102370007 | 8202243876 |  | Perbaikan Mechseal Pompa 11-P-109B | RU6-HSC | 11-P-109B/01 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 276401266 | 276401266 | MA1-ROT |  | DANDARWANI |  | 2026-06-17 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-05-04 | 2026-05-29 | 2102368628 | 8202243105 |  | Perbaikan Mechanical SealPompa 15-P-109B | RU6-RCC | 15-P-109B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 15223168 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K201 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-16 | 2102365104 | 8202241540 |  | Perbaikan Mechanical Seal 140-P-22A | RU2-HOC | 140-P-22A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 3572162 | 0 | MA1-ROT |  | MSADLI |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-07-01 | 2102367983 | 8202243143 |  | Perbaikan Mechanical Seal 11-P-102A | RU6-HSC | 11-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 208050000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-03-17 | 2102364453 | 8202238920 |  | Perbaikan Mech. Seal 15-P-104A | RU6-RCC | 15-P-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 603196 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-13 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-04-17 | 2102366596 | 8202241667 |  | Perbaikan Mech Seal Pompa 53-P-303A | RU6-UTL | 53-P-303A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 18177640 | 18175000 | MA4-ROT |  | DANDARWANI |  | 2026-03-12 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-09 | 2026-06-08 | 2026-07-21 | 2102369696 | 8202243682 |  | Perbaikan Mech Seal Pompa 42-P-101D | RU6-ITP | 42-P-101D/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 122041241 | 122037281 | MA4-ROT |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-05-12 | 2102368392 | 8202242756 |  | Perbaikan Mech Seal Pompa 15-P-118C | RU6-RCC | 15-P-118C/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 266216194 | 217894744 | MA1-ROT |  | DANDARWANI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K601 | 2026-04-27 | 2026-05-04 | 2026-04-27 | 2026-05-12 | 2102368391 | 8202242775 |  | Perbaikan Mech Seal Pompa 15-P-118A | RU6-RCC | 15-P-118A/00 | 50 | REL CSER GMCO GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 266216194 | 62400053 | MA1-ROT |  | DANDARWANI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K601 | 2026-05-12 | 2026-06-04 | 2026-05-12 | 2026-06-02 | 2102368971 | 8202243161 |  | Perbaikan Mech Seal Pompa 15-P-111B | RU6-RCC | 15-P-111B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 223106882 | 189106882 | MA1-ROT |  | ABDULAZIZ70 |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-12 | 2026-02-26 | 2026-04-17 | 2102364987 | 8202241621 |  | Perbaikan Mech Seal 34-P-108B | RU6-POC | 34-P-108B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-03-12 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-12 | 2026-02-26 | 2026-04-17 | 2102364986 | 8202241619 |  | Perbaikan Mech Seal 34-P-108A | RU6-POC | 34-P-108A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-03-12 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K601 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-05-13 | 2102367792 | 8202242400 |  | Perbaikan Mech Seal 32-P-103A | RU6-HSC | 32-P-103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 197309215 | 0 | MA3-STA |  | DANDARWANI |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 003
| K601 | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-20 | 2102368668 | 8202242966 |  | Perbaikan Mech Seal 31-P-101B | RU6-HSC | 31-P-101B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 236390134 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-05 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-04-27 | 2026-05-04 | 2026-04-23 | 2026-05-08 | 2102368313 | 8202242776 |  | Perbaikan Mech Seal 16-K-102B | RU6-RCC | 16-K-102B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 76000000 | 76000000 | MA1-ROT |  | PANDUA |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K601 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  | 8202242932 | 8202242775 | Perbaikan Mech Seal 15-P-118A | RU6-RCC | 15-P-118A/00 | 60 | CLSD CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-05-22 | 2026-05-29 | 2026-05-22 | 2026-06-10 | 2102369245 | 8202243418 |  | Perbaikan Mech Seal 15-P-111E | RU6-RCC | 15-P-111E/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 245151998 | 245151998 | MA1-ROT |  | DANDARWANI |  | 2026-05-29 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-19 | 2102368421 | 8202242850 |  | Perbaikan Mech Seal (Tandem) 37-P-102A | RU6-POC | 37-P-102A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 726860546 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-04-30 | PT02 | 4 | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-21 | 2026-06-17 | 2026-12-30 | 2102369765 | 8202243750 |  | Perbaikan Man Hole 85C204 - gasket | RU4-KPC |  | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 9345004 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 045
| K601 | 2026-05-25 | 2026-06-09 | 2026-05-25 | 2026-06-11 | 2102369271 | 8202243466 |  | Perbaikan Lube Oil Pump 62-P-201A | RU6-UTL | 62-P-201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 84641675 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-06-03 | PT02 | 5 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-07-21 | 2102369275 | 8202243423 |  | Perbaikan LPS area tangki Oil Movement | RU6-ITP | 42-LPS-01-T107A/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/26/B6/RT-C2H | 63503466 | 0 | MA4-LIS |  | DINDINS |  |  | PT02 | 5 | 2 | 2026-05-22 | PM |  | 003
| K601 | 2026-05-20 | 2026-05-25 | 2026-05-20 | 2026-06-15 | 2102368242 | 8202243322 |  | Perbaikan LO Pompa 12-P-101A | RU6-DHC | 12-P-101A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 33500000 | MA2-ROT |  | SAPBATCH | 2026-05-22 | 2026-05-20 | PT02 | 5 | 3 | 2026-05-22 | PM |  | 003
| K301 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-09 | 2102367706 | 8202242286 |  | Perbaikan Line Water 3" Jetty 11 Passing |  |  | 01 | CRTD CSER MACM PRC | 3MR |  | 15604685 | 0 | MA4-STA |  | MUSAAA |  |  | PT02 | 3 | 2 | 2026-04-09 | PM |  | 045
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-05 | 2026-07-28 | 2102366210 | 8202241520 |  | Perbaikan Line Pompa Injeksi Molases EWT | RU6-ITP | 63-Z-403/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 32700000 | 32700000 | MA4-STA |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-05-29 | 2026-06-19 | 2026-05-08 | 2026-05-08 | 2102368886 | 8202243550 |  | Perbaikan Line Injeksi Kaporit Sea Water | RU2-ITP | 6-SSW-92562-S1/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-C2H | 401121262 | 0 | MA3-STA |  | DJOKOTRIONO |  | 2026-06-19 | PT02 | 7 | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-04-24 | 2102363540 | 8202239654 |  | Perbaikan Line 601-4" Pompa R | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD CSER MACM PRC | 5MR |  | 27707921 | 0 | MA4-STA |  | OCTARIOHS |  |  | PT02 | 5 | 2 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-13 | 2026-02-13 | 2026-02-06 | 2026-04-01 | 2102361718 | 8202238907 |  | Perbaikan limit switch SB 11-F-101-M | RU6-HSC | 11-F-101-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 55000000 | 16500000 | MA1-LIS |  | DANDARWANI |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-08-04 | 2102361948 | 8202242386 |  | Perbaikan Limit Switch 56-XV-001D | RU6-UTL | 56-XV-001D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 23509768 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-04-14 | 2102365235 | 8202239395 |  | Perbaikan Level Transmitter 15-LT-510 | RU6-RCC | 15-LT-510/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 470300 | 0 | MA1-INT |  | DANDARWANI |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-08-11 | 2102365155 | 8202241678 |  | Perbaikan Level Transmitter 15-LT-510 | RU6-RCC | 15-LT-510/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 130000000 | 0 | MA1-INT |  | DANDARWANI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-09-22 | 2102367947 | 8202242854 |  | Perbaikan Level Transmiitter 31-LT-008 | RU6-HSC | 31-LT-008/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 146770983 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 5 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-05-08 | 2026-05-11 | 2026-05-08 | 2026-11-06 | 2102368901 | 8202243099 |  | Perbaikan Level Transmiitter 15-LT-504 | RU6-RCC | 15-LT-504/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 65000000 | 0 | MA1-INT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-03-09 | 2026-03-13 | 2026-08-03 | 2026-09-02 | 2102365078 | 8202241497 |  | PERBAIKAN LEVEL SWITCH SEPARATOR K-4-01B | RU5-E15111 | K-4-01B-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 156000000 | 0 | MA2-INT |  | RIANDAADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 004
| K601 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-07-31 | 2102361481 | 8202242391 |  | Perbaikan Level Switch Radiator EDG | RU6-UTL | 51-G-102-E1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 9504 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-13 | PM |  | 003
| K601 | 2026-06-03 |  | 2026-06-03 | 2026-12-09 | 2102361478 | 8202243601 |  | Perbaikan level switch LO 056-K-101A1~B3 | RU6-UTL | 056-K-101-A1/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/26/B6/RT-C2H | 17430 | 0 | MA4-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-30 | 2026-03-11 | 2026-03-11 | 2102366547 | 8202241653 |  | Perbaikan LDS SPM di OM 70 |  |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/09/B6/RT1-770-S0NH | 0 | 0 | MA3-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-03-30 | PM |  | 045
| K601 | 2026-03-05 | 2026-04-29 | 2026-03-05 | 2026-05-22 | 2102366137 | 8202239826 |  | Perbaikan lampu TL area OM | RU6-UTL | TR-17/00 | 60 | REL CSER GMPS MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 536229854 | 107545460 | MA4-LIS |  | DANDARWANI |  | 2026-03-06 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-04-07 | 2026-05-19 | 2026-04-02 | 2026-04-02 | 2102367326 | 8202242181 |  | Perbaikan lampu penerangan area UTL | RU2-UTL | 905-LPN-SCES1/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 4429000 | 4429000 | MA3-LIS |  | ADEMULYADI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-04-01 | 2026-06-09 | 2026-04-01 | 2026-04-06 | 2102367054 | 8202242019 |  | Perbaikan lampu penerangan area Utilties | RU2-UTL | 905-LPN-SCES1/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/NR-D2H | 637 | 0 | MA3-LIS |  | SUJATMIKO1 |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-03-06 | 2026-05-06 | 2026-03-06 | 2026-08-31 | 2102364959 | 8202241352 |  | Perbaikan Lampu Penerangan Area RFCC | RU4-RFCUTL | 30BD12EE0102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-05-26 | 2026-05-26 | 2026-05-05 | 2026-06-29 | 2102368697 | 8202243508 |  | Perbaikan lampu penerangan area pompa 56 | RU6-UTL | 56-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 78484356 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K501 | 2026-06-08 | 2026-06-18 | 2026-12-30 | 2026-12-30 | 2102366410 | 8202243699 |  | PERBAIKAN LAMPU INDIKATOR SS80 | RU5-UTL | 1HT-11/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 7800150 | 0 | MA1-LIS |  | FAUZANR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-04 | 2026-02-18 | 2026-02-18 | 2102364535 | 8202239391 |  | Perbaikan Lampu Indikator On/Off 140E607 | RU4-GTO | 140E607C-A/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 003
| K201 | 2026-03-06 | 2026-05-19 | 2026-03-04 | 2026-03-04 | 2102365712 | 8202241346 |  | Perbaikan lampu area WPS Rokan | RU2-UTL | 510-M-C-OH/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 1854000 | 1854000 | MA3-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-20 | 2026-02-02 | 2026-02-02 | 2102355701 | 8202238707 |  | Perbaikan KV Evaporator 180-KV-608 A/B | RU4-GTO | 180KV608A/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-02-20 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-18 | 2102369354 | 8202243588 |  | Perbaikan Kompressor 22-K-101C (MIV) | RU6-DHC | 22-K-101C/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 958126 | 958126 | MA2-ROT |  | DANDARWANI |  | 2026-06-03 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-18 | 2026-03-05 | 2026-02-09 | 2026-04-30 | 2102363893 | 8202238947 |  | Perbaikan kompresor K-3-02B | RU5-E15112 | K-3-02B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 367344501 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K201 | 2026-02-25 | 2026-02-25 | 2026-02-26 | 2026-02-26 | 2102364580 | 8202239167 |  | Perbaikan Kerusakan Gearbox AFT07 | RU2-PK | AFT-07/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2 | 445951 | 0 | WS-KAB |  | STEVANEKOPP |  | 2026-02-25 | PT02 | 8 | 3 | 2026-02-26 | PM |  | 003
| K501 | 2026-04-13 | 2026-04-23 | 2026-08-12 | 2026-08-20 | 2102364762 | 8202242347 |  | Perbaikan kabel signal AT-501 HHP V | RU5-UTL | B5-AT-501/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 19500003 | 0 | WS-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-08-12 | PM |  | 004
| K201 | 2026-04-13 | 2026-05-19 | 2026-04-13 | 2026-04-13 | 2102367474 | 8202242356 |  | Perbaikan kabel power supply pompa motor | RU2-UTL | 940-PM-4A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 6537080 | 6537080 | MA3-LIS |  | ADEMULYADI |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K601 | 2026-02-20 | 2026-06-17 | 2026-02-19 | 2026-04-20 | 2102364640 | 8202239002 |  | Perbaikan kabel motor 63-K-401C | RU6-ITP | 63-K-401C-M/00 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 106534752 | 106530000 | MA4-LIS |  | DANDARWANI |  | 2026-02-20 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K501 | 2026-06-22 | 2026-06-22 | 2026-11-20 | 2026-12-18 | 2102364451 | 8202244029 |  | PERBAIKAN K-3-02A TI SUCTION CYL-6 | RU5-E15112 | K-3-02A/00 | 50 | CRTD CSER MACM PRC | 5IR | D15/26/B6/RT-C2H | 34524775 | 0 | MA3-INT |  | RIANDAADI |  |  | PT02 | 3 | 2 | 2026-11-20 | PM |  | 004
| K501 | 2026-02-22 | 2026-02-26 | 2026-02-13 | 2026-12-31 | 2102364450 | 8202239007 |  | Perbaikan K-3-02A Conrod cyl 6 | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 12283005 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-13 | PM |  | 003
| K201 | 2026-02-27 | 2026-05-19 | 2026-02-27 | 2026-04-20 | 2102351750 | 8202239257 |  | Perbaikan Jangka Menengah | RU2-HCC | 212-P-9B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 254001828 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 045
| K601 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-22 | 2102368808 | 8202243086 |  | Perbaikan Isolasi Kabel 18-PTR2-02B | RU6-POC | 18-PTR2-02B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1672553 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-24 | 2026-02-26 | 2026-02-24 | 2026-04-29 | 2102360703 | 8202239132 |  | Perbaikan Isolasi Area HCC (2) | RU5-E15112 | C-2-01/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2 | 778810000 | 0 | MA3-STA |  | ABDULLOH |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K501 | 2026-04-27 | 2026-05-04 | 2026-10-02 | 2026-12-29 | 2102357868 | 8202242739 |  | Perbaikan Instrumentasi STG 2.2 | RU5-UTL | 2SP10/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 250161918 | 0 | MA1-INT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-10-02 | PM |  | 004
| K401 | 2026-06-11 |  | 2026-06-09 | 2026-06-09 | 2102369788 | 8202243809 |  | Perbaikan Instrumentasi FT-41 |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | WS-KAB |  |  |  |  | PT02 | 3 | 2 | 2026-06-09 | PM |  | 045
| K401 | 2026-06-11 |  | 2026-06-09 | 2026-06-09 | 2102369787 | 8202243808 |  | Perbaikan Instrumentasi FT-40 |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | WS-KAB |  |  |  |  | PT02 | 3 | 2 | 2026-06-09 | PM |  | 045
| K401 | 2026-05-04 | 2026-05-06 | 2026-04-30 | 2026-11-11 | 2102368619 | 8202242953 |  | Perbaikan instrumentasi 11K-401 A/B | RU4-FOC1 | 11K401A/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-05-04 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K601 | 2026-06-17 | 2026-06-17 | 2026-04-29 | 2026-12-22 | 2102368543 | 8202243906 |  | Perbaikan impeller pompa 56-P-101A/B | RU6-UTL | 56-P-101A/00 | 50 WASR | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 2200000001 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-06-17 | PT02 | 5 | 3 | 2026-04-29 | PM |  | 004
| K501 | 2026-05-06 |  | 2026-05-29 | 2026-07-28 | 2102366387 | 8202243002 |  | Perbaikan HVAC SPLIT DUCT SS61-64 | RU5-D&W | SS80-MCC-02C1B/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-29 | PM |  | 004
| K601 | 2026-05-07 | 2026-05-07 | 2026-04-27 | 2026-09-11 | 2102368364 | 8202243061 |  | Perbaikan hot insullation area DHC 11 | RU6-DHC | 12-R-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 543381000 | 543381000 | MA2-STA |  | DANDARWANI |  | 2026-05-07 | PT02 | 5 | 3 | 2026-04-27 | PM |  | 003
| K701 | 2026-03-26 | 2026-03-27 | 2026-01-02 | 2026-01-02 | 2102366933 | 8202241888 |  | Perbaikan High Vibrasi di 1-P-02B | RU7-CDU | 1-P-02B/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 10748801 | 0 | MA-ROT |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 005
| K601 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-04-16 | 2102366895 | 8202241878 |  | Perbaikan Governor Turbine 055-P-101A | RU6-UTL | 055-P-101A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3601848 | 3600000 | MA4-ROT |  | DANDARWANI |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K601 | 2026-04-22 | 2026-04-22 | 2026-04-20 | 2026-05-21 | 2102368201 | 8202242648 |  | Perbaikan Governor Turbin 15-P-101C-T | RU6-RCC | 15-P-101C-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 61253118 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-04-22 | 2026-06-05 | 2026-04-21 | 2026-05-13 | 2102368202 | 8202242647 |  | Perbaikan Governor Turbin 15-P-101B-T | RU6-RCC | 15-P-101B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 61253118 | 0 | MA1-ROT |  | PANDUA |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-04-27 |  | 2026-04-24 | 2026-04-24 |  | 8202242774 | 8202242724 | Perbaikan Gedung SS 25-26 Tagihan 9 | RU6-ITP | 42-T-201A/00 | 01 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-24 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-05-06 | 2102368648 | 8202243036 |  | perbaikan gearbox set 14-P-102B | RU6-DHC | 14-P-102B/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 200000001 | 0 | MA2-ROT |  | PANDUA |  | 2026-05-06 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-29 | 2102368696 | 8202243127 |  | Perbaikan Gearbox Pompa 56-P-101D | RU6-UTL | 56-P-101D/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2176833622 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-07-31 | 2102365115 | 8202241526 |  | Perbaikan gearbox 12-P-501B | RU6-DHC | 12-P-501B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 67824718 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-31 | 2026-03-03 | 2026-04-08 | 2102365301 | 8202239412 |  | Perbaikan Forced Draft Fan 15-K-102A | RU6-RCC | 15-K-102A/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 19911704 | 35790791 | MA1-ROT |  | PANDUA |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-04-27 |  | 2026-07-13 | 2026-08-10 | 2102367202 | 8202242778 |  | Perbaikan FO LDS BPP-LAWE2 | TBL-UP5 | BERTH-MONITOR/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 3 | 2 | 2026-07-13 | PM |  | 004
| K601 | 2026-05-08 | 2026-05-11 | 2026-05-08 | 2026-11-06 | 2102368876 | 8202243096 |  | Perbaikan Flow Transmitter 23-FT-013 | RU6-HSC | 23-FT-013/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 11663450 | 0 | MA1-INT |  | DANDARWANI |  | 2026-05-11 | PT02 | 5 | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-12-04 | 2102369903 | 8202243818 |  | Perbaikan Flow Transmitter 23-FT-013 | RU6-HSC | 23-FT-013/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 11663450 | 0 | MA1-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 5 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-04-13 | 2026-08-28 | 2102367815 | 8202243396 |  | Perbaikan Flow Transmitter 11-FI-410 | RU6-HSC | 11-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA1-INT |  | DANDARWANI |  | 2026-05-21 | PT02 | 5 | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-24 | 2026-03-04 | 2026-03-02 | 2026-03-05 | 2102363903 | 8202239114 |  | PERBAIKAN FLOW TRANSMITTER 05-FT-302 | RU5-E15111 | 05-FT-302/00 | 60 | CLSD CSER DLFL MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 11601019 | 0 | MA2-INT |  | RIANDAADI |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 004
| K501 | 2026-02-24 | 2026-03-04 | 2026-03-02 | 2026-03-05 | 2102363925 | 8202239112 |  | PERBAIKAN FLOW TRANSMITTER 05-FT-069 | RU5-E15111 | 05-FT-069/00 | 60 | CLSD CSER DLFL MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 10974075 | 0 | MA2-INT |  | RIANDAADI |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 004
| K501 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-17 | 2102365114 | 8202243789 |  | Perbaikan Flow Meter Mix Bed 2 | RU5-UTL | DEMIN-123-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 13857501 | 0 | MA1-INT |  | MANKURNIAWAN |  | 2026-06-12 | PT02 | 4 | 3 | 2026-06-19 | PM |  | 004
| K501 | 2026-04-27 | 2026-05-04 | 2026-09-18 | 2026-10-02 | 2102360817 | 8202242728 |  | Perbaikan Flow Meter Deepwell P-6 | RU5-UTL | P-6A-DWELL-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | MA4-INT |  | FAUZANR |  | 2026-05-04 | PT02 | 4 | 3 | 2026-09-18 | PM |  | 004
| K601 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-08-14 | 2102366389 | 8202241735 |  | Perbaikan Flow Control 42-T-101G | RU6-ITP | 42-T-101G/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 75012672 | 0 | MA4-INT |  | DANDARWANI |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-16 | PM |  | 003
| K501 | 2026-03-02 | 2026-03-04 | 2026-02-25 | 2026-08-30 | 2102364887 | 8202239306 |  | Perbaikan Fire Water Pump TSP 513 | RU5-E15500 | TSP-513/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | WS-ROT |  | ANDREAYR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-04-02 | 2026-06-18 | 2026-03-09 | 2026-12-31 | 2102366390 | 8202242037 |  | Perbaikan Finfan EA-32-01R | RU5-E15112 | EA-32-01R/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 15584371 | 0 | MA3-ROT |  | YONZHETG |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-06-02 | 2102367114 | 8202243149 |  | Perbaikan Finfan 57-E-401C | RU6-DHC | 57-E-401C/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 4456078 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-03-03 | 2026-03-06 | 2026-02-20 | 2026-08-30 | 2102364646 | 8202239383 |  | Perbaikan fin-fan EA-2-12B | RU5-E15112 | EA-2-12B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 26077024 | 0 | MA3-ROT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K501 | 2026-03-30 | 2026-05-04 | 2026-03-26 | 2026-08-30 | 2102366952 | 8202241925 |  | Perbaikan Fin-fan EA-1-27A | RU5-E15111 | EA-1-27A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 19060642 | 0 | MA2-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K501 | 2026-02-09 | 2026-02-09 | 2026-02-02 | 2026-04-30 | 2102360782 | 8202238789 |  | Perbaikan Fin- FAN EA-2-12B | RU5-E15112 | EA-2-12C/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 1807400 | 0 | MA3-ROT |  | YONZHETG |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-06-09 | 2102368988 | 8202243368 |  | Perbaikan Fin Fan 32-E-112A1 & B | RU6-HSC | 32-E-112A1/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 18014352 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-21 | PT02 | 5 | 3 | 2026-05-21 | PM |  | 003
| K601 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-07-03 | 2102368987 | 8202243982 |  | Perbaikan Fin Fan 32-E-103 A-D | RU6-HSC | 32-E-103A1/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 53455024 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-04-30 | 2026-05-19 | 2102368600 | 8202243107 |  | Perbaikan Fin Fan 20-E-108B | RU6-RCC | 20-E-108B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 8250387 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-04-16 | 2102366505 | 8202241622 |  | Perbaikan Fin Fan 20-E-108A | RU6-RCC | 20-E-108A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 9954718 | 9387668 | MA1-ROT |  | DANDARWANI |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-04-23 | 2026-04-27 | 2026-04-23 | 2026-05-08 | 2102368275 | 8202242698 |  | Perbaikan Fin Fan 16-E-117D | RU6-RCC | 16-E-117D/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 12904935 | 12165500 | MA1-ROT |  | ERWINSURYAG |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-04-27 | 2026-05-12 | 2102368442 | 8202243109 |  | Perbaikan Fin Fan 15-E-110H | RU6-RCC | 15-E-110H/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 12165500 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K601 | 2026-03-04 | 2026-04-08 | 2026-03-03 | 2026-05-25 | 2102365274 | 8202239415 |  | Perbaikan Fin Fan 12-E-105D | RU6-DHC | 12-E-105D/00 | 50 WAMA | REL CSER MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ABDULAZIZ70 |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-04-15 | 2026-06-17 | 2026-04-15 | 2026-04-15 | 2102367171 | 8202242444 |  | Perbaikan filter 905-TG-1/2/3 | RU2-UTL | 905-G-1/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 110000000 | 0 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-04-09 | 2026-04-23 | 2026-12-01 | 2026-12-31 | 2102366244 | 8202242267 |  | Perbaikan FGDS Tangki Lawe-Lawe |  | 341-FGDS-F-33/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 975500000 | 0 | HSSE |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 5 | 3 | 2026-12-01 | PM |  | 004
| K701 | 2026-06-03 | 2026-06-08 | 2026-06-04 | 2026-06-04 | 2102369541 | 8202243596 |  | Perbaikan FGDS Area Proses | RU7-CDU1 |  | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-5-D1H | 1 | 0 | MA-LINT |  | YAYANHER |  | 2026-06-03 | PT02 | 6 | 3 | 2026-06-04 | PM |  | 005
| K401 | 2026-02-24 |  | 2026-02-02 | 2026-02-02 | 2102356893 | 8202239085 |  | Perbaikan Feedback transmitter 14ZT205 | RU4-FOC1 | 14ZT500/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-03-26 | 2026-03-30 | 2026-03-17 | 2026-06-26 | 2102366830 | 8202241884 |  | Perbaikan feed filter 12-J-501/550 | RU6-DHC | 12-J-501/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 215911080 | 215911080 | MA2-STA |  | DANDARWANI |  | 2026-03-26 | PT02 | 5 | 3 | 2026-03-17 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-09 | 2026-04-08 | 2026-05-25 | 2102367584 | 8202242282 |  | Perbaikan feed filter 12-J-501/550 | RU6-DHC | 12-J-501/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 14326649 | 537458 | MA2-STA |  | DANDARWANI |  | 2026-04-09 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-09-28 | 2102368432 | 8202242800 |  | Perbaikan FDF Boiler 52-B-101B-K1 | RU6-UTL | 52-B-101B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 4613200 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K501 | 2026-05-25 | 2026-06-08 | 2026-10-08 | 2027-01-05 | 2102358784 | 8202243432 |  | Perbaikan FASS Area Gedung HSSE |  | 341-PNL-FS-01/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 27000065 | 0 | HSSE |  | MANKURNIAWAN |  | 2026-06-08 | PT02 | 5 | 3 | 2026-10-08 | PM |  | 004
| K601 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2102368009 | 8202242472 |  | Perbaikan Endflange 8 inch HP Steam | RU6-POC | 38-E-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2332116 | 2035287 | MA3-STA |  | DANDARWANI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-19 | 2026-06-03 | 2026-02-09 | 2026-12-31 | 2102363894 | 8202238976 |  | Perbaikan EA-2-12A | RU5-E15112 | EA-2-12A/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | HIMMATUSS |  |  | PT02 | 3 | 2 | 2026-02-09 | PM |  | 003
| K501 | 2026-03-31 | 2026-05-06 | 2026-03-31 | 2026-03-31 | 2102366954 | 8202241986 |  | Perbaikan EA-1-21 bank nomor 4 bocor | RU5-E15111 | EA-1-21A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 55777186 | 0 | MA2-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K501 | 2026-03-30 | 2026-06-18 | 2026-03-30 | 2026-03-30 | 2102365211 | 8202241924 |  | PERBAIKAN E-1-07 BOCOR SISI SHELL | RU5-E15111 | E-1-07A1/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 231053153 | 0 | MA2-STA |  | HENDRYS |  | 2026-03-31 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-03-30 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2102365245 | 8202241921 |  | Perbaikan E-1-06 A/B Bocor Sisi Shell | RU5-E15111 | E-1-06A/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 33264292 | 0 | MA2-STA |  | BERNANDOP |  | 2026-05-04 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-04-10 | 2026-04-23 | 2026-10-31 | 2026-12-30 | 2102366452 | 8202242312 |  | Perbaikan DS incoming SS 35 |  |  | 50 | REL MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 50276256 | 0 | GM-LIS |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 8 | 3 | 2026-10-31 | PM |  | 045
| K601 | 2026-04-08 | 2026-04-08 | 2026-03-31 | 2026-08-18 | 2102367079 | 8202242182 |  | Perbaikan door inverter elevator NPU | RU6-HSC | 32-R-101-UP6/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K501 | 2026-02-27 | 2026-03-04 | 2026-08-03 | 2026-09-02 | 2102363848 | 8202239245 |  | Perbaikan Display AIT HCU-B | RU5-E15112 | 03B-AIT-222/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 191260000 | 0 | MA3-INT |  | RIANDAADI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 003
| K501 | 2026-02-27 | 2026-03-04 | 2026-08-03 | 2026-09-02 | 2102363849 | 8202239243 |  | Perbaikan Display AIT HCU-A | RU5-E15112 | 03B-AIT-733/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 191260000 | 0 | MA3-INT |  | RIANDAADI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 003
| K701 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2102366863 | 8202241864 |  | Perbaikan dan Cleaning 1-C-04 | RU7-CDU | 1-C-04/00 | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/10/B6/RT1-CDUNH | 2882000 | 2882000 | MA-STA |  | YAYANHER |  | 2026-03-24 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 005
| K701 | 2026-03-24 | 2026-04-07 | 2026-01-02 | 2026-01-02 | 2102366860 | 8202241862 |  | Perbaikan dan Cleaning 1-C-01 | RU7-CDU | 1-C-01/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 5804592 | 0 | MA-STA |  | YAYANHER |  | 2026-03-26 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K601 | 2026-03-17 | 2026-03-31 | 2026-03-17 | 2026-07-14 | 2102366597 | 8202241811 |  | Perbaikan Ctrl Valve 34-PV-050 (Gasket) | RU6-POC | 34-PV-050/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 179400 | 0 | MA3-INT |  | DANDARWANI |  | 2026-03-31 | PT02 | 4 | 3 | 2026-03-17 | PM |  | 003
| K601 | 2026-06-09 | 2026-06-09 | 2026-06-04 | 2026-09-03 | 2102369575 | 8202243722 |  | Perbaikan cover sensor COD SPARING Gate7 | RU6-LK/KK | JALANKILANG/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | INSP-INT |  | DANDARWANI |  | 2026-06-09 | PT02 | 5 | 3 | 2026-06-04 | PM |  | 003
| K201 | 2026-04-10 | 2026-05-19 | 2026-05-20 | 2026-06-22 | 2102367012 | 8202242329 |  | Perbaikan Coupling Pompa 220-P-54 | RU2-HOC | 220-P-54A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 1087864 | 1087864 | MA1-ROT |  | ADEMULYADI |  | 2026-04-10 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K201 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2102367170 | 8202242443 |  | Perbaikan coupling 940-P-1A | RU2-UTL | 940-P-1A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 26895000 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-17 | 2026-07-15 | 2102369823 | 8202243796 |  | Perbaikan Cooler 14-P-903B | RU6-DHC | 14-P-903B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 0 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-06-11 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K501 | 2026-02-27 | 2026-03-06 | 2026-06-22 | 2026-10-28 | 2102365003 | 8202239255 |  | PERBAIKAN CONTROL VALVE KV MASONEILAN | RU5-E15111 | 05-KV-549/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 93740010 | 0 | MA2-INT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-15 | 2102362456 | 8202244036 |  | Perbaikan Control Valve 37-XV-029B/030B | RU6-POC | 37-V-108B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 4 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-22 | PM |  | 005
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-15 | 2102368897 | 8202244022 |  | Perbaikan Control Valve 37-XV-011A | RU6-POC | 37-XV-011A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 005
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-15 | 2102368896 | 8202244021 |  | Perbaikan Control Valve 37-XV-009A | RU6-POC | 37-XV-009A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 005
| K601 | 2026-05-26 | 2026-06-22 | 2026-05-26 | 2026-12-02 | 2102368899 | 8202243527 |  | Perbaikan Control Valve 37-HV-003 | RU6-POC | 37-HV-003/00 | 50 WAMA | REL CSER MANC PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DEATASAP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-05-26 | 2026-06-22 | 2026-05-12 | 2026-11-20 | 2102368898 | 8202243528 |  | Perbaikan Control Valve 36-HV-001 | RU6-POC | 36-HV-001/00 | 50 WAMA | REL CSER MANC PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DEATASAP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-10-23 | 2102351040 | 8202242642 |  | Perbaikan Control Valve 33-XV-084 | RU6-HSC | 33-XV-084/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 25415010 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-05-21 | 2102364582 | 8202239010 |  | Perbaikan Control Valve 31-PV-006 | RU6-HSC | 31-PV-006/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2 | 133640 | 0 | MA3-INT |  | DANDARWANI |  | 2026-02-23 | PT02 | 5 | 3 | 2026-02-23 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-10-21 | 2102363178 | 8202242638 |  | Perbaikan Control Valve 31-LV-003 | RU6-HSC | 31-LV-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-11-18 | 2102368517 | 8202242886 |  | Perbaikan Control Valve 20-FV-003 | RU6-RCC | 20-FV-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-03-11 | 2102364466 | 8202238952 |  | Perbaikan control valve 052-FV-911B | RU6-UTL | 052-B-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2 | 25001980 | 25000000 | MA4-INT |  | DANDARWANI |  | 2026-02-19 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K501 | 2026-04-09 | 2026-04-23 | 2026-12-01 | 2026-12-31 | 2102367500 | 8202242272 |  | PERBAIKAN CONTROL VALVE 05-FCV-170/172 | RU5-E15111 | 05-FCV-172/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 160800001 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-12-01 | PM |  | 004
| K501 | 2026-04-01 | 2026-04-07 | 2026-09-16 | 2026-09-30 | 2102364619 | 8202241997 |  | Perbaikan Control Valve 03B-FCV-180 | RU5-E15112 | 03B-FCV-180/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-09-16 | PM |  | 004
| K501 | 2026-04-01 | 2026-04-07 | 2026-09-14 | 2026-09-28 | 2102364618 | 8202241996 |  | Perbaikan Control Valve 03A-FCV-180 | RU5-E15112 | 03A-FCV-180/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-09-14 | PM |  | 004
| K601 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-04-07 | 2102366241 | 8202241392 |  | Perbaikan control level 052-LV-001A | RU6-UTL | 052-DA-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 25001980 | 25000000 | MA4-INT |  | DANDARWANI |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-04-30 | 2026-05-21 | 2026-04-30 | 2026-12-30 | 2102368021 | 8202242899 |  | Perbaikan Bordesk di area Jetty 67 & 68 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 045
| K601 | 2026-03-12 | 2026-03-13 | 2026-03-11 | 2026-08-03 | 2102366567 | 8202241604 |  | Perbaikan Bordes&Steel Structure Tahap 8 | RU6-DHC | 22BD0405MS134PP/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 1184200000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-03-13 | PT02 | 5 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-08-03 | 2102366565 | 8202241598 |  | Perbaikan Bordes dan Steel Structure di | RU6-HSC | 31-E-101B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 42900000 | 42900000 | MA3-STA |  | DANDARWANI |  | 2026-03-12 | PT02 | 5 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-08-03 | 2102366566 | 8202241606 |  | Perbaikan Bordes dan Steel Structure | RU6-HSC | 31-E-101A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 80600000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-03-12 | PT02 | 5 | 3 | 2026-03-11 | PM |  | 003
| K501 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-27 | 2102366222 | 8202241311 |  | Perbaikan Bola Prover Metering System | RU5-TBL | METER-7861/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 12390000 | 0 | MA4-INT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-06-09 | 2026-06-18 | 2026-06-09 | 2026-09-09 | 2102369786 | 8202243706 |  | Perbaikan bocoran line HP 052-B-101C | RU6-UTL | 052-B-101C/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 55445414 | 46199000 | MA4-STA |  | HARSARIZANO |  | 2026-06-09 | PT02 | 3 | 3 | 2026-06-09 | PM |  | 003
| K201 | 2026-04-23 | 2026-05-19 | 2026-07-01 | 2026-07-01 | 2102368175 | 8202242693 |  | Perbaikan Blower di WS | RU2-WS | DMAC-02/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 1788800 | 1788800 | WS-TL |  | ADEMULYADI |  | 2026-04-24 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K601 | 2026-02-10 | 2026-06-10 | 2026-06-10 | 2026-11-02 | 2102364012 | 8202238813 |  | Perbaikan Blower 22-K-105A | RU6-DHC | 22-K-105A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 145114000 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-02-10 | PT02 | 5 | 3 | 2026-06-10 | PM |  | 005
| K601 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2102364496 | 8202238924 |  | Perbaikan blockvalve 10-OS-901 | RU6-DHC | 10-OS-901/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C1H | 11375625 | 0 | MA2-STA |  | DANDARWANI |  | 2026-02-18 | PT02 | 5 | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-20 | 2026-02-02 | 2026-02-02 | 2102355629 | 8202238706 |  | Perbaikan Benzene Analizer 140AI005 | RU4-GTO | 140AT005/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-02-20 | PM |  | 003
| K201 | 2026-05-26 | 2026-05-29 | 2026-08-03 | 2026-08-03 | 2102365263 | 8202243514 |  | Perbaikan bearingmotor turninggear905TG5 | RU2-UTL | 905-GGM-55/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ER | D12/XX/B6/RT-D2NH | 247239 | 247239 | MA3-LIS |  | NURFADHILLA |  | 2026-05-26 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 003
| K601 | 2026-02-19 | 2026-03-11 | 2026-02-09 | 2026-12-09 | 2102363833 | 8202238964 |  | Perbaikan bearing pompa HBW 052-P-101B | RU6-UTL | 052-P-101B/00 | 50 | REL GMCO MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 207700181 | 0 | MA4-ROT |  | PANDUA |  | 2026-02-19 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-05-07 | 2026-05-25 | 2102368775 | 8202243104 |  | Perbaikan Bearing Pompa 15-P-105A | RU6-RCC | 15-P-105A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 10119668 | 10119668 | MA1-ROT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K201 | 2026-04-07 | 2026-04-07 | 2026-03-03 | 2026-03-03 | 2102365217 | 8202242132 |  | Perbaikan bearing motor FDF 940CM55 | RU2-UTL | 940-CM-55/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/NR-D2H | 6744000 | 6744000 | MA3-LIS |  | STEVANEKOPP |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-05-26 | 2026-06-05 | 2102369377 | 8202243762 |  | Perbaikan bearing motor 57-E-401A | RU6-DHC | 57-E-401A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1256811 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-06 | 2026-03-30 | 2026-04-28 | 2102367017 | 8202242072 |  | Perbaikan Bearing Fin Fan 16-E-117N | RU6-RCC | 16-E-117N/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 12165500 | 12165500 | MA1-ROT |  | DANDARWANI |  | 2026-04-06 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-21 | 2102367555 | 8202242188 |  | Perbaikan Bearing Fan 33-E-101B2 | RU6-HSC | 33-E-101B2/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C3H | 8713152 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-14 | 2026-03-31 | 2026-04-15 | 2102367117 | 8202242191 |  | Perbaikan Bearing Fan 31-E-112F | RU6-HSC | 31-E-112F/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 7552300 | 0 | MA3-ROT |  | PANDUA |  | 2026-04-08 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-05-04 | 2026-05-20 | 2102368658 | 8202243106 |  | Perbaikan Bearing Fan 20-E-108C | RU6-RCC | 20-E-108C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 9283493 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-11 | 2026-06-26 | 2102369867 | 8202243875 |  | Perbaikan Bearing Fan 16-E-120L | RU6-RCC | 16-E-120L/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 13292653 | 13292653 | MA1-ROT |  | DANDARWANI |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-06 | 2026-03-31 | 2026-06-19 | 2102367116 | 8202242071 |  | Perbaikan Bearing 23-P-101B | RU6-HSC | 23-P-101B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 43972280 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-06 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K201 | 2026-05-21 | 2026-06-22 | 2026-07-01 | 2026-07-01 | 2102367496 | 8202243369 |  | Perbaikan bearing 211 PM 27 A | RU2-ITP | 211-PM-27A/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 2349660 | 0 | MA4-LIS |  | NURFADHILLA |  | 2026-05-21 | PT02 | 5 | 3 | 2026-07-01 | PM |  | 003
| K201 | 2026-04-15 | 2026-06-19 | 2026-06-17 | 2026-06-17 | 2102366773 | 8202242453 |  | Perbaikan Bearing | RU2-HSC | 100-P-5B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 3352538 | 3352538 | MA2-ROT |  | NURFADHILLA |  | 2026-05-04 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K501 | 2026-02-24 | 2026-05-04 | 2026-02-09 | 2026-09-30 | 2102364014 | 8202239104 |  | Perbaikan Bangunan PP1 PP2 DEMIN RPAL | RU5-UTL | 41-AC-CR-PP1/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 1 | 0 | MA1-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 4 | 3 | 2026-02-09 | PM |  | 003
| K501 | 2026-02-24 | 2026-05-04 | 2026-02-09 | 2026-09-30 | 2102364015 | 8202239106 |  | Perbaikan Bangunan CWI dan SWD | RU5-UTL | 32-HV-01/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 1 | 0 | MA1-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 4 | 3 | 2026-02-09 | PM |  | 003
| K501 | 2026-04-09 | 2026-05-07 | 2026-10-23 | 2026-11-26 | 2102365268 | 8202242274 |  | Perbaikan ATG Tank Area OM | RU5-D&W | 01-LT-R10/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 6395940000 | 0 | MA4-INT |  | YUSUFM |  | 2026-05-07 | PT02 | 5 | 3 | 2026-10-23 | PM |  | 004
| K701 | 2026-05-07 | 2026-06-16 | 2026-05-07 | 2026-05-07 | 2102368799 | 8202243052 |  | Perbaikan Area Process | RU7-NHT | 2-EA-04/00 | 60 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 152112279 | 124102030 | MA-STA |  | RYANMANGGASA |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 005
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-12-15 | 2102361692 | 8202243931 |  | Perbaikan Analyzer 15-AT-901/902 | RU6-RCC | 15-A-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 40000003 | 0 | MA1-INT |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K501 | 2026-04-14 | 2026-04-23 | 2026-10-06 | 2026-10-20 | 2102367725 | 8202242411 |  | Perbaikan Analyzer 05-AIT-151 | RU5-E15111 | 05-AIT-151/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 383110000 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-10-06 | PM |  | 004
| K501 | 2026-04-14 | 2026-04-23 | 2026-10-19 | 2026-11-02 | 2102367724 | 8202242410 |  | Perbaikan Analyzer 04-AIT-136 | RU5-E15111 | 04-AIT-136/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 383110000 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-10-19 | PM |  | 004
| K701 | 2026-03-03 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102365040 | 8202239341 |  | Perbaikan All area Kilang Maret 2026 |  |  | 50 | REL GMCO NMAT PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | YAYANHER |  | 2026-03-05 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-04-10 | 2026-04-23 | 2026-10-01 | 2026-12-30 | 2102364336 | 8202242313 |  | Perbaikan Alarm Torsi MOV-5D Lawe |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 1 | 0 | MA4-LIS |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 8 | 3 | 2026-10-01 | PM |  | 045
| K201 | 2026-03-04 | 2026-03-04 | 2026-04-01 | 2026-04-01 | 2102365064 | 8202239426 |  | Perbaikan Air Motor 140-PX-55C | RU2-HOC | 140-PX-55C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 7816000 | 0 | MA1-ROT |  | STEVANEKOPP |  | 2026-03-04 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K301 | 2026-05-19 | 2026-06-11 | 2026-04-23 | 2026-04-23 | 2102368259 | 8202243283 |  | Perbaikan Agitator AM 61 252B DWP II | RU3-UTL |  | 50 WAMA | CRTD CSER MACM PRC | 3RR |  | 133200 | 0 | MA3-ROT |  | AIRLANGGAS |  |  | PT02 | 6 | 2 | 2026-04-23 | PM |  | 045
| K201 | 2026-06-17 | 2026-06-18 | 2026-09-01 | 2026-09-01 | 2102368811 | 8202243900 |  | Perbaikan 945-PM-7C motor vibrasi | RU2-ITP | 945-PM-7C/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 2474703 | 0 | MA4-LIS |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K201 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2102367172 | 8202242447 |  | Perbaikan 940-P-1B | RU2-UTL | 940-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 1499982 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-04-13 |  | 2026-04-10 | 2026-04-10 | 2102367801 | 8202242365 |  | Perbaikan 93FI-203 INT-MA1 | RU4-SRU | FI-U93/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 5 | 2 | 2026-04-10 | PM |  | 003
| K401 | 2026-04-13 |  | 2026-04-10 | 2026-04-10 | 2102367800 | 8202242366 |  | Perbaikan 93FI-201 INT-MA1 | RU4-SRU | LI-U93/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 003
| K201 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2102367174 | 8202242452 |  | Perbaikan 925-P-2 (Drinking Water Pump) | RU2-UTL | 925-P-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6694252 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-05-07 | 2026-06-18 | 2026-05-07 | 2026-05-07 | 2102368703 | 8202243050 |  | Perbaikan 925 P-7A | RU2-UTL | 925-P-7A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 272185000 | 0 | MA3-ROT |  | AHILMANSYAH |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-14 | 2026-04-10 | 2026-04-10 | 2102367803 | 8202242364 |  | Perbaikan 91LI112 INT-MA1 | RU4-SRU | 91LT112/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 5 | 2 | 2026-04-14 | PM |  | 003
| K401 | 2026-04-14 |  | 2026-04-10 | 2026-04-10 | 2102367802 | 8202242412 |  | Perbaikan 91FI606 INT-MA1 |  |  | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 5 | 2 | 2026-04-10 | PM |  | 045
| K201 | 2026-02-23 | 2026-06-17 | 2026-05-01 | 2026-05-04 | 2102364084 | 8202239026 |  | Perbaikan 905-DE-1 | RU2-UTL | 905-DEG-01/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 90556438 | 90556438 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-02-23 | PT02 | 3 | 3 | 2026-05-01 | PM |  | 003
| K201 | 2026-04-10 | 2026-04-15 | 2026-05-20 | 2026-06-22 | 2102367424 | 8202242324 |  | Perbaikan 905 DEG 01 | RU2-UTL | 905-DEG-01/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 90556438 | 0 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-04-15 | 2026-04-23 | 2026-12-01 | 2026-12-31 | 2102363910 | 8202242459 |  | PERBAIKAN 8B-LT-251 | RU5-E15112 | C-8-15B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 144241665 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-12-01 | PM |  | 004
| K401 | 2026-05-04 | 2026-06-22 | 2026-05-04 | 2026-11-24 | 2102368657 | 8202242959 |  | Perbaikan 84C204 Mei 25 - Hardcoatig | RU4-KPC | 84C204/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-05-04 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 045
| K201 | 2026-02-27 | 2026-03-02 | 2026-03-27 | 2026-03-27 | 2102364419 | 8202239265 |  | Perbaikan 610 PM-201D | RU2-ITP | P-201D-M/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 898119 | 0 | MA4-LIS |  | AZIZFATONI |  | 2026-03-02 | PT02 | 5 | 3 | 2026-03-27 | PM |  | 003
| K601 | 2026-06-10 | 2026-06-10 | 2026-06-09 | 2026-10-16 | 2102369842 | 8202243745 |  | Perbaikan 6 unit ball valve OM | RU6-ITP | 42-FV-001/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/NR-C2H | 300000001 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-10 | PT02 | 5 | 3 | 2026-06-09 | PM |  | 003
| K201 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2102366617 | 8202241648 |  | Perbaikan 580-PM-301 D | RU2-UTL | 580-PM-301D/00 | 60 | REL PRT CSER MACM PRC SETC | 2ER | D12/26/B6/NR-D2H | 3159022 | 0 | MA3-LIS |  | AZIZFATONI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-22 | 2026-04-02 | 2026-04-02 | 2102367300 | 8202243967 |  | Perbaikan 580-P-608 | RU2-UTL | 580-AND-32/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 30805500 | 0 | MA3-STA |  | NURFADHILLA |  | 2026-06-19 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-06-01 | 2026-07-31 | 2102368148 | 8202243353 |  | Perbaikan 580-P-301D | RU2-UTL | 580-P-301D/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-06-01 | PM |  | 003
| K201 | 2026-05-04 | 2026-05-19 | 2026-05-04 | 2026-05-04 | 2102367687 | 8202242952 |  | Perbaikan 580-P-301B | RU2-UTL | 580-P-301B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 2040000 | 2040000 | MA3-ROT |  | ADEMULYADI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K201 | 2026-02-23 | 2026-02-23 | 2026-05-01 | 2026-05-04 | 2102364085 | 8202239027 |  | Perbaikan 560-GT-03 | RU2-UTL | 560-GT-3/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2 | 93961156 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-02-23 | PT02 | 3 | 3 | 2026-05-01 | PM |  | 003
| K201 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-07-30 | 2102364234 | 8202238857 |  | Perbaikan 550-P-102 | RU2-UTL | 550-P-102/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-02-11 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 003
| K201 | 2026-04-15 | 2026-06-17 | 2026-04-15 | 2026-04-15 | 2102367173 | 8202242450 |  | Perbaikan 520-P-609A | RU2-UTL | 520-P-609/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6694252 | 0 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-06-15 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2102369930 | 8202243842 |  | Perbaikan 520-P-608D | RU2-UTL | 520-P-608D/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 18169000 | 0 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-06-15 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K201 | 2026-06-15 | 2026-06-15 | 2026-06-11 | 2026-06-11 | 2102369898 | 8202243843 |  | Perbaikan 520-P-608D | RU2-UTL | 520-P-608D/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-06-15 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K201 | 2026-05-12 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 2102368815 | 8202243163 |  | Perbaikan 510-DE-12 | RU2-UTL | 510-DE-12/00 | 50 | REL GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 245486490 | 245486490 | MA3-ROT |  | ERLANGGA |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K201 | 2026-05-12 | 2026-06-02 | 2026-05-21 | 2026-05-21 | 2102368814 | 8202243162 |  | Perbaikan 510-DE-11 | RU2-UTL | 510-DE-11/00 | 50 | REL GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 402631722 | 402631722 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K601 | 2026-04-16 | 2026-04-16 | 2026-04-15 | 2026-06-04 | 2102367999 | 8202242485 |  | Perbaikan 51-G-101B-P1A-T | RU6-UTL | 51-G-101B-P1A-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 347559127 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-16 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 005
| K601 | 2026-06-15 | 2026-06-18 | 2026-06-15 | 2026-07-28 | 2102370004 | 8202243864 |  | Perbaikan 51-G-101A-P2A | RU6-UTL | 51-G-101A-P2A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 1603960 | 1600000 | MA4-ROT |  | PANDUA |  | 2026-06-15 | PT02 | 5 | 3 | 2026-06-15 | PM |  | 003
| K501 | 2026-04-09 | 2026-04-23 | 2026-04-09 | 2026-05-08 | 2102367654 | 8202242280 |  | PERBAIKAN 3A-TI-5223 dan 3A-TI-5226 F-3- | RU5-E15112 | F-3-03A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C1H | 18186000 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 004
| K501 | 2026-04-09 | 2026-04-23 | 2026-04-09 | 2026-05-08 | 2102367655 | 8202242279 |  | PERBAIKAN 3A-TI-5212E F-3-04A | RU5-E15112 | F-3-04A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 9093000 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 004
| K601 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-06-08 | 2102368907 | 8202243124 |  | Perbaikan 37-PT-016 | RU6-POC | 37-F-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C3H | 106966400 | 58313600 | MA3-INT |  | DANDARWANI |  | 2026-05-11 | PT02 | 4 | 3 | 2026-05-11 | PM |  | 003
| K601 | 2026-03-17 | 2026-06-17 | 2026-03-10 | 2026-10-27 | 2102366357 | 8202241782 |  | Perbaikan 35-P-101 A | RU6-POC | 35-P-101A/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 189800001 | 0 | MA3-ROT |  | YOSUA |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K201 | 2026-05-21 | 2026-06-18 | 2026-06-01 | 2026-06-03 | 2102366876 | 8202243356 |  | Perbaikan 310-C-1 | RU2-HSC | 310-C-1/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 69898000 | 34949000 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-05-22 | PT02 | 5 | 3 | 2026-06-01 | PM |  | 003
| K201 | 2026-02-23 | 2026-02-23 | 2026-05-05 | 2026-05-05 | 2102364620 | 8202239033 |  | Perbaikan 301-ONP-1B | RU2-HSC | 301-ONP-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2 | 1892334 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-02-23 | PT02 | 5 | 3 | 2026-05-05 | PM |  | 003
| K201 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-04-29 | 2102367417 | 8202242660 |  | Perbaikan 300-FT-176 | RU2-HSC | 300-FT-176/00 | 60 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 9900000 | 9900000 | MA2-INT |  | ADEMULYADI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-22 | PM |  | 003
| K701 | 2026-03-11 |  | 2026-03-11 | 2026-03-11 |  | 8202241587 | 8202239341 | PERBAIKAN 3-K-01AB |  |  | 50 | REL CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-3-D3H | 3452000 | 3452000 | MA-ROT |  |  |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K601 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-11-25 | 2102364962 | 8202239162 |  | Perbaikan 23-P-101 B | RU6-HSC | 23-P-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 2880518 | 2880518 | MA1-ROT |  | DANDARWANI |  | 2026-02-25 | PT02 | 5 | 3 | 2026-02-25 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-09-14 | 2102368399 | 8202242760 |  | Perbaikan 22-UV-701 | RU6-DHC | 22-UV-701/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 26000000 | 26000000 | MA2-INT |  | DANDARWANI |  | 2026-04-27 | PT02 | 4 | 3 | 2026-04-27 | PM |  | 003
| K601 | 2026-03-30 | 2026-03-30 | 2026-03-26 | 2026-03-26 | 2102366886 | 8202241923 |  | Perbaikan 20PSV005A | RU6-RCC | 20-PSV-005A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 56380759 | 0 | MA1-STA |  | DANDARWANI |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K201 | 2026-05-04 | 2026-06-19 | 2026-04-09 | 2026-04-09 | 2102367649 | 8202242927 |  | Perbaikan 200-P-4 B | RU2-HSC | 200-P-4B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 334219 | 334219 | MA2-ROT |  | NURFADHILLA |  | 2026-05-04 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 003
| K601 | 2026-02-12 | 2026-02-12 | 2026-02-10 | 2026-05-20 | 2102363986 | 8202238874 |  | Perbaikan 20-P-103A | RU6-RCC | 20-P-103A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 300000001 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-06-18 | 2102368608 | 8202243043 |  | Perbaikan 20-E-108C | RU6-RCC | 20-E-108C/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 25534111 | 8570694 | MA1-ROT |  | ERWINSURYAG |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K701 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2102369917 | 8202243862 |  | Perbaikan 2-EA-04 A/B | RU7-NHT | 2-EA-04/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 7600000 | 0 | MA-STA |  |  |  |  | PT02 | 3 | 2 | 2026-06-15 | PM |  | 005
| K701 | 2026-05-14 | 2026-05-14 | 2026-05-18 | 2026-05-18 | 2102369073 | 8202243200 |  | Perbaikan 2-EA-01A | RU7-NHT | 2-EAM-01A/00 | 50 | REL CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 152224 | 152224 | MA-LINT |  | RYANMANGGASA |  | 2026-05-14 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 005
| K601 | 2026-04-06 | 2026-04-07 | 2026-03-31 | 2026-08-19 | 2102367100 | 8202242084 |  | Perbaikan 19-PMC3-01E | RU6-UTL | 01-PSW3-04-011/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 4512144 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-07 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-04-21 |  | 2026-04-14 | 2026-04-14 | 2102367878 | 8202242637 |  | Perbaikan 152 VI 765B | RU4-RFCUTL |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  |  |  |  | PT02 | 3 | 2 | 2026-04-14 | PM |  | 045
| K401 | 2026-04-21 |  | 2026-04-14 | 2026-04-14 | 2102367877 | 8202242639 |  | Perbaikan 152 VI 664A | RU4-RFCUTL |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  |  |  |  | PT02 | 3 | 2 | 2026-04-14 | PM |  | 045
| K201 | 2026-03-04 | 2026-05-04 | 2026-04-01 | 2026-04-01 | 2102364991 | 8202239428 |  | Perbaikan 140-PX-54 A/B | RU2-HOC | 140-PX-54A/00 | 60 | REL CSER GMPS MSPT PRC SETC | 2RR | D12/26/B6/RT-D2H | 4213445 | 2891908 | MA1-ROT |  | MDSYAHPUTRA |  | 2026-03-04 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K601 | 2026-04-28 | 2026-04-29 | 2026-03-31 | 2026-09-01 | 2102367145 | 8202242789 |  | Perbaikan 14-P-102B | RU6-DHC | 14-P-102B/00 | 50 | CRTD NMAT PRC | 6RR | D16/26/B6/RT-C2H | 100000001 | 0 | MA2-ROT |  | DANDARWANI |  |  | PT02 | 6 | 2 | 2026-03-31 | PM |  | 003
| K601 | 2026-04-29 |  | 2026-03-31 | 2026-09-01 |  | 8202242820 | 8202242789 | Perbaikan 14-P-102B | RU6-DHC | 14-P-102B/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 100000001 | 0 | MA2-ROT |  |  |  | 2026-04-29 | PT02 | 6 | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-03-02 | 2026-03-04 | 2026-02-06 | 2026-04-08 | 2102362278 | 8202239287 |  | Perbaikan 14-E-102F-M | RU6-DHC | 14-E-102F-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 319400 | 319399 | MA2-LIS |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-03-02 | 2026-03-04 | 2026-02-06 | 2026-02-20 | 2102362228 | 8202239286 |  | Perbaikan 14-E-102E-M | RU6-DHC | 14-E-102E-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 319400 | 319400 | MA2-LIS |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-12-11 | 2102361854 | 8202243929 |  | Perbaikan 12-LSLL-217 dan 12-LSHH-211 | RU6-DHC | 12-V-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA2-INT |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-06-11 |  | 2026-06-03 | 2026-06-03 | 2102369591 | 8202243807 |  | Perbaikan 103LV020 - Leak body valve | RU4-RFCC | 103LV020/00 | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA6-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-26 | 2026-05-18 | 2026-05-18 | 2102369131 | 8202243477 |  | Perbaikan 102LI013 - Indikasi Fault | RU4-RFCC | 102LT013/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-26 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-10 | 2026-06-10 | 2102369862 | 8202243805 |  | Perbaikan 101PG603A - PG mist separator | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA6-INT |  | BENYHIDAYAT |  |  | PT02 | 3 | 2 | 2026-06-10 | PM |  | 045
| K401 | 2026-05-25 | 2026-05-26 | 2026-05-19 | 2026-05-19 | 2102369162 | 8202243470 |  | Perbaikan 101P523C - TG Rusak & line | RU4-RFCC | 101P523C/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-26 | PM |  | 003
| K401 | 2026-06-11 |  | 2026-06-04 | 2026-06-04 | 2102369598 | 8202243806 |  | Perbaikan 101P501B - 101TG901BC rusak | RU4-RFCC | 101P501B/00 | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA6-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-04 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2102366700 | 8202241741 |  | Perbaikan 101FIC062 - PV OP Abrnormal | RU4-RFCC | 101FIC-U101/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-03-16 | PM |  | 003
| K501 | 2026-03-17 | 2026-05-04 | 2026-02-11 | 2026-12-31 | 2102364096 | 8202241797 |  | Perbaikan 101-PT-1A | RU5-TBL | 101-PT-1C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 003
| K701 | 2026-04-24 |  | 2026-04-24 | 2026-04-24 | 2102368331 | 8202242704 |  | Perbaikan 1-P-04A | RU7-CDU | 1-P-04A/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 15075000 | 0 | MA-ROT |  |  |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 005
| K701 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2102366861 | 8202241863 |  | PERBAIKAN 1-C-02.03 | RU7-CDU | 1-C-02/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/10/B6/RT1-CDUNH | 6558800 | 0 | MA-STA |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-03-25 | PM |  | 005
| K501 | 2026-04-20 | 2026-05-13 | 2026-04-20 | 2026-05-21 | 2102368041 | 8202242598 |  | PERBAIKAN 05-KV-514 | RU5-E15111 | 05-KV-514/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 246750000 | 0 | MA2-INT |  | RIANDAADI |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 004
| K401 | 2026-06-15 | 2026-06-17 | 2026-06-11 | 2026-06-11 | 2102369923 | 8202243863 |  | Perbaikan 014BV-75 | RU4-FOC2 | 014BV75/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | HARISWIDI |  |  | PT02 | 3 | 2 | 2026-06-17 | PM |  | 003
| K601 | 2026-05-19 | 2026-06-15 | 2026-05-12 | 2026-11-20 | 2102368909 | 8202243282 |  | Perbaikan (Permanent Repair) 14-P-102B | RU6-DHC | 14-P-102B/00 | 50 WAMA | REL CSER MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 311300073 | 0 | MA2-ROT |  | PANDUA |  | 2026-05-19 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-03-16 | 2026-05-04 | 2026-02-06 | 2026-12-31 | 2102363571 | 8202241766 |  | Perbaikan 101-M-01A3 | RU5-TBL | 101-MI-1A3/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 229400123 | 0 | MA4-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-03-17 | 2026-05-04 | 2026-02-06 | 2026-12-31 | 2102363570 | 8202241792 |  | Perbaikan 101-M-01A2 | RU5-TBL | 101-5-MI-1A2/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 111097612 | 0 | MA4-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-03-06 | 2102351044 | 8202239003 |  | Perba Fin Fan 24-E-202B, 11-P-114A (MIV) | RU6-HSC | 24-E-202B/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C1 | 14243930 | 13381186 | MA1-ROT |  | PANDUA |  | 2026-02-23 | PT02 | 5 | 3 | 2026-02-20 | PM |  | 003
| K501 | 2026-04-28 | 2026-06-10 | 2026-11-02 | 2026-12-30 |  | 8202242784 |  | Perb.Tiang lampu Dolphin Jetty 5A/B/C OM | RU5-TBL | PLANT-22-LIS/00 | 01 | CLSD NCMP NMAT PRC | 5ER | D15/26/B6/RT-C2H | 1 | 0 | MA4-LIS |  | GHAGASP |  |  | PT02 | 8 | 2 | 2026-06-10 | PM |  | 003
| K501 | 2026-04-24 | 2026-05-04 | 2026-04-27 | 2026-04-30 | 2102367528 | 8202242723 |  | Perb.Drain Sewer Pompa 101-P-1ABCD | RU5-TBL | 101-P-1D/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 17629753 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K501 | 2026-04-09 | 2026-05-04 | 2026-04-09 | 2026-05-26 | 2102367143 | 8202242268 |  | Perb. Valve line 858-10" depan A20 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 24582702 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K501 | 2026-04-07 | 2026-05-04 | 2026-04-07 | 2026-05-22 | 2102367144 | 8202242133 |  | Perb. Valve by pass 3" RP A Putih | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 4943342 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K501 | 2026-04-06 | 2026-04-07 | 2026-10-19 | 2026-11-16 | 2102366117 | 8202242067 |  | PERB. TRANSMITTER 01-FT-099A/B,118A/B | RU5-E15111 | 01-FT-099A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 4 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-10-19 | PM |  | 004
| K501 | 2026-05-18 | 2026-06-18 | 2026-05-18 | 2026-07-03 | 2102363939 | 8202243236 |  | Perb. Steam Injektor Rp P | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 16754424 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-03-31 | 2026-06-11 | 2026-02-02 | 2026-02-18 | 2102360152 | 8202241958 |  | Perb. Solenoid Backwash Filter V-3-02B | RU5-E15112 | V-3-02B/01 | 60 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 36950000 | 0 | MA3-INT |  | BERNANDOP |  | 2026-04-07 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-03-31 | 2026-04-07 | 2026-07-16 | 2026-08-13 | 2102365793 | 8202241962 |  | PERB. SENSOR TEMP. BEARING K-19-01A | RU5-E15112 | K-19-01A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 4 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-07-16 | PM |  | 004
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-09 | 2026-04-28 | 2102364861 | 8202241454 |  | Perb. Low Drain P. inlet Filter Avtur OM | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 989506 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-03-10 | 2026-05-04 | 2026-03-10 | 2026-04-29 | 2102364624 | 8202241542 |  | Perb. LineGasoline Slop frm Drum Jt5B OM | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 14323154 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K501 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-13 | 2102363716 | 8202241946 |  | Perb. Line Venting 0,5" Suction P15 A Pt | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 158472856 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 5 | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-04-07 | 2026-05-06 | 2026-04-07 | 2026-05-22 | 2102366977 | 8202242130 |  | Perb. Line Prduksi IDO menuju Tanki O18 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 163804761 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K501 | 2026-04-06 | 2026-06-17 | 2026-04-06 | 2026-05-21 | 2102364112 | 8202242061 |  | Perb. Line Piping Produk kepala Jt VB OM | RU5-TBL | PIPE-SHIP/00 | 50 | CRTD CSER MACM PRC RELR | 5MR | D15/26/B6/RT-C2H | 3057957693 | 0 | MA4-STA |  | FAUZANR |  |  | PT02 | 3 | 2 | 2026-04-06 | PM |  | 003
| K501 | 2026-06-19 | 2026-06-23 | 2026-06-19 | 2026-07-31 | 2102369101 | 8202243975 |  | Perb. Line Fresh Water Kaki Jetty 5 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 3897510 | 0 | MA4-STA |  | BERNANDOP |  | 2026-06-23 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K501 | 2026-03-06 | 2026-05-04 | 2026-03-06 | 2026-04-27 | 2102360741 | 8202241299 |  | Perb. Line Fresh Water 6" | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 29845749 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-03-26 | 2026-04-14 | 2026-03-25 | 2026-08-10 | 2102366894 | 8202241887 |  | Perb. Line Drain WtrDrum&Refrc. Boiler B | RU6-UTL | 52-B-101B/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6MR | D16/26/B6/RT-C2H | 8177644 | 6748863 | MA4-STA |  | PUTRIMAMELLI |  | 2026-03-26 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K501 | 2026-04-23 | 2026-05-04 | 2026-04-23 | 2026-06-12 | 2102367984 | 8202242689 |  | Perb. Line Drain 4" Belakang Gudang RPA | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 34242214 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K501 | 2026-04-23 | 2026-05-29 | 2026-04-23 | 2026-06-12 | 2102367342 | 8202242688 |  | Perb. Line Ballast 16" Belakang Meter123 | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 410683409 | 0 | MA4-STA |  | BERNANDOP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K501 | 2026-04-09 | 2026-05-06 | 2026-04-09 | 2026-05-26 | 2102367032 | 8202242270 |  | Perb. Line 930-10" Bwh Jembatan Kaki Jt3 | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 96697149 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 003
| K501 | 2026-02-27 | 2026-05-06 | 2026-03-02 | 2026-04-21 | 2102358930 | 8202239258 |  | Perb. Line 904-10" Crude Samping A-28 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 241307447 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 5 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-05-20 | 2026-06-18 | 2026-05-20 | 2026-07-07 | 2102369102 | 8202243324 |  | Perb. Line 810-10" Pertadex Stasiun 2 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 178445340 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-04-20 | 2026-05-29 | 2026-04-20 | 2026-06-09 | 2102367931 | 8202242553 |  | Perb. Line 421-16" Belakang Filter Avtur | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 467044997 | 0 | MA4-STA |  | BERNANDOP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K501 | 2026-03-17 | 2026-05-04 | 2026-03-17 | 2026-05-07 | 2102365084 | 8202241790 |  | Perb. Line 4" Disch Torak OC R | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 34177177 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-17 | PM |  | 003
| K501 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-04-24 | 2102363831 | 8202239655 |  | Perb. Line 33-6" Prod Naphtha CDU5 | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD CSER MACM PRC | 5MR |  | 73990942 | 0 | MA4-STA |  | OCTARIOHS |  |  | PT02 | 3 | 2 | 2026-03-05 | PM |  | 003
| K501 | 2026-04-15 | 2026-05-06 | 2026-04-15 | 2026-06-04 | 2102367857 | 8202242441 |  | Perb. Line 18-8" Prod ADO di St 1 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 96107534 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 2 | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-03-12 | 2026-05-04 | 2026-03-12 | 2026-05-04 | 2102365134 | 8202241629 |  | Perb. Line 18-6" Prod ADO BPP1 dp St.1 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 17826687 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K501 | 2026-02-27 | 2026-04-07 | 2026-06-02 | 2026-06-17 | 2102364865 | 8202239239 |  | PERB. LIMIT SWITCH KOMPRESSOR K-4-01A | RU5-E15111 | K-4-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 2 | 0 | MA2-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 004
| K501 | 2026-03-12 | 2026-03-12 | 2026-12-01 | 2026-12-30 | 2102364465 | 8202241603 |  | Perb. Lampu Penerangan Area OM |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 1603904 | 0 | MA4-LIS |  | GHAGASP |  | 2026-03-12 | PT02 | 8 | 3 | 2026-12-01 | PM |  | 045
| K501 | 2026-05-04 | 2026-06-04 | 2026-05-04 | 2026-06-23 | 2102365120 | 8202242957 |  | Perb. L 135-24" ADO Suction GM2008 OM | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | CRTD CSER MACM PRC RELR | 5MR | D15/10/B6/RT1-FJNH | 3136645197 | 0 | MA4-STA |  | BERNANDOP |  |  | PT02 | 3 | 2 | 2026-05-04 | PM |  | 003
| K501 | 2026-03-02 | 2026-06-17 | 2026-03-02 | 2026-05-12 | 2102364134 | 8202239293 |  | PERB. ISOLASI AREA HSC EWTP DHP (4) | RU5-E15111 | 001-FT-0899/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 193166000 | 0 | MA2-STA |  | FAUZANR |  | 2026-06-17 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-27 | 2026-05-04 | 2026-03-25 | 2026-03-25 | 2102366877 | 8202241909 |  | Perb. Gear Box Valve Line Outlet A-24 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 2587200 | 0 | MA4-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K501 | 2026-03-12 | 2026-05-06 | 2026-03-12 | 2026-05-04 | 2102365136 | 8202241632 |  | Perb. Gate Valve 930-10" Kero Kaki Jt 3 | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 60857943 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K501 | 2026-03-31 | 2026-04-07 | 2026-07-22 | 2026-08-20 | 2102360737 | 8202241981 |  | PERB. CURRENT TRANSDUCER GM-32-05 | RU5-UTL | GM-32-05A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 7710000 | 0 | MA1-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 2 | 3 | 2026-07-22 | PM |  | 004
| K501 | 2026-03-02 | 2026-03-06 | 2026-06-02 | 2026-08-28 | 2102365004 | 8202239276 |  | PERB. CONTROL VALVE KV NELES | RU5-E15111 | 05-KV-505/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 94363640 | 0 | MA2-INT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-09 | 2026-04-28 | 2102358770 | 8202241359 |  | Perb. BV 6" Inlet A-28 & Jalur Napasan | RU5-TBL | A-28/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 13086213 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-05-19 | 2026-06-18 | 2026-05-19 | 2026-07-06 | 2102367426 | 8202243268 |  | Perb Valve 18"#150 LSWR depan P1 A Putih | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 72578360 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-24 | 2026-04-10 | 2026-12-28 | 2026-12-28 | 2102364860 | 8202239121 |  | Perb Nipple&Seal Swivel 80 LA No 1 JT.3 | RU5-TBL | L-ARM-1-JT-3/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 378449 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-12-28 | PM |  | 003
| K501 | 2026-05-20 | 2026-06-18 | 2026-05-20 | 2026-07-07 | 2102367427 | 8202243328 |  | Perb Line LSWR 956-20" samping slop RPA | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 1062266741 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-05-19 | 2026-06-18 | 2026-05-19 | 2026-07-06 | 2102367425 | 8202243291 |  | Perb Line LSWR 24" depan Tangki A-29 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 395336540 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-05-13 | 2026-05-29 | 2026-05-13 | 2026-07-02 | 2102367428 | 8202243185 |  | Perb Line 911-20" depan Tangki A-29 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 267296196 | 0 | MA4-STA |  | BERNANDOP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-03-02 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2102365203 | 8202239307 |  | Perb Line 909-20" depan A17 Pertaseries | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 354703233 | 0 | MA4-STA |  | BERNANDOP |  | 2026-04-17 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K201 | 2026-06-02 | 2026-06-09 | 2026-06-03 | 2026-06-03 | 2102369327 | 8202243555 |  | Perb Jalan Kilang Tahap 1 | RU2-HCC |  | 50 | CRTD NMAT PRC | 2MR |  | 10000000000 | 0 | MA2-STA |  | DJOKOTRIONO |  |  | PT02 | 5 | 2 | 2026-06-03 | PM |  | 045
| K601 | 2026-04-07 | 2026-05-12 | 2026-04-07 | 2026-04-21 | 2102367493 | 8202242144 |  | Perb Governor Turbine 055-P-101A-T (MIV) | RU6-UTL | 055-P-101A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 59916931 | 59915611 | MA4-ROT |  | PANDUA |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K501 | 2026-04-13 | 2026-04-28 | 2026-04-13 | 2026-04-13 | 2102367480 | 8202242350 |  | Perb Gearbox Valve Tangki A24 Luar Bundw | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 2242800 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-06-02 |  | 2026-05-12 | 2026-05-12 | 2102369021 | 8202243578 |  | Perb filter purging mechseal N2 14K650 | RU4-FOC1 | 14K650/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-08-31 | 2102364973 | 8202241325 |  | PERB & PENGGUNAAN LAMPU PENERANGAN FOC I | RU4-FOC1 | 10BDN2PLIU1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 343200000 | 343200000 | MA1-INT |  | YMOHAMMAD |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-06 | 2026-04-24 | 2026-03-06 | 2026-08-31 | 2102364974 | 8202241326 |  | PERB & PENGGUNAAN LAMPU PENERANGAN FOC I | RU4-FOC1 | 10BDN2PLIU1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 79200000 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-26 | 2026-04-15 | 2026-04-15 | 2026-06-04 | 2102364774 | 8202239223 |  | Per.Gen. Steam Turbin 51-P-101A-T SPK 17 | RU6-UTL | 51-P-101A-T/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 364800000 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-15 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 004
| K601 | 2026-02-26 | 2026-04-15 | 2026-04-15 | 2026-06-04 | 2102364896 | 8202239229 |  | Per.Gen. Steam Turbin 42-P-502B-T SPK 20 | RU6-ITP | 42-P-502B-T/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 386300000 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-15 | PT02 | 4 | 3 | 2026-04-15 | PM |  | 004
| K601 | 2026-02-26 | 2026-04-15 | 2026-04-15 | 2026-06-04 | 2102364689 | 8202239227 |  | Per.Gen. Steam Turbin 11-P-104A-T SPK 19 | RU6-HSC | 11-P-104A-T/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 406500000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-15 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 004
| K601 | 2026-02-26 | 2026-05-18 | 2026-02-26 | 2026-07-21 | 2102364764 | 8202239225 |  | Per.Gen. Steam Turbin 055-P-101AT SPK 18 | RU6-UTL | 055-P-101A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 434300000 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 004
| K601 | 2026-06-02 | 2026-06-12 | 2026-06-02 | 2026-10-12 |  | 8202243566 | 8202233429 | Penyelesaian PMPDM Elect&Inst. MA3 Thp 8 | RU6-POC | 18-PBC3-01A/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 70346000 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-05-22 | 2026-06-02 | 2026-05-25 | 2026-10-06 |  | 8202243430 | 8202233429 | Penyelesaian PMPDM Elect&Inst. MA3 Thp 7 | RU6-POC | 18-PSW2-01-001/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 69708000 | 0 | MA3-LIS |  | DINDINS |  | 2026-06-02 | PT02 | 1 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-05-22 | 2026-05-26 | 2026-05-22 | 2026-10-06 |  | 8202243429 | 8202233429 | Penyelesaian PMPDM Elect&Inst. MA3 Thp 6 | RU6-POC | 18-PSW2-01-001/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 95022000 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K601 | 2026-03-13 | 2026-03-13 | 2026-01-19 | 2026-06-12 |  | 8202241672 | 8202233429 | Penyelesaian PMPDM Elect&Inst. MA3 Thp 5 | RU6-POC | 18-PSW2-01-001/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 69785000 | MA3-LIS |  | DANDARWANI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-03-12 | 2026-04-09 | 2026-01-19 | 2026-06-12 |  | 8202241635 | 8202233429 | Penyelesaian PMPDM Elect&Inst. MA3 Thp 4 | RU6-POC | 18-PSW2-01-001/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA3-LIS |  | DINDINS |  | 2026-03-13 | PT02 | 3 | 3 | 2026-01-19 | PM |  | 003
| K201 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-12-30 | 2102369577 | 8202243633 |  | Penyelesaian Penyusunan CCD Area HSC | RU2-HSC | 100-H-1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 568616950 | 0 | MA2-STA |  | STEVANEKOPP |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-10-26 |  | 8202243945 | 8202239013 | Penyelesaian Pekerjaan EI MA1 tahap 15 | RU6-RCC | 09-14B-PSW2-01A/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 53087000 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-02-23 | 2026-06-17 | 2026-02-20 | 2026-06-03 |  | 8202239018 | 8202239013 | Penyelesaian Pekerjaan EI MA1 tahap 14 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | TECO CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 53089000 | 53089000 | MA1-LIS |  | ZAMZAMKHALID |  | 2026-02-23 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-02-23 | 2026-06-17 | 2026-02-20 | 2026-06-03 |  | 8202239017 | 8202239013 | Penyelesaian Pekerjaan EI MA1 tahap 13 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | TECO CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 53411000 | 53411000 | MA1-LIS |  | ZAMZAMKHALID |  | 2026-02-23 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-02-23 | 2026-06-17 | 2026-02-20 | 2026-06-03 |  | 8202239016 | 8202239013 | Penyelesaian Pekerjaan EI MA1 tahap 12 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | TECO CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 53040000 | 53040000 | MA1-LIS |  | ZAMZAMKHALID |  | 2026-02-23 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-10-26 |  | 8202243943 | 8202232778 | Penyelesaian Pek. PM PDM EI MA4 tahap 16 | RU6-UTL | SS-01/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 91424300 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-06-20 | 2026-06-22 | 2026-06-22 | 2026-10-28 |  | 8202243985 | 8202232778 | Penyelesaian Pek. PM PDM EI MA4 tahap 15 | RU6-UTL | SS-01/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 154452650 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-20 | 2026-01-09 | 2026-06-05 |  | 8202242541 | 8202232778 | Penyelesaian Pek. PM PDM EI MA4 tahap 14 | RU6-UTL | SS-01/00 | 50 | REL GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 91424300 | MA4-LIS |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-04-10 | 2026-06-11 | 2026-01-09 | 2026-06-05 |  | 8202242338 | 8202232778 | Penyelesaian Pek. PM PDM EI MA4 tahap 13 | RU6-UTL | SS-01/00 | 50 | REL GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 91424300 | MA4-LIS |  | DINDINS |  | 2026-04-13 | PT02 | 2 | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-13 | 2026-01-09 | 2026-06-05 |  | 8202241634 | 8202232778 | Penyelesaian Pek. PM PDM EI MA4 tahap 12 | RU6-UTL | SS-01/00 | 50 | REL GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 91424300 | MA4-LIS |  | DINDINS |  | 2026-03-13 | PT02 | 3 | 3 | 2026-01-09 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-09 | 2026-02-26 | 2026-02-26 | 2102364997 | 8202239290 |  | Penyehatan RSBV Area LNHT-Isom | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-09 | PM |  | 045
| K201 | 2026-02-23 | 2026-02-27 | 2026-02-18 | 2026-03-17 | 2102364555 | 8202239031 |  | Penyehatan gearbox aerator 930-ME-15 | RU2-ITP | 930-ME-15/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 7806561 | 0 | MA4-ROT |  | STEVANEKOPP |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K601 | 2026-03-13 | 2026-03-13 | 2026-03-05 | 2026-07-28 | 2102366204 | 8202241679 |  | Penyehatan 63-Z-305A/B tkdn | RU6-ITP | 63-Z-305A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 32250000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-13 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-12-30 | 2026-12-30 |  | 8202243385 | 8202242594 | Penyediaan Sewa Kendaraan Truck Cargo PT |  |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 159912012 | MA1-STA |  | DJOKOTRIONO |  | 2026-05-21 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 045
| K202 | 2026-04-07 | 2026-04-25 | 2026-03-16 | 2026-03-16 | 2102366763 | 8202242139 |  | PENURUNAN PIPING JETTY 1 SPK | RU2S-KIL | 10PL900003-A1A1/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-04 | 2026-02-23 | 2026-02-23 | 2102364840 | 8202239384 |  | Penunjukkan TG Meragukan 105-TG-904 | RU4-RFCGTO | 105TG-U105/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2102364891 | 8202239297 |  | Penunjukkan PG Meragukan 105-PG-110 | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-02 | PM |  | 045
| K401 | 2026-03-02 | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2102364890 | 8202239298 |  | Penunjukkan PG Meragukan 105-PG-109 | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-02 | PM |  | 045
| K401 | 2026-03-02 | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2102364855 | 8202239294 |  | Penunjukkan PG Meragukan 105-PG-103 | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-02 | PM |  | 045
| K401 | 2026-03-02 | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2102364854 | 8202239295 |  | Penunjukkan PG Meragukan 105-PG-102 | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-02 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-04 | 2026-02-24 | 2026-02-24 | 2102364842 | 8202239382 |  | Penunjukkan PG Meragukan 105-PG-086 | RU4-RFCGTO | 105PG-U105/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-04 | 2026-02-24 | 2026-02-24 | 2102364841 | 8202239381 |  | Penunjukkan PG Meragukan 105-PG-085 | RU4-RFCGTO | 105PG-U105/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-05 | 2026-02-23 | 2026-02-23 | 2102364763 | 8202239218 |  | Penunjukan O2 analizer maksimal 260AT001 | RU4-LOC3 | 260AT001/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | FARIZSETYANA |  |  | PT02 | 2 | 2 | 2026-03-05 | PM |  | 003
| K301 | 2026-03-10 | 2026-03-10 | 2026-01-01 | 2026-12-31 | 2102352842 | 8202241547 |  | Pengukuran Thermograp RU III | RU3-PP | 22-V-212/00 | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  |  | PT02 | 4 | 2 | 2026-01-01 | PM |  | 045
| K601 | 2026-04-20 |  | 2026-04-20 | 2026-07-22 | 2102368163 | 8202242570 |  | Pengujian Minyak Trafo | RU6-UTL | 01-PTR2-01A/00 | 50 | CRTD NMAT PRC RELR | 6ER | D16/26/B6/RT-C2H | 300000001 | 0 | MA4-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-04-20 | PM |  | 003
| K601 | 2026-02-09 | 2026-02-12 | 2026-02-09 | 2026-03-13 | 2102362244 | 8202238779 |  | Pengggantian Transmitter 31-FT-034 | RU6-HSC | 31-FT-034/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 23326900 | MA3-INT |  | ANDRIES |  | 2026-02-09 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 003
| K501 | 2026-05-26 | 2026-06-18 | 2026-05-26 | 2026-06-12 | 2102369254 | 8202243497 |  | Penggantian Wire Mata 2 untuk SPM 150 | RU5-TBL | PIPE-ON-SHORE/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 3568760 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-04-10 | 2026-04-23 | 2026-11-02 | 2026-12-30 | 2102359631 | 8202242309 |  | PENGGANTIAN VOLTAGE RELAY OHC AREA WS | RU5-UTL | BEN-BN-TB-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 5274000 | 0 | MA4-LIS |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 8 | 3 | 2026-11-02 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-11 | 2026-06-19 | 2102369895 | 8202243835 |  | Penggantian valve steam inlet 62-T-201B | RU6-UTL | 62-T-201B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 3657223 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-12-31 | 2102366187 | 8202241314 |  | Penggantian Valve Outlet Polisher 2 | RU5-UTL | D5-BV-1-2/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 9700000 | 0 | MA1-STA |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 004
| K601 | 2026-06-10 | 2026-06-10 | 2026-06-09 | 2026-08-07 | 2102369785 | 8202243734 |  | Penggantian valve inlet 055-T-103 | RU6-UTL | 055-T-103/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 20521576 | 20365769 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 3 | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-11-23 | 2102365034 | 8202239473 |  | Penggantian Valve Drain area OM 60 & NBM | RU4-TRML | 49PSV003/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 75095503 | 75095503 | MA3-STA |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 4 | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-22 | 2102369936 | 8202243833 |  | Penggantian valve CBD Boiler 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 5515896 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-12 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-27 | 2026-02-02 | 2026-12-31 | 2102358749 | 8202238622 |  | Penggantian Valve Boiler HHP 3 | RU5-UTL | HHP-3/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 4215290 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-09 | 2026-04-28 | 2102363832 | 8202241356 |  | Penggantian Valve 8"-150 Inlet B/T O15 | RU5-TBL | O-15/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 25330532 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-06-12 | 2102367322 | 8202242672 |  | Penggantian Valve 16" Ballast depan V-1 | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 84266810 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-12 | 2026-03-06 | 2026-07-29 | 2102366215 | 8202241661 |  | Penggantian Valve 1-7 22-V-109C | RU6-DHC | 22-V-109C/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 33332055 | 0 | MA2-INT |  | DANDARWANI |  | 2026-03-12 | PT02 | 6 | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365202 | 8202241408 |  | Penggantian V-BELT EA-32-01T | RU5-E15112 | EA-32-01T/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365201 | 8202241409 |  | Penggantian V-BELT EA-32-01S | RU5-E15112 | EA-32-01S/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365200 | 8202241457 |  | Penggantian V-BELT EA-32-01R | RU5-E15112 | EA-32-01R/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365188 | 8202241455 |  | Penggantian V-belt EA-32-01P | RU5-E15112 | EA-32-01P/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365185 | 8202241432 |  | Penggantian V-Belt EA-32-01K | RU5-E15112 | EA-32-01K/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365183 | 8202241406 |  | Penggantian V-BELT EA-32-01D | RU5-E15112 | EA-32-01D/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365182 | 8202241411 |  | Penggantian V-Belt EA-32-01A | RU5-E15112 | EA-32-01A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-03 | 2026-03-06 | 2026-02-26 | 2026-08-30 | 2102364969 | 8202239376 |  | Penggantian V-belt EA-31-21G |  |  | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 4481344 | 0 | MA3-ROT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 045
| K501 | 2026-03-03 |  | 2026-03-03 | 2026-08-30 | 2102365174 | 8202239379 |  | Penggantian V-belt EA-2-12D | RU5-E15112 | EA-2-12B/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 3259628 | 0 | MA3-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-03-03 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365187 | 8202241458 |  | Penggantian V-belt EA-32-01N | RU5-E15112 | EA-32-01N/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 9999444 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K601 | 2026-03-11 | 2026-04-15 | 2026-02-06 | 2026-08-21 |  | 8202241577 |  | Penggantian Transmitter 38-TI-016 A/B | RU6-POC | 38-F-101/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/XX/B6/RT-C2NH | 0 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-15 | PT02 | 1 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-15 | 2102368943 | 8202244011 |  | Penggantian Transmitter 37-PT-016 B/D | RU6-POC | 37-F-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K601 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-11-06 | 2102368832 | 8202243094 |  | Penggantian transmitter 32-PI-096A | RU6-HSC | 32-C-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 27478635 | 0 | MA3-INT |  | DANDARWANI |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-15 | 2026-04-02 | 2026-07-13 | 2102367112 | 8202242041 |  | Penggantian Transmitter 32-FT-032 | RU6-HSC | 32-FT-032/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 23326900 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-15 | PT02 | 5 | 3 | 2026-04-02 | PM |  | 003
| K601 | 2026-02-09 | 2026-02-09 | 2026-02-03 | 2026-03-09 | 2102351021 | 8202238776 |  | Penggantian Transmitter 25-FT-067 | RU6-HSC | 25-FT-067/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-02-09 | PT02 | 5 | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-03-13 | 2102350998 | 8202238772 |  | Penggantian Transmitter 25-FT-062 | RU6-HSC | 25-FT-062/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-02-09 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-14 | 2026-04-09 | 2026-04-09 | 2102367658 | 8202242368 |  | Penggantian Transmitter 152FT020 | RU4-RFCC | 152FT020/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-04-14 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-17 | 2026-06-12 | 2026-12-04 | 2102361811 | 8202243836 |  | Penggantian Transmitter 13-PDT-296 | RU6-DHC | 13-PDT-296/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2 | 0 | MA2-INT |  | DANDARWANI |  | 2026-06-17 | PT02 | 2 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-06 | 2026-04-09 | 2027-03-18 | 2102367681 | 8202243010 |  | Penggantian Trafo Stabilizer SS-14B | RU6-RCC | SS-14B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 2 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 004
| K601 | 2026-05-06 | 2026-05-06 | 2026-04-09 | 2028-02-04 | 2102367680 | 8202243014 |  | Penggantian Trafo Stabilizer SS-14A | RU6-RCC | SS-14A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 2 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 004
| K601 | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-12-15 | 2102367804 | 8202242353 |  | penggantian Trafo stabilizer di SS#21,22 | RU6-ITP | 42-LPB-SS21/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 22180 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-15 | PT02 | 6 | 3 | 2026-04-13 | PM |  | 004
| K201 | 2026-04-14 | 2026-05-19 | 2026-04-14 | 2026-04-20 | 2102367816 | 8202242429 |  | Penggantian Torque Tube 301-ON-D-2 | RU2-HSC | 301-ON-D-2/00 | 60 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 51100000 | 51100000 | MA2-INT |  | ADEMULYADI |  | 2026-05-08 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 004
| K601 | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-09-15 | 2102367178 | 8202242773 |  | Penggantian TI analog 43-TI-001 | RU6-ITP | 43-SPM-HPU-B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 12144 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-28 | PT02 | 4 | 3 | 2026-04-27 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-03-31 | 2102364883 | 8202239113 |  | Penggantian Throat Bushing Pompa 15-P-10 | RU6-RCC | 15-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | ABDULAZIZ70 |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K201 | 2026-04-22 | 2026-06-15 | 2026-04-22 | 2026-04-28 | 2102365180 | 8202242665 |  | Penggantian Thermodial 200-C-1 B | RU2-HSC | 200-C-1B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 4420000 | 4420000 | MA2-INT |  | NURFADHILLA |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-22 | PM |  | 005
| K401 | 2026-04-13 | 2026-04-14 | 2026-04-09 | 2026-04-09 | 2102367683 | 8202242370 |  | Penggantian Thermocouple 101TI761 COB | RU4-RFCC | 101F503/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | YMOHAMMAD |  |  | PT02 | 8 | 2 | 2026-04-14 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-08-05 | 2102361480 | 8202244002 |  | Penggantian Thermal OL Relay Mtr 31P108B | RU6-HSC | 31-P-108B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 434187 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-22 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-12-09 | 2102367490 | 8202243926 |  | Penggantian Temperature Local 31-TI-104B | RU6-HSC | 31-K-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-04-21 |  | 2026-04-08 | 2026-04-08 | 2102367564 | 8202242640 |  | Penggantian Temperature Indicator 49T2 |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  |  |  |  | PT02 | 3 | 2 | 2026-04-08 | PM |  | 045
| K601 | 2026-06-11 | 2026-06-12 | 2026-06-11 | 2026-12-03 | 2102366706 | 8202243766 |  | Penggantian temp. indikator 52-TI-217E | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16105 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K601 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-03-27 | 2102361322 | 8202239009 |  | Penggantian Temp Transmitter 39-TI-002 | RU6-POC | 39-K-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2 | 34640000 | 0 | MA3-INT |  | ANDRIES |  | 2026-02-23 | PT02 | 5 | 3 | 2026-02-23 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-12 | 2026-06-11 | 2026-12-03 | 2102362385 | 8202243761 |  | Penggantian Temp Transmitter 35-TI-013B | RU6-POC | 35-R-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 4 | 3 | 2026-06-11 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-12 | 2026-06-11 | 2026-12-03 | 2102362346 | 8202243759 |  | Penggantian Temp Transmitter 34-TI-049 | RU6-POC | 34-C-104/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 5 | 3 | 2026-06-11 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-12 | 2026-06-11 | 2026-12-03 | 2102361385 | 8202243760 |  | Penggantian Temp Transmitter 32-TI-344 | RU6-HSC | 32-A-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 5 | 3 | 2026-06-11 | PM |  | 003
| K401 | 2026-05-26 |  | 2026-05-04 | 2026-05-04 | 2102368667 | 8202243521 |  | Penggantian Temp Indikator 37P552B |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  |  |  |  | PT02 | 5 | 2 | 2026-05-04 | PM |  | 045
| K501 | 2026-06-09 | 2026-06-11 | 2026-06-09 | 2026-07-22 | 2102369813 | 8202243721 |  | Penggantian tali 6 & 10 SPM 150.000 DWT | RU5-TBL | PIPE-ON-SHORE/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FLNH | 36661630 | 0 | MA4-STA |  | BERNANDOP |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-04-20 | 2026-05-19 | 2026-04-20 | 2026-05-05 | 2102368155 | 8202242590 |  | Penggantian Tachometer Turbine 56-P-101E | RU6-UTL | 56-P-101E/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 48001320 | 48000000 | MA4-ROT |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-05-05 | 2102368154 | 8202242589 |  | Penggantian Tachometer Turbine 56-P-101B | RU6-UTL | 56-P-101B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 48001320 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-05-05 | 2102368153 | 8202242588 |  | Penggantian Tachometer Turbine 56-P-101A | RU6-UTL | 56-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 48001320 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-06-08 |  | 2026-06-04 | 2026-06-04 | 2102369633 | 8202243690 |  | Penggantian Tabung Sample 14AT500 | RU4-FOC1 | 14R650/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-04 | PM |  | 003
| K501 | 2026-02-25 | 2026-03-06 | 2026-02-20 | 2026-12-31 | 2102364663 | 8202239155 |  | Penggantian Steam Trap Area SWD |  | FA-201/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/NR-C2H | 120269865 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 004
| K601 | 2026-05-06 | 2026-05-06 | 2026-04-08 | 2027-03-18 | 2102367669 | 8202243007 |  | Penggantian Stabilizer Trafo di SS15 | RU6-HSC | 11-LPB-01/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 2 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-05-06 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-04-15 | 2102364825 | 8202239083 |  | Penggantian spring T&T valve 52-B-101D | RU6-UTL | 52-B-101D/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 13871802 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-08 | 2026-06-03 | 2026-11-25 | 2102368234 | 8202243598 |  | Penggantian Splitter Signal BMS 52B101E | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16105 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-07-31 | 2102366782 | 8202241969 |  | Penggantian Solenoid Valve 33-XV-098 | RU6-HSC | 33-XV-098/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 155740000 | 0 | MA3-INT |  | DANDARWANI |  | 2026-03-31 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-05-08 | 2026-05-11 | 2026-05-08 | 2026-11-18 | 2102361563 | 8202243095 |  | Penggantian Solenoid Valve 33-XV-083 | RU6-HSC | 33-V-105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 57000000 | 0 | MA3-INT |  | DANDARWANI |  | 2026-05-11 | PT02 | 5 | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-07-13 | 2102368235 | 8202242652 |  | Penggantian solenoid 52-XV-206D | RU6-UTL | 52-B-101D/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 45955719 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K601 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-09-10 | 2102368233 | 8202242653 |  | Penggantian solenoid 52-XV-206B | RU6-UTL | 52-XV-206B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 15328473 | 15316329 | MA4-INT |  | DANDARWANI |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-12-11 | 2102362290 | 8202243932 |  | Penggantian Solenoid 16-XV-103 | RU6-RCC | 16-K-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2 | 0 | MA1-INT |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-12-08 | 2102362195 | 8202243620 |  | Penggantian Solenoid 052-XV-911A/910A | RU6-UTL | 052-XV-911A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 17165 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 003
| K501 | 2026-03-16 | 2026-06-02 | 2026-08-16 | 2026-08-30 | 2102366721 | 8202241734 |  | Penggantian Sight Glass Pompa G-2-04 | RU5-E15112 | G-2-04/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 4533030 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-08-16 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-03-10 | 2102364673 | 8202238990 |  | Penggantian Shut off valve 52-XV-206B | RU6-UTL | 52-B-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2 | 3827558 | 3825974 | MA4-INT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K401 | 2026-03-17 | 2026-03-17 | 2026-03-13 | 2026-03-13 | 2102366691 | 8202241802 |  | Penggantian Sensor, Proximitor, Ext Cabl | RU4-RFCUTL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-17 | PM |  | 045
| K401 | 2026-03-17 | 2026-03-17 | 2026-03-13 | 2026-03-13 | 2102366690 | 8202241803 |  | Penggantian Sensor, Proximitor, Ext Cabl | RU4-RFCUTL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-17 | PM |  | 045
| K601 | 2026-05-25 | 2026-05-25 | 2026-05-08 | 2026-06-05 | 2102368900 | 8202243457 |  | Penggantian Sensor Door Zone Levelling | RU6-HSC | 32-R-101-UP6/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 3 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-05-25 | PT02 | 5 | 3 | 2026-05-08 | PM |  | 003
| K701 | 2026-03-26 | 2026-03-26 | 2026-12-30 | 2026-12-30 | 2102366938 | 8202241879 |  | Penggantian Sensor Debit Alat Sparing |  |  | 50 | REL GMPS MACM PRC SETC | 7RT | D17/26/B6/NR-4-D1H | 114000000 | 114000000 | MA-LINT |  | RIZKAANDIKAP |  | 2026-03-26 | PT02 | 6 | 3 | 2026-12-30 | PM |  | 003
| K401 | 2026-03-17 | 2026-03-17 | 2026-03-13 | 2026-03-13 | 2102366629 | 8202241804 |  | Penggantian Sensor 152AI002 | RU4-RFCUTL | 152AT002/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-17 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-20 | 2026-02-02 | 2026-02-02 | 2102356428 | 8202238713 |  | Penggantian Rotameter Reaction Furnace | RU4-SRU | 93FI103/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | FARIZSETYANA |  |  | PT02 | 4 | 2 | 2026-02-20 | PM |  | 003
| K401 | 2026-02-09 | 2026-04-27 | 2026-02-05 | 2026-12-30 | 2102361237 | 8202238802 |  | Penggantian relay prteksi 80SS21&60SS21 |  |  | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 100000 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 | 5 | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-05-06 | 2026-05-08 | 2026-05-05 | 2026-12-29 | 2102368713 | 8202243025 |  | Penggantian REJ 42" Suction 56-P-101D | RU6-UTL | 56-P-101D/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 164770454 | 157990458 | MA4-STA |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-12 | 2026-06-19 | 2102369946 | 8202243925 |  | Penggantian REJ 34" discharge 56-P-101D | RU6-UTL | 56-P-101D/00 | 50 | REL CSER MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 119851308 | 0 | MA4-STA |  | HARSARIZANO |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-12-10 | 2102369585 | 8202243891 |  | Penggantian Regulator Control Pneumix | RU6-RCC | 15-A-107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 62700000 | 0 | MA1-INT |  | DANDARWANI |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-20 | 2026-05-19 | 2026-08-18 | 2102368190 | 8202243306 |  | Penggantian Pump Assy 34-P-101B | RU6-POC | 34-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 97400000 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 004
| K401 | 2026-04-15 | 2026-04-23 | 2026-04-15 | 2026-10-13 | 2102367692 | 8202242476 |  | penggantian pulley motor 11E50SM | RU4-FOC1 | 11E50SM/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 15175000 | 15175000 | MA1-LIS |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-05-25 |  | 2026-05-18 | 2026-05-18 | 2102369139 | 8202243474 |  | Penggantian prover FT-6792 PertamaxTurbo |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  |  |  |  | PT02 | 5 | 2 | 2026-05-18 | PM |  | 045
| K601 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-07-27 | 2102368016 | 8202242603 |  | Penggantian Pressure Transmitt 31-PT-013 | RU6-HSC | 31-PT-013/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-08-12 | 2102362273 | 8202241746 |  | Penggantian Pressure Switch 52-PSHH-212B | RU6-UTL | 52-B-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 54264908 | 0 | MA4-INT |  | DANDARWANI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K601 | 2026-03-17 | 2026-03-31 | 2026-03-31 | 2026-07-17 | 2102364045 | 8202241813 |  | Penggantian Pressure switch 42-PSL-007 | RU6-ITP | 42-P-101A/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 80709240 | 26900000 | MA4-INT |  | DANDARWANI |  | 2026-03-31 | PT02 | 1 | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-08-11 | 2102361282 | 8202241784 |  | Penggantian Pressure Switch 055-PSL-501 | RU6-UTL | 055-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 8845477 | 0 | MA4-INT |  | DANDARWANI |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K201 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-27 | 2102368183 | 8202242611 |  | Penggantian Press Guage 212-H1 Rusak | RU2-HCC | 212-H-1/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 15000000 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 005
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-11 | 2102362305 | 8202244031 |  | Penggantian Press Gauge 31-PI-102 A | RU6-HSC | 31-K-101A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-22 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-09-01 | 2102367448 | 8202242169 |  | Penggantian Press Gauge 31-PI-101A | RU6-HSC | 31-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-09-01 | 2102367446 | 8202242170 |  | Penggantian Press Gauge 31-PI-101 C | RU6-HSC | 31-K-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K201 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2102367870 | 8202242428 |  | Penggantian Press Gauge 301-PCV-241 | RU2-HSC | 301-PCV-241/00 | 50 | CRTD CSER MACM PRC | 2IR | D12/26/B6/RT-D2H | 1984600 | 0 | MA2-INT |  | DONITGN |  |  | PT02 | 5 | 2 | 2026-04-14 | PM |  | 005
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-09 | 2102361544 | 8202244034 |  | Penggantian Press Diff Gauge OCU | RU6-POC | 36-C-101/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 10 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-22 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-07-14 | 2102367210 | 8202242068 |  | Penggantian Positioner CV 15-FV-027 | RU6-RCC | 15-FV-027/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-15 | 2026-04-02 | 2026-07-13 | 2102366944 | 8202242042 |  | Penggantian Positioner Control Valve PSA | RU6-DHC | 22-V-109B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 141000000 | 0 | MA2-INT |  | DANDARWANI |  | 2026-04-15 | PT02 | 5 | 3 | 2026-04-02 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-12-08 | 2102362732 | 8202243824 |  | Penggantian Positioner 50-PC-004B | RU6-UTL | 50-PV-004B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 32737 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-03-17 | 2026-03-31 | 2026-03-17 | 2026-05-11 | 2102366696 | 8202241812 |  | Penggantian Positioner 33-FV-032 | RU6-HSC | 33-FV-032/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 60875000 | 0 | MA3-INT |  | DANDARWANI |  | 2026-03-31 | PT02 | 5 | 3 | 2026-03-17 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-14 | 2026-04-09 | 2026-04-09 | 2102367657 | 8202242369 |  | Penggantian Positioner 152PV020 | RU4-RFCUTL | 152PV020/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-04-14 | PM |  | 003
| K601 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-11-16 | 2102369179 | 8202243334 |  | Penggantian Positioner 15-PV-501 | RU6-RCC | 15-V-106/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 60875000 | 0 | MA1-INT |  | DANDARWANI |  | 2026-05-20 | PT02 | 1 | 3 | 2026-05-20 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-06-25 | 2102368044 | 8202242523 |  | Penggantian Positioner 15-FV-008 | RU6-RCC | 15-FV-008/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 48236464 | 0 | MA1-INT |  | ANDRIES |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-09 | 2026-04-07 | 2026-04-21 | 2102364088 | 8202242148 |  | Penggantian Pompa 55-A-101C | RU6-UTL | 55-A-101C/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 98320590 | 98319270 | MA4-ROT |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-05 | 2026-07-28 | 2102366209 | 8202241522 |  | Penggantian Pipeline Area 42 (RKAP 2023) | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 310503100 | 310503100 | MA4-STA |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-05-29 | 2026-06-15 | 2026-05-29 | 2026-09-29 | 2102369432 | 8202243547 |  | Penggantian Pipa Naptha | RU6-ITP | 42-T-107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 684627 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-15 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 004
| K501 | 2026-04-02 | 2026-04-13 | 2026-11-02 | 2026-11-02 | 2102364589 | 8202242024 |  | Penggantian Pinion Gear Mixer Tanki | RU5-TBL | 101-MI-1E2/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 228200212 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-11-02 | PM |  | 003
| K501 | 2026-04-02 | 2026-04-13 | 2026-11-02 | 2026-11-02 | 2102364588 | 8202242025 |  | Penggantian Pinion Gear Mixer Tanki | RU5-TBL | 101-MI-1B2/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 228200212 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-11-02 | PM |  | 003
| K401 | 2026-03-06 | 2026-05-06 | 2026-03-06 | 2026-08-31 | 2102364958 | 8202241332 |  | PENGGANTIAN PILOT IGNITOR DFAH | RU4-RFCC | 101F501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-LIS |  | WAHYUCATUR |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-10-07 | 2102369329 | 8202243493 |  | Penggantian PI 23-PI-011 | RU6-HSC | 23-V-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 4468700 | 4468700 | MA1-INT |  | DANDARWANI |  | 2026-05-25 | PT02 | 5 | 3 | 2026-05-25 | PM |  | 003
| K701 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2102368006 | 8202242521 |  | Penggantian PI 2-P-01A | RU7-NHT | 2-P-01A/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 1726000 | 0 | MA-ROT |  | YAYANHER |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 005
| K701 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2102368005 | 8202242520 |  | Penggantian PI 1-P-02A | RU7-CDU | 1-P-02A/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 1687938 | 0 | MA-ROT |  | YAYANHER |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 005
| K701 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2102368007 | 8202242522 |  | Penggantian PI 1-E-31 | RU7-CDU | 1-E-31/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 1687938 | 0 | MA-ROT |  | YAYANHER |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 005
| K201 | 2026-02-24 | 2026-02-24 | 2026-05-05 | 2026-05-05 | 2102364695 | 8202239108 |  | Penggantian Parts Pompa | RU2-HCC | 211-P-34B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2 | 0 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-02-24 | PT02 | 5 | 3 | 2026-05-05 | PM |  | 003
| K601 | 2026-06-23 |  | 2026-06-19 | 2026-10-30 | 2102370165 | 8202244043 |  | Penggantian oli trafo 01-PTR1-01A | RU6-UTL | 01-PTR1-01A/00 | 50 | CRTD MACM PRC | 6ER | D16/26/B6/RT-C2H | 142432276 | 0 | MA4-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-06-19 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-04 | 2026-04-24 | 2026-04-24 | 2102368352 | 8202242949 |  | Penggantian Needle Valve 1/2" 93HV184 | RU4-SRU | 93HV184/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-05-04 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-08-12 | 2102368120 | 8202242624 |  | Penggantian Mouse Panel DCS | RU6-RCC | OS-14/00 | 50 WAMA | REL CSER PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DEATASAP |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-04-23 | 2026-04-23 | 2026-03-10 | 2026-12-16 | 2102366467 | 8202242679 |  | Penggantian Motor Sootblower Boiler UTL | RU6-UTL | 52-B-101A/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 24560 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-23 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-05-22 | 2026-06-12 | 2026-05-22 | 2026-10-29 | 2102369282 | 8202243428 |  | Penggantian motor soot blower 52-B-101E | RU6-UTL | 52-B-101E-K2/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 14258 | 0 | MA4-LIS |  | DINDINS |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-22 | PM |  | 003
| K601 | 2026-05-22 | 2026-06-12 | 2026-05-22 | 2026-10-29 | 2102369281 | 8202243427 |  | Penggantian motor soot blower 52-B-101D | RU6-UTL | 52-B-101D-K2/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 14258 | 0 | MA4-LIS |  | DINDINS |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-22 | PM |  | 003
| K601 | 2026-05-22 | 2026-06-12 | 2026-05-22 | 2026-10-29 | 2102369280 | 8202243426 |  | Penggantian motor soot blower 52-B-101C | RU6-UTL | 52-B-101C-K2/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 14258 | 0 | MA4-LIS |  | DINDINS |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-22 | PM |  | 003
| K601 | 2026-05-22 | 2026-06-12 | 2026-05-22 | 2026-10-29 | 2102369269 | 8202243425 |  | Penggantian motor soot blower 52-B-101B | RU6-UTL | 52-B-101B-K2/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 14258 | 0 | MA4-LIS |  | DINDINS |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-22 | PM |  | 003
| K601 | 2026-05-22 | 2026-06-12 | 2026-05-21 | 2026-10-28 | 2102369270 | 8202243424 |  | Penggantian motor soot blower 52-B-101A | RU6-UTL | 52-B-101A-K2/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 14260 | 0 | MA4-LIS |  | DINDINS |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-21 | PM |  | 003
| K601 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-10-23 | 2102362773 | 8202242676 |  | Penggantian Motor Servo 32-P-111B | RU6-HSC | 32-P-111B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-23 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-03-06 | 2026-05-25 | 2026-03-06 | 2026-08-31 | 2102364038 | 8202241328 |  | Penggantian motor 21P-7AM | RU4-LOC1 | 21P7AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-LIS |  | WAHYUCATUR |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-04-09 | 2026-04-28 | 2026-04-08 | 2026-05-29 | 2102367637 | 8202242269 |  | Penggantian Module Digital Output PLCESD | RU6-HSC | OS-17/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 246920180 | 246920180 | MA3-INT |  | DANDARWANI |  | 2026-04-15 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-05-13 | 2102366791 | 8202241781 |  | Penggantian Modul Sinyal Boiler E | RU6-UTL | 52-B-101E/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 38029688 | 0 | MA4-INT |  | DANDARWANI |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-12-11 | 2102361562 | 8202243933 |  | Penggantian Modul flowmeter Transmitter | RU6-UTL | 70-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 32737 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-18 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-06 | 2026-08-30 | 2102366158 | 8202241387 |  | Penggantian Membran coupling G-3-01A | RU5-E15112 | G-3-01A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 79380000 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-07-06 | 2102367793 | 8202243299 |  | Penggantian Membran Coupling 62-P-201C | RU6-UTL | 62-P-201C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3962 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-21 | 2026-05-06 | 2026-10-05 | 2102368752 | 8202243047 |  | Penggantian Mem Coupling Pump 056-P-101A | RU6-UTL | 056-P-101A/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 193328202 | 96657500 | MA4-ROT |  | DANDARWANI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K701 | 2026-02-20 | 2026-02-20 | 2026-12-30 | 2026-12-30 | 2102364596 | 8202238987 |  | Penggantian Mecseal 1-P-12A | RU7-CDU | 1-P-12A/00 | 50 | REL MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 86276000 | 0 | MA-ROT |  | YAYANHER |  | 2026-02-20 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 003
| K701 | 2026-03-28 |  | 2026-01-02 | 2026-01-02 | 2102366995 | 8202241912 |  | Penggantian MechSeal 3-P-02 B | RU7-CRU | 3-P-02B/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-4-D4H | 49739075 | 0 | MA-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 005
| K401 | 2026-05-25 | 2026-06-21 | 2026-06-19 | 2026-12-30 |  | 8202243444 | 8202242530 | Penggantian Mech Seal Complete 90P401B | RU4-SRU | 90P401B/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 45217450 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-05-25 | 2026-06-21 | 2026-06-19 | 2026-12-30 |  | 8202243435 | 8202241703 | Penggantian Mech Seal Assy IB 46P101B | RU4-FOC1 | 11P8A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 101160200 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-05-25 | 2026-06-21 | 2026-06-19 | 2026-12-30 |  | 8202243456 | 8202240915 | Penggantian Mech Seal Assy 47P102B | RU4-TRML | 47P102B/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 122734900 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102366583 | 8202242202 |  | Penggantian Mech Seal 34-P-107B | RU6-POC | 34-P-107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 86284566 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 4 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102366582 | 8202242201 |  | Penggantian Mech Seal 34-P-107A | RU6-POC | 34-P-107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 86284566 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 4 | 3 | 2026-04-08 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-12 | 2102363871 | 8202242855 |  | Penggantian Mech Seal 100-P-11A | RU2-HSC | 100-P-11A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 39945000 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K701 | 2026-05-31 |  | 2026-06-02 | 2026-06-02 | 2102369490 | 8202243551 |  | Penggantian Mech Seal 1-P-03 A/B | RU7-CDU | 1-P-03A/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 41582000 | 0 | MA-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-02 | PM |  | 005
| K701 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2102369491 | 8202243595 |  | Penggantian Mech Seal 1-P-03 | RU7-CDU | 1-P-03B/00 | 50 | CRTD NMAT PRC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 005
| K601 | 2026-06-05 | 2026-06-08 | 2026-06-05 | 2026-07-28 | 2102369662 | 8202243660 |  | Penggantian MCB 2 pole 20A di 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 4752 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-05 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-09 | 2026-04-07 | 2026-04-07 | 2102367530 | 8202242165 |  | Penggantian Material SPD 102-UV-102/103 | RU4-RFCC | 102UV102/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | FARIZSETYANA |  |  | PT02 | 8 | 2 | 2026-04-09 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2102368445 | 8202242851 |  | Penggantian Material Bearing | RU2-HCC | 211-P-9B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 19907630 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-12 | 2102368446 | 8202242857 |  | Penggantian Material Bearing | RU2-HCC | 211-P-9C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 19907907 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368447 | 8202242859 |  | Penggantian Material Bearing | RU2-HCC | 212-P-9A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 19907907 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-12 | 2102368448 | 8202242861 |  | Penggantian Material Bearing | RU2-HCC | 212-P-9B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 19907907 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-04-27 | 2102368449 | 8202242862 |  | Penggantian Material Bearing | RU2-HCC | 212-P-9C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 19907630 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368460 | 8202242863 |  | Penggantian Material Bearing | RU2-HCC | 211-P-4A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 38670549 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368461 | 8202242865 |  | Penggantian Material Bearing | RU2-HCC | 211-P-4B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 38670549 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368462 | 8202242866 |  | Penggantian Material Bearing | RU2-HCC | 212-P-4A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 38670549 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368464 | 8202242867 |  | Penggantian Material Bearing | RU2-HCC | 212-P-4B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 38670549 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368465 | 8202242868 |  | Penggantian Material Bearing | RU2-HCC | 701-P-4A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 46824907 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368466 | 8202242869 |  | Penggantian Material Bearing | RU2-HCC | 701-P-4B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 46824907 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368467 | 8202242870 |  | Penggantian Material Bearing | RU2-HCC | 702-P-4A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 46824722 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-04-27 | 2026-05-07 | 2102368468 | 8202242871 |  | Penggantian Material Bearing | RU2-HCC | 702-P-4B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 46824907 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-05-20 | 2026-05-22 | 2026-06-02 | 2026-06-03 | 2102368502 | 8202243323 |  | Penggantian Material Bearing | RU2-HCC | 212-P-13BR/01 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6773438 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-07-01 | 2026-07-02 | 2102368389 | 8202243351 |  | Penggantian Material Bearing | RU2-HCC | 211-P-13AR/01 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 353419038 | 0 | MA2-ROT |  | DJOKOTRIONO |  | 2026-05-22 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-08 | 2026-06-03 | 2026-11-25 | 2102361391 | 8202243606 |  | Penggantian Magnetic Level Glass 55LI105 | RU6-UTL | 55-A-101A-V4/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16105 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-04-10 | 2026-05-07 | 2026-10-30 | 2027-06-29 | 2102364585 | 8202242315 |  | Penggantian LV Switchgear 440V SS 6 & 10 | RU5-UTL | 41-R-SS-10-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 2657400000 | 0 | MA4-LIS |  | YUSUFM |  | 2026-05-07 | PT02 | 8 | 3 | 2026-10-30 | PM |  | 004
| K401 | 2026-03-26 | 2026-04-13 | 2026-03-17 | 2026-03-17 | 2102366802 | 8202241895 |  | Penggantian LT magnetic 260LT145 | RU4-LOC3 | 260LT145/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-04-13 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-13 | 2026-03-17 | 2026-03-17 | 2102366804 | 8202241894 |  | Penggantian LT magnetic 260LT142 | RU4-LOC3 | 260LT142/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-04-13 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-13 | 2026-03-17 | 2026-03-17 | 2102366800 | 8202241893 |  | Penggantian LT magnetic 260LT051 | RU4-LOC3 | 260LT051/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-04-13 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-13 | 2026-03-17 | 2026-03-17 | 2102366801 | 8202241892 |  | Penggantian LT magnetic 260LT045 | RU4-LOC3 | 260LT045/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-04-13 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-09 | 2026-03-17 | 2026-03-17 | 2102366803 | 8202241891 |  | Penggantian LT magnetic 260LT042 | RU4-LOC3 | 260LT042/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | FARIZSETYANA |  |  | PT02 | 5 | 2 | 2026-04-09 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-05-06 | 2102368169 | 8202242630 |  | Penggantian Loader Valve 22-K-101B (MIV) | RU6-DHC | 22-K-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 79177000 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K501 | 2026-04-08 | 2026-04-22 | 2026-03-30 | 2026-12-31 | 2102367014 | 8202242222 |  | Penggantian Line Oil Cooler STG 1.6 | RU5-UTL | TG-6-LK-PIPE-ST/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 91842504 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-04-14 | PT02 | 2 | 3 | 2026-03-30 | PM |  | 004
| K701 | 2026-05-14 | 2026-05-14 | 2026-05-18 | 2026-05-18 | 2102369077 | 8202243204 |  | Penggantian Line Kondensat BFW SC-170 |  |  | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D2H | 17450000 | 0 | MA-ROT |  | YAYANHER |  | 2026-05-14 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 005
| K601 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2102367438 | 8202242127 |  | Penggantian Line Drain 37-XV-073B | RU6-POC | 37-XV-073B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2816935 | 1038750 | MA3-STA |  | DANDARWANI |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K501 | 2026-04-08 | 2026-04-14 | 2026-03-30 | 2026-12-31 | 2102367015 | 8202242226 |  | Penggantian Line Air Cooler STG 1.6 | RU5-UTL | TG-6-LK-PIPE-ST/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/26/B6/NR-C2H | 216899978 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-04-14 | PT02 | 2 | 3 | 2026-03-30 | PM |  | 004
| K401 | 2026-06-02 |  | 2026-05-25 | 2026-05-25 | 2102369336 | 8202243573 |  | Penggantian Limit Switch 140UV011 | RU4-GTO | 140UV014/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K601 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-07-10 | 2102368411 | 8202243709 |  | Penggantian LG Magnetic 34-LG-038 | RU6-POC | 34-V-108/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 125573764 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-09 | PT02 | 5 | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-08-24 | 2102367461 | 8202242121 |  | Penggantian Level Trasnmitter 14-LT-011 | RU6-DHC | 14-LT-011/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 81296000 | 0 | MA2-INT |  | DANDARWANI |  | 2026-04-07 | PT02 | 4 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-08 | 2026-06-03 | 2026-11-25 | 2102367704 | 8202243604 |  | Penggantian Level Trasmitter 56-LT-001B | RU6-UTL | 56-LT-001B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16105 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-08-24 | 2102367462 | 8202242124 |  | Penggantian Level Trasmitter 12-LT-806 | RU6-DHC | 12-LT-806/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 81296000 | 0 | MA2-INT |  | DANDARWANI |  | 2026-04-07 | PT02 | 4 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-03-11 | 2026-03-12 | 2026-02-06 | 2026-04-02 | 2102362697 | 8202241573 |  | Penggantian Level Transmitter 38-LT-002 | RU6-POC | 38-V-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/XX/B6/RT-C2NH | 39095196 | 0 | MA3-INT |  | DANDARWANI |  | 2026-03-12 | PT02 | 6 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-10-21 | 2102365774 | 8202242633 |  | Penggantian Level Transmitter 33-LT-023 | RU6-HSC | 33-LT-023/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-11-26 | 2102368683 | 8202243626 |  | Penggantian Level Transmitter 33-LT-005 | RU6-HSC | 33-LT-005/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-08 | 2026-06-04 | 2026-11-26 | 2102361906 | 8202243616 |  | Penggantian Level Transmitter 055-LT-512 | RU6-UTL | 055-LT-511/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16105 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 003
| K201 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2102367721 | 8202243421 |  | Penggantian Level Glass 301-ON-D-2 | RU2-HSC | 301-ON-D-2/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/26/B6/NR-D2H | 780750 | 0 | MA2-STA |  | CHANRARD |  |  | PT02 | 5 | 2 | 2026-05-22 | PM |  | 003
| K601 | 2026-06-09 | 2026-06-18 | 2026-06-09 | 2026-12-01 | 2102361810 | 8202243717 |  | Penggantian LCL CTRL Selector 42-MOV-036 | RU6-ITP | 42-T-104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16105 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-18 | PT02 | 2 | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-25 | 2026-05-21 | 2026-11-17 | 2102369059 | 8202243360 |  | Penggantian LCD Transmitter 42-LT-071 | RU6-ITP | 42-LT-071/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16104 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-25 | PT02 | 6 | 3 | 2026-05-21 | PM |  | 003
| K601 | 2026-03-10 | 2026-05-18 | 2026-03-10 | 2026-05-06 | 2102365014 | 8202241508 |  | Penggantian LCD display 11-LT-024 | RU6-HSC | 11-LT-024/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 81296000 | 81296000 | MA1-INT |  | AHMADAKHYAR |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-05-26 | 2026-05-29 | 2026-05-26 | 2026-07-13 | 2102368469 | 8202243530 |  | Penggantian Lampu PJU Area Unit 14 | RU6-DHC | SHELTER-14K101/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 12310000 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-05-29 | PT02 | 4 | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-06-09 | 2102364605 | 8202238981 |  | Penggantian lampu penerangan area UTL | RU6-UTL | 50-DS-001A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2 | 8712 | 0 | MA4-LIS |  | DINDINS |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-03-05 | 2026-04-29 | 2026-03-03 | 2026-05-19 | 2102365258 | 8202239543 |  | Penggantian lampu penerangan area UTL | RU6-UTL | 53-RREC-001/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 116808802 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-24 | 2026-04-24 | 2026-04-21 | 2026-07-17 | 2102368213 | 8202242710 |  | Penggantian Lampu Penerangan Area RCC | RU6-RCC | 15-R-REGEN/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 32700000 | 32700000 | MA1-LIS |  | DANDARWANI |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-21 | 2026-04-09 | 2026-07-23 | 2102367733 | 8202242289 |  | Penggantian lampu mercury ke LED | RU6-POC | 37-C-101/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 15200000 | 0 | MA3-LIS |  | DINDINS |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K601 | 2026-03-16 | 2026-04-08 | 2026-03-16 | 2026-08-12 | 2102366698 | 8202241776 |  | Penggantian Lampu Menara Jety | RU6-ITP | 41-UPS3-01/00 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 828854 | 816446 | MA4-LIS |  | DINDINS |  | 2026-03-17 | PT02 | 6 | 3 | 2026-03-16 | PM |  | 003
| K601 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-07-28 | 2102368238 | 8202242668 |  | Penggantian Lampu HPLN area STG | RU6-UTL | SHELTER-STG/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1368927 | 1360743 | MA4-LIS |  | DANDARWANI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-22 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-04-28 | 2026-08-04 | 2102368534 | 8202243764 |  | Penggantian lampu di area DTU | RU6-HSC | 24-C-101/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 3996000 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-06-11 | PT02 | 5 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-03-05 | 2026-04-29 | 2026-03-05 | 2026-05-11 | 2102366146 | 8202239582 |  | Penggantian Lampu area Salamdarma | RU6-UTL | 53-LPB-WF/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 88970280 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-29 | PT02 | 5 | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-23 | 2026-03-06 | 2026-12-22 | 2026-12-30 | 2102364686 | 8202239008 |  | Penggantian Lampu 3C Rumah K-3-02ABC | RU5-E15112 |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 223188420 | 0 | MA3-LIS |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 8 | 3 | 2026-12-22 | PM |  | 045
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-12 | 2026-05-12 | 2102368994 | 8202243187 |  | Penggantian Kerangan Gland Packing 32-PS | RU6-HSC | 32-PSV-120/00 | 50 | REL CSER MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 5455993 | 0 | MA3-STA |  | DANDARWANI |  | 2026-05-13 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-05-25 | 2026-05-25 | 2026-04-07 | 2026-12-31 | 2102367525 | 8202243433 |  | Penggantian Kaca Peep Hole Boiler HHP 6 | RU5-UTL | HHP-6/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 4 | 0 | MA1-STA |  | MANKURNIAWAN |  | 2026-05-25 | PT02 | 2 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-03-05 | 2026-03-10 | 2026-03-04 | 2026-06-19 | 2102365881 | 8202239465 |  | Penggantian kabel power water jacket edg | RU6-UTL | 51-G-102-P1A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 6358448 | 0 | MA4-LIS |  | DINDINS |  | 2026-03-05 | PT02 | 5 | 3 | 2026-03-04 | PM |  | 003
| K201 | 2026-02-23 | 2026-06-15 | 2026-02-23 | 2026-02-23 | 2102364417 | 8202239011 |  | Penggantian Iso Carbon Seal 301-C-1 | RU2-HSC | 301-C-1/00 | 60 | REL CSER GMPS MANC PRC SETC | 2RR | D12/26/B6/RT-D2H | 836905554 | 836905554 | MA2-ROT |  | NURFADHILLA |  | 2026-02-23 | PT02 | 5 | 3 | 2026-02-23 | PM |  | 003
| K601 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-06-02 | 2102367871 | 8202242392 |  | Penggantian Inlet Filter MAC N2 Plant | RU6-UTL | 059-A-101B-K1/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 11892 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K601 | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-05-21 | 2102364776 | 8202239036 |  | Penggantian Indikator UV 52-B-101B | RU6-UTL | 52-B-101B/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6IR | D16/26/B6/RT-C2 | 417816463 | 134836445 | MA4-INT |  | DANDARWANI |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K601 | 2026-04-27 | 2026-06-02 | 2026-03-09 | 2026-07-30 | 2102366386 | 8202242745 |  | Penggantian IGV & Bearing FDF 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 558649555 | 558637674 | MA4-ROT |  | DANDARWANI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 005
| K501 | 2026-06-17 | 2026-06-18 | 2026-06-17 | 2026-06-17 | 2102369994 | 8202243902 |  | Penggantian hose untuk kebutuhan STS | RU5-TBL | PIPE-ON-SHORE/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 396809152 | 0 | MA4-STA |  | MANKURNIAWAN |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-09-01 | 2102366851 | 8202241877 |  | Penggantian Ground Fault Relay SS 18 | RU6-POC | SS-18/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 45000000 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-06-02 | 2102368178 | 8202243140 |  | Penggantian Governor Turbin 56-P-101B-T | RU6-UTL | 56-P-101B-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 56316931 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-04-15 | 2102366466 | 8202241544 |  | Penggantian Governoor Turbine 56-P-101DT | RU6-UTL | 56-P-101D-T/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 104318251 | 104315611 | MA4-ROT |  | DANDARWANI |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-04-06 | 2102366385 | 8202241477 |  | Penggantian governoor 055-P-101A-T | RU6-UTL | 055-P-101A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 56317459 | 56315611 | MA4-ROT |  | DANDARWANI |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-26 | 2026-04-29 | 2026-02-26 | 2026-05-26 | 2102365029 | 8202239191 |  | Penggantian gasket suc. str 56-P-101A~H | RU6-UTL | 56-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 11880 | 0 | MA4-STA |  | HARSARIZANO |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K601 | 2026-04-30 | 2026-06-09 | 2026-04-30 | 2026-10-30 | 2102368539 | 8202242884 |  | Penggantian Gas Detector 16-GDF-102 | RU6-RCC | 16-GDF-102/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 75000000 | 0 | MA1-INT |  | DEATASAP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-04-30 | 2026-06-09 | 2026-04-30 | 2026-10-30 | 2102368546 | 8202242879 |  | Penggantian Gas Detector 15-GDF-108 | RU6-RCC | 15-GDF-108/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C1H | 75000000 | 0 | MA1-INT |  | DEATASAP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-04-30 | 2026-06-09 | 2026-04-30 | 2026-11-03 | 2102368545 | 8202242876 |  | Penggantian Gas Detector 15-GDF-103 | RU6-RCC | 15-GDF-103/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C1H | 150000000 | 0 | MA1-INT |  | DEATASAP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-04-30 | 2026-06-09 | 2026-04-30 | 2026-11-03 | 2102368544 | 8202242874 |  | Penggantian Gas Detector 15-GDF-102 | RU6-RCC | 15-GDF-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C1H | 150000000 | 0 | MA1-INT |  | DEATASAP |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-02-09 | 2026-02-10 | 2026-02-06 | 2026-04-01 | 2102362131 | 8202238804 |  | Penggantian fuse Sootblower 52-B-101A6-K | RU6-UTL | 52-B-101A6-K2-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 15479 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-10 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-11-25 | 2102367954 | 8202243281 |  | Penggantian Fuse Area 059-A-101A/B | RU6-UTL | 059-A-101A-V1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 17160 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-10-27 | 2102370079 | 8202243938 |  | Penggantian fuse 53-P-201D | RU6-UTL | 53-P-201D-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1755130 | 1743118 | MA4-LIS |  | ANDRIN |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-04-15 | 2102361713 | 8202238873 |  | Penggantian Flow Transmitter 37-FT-032 | RU6-POC | 37-FT-032/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 34990350 | 34990350 | MA3-INT |  | DANDARWANI |  | 2026-02-12 | PT02 | 5 | 3 | 2026-02-12 | PM |  | 003
| K601 | 2026-03-31 | 2026-04-15 | 2026-03-31 | 2026-07-07 | 2102366957 | 8202241983 |  | Penggantian Flow Transmitter 36-FT-013 | RU6-POC | 36-FT-013/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 11663450 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-08-10 | 2102368112 | 8202242524 |  | Penggantian Flow Transmitter 23-FT-013 | RU6-HSC | 23-FT-013/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 23326900 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-17 | PT02 | 5 | 3 | 2026-04-17 | PM |  | 003
| K601 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-07-30 | 2102368334 | 8202242707 |  | Penggantian Flow Transmitter 10-FT-001 | RU6-RCC | 15-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 11663450 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K601 | 2026-05-07 | 2026-05-07 | 2026-05-06 | 2026-06-25 | 2102368774 | 8202243066 |  | Penggantian Flame Aerester 11F101 | RU6-HSC | 11-F-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 82000000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-05-07 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-04-14 | 2026-05-08 | 2026-04-14 | 2026-08-31 | 2102367898 | 8202242407 |  | Penggantian Fire Water Line 66 | RU6-LK/KK | 66-T-101/00 | 50 | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/NR-C2H | 300366536 | 300354656 | MA4-STA |  | SHELFIANCBP |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 004
| K601 | 2026-04-15 | 2026-04-17 | 2026-04-14 | 2026-04-28 | 2102367955 | 8202242471 |  | Penggantian Filter LO 15-K-102B-T | RU6-RCC | 15-K-102B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3751132 | 3751132 | MA1-ROT |  | ERWINSURYAG |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K501 | 2026-03-03 | 2026-03-06 | 2026-02-25 | 2026-12-31 | 2102364956 | 8202239329 |  | penggantian filter L.O K-3-01B | RU5-E15112 | K-3-01B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 59348124 | 0 | MA3-ROT |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 003
| K501 | 2026-02-09 | 2026-05-04 | 2026-02-02 | 2026-04-30 | 2102359354 | 8202238787 |  | Penggantian Filter L.O G-3-30CD | RU5-E15112 | K-3-01B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 59348124 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-04-10 | 2026-04-10 | 2026-05-20 | 2026-06-22 | 2102367643 | 8202242323 |  | Penggantian Filter DGS | RU2-HSC | 300-C-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-10 | PT02 | 5 | 3 | 2026-05-20 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102365757 | 8202242216 |  | Penggantian Filter Control Oil 39-K-101 | RU6-POC | 39-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-29 | 2102369620 | 8202243799 |  | Penggantian Filter 21-K-101A-S1A | RU6-DHC | 21-K-101A-S1A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 1324375 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-06-11 | PT02 | 4 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-11-09 | 2102366806 | 8202242888 |  | Penggantian FCU 42-MOV-034/045/110/208 | RU6-ITP | 42-T-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 117816896 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 6 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-25 | 2026-05-21 | 2026-11-19 | 2102368548 | 8202243386 |  | Penggantian ethernet comm. mod 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 146335460 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-07-02 | 2102369945 | 8202243956 |  | Penggantian driveshaft 56-K-101F | RU6-UTL | 56-K-101F/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 183967858 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-11-03 | 2102367204 | 8202242889 |  | Penggantian Displacer ATG 62-T-201B | RU6-UTL | 62-T-201B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16368 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K201 | 2026-03-26 | 2026-04-06 | 2026-03-26 | 2026-04-30 | 2102366917 | 8202241900 |  | Penggantian diapragm 300-TV-46 | RU2-HSC | 300-TV-46/00 | 50 | CRTD CSER MACM PRC | 2IR | D12/26/B6/RT-D2H | 1800000 | 0 | MA2-INT |  | DONITGN |  |  | PT02 | 5 | 2 | 2026-03-26 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-06-17 | 2102367642 | 8202243148 |  | Penggantian Coupling Pompa 42-P-203B | RU6-ITP | 42-P-203B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2643 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 6 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-09 | 2026-04-07 | 2026-04-21 | 2102364848 | 8202242147 |  | Penggantian Coupling 55-A-101BP1 (MIV) | RU6-UTL | 55-A-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 26001320 | 26000000 | MA4-ROT |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-25 | 2102365717 | 8202239435 |  | Penggantian Coupling 055-A-101-P1/P2/P3 | RU6-UTL | 055-A-101-V1/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 517201320 | 517200000 | MA4-ROT |  | DANDARWANI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-15 | 2102362171 | 8202244028 |  | Penggantian Control Valve 61-LV-301 | RU6-POC | 61-SK-301/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-22 | PM |  | 005
| K601 | 2026-02-24 | 2026-02-24 | 2026-02-23 | 2026-04-06 | 2102364775 | 8202239092 |  | Penggantian control valve 52-TV-219E | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2 | 3168 | 88760875 | MA4-INT |  | DANDARWANI |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-14 | 2026-04-07 | 2026-06-10 | 2102363882 | 8202242145 |  | Penggantian control valve 52-TV-219ABCDE | RU6-UTL | 52-TV-219A/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 443809655 | 88760875 | MA4-INT |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-03-30 | 2026-03-30 | 2026-03-25 | 2026-08-10 | 2102366842 | 8202241932 |  | Penggantian Control Valve 24-FV-038 | RU6-HSC | 24-FV-038/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 60875000 | 0 | MA1-INT |  | DANDARWANI |  | 2026-03-30 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-22 | 2102369957 | 8202243823 |  | Penggantian Check Valve 4in 55-A-101A-V5 | RU6-UTL | 55-A-101A-V5/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 13543642 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-04-08 | 2026-05-29 | 2026-04-08 | 2026-05-07 | 2102366950 | 8202242195 |  | Penggantian Cartridge Filter 12-K-502A | RU6-DHC | 12-K-502A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2866410 | 2866410 | MA2-ROT |  | SAPBATCH | 2026-05-29 | 2026-04-08 | PT02 | 4 | 3 | 2026-05-29 | PM |  | 003
| K601 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-12-01 | 2102369146 | 8202243436 |  | Penggantian Carrier Gas 19-AT-001 | RU6-RCC | 19-AT-001/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 5 | 0 | MA1-INT |  | DANDARWANI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-15 | 2102363447 | 8202244027 |  | Penggantian Cabl Gland Transducer 15K103 | RU6-RCC | 15-K-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 10 | 0 | MA1-INT |  | DANDARWANI |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-27 | 2026-05-04 | 2026-03-05 | 2026-04-24 | 2102363551 | 8202239259 |  | Penggantian BV 2"-300 Ejector Rp A Hitam | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 5068872 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-12-01 | 2102368560 | 8202243707 |  | Penggantian Breaker HMI demin OSBL | RU6-UTL | 055-A-101-V1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16104 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-09 | PT02 | 3 | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-04-09 |  | 2026-02-27 | 2026-05-12 | 2102365100 | 8202242250 |  | Penggantian Belt 37-E-102 | RU6-POC | 37-E-102/00 | 50 | CRTD CSER MACM PRC | 6RR | D16/26/B6/RT-C2H | 2011115 | 0 | MA3-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-02-27 | PM |  | 005
| K601 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-25 | 2102369833 | 8202243742 |  | Penggantian Bearing Turbine 39-K-101-P1T | RU6-POC | 39-K-101-P1-T/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 189000 | 189000 | MA3-ROT |  | DANDARWANI |  | 2026-06-10 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-06 | 2026-05-04 | 2026-05-20 | 2102368712 | 8202243046 |  | Penggantian Bearing Pump 39-K-101-P2 | RU6-POC | 39-K-101-P2/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 203454 | 203454 | MA3-ROT |  | DANDARWANI |  | 2026-05-06 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K501 | 2026-03-03 | 2026-03-04 | 2026-02-27 | 2026-08-30 | 2102365077 | 8202239377 |  | Penggantian Bearing Pompa G-31-39A | RU5-E15112 | G-31-39A/00 | 50 | CLSD CSER MACM NCMP PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | ANDREAYR |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 003
| K601 | 2026-06-18 | 2026-06-19 | 2026-06-18 | 2026-07-02 | 2102369853 | 8202243955 |  | Penggantian bearing pompa 23-P-201 A | RU6-HSC | 23-P-201A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 4675500 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-06-02 | 2102368541 | 8202243134 |  | Penggantian Bearing Pompa 14-P-106B | RU6-DHC | 14-P-106B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 58594294 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-05-07 | 2102366772 | 8202241786 |  | Penggantian Bearing pompa 055-A-101-P4B | RU6-UTL | 055-A-101-P4B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 496484 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-06-02 | 2102366723 | 8202243154 |  | Penggantian Bearing Pompa 052-P-101B | RU6-UTL | 052-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2401320 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-08 | 2026-05-26 | 2102368877 | 8202243133 |  | Penggantian Bearing NDE Pompa 12-P-505B | RU6-DHC | 12-P-505B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3318800 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-05-12 | PT02 | 4 | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-06-02 | 2102367652 | 8202242234 |  | Penggantian bearing motor 62-P-201C | RU6-UTL | 62-P-201C/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1715512 | 1711156 | MA4-LIS |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K201 | 2026-06-18 | 2026-06-18 | 2026-09-01 | 2026-09-01 | 2102369993 | 8202243946 |  | Penggantian Bearing Motor 140 PM-8B | RU2-HOC | 140-PM-8B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 88000 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-05-19 | 2026-08-31 | 2102369160 | 8202243765 |  | Penggantian bearing motor 14-P-601B | RU6-DHC | 14-P-601B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 398049 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-06-11 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-05-20 | 2102367057 | 8202242009 |  | Penggantian Bearing Motor 12-A-501-P1B | RU6-DHC | 12-A-501-P1B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 435711 | 435711 | MA2-LIS |  | DANDARWANI |  | 2026-04-01 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-04-14 | 2026-06-05 | 2026-04-14 | 2026-07-22 | 2102367956 | 8202242433 |  | Penggantian bearing motor 055-A-101P2B | RU6-UTL | 055-A-101-P1B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 2155402 | 2146954 | MA4-LIS |  | DINDINS |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K601 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-09-01 | 2102367953 | 8202242425 |  | Penggantian bearing motor 055-A-101P1A | RU6-UTL | 055-A-101-P1A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 2159049 | 2146954 | MA4-LIS |  | ANDRIN |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K601 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-07-08 | 2102368880 | 8202243087 |  | Penggantian bearing motor 050-P-901A | RU6-UTL | 050-P-901A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1400213 | 1077310 | MA4-LIS |  | DANDARWANI |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-04-20 | 2026-05-29 | 2026-04-09 | 2026-05-19 | 2102367685 | 8202242592 |  | Penggantian Bearing Fan 21-E-102G | RU6-DHC | 21-E-102G/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 11618000 | 11618000 | MA2-ROT |  | SAPBATCH | 2026-05-29 | 2026-04-20 | PT02 | 4 | 3 | 2026-05-29 | PM |  | 003
| K701 | 2026-04-06 |  | 2026-01-02 | 2026-01-02 | 2102367433 | 8202242066 |  | Penggantian Bearing di 5-P-19A | RU7-OFF | 5-P-19A/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-4-D4H | 3572769 | 0 | MA-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 005
| K701 | 2026-04-06 | 2026-04-10 | 2026-01-02 | 2026-01-02 | 2102367421 | 8202242064 |  | Penggantian Bearing di 1-P-02A | RU7-CDU | 1-P-02A/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 204469580 | 0 | MA-ROT |  | YAYANHER |  | 2026-04-08 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K201 | 2026-05-21 | 2026-05-22 | 2026-06-01 | 2026-06-03 | 2102365214 | 8202243357 |  | Penggantian Bearing Damper 100-DA-12345 | RU2-HSC | 100-BH-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 15334016 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 5 | 3 | 2026-06-01 | PM |  | 003
| K601 | 2026-05-25 | 2026-06-22 | 2026-05-18 | 2026-05-18 | 2102369055 | 8202243441 |  | Penggantian Bearing 66-P-102 A | RU6-UTL | 66-P-102A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 2418068 | 1498020 | MA4-LIS |  | DINDINS |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K201 | 2026-04-10 | 2026-05-12 | 2026-03-26 | 2026-03-26 | 2102366908 | 8202242332 |  | Penggantian Bearing 140 PC-51 | RU2-HOC | 140-PC-51/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RR | D12/XX/B6/RT-D2NH | 13560000 | 13560000 | MA1-ROT |  | NURFADHILLA |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K201 | 2026-04-10 | 2026-06-19 | 2026-04-10 | 2026-04-10 | 2102366972 | 8202242331 |  | Penggantian Bearing 102-P-3B | RU2-HSC | 102-P-3B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RR | D12/XX/B6/RT-D2NH | 955833 | 955833 | MA2-ROT |  | NURFADHILLA |  | 2026-04-10 | PT02 | 5 | 3 | 2026-04-10 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-05-08 | 2026-05-21 | 2102368167 | 8202242860 |  | Penggantian bearing 100-P-10 C | RU2-ITP | 100-P-10C/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 7440734 | 3986608 | MA4-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 5 | 3 | 2026-05-08 | PM |  | 003
| K201 | 2026-04-23 | 2026-04-23 | 2026-07-01 | 2026-07-01 | 2102367563 | 8202242696 |  | Penggantian Bearing | RU2-HSC | 200-PM-4B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/NR-D2H | 0 | 0 | MA2-LIS |  | AZIZFATONI |  |  | PT02 | 5 | 2 | 2026-07-01 | PM |  | 003
| K201 | 2026-04-30 | 2026-06-19 | 2026-04-30 | 2026-05-12 | 2102368429 | 8202242849 |  | Penggantian Bearing | RU2-HCC | 211-P-9A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 19907907 | 2157695 | MA2-ROT |  | NURFADHILLA |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-07-01 | 2026-07-02 | 2102368500 | 8202243348 |  | Penggantian Bearing | RU2-HCC | 211-P-13BR/01 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6773438 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K501 | 2026-04-09 | 2026-04-14 | 2026-07-01 | 2026-12-30 |  | 8202242273 |  | Penggantian Battery Bank SS33 | RU5-UTL | 41-R-SS-33/00 | 50 | CLSD CSER MACM NCMP PRC | 5ER | D15/26/B6/RT-C2H | 1 | 0 | MA4-LIS |  | GHAGASP |  |  | PT02 | 8 | 2 | 2026-04-14 | PM |  | 003
| K601 | 2026-04-06 |  | 2026-03-05 | 2026-05-11 | 2102366128 | 8202242074 |  | Penggantian Basic Mech Seal 34-P-105A | RU6-POC | 34-P-105A/00 | 50 | CRTD CSER MACM PRC | 6RR | D16/26/B6/RT-C2H | 279992416 | 0 | MA3-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-03-05 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-27 | 2026-04-24 | 2026-09-11 | 2102368353 | 8202242740 |  | Penggantian Baru Transmiter 24 FT 021 | RU6-HSC | 24-FT-021/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 11663450 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-27 | PT02 | 5 | 3 | 2026-04-24 | PM |  | 003
| K701 | 2026-06-03 |  | 2026-06-02 | 2026-06-02 | 2102369481 | 8202243594 |  | Penggantian baru baut Cover 2-E-01 | RU7-NHT | 2-R-01/00 | 50 | CRTD NMAT PRC | 7RT | D17/10/B6/RT1-NHTNH | 0 | 0 | MA-STA |  |  |  |  | PT02 | 3 | 2 | 2026-06-02 | PM |  | 005
| K601 | 2026-03-09 | 2026-03-09 | 2026-02-25 | 2026-03-25 | 2102364943 | 8202241400 |  | Penggantian baru 31-FT-036 | RU6-HSC | 31-FT-036/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 11663450 | 0 | MA3-INT |  | DANDARWANI |  | 2026-03-09 | PT02 | 5 | 3 | 2026-02-25 | PM |  | 003
| K501 | 2026-03-05 | 2026-05-04 | 2026-03-05 | 2026-04-24 | 2102364994 | 8202239478 |  | Penggantian Ball Valve LPG Jetty 3 | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 28790664 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-06-05 | 2102369050 | 8202243294 |  | Penggantian Air Inlet Filter 58-K-101D | RU6-UTL | 58-K-101D/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 41153320 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-09 | 2026-03-04 | 2026-04-16 | 2102365760 | 8202239419 |  | Penggantian Air Filter 15-K-103 | RU6-RCC | 15-K-103/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 124565110 | 88773000 | MA1-ROT |  | ERWINSURYAG |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-07-29 | 2102369908 | 8202243894 |  | Penggantian Accessories CV 24-FV-010 | RU6-HSC | 24-FV-010/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 67425407 | 0 | MA1-INT |  | DEATASAP |  | 2026-06-17 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K501 | 2026-04-07 | 2026-04-23 | 2026-12-01 | 2026-12-31 | 2102364121 | 8202242180 |  | PENGGANTIAN 8A/8B-PCV-114B | RU5-E15112 | 08A-PCV-114/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 2 | 0 | MA3-INT |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-12-01 | PM |  | 004
| K601 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-09-11 | 2102364476 | 8202241736 |  | Penggantian 52-TIS-222 Boiler 52-B-101B | RU6-UTL | 52-B-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 259215048 | 0 | MA4-INT |  | DANDARWANI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K601 | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-03-11 | 2102364540 | 8202238953 |  | Penggantian 52-FALL-207B | RU6-UTL | 52-B-101B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2 | 10492238 | 0 | MA4-INT |  | DANDARWANI |  | 2026-02-19 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K601 | 2026-04-20 | 2026-04-20 | 2026-04-16 | 2026-09-03 | 2102368067 | 8202242555 |  | Penggantian 36-TG-015 di CWR 36-E-105 | RU6-POC | 36-E-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 1800000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-08-04 | 2102362381 | 8202242281 |  | Penggantian 12-LALL-624 di 12-K-501A | RU6-DHC | 12-K-501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | DANDARWANI |  | 2026-04-09 | PT02 | 1 | 3 | 2026-04-09 | PM |  | 003
| K601 | 2026-03-30 | 2026-03-30 | 2026-03-16 | 2026-08-06 | 2102366697 | 8202241937 |  | Penggantian Transmitter 11-LT-407 | RU6-HSC | 11-LT-407/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16888382 | 0 | MA1-INT |  | DANDARWANI |  | 2026-03-30 | PT02 | 5 | 3 | 2026-03-16 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-12-14 | 2102369906 | 8202243817 |  | Penggantia Rotameter line N2 injeksi chl | RU6-HSC | 32-P-112A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 173600000 | 0 | MA3-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 5 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-11 | 2026-06-08 | 2026-09-03 |  | 8202243702 | 8202242039 | Pengganti matrial OH untuk UCO | RU6-DHC | 22-R-101/00 | 50 | REL CSER MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 395219298 | 0 | MA2-STA |  | SHELFIANCBP |  | 2026-06-09 | PT02 | 1 | 3 | 2026-06-08 | PM |  | 004
| K601 | 2026-02-25 | 2026-04-24 | 2026-02-18 | 2026-02-18 |  | 8202239137 | 8202238961 | Pengganti material MIV perbaikan RCC (2) | RU6-RCC | 15-C-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 10442474250 | 10442474250 | MA1-STA |  | DANDARWANI |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K601 | 2026-02-19 | 2026-04-06 | 2026-02-18 | 2026-02-18 | 2102364554 | 8202238961 |  | Pengganti material MIV perbaikan RCC | RU6-RCC | 15-C-101/00 | 50 | REL CSER GMCO GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 651760827 | 612908569 | MA1-STA |  | DANDARWANI |  | 2026-02-19 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K501 | 2026-06-03 | 2026-06-04 | 2026-06-03 | 2026-07-16 | 2102367602 | 8202243591 |  | Pengantian Gate Valve 24"-150 Tangki P31 | RU5-TBL | P-31/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/10/B6/RT1-FINH | 423719791 | 0 | MA4-STA |  | NSUCIPTO |  | 2026-06-04 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 003
| K201 | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-03-16 | 2102366479 | 8202241545 |  | Pengambilan Transmitter untuk 140 H-1AB | RU2-HOC | 140-H-1A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/NR-C2H | 9900000 | 0 | MA1-INT |  | STEVANEKOPP |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 005
| K601 | 2026-03-11 | 2026-03-11 | 2026-03-10 | 2026-05-18 | 2102366480 | 8202241567 |  | Pengambilan Press Gauge untuk 31-E-104 | RU6-HSC | 31-E-104A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C3H | 14695300 | 14695300 | MA3-INT |  | DANDARWANI |  | 2026-03-11 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K501 | 2026-02-23 | 2026-03-10 | 2026-08-28 | 2026-08-31 | 2102364800 | 8202239044 |  | Pengambilan oli TRAFO SS 64 | RU5-UTL | 1AL17/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 11902511 | 0 | MA2-LIS |  | GHAGASP |  | 2026-03-10 | PT02 | 8 | 3 | 2026-08-28 | PM |  | 045
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-08-31 | 2102364960 | 8202241327 |  | Pengambilan Material Perbaikan 11P10AM | RU4-FOC1 | 11P10AM/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 169000000 | 169000000 | MA1-LIS |  | YMOHAMMAD |  | 2026-03-07 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K201 | 2026-04-23 | 2026-05-19 | 2026-04-07 | 2026-04-07 | 2102367501 | 8202242699 |  | Pengambilan Hand Lamp Area HOC | RU2-HOC | 110-PM-4A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 34200000 | 34200000 | MA1-LIS |  | ADEMULYADI |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K201 | 2026-06-18 | 2026-06-18 | 2026-03-13 | 2026-03-13 | 2102366665 | 8202243952 |  | Pengambilan Gate Valve area 140-H-1 CD | RU2-HOC | 140-H-1C/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 23636345 | 23636345 | MA1-STA |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K601 | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-03-04 | 2102364488 | 8202238951 |  | Pengambilan gasket 31-PV-006 | RU6-HSC | 31-PV-006/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2 | 60426728 | 60426728 | MA3-INT |  | DANDARWANI |  | 2026-02-19 | PT02 | 5 | 3 | 2026-02-18 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-29 | 2026-06-02 | 2026-06-02 | 2102368303 | 8202243289 |  | Pengambilan Breaker untuk Area HOC | RU2-HOC | 140-PM-10A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 10800000 | 10800000 | MA1-LIS |  | NURFADHILLA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K201 | 2026-04-23 | 2026-05-19 | 2026-06-02 | 2026-06-02 | 2102366607 | 8202242697 |  | Pengambilan Bearing Motor 140-PM-54B | RU2-HOC | 140-PM-54B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 108200 | 72000 | MA1-LIS |  | ADEMULYADI |  | 2026-04-24 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K201 | 2026-04-17 | 2026-04-17 | 2026-05-29 | 2026-05-29 | 2102367750 | 8202242546 |  | Pengambilan Bearing Motor 140 PM-6B | RU2-HOC | 140-PM-6B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 453119 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-04-17 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 003
| K201 | 2026-04-01 | 2026-04-01 | 2026-03-30 | 2026-03-30 | 2102366969 | 8202242004 |  | Pengambilan Bearing 140 PM-6B | RU2-HOC | 140-PM-6B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 445000 | 445000 | MA1-LIS |  | AZIZFATONI |  | 2026-04-01 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K601 | 2026-04-22 | 2026-04-23 | 2026-04-20 | 2026-12-29 | 2102368191 | 8202242650 |  | Pengadaan Sewa Skid Tank Ethylene | RU6-POC | 34-V-106/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C1H | 2200000001 | 0 | MA3-STA |  | ZAMZAMKHALID |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-20 | 2026-05-19 | 2026-08-18 | 2102369000 | 8202243303 |  | Pengadaan Pump Assy 12-P-501B | RU6-DHC | 12-P-501B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2 | 0 | MA2-ROT |  | ABDULAZIZ70 |  | 2026-05-19 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 004
| K501 | 2026-06-15 | 2026-06-17 | 2026-06-15 | 2026-06-15 | 2102365135 | 8202243841 |  | PENGADAAN PART MCC SS80 |  |  | 01 | CRTD CSER NMAT PRC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | FAUZANR |  |  | PT02 | 3 | 2 | 2026-06-15 | PM |  | 045
| K601 | 2026-06-18 | 2026-06-22 | 2026-06-18 | 2026-10-28 | 2102370107 | 8202243940 |  | Pengadaan oli untuk trafo SS23 area OM | RU6-ITP | 23-PTR1-01B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 12144 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364708 | 8202238995 |  | Pengadaan Mech Seal 15-P-110A | RU6-RCC | 15-P-110A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364704 | 8202239001 |  | Pengadaan Mech Seal 15-P-109A | RU6-RCC | 15-P-109A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | PANDUA |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364703 | 8202238994 |  | Pengadaan Mech Seal 15-P-108A | RU6-RCC | 15-P-108A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 121340000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364702 | 8202238993 |  | Pengadaan Mech Seal 15-P-107A | RU6-RCC | 15-P-107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364701 | 8202238999 |  | Pengadaan Mech Seal 15-P-106A | RU6-RCC | 15-P-106A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364700 | 8202238998 |  | Pengadaan Mech Seal 15-P-104A | RU6-RCC | 15-P-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364679 | 8202238997 |  | Pengadaan Mech Seal 15-P-103A | RU6-RCC | 15-P-103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364678 | 8202238992 |  | Pengadaan Mech Seal 15-P-102A | RU6-RCC | 15-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-04-13 | 2102364676 | 8202239000 |  | Pengadaan Mech Seal 15-P-101A | RU6-RCC | 15-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 218639768 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-20 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K201 | 2026-03-10 | 2026-03-10 | 2026-07-31 | 2026-07-31 | 2102365792 | 8202241539 |  | Pengadaan Mech Seal 140 P-2B | RU2-HOC | 140-P-2B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA1-ROT |  | STEVANEKOPP |  | 2026-03-10 | PT02 | 3 | 3 | 2026-07-31 | PM |  | 003
| K601 | 2026-04-02 | 2026-06-08 | 2026-02-25 | 2026-02-25 |  | 8202242039 | 8202239152 | Pengadaan Material Project UCO | RU6-DHC | 22-R-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 375369298 | 321277393 | MA2-STA |  | DANDARWANI |  | 2026-06-08 | PT02 | 1 | 3 | 2026-02-25 | PM |  | 004
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102364712 | 8202242208 |  | Pengadaan Material Pompa 15-P-601A | RU6-RCC | 15-P-601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102364711 | 8202242210 |  | Pengadaan Material Pompa 15-P-119A | RU6-RCC | 15-P-119A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 8110224 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102364709 | 8202242212 |  | Pengadaan Material Pompa 15-P-113A | RU6-RCC | 15-P-113A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-03-11 | 2026-03-13 | 2026-03-02 | 2026-06-25 | 2102365164 | 8202241564 |  | Pengadaan material persiapan Satgas RAFI | RU6-DHC | 14-C-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 694044055 | 668444055 | MA2-INT |  | DANDARWANI |  | 2026-03-11 | PT02 | 4 | 3 | 2026-03-02 | PM |  | 003
| K601 | 2026-02-24 | 2026-03-11 | 2026-02-24 | 2026-06-19 | 2102364779 | 8202239087 |  | Pengadaan Material Persiapan Lebaran 26 | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6IR | D16/26/B6/RT-C2H | 688334791 | 370327058 | MA4-INT |  | DANDARWANI |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-09-11 | 2102365772 | 8202242628 |  | Pengadaan Material Part Triconnex | RU6-HSC | OS-17/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 288011204 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-06-02 |  | 2026-05-25 | 2026-05-25 | 2102369355 | 8202243570 |  | Pengadaan Material modul converter NRM |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 045
| K401 | 2026-03-03 | 2026-06-03 | 2026-03-03 | 2026-06-29 | 2102365210 | 8202239401 |  | Pengadaan Material Microfilter | RU4-TRML | 70P11/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-03-03 | 2026-05-21 | 2026-03-03 | 2026-06-29 | 2102365158 | 8202239400 |  | Pengadaan Material Coalescer Element | RU4-TRML | 70P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 045
| K201 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-05-08 | 2102368438 | 8202242818 |  | Pengadaan Material Bearing Damper | RU2-HCC | 212-C-51/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/RT-D2H | 277 | 0 | MA2-ROT |  | MAULANAHARUN |  |  | PT02 | 3 | 2 | 2026-04-28 | PM |  | 045
| K201 | 2026-05-04 | 2026-05-19 | 2026-04-28 | 2026-05-08 | 2102368501 | 8202242961 |  | Pengadaan Material Bearing | RU2-HCC | 212-P-13AR/01 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 353419315 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-07-01 | 2026-07-02 | 2102368471 | 8202243349 |  | Pengadaan Material Bearing | RU2-HCC | 702-P-9B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6694252 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-07-01 | 2026-07-02 | 2102368470 | 8202243350 |  | Pengadaan Material Bearing | RU2-HCC | 702-P-9A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6694252 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K701 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2102366306 | 8202241364 |  | PENGADAAN MAT STRUKTUR FINFAN | RU7-CDU | 1-EA-01A/00 | 50 | REL CSER MSPT PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-STA |  | RYANMANGGASA |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 005
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102365803 | 8202242214 |  | Pengadaan LUBE OIL FILTER 32-K-101 | RU6-HSC | 32-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 003
| K201 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-12-29 | 2102351671 | 8202242618 |  | Pengadaan Local Indicator Area HSC | RU2-HSC | 100-PM-1A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  | DONITGN |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K501 | 2026-03-09 | 2026-03-13 | 2026-05-04 | 2026-06-23 | 2102366216 | 8202241357 |  | Pengadaan Lisensi Software HMI FGDS FS |  | HMIFGDS/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | HSSE |  | RIANDAADI |  | 2026-03-13 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-05-05 | 2026-08-05 | 2102368734 | 8202243996 |  | Pengadaan kebutuhan mtral MA 1 | RU6-RCC | 15-L-108/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 33701220 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-22 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K501 | 2026-02-18 | 2026-05-04 | 2026-02-13 | 2026-12-31 | 2102364247 | 8202238946 |  | Pengadaan GASKET casing G-31-41AB | RU5-E15112 | G-31-41A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-02-13 | PM |  | 003
| K401 | 2026-04-23 |  | 2026-04-22 | 2026-04-22 | 2102368217 | 8202242674 |  | Pengadaan Gasket 11E55 | RU4-FOC1 |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-22 | PM |  | 045
| K601 | 2026-04-23 | 2026-04-23 | 2026-02-06 | 2026-03-10 | 2102361655 | 8202242686 |  | Pengadaan gasket 11-E-1015 AB | RU6-HSC | 11-E-105A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 34620000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-04-23 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 004
| K201 | 2026-03-27 | 2026-04-07 | 2026-08-28 | 2026-12-29 | 2102366254 | 8202241907 |  | Pengadaan flexible hose area jetty | RU2-ITP | 990-PX-2C/00 | 50 | REL MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 1311690067 | 0 | MA4-STA |  | INDRAHS |  | 2026-04-07 | PT02 | 5 | 3 | 2026-08-28 | PM |  | 003
| K201 | 2026-02-25 | 2026-02-25 | 2026-06-15 | 2026-06-15 | 2102364460 | 8202239146 |  | Pengadaan DP Transmitter Pressure Furnac | RU2-UTL | 940-B-1/00 | 50 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2 | 118800000 | 9900000 | MA3-INT |  | STEVANEKOPP |  | 2026-02-25 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-22 | 2026-04-21 | 2026-10-21 | 2102366805 | 8202242643 |  | Pengadaan Cover Actuator MOV 42-MOV-053 | RU6-ITP | 42-T-106/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16105 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-22 | PT02 | 6 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-07-17 | 2102364884 | 8202239111 |  | Pengadaan Copper Tube 15-P-102A | RU6-RCC | 15-P-102A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K601 | 2026-03-17 | 2026-06-11 | 2026-03-16 | 2026-05-06 | 2102366722 | 8202241783 |  | Pengadaan consumable matr'l area UTL | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 391877508 | 63440000 | MA4-ROT |  | PANDUA |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-09-04 | 2102367166 | 8202242207 |  | Pengadaan Consumable Material N2 OSBL | RU6-UTL | 059-A-101A-D1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16756295 | 11340219 | MA4-INT |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-06-19 | 2102361809 | 8202239081 |  | Pengadaan Consumable Material CV Boiler | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2 | 353865018 | 0 | MA4-INT |  | DANDARWANI |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K201 | 2026-05-13 | 2026-05-19 | 2026-05-13 | 2026-05-13 | 2102351371 | 8202243184 |  | Pengadaan Belt Cleaner Untuk Belt Convey | RU2-HOC | 170-ME-103-1/00 | 50 | REL MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 252757644 | 0 | MA1-ROT |  | ADEMULYADI |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K201 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-11 | 2102368437 | 8202242817 |  | Pengadaan Bearing Damper | RU2-HCC | 211-C-51/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 277 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K201 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-21 | 2102368168 | 8202242864 |  | Pengadaan bearing 110-P-1B | RU2-ITP | 110-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA4-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-05-04 | 2026-05-04 | 2026-04-30 | 2026-06-22 | 2102368630 | 8202242962 |  | Pengadaan Air Motor 11-P-121B | RU6-HSC | 11-P-121B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-04 | PT02 | 5 | 3 | 2026-04-30 | PM |  | 003
| K601 | 2026-06-03 | 2026-06-03 | 2026-06-02 | 2026-10-09 | 2102369473 | 8202243589 |  | Pengadaan 15-LG-527s/d530 ( Urgent ) | RU6-RCC | 15-E-104A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-03 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 004
| K201 | 2026-04-07 | 2026-05-20 | 2026-03-11 | 2026-03-11 | 2102366497 | 8202242151 |  | Penarikan Kabel Power 140-PM-1B | RU2-HOC | 140-PM-1B/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 810000000 | 0 | MA1-LIS |  | AHILMANSYAH |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K401 | 2026-02-12 |  | 2026-02-06 | 2026-02-06 | 2102363525 | 8202238884 |  | Penambahan Valve di LT dan LG 12V3 | RU4-FOC1 | 12V3/00 | 01 WENG | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 | 3 | 2 | 2026-02-06 | PM |  | 045
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-09 | 2026-04-28 | 2102364001 | 8202241396 |  | Penambahan Valve 0,5" PI Line 910 Napht | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 1365296 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-03-27 | 2026-05-05 | 2026-03-30 | 2026-04-07 | 2102366608 | 8202241906 |  | Penambahan Strainer Discharge P4 A Pth | RU5-TBL | P-4RP-A-PUTIH/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 214886368 | 0 | MA4-STA |  | OCTARIOHS |  | 2026-05-04 | PT02 | 5 | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-04-10 | 2026-06-10 | 2026-09-29 | 2026-09-29 | 2102363417 | 8202242316 |  | PENAMBAHAN COVER TOMBOL PADA SS-VI/VIA | RU5-UTL | 41-R-SS-6-LIS/00 | 60 | CLSD CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 35 | 0 | MA4-LIS |  | GHAGASP |  | 2026-04-23 | PT02 | 6 | 3 | 2026-06-10 | PM |  | 045
| K501 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-04-24 | 2102363550 | 8202239760 |  | Penambahan BV 4" Line drain A-26 | RU5-TBL | A-26/00 | 01 | CRTD CSER MACM PRC | 5MR |  | 8362019 | 0 | MA4-STA |  | OCTARIOHS |  |  | PT02 | 3 | 2 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-06 | 2026-06-18 | 2026-03-06 | 2026-12-30 | 2102365248 | 8202241296 |  | Pemutakhiran Master Data Peralatan | RU4-FOC2 | 012F102/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1492499850 | 1492499850 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-03-16 | 2026-03-16 | 2026-03-12 | 2026-03-12 |  | 8202241756 | 8202241614 | PEMERIKSAAN PERALATAN PRESSURE VESSEL & | RU2-UTL | 925-PIPING/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 812613601 | MA3-STA |  | ADEMULYADI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K201 | 2026-06-22 | 2026-06-22 | 2026-09-23 | 2026-09-23 |  | 8202244041 | 8202241756 | PEMERIKSAAN PERALATAN PRESSURE VESSEL & | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA3-STA |  | STEVANEKOPP |  | 2026-06-22 | PT02 | 3 | 3 | 2026-09-23 | PM |  | 045
| K201 | 2026-03-16 | 2026-03-17 | 2026-08-03 | 2026-08-03 |  | 8202241739 | 8202238400 | Pemeriksaan LRUT WTP Bukit Datuk sd WPS | RU2-UTL | 510-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1856140000 | 0 | MA3-STA |  | MAULANAHARUN |  | 2026-03-16 | PT02 |  | 3 | 2026-08-03 | PM |  | 003
| K601 | 2026-03-05 | 2026-05-20 | 2026-03-05 | 2026-06-15 | 2102366173 | 8202239479 |  | Pemeriksaan dan Pengujian 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 52750000 | 52750000 | MA4-STA |  | HARSARIZANO |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-07-30 | 2102366228 | 8202241412 |  | Pemeriksaan dan Pengujian 52-B-101B | RU6-UTL | 52-B-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 52750000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-05 | 2026-09-10 | 2102366201 | 8202241509 |  | Pemenuhan stock material rotating | RU6-RCC | 16-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 54270400 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102365765 | 8202242196 |  | Pemenuhan Stock Material 16-K-101 | RU6-RCC | 16-K-101/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-05-25 | 2102365764 | 8202242215 |  | Pemenuhan Stock Material 15-K-101 | RU6-RCC | 15-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K201 | 2026-03-10 | 2026-03-11 | 2026-12-03 | 2026-12-03 |  | 8202241549 | 8202241441 | PEMELIHARAAN/ PEMBERSIHAN BERKALA OPEN S | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 488800000 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-12-03 | PM |  | 045
| K201 | 2026-03-09 | 2026-03-10 | 2026-12-11 | 2026-12-11 | 2102364149 | 8202241488 |  | Pemeliharaan Spring Support/hanger HCC | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 600000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-03-10 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-03-13 | 2026-03-13 | 2026-12-02 | 2026-12-02 |  | 8202241702 | 8202241701 | PEMELIHARAAN DAN PENGGANTIAN SPRING SUPP | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-13 | 2026-03-13 | 2026-12-02 | 2026-12-02 |  | 8202241722 | 8202241701 | PEMELIHARAAN DAN PENGGANTIAN SPRING SUPP | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 291500000 | 0 | MA1-STA |  | STEVANEKOPP |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-12 | 2026-03-13 | 2026-03-10 | 2026-03-10 | 2102366462 | 8202241618 |  | Pemeliharaan AC dalam Kilang HCC | RU2-HCC | HCC-AC-MCR/00 | 50 | REL GMPS NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 400000000 | 224479000 | MA2-INT |  | DJOKOTRIONO |  | 2026-03-13 | PT02 | 2 | 3 | 2026-03-10 | PM |  | 045
| K601 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-04-09 | 2102366119 | 8202239463 |  | Pembuatan Sample Cooler 14-R-101 | RU6-DHC | 14-R-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 52358624 | 52358624 | MA2-STA |  | DANDARWANI |  | 2026-03-04 | PT02 | 5 | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-03-31 | 2026-05-04 | 2026-03-27 | 2026-03-27 | 2102366967 | 8202241978 |  | Pembuatan Ejector untuk penanganan sump | RU5-E15112 | G-34-60/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-03NH | 5625000 | 0 | WS-LAS |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-27 | PM |  | 003
| K701 | 2026-03-13 | 2026-03-28 | 2026-11-30 | 2026-11-30 | 2102366539 | 8202241684 |  | Pembenaan Data Base Plan |  |  | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 1 | 0 | MA-STA |  | RYANMANGGASA |  | 2026-03-13 | PT02 | 3 | 3 | 2026-11-30 | PM |  | 005
| K601 | 2026-05-06 | 2026-05-06 | 2026-03-04 | 2026-04-09 | 2102365817 | 8202243011 |  | Pembelian Gasket Level Glass 15-V-101 | RU6-RCC | 15-V-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-20 | 2026-04-08 | 2026-07-10 | 2102367679 | 8202242534 |  | Pembayaran TKDN Kontrak PM EI MA3 | RU6-POC | 18-PSW2-01-001/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-30 | 2026-03-03 | 2026-07-24 | 2102365284 | 8202242747 |  | Pemb. TKDN LTSA Metering Thp 27 - 35 | RU6-ITP | 42-A-100/00 | 50 | REL GMCO NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 150218250 | 0 | MA4-INT |  | ANDRIES |  | 2026-04-27 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-30 | 2026-05-04 | 2026-03-11 | 2026-08-03 | 2102366521 | 8202242847 |  | Pemb. PM - 4 LTSA Nitrogen Kjeldahl | RU6-LAB | LABORATORIUM/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 1 | 0 | MA3-STA |  | DANDARWANI |  | 2026-04-30 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-07 | 2026-02-06 | 2026-07-03 | 2102363380 | 8202242040 |  | Pemb. LTSA PT Spektris Termin 4 (100%) | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 122164000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-07 | 2026-02-06 | 2026-07-03 |  | 8202242035 | 8202241976 | Pemb. LTSA PT Spektris Termin 3 (100%) | RU6-LAB | LABORATORIUM/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 242217200 | 205884620 | MA3-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-07 | 2026-02-06 | 2026-07-03 |  | 8202242034 | 8202241976 | Pemb. LTSA PT Spektris Termin 2 | RU6-LAB | LABORATORIUM/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 293162752 | 249188339 | MA3-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-03-31 | 2026-04-02 | 2026-02-06 | 2026-08-14 | 2102361849 | 8202241976 |  | Pemb. LTSA PT Spektris | RU6-LAB | LABORATORIUM/00 | 01 | CRTD CSER GMCO NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | ANDRIES |  |  | PT02 | 3 | 2 | 2026-02-06 | PM |  | 003
| K601 | 2026-04-24 | 2026-04-29 | 2026-04-06 | 2026-04-06 |  | 8202242712 | 8202242157 | Pemb. LTSA Perawatan AC Tahap 4 (85%) | RU6-RCC | 20-FV-030/00 | 60 | TECO CSER NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-29 | PM |  | 003
| K601 | 2026-04-07 | 2026-06-04 | 2026-04-06 | 2026-08-20 |  | 8202242159 | 8202242157 | Pemb. LTSA Perawatan AC Tahap 3 (85%) | RU6-RCC | 20-FV-030/00 | 60 | TECO GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 212198250 | 212198250 | WS-INT |  | ZAMZAMKHALID |  | 2026-04-07 | PT02 | 5 | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-03-16 | 2026-05-18 | 2026-03-04 | 2026-07-27 | 2102365791 | 8202241732 |  | Pemb. LTSA Perawatan AC Tahap 2 (100%) | RU6-RCC | 20-FV-030/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 238939000 | 203098150 | WS-INT |  | MRBASUKI |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2027-01-27 | 2102367463 | 8202242157 |  | Pemb. LTSA Perawatan AC | RU6-RCC | 20-FV-030/00 | 01 | CRTD CSER GMCO NMAT PRC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | ANDRIES |  |  | PT02 | 5 | 2 | 2026-04-06 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-18 | 2026-05-04 | 2026-09-17 | 2102368579 | 8202243145 |  | Pemb. LTSA O2 Ametek | RU6-RCC | 15-AT-002/00 | 01 | CRTD CSER GMCO NMAT PRC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | AHMADAKHYAR |  |  | PT02 | 5 | 2 | 2026-05-04 | PM |  | 003
| K601 | 2026-06-15 | 2026-06-15 | 2026-03-11 | 2026-08-03 |  | 8202243845 | 8202242028 | Pemb. LTSA ConMon PLC/MMS Thp4 (85%) | RU6-RCC | OS-14/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 126463321 | 0 | MA1-STA |  | DANDARWANI |  | 2026-06-15 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-05-07 | 2026-05-07 | 2026-03-11 | 2026-08-03 |  | 8202243058 | 8202242028 | Pemb. LTSA ConMon PLC/MMS Thp3 (85%) | RU6-RCC | OS-14/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 122623368 | 122623368 | MA1-STA |  | DANDARWANI |  | 2026-05-07 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-07 | 2026-03-11 | 2026-08-03 |  | 8202242031 | 8202242028 | Pemb. LTSA ConMon PLC/MMS Thp1 (85%) | RU6-RCC | OS-14/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 153712716 | 153712716 | MA1-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-03-11 | 2026-08-03 |  | 8202242225 | 8202242028 | Pemb. LTSA ConMon PLC/MMS Thp 2 (85%) | RU6-RCC | OS-14/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 90344682 | 90344682 | MA1-STA |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-21 | 2026-05-13 | 2026-09-28 | 2102369033 | 8202243361 |  | Pemb. LTSA CEMS COB | RU6-RCC | 15-B-101/00 | 01 | CRTD CSER GMCO NMAT PRC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | AHMADAKHYAR |  |  | PT02 | 3 | 2 | 2026-05-13 | PM |  | 003
| K601 | 2026-04-10 | 2026-04-10 | 2026-04-08 | 2027-01-29 | 2102367664 | 8202242320 |  | Pemb. LTSA CEMS 11-F-101 | RU6-HSC | 11-F-101/00 | 01 | CRTD CSER GMCO NMAT PRC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | AHMADAKHYAR |  |  | PT02 | 5 | 2 | 2026-04-08 | PM |  | 003
| K601 | 2026-03-16 | 2026-03-17 | 2026-03-03 | 2026-07-24 | 2102365286 | 8202241731 |  | Pemb. LTSA ATG Termin 9 (100%) | RU6-ITP | 42-T-403A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 310350000 | 310350000 | MA4-STA |  | DANDARWANI |  | 2026-03-17 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-06-19 | 2026-06-19 | 2026-04-16 | 2026-09-02 |  | 8202243974 | 8202242941 | Pemb. LTSA ATG Termin 8 (15%) | RU6-ITP | 42-T-403A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 167490000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-19 | PT02 | 5 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-05-04 | 2026-05-04 | 2026-04-16 | 2026-10-14 | 2102368050 | 8202242941 |  | Pemb. LTSA ATG | RU6-ITP | 42-T-403A/00 | 01 | CRTD GMCO NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | AHMADAKHYAR |  |  | PT02 | 5 | 2 | 2026-04-16 | PM |  | 003
| K601 | 2026-02-25 | 2026-03-03 | 2026-02-20 | 2026-07-15 | 2102364680 | 8202239141 |  | Pemb LTSA DCS Centum VP&ESD Thp 9 (85%) | RU6-RCC | 20-FV-030/00 | 50 | REL GMCO NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 1 | 0 | MA1-INT |  | DANDARWANI |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-07-24 |  | 8202239344 | 8202239141 | Pemb LTSA DCS Centum VP&ESD Thp 9 (85%) | RU6-RCC | 20-FV-030/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 374170000 | 374170000 | MA1-INT |  | RONALDIH |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-25 | 2026-05-18 | 2026-02-20 | 2026-07-15 | 2102364649 | 8202239140 |  | Pemb LTSA DCS Centum VP&ESD Thp 8 (85%) | RU6-RCC | 20-FV-030/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 538568500 | 538568500 | MA1-INT |  | AHMADAKHYAR |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-05-07 | 2102368012 | 8202242448 |  | Pemasangan valve poliser H2 Plant | RU6-DHC | 22-A-105/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 52793000 | 52793000 | MA2-STA |  | DANDARWANI |  | 2026-04-15 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-05 |  | 2026-03-05 | 2026-05-29 | 2102365035 | 8202239474 |  | Pemasangan Steam Trace Line Block Mode |  |  | 50 | CRTD CSER MACM PRC | 4MR |  | 99000000 | 0 | MA3-STA |  |  |  |  | PT02 | 4 | 2 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-26 |  | 2026-02-25 | 2026-02-25 | 2102365020 | 8202239209 |  | Pemasangan OTS PL II |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RT1-2J1-S0NH | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-02-25 | PM |  | 045
| K601 | 2026-05-06 | 2026-05-06 | 2026-02-18 | 2026-02-18 | 2102364485 | 8202243005 |  | Pemasangan Jumper Line 15-FV-517 | RU6-RCC | 15-FV-517/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 200000001 | 0 | MA1-STA |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K601 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-12-14 | 2102363984 | 8202243820 |  | Pemasangan FlowMeter Area Filling Shed | RU6-ITP | 42-T-201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 104099026 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-05-13 | 2102365894 | 8202241785 |  | Pemasangan Flow Meter 53-FT-101 | RU6-UTL | 53-T-301B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 214664 | 0 | MA4-INT |  | DANDARWANI |  | 2026-03-17 | PT02 | 5 | 3 | 2026-03-17 | PM |  | 003
| K201 | 2026-04-28 | 2026-05-22 | 2026-04-28 | 2026-12-31 | 2102366628 | 8202242787 |  | Pemasangan FGDS All Area Process | RU2-HSC | 102-PIPING/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 1 | 0 | MA2-INT |  | ADEMULYADI |  | 2026-05-22 | PT02 | 5 | 3 | 2026-04-28 | PM |  | 045
| K201 | 2026-05-07 | 2026-06-09 | 2026-12-29 | 2026-12-29 | 2102368594 | 8202243068 |  | Pemasangan dan Pembongkaran Drip Sampler | RU2-ITP | 690-PX-2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 200000000 | 0 | MA4-STA |  | ADEMULYADI |  | 2026-05-08 | PT02 | 5 | 3 | 2026-12-29 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-26 | 2026-05-25 | 2026-05-25 | 2102364162 | 8202243445 |  | Pemasangan & Pembongkaran Scaffolding | RU2-HOC | 140-V-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1110000900 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K201 | 2026-03-13 | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2102366599 | 8202241673 |  | Pemasangan & Pembongkaran Drip Sampler | RU2-ITP | 690-PX-2/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 530899000 | 320240000 | MA4-STA |  | DJOKOTRIONO |  | 2026-03-13 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-07 |  | 2026-05-07 | 2026-05-07 | 2102368826 | 8202243083 |  | Pemanfaatan Switch Network PSA | RU4-RFCGTO | 108A501A1/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 2950000 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-07 | PM |  | 003
| K401 | 2026-05-07 |  | 2026-05-07 | 2026-05-07 | 2102368825 | 8202243082 |  | Pemanfaatan Modul Kompresor 108 | RU4-RFCGTO | 108K501A/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 19250000 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-07 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2102368821 | 8202243078 |  | Pemanfaatan Material Amplifier 105LT-018 | RU4-RFCGTO | 105LT-U105/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 90389290 | 0 | MA7-INT |  | YOHANESMVIS |  |  | PT02 | 3 | 2 | 2026-05-07 | PM |  | 003
| K401 | 2026-05-07 |  | 2026-05-07 | 2026-05-07 | 2102368823 | 8202243080 |  | Pemanfaatan Material 105LT018 | RU4-RFCGTO | 105LT-U105/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 87273400 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-07 | PM |  | 003
| K401 | 2026-05-07 |  | 2026-05-07 | 2026-05-07 | 2102368822 | 8202243079 |  | Pemanfaatan Material 105LT001 & 012A | RU4-RFCGTO | 105LT-U105/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 94221400 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-07 | PM |  | 003
| K401 | 2026-05-07 |  | 2026-05-07 | 2026-05-07 | 2102368824 | 8202243081 |  | Pemanfaatan Material 105-FV-048 | RU4-RFCC | 105FT048/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 64000000 | 0 | MA7-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-07 | PM |  | 003
| K601 | 2026-05-05 | 2026-05-05 | 2026-04-24 | 2026-04-24 | 2102368349 | 8202242984 |  | PEKERJAAN SIPIL AREA UTL 2026 | RU6-UTL | 56-P-101C/00 | 01 | CRTD GMCO NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | JULIODWIP |  |  | PT02 | 3 | 2 | 2026-04-24 | PM |  | 003
| K601 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2102368357 | 8202242724 |  | PEKERJAAN SIPIL AREA OM 2026 | RU6-ITP | 42-T-201A/00 | 01 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | JULIODWIP |  |  | PT02 | 5 | 2 | 2026-04-24 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-28 | 2026-04-10 | 2026-04-10 | 2102367689 | 8202242528 |  | PEKERJAAN SIPIL AREA DHC 2026 | RU6-DHC | 14-C-201/00 | 01 | CRTD CSER GMCO NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | JANUARM |  |  | PT02 | 5 | 2 | 2026-04-10 | PM |  | 003
| K701 | 2026-06-13 |  | 2026-06-15 | 2026-06-15 | 2102369962 | 8202243840 |  | Pekerjaan Preventive 5-P-16A | RU7-OFF | 5-P-16A/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 988217 | 0 | MA-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-15 | PM |  | 005
| K701 | 2026-04-17 |  | 2026-04-17 | 2026-04-17 | 2102368064 | 8202242540 |  | Pekerjaan Prefentife Mentanance 5-T-20 | RU7-OFF | 5-T-20/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-4-D4H | 1184805 | 0 | MA-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-04-17 | PM |  | 005
| K601 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-06-11 | 2102365056 | 8202239336 |  | Pekerjaan PM Stationary THP 7 | RU6-RCC | 15-R-103/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 80856000 | 80856000 | MA1-STA |  | DANDARWANI |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K301 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2102367875 | 8202242427 |  | Pekerjaan Perbaikan Silo 10-DT004 | RU3-PP | 23-10-DT-004/00 | 01 | CRTD MACM PRC | 3MR | D13/26/B6/RT-1-C2H | 443785500 | 0 | MA2-STA |  | BUDIRAHARJO |  |  | PT02 | 3 | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-03-06 | 2026-03-06 | 2026-02-19 | 2026-02-19 |  | 8202241298 | 8202239086 | Pekerjaan Perbaikan Normalisasi RCC (2) | RU6-RCC | 15-P-104A-E1/00 | 50 | CRTD CSER MACM PRC | 6MR | D16/26/B6/RT-C2H | 6 | 0 | MA1-STA |  | MARSHAL |  |  | PT02 | 3 | 2 | 2026-02-19 | PM |  | 003
| K601 | 2026-02-24 | 2026-03-06 | 2026-02-19 | 2026-03-12 | 2102364617 | 8202239086 |  | Pekerjaan Perbaikan Normalisasi RCC | RU6-RCC | 15-P-104A-E1/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | MARSHAL |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K201 | 2026-06-12 | 2026-06-12 | 2026-12-11 | 2026-12-11 |  | 8202243825 | 8202242761 | PEKERJAAN PEMASANGAN FIRE HYDRANT PADA L | RU2-PK | 970-HYD-FIRE-01/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 66249200 | 0 | MA2-STA |  | STEVANEKOPP |  | 2026-06-12 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-10 | 2026-04-08 | 2026-07-16 | 2102367672 | 8202242258 |  | Pekerjaan Overhaul motor 36-P-102-AM | RU6-POC | 36-P-102A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 690713 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-13 | 2026-04-08 | 2026-07-16 | 2102367674 | 8202242262 |  | Pekerjaan Overhaul motor 36-K-101-D2M | RU6-POC | 36-K-101-D2-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 1128420 | 1036515 | MA3-LIS |  | DINDINS |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-09 | 2026-05-18 | 2026-04-08 | 2026-07-16 | 2102367670 | 8202242253 |  | Pekerjaan Overhaul motor 34A101-P-101BM | RU6-POC | 34-A-101P-101B-M/0 | 50 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 3588294 | 2304684 | MA3-LIS |  | DINDINS |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-10 | 2026-04-08 | 2026-07-16 | 2102367671 | 8202242255 |  | Pekerjaan Overhaul motor 34-P-110-BM | RU6-POC | 34-P-110B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 690713 | 0 | MA3-LIS |  | DANDARWANI |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-09 | 2026-05-11 | 2026-04-08 | 2026-07-16 | 2102367673 | 8202242260 |  | Pekerjaan Overhaul motor 34-P-101BM | RU6-POC | 34-P-101B-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 569438 | 402033 | MA3-LIS |  | DINDINS |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-10-19 | 2102369875 | 8202243755 |  | Pekerjaan LTSA scafflonding tahap ke 7 | RU6-ITP | 42-PIPE/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 540858000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 5 | 3 | 2026-06-10 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-20 | 2026-04-07 | 2026-08-21 | 2102367504 | 8202242235 |  | Pekerjaan LTSA Piping Works Tahap 20 | RU6-DHC | 14-V-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 308992000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K201 | 2026-04-28 | 2026-06-09 | 2026-12-28 | 2026-12-28 | 2102368038 | 8202242790 |  | pekerjaan LTSA Piping System area OM | RU2-ITP | 0-5P94661A2A1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 200000000 | 0 | MA4-STA |  | ADEMULYADI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-28 | PM |  | 003
| K701 | 2026-04-10 | 2026-04-11 | 2026-01-02 | 2026-01-02 | 2102367736 | 8202242302 |  | Pekerjaan Kebutuhan 3-PM-02 | RU7-CRU | 3-PM-02A/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 52333892 | 0 | MA-LINT |  | YAYANHER |  | 2026-04-10 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K701 | 2026-05-22 | 2026-05-23 | 2026-05-22 | 2026-05-22 | 2102369251 | 8202243419 |  | Pekerjaan di 5-P-16/25 | RU7-OFF | 5-P-16A/00 | 50 | REL CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 755773 | 755772 | MA-ROT |  | YAYANHER |  | 2026-05-23 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 005
| K701 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 |  | 8202241725 | 8202239341 | Pekerjaan di 1-C-01 | RU7-CDU | 1-C-01/00 | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 4799802 | 2159799 | MA-ROT |  | YAYANHER |  | 2026-03-14 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 005
| K701 | 2026-03-16 | 2026-03-16 | 2026-01-02 | 2026-01-02 | 2102366742 | 8202241774 |  | Pekerjaan Corrosion Thikness Gauge |  |  | 50 | REL MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 100000000 | 0 | MA-ROT |  | YAYANHER |  | 2026-03-16 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-05-05 | 2026-06-12 | 2026-04-30 | 2026-06-22 | 2102368558 | 8202242981 |  | Pekerjaan Cleaning Tangki 34-A-101-T-101 | RU6-POC | 34-A-101-T-101/00 | 50 | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C1H | 2671697 | 2232163 | MA3-STA |  | MARSHAL |  | 2026-05-05 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-06-17 | 2026-06-18 | 2026-06-22 | 2026-08-18 | 2102364777 | 8202243893 |  | PEK.PERB. PIPING OLS (3) | RU5-E15111 | 001-FT-0899/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 758163000 | 0 | MA2-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-05-07 | 2026-05-25 | 2026-05-08 | 2026-07-13 | 2102364135 | 8202243085 |  | Pek.Perb. Piping OLS (2) | RU5-E15111 | 001-FT-0899/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 566408000 | 0 | MA2-STA |  | FAUZANR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-08-04 | 2102366584 | 8202241669 |  | Pek. Smoke Fire Damper SS 01 MOC 2181 | RU6-UTL | SS-01/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-31 | 2026-04-06 | 2026-02-25 | 2026-02-25 | 2102364929 | 8202241980 |  | Pek. Penyehatan Online Analyzer (Tag. 5) | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | DWIHIZZKI |  |  | PT02 | 8 | 2 | 2026-02-25 | PM |  | 045
| K701 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2102369793 | 8202243730 |  | Pebaikan Equipment 1-V-03 | RU7-CDU | 1-V-03/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 6500 | 0 | MA-STA |  | YAYANHER |  | 2026-06-10 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 005
| K601 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-08-14 | 2102368306 | 8202242694 |  | Pebaikan Analyzer 32-AIC-010 | RU6-HSC | 32-E-101/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 19310779 | 16746810 | WS-INT |  | DANDARWANI |  | 2026-04-23 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K201 | 2026-04-17 | 2026-06-12 | 2026-11-30 | 2026-12-30 | 2102367771 | 8202242544 |  | Pebaikan 580-P-303 | RU2-UTL | 580-P-303B/00 | 50 | REL MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 380000000 | 0 | MA3-ROT |  | ADEMULYADI |  | 2026-04-17 | PT02 | 3 | 3 | 2026-11-30 | PM |  | 004
| K501 | 2026-05-12 | 2026-05-22 | 2026-05-13 | 2026-07-02 | 2102363519 | 8202243165 |  | PASANG & BONGKAR SCAFFOLDING BPP II (12) |  |  | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C1H | 1301629000 | 1301629000 | WS-POK |  | BETCYLYABS |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K301 | 2026-06-18 | 2026-06-18 | 2026-06-12 | 2026-06-12 | 2102369956 | 8202243953 |  | Overhaul Motor PM-61-331A | RU3-ITP | PM-61-331A/00 | 50 | CRTD CSER MACM PRC | 3ER |  | 0 | 0 | MA4-LIS |  | MALFINUSAR |  |  | PT02 | 3 | 2 | 2026-06-12 | PM |  | 045
| K601 | 2026-03-02 |  | 2026-02-24 | 2026-06-12 | 2102364893 | 8202239280 |  | Overhaul motor 42-P-915 | RU6-ITP | 42-P-915-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/26/B6/RT-C2H | 3557790 | 0 | MA4-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-02-24 | PM |  | 003
| K601 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-06-29 | 2102368409 | 8202242816 |  | Overhaul Motor 18P102 B | RU6-RCC | 18-P-102B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 863156 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K601 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-07-22 | 2102367938 | 8202242423 |  | Overhaul Minor Motor Finfan 33-E-101B2 | RU6-HSC | 33-E-101B2/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1453861 | 1361956 | MA3-LIS |  | DANDARWANI |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 003
| K601 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-07-23 | 2102367850 | 8202242382 |  | Overhaul Minor Motor Finfan 33-E-101B1 | RU6-HSC | 33-E-101B1/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1453861 | 1361956 | MA3-LIS |  | DANDARWANI |  | 2026-04-13 | PT02 | 5 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-06-23 |  | 2026-06-19 | 2026-06-19 | 2102370164 | 8202244050 |  | optimalisasi program digitalisasi |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-19 | PM |  | 045
| K601 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-06-15 | 2102368669 | 8202242988 |  | okvernoor Rusak | RU6-RCC | 15-P-118A-T/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 57000000 | 57000000 | MA1-ROT |  | DANDARWANI |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K701 | 2026-03-04 | 2026-03-04 | 2026-04-30 | 2026-04-30 | 2102365147 | 8202239417 |  | Oil Pump & Pulley driver 2-K-01/02 | RU7-NHT | 2-K-01-02/00 | 50 | REL CSER MSPT PRC SETC | 7RT | D17/26/B6/RT-2-D1H | 2 | 0 | MA-ROT |  | YAYANHER |  | 2026-03-04 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 005
| K601 | 2026-03-02 |  | 2026-02-24 | 2026-06-12 | 2102364870 | 8202239282 |  | OH Oil Sumpit 42-P-917 | RU6-ITP | 42-P-917-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/26/B6/RT-C2H | 3557790 | 0 | MA4-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-02-24 | PM |  | 003
| K501 | 2026-06-19 | 2026-06-22 | 2026-06-08 | 2026-12-30 | 2102359281 | 8202243979 |  | NRK-Revitalisasi Parit HCC & HSC |  |  | 50 | CRTD NMAT PRC | 5MR | D15/26/B6/RT-C2H | 4735000000 | 0 | MA3-STA |  | DWIYUDAAM |  |  | PT02 | 4 | 2 | 2026-06-08 | PM |  | 045
| K501 | 2026-03-03 |  | 2026-02-25 | 2026-08-30 | 2102364957 | 8202239330 |  | NRK_Perbaikan Turbine G-3-17B | RU5-E15112 | GT-3-17B/00 | 01 | CRTD CSER NMAT PRC | 5RR | D15/10/B6/RT1-03NH | 0 | 0 | MA3-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-02-25 | PM |  | 003
| K501 | 2026-05-26 |  | 2026-07-01 | 2026-08-28 | 2102369231 | 8202243505 |  | NRK_PERBAIKAN SOLAR CHARGER SPM 150 | RU5-TBL | SP-MOORING-BUOY/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 3 | 2 | 2026-07-01 | PM |  | 004
| K501 | 2026-02-23 | 2026-02-25 | 2026-02-09 | 2026-12-31 |  | 8202239064 | 8202238782 | NRK_Perbaikan Pompa G-3-01B | RU5-E15112 | G-3-01B/00 | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 58400000 | 0 | MA3-ROT |  | YONZHETG |  | 2026-02-25 | PT02 | 1 | 3 | 2026-02-09 | PM |  | 003
| K501 | 2026-05-18 | 2026-05-29 | 2026-11-03 | 2026-12-01 |  | 8202243238 | 8202241501 | NRK_PERBAIKAN PC & SOFTWARE LDS | RU5-TBL | SP-MOORING-BUOY/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  | RIANDAADI |  |  | PT02 | 5 | 2 | 2026-11-03 | PM |  | 004
| K501 | 2026-05-20 | 2026-05-29 | 2026-07-01 | 2026-09-25 | 2102368769 | 8202243319 |  | NRK_Perbaikan Komunikasi SCADAPack RTU | RU5-TBL | SP-MOORING-BUOY/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 196700000 | 0 | MA4-INT |  | BERNANDOP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 004
| K501 | 2026-06-10 | 2026-06-11 | 2026-12-01 | 2026-12-31 | 2102368939 | 8202243726 |  | NRK_PENGGANTIAN PROVER LPG PPKBBM | RU5-TBL | 22-MOV-791/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  | RIANDAADI |  |  | PT02 | 3 | 2 | 2026-12-01 | PM |  | 004
| K501 | 2026-02-22 | 2026-06-17 | 2026-02-02 | 2026-12-31 |  | 8202239006 | 8202234610 | NRK_Pemindahan Pompa G-3-01AC | RU5-E15112 | G-3-01C/00 | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 189000000 | 0 | MA3-ROT |  | FAUZANR |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-04-28 | 2026-06-08 | 2026-05-29 | 2026-07-14 | 2102368262 | 8202242791 |  | NRK_Pemasangan Modem Radio LDS SPM | RU5-TBL | SP-MOORING-BUOY/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 218300000 | 0 | MA4-INT |  | BERNANDOP |  | 2026-06-08 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 004
| K501 | 2026-04-22 | 2026-04-23 | 2026-05-29 | 2026-07-02 | 2102364888 | 8202242646 |  | NRK_Pekerjaan Refill FM-200 SS-62 | RU5-TBL | FM-2/00 | 01 | CRTD NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | HSSE |  | RIANDAADI |  |  | PT02 | 5 | 2 | 2026-05-29 | PM |  | 004
| K501 | 2026-04-24 | 2026-05-19 | 2026-12-07 | 2026-12-07 | 2102363534 | 8202242713 |  | NRK - pompa G-37-06AB | RU5-UTL | G-37-06A/00 | 50 | CLSD CSER MACM NCMP PRC RELR | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  |  | PT02 | 4 | 2 | 2026-05-19 | PM |  | 003
| K301 | 2026-05-07 | 2026-05-25 | 2026-01-01 | 2026-12-31 | 2102368831 | 8202243077 |  | NR26-Pompa Vibrasi | RU3-CDGP | CD4-P-008/00 | 60 | REL CSER GMPS MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 27738500 | 27738500 | MA1-ROT |  | ALEPDALITAN |  | 2026-05-08 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-02-20 | 2026-02-20 | 2026-02-02 | 2026-02-02 | 2102353029 | 8202238989 |  | NR26-Penggantian Saklar Lighting CDGP | RU3-CDGP | LP-83-1/00 | 50 WAMA | CRTD CSER MACM PRC | 3ER |  | 0 | 0 | MA1-LIS |  | APUGUHA |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 045
| K301 | 2026-05-18 | 2026-05-25 | 2026-05-18 | 2026-05-18 | 2102369043 | 8202243242 |  | NR26 -Valve stripping stm T2 CD VI | RU3-CDL | CDU-6-T-2/00 | 60 | REL CSER GMPS MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 7600000 | 7600000 | MA3-STA |  | ALEPDALITAN |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K301 | 2026-02-26 | 2026-02-26 | 2026-01-01 | 2026-12-31 | 2102364874 | 8202239214 |  | NR-26 Vibrasi P-4 CDU III | RU3-CDGP | CD3-P-004/00 | 50 | REL CSER MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 18932600 | 0 | MA1-ROT |  | RRAMADHANI |  | 2026-02-26 | PT02 | 4 | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-06-04 | 2026-06-11 | 2026-01-01 | 2026-12-31 | 2102368781 | 8202243619 |  | NR-26 Valve rusak | RU3-CDGP | FWSS-TK-1207/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/26/B6/NR-2-D2H | 5509621 | 0 | MA1-STA |  | RRAMADHANI |  | 2026-06-11 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-02-26 | 2026-04-29 | 2026-01-01 | 2026-12-31 | 2102364872 | 8202239210 |  | NR-26 Putus Membran Coupling | RU3-CDGP | CD5-P-010A/00 | 60 | REL CSER GMPS MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 18932600 | 18932600 | MA1-ROT |  | ALEPDALITAN |  | 2026-02-26 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 003
| K301 | 2026-03-05 | 2026-03-05 | 2026-01-01 | 2026-12-31 | 2102365795 | 8202239469 |  | NR-26 Bocor Mech Seal P-62-101A | RU3-CDGP | CD4-P-62-101A/00 | 50 | REL CSER MACM PRC SETC | 3MR | D13/26/B6/NR-2-D2H | 1535758 | 0 | MA1-ROT |  | RRAMADHANI |  | 2026-03-05 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-11 | 2026-03-10 | 2026-04-29 | 2102366368 | 8202241517 |  | Notifikasi Penggantian Pulley Mixer | RU6-ITP | 42-M-101A1/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 56488700 | 56484740 | MA4-ROT |  | ZAMZAMKHALID |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-05-26 | 2026-06-02 | 2026-05-25 | 2026-06-11 | 2102369345 | 8202243507 |  | Notifikasi Penggantian ATS 42-T-107B | RU6-ITP | 42-T-107B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 379501320 | 379500000 | MA4-INT |  | DANDARWANI |  | 2026-05-26 | PT02 | 4 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-28 | 2026-04-23 | 2026-09-09 | 2102368244 | 8202242750 |  | Notifikasi bearing 35-P-101 A | RU6-POC | 35-P-101A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 14118000 | 14118000 | MA3-ROT |  | DANDARWANI |  | 2026-04-28 | PT02 | 4 | 3 | 2026-04-23 | PM |  | 005
| K601 | 2026-04-01 | 2026-05-19 | 2026-02-24 | 2026-07-17 | 2102364844 | 8202242008 |  | Notifikasi MOC 2198 bpass CW 32A119 | RU6-HSC | 32-A-119/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 615000000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-04-01 | PT02 | 5 | 3 | 2026-02-24 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-19 | 2026-03-30 | 2026-03-30 |  | 8202243304 | 8202242594 | NON DESTRUCTIVE TEST (NDT) PERALATAN KIL | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 963000000 | 585849000 | MA1-STA |  | STEVANEKOPP |  | 2026-05-19 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 045
| K601 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-12-22 | 2102366430 | 8202241513 |  | NDT Internal Inspection Tangki Bola | RU6-ITP | 42-T-401B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 105640000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-10 | PM |  | 003
| K301 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102370134 | 8202243984 |  | N26-Rewinding Stator FLRS-PM-404C | RU3-CDL | FLRS-PM-404C/00 | 50 WAMA | CRTD CSER MACM PRC | 3ER |  | 0 | 0 | MA3-LIS |  | MALFINUSAR |  |  | PT02 | 5 | 2 | 2026-06-19 | PM |  | 045
| K301 | 2026-04-24 | 2026-04-29 | 2026-01-01 | 2026-12-31 | 2102368316 | 8202242708 |  | N26-Relay REF615 Feeder 2001K to SS#28PL |  |  | 60 | REL CSER GMPS MACM PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 124408800 | 124408800 | MA2-LIS |  | ALEPDALITAN |  | 2026-04-24 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-03-10 |  | 2026-02-09 | 2026-02-09 | 2102363837 | 8202241506 |  | N26-Perbaikan MCC PM-16 RPM AVAK | RU3-ITP | ITP-PM-02N/00 | 50 WAMA | CRTD CSER MACM PRC | 3ER |  | 10004795 | 0 | MA4-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-02-09 | PM |  | 005
| K301 | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-04-22 | 2102368271 | 8202242658 |  | N26-Peralatan electrical area FC-F-2 |  |  | 01 | CRTD CSER MACM PRC | 3ER |  | 5560930 | 0 | MA3-LIS |  | ARISNUGRAHA |  |  | PT02 | 5 | 2 | 2026-04-22 | PM |  | 045
| K301 | 2026-03-06 | 2026-04-29 | 2026-01-01 | 2026-12-31 | 2102366217 | 8202241344 |  | N26_Pek. Less Flow Outlet Furnace 2 CD 5 | RU3-CDGP | 85-PICA-830-8/00 | 60 | REL CSER GMPS MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 159819908 | 159819908 | MA1-STA |  | ALEPDALITAN |  | 2026-03-10 | PT02 | 4 | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-04-09 | 2026-04-13 | 2026-04-06 | 2026-04-06 | 2102367471 | 8202242249 |  | N26 - Overhaul PM-6C CD VI | RU3-CDL | CDU-6-PM-6C/00 | 50 WAMA | CRTD CSER MACM PRC | 3ER |  | 567524 | 0 | MA3-LIS |  | ARISNUGRAHA |  |  | PT02 | 3 | 2 | 2026-04-06 | PM |  | 045
| K301 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2102367798 | 8202242408 |  | N26 - Overhaul PM-008 A CD VI | RU3-CDL | CDU-6-PM-8A/00 | 50 WAMA | CRTD CSER MACM PRC | 3ER |  | 38146 | 0 | MA3-LIS |  | ARISNUGRAHA |  |  | PT02 | 3 | 2 | 2026-04-14 | PM |  | 045
| K301 | 2026-02-23 | 2026-04-29 | 2026-01-01 | 2026-12-31 | 2102353040 | 8202239079 |  | N_Perbaikan TT Wheelspace 3FO1 GT2015UA | RU3-UTL | FT-20255A/00 | 60 | REL CSER GMPS MACM PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 27375000 | 27375000 | MA2-INT |  | ALEPDALITAN |  | 2026-03-05 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-03-30 | 2026-04-10 | 2026-01-01 | 2026-12-31 | 2102353270 | 8202241928 |  | N_Penggantian Temp Transmitter TT20270B | RU3-UTL | TY-20270B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 1 | 0 | MA2-INT |  | RRAMADHANI |  | 2026-04-10 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-05-29 | 2026-06-11 | 2026-01-01 | 2026-12-31 | 2102369006 | 8202243548 |  | N_Penggantian Temp Transmitter CDU III | RU3-CDGP | CD3-TT-8304/00 | 50 WAMA | REL CSER MSPT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | ALEPDALITAN |  | 2026-06-02 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-06-02 | 2026-06-15 | 2026-12-31 | 2026-12-31 | 2102369458 | 8202243558 |  | N_Penggantian Spare Part MOV Rotork | RU3-ITP | 38-VAGM-T200OB/00 | 50 WAMA | REL MACM PRC SETC | 3IR | D13/26/B6/NR-2-D2H | 378000000 | 0 | MA4-INT |  | RRAMADHANI |  | 2026-06-11 | PT02 | 4 | 3 | 2026-12-31 | PM |  | 045
| K301 | 2026-03-10 | 2026-04-10 | 2026-01-01 | 2026-12-31 | 2102364575 | 8202241538 |  | N_Penggantian Solenoid EIV T173 | RU3-CDL | EIV-T-173-IN/00 | 50 WAMA | REL CSER MSPT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 1 | 0 | MA3-INT |  | RRAMADHANI |  | 2026-04-10 | PT02 | 5 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-05-07 | 2026-05-13 | 2026-01-01 | 2026-12-31 | 2102368340 | 8202243067 |  | N_Penggantian Solenoid Coil XY20257C | RU3-UTL | 2010-UC/00 | 50 WAMA | REL CSER MSPT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 2 | 0 | MA2-INT |  | RRAMADHANI |  | 2026-05-13 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-03-05 | 2026-04-02 | 2026-12-31 | 2026-12-31 | 2102366176 | 8202239740 |  | N_Penggantian Sensor O2 Analyzer CEMS | RU3-CDL | FC-LT-2602/00 | 50 WAMA | REL MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 178584000 | 0 | MA3-INT |  | ALEPDALITAN |  | 2026-03-09 | PT02 | 3 | 3 | 2026-12-31 | PM |  | 005
| K301 | 2026-05-29 | 2026-05-29 | 2026-04-09 | 2026-04-09 | 2102367717 | 8202243543 |  | N_Penggantian Remote Display ATG T210 | RU3-ITP | ATG-TK-210/00 | 50 | CRTD MACM PRC | 3MR |  | 68290000 | 0 | MA4-INT |  | MIFTAKHFH |  |  | PT02 | 4 | 2 | 2026-04-09 | PM |  | 045
| K301 | 2026-06-04 | 2026-06-04 | 2026-05-18 | 2026-05-18 | 2102369091 | 8202243631 |  | N_Penggantian Press Regulator PCV-20767 | RU3-UTL | XY20704/00 | 50 | CRTD CSER MACM PRC | 3MR |  | 1 | 0 | MA2-INT |  | MIFTAKHFH |  |  | PT02 | 3 | 2 | 2026-05-18 | PM |  | 005
| K301 | 2026-03-05 | 2026-05-18 | 2026-01-01 | 2026-12-31 | 2102353120 | 8202239475 |  | N_Penggantian Module C300 STN07 dan STN0 | RU3-UTL | UTL-DCS/00 | 50 WAMA | REL CSER MSPT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 3 | 0 | MA2-INT |  | MIFTAKHFH |  | 2026-04-28 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-03-02 | 2026-03-10 | 2026-12-31 | 2026-12-31 | 2102365071 | 8202239281 |  | N_Penggantian Loop Module RMS MOV | RU3-ITP | 34-VAGM-A-15IN/00 | 50 WAMA | REL MACM PRC SETC | 3IR | D13/26/B6/NR-2-D2H | 230000000 | 0 | MA4-INT |  | ALEPDALITAN |  | 2026-03-02 | PT02 | 5 | 3 | 2026-12-31 | PM |  | 005
| K301 | 2026-04-17 | 2026-05-11 | 2026-01-01 | 2026-12-31 | 2102367074 | 8202242532 |  | N_Penggantian Flow Meter FuelGas WHRU UC | RU3-UTL | FT-20234C/00 | 50 | REL CSER MSPT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 2 | 0 | MA2-INT |  | RRAMADHANI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-04-27 | 2026-05-11 | 2026-01-01 | 2026-12-31 | 2102367073 | 8202242765 |  | N_Penggantian Flame Scanner 45FTV 2015UA | RU3-UTL | 2015-UA/00 | 50 | REL CSER MSPT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 2 | 0 | MA2-INT |  | RRAMADHANI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-05-18 | 2026-06-17 | 2026-12-31 | 2026-12-31 | 2102367715 | 8202243264 |  | N_Penggantian ATG dan Pwr Spply EH | RU3-ITP | LT-A-008/00 | 50 WAMA | REL MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 695920000 | 0 | MA4-INT |  | ALEPDALITAN |  | 2026-06-02 | PT02 | 4 | 3 | 2026-12-31 | PM |  | 005
| K301 | 2026-02-25 | 2026-03-10 | 2026-02-27 | 2026-02-27 | 2102353290 | 8202239149 |  | N_Pengadaan Office Container ATG MA-IV | RU3-ITP | LT-A-010/00 | 50 WAMA | CRTD MACM PRC | 3IR |  | 98000000 | 0 | MA4-INT |  | ALEPDALITAN |  |  | PT02 | 5 | 2 | 2026-02-27 | PM |  | 045
| K301 | 2026-02-23 | 2026-05-29 | 2026-12-31 | 2026-12-31 | 2102353162 | 8202239078 |  | N_Pemasangan H2S Gas Detector CDL | RU3-CDL | FCC-CR-FGDS/00 | 50 WAMA | REL MACM PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 297199560 | 0 | MA3-INT |  | MIFTAKHFH |  | 2026-02-24 | PT02 | 3 | 3 | 2026-12-31 | PM |  | 005
| K301 | 2026-02-27 | 2026-03-05 | 2026-01-01 | 2026-12-31 | 2102365055 | 8202239260 |  | N_Pemasangan DP Flow Trans T1207/1208 | RU3-CDGP | ALK-LT-009/00 | 50 | REL CSER MSPT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 23397821 | 0 | MA1-INT |  | RRAMADHANI |  | 2026-03-05 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-27 | 2026-03-10 | 2026-12-31 | 2026-12-31 | 2102365036 | 8202239269 |  | N_Pemasangan Card TRL ATG Rosemount | RU3-ITP | LH-TK-200/00 | 50 WAMA | REL MACM PRC SETC | 3MR | D13/26/B6/NR-2-D2H | 180540000 | 0 | MA4-INT |  | ALEPDALITAN |  | 2026-03-02 | PT02 | 5 | 3 | 2026-12-31 | PM |  | 045
| K601 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-18 | 2102368497 | 8202242993 |  | Mtl Consmble Cleaning 11-E-105 Urgent | RU6-HSC | 11-E-105B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2218309 | 0 | MA1-STA |  | DANDARWANI |  | 2026-05-05 | PT02 | 2 | 3 | 2026-05-05 | PM |  | 004
| K401 | 2026-05-26 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102369118 | 8202243509 |  | MOV outlet 39T212 yoke sleeve rusak -rep | RU4-KPC |  | 50 | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 6 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 045
| K201 | 2026-05-21 | 2026-05-25 | 2026-07-01 | 2026-07-01 | 2102368330 | 8202243367 |  | Motor Vibrasi | RU2-HCC | 211-PM-31/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA2-LIS |  | AZIZFATONI |  | 2026-05-21 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K201 | 2026-03-03 | 2026-05-07 | 2026-02-11 | 2026-02-11 | 2102364156 | 8202239362 |  | Motor Rusak | RU2-HCC | 211-EM-18A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ER | D12/XX/B6/RT-C2NH | 250000 | 250000 | MA2-LIS |  | ERLANGGA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 003
| K401 | 2026-06-02 |  | 2026-05-20 | 2026-05-20 | 2102369117 | 8202243575 |  | monitor LHCS CCR rusak |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-05-20 | PM |  | 045
| K202 | 2026-05-13 | 2026-05-22 | 2026-04-28 | 2026-04-28 | 2102368530 | 8202243190 |  | Modifikasi pipa loading kero ke bridge |  | 10PL946Y77-A1A1/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 259647 | 259647 | MAS-ME1 |  | JUNAIDIT |  | 2026-05-21 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K501 | 2026-02-12 | 2026-03-03 | 2026-02-10 | 2026-12-31 | 2102364120 | 8202238872 |  | Modifikasi Line Kerosene Pertasolvent | RU5-D&W | 201-P163-6-B20/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 804725 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 001
| K501 | 2026-03-04 | 2026-03-04 | 2026-02-02 | 2026-12-31 | 2102359637 | 8202239413 |  | Modifikasi Line Flushing Sei Wain WTP 1 | RU5-UTL | PIPA-WTP-PCR/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 23690698 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 001
| K501 | 2026-03-06 | 2026-05-06 | 2026-03-06 | 2026-04-27 | 2102358759 | 8202241349 |  | Modifikasi Line Flare Aea M | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 114116406 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-12-31 | 2102369816 | 8202243733 |  | Modifikasi Bundwall Tangki 42T301ABCD | RU6-ITP | 42-T-301A/00 | 50 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 2000000001 | 0 | MA4-STA |  | JULIODWIP |  |  | PT02 | 3 | 2 | 2026-06-10 | PM |  | 003
| K501 | 2026-02-27 | 2026-03-06 | 2026-03-02 | 2026-04-21 |  | 8202239273 | 8202239270 | MOC Jumper Line Outlet Tank C20-01A(Add) | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD CSER MACM PRC | 5MR |  | 226529872 | 0 | MA4-STA |  | OCTARIOHS |  |  | PT02 | 4 | 2 | 2026-03-02 | PM |  | 003
| K501 | 2026-02-27 | 2026-05-06 | 2026-03-02 | 2026-04-21 | 2102360599 | 8202239270 |  | MOC Jumper Line Outlet Tangki C20-01A | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 83608181 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-20 | 2026-02-02 | 2026-02-02 | 2102355336 | 8202238726 |  | Membran booster 260PV335 bocor | RU4-LOC3 | 260PV335/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | FARIZSETYANA |  |  | PT02 | 5 | 2 | 2026-02-20 | PM |  | 003
| K201 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-23 | 2102360595 | 8202242465 |  | Mechseal Bocor | RU2-HCC | 212-P-13A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RR | D12/XX/B6/RT-D2NH | 334496 | 334219 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K701 | 2026-04-02 | 2026-04-02 | 2026-01-02 | 2026-01-02 | 2102367360 | 8202242046 |  | Mechanical Seal 1-PM-06A/B Rusak |  |  | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | YAYANHER |  | 2026-04-02 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K601 | 2026-05-22 | 2026-05-22 | 2026-05-20 | 2026-08-19 | 2102369213 | 8202243417 |  | Mechanical Cleaning 11-E-105 A | RU6-HSC | 11-E-105A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 24856036 | 23832036 | MA1-STA |  | DANDARWANI |  | 2026-05-22 | PT02 | 5 | 3 | 2026-05-20 | PM |  | 003
| K601 | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-05-18 | 2102368278 | 8202242706 |  | Mech. seal bocor | RU6-RCC | 16-P-109B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 6194446 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K501 | 2026-02-21 | 2026-05-04 | 2026-03-25 | 2026-09-25 |  | 8202239005 | 8202238949 | Mech Seal Pompa G-1-14B | RU5-E15111 | G-1-14A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 81000000 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K201 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-07 | 2102366807 | 8202241988 |  | Mech seal bocor | RU2-HCC | 211-P-9A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 9552975 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-01 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 005
| K201 | 2026-03-31 | 2026-05-19 | 2026-03-31 | 2026-04-06 | 2102366808 | 8202241989 |  | Mech seal bocor | RU2-HCC | 211-P-9C/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 9552817 | 7333398 | MA2-ROT |  | ADEMULYADI |  | 2026-04-01 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 005
| K201 | 2026-03-31 | 2026-04-01 | 2026-03-17 | 2026-03-27 | 2102366809 | 8202241990 |  | Mech seal bocor | RU2-HCC | 212-P-9A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 9552817 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-01 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 005
| K701 | 2026-03-20 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2102366745 | 8202241821 |  | Mech Seal 1-P-03 B Bocor | RU7-CDU | 1-P-03B/00 | 60 | REL CSER GMPS MANC PRC SETC | 7RT | D17/10/B6/RT1-CDUNH | 111906587 | 111906587 | MA-ROT |  | YAYANHER |  | 2026-03-20 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 005
| K401 | 2026-02-12 | 2026-03-16 | 2026-03-09 | 2026-12-30 | 2102364443 | 8202238900 |  | Measuring Tools Electrical Workshop | RU4-WS | 037BD101-6795Z2/00 | 50 | CLSD CSER MACM NCMP PRC | 4ER | D14/26/B6/RT-15-C1H | 159744717 | 0 | WS-LIS |  | WAHYUCATUR |  |  | PT02 | 4 | 2 | 2026-03-16 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-09 | 2026-04-08 | 2026-04-08 | 2102367677 | 8202242251 |  | Matl Perbaikan & Penggantian Valve POC | RU6-POC | 34-E-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 11026666 | 11026666 | MA3-STA |  | DANDARWANI |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K601 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2102367094 | 8202242349 |  | Matl EBJ Suction & Discharge 38-K-101 A | RU6-POC | 38-K-101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6MR | D16/26/B6/RT-C2H | 2 | 0 | MA3-STA |  | DANDARWANI |  | 2026-04-13 | PT02 | 4 | 3 | 2026-04-13 | PM |  | 003
| K601 | 2026-04-11 | 2026-04-11 | 2026-01-20 | 2026-07-28 |  | 8202242344 | 8202233889 | Matl Cons. Resertifikasi PSV | RU6-ITP | 42-T-101B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 67829677 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-11 | PT02 | 3 | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-05-21 | 2026-05-25 | 2026-05-21 | 2026-11-17 | 2102368905 | 8202243378 |  | Material Terminal Block 42-LT-043 | RU6-ITP | 42-LT-043/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16104 | 0 | MA4-INT |  | DANDARWANI |  | 2026-05-25 | PT02 | 7 | 3 | 2026-05-21 | PM |  | 003
| K601 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2102368355 | 8202242719 |  | Material tambahan valve 10 inch 32-A-119 | RU6-HSC | 32-A-119/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 28782081 | 28426067 | MA3-STA |  | DANDARWANI |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-24 | PM |  | 003
| K601 | 2026-04-29 | 2026-04-29 | 2026-02-26 | 2026-11-26 |  | 8202242844 | 8202239191 | Material tambahan 56-P-101A~H | RU6-UTL | 56-P-101A/00 | 50 WAMA | CLSD CSER MACM NCMP PRC | 6MR | D16/26/B6/RT-C2H | 163 | 0 | MA4-STA |  | HARSARIZANO |  |  | PT02 | 3 | 2 | 2026-04-29 | PM |  | 003
| K701 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2102366862 | 8202241865 |  | MATERIAL STOP UNIT CDU | RU7-CDU | 1-C-01/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 1000634 | 0 | MA-STA |  | YAYANHER |  | 2026-03-24 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 005
| K601 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2102367089 | 8202241982 |  | Material perbaikan support pipa fire | RU6-ITP | 42-T-301E/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 3342710 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-31 | PT02 | 4 | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-04-23 | 2026-05-25 | 2026-05-25 | 2026-06-26 |  | 8202242700 | 8202241782 | Material Perbaikan Pompa 35-P-101A | RU6-POC | 35-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 14118000 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-03 | 2026-02-09 | 2026-04-01 |  | 8202239358 | 8202238964 | Material Perbaikan Pompa 052-P-101B | RU6-UTL | 052-P-101B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 7704140 | 7700180 | MA4-ROT |  | DANDARWANI |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K601 | 2026-04-02 |  | 2026-10-01 | 2026-11-02 |  | 8202242049 | 8202241529 | Material Modif Pipa 20 inch Pig35000 (2) | RU6-ITP | 41-A-102/00 | 50 | CRTD CSER MACM PRC | 6MR | D16/26/B6/RT-C2H | 2907 | 0 | MA4-STA |  |  |  |  | PT02 | 5 | 2 | 2026-10-01 | PM |  | 003
| K601 | 2026-03-10 | 2026-04-02 | 2026-10-01 | 2026-11-02 | 2102366422 | 8202241529 |  | Material Modif Pipa 20 inch Pig 35000 | RU6-ITP | 41-A-102/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2904 | 0 | MA4-STA |  | MARSHAL |  | 2026-03-10 | PT02 | 5 | 3 | 2026-10-01 | PM |  | 003
| K601 | 2026-03-09 | 2026-03-09 | 2026-03-03 | 2026-07-24 |  | 8202241362 | 8202239394 | Material Electrical UCO Thp 1 | RU6-DHC | 21-S-101/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 48403087 | 0 | MA2-LIS |  | DANDARWANI |  | 2026-03-09 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-06-22 | 2026-06-22 | 2026-12-30 | 2026-12-30 | 2102370221 | 8202244024 |  | MATERIAL ELECTRICAL RU V | RU5-E15112 | C-2-101/00 | 50 | CRTD CSER MACM PRC | 5ER | D15/26/B6/RT-C2H | 156289452 | 0 | MA3-LIS |  | AGUSHIDAYAT |  |  | PT02 | 5 | 2 | 2026-12-30 | PM |  | 045
| K701 | 2026-02-11 | 2026-03-20 | 2026-01-02 | 2026-01-02 | 2102364264 | 8202238858 |  | Material Draft Gauge Area CDU Rusak |  |  | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-LINT |  | YAYANHER |  | 2026-03-18 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K701 | 2026-03-03 | 2026-04-07 | 2026-12-30 | 2026-12-30 |  | 8202239348 | 8202239341 | MATERIAL CONSUMABLE ME MARET 2026 |  |  | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 48215442 | 39251771 | MA-ROT |  | RYANMANGGASA |  | 2026-03-04 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 045
| K701 | 2026-04-10 | 2026-04-15 | 2026-04-16 | 2026-04-16 | 2102367737 | 8202242304 |  | Material Consumable April 2026 |  |  | 50 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 369990100 | 279708179 | MA-STA |  | RYANMANGGASA |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K601 | 2026-02-20 | 2026-02-23 | 2026-02-20 | 2026-02-20 | 2102364687 | 8202239004 |  | Material check valve 3" 30-P-902 | RU6-HSC | 30-P-902/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/XX/B6/RT-C1NH | 68600 | 0 | MA3-STA |  | DANDARWANI |  | 2026-02-23 | PT02 | 5 | 3 | 2026-02-20 | PM |  | 003
| K501 | 2026-04-05 | 2026-05-29 | 2026-04-06 | 2026-05-21 | 2102364964 | 8202242059 |  | MAT.Tie-in Flush Oil CDU IV to RFCC(MOC) | RU5-E15111 | 1-FO17-3-C3/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 460653847 | 0 | MA2-STA |  | BERNANDOP |  | 2026-05-29 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K501 | 2026-03-03 | 2026-06-17 | 2026-06-17 | 2026-07-01 | 2102365191 | 8202239334 |  | MAT.PERB.Tube E-3-35B | RU5-E15112 | E-3-35B/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 45719098 | 0 | MA3-STA |  | BERNANDOP |  | 2026-04-08 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K501 | 2026-04-07 | 2026-06-09 | 2026-04-07 | 2026-04-21 | 2102367325 | 8202242172 |  | MAT.PERB.EA-1-21 nomor 22 | RU5-E15111 | EA-1-21A/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 45441011 | 0 | MA2-STA |  | HENDRYS |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K501 | 2026-02-27 | 2026-06-11 | 2026-02-20 | 2026-02-27 | 2102364721 | 8202239272 |  | MAT.PERB.CHECK VALVE G-1-14C | RU5-E15111 | G-1-14C/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 84000000 | 0 | MA2-STA |  | BERNANDOP |  | 2026-04-08 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K501 | 2026-02-27 | 2026-06-11 | 2026-06-11 | 2026-06-19 | 2102364720 | 8202239271 |  | MAT.PERB.CHECK VALVE G-1-14B | RU5-E15111 | G-1-14B/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 89772273 | 0 | MA2-STA |  | BERNANDOP |  | 2026-04-08 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-25 | 2026-06-11 | 2026-06-11 | 2026-06-26 | 2102364853 | 8202239145 |  | MAT.PERB. Tube finfan EA-32-01O | RU5-E15112 | EA-32-01O/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 16150425 | 0 | MA3-STA |  | BERNANDOP |  | 2026-04-08 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-25 | 2026-06-11 | 2026-06-11 | 2026-06-26 | 2102364839 | 8202239142 |  | MAT.PERB. Tube finfan EA-32-01N | RU5-E15112 | EA-32-01N/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 16150425 | 0 | MA3-STA |  | BERNANDOP |  | 2026-04-08 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-24 | 2026-06-11 | 2026-06-11 | 2026-06-26 | 2102363919 | 8202239082 |  | MAT.PERB. Tube finfan EA-32-01M | RU5-E15112 | EA-32-01M/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 16150425 | 0 | MA3-STA |  | BERNANDOP |  | 2026-05-04 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-20 | 2102367044 | 8202242396 |  | MAT. GASKET E-3-44C | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/09/B6/RT1-03NH | 140 | 0 | MA3-STA |  | MANKURNIAWAN |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-02-12 | 2026-02-24 | 2026-02-12 | 2026-03-16 | 2102364117 | 8202238877 |  | Mat Per Pompa 15-P-102 Body F - SPKR 7 | RU6-RCC | 15-P-102A/00 | 50 | REL CSER GMCO GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3226075 | 3226075 | MA1-ROT |  | PANDUA |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 004
| K601 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-03-16 | 2102364116 | 8202238875 |  | Mat Per Pompa 15-P-101 Body F - SPKR 8 | RU6-RCC | 15-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 232028348 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 004
| K301 | 2026-06-11 | 2026-06-11 | 2026-06-10 | 2026-06-10 | 2102369826 | 8202243788 |  | MAL - Pompa 7 WTP Plaju |  |  | 01 WAMA | CRTD CSER MACM PRC | 3RR |  | 1773603 | 0 | MA2-ROT |  | AIRLANGGAS |  |  | PT02 | 3 | 2 | 2026-06-10 | PM |  | 045
| K601 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-04-17 | 2102365053 | 8202239204 |  | Makeup Rocksalt 21-V-108 | RU6-DHC | 21-V-108/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2092156 | 0 | MA2-STA |  | DANDARWANI |  | 2026-02-26 | PT02 | 5 | 3 | 2026-02-26 | PM |  | 003
| K601 | 2026-06-19 | 2026-06-19 | 2026-06-15 | 2026-06-30 | 2102369969 | 8202243958 |  | Makeup Rocksalt 21-V-108 | RU6-DHC | 21-V-108/00 | 50 | REL CSER MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 2698167 | 0 | MA2-STA |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-03-31 | 2026-04-06 | 2026-03-31 | 2026-05-18 | 2102367103 | 8202241975 |  | Lube oil trafo 11-V-101 B3 | RU6-HSC | 11-V-101B-3/01 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 49847000 | 49847000 | MA1-LIS |  | DINDINS |  | 2026-03-31 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K201 | 2026-04-22 | 2026-04-27 | 2026-10-10 | 2026-10-12 | 2102364684 | 8202242655 |  | Lube Oil Emulsi | RU2-HSC | 200-C-1A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/25/B6/RT-D2H | 1508577112 | 0 | MA2-ROT |  | ADEMULYADI |  |  | PT02 | 5 | 2 | 2026-10-10 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-22 | 2026-05-22 | 2026-05-22 | 2102369228 | 8202243980 |  | LTSA Water Sprinkle & Deluge System | RU2-HOC | 110-PIPING/00 | 50 | CRTD NMAT PRC RELR | 2MR | D12/09/B6/RT1-110NH | 4095250000 | 0 | MA1-STA |  | DJOKOTRIONO |  |  | PT02 | 3 | 2 | 2026-05-22 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-09-28 |  | 8202243180 | 8202233889 | LTSA Tabel Volume Tangki Thp 4 | RU6-ITP | 42-T-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 37100000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-13 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-09-28 |  | 8202243179 | 8202233889 | LTSA Tabel Volume Tangki Thp 3 | RU6-ITP | 42-T-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 41500000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-13 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-06-22 |  | 2026-06-22 | 2026-07-22 | 2102369366 | 8202244032 |  | LTSA Sweefblasting Outer Tube 52-B-101B | RU6-UTL | 52-B-101B/00 | 50 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 7423200 | 0 | MA4-STA |  |  |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K601 | 2026-05-06 | 2026-05-06 | 2026-05-04 | 2026-08-04 | 2102368711 | 8202243004 |  | LTSA steam leak Tahap 3 Area AHU | RU6-DHC | 12-E-527/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 99379000 | 84472150 | MA2-STA |  | DANDARWANI |  | 2026-05-06 | PT02 | 6 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-03-10 | 2026-03-26 | 2026-03-09 | 2026-07-30 | 2102366391 | 8202241528 |  | LTSA steam leak Tahap 2 | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 387370000 | 329264500 | MA1-STA |  | DANDARWANI |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-28 | 2026-01-19 | 2026-06-11 |  | 8202242240 | 8202238452 | LTSA Service Water Tahap 4 (85%) | RU6-UTL | 54SW0103MS0124N/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 204450500 | 204450500 | MA4-STA |  | DANDARWANI |  | 2026-04-09 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-09 | 2026-02-02 | 2026-05-08 | 2102351041 | 8202242265 |  | LTSA Scaffolding Tahap 5 | RU6-RCC | 19-C-102/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 407789000 | 407789000 | MA1-STA |  | DANDARWANI |  | 2026-04-09 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-03-02 | 2026-03-03 | 2026-03-03 | 2026-07-24 | 2102362321 | 8202239323 |  | LTSA Scaffolding Tahap 4 | RU6-DHC | 12-V-103/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 662131000 | 662131000 | MA1-STA |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-06-18 |  | 8202242808 | 8202242404 | LTSA Prbkan 15-P-102 Body G Tahap 11 | RU6-RCC | 15-P-102A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 142800000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-06-18 |  | 8202242806 | 8202242404 | LTSA Prbkan 15-P-102 Body C Tahap 9 | RU6-RCC | 15-P-102A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 145300000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-06-18 |  | 8202242807 | 8202242405 | LTSA Prbkan 15-P-101 Body B Tahap 10 | RU6-RCC | 15-P-101A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 146100000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-02-27 | 2026-03-03 | 2026-03-03 | 2026-04-22 | 2102365081 | 8202239254 |  | LTSA pompa 63-P-101C | RU6-ITP | 63-P-101C/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 240630000 | 204535500 | MA4-ROT |  | DANDARWANI |  | 2026-03-03 | PT02 | 6 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-06-11 | 2026-06-11 | 2026-03-03 | 2026-11-03 | 2102365269 | 8202243781 |  | LTSA PM Trafo 2026 | RU6-UTL | 01-PTR1-01A/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 21120 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-06-11 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-24 | 2026-06-09 | 2026-02-02 | 2026-12-30 | 2102351617 | 8202239088 |  | LTSA PM Motor MV | RU2-WS | PC-01/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 400000000 | 0 | WS-LAS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-06-10 | 2026-06-10 | 2026-05-25 | 2026-10-06 | 2102369389 | 8202243738 |  | LTSA PM General Purpose tahap 9 | RU6-ITP | 63-A-310A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 21047550 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 6 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-06-10 | 2026-06-10 | 2026-05-25 | 2026-10-06 | 2102369388 | 8202243736 |  | LTSA PM General Purpose tahap 6 (15%) | RU6-ITP | 63-A-310A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 30314250 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 6 | 3 | 2026-05-25 | PM |  | 003
| K701 | 2026-04-03 | 2026-04-03 | 2026-05-04 | 2026-05-04 |  | 8202242056 | 8202239174 | LTSA PM DEG 4-KDE-03 DE (SPK2) |  |  | 50 | REL GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-4-D2H | 136956000 | 136956000 | MA-ROT |  | YAYANHER |  | 2026-04-03 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K701 | 2026-02-26 | 2026-04-03 | 2026-12-30 | 2026-12-30 | 2102364949 | 8202239174 |  | LTSA PM DEG 4-KDE-03 DE (SPK1) |  |  | 60 | REL GMCO GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-4-D2H | 1090117000 | 1090117000 | MA-ROT |  | RYANMANGGASA |  | 2026-03-08 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 003
| K201 | 2026-06-09 | 2026-06-09 | 2026-07-24 | 2026-07-24 |  | 8202243725 | 8202240011 | LTSA PM DAN PEMASANGAN MECHANICAL SEAL J | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1000000000 | 181689000 | MA1-ROT |  | STEVANEKOPP |  | 2026-06-09 | PT02 | 3 | 3 | 2026-07-24 | PM |  | 045
| K201 | 2026-05-20 | 2026-06-11 | 2026-02-18 | 2026-12-30 | 2102364530 | 8202243318 |  | LTSA PM & CM Rotating Equipment UTL | RU2-UTL | 925-P-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-06-11 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K601 | 2026-03-10 | 2026-04-02 | 2026-03-05 | 2026-07-28 | 2102366205 | 8202241518 |  | LTSA Piping Works Tahap 8 (63-Z-305A/B) | RU6-ITP | 42-T-101D/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 117563850 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-04-02 |  | 2026-03-05 | 2026-07-28 |  | 8202242033 | 8202241518 | LTSA Piping Works Tahap 8 (63-Z-305A/B) | RU6-ITP | 42-T-101D/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 117563850 | 117563850 | MA4-STA |  |  |  | 2026-04-02 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-03-10 | 2026-04-02 | 2026-03-05 | 2026-07-28 | 2102366206 | 8202241519 |  | LTSA Piping Works Tahap 5 | RU6-ITP | 42-T-203B/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 25311300 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-04-02 | 2026-04-02 | 2026-03-05 | 2026-07-28 |  | 8202242032 | 8202241519 | LTSA Piping Works Tahap 5 | RU6-ITP | 42-T-203B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 25311300 | 25311300 | MA4-STA |  | DANDARWANI |  | 2026-04-02 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-03-10 | 2026-04-02 | 2026-03-05 | 2026-07-28 | 2102366203 | 8202241516 |  | LTSA Piping Works Tahap 13 | RU6-ITP | 42-PIPE/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 102295350 | 0 | MA4-STA |  | DANDARWANI |  | 2026-03-10 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-04-02 |  | 2026-03-05 | 2026-07-28 |  | 8202242036 | 8202241516 | LTSA Piping Works Tahap 13 | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 102295350 | 102295350 | MA4-STA |  |  |  | 2026-04-02 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-04-06 | 2026-04-06 | 2026-03-13 | 2026-09-18 | 2102366673 | 8202242125 |  | LTSA Piping Works Tahap 11 | RU6-DHC | 22-F-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 69419500 | 0 | MA2-STA |  | DANDARWANI |  | 2026-04-06 | PT02 | 5 | 3 | 2026-03-13 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-10 | 2026-05-07 | 2026-09-22 | 2102368835 | 8202243705 |  | LTSA Piping Work tahap 7 (15%) | RU6-ITP | 42-PIPE/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 33101250 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 5 | 3 | 2026-05-07 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-10 | 2026-05-07 | 2026-09-22 | 2102368833 | 8202243704 |  | LTSA Piping Work tahap 2 (15%) | RU6-ITP | 42-PIPE/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 33795000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 4 | 3 | 2026-05-07 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-18 | 2026-06-15 | 2026-10-22 | 2102369976 | 8202243877 |  | LTSA Piping tahap 4 area DHC (TKDN) | RU6-DHC | 14-V-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 273180000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-15 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-19 | 2026-12-30 | 2026-12-30 |  | 8202243305 | 8202242594 | LTSA Piping Boardesk HSC SP 3950471422 | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA1-STA |  | STEVANEKOPP |  | 2026-05-19 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 045
| K201 | 2026-04-20 | 2026-04-21 | 2026-10-30 | 2026-10-30 |  | 8202242594 | 8202241701 | LTSA PERBAIKAN/ PEMELIHARAAN WATER SPRIN | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-04-21 | PT02 | 3 | 3 | 2026-10-30 | PM |  | 045
| K601 | 2026-04-17 |  | 2026-04-10 | 2026-04-10 |  | 8202242533 | 8202242528 | LTSA Perbaikan Support DHC 24-26 | RU6-DHC | 14-C-201/00 | 01 | CRTD CSER NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 003
| K201 | 2026-03-13 | 2026-03-13 | 2026-12-02 | 2026-12-02 |  | 8202241723 | 8202241701 | LTSA PERBAIKAN STEAM LEAKS NON TRAP AREA | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | STEVANEKOPP |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K601 | 2026-02-24 | 2026-03-03 | 2026-03-03 | 2026-07-24 | 2102351029 | 8202239097 |  | LTSA Perbaikan SS & OS Tahap 8 | RU6-DHC | GROUNDSYS-14/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 125533000 | 106703050 | MA2-LIS |  | DANDARWANI |  | 2026-03-03 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-26 | 2026-02-02 | 2026-06-29 | 2102351030 | 8202239098 |  | LTSA Perbaikan SS & OS Tahap 7 | RU6-ITP | 23-ANN-01/00 | 50 | REL GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 123747000 | 105184950 | MA4-LIS |  | DANDARWANI |  | 2026-02-24 | PT02 | 6 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-26 | 2026-02-24 | 2026-07-17 | 2102351028 | 8202239096 |  | LTSA Perbaikan SS & OS Tahap 6 | RU6-HSC | SS-17/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 212883000 | 180950550 | MA3-STA |  | DANDARWANI |  | 2026-02-24 | PT02 | 5 | 3 | 2026-02-24 | PM |  | 003
| K201 | 2026-06-08 | 2026-06-09 | 2026-10-12 | 2026-10-12 |  | 8202243703 | 8202241756 | LTSA PERBAIKAN ROOF TANK DENGAN METODE | RU2-ITP | 945-T-35/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 86900000 | 0 | MA3-STA |  | ADEMULYADI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-10-12 | PM |  | 045
| K601 | 2026-04-17 |  | 2026-04-10 | 2026-04-10 |  | 8202242537 | 8202242528 | LTSA Perbaikan Pagar Area DHC 25-26 | RU6-DHC | 14-C-201/00 | 01 | CRTD CSER NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 003
| K601 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-10-27 | 2102369159 | 8202243961 |  | LTSA Perbaikan General Purpose Thp 11 | RU6-ITP | 42-T-101D/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 221621000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K201 | 2026-04-15 | 2026-06-05 | 2026-12-14 | 2026-12-14 | 2102364442 | 8202242451 |  | LTSA Perbaikan Fire Protection area OM | RU2-ITP | 945-T-11-FCT-1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA4-STA |  | ADEMULYADI |  | 2026-04-21 | PT02 | 5 | 3 | 2026-12-14 | PM |  | 003
| K201 | 2026-04-22 | 2026-04-22 | 2026-12-11 | 2026-12-11 |  | 8202242659 | 8202241554 | LTSA PERBAIKAN DAN PENGGANTIAN PIPING ST | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 700000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-04-22 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-04-29 | 2026-05-04 | 2026-12-02 | 2026-12-02 |  | 8202242838 | 8202241701 | LTSA PERBAIKAN DAN PENGGANTIAN PIPING ST | RU2-HCC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 486052000 | MA1-STA |  | ADEMULYADI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K601 | 2026-04-29 | 2026-05-11 | 2026-04-06 | 2026-08-20 |  | 8202242813 | 8202242157 | LTSA Perawatan AC Tahap 4 (85%) | RU6-RCC | 20-FV-030/00 | 50 | REL GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 414876500 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-29 | PT02 | 5 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-05-19 | 2026-05-20 | 2026-05-19 | 2026-09-30 | 2102369157 | 8202243302 |  | LTSA Penyediaan N2 tahap 16 | RU6-ITP | 42-T-401B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 162330000 | 137980500 | MA4-STA |  | DANDARWANI |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K201 | 2026-03-10 | 2026-05-26 | 2026-12-11 | 2026-12-11 | 2102364145 | 8202241554 |  | LTSA Penggantian Piping Steam Leak | RU2-HCC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 500000000 | MA2-STA |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-03-09 | 2026-06-11 | 2026-02-12 | 2026-02-12 | 2102364441 | 8202241486 |  | LTSA Pengecatan equipment area OM | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA4-STA |  | AHILMANSYAH |  | 2026-03-11 | PT02 | 7 | 3 | 2026-02-12 | PM |  | 045
| K201 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  | 8202243802 | 8202241486 | LTSA Pengecatan Equipment | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 700000000 | 0 | MA4-STA |  | AHILMANSYAH |  | 2026-06-11 | PT02 | 7 | 3 | 2026-06-11 | PM |  | 045
| K601 | 2026-04-07 | 2026-04-08 | 2026-03-05 | 2026-07-28 | 2102366208 | 8202242174 |  | LTSA Pengadaan N2 Tahap 15 TKDN | RU6-ITP | 42-T-402A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 41800500 | 41800500 | MA4-STA |  | DANDARWANI |  | 2026-04-08 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-03-05 | 2026-07-28 | 2102366207 | 8202242162 |  | LTSA Pengadaan N2 Tahap 13 TKDN | RU6-ITP | 42-T-404H/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 38256750 | 38256750 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 6 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-04 | 2026-03-03 | 2026-07-24 | 2102365256 | 8202239423 |  | LTSA Pemeriksaan dan Pengujian 52-B-101F | RU6-UTL | 52-B-101F/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 52750000 | 52750000 | MA4-STA |  | DANDARWANI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-03-12 | 2026-03-13 | 2026-12-14 | 2026-12-14 |  | 8202241657 | 8202241614 | LTSA PEMELIHARAAN/PERBAIKAN THERMAL INSU | RU2-HSC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 200005000 | MA3-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-14 | PM |  | 045
| K201 | 2026-03-12 | 2026-03-13 | 2026-12-14 | 2026-12-14 |  | 8202241617 | 8202241614 | LTSA PEMELIHARAAN THERMAL INSULATION ARE | RU2-ITP |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 135028000 | MA3-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-14 | PM |  | 045
| K501 | 2026-02-27 | 2026-04-06 | 2026-03-31 | 2026-07-03 | 1102329925 | 8202239248 |  | LTSA PEMELIHARAAN ONLINE ANALYZER (4) | RU5-E15111 | 01-AIT-539/00 | 50 | CLSD NCMP NMAT PRC | 5IR | D15/26/B6/RT-C2H | 150029000 | 0 | WS-INT |  | RUDIEKO |  |  | PT02 | 3 | 2 | 2026-04-06 | PM |  | 045
| K201 | 2026-04-22 | 2026-05-26 | 2026-12-02 | 2026-12-02 |  | 8202242654 | 8202239992 | LTSA PEMELIHARAAN DAN PERBAIKAN SOOT BLO | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 2000000000 | 1692215000 | MA1-LIS |  | ADEMULYADI |  | 2026-04-22 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K601 | 2026-06-08 | 2026-06-12 | 2026-05-25 | 2026-10-06 | 2102369365 | 8202243679 |  | LTSA Pemeliharaan Boiler 52-B-101C | RU6-UTL | 52-B-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 16601250 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-12 | 2026-05-25 | 2026-07-24 | 2102369363 | 8202243678 |  | LTSA Pemeliharaan Boiler 52-B-101A | RU6-UTL | 52-B-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 13953000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-06-08 | 2026-06-12 | 2026-05-25 | 2026-07-24 | 2102369362 | 8202243677 |  | LTSA Pemeliharaan Boiler 052-B-101A | RU6-UTL | 52-B-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 13953000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-12 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K201 | 2026-04-29 | 2026-05-04 | 2026-12-02 | 2026-12-02 |  | 8202242837 | 8202241701 | LTSA PEMELIHARAAN & CLEANING FILTER PERI | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K601 | 2026-04-08 | 2026-05-12 | 2026-03-10 | 2026-06-19 | 2102366433 | 8202242192 |  | LTSA Patching Wrapping Pipa Tahap 3 RCC | RU6-RCC | 15-V-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 534442000 | 534400000 | MA1-STA |  | DANDARWANI |  | 2026-04-08 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-03-30 | 2026-04-07 | 2026-03-12 | 2026-08-04 | 2102366587 | 8202241936 |  | LTSA Patching Wrapping Pipa Tahap 2 UTL | RU6-UTL | 56-CT-101A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 73537000 | 73537000 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-04-17 |  | 2026-04-10 | 2026-04-10 |  | 8202242538 | 8202242528 | LTSA OPEN SEWER 25-27 | RU6-DHC | 14-C-201/00 | 01 | CRTD CSER NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 003
| K601 | 2026-02-26 | 2026-03-04 | 2026-02-25 | 2026-04-16 |  | 8202239215 | 8202239206 | LTSA Online Leak Sealing Tahap 53 2026 | RU6-DHC | 13-R-102/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 387033000 | 387033000 | MA2-STA |  | DANDARWANI |  | 2026-03-04 | PT02 | 5 | 3 | 2026-02-25 | PM |  | 003
| K601 | 2026-03-03 | 2026-03-05 | 2026-03-03 | 2026-04-22 |  | 8202239352 | 8202239213 | LTSA Online Leak Sealing Tahap 52 2026 ( | RU6-POC | 38-E-110/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 307979000 | 307979000 | MA3-STA |  | DANDARWANI |  | 2026-03-05 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-26 | 2026-03-03 | 2026-03-03 | 2026-04-22 |  | 8202239213 | 8202239206 | LTSA Online Leak Sealing Tahap 52 2026 | RU6-POC | 38-E-110/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 1 | 0 | MA3-STA |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-26 | 2026-03-03 | 2026-03-03 | 2026-04-22 |  | 8202239211 | 8202239206 | LTSA Online Leak Sealing Tahap 50 2026 | RU6-DHC | 14-E-102H/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 94016000 | 94016000 | MA2-STA |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-08-26 |  | 8202242319 | 8202237754 | LTSA Online Leak Sealing Tahap 49 (85%) | RU6-HSC | 32PG4803PR366H/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 92890550 | 92890550 | MA3-STA |  | DANDARWANI |  | 2026-04-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K601 | 2026-02-26 | 2026-03-03 | 2026-03-03 | 2026-04-22 |  | 8202239208 | 8202239206 | LTSA Online Leak Sealing Tahap 46 2026 | RU6-DHC | 22-E-102G/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 91676000 | 91676000 | MA2-STA |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-26 | 2026-04-24 | 2026-02-25 | 2026-07-20 | 2102364941 | 8202239206 |  | LTSA Online Leak Sealing Tahap 45 2026 | RU6-DHC | 13-F-101/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 105172000 | 105172000 | MA2-STA |  | DANDARWANI |  | 2026-02-26 | PT02 | 5 | 3 | 2026-02-25 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-15 | 2026-03-26 | 2026-08-11 | 2102366953 | 8202242461 |  | LTSA OLS Thp 4 (UTL) | RU6-UTL | 52-B-101D/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 156870000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K601 | 2026-03-31 | 2026-04-01 | 2026-03-26 | 2026-08-11 | 2102366973 | 8202241993 |  | LTSA OLS Thp 3 (RCC) | RU6-RCC | 16-E-116A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 330060000 | 280551000 | MA1-STA |  | DANDARWANI |  | 2026-04-01 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K601 | 2026-03-31 | 2026-04-01 | 2026-03-27 | 2026-08-12 | 2102366976 | 8202241992 |  | LTSA OLS Thp 2 (DHC) | RU6-DHC | 14-P-107A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 106100000 | 90185000 | MA2-STA |  | DANDARWANI |  | 2026-04-01 | PT02 | 6 | 3 | 2026-03-27 | PM |  | 003
| K601 | 2026-03-31 | 2026-04-01 | 2026-03-27 | 2026-08-12 | 2102366992 | 8202241985 |  | LTSA OLS Thp 1 (POC) | RU6-POC | 37-R-101B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 45490000 | 38666500 | MA3-STA |  | DANDARWANI |  | 2026-04-01 | PT02 | 4 | 3 | 2026-03-27 | PM |  | 003
| K601 | 2026-06-05 | 2026-06-08 | 2026-06-04 | 2026-10-13 | 2102369571 | 8202243667 |  | LTSA Maintenance Bawah Thp 1 | RU6-ITP | 41-A-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 372090000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-08 | PT02 | 4 | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-21 | 2026-04-16 | 2026-09-02 | 2102368075 | 8202242609 |  | LTSA Maint Bawah Air SPM & Jetty Thp 5 | RU6-ITP | 41-A-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 29119500 | 29119500 | MA4-STA |  | DANDARWANI |  | 2026-04-21 | PT02 | 6 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-21 | 2026-04-16 | 2026-09-02 | 2102368074 | 8202242607 |  | LTSA Maint Bawah Air SPM & Jetty Thp 3 | RU6-ITP | 41-A-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 75636750 | 75636750 | MA4-STA |  | DANDARWANI |  | 2026-04-21 | PT02 | 6 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-04-21 | 2026-04-21 | 2026-04-16 | 2026-09-02 | 2102368072 | 8202242604 |  | LTSA Maint Bawah Air SPM & Jetty Thp 2 | RU6-ITP | 41-A-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 17852400 | 17852400 | MA4-STA |  | DANDARWANI |  | 2026-04-21 | PT02 | 6 | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-04-14 | 2026-04-20 | 2026-04-20 | 2026-09-04 | 2102367601 | 8202242417 |  | LTSA Leveling Tahap 2 Area OM (15%) | RU6-ITP | WWT-STORAGE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C1H | 134241750 | 134241750 | MA4-STA |  | DANDARWANI |  | 2026-04-14 | PT02 | 6 | 3 | 2026-04-20 | PM |  | 003
| K601 | 2026-05-05 | 2026-05-06 | 2026-04-24 | 2026-12-31 |  | 8202242987 | 8202242985 | LTSA Leveling Area UTL 24-26 Tahap 4 | RU6-UTL | 056-P-101B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 595600000 | 506260000 | MA4-STA |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K601 | 2026-05-05 |  | 2026-04-24 | 2026-04-24 |  | 8202242985 | 8202242984 | LTSA Leveling Area UTL 24-26 | RU6-UTL | 56-P-101H-P1B/00 | 01 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-24 | PM |  | 003
| K601 | 2026-04-24 |  | 2026-04-24 | 2026-04-24 |  | 8202242725 | 8202242724 | LTSA Leveling Area OM 24-26 | RU6-ITP | 42-T-201A/00 | 01 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-24 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-20 | 2026-04-10 | 2026-10-08 |  | 8202242539 | 8202242531 | LTSA Leveling Area DHC 24-26 Tahap 11 | RU6-DHC | 14-C-201/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 197120000 | 167552000 | MA2-STA |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-20 | 2026-04-10 | 2026-04-10 |  | 8202242531 | 8202242528 | LTSA Leveling Area DHC 24-26 | RU6-DHC | 14-C-201/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K601 | 2026-03-30 | 2026-04-07 | 2026-03-12 | 2026-08-04 | 2102366589 | 8202241943 |  | LTSA hot Insulation Tahap 9 area UTL | RU6-UTL | 52-B-101A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 218141000 | 218141000 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-04-08 | 2026-04-08 | 2026-04-02 | 2026-07-07 | 2102367292 | 8202242189 |  | LTSA hot Insulation Tahap 10 area NPU | RU6-HSC | 31-E-101A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 348736000 | 348736000 | MA3-STA |  | DANDARWANI |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-02 | PM |  | 003
| K601 | 2026-05-20 | 2026-05-20 | 2026-04-24 | 2026-09-10 |  | 8202243341 | 8202243338 | LTSA GRID CHAMBER Tahap 3 | RU6-UTL | 54-V-103/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 230720000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-20 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K601 | 2026-05-20 |  | 2026-04-24 | 2026-04-24 |  | 8202243338 | 8202242984 | LTSA GRID CHAMBER 2023-2026 | RU6-UTL | 54-V-103/00 | 01 | CRTD NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-24 | PM |  | 003
| K601 | 2026-05-05 | 2026-05-05 | 2026-04-27 | 2026-06-17 | 2102368443 | 8202242983 |  | LTSA Fin Fan Prbaikan (Major Rep) SPKR 4 | RU6-RCC | 15-E-110AN/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 321281000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-05 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K201 | 2026-04-08 | 2026-04-28 | 2026-02-02 | 2026-02-02 | 2102351052 | 8202242206 |  | LTSA DIESEL ENGINE CATERPIL | RU2-UTL | 905-DEG-01/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 500000000 | 0 | MA3-ROT |  | MDSYAHPUTRA |  | 2026-04-28 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-03-06 | 2026-05-26 | 2026-03-05 | 2026-03-05 | 2102366142 | 8202241318 |  | LTSA DC System dan UPS | RU2-HCC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1400000000 | 1015200000 | MA2-INT |  | ADEMULYADI |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-05 | PM |  | 045
| K701 | 2026-04-24 | 2026-04-24 | 2026-12-30 | 2026-12-30 | 2102366743 | 8202242711 |  | LTSA Crane Link belt RTC 8050 Lanjutan | RU7-WS | 7-CR-04/00 | 50 | REL GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-5-D1H | 443576800 | 94295510 | MA-ROT |  | RIZKAANDIKAP |  | 2026-04-24 | PT02 | 6 | 3 | 2026-12-30 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-22 | 2026-04-06 | 2026-12-30 | 2102367444 | 8202243981 |  | LTSA CONMON ROT | RU2-HSC |  | 50 | CRTD NMAT PRC RELR | 2RR | D12/25/B6/RT-D2H | 2100000000 | 0 | MA2-ROT |  | ADEMULYADI |  |  | PT02 | 3 | 2 | 2026-04-06 | PM |  | 045
| K601 | 2026-04-24 | 2026-05-06 | 2026-04-08 | 2026-07-10 | 2102367678 | 8202242721 |  | LTSA Cold Insulation Tahap 6 Area POC | RU6-POC | 34-P-107A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 96700000 | 96700000 | MA3-STA |  | DANDARWANI |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-22 | 2026-04-17 | 2026-04-17 | 2102368149 | 8202243352 |  | LTSA CM Water Treatment Pump | RU2-UTL | 520-P-607A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K601 | 2026-06-05 | 2026-06-08 | 2026-05-19 | 2026-09-30 | 2102369158 | 8202243668 |  | LTSA Cleaning Minyak Ringan Thp 7 103B | RU6-ITP | 42-T-103B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 281950000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-08 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-06-10 | 2026-06-10 | 2026-05-25 | 2026-10-06 | 2102369373 | 8202243740 |  | LTSA Cleaning Minyak Ringan Thp 2 - 15% | RU6-ITP | 63-A-310A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 45893700 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 6 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-06-10 | 2026-06-10 | 2026-05-25 | 2026-10-06 | 2102369372 | 8202243739 |  | LTSA Cleaning Minyak Ringan Tahap 1 (15% | RU6-ITP | 63-A-310A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 31732437 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-10 | PT02 | 6 | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-04-22 | 2026-04-22 | 2026-04-21 | 2026-07-23 | 2102368215 | 8202242651 |  | LTSA Cleaning HE 31-E-102A Tahap 2 | RU6-HSC | 31-E-102A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 68900000 | 0 | MA3-STA |  | DANDARWANI |  | 2026-04-22 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-20 | 2026-02-19 | 2026-08-27 |  | 8202242536 | 8202238957 | LTSA BBM ke Salamdarma Thp 7 (85%) | RU6-UTL | 53-T-301A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 63750000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-04-17 | 2026-04-20 | 2026-02-19 | 2026-08-27 |  | 8202242535 | 8202238957 | LTSA BBM ke Salamdarma Thp 6 (85%) | RU6-UTL | 53-T-301A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 76500000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-20 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-02-19 | 2026-04-17 | 2026-02-19 | 2026-07-28 |  | 8202238959 | 8202238957 | LTSA BBM ke Salamdarma Thp 5 (85%) | RU6-UTL | 53-T-301A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 80325000 | 80325000 | MA4-STA |  | ZAMZAMKHALID |  | 2026-02-19 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-02-19 | 2026-04-17 | 2026-02-19 | 2026-07-28 |  | 8202238958 | 8202238957 | LTSA BBM ke Salamdarma Thp 4 (85%) | RU6-UTL | 53-T-301A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 77775000 | 77775000 | MA4-STA |  | ZAMZAMKHALID |  | 2026-02-19 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-02-19 | 2026-04-17 | 2026-02-19 | 2026-07-28 | 2102364573 | 8202238957 |  | LTSA BBM ke Salamdarma Thp 3 (85%) | RU6-UTL | 53-T-301A/00 | 60 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 71400000 | 71400000 | MA4-STA |  | ZAMZAMKHALID |  | 2026-02-19 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-04-29 | 2026-04-29 | 2026-04-10 | 2026-08-27 |  | 8202242821 | 8202242805 | LTSA Bangunan Dlm Kilang Thn 25-26 Thp 7 | RU6-DHC | 14-C-201/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 66740000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K601 | 2026-04-29 | 2026-04-29 | 2026-04-10 | 2026-08-27 |  | 8202242819 | 8202242805 | LTSA Bangunan Dlm Kilang Thn 25-26 Thp 6 | RU6-DHC | 14-C-201/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 91250000 | 77562500 | MA2-STA |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K601 | 2026-05-18 | 2026-05-18 | 2026-04-10 | 2026-12-31 |  | 8202243246 | 8202242805 | LTSA Bangunan Dalam Kilang Thp 8 (85%) | RU6-DHC | 14-C-201/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 74009500 | 0 | MA2-STA |  | DANDARWANI |  | 2026-05-18 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K601 | 2026-04-28 | 2026-04-28 | 2026-04-10 | 2026-04-10 |  | 8202242805 | 8202242528 | LTSA Bangunan Dalam Kilang Thn 25-26 | RU6-DHC | 14-C-201/00 | 01 | CRTD CSER NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | JANUARM |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 003
| K501 | 2026-03-12 | 2026-05-04 | 2026-03-12 | 2026-05-04 | 2102363933 | 8202241659 |  | Line Press Pompa OC Kaki Jetty 5 Leaking | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 7700744 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K501 | 2026-03-12 | 2026-05-04 | 2026-03-12 | 2026-05-04 | 2102363928 | 8202241668 |  | Line Ejector OC Kaki Jetty 5 Leaking | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 21217107 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K501 | 2026-06-22 | 2026-06-23 | 2026-06-22 | 2026-08-03 | 2102367791 | 8202243987 |  | Line Disch Pompa AO/ASA 1" St 2 Leak | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 4128788 | 0 | MA4-STA |  | BERNANDOP |  | 2026-06-23 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K301 | 2026-03-27 |  | 2026-03-16 | 2026-03-16 | 2102366725 | 8202241901 |  | Line caustic C-206 ke E-208 | RU3-PP | 22-PICA-010-3/00 | 50 | CRTD NMAT PRC | 3MR |  | 0 | 0 | MA2-STA |  |  |  |  | PT02 | 7 | 2 | 2026-03-16 | PM |  | 003
| K501 | 2026-04-14 | 2026-05-06 | 2026-04-14 | 2026-06-03 | 2102367556 | 8202242397 |  | Line 913-20" depan Pompa 6 A Putih Leak | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 59364789 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K501 | 2026-04-13 | 2026-05-06 | 2026-04-13 | 2026-06-02 | 2102367853 | 8202242389 |  | Line 421-18" belakang gudang RPA Leak | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 205484407 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-04-13 | 2026-05-06 | 2026-04-13 | 2026-06-02 | 2102367710 | 8202242355 |  | Line 21P421-18" LSWR Jl 114 Leak | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 155357178 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K701 | 2026-02-11 | 2026-05-01 | 2026-05-04 | 2026-05-04 | 2102363869 | 8202238854 |  | Level Switch 5-LSHH-428/429 Rusak | RU7-OFF | 5-LSHH-428/00 | 60 | REL CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-5-D3H | 84000000 | 84000000 | MA-STA |  | YAYANHER |  | 2026-05-01 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 005
| K401 | 2026-03-02 | 2026-03-02 | 2026-02-24 | 2026-02-24 | 2102364895 | 8202239299 |  | Layar Transmitter 106-LI-012 B Buram | RU4-RFCGTO | 106LI-U106/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-02 | PM |  | 003
| K701 | 2026-04-09 | 2026-04-09 | 2026-12-30 | 2026-12-30 | 2102364503 | 8202242266 |  | Lanjutan Conmon Peralatan Rotating |  |  | 50 | REL GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-5-D2H | 1422570000 | 262225000 | MA-ROT |  | RIZKAANDIKAP |  | 2026-04-09 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 003
| K401 | 2026-03-06 | 2026-05-06 | 2026-03-06 | 2026-08-31 | 2102364984 | 8202241331 |  | lamp, indicator, AD11622DS/MFS, 220V, ye | RU4-WS | 048A201-IGN/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 0 | WS-TLS |  | WAHYUCATUR |  | 2026-03-07 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 045
| K301 | 2026-02-27 | 2026-03-10 | 2026-01-01 | 2026-01-01 | 2102353371 | 8202239249 |  | KV Cleaning dan Pngerukan Lmpr SG |  |  | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  |  | PT02 | 5 | 2 | 2026-01-01 | PM |  | 045
| K201 | 2026-04-13 | 2026-04-13 | 2026-12-11 | 2026-12-11 |  | 8202242360 | 8202241483 | Kontrak Volume PM Compliance RU II Dumai | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 500000000 | 0 | MA2-ROT |  | MAULANAHARUN |  | 2026-04-13 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-06-02 | 2026-06-09 | 2026-03-31 | 2026-03-31 |  | 8202243572 | 8202238410 | Kontrak Semenisasi All Area RU II Dumai | RU2-UTL | 940-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 450300000 | 0 | MA1-STA |  | AHILMANSYAH |  | 2026-06-09 | PT02 |  | 3 | 2026-03-31 | PM |  | 003
| K201 | 2026-06-02 | 2026-06-09 | 2026-03-31 | 2026-03-31 |  | 8202243571 | 8202238410 | Kontrak Semenisasi All Area | RU2-HSC | 100-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 700000000 | 0 | MA1-STA |  | AHILMANSYAH |  | 2026-06-09 | PT02 |  | 3 | 2026-03-31 | PM |  | 003
| K201 | 2026-05-04 | 2026-05-04 | 2026-12-11 | 2026-12-11 |  | 8202242967 | 8202242761 | KONTRAK RUTIN PERBAIKAN DAN PERAWATAN LI | RU2-PK |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 205789301 | 205773363 | MA3-STA |  | STEVANEKOPP |  | 2026-05-04 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K202 | 2026-05-19 | 2026-05-21 | 2026-04-21 | 2026-04-21 | 2102368214 | 8202243297 |  | Kerusakan VCB OGF 946-P3B | RU2S-KIL | 946-P-3B-M/00 | 50 | REL NMAT PRC SETC | 2ES | D12/26/B6/NRZ-C1H | 0 | 0 | MAS-LIS |  | JUNIANTO |  | 2026-05-19 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K202 | 2026-04-21 | 2026-06-09 | 2026-04-17 | 2026-04-17 | 2102368047 | 8202242606 |  | Kerusakan Valve 2" pipa BFW di Utilities | RU2S-KIL | 3BW900036-MS1/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 7104793 | 7104795 | MAS-ME1 |  | JUNAIDIT |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K202 | 2026-05-07 | 2026-05-07 | 2026-04-07 | 2026-04-07 | 2102367543 | 8202243059 |  | Kerusakan Temp Tube Skin 150 H-3 |  | 101-TT-150/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 17100000 | 0 | MAS-INT |  | JUNIANTO |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K202 | 2026-05-07 | 2026-06-09 | 2026-04-07 | 2026-04-07 | 2102367544 | 8202243060 |  | Kerusakan Temp Stack 148 H-3 | RU2S-KIL | 101-TT-148/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 10605594 | 10605594 | MAS-INT |  | JUNAIDIT |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K202 | 2026-06-10 | 2026-06-11 | 2026-05-25 | 2026-05-25 | 2102369370 | 8202243754 |  | KERUSAKAN REDUCER 900-01-P1B | RU2S-KIL | 900-01P-1D/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 6071124 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-06-11 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-20 | 2026-02-02 | 2026-02-02 | 2102357495 | 8202238721 |  | Kerusakan Positioner 140TV008 A/B | RU4-GTO | 140TV008B/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-02-20 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-20 | 2026-02-20 | 2026-12-17 | 2102355355 | 8202238704 |  | Kerusakan Positioner 108PV6 | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-02-20 | PM |  | 045
| K202 | 2026-04-14 | 2026-04-16 | 2026-02-26 | 2026-02-26 | 2102364999 | 8202242435 |  | Kerusakan Pompa 101-P3B | RU2S-KIL | 101-P-3B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 8182168 | 8182167 | MAS-ME1 |  | JUNIANTO |  | 2026-04-14 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K202 | 2026-04-17 | 2026-04-17 | 2026-02-26 | 2026-02-26 | 2102364998 | 8202242550 |  | Kerusakan Pompa 101-P2A | RU2S-KIL | 101-P-2A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 55000000 | 55000000 | MAS-ME1 |  | JUNIANTO |  | 2026-04-17 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K202 | 2026-05-20 | 2026-05-20 | 2026-05-08 | 2026-05-08 | 2102368910 | 8202243321 |  | Kerusakan Pipa Air 3" untuk BFW di CDU | RU2S-KIL | 3JP900I49-A1A1/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 15693263 | 15693263 | MAS-ME1 |  | JUNIANTO |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 003
| K301 | 2026-05-19 |  | 2026-04-21 | 2026-04-21 | 2102368187 | 8202243284 |  | Kerusakan P-53-101 B CTU Sungai Gerong |  |  | 50 WAMA | CRTD CSER MACM PRC | 3RR |  | 0 | 0 | MA3-ROT |  |  |  |  | PT02 | 6 | 2 | 2026-04-21 | PM |  | 045
| K202 | 2026-04-14 | 2026-04-16 | 2026-02-05 | 2026-02-05 | 2102360961 | 8202242436 |  | Kerusakan Motor Pompa 946-P1B Eksisting | RU2S-KIL | 946-P-1B-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 11534000 | 11534000 | MAS-LIS |  | JUNIANTO |  | 2026-04-14 | PT02 | 3 | 3 | 2026-02-05 | PM |  | 003
| K202 | 2026-03-12 | 2026-03-16 | 2026-02-05 | 2026-02-05 | 2102360960 | 8202241627 |  | Kerusakan Motor Pompa 946-P1A Eksisting | RU2S-KIL | 946-P-1A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 94000000 | 94000000 | MAS-LIS |  | JUNIANTO |  | 2026-03-12 | PT02 | 3 | 3 | 2026-02-05 | PM |  | 003
| K202 | 2026-05-19 | 2026-05-19 | 2026-05-12 | 2026-05-12 | 2102368981 | 8202243287 |  | Kerusakan Motor Fan Cooler | RU2S-KIL | 101-E9-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 2001028 | 2001028 | MAS-LIS |  | JUNIANTO |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K202 | 2026-03-02 | 2026-03-26 | 2026-02-11 | 2026-02-11 | 2102364109 | 8202239315 |  | Kerusakan Motor 946-P4-C | RU2S-KIL | 946-P-4C-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 4215720 | 0 | MAS-LIS |  | PRIHARTONO |  | 2026-03-08 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 003
| K202 | 2026-05-05 | 2026-05-05 | 2026-02-11 | 2026-02-11 | 2102364140 | 8202242974 |  | Kerusakan Motor 946-P2-D | RU2S-KIL | 946-P-2D-M/00 | 50 | REL NMAT PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-LIS |  | JUNIANTO |  | 2026-05-05 | PT02 | 3 | 3 | 2026-02-11 | PM |  | 003
| K202 | 2026-04-29 | 2026-05-05 | 2026-03-10 | 2026-03-10 | 2102366249 | 8202242824 |  | Kerusakan Motor 900-08P-4D | RU2S-KIL | 900-08-P-4D-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 4 | 0 | MAS-LIS |  | JUNIANTO |  | 2026-05-05 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-07-08 | 2102370037 | 8202243905 |  | Kerusakan Mechseal 42-P-101C | RU6-ITP | 42-P-101C/00 | 50 | REL CSER MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 122039261 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K202 | 2026-03-11 | 2026-04-25 | 2026-03-03 | 2026-03-03 | 2102365246 | 8202241578 |  | Kerusakan Mechanical Seal 101-P-5A | RU2S-KIL | 101-P-5A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 7442800 | 6188293 | MAS-ME1 |  | JUNIANTO |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-06-17 | 2026-06-18 | 2026-06-17 | 2026-07-01 | 2102370038 | 8202243904 |  | Kerusakan Flexible Hose Avtur | RU6-ITP | 41-LA-102/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 173401320 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-17 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K202 | 2026-05-19 |  | 2026-04-28 | 2026-04-28 | 2102368379 | 8202243285 |  | Kerusakan fan air dryer AD-1B | RU2S-KIL | 900-09AD-1B/01 | 01 | CRTD NMAT PRC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  |  |  |  | PT02 | 3 | 2 | 2026-04-28 | PM |  | 003
| K202 | 2026-06-08 | 2026-06-09 | 2026-05-18 | 2026-05-18 | 2102369124 | 8202243675 |  | Kerusakan Bearing Pompa P-6D WDcP | RU2S-KIL | 900-03P-6D/01 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 3150700 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-06-09 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K202 | 2026-04-11 | 2026-06-09 | 2026-03-13 | 2026-03-13 | 2102366681 | 8202242343 |  | Kerangan Main Fire Line 10" 150 | RU2S-KIL | 946-F-132-D/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 31822000 | 30000000 | MAS-ME2 |  | JUNAIDIT |  | 2026-04-14 | PT02 | 8 | 3 | 2026-03-13 | PM |  | 003
| K202 | 2026-03-11 | 2026-06-19 | 2026-02-19 | 2026-02-19 | 2102364641 | 8202241570 |  | KELAINAN BUNYI 900-02-P3A WTP | RU2S-KIL | 900-02P-3A-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 15262000 | 444000 | MAS-LIS |  | JUNAIDIT |  | 2026-03-11 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K601 | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-07-09 | 2102364179 | 8202242667 |  | Kebutuhan Temp Indiicator Filling Shed | RU6-ITP | 42-P-930A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 3606468 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K601 | 2026-03-05 | 2026-03-13 | 2026-03-02 | 2026-08-18 | 2102365129 | 8202239522 |  | Kebutuhan Siaga RAFI 15-A-107 AB | RU6-RCC | 15-A-107A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 121830780 | 0 | MA1-INT |  | DANDARWANI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K202 | 2026-05-19 | 2026-05-19 | 2026-05-08 | 2026-05-08 | 2102368912 | 8202243288 |  | Kebutuhan Rumah Sample Area Production | RU2S-KIL | LAB-ANALIS-06/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 4954545 | 4954545 | MAS-INT |  | JUNIANTO |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-12-29 | 2102367645 | 8202243280 |  | Kebutuhan Positioner Electric Governor | RU2-HCC | 211-C-1/00 | 50 | REL CSER MSPT PRC SETC | 2IR | D12/26/B6/NR-D2H | 0 | 0 | MA2-INT |  | DONITGN |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 005
| K201 | 2026-04-14 | 2026-06-15 | 2026-04-14 | 2026-04-20 | 2102367635 | 8202242431 |  | Kebutuhan Material Transmitter 140-DCU | RU2-HOC | 140-H-1A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 269150000 | 277883333 | MA1-INT |  | NURFADHILLA |  | 2026-05-08 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 004
| K201 | 2026-04-14 | 2026-05-11 | 2026-04-14 | 2026-04-20 | 2102367423 | 8202242426 |  | Kebutuhan Material Thermodial 945-T-02 | RU2-ITP | 945-T-02/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA4-INT |  | NURFADHILLA |  | 2026-05-08 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 005
| K601 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-11-23 | 2102369119 | 8202243438 |  | Kebutuhan Material PI untuk DTU | RU6-HSC | 61-V-102/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2330400 | 2330400 | MA1-INT |  | DANDARWANI |  | 2026-05-25 | PT02 | 5 | 3 | 2026-05-25 | PM |  | 003
| K201 | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-28 | 2102367799 | 8202242663 |  | Kebutuhan Cable Signal Area HOC | RU2-HOC | 110-PIPING/00 | 60 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 18903000 | 18903000 | MA1-INT |  | ADEMULYADI |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 005
| K202 | 2026-06-08 | 2026-06-09 | 2026-06-03 | 2026-06-03 | 2102369531 | 8202243696 |  | KEBOCORAN POMPA 101-P5B |  | 101-P-5B/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 10126000 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-06-09 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-19 | 2026-04-02 | 2026-04-02 | 2102367302 | 8202243972 |  | kebocoran pipa treated water 12" | RU2-UTL | 520-PIPING/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 88962817 | 88962817 | MA3-STA |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K202 | 2026-04-29 | 2026-05-20 | 2026-03-25 | 2026-03-25 | 2102366872 | 8202242823 |  | Kebocoran Mech Seal DE 946-P1-B | RU2S-KIL | 946-P-1B/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RS | D12/26/B6/NRZ-C1H | 98696526 | 94000000 | MAS-ME1 |  | JUNIANTO |  | 2026-05-05 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K202 | 2026-04-07 | 2026-04-25 | 2026-02-19 | 2026-02-19 | 2102364660 | 8202242163 |  | KEBOCORAN LINE STEAM DEARATOR | RU2S-KIL | 2BW90001-MS1/00 | 50 | REL CSER MSPT PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-04-07 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K202 | 2026-06-10 | 2026-06-11 | 2026-06-08 | 2026-06-08 | 2102369695 | 8202243756 |  | KEBOCORAN LINE STEAM 101-E5A |  | 4LS101020A-A1A1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 216000 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-06-11 | PT02 | 3 | 3 | 2026-06-08 | PM |  | 003
| K202 | 2026-03-30 | 2026-03-30 | 2026-03-25 | 2026-03-25 | 2102366875 | 8202241941 |  | KEBOCORAN LINE ADO 10 INCH JETTY I | RU2S-KIL | 10PL900003-A1A1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 3235404 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K601 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-08-12 | 2102368926 | 8202243135 |  | Kebocoran Flange Discharge 15-P-118C | RU6-RCC | 15-P-118C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | DANDARWANI |  | 2026-05-12 | PT02 | 4 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-16 | 2026-06-09 | 2026-03-09 | 2026-12-21 | 2102366320 | 8202241754 |  | Kalibrasi O2 Analyzer 14F602 | RU4-FOC1 | 14AT205/00 | 60 | CLSD CNF NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-16 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K501 | 2026-05-06 | 2026-05-06 | 2026-07-15 | 2026-07-29 | 2102368369 | 8202243003 |  | KALIBRASI ANALYZER 05-AIT-383 |  | 05-AIT-383/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 24802000 | 0 | MA2-INT |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-07-15 | PM |  | 003
| K501 | 2026-04-10 | 2026-04-23 | 2026-10-01 | 2026-12-30 | 2102364501 | 8202242306 |  | Kabel Power Lighting Jetty4 | RU5-TBL | DER-JT-04/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 112250000 | 0 | MA4-LIS |  | ANTONIUSAD |  | 2026-04-23 | PT02 | 8 | 3 | 2026-10-01 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-13 | 2026-04-09 | 2026-09-02 | 2102364076 | 8202242238 |  | Kabel Ignitor DFAH 101-F-501 Mengelupas | RU4-RFCC | 101F501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 204 | 0 | MA6-LIS |  | WAHYUCATUR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K501 | 2026-05-26 | 2026-06-10 | 2026-05-26 | 2026-07-13 | 2102369202 | 8202243502 |  | Jumper Line 19-8" ke O-10 Crack | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 48562881 | 0 | MA4-STA |  | NSUCIPTO |  | 2026-05-29 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-09 | 2026-02-27 | 2026-02-02 | 2026-04-30 | 2102358735 | 8202238770 |  | Jasa Sewa Forklift & Truck (1) | RU5-E15112 | F-3-01A/00 | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 270261000 | 0 | WS-KAB |  | YONZHETG |  | 2026-02-20 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-04-24 | 2026-04-24 | 2026-10-30 | 2026-10-30 |  | 8202242717 | 8202242594 | Jasa Resertifikasi PSV RU II Dumai | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 2136419250 | 1572021000 | MA1-STA |  | STEVANEKOPP |  | 2026-04-24 | PT02 | 3 | 3 | 2026-10-30 | PM |  | 045
| K201 | 2026-06-17 | 2026-06-17 | 2026-03-11 | 2026-03-11 |  | 8202243880 | 8202241484 | JASA PSA METERING SYSTEM DI REFINERY UNI | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 1400000000 | 0 | MA4-INT |  | STEVANEKOPP |  | 2026-06-17 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K201 | 2026-03-27 | 2026-05-12 | 2026-08-03 | 2026-08-03 | 2102360593 | 8202241908 |  | Jasa perbaikan motor 610-P-1103-A | RU2-ITP | P-1103A-M/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 900000000 | 0 | MA4-LIS |  | ADEMULYADI |  | 2026-04-07 | PT02 | 5 | 3 | 2026-08-03 | PM |  | 003
| K201 | 2026-04-24 | 2026-04-24 | 2026-12-30 | 2026-12-30 |  | 8202242715 | 8202242594 | Jasa Pemeliharaan / Long Term Service Ag | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | STEVANEKOPP |  | 2026-04-24 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 045
| K201 | 2026-04-24 | 2026-04-24 | 2026-10-30 | 2026-10-30 |  | 8202242716 | 8202242594 | Instalasi Fire Gas Detector System (FGDS | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 278000000 | 278000000 | MA1-STA |  | STEVANEKOPP |  | 2026-04-24 | PT02 | 3 | 3 | 2026-10-30 | PM |  | 045
| K201 | 2026-04-24 | 2026-04-24 | 2026-12-11 | 2026-12-11 |  | 8202242714 | 8202241483 | INSPEKSI, QUALITY CONTROL PERALATAN ELEC | RU2-HCC |  | 50 | REL GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1500000000 | 319233033 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-24 | PT02 | 3 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-04-01 | 2026-05-19 | 2026-04-01 | 2026-04-01 | 2102366399 | 8202242002 |  | Inspeksi Pompa 200-P-2 A | RU2-HSC | 200-P-2A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 334219 | 334219 | MA2-ROT |  | ADEMULYADI |  | 2026-04-01 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K201 | 2026-04-10 | 2026-06-18 | 2026-04-10 | 2026-04-10 | 2102366398 | 8202242333 |  | Inspeksi Pompa 100-P-4 A | RU2-HSC | 100-P-4A/00 | 50 | REL CSER MANC PRC SETC | 2RR | D12/26/B6/RT-D2H | 85566015 | 0 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-04-10 | PT02 | 5 | 3 | 2026-04-10 | PM |  | 003
| K201 | 2026-04-30 | 2026-06-15 | 2026-05-04 | 2026-05-18 | 2102368404 | 8202242858 |  | Inspeksi Pompa | RU2-HSC | 100-P-1A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 163164052 | 0 | MA2-ROT |  | NURFADHILLA |  | 2026-04-30 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K201 | 2026-05-04 | 2026-05-04 | 2026-05-16 | 2026-05-18 | 2102368405 | 8202242925 |  | Inspeksi Pompa | RU2-HSC | 300-P-7A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 4830136 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-04 | PT02 | 5 | 3 | 2026-05-16 | PM |  | 003
| K201 | 2026-05-04 | 2026-05-04 | 2026-05-06 | 2026-05-06 | 2102368406 | 8202242926 |  | Inspeksi Pompa | RU2-HSC | 300-P-9A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 146715924 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-04 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 003
| K201 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-18 | 2102368407 | 8202242856 |  | Inspeksi & balancing fan | RU2-HSC | 310-C-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 69898000 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-30 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-05-04 | 2026-05-04 | 2026-05-12 | 2026-05-12 | 2102366364 | 8202242963 |  | Indikasi passing drainpoint 34-TV-002 | RU6-POC | 34-E-101/00 | 50 | REL CSER MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 2142935 | 0 | MA3-STA |  | DANDARWANI |  | 2026-05-04 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-05-04 | 2026-05-06 | 2026-04-27 | 2026-09-11 | 2102368423 | 8202242958 |  | Indikasi membran rusak 34-A-102-P-101B | RU6-POC | 34-A-102-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 22450000 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-06 | PT02 | 4 | 3 | 2026-04-27 | PM |  | 005
| K701 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-11 | 2102368957 | 8202243103 |  | Indikasi Bocoran Mechanical Seal 2-P-02B | RU7-NHT | 2-P-02B/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D2H | 63980000 | 0 | MA-ROT |  | YAYANHER |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 005
| K601 | 2026-02-10 | 2026-02-12 | 2026-02-10 | 2026-04-16 | 2102364067 | 8202238816 |  | Indikasi bearing defect 30-P-901 A | RU6-HSC | 30-P-901A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1074790 | 989790 | MA3-LIS |  | DANDARWANI |  | 2026-02-12 | PT02 | 5 | 3 | 2026-02-10 | PM |  | 003
| K202 | 2026-06-11 | 2026-06-22 | 2026-06-08 | 2026-06-08 | 2102369734 | 8202243803 |  | In CW E10-C menggunakan Flex Hose |  | 101-E-10C/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 12655275 | 7696000 | MAS-ME1 |  | JUNIANTO |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-08 | PM |  | 003
| K501 | 2026-02-12 | 2026-05-06 | 2026-06-02 | 2026-06-02 | 2102363537 | 8202238885 |  | Impeller FDF Turbin HHP 2 |  |  | 60 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 249000000 | 0 | WS-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 045
| K701 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2102368862 | 8202243093 |  | High Vibrasi 5-P-19A | RU7-OFF | 5-P-19A/00 | 50 | REL CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-5-D2H | 1609059 | 1609059 | MA-ROT |  | YAYANHER |  | 2026-05-08 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 005
| K601 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2027-03-24 | 2102367482 | 8202242126 |  | Hasil Pemeriksaan Internal Part | RU6-RCC | 15-K-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 9955852 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K501 | 2026-02-24 | 2026-03-08 | 2026-05-11 | 2026-05-11 | 2102364130 | 8202239084 |  | GT-1-08A VIBRASI TINGGI | RU5-E15111 | GT-1-08A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 239238900 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 003
| K201 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-10-15 | 2102364815 | 8202242463 |  | GOVERNOR TIDAK RESPON | RU2-HCC | 702-PT-4B/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 7128 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-15 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-03-31 | 2026-06-15 | 2026-04-01 | 2026-04-01 | 2102365033 | 8202241984 |  | Gland Packing Bocor | RU2-HCC | 211-P-6/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RR | D12/26/B6/RT-D2H | 224334150 | 186690390 | MA2-ROT |  | NURFADHILLA |  | 2026-04-01 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K601 | 2026-05-11 | 2026-05-11 | 2026-04-24 | 2026-12-31 |  | 8202243120 | 8202242774 | Gedung SS OS Thn 25-26 All Area TKDN 15% | RU6-ITP | 42-T-201A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 268709400 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K601 | 2026-04-30 | 2026-05-08 | 2026-04-24 | 2026-09-10 |  | 8202242890 | 8202242774 | Gedung SS OS 21-22 Thn 25-26 Thp 9 (85%) | RU6-ITP | 42-T-201A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 75343150 | 0 | MA4-STA |  | DANDARWANI |  | 2026-05-08 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K201 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-04-20 | 2102365082 | 8202239242 |  | Gearbox Rusak | RU2-HCC | 211-P-6AR/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 41070408 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 005
| K601 | 2026-06-02 | 2026-06-02 | 2026-05-29 | 2026-06-22 | 2102369460 | 8202243580 |  | Gasket untuk Makeup Rocksalt 14-V-108 | RU6-DHC | 14-V-108/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2145851 | 0 | MA2-STA |  | DANDARWANI |  | 2026-06-02 | PT02 | 4 | 3 | 2026-05-29 | PM |  | 003
| K701 | 2026-06-04 | 2026-06-04 | 2026-12-30 | 2026-12-30 | 2102369565 | 8202243618 |  | Ganti Vibration Switch & Flow Switch | RU7-CRU | 3-K-01A/00 | 50 | REL MACM PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 152000000 | 0 | MA-ROT |  | RIZKAANDIKAP |  | 2026-06-04 | PT02 | 6 | 3 | 2026-12-30 | PM |  | 005
| K501 | 2026-03-04 | 2026-03-04 | 2026-02-09 | 2026-12-31 | 2102363938 | 8202239416 |  | Ganti Valve Steam Auto. Indiv. Burner | RU5-UTL | HHP-3/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 11954284 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-03-04 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 004
| K501 | 2026-04-14 | 2026-05-04 | 2026-04-14 | 2026-04-15 | 2102367854 | 8202242398 |  | Ganti Valve Pipa Air Bersih 3" k RDP TNT | RU5-UTL | PIPA-WTP-PCR/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-W1NH | 4858316 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K501 | 2026-04-02 | 2026-04-07 | 2026-04-06 | 2026-04-08 | 2102366504 | 8202242038 |  | GANTI VALVE DISCHARGE P18 YANG RUSAK | RU5-UTL | P-18PAMPANCUR/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 1611431 | 0 | MA4-STA |  | MANKURNIAWAN |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K501 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 2026-06-23 | 2102369963 | 8202243924 |  | Ganti Valve 6"300&3"300 Prsiapan Pigging | RU5-TBL | PIPE-ON-SHORE/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 20378825 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K501 | 2026-02-26 | 2026-04-17 | 2026-03-09 | 2026-04-28 | 2102364717 | 8202239201 |  | Ganti Valve 30" koneksi new line RDMP | RU5-TBL | PIPE-ON-SHORE/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 329501462 | 0 | MA4-STA |  | ABDULLOH |  | 2026-04-17 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K701 | 2026-05-06 | 2026-06-16 | 2026-05-06 | 2026-05-06 | 2102368737 | 8202243037 |  | Ganti Transmitter 1-FT-203 | RU7-CDU | 1-FT-203/00 | 60 | REL CSER GMPS MANC PRC SETC | 7RT | D17/26/B6/RT-1-D2H | 93187101 | 91352449 | MA-LINT |  | RYANMANGGASA |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 005
| K701 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102368736 | 8202243038 |  | Ganti Transmitter 1-FT-120 | RU7-CDU | 1-FT-120/00 | 50 | REL CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-1-D2H | 16913000 | 16913000 | MA-LINT |  | YAYANHER |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 005
| K701 | 2026-06-04 | 2026-06-04 | 2026-12-30 | 2026-12-30 | 2102369567 | 8202243622 |  | Ganti Selenoid Valve 4-P-02B | RU7-UTL | 4-P-02B/00 | 50 | REL MACM PRC SETC | 7RT | D17/26/B6/RT-4-D1H | 22538492 | 0 | MA-ROT |  | RIZKAANDIKAP |  | 2026-06-04 | PT02 | 6 | 3 | 2026-12-30 | PM |  | 005
| K701 | 2026-05-28 | 2026-05-30 | 2026-05-29 | 2026-05-29 | 2102369433 | 8202243534 |  | Ganti Pressure Switch 4-B-01 | RU7-HSE | 4-B-01/01 | 50 | REL CSER MSPT PRC SETC | 7RT | D17/26/B6/OHK-1-D2H | 5 | 0 | MA-STA |  | YAYANHER |  | 2026-05-29 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 005
| K201 | 2026-04-15 | 2026-05-19 | 2026-04-15 | 2026-04-22 | 2102364272 | 8202242464 |  | Ganti membran coupling | RU2-HCC | 702-P-2/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 19722627 | 19722350 | MA2-ROT |  | ADEMULYADI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K701 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2102369792 | 8202243729 |  | Ganti Mechanical Seal 1-P-06-B | RU7-CDU | 1-P-06B/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 50740000 | 0 | MA-ROT |  | YAYANHER |  | 2026-06-10 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 005
| K701 | 2026-02-28 | 2026-02-28 | 2026-12-30 | 2026-12-30 | 2102365144 | 8202239275 |  | Ganti LT 2-LT-110, 2-LT-111 & 3-LT-109 | RU7-NHT | 2-LT-110/00 | 50 | REL MACM PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 480500000 | 0 | MA-ROT |  | YAYANHER |  | 2026-02-28 | PT02 | 3 | 3 | 2026-12-30 | PM |  | 003
| K501 | 2026-03-04 | 2026-03-06 | 2026-02-02 | 2026-12-31 | 2102360045 | 8202239424 |  | Ganti Line Cooling Pump Fuel Oil 1 & 2 | RU5-UTL | HHP-1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 17098092 | 0 | MA1-STA |  | MANKURNIAWAN |  | 2026-03-06 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 004
| K701 | 2026-03-08 | 2026-04-24 | 2026-12-30 | 2026-12-30 | 2102365145 | 8202241355 |  | Ganti Level Glass 2LG105, 3LG424, 3LG108 | RU7-NHT | 2-LG-105/00 | 50 | REL MACM PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 176300400 | 0 | MA-LINT |  | RYANMANGGASA |  | 2026-03-08 | PT02 | 6 | 3 | 2026-12-30 | PM |  | 003
| K501 | 2026-05-25 | 2026-05-25 | 2026-04-07 | 2026-12-31 | 2102367523 | 8202243434 |  | Ganti Kaca Peep Hole Boiler HHP 1, 2, 3 | RU5-UTL | HHP-1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 9 | 0 | MA1-STA |  | MANKURNIAWAN |  | 2026-05-25 | PT02 | 2 | 3 | 2026-04-07 | PM |  | 003
| K701 | 2026-02-09 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2102363991 | 8202238798 |  | Ganti Gasket 1-P-06 AB | RU7-CDU | 1-P-06A/00 | 60 | REL PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | YAYANHER |  | 2026-05-17 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 005
| K501 | 2026-03-06 | 2026-06-03 | 2026-02-20 | 2026-02-20 | 2102364732 | 8202241291 |  | Ganti Floating Hose Rusak(inner) SPM150K | RU5-TBL | PIPE-ON-SHORE/00 | 50 | CRTD CSER MACM PRC RELR | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | HIMMATUSS |  |  | PT02 | 3 | 2 | 2026-02-20 | PM |  | 003
| K701 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102368751 | 8202243039 |  | Ganti Bearing Pompa 5-P-19A | RU7-OFF | 5-P-19A/00 | 60 | REL CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-5-D2H | 3608118 | 3608118 | MA-ROT |  | YAYANHER |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 005
| K701 | 2026-06-08 | 2026-06-15 | 2026-06-08 | 2026-06-08 | 2102369674 | 8202243700 |  | Ganti Bearing Pompa 1-P-07 B | RU7-CDU | 1-PM-07B/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 2039601 | 0 | MA-LINT |  | YAYANHER |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-08 | PM |  | 005
| K501 | 2026-02-09 | 2026-03-05 | 2026-03-09 | 2026-03-09 | 2102363554 | 8202238801 |  | G-5-12A FLOW RENDAH | RU5-E15111 | G-5-12A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-03-03 | 2026-05-04 | 2026-03-04 | 2026-09-04 | 2102363530 | 8202239409 |  | G-1-20B perbaikan MS NDE | RU5-E15111 | G-1-20B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 7927500 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-03-03 | 2026-05-04 | 2026-06-04 | 2026-06-04 | 2102363531 | 8202239408 |  | G-1-08C VIBRASI TINGGI | RU5-E15111 | G-1-08C/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 7610110 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 003
| K401 | 2026-03-25 | 2026-04-24 | 2026-03-25 | 2026-12-30 | 2102366675 | 8202241872 |  | Flame Arrester 85S202 A/B rusak - ganti | RU4-KPC | 85S202A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 045
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365189 | 8202241460 |  | FANBELT EA-32-01Q PUTUS | RU5-E15112 | EA-32-01Q/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-03-09 | 2026-05-04 | 2026-03-02 | 2026-08-30 | 2102365186 | 8202241456 |  | FANBELT EA-32-01L PUTUS | RU5-E15112 | EA-32-01L/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | FAUZANR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K601 | 2026-05-26 | 2026-06-03 | 2026-05-26 | 2026-05-26 | 2102369394 | 8202243531 |  | Fabrikasi Silencer 39-K-101 | RU6-POC | 39HS9002D1A4H/00 | 50 | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 103941231 | 91662648 | MA3-STA |  | DANDARWANI |  | 2026-05-29 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K701 | 2026-05-14 | 2026-05-14 | 2026-06-29 | 2026-06-29 | 2102367841 | 8202243205 |  | Fabrikasi Pekerjaan Pompa PT IAS | RU7-CDU | 1-PM-07B/00 | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-1-D2H | 1680000000 | 0 | MA-LINT |  | RIZKAANDIKAP |  | 2026-05-14 | PT02 | 6 | 3 | 2026-06-29 | PM |  | 005
| K701 | 2026-03-10 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366354 | 8202241511 |  | Evergreening RBI | RU7-CDU |  | 50 | REL GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 875000000 | 743750000 | MA-STA |  | MALFANF |  | 2026-03-10 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-03-05 | 2026-05-04 | 2026-03-06 | 2026-09-06 | 2102365290 | 8202240699 |  | EA-1-25C BEARING FAN VIBRASI TINGGI | RU5-E15111 | EA-1-25C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 19061616 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-03-05 | 2026-05-04 | 2026-03-06 | 2026-09-06 | 2102365289 | 8202240700 |  | EA-1-24C BEARING FAN VIBRASI TINGGI | RU5-E15111 | EA-1-24C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 19060642 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-03-05 | 2026-05-04 | 2026-03-06 | 2026-09-06 | 2102365288 | 8202240701 |  | EA-1-24A BEARING FAN VIBRASI TINGGI | RU5-E15111 | EA-1-24A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 19060642 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-03-06 | 2026-03-10 | 2026-02-23 | 2026-05-25 | 2102364698 | 8202241307 |  | Doubling Pipa RWI Sei Rokan KM 14-18 | RU2-UTL | 510-PIPING/00 | 50 | CRTD NMAT PRC RELR | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA3-STA |  | AHILMANSYAH |  |  | PT02 | 3 | 2 | 2026-02-23 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-29 | 2026-05-11 |  | 8202237448 |  | don'tUse8202232040#Perbaikan Motor 20-E- | RU6-RCC | 20-E-104A-M/00 | 01 | CRTD CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-29 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-01-02 | 2026-01-02 |  | 8202238472 |  | don'tUse8202231623#Tag Ke- 5 Pek Hose Ha |  |  | 50 | CRTD NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-02 | 2026-02-02 | 2026-02-02 |  | 8202235291 |  | don'tUse8202226114#Kontrak Volume Mekani |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SEALTIELS |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-04 | 2026-06-11 | 2026-01-02 | 2026-01-02 |  | 8202238177 |  | don'tUse8202225542#Perb. Tangga Beton SS | RU6-DHC | SS-12/00 | 01 | CLSD CSER NCMP NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-06-11 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-12-04 | 2026-12-04 |  | 8202238175 |  | don'tUse8202225499#CLEANING INSIDE SEA W |  |  | 01 | CRTD NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-12-04 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-26 | 2026-12-04 | 2026-12-04 |  | 8202238176 |  | don'tUse8202225499#CLEANING INSIDE SEA W | RU2-UTL |  | 01 | CLSD NCMP NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA3-STA |  | ADEMULYADI |  |  | PT02 |  | 2 | 2026-05-26 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-26 | 2026-01-02 | 2026-01-02 |  | 8202238172 |  | don'tUse8202225368#Service System-1 Vibr | RU2-UTL | 905-DEG-01/00 | 01 | CLSD NCMP NMAT PRC SETC | 2IR | D12/26/B6/NR-D2H | 0 | 0 | MA3-INT |  | ADEMULYADI |  |  | PT02 |  | 2 | 2026-05-26 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-16 | 2026-02-02 | 2026-02-02 |  | 8202234626 |  | don'tUse8202224333#tagihan 2025 Pek Per. | RU3-CDGP |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | T_FATAHY |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-26 | 2026-03-27 | 2026-03-27 |  | 8202238268 |  | don'tUse8202223371#Perbaikan struktur je | RU2-ITP | DPN-PIPING/00 | 01 | CLSD NCMP NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA4-STA |  | ADEMULYADI |  |  | PT02 |  | 2 | 2026-05-26 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-26 | 2026-03-25 | 2026-03-25 |  | 8202238266 |  | don'tUse8202223368#Pekerjaan Piping Bord | RU2-HCC | 0-75CC21133MS11/00 | 01 | CLSD NCMP NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA2-STA |  | ADEMULYADI |  |  | PT02 |  | 2 | 2026-05-26 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238265 |  | don'tUse8202223277#Tag 5 KV Penyediaan J |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238253 |  | don'tUse8202223270#Tag 7 Kontrak Volume |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238249 |  | don'tUse8202223269#Tag 6 Steam Leak non |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238223 |  | don'tUse8202221799#Perbaikan Tangga Cool |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238215 |  | don'tUse8202221780# LTSA PERBAIKAN ROOF |  |  | 01 | CRTD NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202235548 |  | don'tUse8202221279#kerangan drain 4"300 |  |  | 01 | CRTD CSER MACM PRC SETC | 3MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-02-02 |  | 8202234515 |  | don'tUse8202220925#Tagihan LTSA Fire Ext | RU3-LKKK |  | 01 | CLSD NCMP NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | T_FATAHY |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235237 |  | don'tUse8202220169#Kontrak Volume Mekani |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 |  | 8202235531 |  | don'tUse8202218992#Kerusakan Flowmeter D |  |  | 01 | CRTD NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235224 |  | don'tUse8202211407#Kontrak Volume Mekani |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235250 |  | don'tUse8202205959#Kontrak Volume Mekani |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-23 | 2026-01-02 | 2026-01-02 |  | 8202235464 |  | don'tUse8202205862#Kontr.Vol Cleaning Ta |  |  | 01 | CRTD GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202235388 |  | don'tUse8202038288#Kontr.Vol Steam Leak |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-18 | 2026-02-03 | 2026-12-31 |  | 8202235505 |  | don'tUse8202030536#Kontr. Vol Perbaikan |  |  | 01 | CRTD NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K201 | 2026-03-31 | 2026-05-19 | 2026-03-31 | 2026-10-29 | 2102363542 | 8202241977 |  | Display Vibration Monitoring 300-CT-1 | RU2-HSC | 300-CT-1/00 | 50 | REL MACM PRC SETC | 2IR | D12/26/B6/NR-D2H | 164829166 | 0 | MA2-INT |  | DONITGN |  | 2026-04-06 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-26 | 2026-03-03 | 2026-12-02 | 2102366551 | 8202241654 |  | D26_TI di line CW supplay 84K202C rusak | RU4-KPC | 84K202C/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-26 | PT02 | 5 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102368864 | 8202243393 |  | D26_Stem control valve patah 260FV019 | RU4-LOC3 | 260FV019/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-05-25 | PT02 | 2 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-06 | 2026-02-11 | 2026-11-30 | 2102364761 | 8202239217 |  | D26_Selisih out put control valve 220TV1 | RU4-LOC3 | 220TV130/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 5 | 3 | 2026-02-11 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-11-27 | 2102365059 | 8202239289 |  | D26_Perbaikan PSL 102P509A/B range 500 p | RU4-RFCC | 102P509A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | DWIHIZZKI |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-08 | 2026-06-08 | 2102369753 | 8202244016 |  | D26_Perbaikan Meltube Area Proses |  |  | 50 | CRTD NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | INSP-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-08 | PM |  | 045
| K401 | 2026-03-09 | 2026-06-09 | 2026-03-10 | 2026-12-23 | 2102365038 | 8202241479 |  | D26_Perbaikan Level Transmitter 12LT005/ | RU4-FOC1 | 12LT006/00 | 60 | CLSD CNF NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368929 | 8202243579 |  | D26_Perbaikan Instrumentasi Pompa 38P103 | RU4-TRML | 38P103A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-06-30 | 2102367592 | 8202242376 |  | D26_Perbaikan HMI controller 560K301 | RU4-UTL | 560K301/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-09-29 | 2102365788 | 8202242119 |  | D26_Perbaikan Flexible Hose Pneumix B RF | RU4-RFCC | 101A525B/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-02-06 | 2026-06-09 | 2026-02-13 | 2026-11-27 | 2102357498 | 8202238722 |  | D26_perbaikan Electric motor HVAC | RU4-LOC1 | 20BD1/00 | 60 | CLSD CNF NMAT PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-02-13 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-10 | 2026-03-10 | 2026-12-17 | 2102365234 | 8202239461 |  | D26_Perbaikan Control Valve 46FV310 | RU4-TRML | 46FV310/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369109 | 8202243478 |  | D26_Perbaikan channel 102LI013 (ESD) | RU4-RFCC | 102LT013/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | DWIHIZZKI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-28 | 2026-04-22 | 2026-11-25 | 2102368260 | 8202242753 |  | D26_Perbaikan bocoran 140KV018B | RU4-GTO | 140KV018B/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | DWIHIZZKI |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-04 | 2026-04-22 | 2026-10-27 | 2102368229 | 8202242950 |  | D26_Perbaikan bocoran 140KV018A | RU4-GTO | 140KV018A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | DWIHIZZKI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-05-13 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369020 | 8202243194 |  | D26_Perbaikan 14PDCV522 | RU4-FOC1 | 14PDCV522/00 | 60 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369464 | 8202243568 |  | D26_Perbaikan 104LI008 - Normalisasi for | RU4-RFCC | 104LT008/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-20 | 2026-06-17 | 2026-12-22 | 2102369463 | 8202243567 |  | D26_Perbaikan 102LI013 - Normalisasi for | RU4-RFCC | 102LT013/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 8 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-09-29 | 2102366823 | 8202242116 |  | D26_Perbaikan 102FIC032 Action Lambat | RU4-RFCC | 102FI-U102/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369233 | 8202243467 |  | D26_Perbaikan 102FIC024 - Control huntin | RU4-RFCC | 102FT024/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | DWIHIZZKI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-10-29 | 2102366822 | 8202242117 |  | D26_Perbaikan 102FI019 (top C503) huntin | RU4-RFCC | 102FI-U102/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-21 | 2026-05-12 | 2026-12-09 | 2102369003 | 8202243240 |  | D26_Perbaikan 101UV002 - Leak IA di unio | RU4-RFCC | 101UV002/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369249 | 8202243627 |  | D26_Perbaikan 101A515 - Valve filter pat | RU4-RFCC | 101A515/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369173 | 8202243391 |  | D26_Penunjukkan 120LIC019 rusak | RU4-GTO |  | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 045
| K401 | 2026-04-13 | 2026-04-14 | 2026-04-09 | 2026-04-09 | 2102367656 | 8202242367 |  | D26_Penggantian Transmitter 151TT003 | RU4-RFCUTL |  | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-INT |  | FATAHALFI |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-11-30 | 2102367082 | 8202242113 |  | D26_Penggantian Refrigerant 134 A 180A60 | RU4-GTO | 180A601K1A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-21 | 2026-06-17 | 2026-12-31 | 2102369864 | 8202243850 |  | D26_Penggantian PG Microfeilter 109MF501 | RU4-RFCGTO | 109PG-U109/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-06-30 | 2102368230 | 8202242754 |  | D26_Penggantian Material Kursor HMI MAB | RU4-RFCC | 101K501/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | DWIHIZZKI |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-01 | 2026-11-11 | 2102367968 | 8202242578 |  | D26_Penggantian Local Indicator 93FI055 | RU4-SRU | FI-U93/00 | 60 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-INT |  | DWIHIZZKI |  | 2026-04-20 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-14 | 2026-08-11 | 2102367967 | 8202242576 |  | D26_Penggantian Local Indicator 93FI053 | RU4-SRU | FI-U93/00 | 60 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-INT |  | DWIHIZZKI |  | 2026-04-20 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-14 | 2026-11-24 | 2102367966 | 8202242579 |  | D26_Penggantian Local Indicator 93FI050 | RU4-SRU | FI-U93/00 | 60 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-INT |  | DWIHIZZKI |  | 2026-04-20 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-06 | 2026-02-10 | 2026-02-10 | 2102364090 | 8202239224 |  | D26_Penggantian 510FT001 - unit 510G301 | RU4-UTL | 510G301/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-18 | 2026-03-10 | 2026-03-10 | 2026-12-22 | 2102364059 | 8202238927 |  | D26_Penggantian 052LT401 - unit 052B104 | RU4-UTL | 052B104/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-04 | 2026-04-30 | 2026-10-06 | 2102368566 | 8202242940 |  | D26_Penambahan TI Di 024S-102 | RU4-LOC2 | 024S102A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | DWIHIZZKI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-18 | 2026-06-17 | 2026-12-31 | 2102369496 | 8202243858 |  | D26_Pemasangan O2 Analyzer 14F602 | RU4-FOC1 | 14AT205/00 | 60 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | FATAHALFI |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-06-30 | 2102367634 | 8202242372 |  | D26_Malfunction 240PCV236 case trip 240K | RU4-LOC3 | 240PCV236/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-14 | PT02 | 4 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-10 | 2026-12-29 | 2102366418 | 8202241745 |  | D26_Deviasi 014TI-010 dengan 014TIC-166 | RU4-FOC2 | 014TE010/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-10 | 2026-11-24 | 2102366450 | 8202241744 |  | D26_Deviasi 014TI-008 dengan 014TIC-165 | RU4-FOC2 | 014TE008/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-10 | 2026-11-24 | 2102366417 | 8202241747 |  | D26_Deviasi 014TI-012 dengan 014TIC-167 | RU4-FOC2 | 014TE012/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-26 | 2026-03-09 | 2026-12-21 | 2102366243 | 8202241656 |  | D26_CV Excess PSA to flare passing 260PV | RU4-LOC3 | 260PV211/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-26 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 2026-12-23 | 2102356362 | 8202238790 |  | D26_ATG 041T113 penunjukan temp | RU4-TRML | 041T113/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 0 | 0 | MA2-INT |  | DWIHIZZKI |  | 2026-02-13 | PT02 | 5 | 3 | 2026-02-13 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-08 | 2026-04-08 | 2026-06-29 | 2102366943 | 8202241889 |  | D26_ATG 041T105 Error | RU4-TRML | 041T105/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 4 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-13 | 2026-09-30 | 2102356360 | 8202238712 |  | D26_ATG 041T104 Penunjukkan level error | RU4-TRML | 041T104/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 0 | 0 | MA2-INT |  | DWIHIZZKI |  | 2026-02-13 | PT02 | 5 | 3 | 2026-02-13 | PM |  | 003
| K401 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-10-29 | 2102368857 | 8202243115 |  | D26_84K202C PI local rusak 5 pcs | RU4-KPC | 84K202C/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-INT |  | FATAHALFI |  | 2026-05-11 | PT02 | 5 | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-04 | 2026-04-14 | 2026-11-25 | 2102367906 | 8202242951 |  | D26_81LV100 kondisi korosif | RU4-KPC | 81A201E4/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-INT |  | DWIHIZZKI |  | 2026-05-04 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-17 | 2026-03-03 | 2026-10-26 | 2102366281 | 8202241467 |  | D26_180PT613A rusak | RU4-GTO | 180PT613A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 2026-10-23 | 2102354934 | 8202238795 |  | D26_048 PV-305 indikasi pasing | RU4-FOC2 | 019K102A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | DWIHIZZKI |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-13 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-04 | 2026-04-30 | 2026-11-03 | 2102368556 | 8202242938 |  | D26_023PV-004 Macet | RU4-LOC2 | 023PV004/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | DWIHIZZKI |  | 2026-05-04 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369086 | 8202243479 |  | D26_018FV047 Output rendah flow tinggi | RU4-FOC2 | 018FV047/00 | 50 WENG | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | DWIHIZZKI |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-12-29 | 2102366245 | 8202241752 |  | D26_014PV019A : Rusak | RU4-FOC2 | 014V127/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-11-30 | 2102365281 | 8202243119 |  | D26_011PAH-025,027,032,038,039 hight ala | RU4-FOC2 | 011V103-A1/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | FATAHALFI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-06-30 | 2102368329 | 8202242752 |  | D26_011AI-323 analizer 011F-101A rusak | RU4-FOC2 | 011F101A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-30 | 2026-04-24 | 2026-03-30 | 2026-06-29 | 2102363563 | 8202241918 |  | D_26 Noise pada motor 240P102A | RU4-LOC3 | 240P102AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 1149300 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-30 | PT02 | 2 | 3 | 2026-03-30 | PM |  | 045
| K401 | 2026-03-30 | 2026-04-23 | 2026-03-30 | 2026-06-29 | 2102364068 | 8202241917 |  | D_26 Motor short 240S101AM2 | RU4-LOC3 | 240S101AM2/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 693300 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-30 | PT02 | 2 | 3 | 2026-03-30 | PM |  | 045
| K401 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-05-20 | 2102366598 | 8202242612 |  | D_26 Motor noise pada sisi NDE 240P102BM | RU4-LOC3 | 240P102BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-LIS |  | WAHYUCATUR |  | 2026-04-21 | PT02 | 1 | 3 | 2026-04-21 | PM |  | 045
| K401 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-09-29 | 2102367078 | 8202242610 |  | D_26 Motor noise dan fan rusak 041P304AM | RU4-TRML | 041P304AM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-LIS |  | WAHYUCATUR |  | 2026-04-21 | PT02 | 2 | 3 | 2026-04-21 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-22 | 2026-06-17 | 2026-12-30 | 2102369513 | 8202243903 |  | D_26 Motor 240P107AM short | RU4-LOC3 | 240P107AM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 2 | 3 | 2026-06-17 | PM |  | 045
| K201 | 2026-04-09 | 2026-05-19 | 2026-04-09 | 2026-04-09 | 2102367593 | 8202242283 |  | Coupling Failure | RU2-HSC | 301-ONP-3A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 2480000 | 2480000 | MA2-ROT |  | ADEMULYADI |  | 2026-04-09 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 003
| K501 | 2026-04-02 | 2026-04-28 | 2026-12-02 | 2026-12-02 | 2102363926 | 8202242021 |  | COOLER SEAL G-4-04A SISI OUTBOARD RUSAK | RU5-E15111 | G-4-04A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K401 | 2026-03-17 |  | 2026-03-09 | 2026-03-09 | 2102366265 | 8202241810 |  | controler 81PIC203B rusak | RU4-KPC | 81A201V1/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-03-09 | PM |  | 003
| K601 | 2026-03-10 | 2026-04-14 | 2026-03-10 | 2026-04-15 | 2102366365 | 8202241503 |  | Consumable Material Perbaikan 15-P-102C | RU6-RCC | 15-P-102C/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 4148149 | 2404753 | MA1-ROT |  | ERWINSURYAG |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-08-27 |  | 8202242318 | 8202237762 | COA 32-V-106B (Tagihan 85%) | RU6-HSC | 32-V-106B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 117657000 | 117657000 | MA3-STA |  | DANDARWANI |  | 2026-04-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K601 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-07-03 | 2102369613 | 8202243638 |  | Cleaning Strainer 56-P-101 (Gasket) | RU6-UTL | 56-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 3960 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-06-08 | PT02 | 5 | 3 | 2026-06-04 | PM |  | 003
| K701 | 2026-04-06 |  | 2026-01-02 | 2026-01-02 | 2102367434 | 8202242065 |  | Cleaning Level Glass 2-LT-111 | RU7-NHT | 2-LT-111/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-2-D2H | 371000 | 0 | MA-LINT |  |  |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 005
| K301 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-12-31 | 2102367879 | 8202242430 |  | Cleaning kanal jalan selatan s.gerong | RU3-LKKK | 06-JLN-PAS/00 | 50 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  | 2026-04-15 | PT02 | 4 | 3 | 2026-04-15 | PM |  | 003
| K202 | 2026-04-27 | 2026-06-02 | 2026-04-27 | 2026-04-27 | 2102368398 | 8202242763 |  | CLEANING HE 101-E-3 GHIJ | RU2S-KIL | 101-E-3G/00 | 50 | REL CSER MANC PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 28965075 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-08-20 | 2102367477 | 8202242153 |  | Cleaning cooler kompresor 58-K-101E | RU6-UTL | 58-K-101E/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 15120000 | 12852000 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-08-20 | 2102367479 | 8202242156 |  | Cleaning cooler kompresor 58-K-101B | RU6-UTL | 58-K-101B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 42500000 | 36125000 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-08-20 | 2102367478 | 8202242155 |  | Cleaning cooler kompresor 059-K-101B-K1 | RU6-UTL | 059-A-101B-K1/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 20030000 | 17025500 | MA4-STA |  | DANDARWANI |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K501 | 2026-03-03 | 2026-03-04 | 2026-02-26 | 2026-12-31 | 2102365018 | 8202239353 |  | Cleaning Condensor STG 2.2 | RU5-UTL | 031-ORF-04-S002/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 965625 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K201 | 2026-03-11 | 2026-05-26 | 2026-03-12 | 2026-03-12 | 2102366561 | 8202241583 |  | Cleaning Berkala Lumpur/ Coke Settling B | RU2-HOC | 140-V-1A/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1091142000 | 57840000 | MA1-STA |  | ADEMULYADI |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K201 | 2026-04-21 | 2026-04-21 | 2026-06-22 | 2026-06-22 |  | 8202242608 | 8202242585 | CLEANING 100-E-7ABCDEFGHI AREA HSC RU II | RU2-HSC | 100-E-7A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 251309000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-04-21 | PT02 | 5 | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-03-30 | 2026-05-06 | 2026-03-30 | 2026-05-13 | 2102366178 | 8202241927 |  | CHECK VALVE POMPA SEI WAIN 2 & 3 RUSAK | RU5-UTL | P-2-S-WAIN/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 56411003 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K701 | 2026-06-03 | 2026-06-10 | 2026-06-03 | 2026-06-03 | 2102369397 | 8202243593 |  | CHANGE OF CATALYST NHTU JUNI 2026 | RU7-NHT | 2-R-01/00 | 50 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 46156727 | 0 | MA-STA |  | YAYANHER |  | 2026-06-05 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 005
| K701 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2102370032 | 8202243927 |  | Cek dan kalibrasi 2-FT-102 B | RU7-NHT | 2-FT-102B/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-4-D4H | 20475350 | 0 | MA-LINT |  |  |  |  | PT02 | 3 | 2 | 2026-06-18 | PM |  | 005
| K601 | 2026-04-29 | 2026-04-29 | 2026-02-09 | 2026-07-06 | 2102364033 | 8202242822 |  | BSTP LTSA Scaffolding 2025-2027 Tahap 6 | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 534516000 | 534516000 | MA1-STA |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K601 | 2026-05-07 | 2026-05-07 | 2026-04-13 | 2026-08-28 | 2102367852 | 8202243062 |  | BSTP LTSA Scaffolding 2025-2027 Tahap 6 | RU6-RCC | 19-V-111/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 534516000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K301 | 2026-05-29 | 2026-06-02 | 2026-01-01 | 2026-12-31 | 2102369467 | 8202243549 |  | BRD-instrument area CD VI | RU3-CDL | 26-FT-016/00 | 50 | REL CSER MSPT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA3-INT |  | RRAMADHANI |  | 2026-06-02 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-05-26 | 2026-06-10 | 2026-01-01 | 2026-12-31 | 2102368993 | 8202243526 |  | BRD-Flame detector YD 7 fault | RU3-CDL | FCC-RGT-FGDS/00 | 60 | REL CSER MACM PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 64900000 | 0 | MA3-INT |  | ALEPDALITAN |  | 2026-05-29 | PT02 | 3 | 3 | 2026-01-01 | PM |  | 005
| K301 | 2026-05-06 | 2026-05-25 | 2026-05-07 | 2026-05-07 | 2102368772 | 8202243044 |  | BRD - Temp. Air Compressor 2027 JC | RU3-UTL | 2027-JC/01 | 60 | REL CSER GMPS MACM PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 21405303 | 21405303 | MA2-ROT |  | ALEPDALITAN |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 045
| K301 | 2026-03-11 | 2026-04-02 | 2026-12-31 | 2026-12-31 | 2102366564 | 8202241589 |  | Bocoran expansion joint T G.01 R.31 |  |  | 50 WAMA | REL MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 108000000 | 0 | MA4-STA |  | ALEPDALITAN |  | 2026-03-12 | PT02 | 4 | 3 | 2026-12-31 | PM |  | 045
| K202 | 2026-04-16 | 2026-04-16 | 2026-04-01 | 2026-04-01 | 2102367181 | 8202242501 |  | BOCOR BAK CHEMICAL C.SODA WTP |  | 900-02TK-2/00 | 50 | CRTD NMAT PRC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | JUNAIDIT |  |  | PT02 | 3 | 2 | 2026-04-01 | PM |  | 003
| K201 | 2026-04-10 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2102365893 | 8202242334 |  | Blade dan Bearing Rusak | RU2-HCC | 211-EF-18A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 2034548 | 2034548 | MA2-ROT |  | ADEMULYADI |  | 2026-04-10 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K701 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2102369396 | 8202243592 |  | Bearing pompa rusak | RU7-OFF | 5-P-19B/00 | 50 | CRTD NMAT PRC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 005
| K501 | 2026-03-05 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2102365272 | 8202240698 |  | BEARING FAN VIBRASI TINGGI PADA EM-4-05A | RU5-E15111 | EA-4-05A/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 6622472 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-03-06 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K202 | 2026-05-18 | 2026-06-03 | 2026-05-12 | 2026-05-12 | 2102369024 | 8202243244 |  | Bearing DE dan NDE Pompa Stuck |  | 101-P-6C/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 109422947 | 109422948 | MAS-ME1 |  | JUNAIDIT |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K201 | 2026-03-13 | 2026-03-13 | 2026-12-02 | 2026-12-02 |  | 8202241719 | 8202241701 | AUDIT KINERJA CONTINOUS EMISSION MONITOR | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | STEVANEKOPP |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K701 | 2026-02-09 |  | 2026-01-02 | 2026-01-02 | 2102363992 | 8202238799 |  | Assessment Heat Tracing |  |  | 50 | CRTD NMAT PRC | 7RT | D17/26/B6/RT-1-D1H | 0 | 0 | MA-STA |  |  |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 005
| K701 | 2026-03-05 | 2026-03-05 | 2026-07-30 | 2026-07-30 | 2102366143 | 8202239476 |  | Assessment Heat Tracing |  |  | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/NR-5-D4H | 240000000 | 0 | MA-STA |  | RIZKAANDIKAP |  | 2026-03-05 | PT02 | 3 | 3 | 2026-07-30 | PM |  | 003
| K601 | 2026-04-09 | 2026-04-09 | 2026-01-20 | 2026-06-12 |  | 8202242263 | 8202238494 | Amandemen Perbaikan 42-T-404H | RU6-ITP | 42-T-404H/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 78000000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-09 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-03-11 | 2026-04-15 | 2026-03-11 | 2026-12-23 | 2102366542 | 8202241585 |  | Amandemen Kontrak Sewa Vacuum Truck | ITP-UP6 |  | 60 | CLSD NCMP NMAT PRC | 6MR | D16/26/B6/RT-C2H | 75240 | 0 | MA4-STA |  | DANDARWANI |  |  | PT02 | 1 | 2 | 2026-04-15 | PM |  | 045
| K501 | 2026-03-03 | 2026-03-10 | 2026-06-04 | 2026-06-04 | 2102365128 | 8202239404 |  | AIR FILTER K-235-01B INDIKASI KOTOR | RU5-D&W | K-235-01B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 24979712 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 003
| K301 | 2026-03-28 |  | 2026-01-02 | 2026-01-02 | 2102367013 | 8202241913 |  | Agitator DA-2102 trip | RU3-PP | 23-DA-BHM-2102/00 | 50 | REL CSER MANC PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 58500000 | 0 | MA2-ROT |  |  |  | 2026-03-28 | PT02 | 3 | 3 | 2026-01-02 | PM |  | 005
| K501 | 2026-06-05 | 2026-06-08 | 2026-06-05 | 2026-07-20 | 2102369002 | 8202243648 |  | aeaking Coupling Johnson Tangki A7 | RU5-TBL | A-7/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FCNH | 529004 | 0 | MA4-STA |  | BERNANDOP |  | 2026-06-08 | PT02 | 3 | 3 | 2026-06-05 | PM |  | 003
| K701 | 2026-04-01 | 2026-04-01 | 2026-01-02 | 2026-01-02 | 2102367244 | 8202242016 |  | Abnormal noise pada motor | RU7-CDU | 1-EAM-02B/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/26/B6/RT-1-D1H | 1276361 | 0 | MA-LINT |  | YAYANHER |  |  | PT02 | 3 | 2 | 2026-01-02 | PM |  | 005
| K301 | 2026-03-15 | 2026-04-29 | 2026-01-02 | 2026-12-31 | 2102366687 | 8202241726 |  | Abnormal noice pada DA-2201-PM1 | RU3-PP | 23-DA-2201-PM1/00 | 60 | REL CSER GMPS MACM PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 124766 | 124766 | MA2-LIS |  | ALEPDALITAN |  | 2026-03-15 | PT02 | 1 | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-06-22 | 2026-06-22 | 2026-09-01 | 2026-09-01 | 2102370090 | 8202244035 |  | 945-MM-28 Suara Motor Kasar | RU2-ITP | 945-MM-8/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 1816949 | 0 | MA4-LIS |  | STEVANEKOPP |  | 2026-06-22 | PT02 | 5 | 3 | 2026-09-01 | PM |  | 003
| K401 | 2026-03-17 | 2026-04-24 | 2026-04-15 | 2026-06-29 | 2102364105 | 8202241799 |  | 87P202C strainer suction kotor - ganti | RU4-KPC | 87P202C/00 | 50 WAMA | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 4 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-04-15 | PT02 | 4 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-03-11 |  | 2026-02-05 | 2026-02-05 | 2102361232 | 8202241584 |  | 85P210 B pengadaan / ganti flow meter | RU4-KPC | 85P210B/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-02-05 | PM |  | 003
| K401 | 2026-02-18 |  | 2026-02-05 | 2026-02-05 | 2102361236 | 8202238934 |  | 85FV235 opening stuck | RU4-KPC | 85FV235/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 4 | 2 | 2026-02-05 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-21 | 2026-06-19 | 2026-12-22 | 2102369766 | 8202243839 |  | 85C204 valve tray rusak | RU4-KPC | 85C204/00 | 50 | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 045
| K401 | 2026-05-26 | 2026-06-19 | 2026-05-26 | 2026-05-26 | 2102369328 | 8202243513 |  | 84C204 terdapat rembers 25 mei - hardcoa | RU4-KPC | 84C204/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 045
| K401 | 2026-06-04 | 2026-06-20 | 2026-06-17 | 2026-12-22 | 2102369449 | 8202243636 |  | 84C204 leakage area stiffener ring #1 | RU4-KPC | 84C204/00 | 50 | REL CSER GMPS MANC PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 93963366 | 90397295 | MA4-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-02-06 | 2026-02-12 | 2026-02-02 | 2026-02-02 | 2102355541 | 8202238705 |  | 84BV55 leakage di gland pac | RU4-KPC | 84BV73/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | DWIHIZZKI |  |  | PT02 | 5 | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2102360362 | 8202234621 |  | 8202232138#Penggantian Hose STS | RU5-E15111 | C-1-01/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/26/B6/RT-C2H | 590362500 | 0 | MA4-STA |  | BERNANDOP |  | 2026-05-29 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-17 | 2026-02-02 | 2026-02-02 | 2102358747 | 8202234610 |  | 8202232137#Perbaikan Pompa G-3-01C (RTJ | RU5-E15112 | G-3-01C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 5621152 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-06-17 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-15 | 1102327682 | 8202234615 |  | 8202232136#Perbaikan Flow Main Steam Boi | RU5-UTL | B5-FT-202/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/26/B6/RT-C2H | 11786000 | 0 | MA1-INT |  | BERNANDOP |  | 2026-03-03 | PT02 |  | 3 | 2026-06-09 | PM |  | 004
| K201 | 2026-02-01 | 2026-05-08 | 2026-01-29 | 2026-01-29 | 2102351564 | 8202232209 |  | 8202232134#Penambahan double valve drain | RU2-ITP | TK-103/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/NR-D2H | 0 | 6647180 | MA4-STA |  | NURFADHILLA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-30 | 2026-12-30 | 2102358750 | 8202234604 |  | 8202232133#Penggantian Valve Outlet CPI | RU5-TBL | V-17A/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 004
| K201 | 2026-02-01 | 2026-05-26 | 2026-01-30 | 2026-01-30 | 2102351562 | 8202232717 |  | 8202232132#Pengambilan material gasket | RU2-ITP | P-207A-DMI/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/NR-D2H | 0 | 266355 | MA4-ROT |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102357518 | 8202235405 |  | 8202232131#D_26 014V-127 perbaikan lamp | RU4-FOC2 | 014V127/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102358264 | 8202235401 |  | 8202232130#D_26 Motor 024P-121A High Vib | RU4-LOC2 | 024P121A/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102356976 | 8202235406 |  | 8202232129#D_26 011P-108: B vibrasi tert | RU4-FOC2 | 011P108BM/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102356515 | 8202235403 |  | 8202232128#D_26 048 K-012 C motor short | RU4-FOC2 | 019K102CM/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K201 | 2026-02-01 | 2026-04-23 | 2026-02-03 | 2026-02-03 | 2102351563 | 8202232683 |  | 8202232127#Perbaikan Indikasi kerusakan | RU2-PK | 970-P-1A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 994300 | 994300 | MA3-STA |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355693 | 8202235407 |  | 8202232126#D_26 011E110M09 motor noise | RU4-FOC2 | 011E110M09/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-26 | 2026-01-30 | 2026-03-16 | 2102363093 | 8202232140 |  | 8202232125#Per.Gen. Steam Turbin 51-P-10 | RU6-UTL | 51-P-101D-T/00 | 50 | REL GMPS NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 343800000 | 292230000 | MA4-ROT |  | DANDARWANI |  | 2026-02-19 | PT02 |  | 3 | 2026-01-30 | PM |  | 004
| K701 | 2026-02-03 | 2026-02-18 | 2026-12-30 | 2026-12-30 | 2102358135 | 8202238010 |  | 8202232124#Perbaikan Crane Link Belt RTC | RU7-WS | 7-CR-01/00 | 50 | REL GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 954278001 | 877935000 | MA-STA |  | RYANMANGGASA |  | 2026-02-18 | PT02 | 6 | 3 | 2026-12-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355651 | 8202235568 |  | 8202232123#26_gland, kable, 3/4 In, 1 in |  |  | 50 | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355608 | 8202235533 |  | 8202232122#26_lamp, indicator, AD11622DS |  |  | 50 | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355654 | 8202235617 |  | 8202232121#26_connection Box, Elect CBL, |  |  | 50 | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-30 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360726 | 8202234606 |  | 8202232120#kontaktor motor GM-32-03B rus | RU5-UTL | GM-32-03B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 4 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-09 | 2026-01-30 | 2026-03-06 | 2102351043 | 8202232166 |  | 8202232118#Penggantian Positioner 17-LV- | RU6-RCC | 17-LV-010/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-02-09 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-02 | 2026-01-30 | 2026-01-30 | 2102358051 | 8202235627 |  | 8202232117#26_[PdM] 011K101BP2 vibrasi c | RU4-FOC2 | 011K101B-P2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 23025000 | 23025000 | MA2-ROT |  | ABDULFM |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2026-01-30 | 2026-01-30 | 2102358052 | 8202235385 |  | 8202232116#Penggantian mechanical seal 1 | RU4-FOC1 | 14P4B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 4475890 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-04 | 2026-03-06 | 2026-01-30 | 2026-01-30 |  | 8202238585 |  | 8202232115#Steam Trap 101-ST-013 | RU4-RFCC | 101E534/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-STA |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2026-01-30 | 2026-01-30 | 2102354428 | 8202235696 |  | 8202232114#26_[CR] Penggantian mechanica | RU4-FOC1 | 14P5A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 9659699 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-30 | 2026-01-30 |  | 8202238602 |  | 8202232113#26_[CR] Penggantian Belt 16K2 | RU4-FOC1 | 16K2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 210600 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-22 | 2026-02-24 | 2026-11-26 | 2102355431 | 8202235663 |  | 8202232112#26_[CR] Perbaikan Tandemseal | RU4-RFCC | 104P503A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102356069 | 8202235691 |  | 8202232111#26_[CR] Perbaikan bocoran Aux | RU4-FOC1 | 11K401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2026-01-30 | 2026-01-30 | 2102360532 | 8202235704 |  | 8202232110#26_[CR] Penggantian Filter Lu | RU4-FOC1 | 14K602BM-S1A/B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 6668182 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2026-02-27 | 2026-12-22 | 2102361030 | 8202235626 |  | 8202232109#26_[PV] Penggantian Belt 11E5 | RU4-FOC1 | 11E50K-R/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 6150926 | 6150926 | MA1-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102356476 | 8202235683 |  | 8202232108#26_[CR] Perbaikan Mech Seal 1 | RU4-RFCC | 103P503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355987 | 8202235636 |  | 8202232107#26_[CR]Perbaikan 47P503B-ROT | LOC1-UP4 | 47P503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-17 | 2026-01-29 | 2026-04-10 | 2102358755 | 8202235954 |  | 8202232106#Tag-6, U/R Cleaning Sump" |  |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 247633000 | 0 | MA3-STA |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102353026 | 8202234383 |  | 8202232105#NR26-Perbaikan motor FC-PM-4B | RU3-CDL | FC-PM-4B/01 | 50 WAMA | CRTD CSER MACM PRC | 3ER |  | 0 | 0 | MA3-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-24 | 2026-04-07 | 2026-08-26 | 2102356196 | 8202235431 |  | 8202232104#26_Perbaikan Pressure Gauge U | RU4-FOC1 | PI-U12/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 43290102 | 43290102 | MA1-INT |  | TEGARPRAMUDY |  | 2026-02-07 | PT02 |  | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-16 | 2026-03-03 | 2026-12-30 | 2102355620 | 8202235697 |  | 8202232102#26_[CR] Penggantian Mech Seal | RU4-TRML | 041P106B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 38688350 | 41950550 | MA2-ROT |  | ABDULFM |  | 2026-03-03 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-17 | 2026-01-29 | 2026-04-10 | 2102358754 | 8202235986 |  | 8202232100#"Tag-5, U/R Cleaning Sump" |  |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 249599000 | 0 | MA3-STA |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-30 | 2026-01-30 | 2102355450 | 8202235711 |  | 8202232099#26_[CR] Belt Finfan Aus 140E6 | RU4-GTO | 140E607J-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 6900000 | MA7-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-30 | 2026-01-30 | 2102357988 | 8202235708 |  | 8202232098#26_[CR] High vibrasi pada pom | RU4-LOC3 | 240P119/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 6928350 | MA4-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-14 | 2026-01-14 | 2102356321 | 8202241290 |  | 8202232097#Penambahan UPS - APC Smart OT | RU4-RFCC | 100UY-U100/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 045
| K401 | 2026-02-02 | 2026-04-23 | 2026-01-30 | 2026-01-30 | 2102357150 | 8202235633 |  | 8202232096#26_[CR]Perbaikan mech seal 91 | RU4-SRU | 91P403B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-05 | 2026-01-30 | 2026-01-30 | 2102357098 | 8202235643 |  | 8202232095#26_[CR] Pompa 88P203B Mech Se | RU4-KPC | 88P203B/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 134327076 | MA4-ROT |  | SAPBATCH | 2026-05-05 | 2026-02-07 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-02 | 2026-01-30 | 2026-01-30 | 2102357092 | 8202235694 |  | 8202232094#26_[CR] Perbaikan 21P7A (pelu | RU4-LOC1 | 21P7A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 8244450 | 8244450 | MA1-ROT |  | ABDULFM |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102356974 | 8202235722 |  | 8202232093#26_[CR] 011K101A abnormal noi | RU4-FOC2 | 011K101A/01 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-30 | 2026-01-30 | 2102356692 | 8202235634 |  | 8202232092#26_[CR]Perbaikan bearing 91E4 | RU4-SRU | 91E409A2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 10798760 | MA1-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-30 | 2026-01-30 | 2102356690 | 8202235647 |  | 8202232091#26_[CR] Pompa 85P205B Mech Se | RU4-KPC | 85P205B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355333 | 8202235713 |  | 8202232090#26_[CR] Belt fin fan putus 26 | RU4-LOC3 | 260E125K1/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355331 | 8202235715 |  | 8202232089#26_[CR] Belt fin fan putus 24 | RU4-LOC3 | 240E125K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-27 | 2026-01-30 | 2026-01-30 | 2102353582 | 8202235718 |  | 8202232088#26_[CR] 86P206B mech seal boc | RU4-KPC | 86P206B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-ROT |  | ABDULFM |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102354632 | 8202235688 |  | 8202232087#26_[CR] Perbaikan Leak Filter | RU4-RFCC | 103P506/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102357497 | 8202235657 |  | 8202232086#26_[CR] Pngadaan gear piston | RU4-RFCGTO | 166P562B/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-12-30 | 2102357491 | 8202235679 |  | 8202232085#26_[CR] Perbaikan mech seal p | RU4-RFCC | 101P502C/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 197315667 | 26463000 | MA6-ROT |  | LUQMANULH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-12-30 | 2102357490 | 8202235676 |  | 8202232084#26_[CR] Perbaikan mech seal p | RU4-RFCC | 101P501A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 26463000 | 0 | MA6-ROT |  | LUQMANULH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-13 | 2026-06-29 | 2026-06-29 | 2102360740 | 8202234465 |  | 8202232083#FIN FAN KEA-201-01A VIBRASI T | RU5-D&W | KEA-201-01A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 2196287 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-03-05 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-06-02 | 2026-06-02 | 2102358774 | 8202235902 |  | 8202232082#SPARE PART K-4-01A (NON OEM - | RU5-E15111 | K-4-01A/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-06-02 | 2026-06-02 | 2102358775 | 8202235898 |  | 8202232081#SPARE PART K-5-02A (NON OEM - | RU5-E15111 | K-5-02A/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358757 | 8202235905 |  | 8202232080#SIGHT GLASS G-5-04B KONDISI P | RU5-E15111 | G-5-04B/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102360724 | 8202234424 |  | 8202232079#MEMBRANE COUPLING POMPA G-5-2 | RU5-E15111 | G-5-22A/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-14 | 2026-03-17 | 2026-04-21 | 2102359144 | 8202234417 |  | 8202232077#Pengadaan Kabel Signal Meteri | RU5-TBL | METER-4581/00 | 50 | REL CSER MANC PRC SETC | 5IR | D15/26/B6/RT-C2H | 103351520 | 0 | MA4-INT |  | RIANDAADI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-17 | PM |  | 004
| K401 | 2026-02-02 | 2026-04-30 | 2026-01-29 | 2026-01-29 | 2102355542 | 8202235462 |  | 8202232076#26_Perbaikan DC Charger 150BD | RU4-RFCUTL | 150BD2EE0131A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 0 | 230000000 | MA5-LIS |  | AHMADZAENURI | 2026-04-30 | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-06-19 | 2026-01-29 | 2026-12-30 | 2102355356 | 8202235467 |  | 8202232075#26_Perbaikan AVR (Thyristor) | RU4-RFCUTL | 152G501C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-LIS |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-06-19 | 2026-01-29 | 2026-12-30 | 2102355198 | 8202235456 |  | 8202232074#26_Perbaikan Lampu Penerangan | RU4-UTL | 051LSL003/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-18 | 2026-08-26 | 2102353411 | 8202235409 |  | 8202232071#87P202C Temp indicator lin | RU4-KPC | 87P202C/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-26 | 2102353409 | 8202235411 |  | 8202232070#87P202B Temp indicator lin | RU4-KPC | 87P202B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-26 | 2102353407 | 8202235412 |  | 8202232069#87P202A Temp indicator lin | RU4-KPC | 87P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-26 | 2102353405 | 8202235414 |  | 8202232068#87P201B Temp indicator lin | RU4-KPC | 87P201B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-24 | 2026-02-10 | 2026-08-27 | 2102353404 | 8202235416 |  | 8202232067#87P201B Press indicator li | RU4-KPC | 87P201B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1355534 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102353402 | 8202235419 |  | 8202232066#87P201A Temp indicator lin | RU4-KPC | 87P201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-24 | 2026-02-10 | 2026-08-27 | 2102353403 | 8202235421 |  | 8202232065#87P201A Press indicator li | RU4-KPC | 87P201A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1355534 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102356271 | 8202235488 |  | 8202232064#26_Penggantian PCV L.O 510PCV | RU4-UTL | 510PSV146/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 90997000 | 0 | MA5-INT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-21 | 2026-01-29 | 2026-01-29 | 2102355244 | 8202235702 |  | 8202232063#26_[CR] Penggantian M. Seal 0 | RU4-UTL | 054P101A-P1A/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | YMOHAMMAD | 2026-06-11 | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K201 | 2026-02-05 | 2026-06-09 | 2026-04-01 | 2026-04-01 | 2102351565 | 8202238650 |  | 8202232062#RK0296 LTSA Sapu Jagat Ele | RU2-UTL | 905-LPN-ES4/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 200000000 | 0 | MA3-LIS |  | ADEMULYADI |  | 2026-02-20 | PT02 |  | 3 | 2026-04-01 | PM |  | 003
| K202 | 2026-02-02 | 2026-05-11 | 2026-04-22 | 2026-07-20 | 2102352365 | 8202234299 |  | 8202232061#Re Notif : Add Penm Waktu Sew | RU2S-KIL | 900-08B-2/01 | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/26/B6/NRZ-D3H | 1067220000 | 125235000 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-11 | PT02 |  | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-14 | 2026-01-14 | 2102356966 | 8202241289 |  | 8202232060#26_[CR] Perbaikan linkage tri | RU4-UTL | 052P102B-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 26172471 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355746 | 8202235481 |  | 8202232057#26_PERB ELEVATOR CDU II PILLO | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 67710000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355749 | 8202235485 |  | 8202232056#26_PERB ELEVATOR CDU II LEVEL | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 74000000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355772 | 8202235504 |  | 8202232055#26_PEK. PM ELEVATOR 011S104 A | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 27750000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K201 | 2026-02-01 | 2026-06-04 | 2026-03-01 | 2026-06-02 | 2102352122 | 8202232690 |  | 8202232054#PERBAIKAN STRUKTUR DAN SLUICE | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 2108800000 | 0 | MA3-STA |  | NURFADHILLA |  | 2026-02-20 | PT02 |  | 3 | 2026-03-01 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355699 | 8202235503 |  | 8202232053#26_PEK. PM ELEVATOR 011S104 L | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 15525000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355744 | 8202235496 |  | 8202232052#26_PEK. PM ELEVATOR 011S104 P | RU4-FOC2 | 011S104/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 8500000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355697 | 8202235473 |  | 8202232051#26_PERB ELEVATOR CDU II SENSO | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355742 | 8202235499 |  | 8202232050#26_PEK. PM ELEVATOR 011S104 P | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 203130000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355740 | 8202235478 |  | 8202232049#26_PERB ELEVATOR CDU II REPEA | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 40250000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K501 | 2026-02-03 | 2026-06-17 | 2026-05-26 | 2026-05-26 | 2102359587 | 8202238000 |  | 8202232048#PSA Transformer di RU V (T18) | RU5-UTL | 1AL07/00 | 50 | REL NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 300000000 | 0 | MA1-LIS |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-25 | 2026-01-14 | 2026-01-14 | 2102355759 | 8202241288 |  | 8202232047#26_[CR] Perbaikan pompa 57P10 | RU4-UTL | 57P102B/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR | 2026-06-11 | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-29 | 2026-01-29 | 2102355776 | 8202235498 |  | 8202232046#26_PEK. PM ELEVATOR 011S104 P | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 41000000 | MA2-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102356701 | 8202235625 |  | 8202232045#26_[PV] RTL Bad Actor Mseal 8 | RU4-KPC | 87P201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102356703 | 8202235624 |  | 8202232044#26_[PV] RTL Bad Actor Mseal 8 | RU4-KPC | 87P201B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-01-14 | 2026-01-14 | 2102355757 | 8202241287 |  | 8202232043#26_[CR] Perbaikan pompa 57P10 | RU4-UTL | 57P102A/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR | 2026-06-11 | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102356705 | 8202235622 |  | 8202232042#26_[PV] RTL Bad Actor Mseal 8 | RU4-KPC | 87P202B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-02-09 | 2026-02-09 | 2102359146 | 8202234439 |  | 8202232041#MAT.PERB. E-8-18B | RU5-E15112 | E-8-18B/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 1933200 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-02-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-29 | 2026-05-11 | 2102361315 | 8202232165 |  | 8202232040#Perbaikan Motor 20-E-104A | RU6-RCC | 20-E-104A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-06-19 | 2102359145 | 8202234447 |  | 8202232039#MAT.PERB. E-8-18A | RU5-E15112 | E-8-18A/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 26120950 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-10-29 | 2026-10-29 | 2102359651 | 8202234458 |  | 8202232038#kabel tray AOP AC & DC STG 1 | RU5-UTL | AOP-TG6-PP1/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 2436024 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-10-29 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-29 | 2026-05-11 | 2102362387 | 8202237444 |  | 8202232037#Perbaikan Motor 20-P-104A | RU6-RCC | 20-P-104A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 |  | 8202234415 |  | 8202232036#Penggantian Bearing motor JP | RU5-E15500 | G-33-02B/01 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 1039200 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-29 | 2026-05-05 |  | 8202232163 | 8202233691 | 8202232035#Penggantian Bearing Pompa 052 | RU6-UTL | 052-P-101C/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-09-29 | 2026-09-29 | 2102360655 | 8202234453 |  | 8202232034#LAMPU PENERANGAN AREA DEMIN R | RU5-UTL | DEMIN-123-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 223188420 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-09-29 | PM |  | 004
| K202 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-01-02 | 2102352362 | 8202234298 |  | 8202232033#Re Notif : Kontr Vol Perb Dal | RU2S-KIL | 101-T-1/00 | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/26/B6/NRZ-D2H | 396343000 | 396343000 | MAS-ME1 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-05-08 | 2026-03-10 | 2026-03-10 | 2102351432 | 8202232680 |  | 8202232032#Perbaikan motor 200-PM-7B | RU2-ITP | 200-PM-7B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 2518908 | 2349660 | MA4-LIS |  | NURFADHILLA |  | 2026-02-07 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-29 | 2026-01-29 | 2102351780 | 8202232507 |  | 8202232031#211-212 F1 Kotor | RU2-HCC | 211-F-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-26 | 2026-02-23 | 2026-07-15 |  | 8202232146 | 8202233889 | 8202232030#LTSA Tabel Volume Tangki Taha | RU6-ITP | 42-T-101B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 73800000 | 58900000 | MA4-STA |  | DANDARWANI |  | 2026-02-23 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-10 | 2026-03-10 | 2102351222 | 8202232681 |  | 8202232029#Perbaikan Motor 140 PM-18 | RU2-HOC | 140-PM-18/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 169248 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-12 | 2026-02-18 | 2026-11-26 | 2102357439 | 8202235725 |  | 8202232028#26_(BON PINJAM) Perbaikan Par | RU4-RFCC | 101A525A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-10 | 2026-03-10 | 2102351011 | 8202232693 |  | 8202232027#Perbaikan Bearing 140 EM-6B | RU2-HOC | 140-EM-6B/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 445000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-29 | 2026-01-29 | 2102355364 | 8202235628 |  | 8202232025#26_[NP] 017P104A mech seal bo | RU4-FOC2 | 017P104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-02-18 | 2026-11-25 | 2102353538 | 8202235728 |  | 8202232022#26_(BON PINJAM) Perbaikan 53P | RU4-UTL | 53P1B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 2350000 | 2350000 | MA5-INT |  | YMOHAMMAD |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-08 | 2026-04-07 | 2026-11-05 | 2102354604 | 8202235378 |  | 8202232021#Perbaikan TG Casing Pompa 101 | RU4-RFCC | 101P501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 2 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-08 | PT02 |  | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2026-02-18 | 2026-11-26 | 2102357493 | 8202235398 |  | 8202232020#D26_Perbaikan Indikasi CV Pas | RU4-RFCC | 102FT-U102/00 | 60 | CLSD CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-02-18 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-23 | 2026-02-18 | 2026-11-26 | 2102357319 | 8202235723 |  | 8202232019#26_(BON PINJAM) Perbaikan Sen | RU4-RFCC | 101-DA0230-1-1/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 9078000 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-02-18 | PT02 | 8 | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-28 | 2026-01-28 | 2102355512 | 8202235458 |  | 8202232018#26_perbaikan Ignitor boiler 5 | RU4-UTL | 52B2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-07-10 | 1102328669 | 8202235890 |  | 8202232017#PENGAMBILAN MATERIAL INTRUMEN | RU5-E15112 | 31-PIC-070/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/26/B6/RT-C2H | 368760427 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 004
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-28 | 2026-01-28 | 2102355687 | 8202235389 |  | 8202232016#Modifikasi Line Produksi Avtu | RU4-TRML | 032PSV302D/00 | 60 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 45324282 | MA3-STA |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-28 | 2026-01-28 | 2102355860 | 8202235707 |  | 8202232015#26_[CR] Kerusakan IDF 105F501 | RU4-RFCGTO | 105F501K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-04 | 2026-01-28 | 2026-03-12 | 2102351031 | 8202232162 |  | 8202232014#Perbaikan pompa | RU6-ITP | 42-P-503B/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 497456846 | 497444966 | MA4-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-08 | 2026-05-07 | 2026-08-07 | 2102358762 | 8202235884 |  | 8202232013#Perbaikan Pompa G-202-04B | RU5-D&W | G-202-04B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 70914800 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-03-05 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2102360729 | 8202235886 |  | 8202232012#Penggantian O-ring Coalescer | RU5-E15112 | K-3-01A/00 | 50 | REL CSER NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2102360728 | 8202235893 |  | 8202232011#Material Rerate GT-3-09C | RU5-E15112 | GT-3-09C/00 | 50 | REL CSER NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K701 | 2026-02-02 | 2026-03-16 | 2026-12-30 | 2026-12-30 | 2102358515 | 8202234957 |  | 8202232010#Priming Pump DE Fire Pump Bac |  |  | 50 | REL GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-4-D1H | 523456058 | 523000000 | MA-ROT |  | RYANMANGGASA |  | 2026-02-07 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-29 | 2026-05-11 | 2102362433 | 8202232161 |  | 8202232008#Overhaul Motor 12-K-501B | RU6-DHC | 12-K-501B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-31 | 2026-01-28 | 2026-01-28 | 2102355834 | 8202235661 |  | 8202232007#26_[CR] Perbaikan Turbin 057P | RU4-UTL | 057P101A-T/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | TONNYADI | 2026-03-25 | 2026-02-07 | PT02 |  | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-28 | 2026-01-28 | 2102356518 | 8202235674 |  | 8202232006#26_[CR] Perbaikan Pompa 103P5 | RU4-RFCC | 103P503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-11 | 2026-01-28 | 2026-06-23 | 2102362173 | 8202232145 |  | 8202232005#LTSA Scaffolding 2025-2027 Ta | RU6-DHC | 13-E-105/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 497526000 | MA2-STA |  | T_YUDIPRAS |  | 2026-03-11 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-28 | 2026-01-28 | 2102357987 | 8202235710 |  | 8202232004#26_[CR] Belt Finfan Aus 140E6 | RU4-GTO | 140E607J-B/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-28 | 2026-01-28 | 2102358019 | 8202235638 |  | 8202232003#26_[CR]Penggantian belt finfa | RU4-SRU | 91E402AM/00 | 60 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-28 | 2026-01-28 | 2102358010 | 8202235686 |  | 8202232001#26_[CR] Perbaikan major repai | RU4-TRML | 42P4A/00 | 60 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-24 | 2026-01-28 | 2026-01-28 | 2102355328 | 8202235720 |  | 8202232000#26_[CR] 011P112B performance | RU4-FOC2 | 011P112B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-08 | 2026-01-21 | 2026-01-21 | 2102352360 | 8202234297 |  | 8202231998#KEBOCORAN LINE 18 INCH 946 TK | RU2S-KIL | 8PL900001-A1A1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 34690155 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-03-08 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-28 | 2026-06-23 |  | 8202232147 | 8202238735 | 8202231996#SWO Sewa Barge Tahap 6 | RU6-ITP | 43-SPM-01/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 40000000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K601 | 2026-02-08 | 2026-04-14 | 2026-01-19 | 2026-06-11 |  | 8202238739 | 8202234037 | 8202231995#SWO LTSA Clning Mnyk Rngn Th | RU6-HSC | 11-V-101B/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 320690000 | 272586500 | MA1-STA |  | DANDARWANI |  | 2026-04-14 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-08 | 2026-01-20 | 2026-01-20 | 2102351448 | 8202234296 |  | 8202231994#MATERIAL FINFAN 101-E6 CDU SP | RU2S-KIL | 6PL101118B-A1A1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-23 | 2026-01-28 | 2026-01-28 | 2102356624 | 8202235671 |  | 8202231993#26_[CR] Perbaikan Pompa 70P1B | RU4-TRML | 70P1B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 28000001 | 0 | MA3-ROT |  | YUNITAMR |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K601 | 2026-02-08 | 2026-04-09 | 2026-01-19 | 2026-06-29 |  | 8202238738 | 8202233429 | 8202231992#Penyelesaian PMPDM Elect&Inst | RU6-POC | 18-PSW2-01-001/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 70992000 | 70992000 | MA3-LIS |  | DANDARWANI |  | 2026-04-09 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K401 | 2026-02-05 |  | 2026-01-28 | 2026-01-28 | 2102357821 | 8202238645 |  | 8202231991#TGH4_24 UP Scaff Rejuve MA-3 |  |  | 50 | CRTD CSER NMAT PRC | 4MR | D14/09/B6/RTNH | 11704970 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-01-28 | PM |  | 045
| K201 | 2026-02-01 | 2026-05-21 | 2026-01-28 | 2026-01-28 | 2102351225 | 8202232708 |  | 8202231990#Penggantian Material 580 P 30 | RU2-UTL | 580-P-302D/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 13161980 | 12825260 | MA3-ROT |  | NURFADHILLA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-01-28 | 2026-01-28 | 2102351999 | 8202232675 |  | 8202231989#Conmon 300-PT-61 | RU2-HSC | 300-PT-61/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-12 | 2026-01-26 | 2026-12-30 | 2102356799 | 8202235495 |  | 8202231988#26_Pengadaan Matl utk 156-K-5 | RU4-RFCUTL | 156K501A/00 | 60 | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 88500000 | 0 | MA5-STA |  | TONNYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 045
| K201 | 2026-02-01 | 2026-04-23 | 2026-01-28 | 2026-01-28 | 2102351683 | 8202232207 |  | 8202231987#Penambahan lampu sorot area O | RU2-ITP | 945-P-4A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 261848 | 261848 | MA4-ROT |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K401 | 2026-02-03 | 2026-05-05 | 2026-04-01 | 2026-12-30 | 2102353418 | 8202237951 |  | 8202231986#TGH6_25 Upgrade APC FOC II | RU4-FOC2 | DCS-FOC2/00 | 60 | CLSD CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 429900000 | 429900000 | MA2-INT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-28 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-28 | 2026-01-28 | 2102352101 | 8202232510 |  | 8202231985#1erbaikan dan pengadaan gear | RU2-ITP | 610-GG-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 15898 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-10-01 | 2026-12-31 | 2102358769 | 8202238614 |  | 8202231984#PENGGANTIAN BREAKER MV SS 6 | RU5-UTL | 41-R-SS-6-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/NR-C3H | 5 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-10-01 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-26 | 2026-01-26 | 2102353536 | 8202237950 |  | 8202231983#[TGH] Tagihan Gland Seal Pomp | LOC1-UP4 | 47P503A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 37427000 | 37427000 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102359471 | 8202238616 |  | 8202231982#Pengadaan Relay STG 2.1 & STG | RU5-UTL | 0VG01D001/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 2 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K401 | 2026-02-05 | 2026-03-06 | 2026-02-23 | 2026-11-26 | 2102357258 | 8202238598 |  | 8202231981#26_Pengadaan Material Freezin | RU4-FOC2 | 30BD12EE0012A/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 3 | 0 | WS-INT |  | YMOHAMMAD |  | 2026-02-23 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102359014 | 8202238606 |  | 8202231980#Perbaikan Speed sensor DEG 1 | RU5-UTL | 0SU50D002/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 6 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K401 | 2026-02-05 | 2026-03-06 | 2026-02-23 | 2026-11-26 | 2102357310 | 8202238597 |  | 8202231979#26_Pengadaan Material JFTOT M | RU4-FOC2 | 30BD12EE0012A/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 2 | 0 | WS-INT |  | YMOHAMMAD |  | 2026-02-23 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-03-09 | 2026-06-18 | 2026-01-20 | 2026-12-30 |  | 8202241383 |  | 8202231974#TGH2_24 UP Piping FOC II | RU4-FOC2 | 012V101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 1188646000 | 1188646000 | MA2-STA |  | FARIZSETYANA |  | 2026-03-09 | PT02 |  | 3 | 2026-01-20 | PM |  | 045
| K201 | 2026-02-01 | 2026-04-10 | 2026-02-25 | 2026-02-25 | 2102351221 | 8202232676 |  | 8202231973#Perbaikan Turbine 110-PT-3B | RU2-HOC | 110-PT-3B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 284000 | 284000 | MA1-ROT |  | MDSYAHPUTRA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-25 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-06 | 2026-01-27 | 2026-01-27 | 2102351220 | 8202232684 |  | 8202231972#Perbaikan FDF 110-C-52A | RU2-HOC | 110-C-52A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 155086080 | 155086080 | MA1-ROT |  | ADEMULYADI |  | 2026-02-25 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-27 | 2026-02-02 | 2102360768 | 8202235867 |  | 8202231971#PERB.LINE SUCTION 6" DI RUMAH | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-27 | PM |  | 003
| K501 | 2026-02-03 | 2026-06-17 | 2026-07-30 | 2026-07-30 |  | 8202237999 | 8202234369 | 8202231970#NRK_Pekerjaan pemasangan EHT | RU5-E15112 | EHT-100-3/00 | 50 | REL NMAT PRC SETC | 5ER | D15/26/B6/NR-C3H | 162323000 | 0 | MA3-LIS |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-04 | 2026-01-27 | 2026-01-27 | 2102356618 | 8202235650 |  | 8202231969#26_[CR] Pompa 85P203B Mech Se | RU4-KPC | 85P203B/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 16111300 | 0 | MA4-ROT |  | EDWINK |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-04 | 2026-01-27 | 2026-01-27 | 2102356616 | 8202235654 |  | 8202231968#26_[CR] Pompa 85P203A Mech Se | RU4-KPC | 85P203A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 16111300 | 0 | MA4-ROT |  | EDWINK |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K201 | 2026-02-01 | 2026-05-19 | 2026-01-27 | 2026-01-27 | 2102352131 | 8202232505 |  | 8202231967#300-P-3B Mechanical Seal Boco | RU2-HSC | 300-P-3B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 3454126 | 3347126 | MA2-ROT |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K401 | 2026-02-05 | 2026-04-23 | 2026-04-23 | 2026-11-30 | 2102358317 | 8202238591 |  | 8202231966#26_Perbaikan Panel GCP Synchr | RU4-UTL | 51G1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 2 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-04-23 | PT02 | 4 | 3 | 2026-04-23 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-06-23 | 2026-06-23 | 2102359089 | 8202235865 |  | 8202231965#PERBAIKAN POMPA G-202-03A | RU5-D&W | G-202-03A/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 22000862 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-04-30 | PT02 |  | 3 | 2026-06-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-27 | 2026-12-30 | 2102358761 | 8202235864 |  | 8202231964#Tube Titanium Kajian E-202-04 | RU5-D&W | E-202-04/00 | 50 | REL CSER NMAT PRC SETC | 5MR | D15/26/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-01-27 | 2026-02-09 |  | 8202235871 |  | 8202231963#PERB.LINE 602-6" HVGO PIPERAC | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-27 | 2026-01-27 | 2102356578 | 8202235641 |  | 8202231962#26_[CR] Shoot blower macet 26 | RU4-LOC3 | 260ME151-SBL-M1/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-03-06 | 2026-05-11 | 2102360575 | 8202235877 |  | 8202231961#Perb PI Loader Valve K-4-01B | RU5-E15111 | K-4-01B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 30 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-24 | 2026-01-26 | 2026-03-10 | 2102350996 | 8202232160 |  | 8202231960#Perbaikan 12-K-502B | RU6-DHC | 12-K-502B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2 | 0 | 4727854 | MA2-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-27 | 2026-02-09 | 2102351025 | 8202232159 |  | 8202231958#Penggantian Mech Seal 32-P-10 | RU6-HSC | 32-P-104A/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-12 | 2026-01-27 | 2026-06-22 |  | 8202232142 | 8202233889 | 8202231957#LTSA Tabel Volume Tangki Taha | RU6-ITP | 42-T-101B/00 | 60 | REL PRT GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 83900000 | 83900000 | MA4-STA |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-27 | 2026-05-07 | 2102362530 | 8202232158 |  | 8202231956#Perbaikan Level Transmitter 1 | RU6-RCC | 15-LT-510/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-27 | 2026-03-13 | 2102351020 | 8202232157 |  | 8202231955#Penggantian Vibration Switch | RU6-DHC | 12-K-501A/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-28 | 2026-08-26 | 1102327777 | 8202235880 |  | 8202231954#PENGADAAN HORN DAN SOLENOID d | RU5-E15111 | G-5-16B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 123196800 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-28 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-11 | 2026-01-26 | 2026-01-26 | 2102358772 | 8202235866 |  | 8202231953#Perbaikan GTH-3-01A | RU5-E15112 | GTH-3-01A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-05-29 | 2026-06-12 | 2102364388 | 8202238609 |  | 8202231952#Perbaikan Level Indicator Tan | RU5-E15500 | 33-FWP-01C/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-05-29 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2102359701 | 8202235844 |  | 8202231951#Perbaikan Kompresor K-3-02C | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 254981369 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-03 | 2026-05-13 | 2026-01-26 | 2026-03-31 | 2102360435 | 8202237998 |  | 8202231950#Pek.Perb.Bocoran Steam & Isol | RU5-E15112 | 2-ACW01-4-A4/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 180000000 | 180000000 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-24 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K201 | 2026-02-05 | 2026-04-29 | 2026-05-26 | 2026-05-26 | 2102351498 | 8202238655 |  | 8202231949#702-H1 Rusak | RU2-HCC | 702-H-1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1525000000 | 0 | MA2-STA |  | CHANRARD |  | 2026-04-28 | PT02 |  | 3 | 2026-05-26 | PM |  | 006
| K401 | 2026-02-02 | 2026-06-12 | 2026-01-26 | 2026-01-26 | 2102356612 | 8202235631 |  | 8202231948#26_[CR]Replace membrane coupl | RU4-UTL | 54P204B/00 | 60 | TECO CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 16784316 | 0 | MA5-ROT |  | TONNYADI | 2026-03-30 | 2026-02-07 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-27 | 2026-01-21 | 2026-12-31 | 2102359478 | 8202235848 |  | 8202231947#Perbaikan E-201-12 | RU5-D&W | E-201-12/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 230797493 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-07 | PT02 | 4 | 3 | 2026-01-21 | PM |  | 004
| K401 | 2026-02-02 | 2026-06-12 | 2026-01-26 | 2026-01-26 | 2102357916 | 8202235666 |  | 8202231946#26_[CR] Perbaikan Pompa Jocke | RU4-RFCUTL | 155P502B/00 | 60 | CLSD CNF CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 6 | 61200000 | MA5-ROT |  | TONNYADI | 2026-06-02 | 2026-02-07 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-26 | 2026-01-26 | 2102354204 | 8202235380 |  | 8202231945#Perbaikan 91E409B2-LIST MA1 | RU4-SRU | 91E409B2M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-26 | 2026-01-26 | 2102354202 | 8202235382 |  | 8202231944#Perbaikan 91E404B-LIST MA1 | RU4-SRU | 91E404BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-01-26 | 2026-01-30 | 2102360319 | 8202235850 |  | 8202231943#PERB.LINE 26-6" SLOP DI JALAN | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-26 | PM |  | 003
| K501 | 2026-02-03 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2102358766 | 8202237997 |  | 8202231942#Sewa Tanki Air (13) | RU5-E15112 | E-3-01J/00 | 50 | REL GMPS NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 39160000 | WS-KAB |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-29 | 2026-06-29 | 2102358943 | 8202235842 |  | 8202231941#Perbaikan MOTOR GM-32-06 | RU5-E15112 | PLANT-2-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 4057800 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-26 | 2026-01-26 | 2102358779 | 8202235854 |  | 8202231940#Perb. P13 A Hitam ADO Loading | RU5-TBL | P-13RP-A-HITAM/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-26 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-16 | 2026-01-27 | 2026-01-27 | 2102357096 | 8202235424 |  | 8202231939#85E206 Perbaikan Indikasi Boc | RU4-KPC | 85E206/00 | 50 | REL CSER MANC PRC SETC | 4MT | D14/26/B6/RT-10-C2H | 184027721 | 0 | MA4-STA |  | MRIZKYB |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 045
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102355415 | 8202238599 |  | 8202231937#26_81TI103 dan 81TI104 rusak | RU4-KPC | 81A201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 045
| K401 | 2026-02-05 | 2026-03-02 | 2026-01-26 | 2026-01-26 | 2102357606 | 8202238600 |  | 8202231936#26_011F-101A, buakan tidak se | RU4-FOC2 | 011F101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 1 | 0 | MA2-INT |  | YOHANESMVIS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102356895 | 8202238592 |  | 8202231933#26_Perbaikan DP Transmitter 1 | RU4-FOC1 | 14FT534/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-27 | 2026-01-27 | 2102356891 | 8202235433 |  | 8202231931#26_Perbaikan Positioner 14HV2 | RU4-FOC1 | 14HV205/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-02 | 2026-03-02 | 2102351442 | 8202232699 |  | 8202231929#Perbaikan 520-PM-607A | RU2-UTL | 520-P-607A/00 | 60 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-28 | 2026-01-28 | 2102358319 | 8202238603 |  | 8202231928#26_[CR] Overload Trip 88P213 | RU4-KPC | 88P213/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-10-02 | 2026-11-27 | 2102359080 | 8202235857 |  | 8202231927#PENGADAAN SPARE PART CEMS HSC | RU5-E15500 | CEMS-SYSTEM-INT/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 932228651 | 0 | MA2-INT |  | NIASIANS |  | 2026-06-02 | PT02 |  | 3 | 2026-10-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-03-28 | 2026-01-02 | 2026-01-02 | 2102358136 | 8202234941 |  | 8202231926#Material Rutin Januari 2026 |  |  | 60 | CLSD CSER GMPS MACM PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 99029427 | 14470000 | MA-LINT |  | RYANMANGGASA |  | 2026-02-07 | PT02 |  | 3 | 2026-03-28 | PM |  | 005
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-26 | 2026-01-26 | 2102356722 | 8202238601 |  | 8202231925#26_[CR]166M575, penggantian g | RU4-RFCUTL | 166M559/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-02 | 2026-03-02 | 2102351789 | 8202232695 |  | 8202231924#Perbaikan 940-CM-55 AJ | RU2-UTL | 940-EM-55AJ/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 2485000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-02-03 | 2026-04-23 | 2026-02-24 | 2026-04-28 | 2102359148 | 8202237996 |  | 8202231923#Pek. Radiografi Test (2) | RU5-E15112 | C-2-01/00 | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 14501000 | 14501000 | ENG-STA |  | HIMMATUSS |  | 2026-02-24 | PT02 |  | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-01-26 | 2026-01-26 | 2102355110 | 8202235394 |  | 8202231921#isolasi rutin ME-I (untuk 86C | RU4-KPC | 86C202/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 220110353 | 43784743 | MA4-STA |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-26 | 2026-02-25 | 2102362539 | 8202232156 |  | 8202231920#Penggantian Transmitter 32-PT | RU6-HSC | 32-F-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102358771 | 8202235843 |  | 8202231919#Perbaikan Motor EAM-201-01A | RU5-D&W | EAM-201-01A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 1097514 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 005
| K501 | 2026-02-05 | 2026-03-12 | 2026-10-01 | 2026-12-31 |  | 8202238615 | 8302407492 | 8202231918#PengadaanKabel reroute beban | RU5-UTL | 41-R-SS-48-LIS/00 | 60 | CLSD CSER MACM PRC SETC | 5ER | D15/26/B6/NR-C3H | 300 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-07 | PT02 |  | 3 | 2026-03-12 | PM |  | 001
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2102359280 | 8202235862 |  | 8202231917#GANTI BLOCK VALVE 12" TANK C- | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 78619178 | 0 | MA4-STA |  | BERNANDOP |  | 2026-03-03 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-06-23 | 2026-06-23 | 2102359085 | 8202235741 |  | 8202231916#POMPA G-1-19B FASILITAS ACW D | RU5-E15111 | G-1-19B/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-06-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-26 | 2026-02-26 | 2102359017 | 8202235780 |  | 8202231915#BOCORAN STEAM AREA TURBIN K-5 | RU5-E15111 | KT-5-02B/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-13 | 2026-02-07 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-26 | 2026-02-26 | 2102359011 | 8202235773 |  | 8202231914#KOMPRESSOR K-5-02C PERBAIKAN | RU5-E15111 | K-5-02C/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-13 | 2026-02-07 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-26 | 2026-02-26 | 2102358947 | 8202235740 |  | 8202231913#POMPA G-5-16A MEMBRANE COUPLI | RU5-E15111 | G-5-16A/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-13 | 2026-02-07 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-19 | 2026-04-01 | 2026-09-02 | 2102364386 | 8202235766 |  | 8202231912#NRK_Perbaikan FO Sirine Syste | RU5-E15500 | PP1-SS-001/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 70000000 | 0 | MA1-INT |  | HIMMATUSS |  | 2026-06-19 | PT02 |  | 3 | 2026-04-01 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-26 | 2026-02-26 | 2102359012 | 8202235776 |  | 8202231911#K-8-01A Bearing Defect | RU5-E15112 | K-8-01A/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-24 | 2102359016 | 8202235756 |  | 8202231910#PENGGANTIAN 1 SET PROBE K-5-0 | RU5-E15111 | K-5-01/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 46392650 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 004
| K501 | 2026-02-02 |  | 2026-01-26 | 2026-01-30 | 2102360819 | 8202235738 |  | 8202231909#PERB.LINE 4" RFO TO D&W DPN R | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102359143 | 8202235717 |  | 8202231908#Perbaikan Motor GM-3-37B | RU5-E15112 | GM-3-37B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 370857 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-10 | 2026-07-30 | 2026-07-30 | 2102359142 | 8202235736 |  | 8202231907#Perbaikan Motor GM-3-30B | HCC-UP5 | GM-3-30B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 370857 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-07-30 | PM |  | 004
| K501 | 2026-02-02 | 2026-03-05 | 2026-05-25 | 2026-05-25 | 2102359087 | 8202235653 |  | 8202231906#POMPA G-201-13B MECH SEAL BOC | RU5-D&W | G-201-13B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 8270000 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-03-05 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-03 | 2026-05-25 | 2026-05-25 | 2102359086 | 8202235656 |  | 8202231905#POMPA G-201-13A TEMP BEARING | RU5-D&W | G-201-13A/00 | 60 | CLSD CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-30 | 2026-01-30 | 2102351685 | 8202232703 |  | 8202231904#PERBAIKAN 140-PC-51-4-M-14 Ga | RU2-HOC | 140-PC-51/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352097 | 8202232458 |  | 8202231903#Service 110 CM-52A | RU2-HOC | 110-CM-52A/00 | 60 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-23 | 2026-01-23 | 2102359141 | 8202235651 |  | 8202231902#POMPA G-7-06 KONDISI MECHSEAL | RU5-E15111 | G-7-06/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/10/B6/RT1-07NH | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-23 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-06-15 | 2026-06-15 | 2102360267 | 8202235714 |  | 8202231901#FDF motor HHP B2 vibrasi ting |  |  | 01 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-18 | 2026-02-18 | 2102351255 | 8202238484 |  | 8202231900#PERBAIKAN RUAS JALAN XIV DAN | RU2-PK | 970-HYD-XIV-01/00 | 50 | CRTD NMAT PRC SETC | 2MR | D12/26/B6/NR-D2H | 299688000 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-18 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-25 | 2026-03-25 | 2102352132 | 8202232710 |  | 8202231899#Penggantian Control Valve 702 | RU2-HCC | 702-LV-189/00 | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-21 | 2026-06-19 | 2026-12-30 | 2102356978 | 8202241286 |  | 8202231898#25_[CR] Perbaikan Desup Pump | RU4-UTL | 052P102A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 49268550 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-06-19 | PM |  | 003
| K501 | 2026-02-03 | 2026-02-07 | 2026-01-23 | 2026-12-30 | 2102359019 | 8202237995 |  | 8202231897#Tagihan 3 Pengelasan di Works |  |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 124117000 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-23 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-11 | 2026-01-23 | 2026-12-30 | 2102359018 | 8202237994 |  | 8202231896#Tagihan 2 Pengelasan di Works |  |  | 60 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 0 | 108685000 | WS-LAS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-23 | PM |  | 045
| K501 | 2026-02-05 | 2026-02-26 | 2026-01-21 | 2026-12-30 | 2102359520 | 8202238610 |  | 8202231895#Perbaikan E-201-21 | RU5-D&W | E-201-21/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 402875321 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-24 | 2102359225 | 8202235680 |  | 8202231894#PERBAIKAN PRESSURE TRANSMITTE | RU5-E15111 | 04-PT-099/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 9881699 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360476 | 8202235684 |  | 8202231893#Perbaikan kabel incoming pane | RU5-UTL | 1NV00DOO1-S1/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 82800000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-24 | 2102359224 | 8202235687 |  | 8202231892#PERBAIKAN FLOW TRANSMITTER 04 | RU5-E15111 | 04-FT-043A/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/26/B6/RT-C2H | 11786000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 004
| K501 | 2026-02-03 | 2026-05-06 | 2026-12-01 | 2026-12-01 |  | 8202237993 | 8202237123 | 8202231891#3d Scan Impeller Blower FDF T |  |  | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 15000000 | 0 | ENG-ROT |  | FAUZANR |  | 2026-05-06 | PT02 |  | 3 | 2026-12-01 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-06-19 | 2026-06-19 | 2102359656 | 8202235690 |  | 8202231890#G-202-06A (impeller,casing,st | RU5-D&W | G-202-06A/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-06-19 | PM |  | 003
| K501 | 2026-02-04 | 2026-05-08 | 2026-01-22 | 2026-01-22 | 2102359355 | 8202238483 |  | 8202231889#NRK_Fabrikasi CounterweightK- | RU5-E15112 | K-3-02A/00 | 60 | TECO NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 89000000 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-07 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-03-25 | 2026-03-25 | 2102359357 | 8202235646 |  | 8202231888#Filter TM25 STG 1.6 PP1 | RU5-UTL | TG-6-OIL-FLTR/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-03-25 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-22 | 2026-06-12 | 2102359228 | 8202235639 |  | 8202231887#Perb. Bordes & handrail Rp A | RU5-TBL | KAN-ITP/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-22 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102356060 | 8202236032 |  | 8202231886#Perbaikan Flow Valve 37FV0 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102354866 | 8202235427 |  | 8202231885#26_Transmitter Rusak 140LT016 | RU4-GTO | 140LT016/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 2 | 0 | MA7-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-26 | 2026-02-19 | 2026-08-27 | 2102357867 | 8202237348 |  | 8202231884#84PT228,84PSH228 error | RU4-KPC | 84K201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-26 | PT02 |  | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102357829 | 8202235435 |  | 8202231883#26_Perbaikan PG Sealing Air 1 | RU4-RFCC | 101K501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102357413 | 8202235207 |  | 8202231881#PI di 84P203B rusak | RU4-KPC | 84P203B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1203449 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102357411 | 8202235209 |  | 8202231880#PI di 84P203A rusak | RU4-KPC | 84P203A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1203449 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-08 | 2026-04-07 | 2026-10-19 | 2102357114 | 8202235959 |  | 8202231879#Perbaikan komunikasi 47A502 d | RU4-RFCGTO | 47MP012/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 4 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 |  | 3 | 2026-04-07 | PM |  | 045
| K401 | 2026-02-02 |  | 2026-01-09 | 2026-01-09 | 2102355441 | 8202234862 |  | 8202231878#Tagihan TSA GC Yokogawa perio |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-01-09 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-06 | 2026-03-05 | 2026-09-29 | 2102357828 | 8202235397 |  | 8202231877#Perbaikan TG CWR 101E525CD | RU4-RFCC | 101E525C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 2 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-19 | 2026-01-12 | 2026-12-30 | 2102357554 | 8202234903 |  | 8202231876#TGH26-30_23 TSA 11 Unit GC KP | RU4-KPC | DCS-KPC/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 388364000 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-04-13 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102357685 | 8202236444 |  | 8202231875#Penggantian TG line flush | RU4-RFCC | 101P523C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-26 | 2026-02-19 | 2026-08-27 | 2102357684 | 8202235437 |  | 8202231874#Perbaikan Sensor Thermocouple | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-02-26 | PT02 |  | 3 | 2026-02-19 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-24 | 2026-01-22 | 2026-01-22 | 2102353163 | 8202234407 |  | 8202231873#NR26-Pompa 2 RPM Ovak Bising | RU3-ITP | ITP-RPO-P-002/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2026-01-29 | 2026-01-29 | 2102356634 | 8202235205 |  | 8202231872#26_PI purging N2 di 84V206 ru | RU4-KPC | 84V206/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 6770960 | 6770960 | MA4-INT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102354521 | 8202236231 |  | 8202231871#TI cooler 84V230P1B rusak | RU4-KPC | 84V230P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102354489 | 8202236233 |  | 8202231870#TI cooler 84V230P1A rusak | RU4-KPC | 84V230P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102354487 | 8202236234 |  | 8202231869#TI cooler 84P207A rusak mo | RU4-KPC | 84P207A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 |  | 2026-01-13 | 2026-01-13 | 2102356281 | 8202237362 |  | 8202231865#81KV441, 81KV442,81KV443 rusa |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RT1-801-S0NH | 0 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-01-13 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102355816 | 8202237018 |  | 8202231864#PENGGANTIAN 151TG641 Aux.B | RU4-RFCUTL | 151TT-U151/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-10 | 2026-01-13 | 2026-01-13 | 2102356532 | 8202235013 |  | 8202231863#Positioner 107FT007 Rusak | RU4-RFCC | 107FT007/00 | 50 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-26 | 2026-02-19 | 2026-08-27 | 2102356226 | 8202235009 |  | 8202231862#Positioner 108PV643 Rusak | RU4-RFCC | 108PT003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 3 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-02-26 | PT02 |  | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102355981 | 8202235386 |  | 8202231861#26_Perbaikan Transmitter 107F | RU4-RFCGTO | 107FT-U107/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 21060000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-18 | 2026-02-10 | 2026-08-27 | 2102355299 | 8202236468 |  | 8202231860#Penggantian Temp Indikator | RU4-TRML | 38T104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1513000 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-10 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102352364 | 8202234295 |  | 8202231859#Re Notif : LTSA Therm Ins dan | RU2S-KIL | 8PL101039-A1A1/00 | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/26/B6/RTZ-D3H | 750000000 | 579500000 | MAS-ME1 |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102357983 | 8202235400 |  | 8202231858#26_Perbaikan TG Casing 101P52 | RU4-RFCC | 101P523A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 2387143 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102357036 | 8202235393 |  | 8202231857#26_Perbaikan TG Flushing Oil | RU4-RFCC | 101P523A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 3100000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-29 | 2026-01-29 | 2102355673 | 8202235470 |  | 8202231856#26_Perbaikan 93TI181-INST MA1 | RU4-SRU | 93TIT181/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K501 | 2026-02-03 | 2026-02-14 | 2026-02-02 | 2026-07-17 |  | 8202238001 |  | 8202231854#PERB.LINE PEMADAM TANK&LINE C | RU5-TBL | PIPE-ON-SHORE/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 3995000000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-23 | 2026-01-29 | 2026-01-29 | 2102357608 | 8202235620 |  | 8202231853#26_011FT-003AB & FT-004AB dev | RU4-FOC2 | 011FT003/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 58451768 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-11-30 | 2102354776 | 8202236229 |  | 8202231852#tinta print DCS FOC II habis | RU4-FOC2 | DCS-FOC2/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-04 | 2026-01-20 | 2026-12-30 | 2102356970 | 8202235058 |  | 8202231851#TGH6_24 PM Field Instr ME II | RU4-RFCGTO | 105FT072/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 228628750 | 228628750 | MA6-INT |  | SAMSUDINH |  | 2026-03-04 | PT02 | 3 | 3 | 2026-01-20 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-20 | 2026-01-20 | 2102356914 | 8202235034 |  | 8202231850#Tagihan Pek. TSA DCS RFCC Com | RU4-REL |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-20 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-22 | 2026-07-01 | 2102362324 | 8202232775 |  | 8202231849#PM Junction Box Area RCC | RU6-RCC | 15-JE-001/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 3458835 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-14 | 2026-01-14 | 2102355817 | 8202237949 |  | 8202231848#TGH7_24 TSA LIGHTNING PROT SY | RU4-TRML | 30EE101A-50GS/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 0 | 587745000 | MA3-LIS |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-15 | 2026-01-15 | 2102355726 | 8202237948 |  | 8202231847#TGH10_25 UP MON&INSP PERALATN | RU4-RFCUTL | 150EE0040A1Z/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 0 | 121904996 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-06 | 2026-01-06 | 2102357232 | 8202237947 |  | 8202231846#TGH11_23 KONTRAK U/P OVERHAUL | RU4-UTL | 54P1BP1M/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-15-C2H | 767900000 | 767900000 | WS-LIS |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-02 | 2026-01-05 | 2026-12-30 | 2102357822 | 8202236278 |  | 8202231845#TGH34-36_22 PSA TRANSFORMATOR | RU4-TRML | 30EE0012A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 799683000 | 0 | MA3-LIS |  | WAHYUCATUR |  | 2026-03-02 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-22 | 2026-01-22 | 2102357864 | 8202235829 |  | 8202231844#Perbaikan motor 11P3 | RU4-FOC1 | 11P3/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-22 | 2026-02-24 | 2102362008 | 8202233005 |  | 8202231843#Perbaikan pompa | RU6-ITP | 42-P-501C/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2904 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-22 | 2026-01-22 | 2102354919 | 8202236925 |  | 8202231842#Penggantian bearing motor 12P | RU4-FOC1 | 12P2/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-22 | 2026-01-22 | 2102354865 | 8202235831 |  | 8202231841#Perbaikan Motor 11E57HM | RU4-FOC1 | 11E57HM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 045
| K601 | 2026-02-06 |  | 2026-01-22 | 2026-12-30 | 2102362327 | 8202238692 |  | 8202231840#pek perbaikan penurunan tanah | RU6-HSC | 33-A-104/00 | 50 | CRTD CSER NMAT PRC | 6MR | D16/26/B6/RT-C2H | 20000000 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-01-22 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-08 | 2026-01-08 | 2102354863 | 8202235833 |  | 8202231839#Perbaikan Motor 11E50TM | RU4-FOC1 | 11E50TM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-26 | 2026-06-04 | 2102362363 | 8202232144 |  | 8202231838#LTSA General Purpose Line Dra | RU6-ITP | 42-OS-906/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 165638000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-22 | 2026-02-11 | 2102362445 | 8202233512 |  | 8202231837#Penggantian safety barrier 58 | RU6-UTL | 58-K-101C/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 1980 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-22 | 2026-01-22 | 2102354868 | 8202235761 |  | 8202231836#Perbaikan motor CPI 20P2M | RU4-LOC1 | 20P2M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 045
| K401 | 2026-02-03 | 2026-05-19 | 2026-01-22 | 2026-01-22 | 2102356082 | 8202237946 |  | 8202231835#Penggantian Kabel Tray CIB I | RU4-TRML | 70BD1IU1/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 100000 | 0 | MA3-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-01-22 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-27 | 2026-02-27 | 2026-04-02 | 2102362718 | 8202237992 |  | 8202231834#LTSA PM O2 ANALYZER (1) | RU5-E15112 | 02-AIT-169A/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 287453000 | 0 | WS-INT |  | RIANDAADI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K601 | 2026-02-01 | 2026-03-10 | 2026-01-22 | 2026-03-10 | 2102362366 | 8202233036 |  | 8202231833#Perbaikan Motor 33-E-118 K1 | RU6-HSC | 33-E-118K1-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1426841 | 563958 | MA3-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-25 | 2026-01-02 | 2026-01-02 | 2102353274 | 8202234416 |  | 8202231832#NR26-Perbaikan motor P-3 A SW | RU3-CDL | SWS-PM-63-003A/00 | 60 | REL CSER GMPS MANC PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 45970075 | 45970075 | MA3-LIS |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-26 | 2026-01-27 | 2026-01-27 | 2102355322 | 8202237944 |  | 8202231831#[TGH] Kontrak PM Rotating Eqp |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 492700000 | 492700000 | MA2-ROT |  | AGHANIAKBAR |  | 2026-02-11 | PT02 |  | 3 | 2026-01-27 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-22 | 2026-01-22 | 2102362049 | 8202233911 |  | 8202231829#Matrial Perbaikan UNit 42 & 6 | RU6-ITP | 63-Z-202B/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C1H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K501 | 2026-02-03 | 2026-06-17 | 2026-03-30 | 2026-03-30 | 2102359226 | 8202237991 |  | 8202231828#NRK_Metalizing Motor GM-4-02 | RU5-E15111 | GM-4-02/00 | 50 | REL NMAT PRC SETC | 5ER | D15/26/B6/NR-C3H | 10341000 | 0 | WS-LIS |  | MANKURNIAWAN |  | 2026-02-07 | PT02 |  | 3 | 2026-03-30 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-07 | 2026-01-02 | 2026-01-02 |  | 8202237943 | 8202237727 | 8202231827#TGH28_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 280775000 | 280775000 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-03 | 2026-06-11 | 2026-06-11 | 2026-07-01 | 2102362770 | 8202237990 |  | 8202231826#LTSA PM ATG OM LAWE DHP (4) | RU5-D&W | 13-LT-D20-07A/00 | 50 | REL GMPS NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 0 | 442673000 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-06-23 | 2102360364 | 8202235637 |  | 8202231825#Perbaikan XCV 12" Tangki C-20 | RU5-TBL | C-20-01A/00 | 50 | REL CSER NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-04 | 2026-02-21 | 2026-12-30 | 2026-12-30 |  | 8202238495 | 8202235356 | 8202231824#NRK_Perbaikan Cylinder 5 K-3- | RU5-E15112 | K-3-02A/00 | 50 | REL GMPS NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 79000000 | 79000000 | MA3-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-14 | 2026-01-20 | 2026-01-20 | 2102359522 | 8202235592 |  | 8202231823#Perbaikan Pompa G-2-03C | RU5-E15112 | G-2-03C/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3462794 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-07 | PT02 |  | 3 | 2026-04-14 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-22 | 2026-01-22 | 2102351616 | 8202232476 |  | 8202231822#Packing Cylinder Bocor | RU2-HCC | 211-P-6AR/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-12 | 2026-01-12 | 2102351216 | 8202232539 |  | 8202231821#Mechseal bocor | RU2-HCC | 701-P-3A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 453119 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-21 | 2026-01-21 | 2102356223 | 8202238588 |  | 8202231820#Measuring Tools Electrical Wo | RU4-WS | 037BD101-6795Z2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-15-C2H | 135 | 0 | WS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K501 | 2026-02-03 | 2026-06-11 | 2026-06-11 | 2026-07-01 |  | 8202237989 |  | 8202231819#TSA PM AUTOMATIC BACKWASH PLA | RU5-E15112 | V-3-01B/01 | 50 | REL GMPS NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 0 | 320462000 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-20 | 2026-03-04 | 2102362098 | 8202234104 |  | 8202231818#11-P-119 B. | RU6-HSC | 11-P-119B/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-21 | 2026-01-21 | 2102352163 | 8202232572 |  | 8202231817#Penggantian Cooler | RU2-HSC | 300-P-3B/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-21 | 2026-06-30 | 2102363455 | 8202233559 |  | 8202231816#Penggantian PI Rusak di Unit | RU6-HSC | 11-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-13 | 2026-01-13 | 2102356288 | 8202237941 |  | 8202231815#monitoring dan inspeksi motor | RU4-LOC1 | 21P11M/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-15-C2H | 0 | 72200000 | WS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-13 | 2026-01-13 | 2102357647 | 8202237940 |  | 8202231814#Kontrak inspeksi motor LOC 2 | RU4-LOC2 | 021P102A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-15-C2H | 0 | 119000000 | WS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-29 | 2026-12-29 | 2102360478 | 8202235600 |  | 8202231813#MCC DRAWER POWER DC CHARGER S | RU5-UTL | 41-R-SS-73-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 3250002 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-29 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-01-20 | 2026-01-26 | 2102359535 | 8202235618 |  | 8202231811#GANTI BALL VALVE 16IN-150LB D | RU5-TBL | PIPE-ON-SHORE/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-20 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-21 | 2026-01-21 | 2102360198 | 8202235593 |  | 8202231810#PERB.LINE 21-P-173-6" REFORM | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-21 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-21 | 2026-01-21 | 2102357504 | 8202238589 |  | 8202231809#85F201 tip burner fuel oil ru | RU4-KPC | 85F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-20 | 2026-02-09 | 2102361460 | 8202233713 |  | 8202231808#Penggantian Air filter 059-A- | RU6-UTL | 059-A-101B-K1/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 1980 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-21 | 2026-05-07 | 2102361611 | 8202238578 |  | 8202231807#Penggantian Flow Control Valv | RU6-HSC | 11-P-132A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-21 | 2026-02-03 | 2102362137 | 8202233174 |  | 8202231806#Perbaikan Fin Fan 15-E-110AE | RU6-RCC | 15-E-110AE/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 12165500 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-21 | 2026-06-15 |  | 8202236705 | 8202233880 | 8202231805#SPK Thp 4 52-B-101F | RU6-UTL | 52-B-101A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 786580000 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-21 | 2026-06-15 |  | 8202236707 | 8202233880 | 8202231804#SPK Thp 3 52-B-101E | RU6-UTL | 52-B-101A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 266194500 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-21 | 2026-06-15 |  | 8202236709 | 8202233880 | 8202231803#SPK Thp 1 052-B-101A | RU6-UTL | 52-B-101A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 332350000 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-11 | 2026-01-21 | 2026-01-21 | 2102362176 | 8202233880 |  | 8202231802#pekerjaan LTSA Refractory Boi | RU6-UTL | 52-B-101A/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-11 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-21 | 2026-01-21 | 2102361288 | 8202232740 |  | 8202231801#Short Bolting All Area UTL | RU6-UTL | 52-B-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-20 | 2026-01-20 | 2102357808 | 8202237939 |  | 8202231798#TGH TKDN_25 UP PIPA UTL RFCC | RU4-UTL | LN54-1004N/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 045
| K501 | 2026-02-03 | 2026-03-09 | 2026-12-01 | 2026-12-31 | 2102359580 | 8202237988 |  | 8202231797#ConMon&Perbaikan MOV (T1) | RU5-TBL | PLANT-21-LIS/00 | 60 | CLSD NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 103679000 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-07 | PT02 | 8 | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-03 | 2026-03-03 | 2026-12-01 | 2026-12-30 | 2102359538 | 8202237987 |  | 8202231796#Perb Grounding Bonding (T6) | RU5-TBL | PLANT-20-LIS/00 | 60 | REL GMPS NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 164708000 | 164708000 | MA4-LIS |  | BERNANDOP |  | 2026-02-07 | PT02 | 8 | 3 | 2026-12-01 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-19 | 2026-10-21 | 2102362047 | 8202236825 |  | 8202231795#PM Grounding & Lightning Syst | RU6-POC | GROUNDSYS-39/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-24 | 2026-01-09 | 2026-08-18 | 2102361541 | 8202237794 |  | 8202231794#LTSA Cleaning Open Sewer Thp | RU6-UTL | 055-A-101-P4B/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 565000000 | MA4-STA |  | DANDARWANI |  | 2026-02-11 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-21 | 2026-06-22 | 2102361615 | 8202238584 |  | 8202231793#11-P-132B | RU6-HSC | 11-P-132B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-20 | 2026-01-20 | 2102356405 | 8202241285 |  | 8202231792#26_Mtl. Oil Gun Assembly 021F | RU4-LOC2 | 021F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-20 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-11 | 2026-01-19 | 2026-03-30 | 2102359705 | 8202237986 |  | 8202231791#UR. Perbaikan Bak Sump OM (1) | RU5-TBL | OFC03401/00 | 60 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 0 | 130583000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 045
| K401 | 2026-02-03 | 2026-03-04 | 2026-02-02 | 2026-12-30 |  | 8202237937 |  | 8202231790#TGH 7-8_24 Jasa LTSA Fire Tru | RU4-WS | FL51/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 39763266 | 33798776 | WS-KAB |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-13 | 2026-01-20 | 2026-01-20 | 2102358137 | 8202234914 |  | 8202231789#PERBAIKAN POMPA INLET 1-EA-01 | RU7-CDU | 1-EA-01A/00 | 50 | CRTD CSER MACM PRC | 7RT |  | 0 | 0 | MA-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-20 | PM |  | 005
| K501 | 2026-02-02 |  | 2026-01-19 | 2026-01-19 | 2102359659 | 8202235564 |  | 8202231788#Perbaikan Pompa G-3-45B | RU5-E15112 | G-3-45B/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-01-20 | 2026-05-26 | 2102361657 | 8202236573 |  | 8202231787#Tgh thp 1 TKDN 15% LTSA COC 2 | RU6-DHC | 22-R-102A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 27337500 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-20 | 2026-05-26 | 2102362282 | 8202232820 |  | 8202231786#Perbaikan Valve Unit Polisher | RU6-DHC | 22-V-105B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-19 | 2026-01-19 | 2102359740 | 8202235578 |  | 8202231785#GANTI VALE LINE 890-10" INLET | RU5-TBL | R-4/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-14 | 2026-05-05 | 2102361715 | 8202232903 |  | 8202231784#Perbaikan Purging N2 di 15-LT | RU6-RCC | 15-LT-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-20 | 2026-11-20 | 2102362170 | 8202238580 |  | 8202231783#Pengadaan motor 056-K-101-A1 | RU6-UTL | 056-K-101-A1-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 26664 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-11 | 2026-01-20 | 2026-01-20 |  | 8202233967 | 8202233889 | 8202231782#LTSA Tabel Volume Tangki Taha | RU6-ITP | 42-T-101B/00 | 01 | CLSD NCMP NMAT PRC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-06-11 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-19 | 2026-06-29 |  | 8202237792 | 8202233429 | 8202231781#Penyelesaian PMPDM Elect&Inst | RU6-POC | 18-PSW2-01-001/00 | 60 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 70996000 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-01-19 | 2026-11-17 | 2102362041 | 8202233429 |  | 8202231780#Penyelesaian PMPDM EI MA3 Th | RU6-POC | 18-PSW2-01-001/00 | 01 | CRTD CSER GMCO NMAT PRC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA3-LIS |  |  |  |  | PT02 |  | 2 | 2026-01-19 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-20 | 2026-01-20 | 2102351493 | 8202232447 |  | 8202231779#Perbaikan 905 DEG 01 | RU2-UTL | 905-DEG-E01/00 | 60 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-20 | 2026-05-08 | 2102362610 | 8202232821 |  | 8202231778#Perbaikan Valve Unit Polisher | RU6-DHC | 22-V-105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-11 | 2026-01-20 | 2026-01-20 | 2102362134 | 8202233889 |  | 8202231775#Notifikasi Sertifikasi Tabel | RU6-ITP | 42-T-101B/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-11 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-09 | 2026-01-20 | 2026-07-28 | 2102361998 | 8202238494 |  | 8202231773#REPAIR LINIER INDICATION 42-T | RU6-ITP | 42-T-404H/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 185000000 | 0 | MA4-STA |  | MARSHAL |  | 2026-03-10 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K201 | 2026-02-01 | 2026-03-10 | 2026-01-20 | 2026-01-20 | 2102352139 | 8202232299 |  | 8202231770#410-TAH 543 Rusak | RU2-HCC | 410-TSHH-543B/00 | 50 | REL CSER MSPT PRC SETC | 2MR | D12/26/B6/NR-D2H | 0 | 0 | MA2-STA |  | DONITGN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K201 | 2026-02-01 | 2026-06-18 | 2026-01-20 | 2026-01-20 | 2102351684 | 8202232407 |  | 8202231765#Conmon High Vibrasi 102-P-4A | RU2-HSC | 102-P-4A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 52211422 | 0 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-20 | 2026-04-23 | 2102361289 | 8202233790 |  | 8202231764#Pengadaan Material MOC 735/HS | RU6-HSC | 11-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-19 | 2026-01-30 | 2102362092 | 8202233933 |  | 8202231763#Material Make Up Rocksalt 14- | RU6-DHC | 14-V-108/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-20 | 2026-01-20 | 2102355455 | 8202236061 |  | 8202231762#Isolasi Roof Tank 47T573 Rusa | RU4-RFCGTO | 47T573/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-20 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | 8202235547 | 8202238855 | 8202231760#MATERIAL PIPING PLANT HVU2&HP | RU5-E15112 | 2-SPW05-3-B6/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 39667114 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-27 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-19 | 2026-01-19 | 2102356077 | 8202235742 |  | 8202231758#Noise dan vibrasi pada motor | RU4-LOC3 | 240P102BM/00 | 50 WAMA | CRTD CSER MACM PRC | 4ER |  | 4193579 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-19 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-19 | 2026-01-19 | 2102354765 | 8202235308 |  | 8202231757#perbaikan valve DBB line ball | RU4-TRML | 70JT1/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-09 | 2026-01-09 | 2102355550 | 8202241284 |  | 8202231756#26_perbaikan fan & lampu cabi | RU4-FOC1 | 10CSL1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 6 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360043 | 8202235541 |  | 8202231755#Perbaikan motor BFW Pump 11 | RU5-UTL | 1NV00DOO1-S1/00 | 50 | REL CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 005
| K401 | 2026-02-02 | 2026-06-17 | 2026-01-19 | 2026-01-19 | 2102353318 | 8202234818 |  | 8202231753#RK_26-RT PERPIPAAN & AKSESORI |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | AKHMADRIZAL |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 045
| K201 | 2026-02-01 | 2026-05-19 | 2026-01-19 | 2026-01-19 | 2102350956 | 8202232351 |  | 8202231752#211-PM 15B Vibrasi Tinggi | RU2-HCC | 211-P-15B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 48784 | 48784 | MA2-ROT |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-19 | 2026-01-19 | 2102350958 | 8202232316 |  | 8202231751#212-PT-14B Governor Rusak | RU2-HCC | 212-PT-14B/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-01-19 | 2026-03-03 | 2102361653 | 8202234037 |  | 8202231750#Cleaning 11-V-101 B | RU6-HSC | 11-V-101B/00 | 50 | REL CSER GMCO MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-19 | 2026-01-19 | 2102350959 | 8202232624 |  | 8202231749#Perbaikan part 925-P-5C | RU2-UTL | 925-PT-5C/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-19 | 2026-01-19 | 2102352390 | 8202234293 |  | 8202231747#Kerusakan Pompa 101-P6-A | RU2S-KIL | 101-P-6A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-02-02 | 2026-04-08 | 1102327771 | 8202238607 |  | 8202231746#Perbaikan PI Area RP, WTP, Je | RU5-TBL | 22-716B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 13217008 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-13 | 2026-01-19 | 2026-06-11 |  | 8202236566 | 8202238452 | 8202231745#Thp 4 LTSA Sevice&Fire Water | RU6-UTL | 54SW0103MS0124N/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 36079500 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-16 | 2026-01-19 | 2026-01-19 | 2102355695 | 8202235221 |  | 8202231744#permintaan filter catridge 85 | RU4-KPC | 85S201/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 100660288 | 74042286 | MA4-STA |  | FAJRIINDRAK |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-19 | 2026-04-14 |  | 8202238572 | 8202238583 | 8202231743#Perbaikan Control Valve 61-FV | RU6-POC | 61-P-303A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-19 | 2026-01-19 | 2102351559 | 8202232567 |  | 8202231742#Perbaikan Turbine 110-PT-3B | RU2-HOC | 110-PT-3B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 188791 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-19 | 2026-01-19 | 2102355300 | 8202241283 |  | 8202231741#26_Pengadaan Gasket LO Sirkul | RU4-UTL | 510G301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 740692 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-09 | 2026-01-15 | 2026-03-05 | 2102361807 | 8202232855 |  | 8202231740#Perbaikan Trafo desalter 11-V | RU6-HSC | 11-V-101B/00 | 60 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 51530344 | 35605000 | MA1-LIS |  | DINDINS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-15 | 2026-03-05 | 2102361428 | 8202232856 |  | 8202231739#Perbaikan Trafo desalter 11-V | RU6-HSC | 11-V-101A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 35826830 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-19 | 2026-01-19 | 2102355932 | 8202236225 |  | 8202231738#filter condom dust collector | RU4-KPC | 84S252/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-30 | 2026-04-07 | 1102327818 | 8202235540 |  | 8202231737#Perbaikan Prover Meter Bunker | RU5-TBL | PROVER-7851/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 8091946 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-01 | 2026-01-07 | 2026-04-13 | 2102361329 | 8202233306 |  | 8202231735#Perbaikan 22-K-101B | RU6-DHC | 22-K-101B/00 | 50 WAMA | CRTD CSER MACM PRC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | KHAERUDIN |  |  | PT02 |  | 2 | 2026-01-07 | PM |  | 003
| K201 | 2026-02-01 | 2026-06-18 | 2026-01-19 | 2026-01-19 | 2102351496 | 8202232318 |  | 8202231734#Perbaikan Governor Drive Turb | RU2-HSC | 200-CT-1A/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RR | D12/26/B6/RT-D2H | 34944074 | 34944074 | MA2-ROT |  | NURFADHILLA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-19 | 2026-06-11 |  | 8202236615 | 8202237898 | 8202231733#SWO SBNP Thp 11 | RU6-ITP | 43-SPM-01/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-05-26 |  | 8202236616 | 8202237898 | 8202231732#SWO SBNP Thp 10 | RU6-ITP | 43-SPM-01/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K501 | 2026-02-03 | 2026-03-03 | 2026-12-01 | 2026-12-31 | 2102360261 | 8202237985 |  | 8202231731#Perbaikan Kabel Tray EI Area | RU5-TBL | PLANT-21-LIS/00 | 60 | CLSD NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 67256000 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-02-03 | 2026-03-03 | 2026-12-01 | 2026-12-31 | 2102360263 | 8202237984 |  | 8202231730#Perbaikan Kabel Tray EI Area | RU5-TBL | PLANT-21-LIS/00 | 60 | CLSD NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 223716000 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-01-19 | 2026-06-26 |  | 8202236568 | 8202236813 | 8202231729#Thp 2 PM Mekanik MA 3 | RU6-HSC | 32-R-102/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 65536000 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-19 | 2026-06-29 | 2102361429 | 8202237790 |  | 8202231728#LTSA Prbkan 15-P-101 Body F T | RU6-RCC | 15-P-101C/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-19 | 2026-06-29 | 2102361993 | 8202237788 |  | 8202231727#LTSA Prbkan 15-P-102 Body F T | RU6-RCC | 15-P-102C/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K501 | 2026-02-03 | 2026-02-11 | 2026-01-14 | 2026-03-26 | 2102360294 | 8202237983 |  | 8202231726#Tag-1 UR. Perb. Bundwall Sela | RU5-TBL | 022-R-RP-PSA/00 | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-D1H | 0 | 120164000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-19 | 2026-06-26 | 2102361371 | 8202237786 |  | 8202231725#LTSA Pemeliharaan Fire Truck | RU6-LK/KK | 66-FT-01/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 767219570 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-19 | PM |  | 004
| K401 | 2026-03-05 | 2026-05-05 | 2026-01-19 | 2026-01-19 | 2102355916 | 8202241282 |  | 8202231724#26_Pengadaan Ignitor Dapur 10 | RU4-RFCGTO | 105F501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-19 | PM |  | 005
| K301 | 2026-02-02 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102353170 | 8202234467 |  | 8202231723#NR-26 Upnarmal Sound P-10 CDU | RU3-CDGP | CD4-P-010/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 1710580 | 0 | MA1-ROT |  | SHAHRONAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102359976 | 8202235544 |  | 8202231722#Motor GM-3-19B | RU5-E15112 | GM-3-19B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 247800 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-19 | 2026-01-19 | 2102356338 | 8202241281 |  | 8202231721#26_[CR] Open Brand Mech Seal | RU4-KPC | 87P204A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-16 | 2026-12-09 | 2026-12-09 | 2102360472 | 8202235552 |  | 8202231720#Connecting Rod K-3-02A | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-04-16 | PT02 |  | 3 | 2026-12-09 | PM |  | 003
| K501 | 2026-02-03 | 2026-06-17 | 2026-01-26 | 2026-06-19 | 2102359978 | 8202237982 |  | 8202231719#NRK_Pemasangan IHLA Tanki V16 | D&W-E5110 | V-16/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/NR-C3H | 380000000 | 0 | MA2-INT |  | FAUZANR |  | 2026-02-11 | PT02 |  | 3 | 2026-01-26 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102359977 | 8202235542 |  | 8202231718#Perb. Power Listrik L/A Jett | RU5-TBL | L-ARM-4-JT-4/00 | 50 | REL CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 8202235487 | 8202238855 | 8202231717#MATERIAL PIPING PLANT HVU2&HP | RU5-E15112 | 2-SPW05-3-B6/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 60798415 | 0 | MA3-STA |  | BERNANDOP |  | 2026-05-13 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-29 | 2026-06-29 | 2102359972 | 8202235482 |  | 8202231716#Perbaikaan Motor GM-202-06B | RU5-D&W | GM-202-06B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 190539 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-29 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102359970 | 8202235476 |  | 8202231715#Perbaikan Motor GM-202-06A | RU5-D&W | GM-202-06A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 190539 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-29 | 2026-06-29 | 2102359973 | 8202235472 |  | 8202231714#Perbaikan Motor GM-202-07A | RU5-D&W | GM-202-07A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 109436 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-29 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-29 | 2026-06-29 | 2102359974 | 8202235479 |  | 8202231713#Perbaikan Motor GM 202-07B | RU5-D&W | GM-202-07B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 109436 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-29 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-19 | 2026-05-20 |  | 8202235490 | 8202234970 | 8202231712#Mat'l Rockwool Ejector H-202- | RU5-D&W | E-202-04/00 | 60 | CLSD CSER PRC SETC | 5MR | D15/26/B6/NR-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-26 | 2026-01-19 | 2026-12-31 |  | 8202235494 | 8202234970 | 8202231711#MAT. INJECTION QUILL | RU5-D&W | E-202-04/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 36001686 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-19 | 2026-01-23 | 2102360612 | 8202235466 |  | 8202231710#GANTI WIRE MATA3&SHACKLE 8,5T | RU5-TBL | PIPE-ON-SHORE/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-08 | 2026-06-18 | 2102361421 | 8202233196 |  | 8202231709#Perbaikan Control Valve 059-A | RU6-UTL | 059-A-101B-E9/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 13200 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-15 | 2026-01-15 | 2102355453 | 8202241280 |  | 8202231708#26_[CR] Mechanical seal bocor | RU4-LOC3 | 260P154A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 11797050 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-15 | 2026-01-15 | 2102352160 | 8202232319 |  | 8202231707#212-LCV167 Rusak | RU2-HCC | 212-LV-167/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/NR-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-12 | 2026-06-05 | 2102361571 | 8202237784 |  | 8202231706#LTSA Patching Tangki Tahap 15 | RU6-HSC | 33-E-119B/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 305070100 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-15 | 2026-06-10 | 2102361526 | 8202237782 |  | 8202231705#LTSA Patching Tangki Tahap 14 | RU6-ITP | 42-T-107C/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 389422400 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K501 | 2026-02-03 | 2026-05-25 | 2026-10-01 | 2026-12-31 | 2102360611 | 8202237981 |  | 8202231704#NRK_Penggantian ACB SS 72 & S |  |  | 50 | REL NMAT PRC SETC | 5ER | D15/26/B6/NR-C3H | 37810000 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-07 | PT02 |  | 3 | 2026-10-01 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102358085 | 8202237921 |  | 8202231703#TGH1_25 UP Piping LOC I | RU4-LOC1 | LN21-108A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-15 | 2026-01-22 |  | 8202233247 | 8202238464 | 8202231702#Perbaikan 63-Z-202B dan 63-P- | RU6-ITP | 63-Z-202B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 660 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-15 | 2026-04-09 |  | 8202233519 |  | 8202231701#Penggantian Probe Vibrasi 13- | RU6-DHC | 13-P-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-26 | 2026-01-02 | 2026-12-30 |  | 8202235451 | 8202234970 | 8202231700#Mat'l Line BFW Belakang Pompa | RU5-D&W | E-202-04/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/26/B6/NR-C2H | 20891388 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-12-30 |  | 8202235450 | 8202234970 | 8202231699#Mat'l Perbaikan Line Suction | RU5-D&W | E-202-04/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-12-30 |  | 8202235443 | 8202234970 | 8202231698#Material Valve Strainer HVGO | RU5-D&W | E-202-04/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-26 | 2026-01-02 | 2026-12-30 |  | 8202235448 | 8202234970 | 8202231697#Material Drain C-202-03 | RU5-D&W | E-202-04/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/26/B6/NR-C2H | 22360110 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-12-30 |  | 8202235442 | 8202234970 | 8202231696#Material Valve Suction G-202- | RU5-D&W | E-202-04/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-26 | 2026-01-02 | 2026-12-30 |  | 8202235445 | 8202234970 | 8202231695#Material Line Chemical Neutra | RU5-D&W | E-202-04/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 12793849 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K701 | 2026-02-03 | 2026-03-28 | 2026-12-30 | 2026-12-30 | 2102358359 | 8202238009 |  | 8202231694#LTSA Elec Instrument_Alat Kal |  |  | 60 | REL GMPS NMAT PRC SETC | 7RT | D17/26/B6/RT-4-D2H | 2034492000 | 2034492000 | MA-LINT |  | RYANMANGGASA |  | 2026-02-11 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K701 | 2026-02-03 | 2026-03-28 | 2026-12-30 | 2026-12-30 | 2102358706 | 8202238008 |  | 8202231693#PM DEG 4-KDE-03 DE_SPK 1 | RU7-UTL | 4-KDE-03D/00 | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-4-D2H | 1 | 0 | MA-ROT |  | RYANMANGGASA |  | 2026-02-06 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-15 | 2026-04-24 | 2102361848 | 8202233033 |  | 8202231692#Perbaikan motor 51-P-102E | RU6-UTL | 51-P-102E-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 8316 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-15 | 2026-06-10 | 2102361340 | 8202237779 |  | 8202231691#LTSA Patching Tangki Tahap 13 | RU6-ITP | 42-T-301A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 321184400 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-15 | 2026-06-10 | 2102361581 | 8202237777 |  | 8202231690#LTSA Patching, Wrapping Thp 1 | RU6-ITP | 63-OS-110/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 111598200 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-12 | 2026-06-05 | 2102361605 | 8202237775 |  | 8202231689#LTSA Patching, Wrapping Thp 1 | RU6-HSC | 32-E-101/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 791520000 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-12 | 2026-06-05 | 2102361425 | 8202237773 |  | 8202231688#LTSA Patching Wrapping Tahap | RU6-HSC | 11-C-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-15 | 2026-02-11 | 2102363056 | 8202233538 |  | 8202231687#Penggantian Positioner Finfan | RU6-RCC | 16-E-119/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-15 | 2026-02-11 | 2102363058 | 8202233539 |  | 8202231686#Penggantian Positioner Finfan | RU6-RCC | 15-E-110/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-09 | 2026-01-09 | 2102355449 | 8202237919 |  | 8202231685#TGH1_UP Wrapping Pipe Pile 24 | RU4-TRML | 030PSV301/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 976340000 | MA3-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-09 | PM |  | 045
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-06 | 2026-01-06 | 2102357230 | 8202237917 |  | 8202231684#TGH19_Building Management Ser | RU4-UTL | 50AUX1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 405619000 | 0 | GEN-SIP |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2026-12-07 | 2026-12-07 | 2102360762 | 8202235422 |  | 8202231683#Perbaikan Pompa G-20-01C | RU5-TBL | G-20-01C/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 3788200 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-05-12 | PT02 |  | 3 | 2026-12-07 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-15 | 2026-01-26 | 2102352158 | 8202232373 |  | 8202231682#211 PT-14B Bearing housing tu | RU2-HCC | 211-PT-14B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 374677 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-07-01 | 2026-12-31 | 2102360269 | 8202238619 |  | 8202231681#Kabel Modifikasi Sump Pump-Mo |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/NR-C3H | 80 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-01 | PM |  | 045
| K501 | 2026-02-05 | 2026-02-07 | 2026-12-01 | 2026-12-31 | 2102360657 | 8202238613 |  | 8202231680#Penggantian Inverter UPS Guto |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/NR-C3H | 1 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-01 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-12 | 2026-01-12 | 2102357640 | 8202241279 |  | 8202231678#26_[CR] 012K101AP2 ALOP high | RU4-FOC2 | 012K101A-P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 5988884 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-14 | 2026-01-14 | 2102360196 | 8202235429 |  | 8202231677#Perbaikan Kompresor K-4-01A | RU5-E15111 | K-4-01A/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-14 | PM |  | 003
| K201 | 2026-02-06 | 2026-05-20 | 2026-12-17 | 2026-12-17 | 2102351911 | 8202238679 |  | 8202231676#LTSA FLOWSERVE AREA HCC | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 6100000000 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-12-17 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-15 | 2026-01-26 | 2102351583 | 8202232436 |  | 8202231675#Gearbox kasar | RU2-HCC | 212-P-25A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 6417954 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-09 | 2026-01-09 | 2102355447 | 8202237915 |  | 8202231674#TGH1_UP Seal Roof Floating Ro | RU4-TRML | 71T10/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 2228877650 | MA3-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-09 | PM |  | 045
| K501 | 2026-02-03 | 2026-06-17 | 2026-07-30 | 2026-07-30 | 2102360659 | 8202237980 |  | 8202231673#COMMON & PM MOTOR LISTRIK (T1 | RU5-E15111 |  | 50 | REL NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 130644000 | 0 | MA2-LIS |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-07-30 | 2026-07-30 | 2102358678 | 8202235417 |  | 8202231672#Pergantian Lampu Penerangan W | RU5-E15112 | 41-AC-RPPK-BPP2/00 | 01 | CRTD CSER NMAT PRC | 5ER | D15/09/B6/RT1-03NH | 0 | 0 | WS-LIS |  |  |  |  | PT02 |  | 2 | 2026-07-30 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-29 | 2026-05-13 | 2026-05-13 | 2102360438 | 8202235425 |  | 8202231671#Perbaikan POMPA G-19-01A | RU5-E15112 | G-19-01A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 409112 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-05-29 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-07-01 | 2026-12-31 | 2102360404 | 8202235440 |  | 8202231670#NRK_Pnggtian GM-3 - 38BD/39BD | RU5-E15112 |  | 01 | CRTD CSER MACM PRC | 5ER | D15/26/B6/NR-C3H | 7 | 0 | MA3-LIS |  |  |  |  | PT02 |  | 2 | 2026-07-01 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352397 | 8202234292 |  | 8202231669#Kerusakan berulang auto drain | RU2S-KIL | 900-02AC-1A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-14 | 2026-01-14 | 2102360194 | 8202235356 |  | 8202231668#Perbaikan Kompresor K-3-02C | RU5-E15112 | K-3-02A/00 | 50 | CRTD CSER GMCO MACM PRC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-14 | PM |  | 003
| K501 | 2026-02-03 | 2026-02-11 | 2026-01-02 | 2026-03-09 | 2102360789 | 8202237979 |  | 8202231666#Tag-2 UR. Sipil,BangunanSS&pi | RU5-TBL | 022-R-RP9/00 | 60 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-D1H | 0 | 750437000 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-14 | 2026-01-14 | 2102355557 | 8202241278 |  | 8202231664#26_[PM] Perawatan Kompresor 8 | RU4-KPC | 81A201K1B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 9916668 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-13 | 2026-01-13 | 2102360296 | 8202235359 |  | 8202231663#Perbaikan Blower K-5-20 | RU5-E15111 | K-5-20/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-16 | 2026-01-14 | 2026-12-11 | 2102361966 | 8202238493 |  | 8202231662#Penyehatan & Perbaikan Pompa | RU6-UTL | 70-P-104A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 1318000000 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-14 | 2026-01-14 | 2102350955 | 8202232364 |  | 8202231659#211-P-14B Vibrasi Tinggi | RU2-HCC | 211-P-14B/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-22 | 2026-09-17 | 2102364387 | 8202235365 |  | 8202231657#Perb. Level Transmitter LT-30 | RU5-UTL | TG-6-PP1-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 121000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-22 | PM |  | 004
| K501 | 2026-02-03 | 2026-02-11 | 2026-01-14 | 2026-03-26 | 2102360298 | 8202237978 |  | 8202231656#Tag-3 Pek. cleaning Sump,Oc,P | RU5-TBL | OC-RP-A/00 | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-D1H | 0 | 176953000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 045
| K601 | 2026-02-02 |  | 2026-01-14 | 2026-07-23 | 2102361752 | 8202236758 |  | 8202231655#SPK 2 PM UPS & DC Charger Bra | RU6-UTL | 01-PBC3-01A/00 | 50 | CRTD CSER NMAT PRC | 6ER | D16/26/B6/RT-C2H | 1348758900 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-01-14 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-04-13 | 2026-04-13 | 2102351723 | 8202232716 |  | 8202231654#Pengambilan Material Kabel 14 | RU2-HOC | 140-C-1/00 | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-14 | 2026-01-14 | 2102356066 | 8202241277 |  | 8202231652#26_[CR] Perbaikan Pompa 101P5 | RU4-RFCC | 101P503B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-14 | 2026-01-14 | 2102357239 | 8202241276 |  | 8202231651#26_[CR] 013P102A Mech Seal bo | RU4-FOC2 | 013P102A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 2180855 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-04-07 | 2026-04-07 | 2102351994 | 8202232711 |  | 8202231650#Penggantian Control Valve 170 | RU2-HOC | 170-FV-157/00 | 01 | CRTD NMAT PRC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102356376 | 8202237913 |  | 8202231649#TGH2_25 UP Cleaning HE Cooler | RU4-UTL | 053S102A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 234538800 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-14 | 2026-12-30 |  | 8202235371 | 8202235370 | 8202231648#Penggantian Mat Valve Bypass | RU5-D&W | 202-P038-2/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/NR-C2H | 15259316 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-12-14 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-04-20 | 2026-07-21 | 2102364110 | 8202235369 |  | 8202231647#Perb. Control Backwash Filter | RU5-E15112 | V-3-01B/01 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1313892000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-13 | 2026-01-13 | 2102355469 | 8202241275 |  | 8202231646#26_Pengadaan Motor 140E607A & | RU4-GTO | 140E607A-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-12 | 2026-01-12 | 2102360365 | 8202235349 |  | 8202231644#Penggantian Filter L.O K-3-01 | RU5-E15112 | K-3-01B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-07 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-05-13 | 2026-05-13 | 2102360470 | 8202235340 |  | 8202231643#Perbaikan Trubine GT-3-30A | RU5-E15112 | G-3-30A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 4007005 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-06-04 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-03-06 | 2026-03-06 | 2102351735 | 8202232682 |  | 8202231642#perbaikan motor 100-PM-201D | RU2-ITP | P-201D-M/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 7200000 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-01-09 | 2026-01-09 | 2102360439 | 8202235346 |  | 8202231641#penggantian filter L/O G-3-09 | RU5-E15112 | G-3-09B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 29493065 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-02 | 2026-05-13 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-01-05 | 2026-01-05 | 2102360738 | 8202235344 |  | 8202231640#Perbaikan FINFAN EA-2-12F | RU5-E15112 | EA-2-12-C2/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-13 | 2026-01-13 | 2102351720 | 8202232377 |  | 8202231639#Perbaikan CB 3 Pole 16 A | RU2-UTL | 550-B-1/00 | 50 | REL CSER NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-06 | 2026-02-06 | 2102352104 | 8202232678 |  | 8202231638#perbaikan motor 580 PM 301 A | RU2-UTL | 580-PM-301A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-14 | 2026-02-04 | 2102361659 | 8202233168 |  | 8202231637#Perbaikan FinFan 16-E-119J-K | RU6-RCC | 16-E-119J-K/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-03-06 | 2026-03-06 | 2102351710 | 8202232679 |  | 8202231636#Perbaikan Motor 520-PM-606 | RU2-UTL | 520-PM-606A/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  |  |  |  | PT02 |  | 2 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-05 | 2026-03-30 | 2026-03-02 | 2026-03-02 | 2102351604 | 8202238658 |  | 8202231635#Perawatan Pembersihan/ Penyed | RU2-UTL | 510-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA3-STA |  | ADEMULYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102356546 | 8202241274 |  | 8202231634#26_Matl Perbaikan Y Globe Vlv | RU4-UTL | 054P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-01-13 | 2026-01-13 | 2102353107 | 8202235304 |  | 8202231633#Perbaikan Gate Valve 24 IN po |  |  | 50 WAMA | CRTD CSER MACM PRC | 3MR |  | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-13 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-01-02 | 2026-01-02 |  | 8202238492 | 8202234623 | 8202231632#Tag 5 KV Isolasi Area PP |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102356130 | 8202241273 |  | 8202231631#26_[CR] Perbaikan 24K1P1AT | RU4-LOC1 | 24K1P1A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 15000000 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-13 | 2026-01-13 | 2102356621 | 8202241272 |  | 8202231630#26_[CR] Perbaikan gearbox 63A | RU4-RFCUTL | 63A501C-M2/00 | 60 | REL CNF CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 17350500 | 6512950 | MA5-ROT |  | FARIZSETYANA | 2026-06-11 | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-01-02 | 2026-01-02 |  | 8202238489 | 8202235030 | 8202231629#Tag 2 KV Pekerjaan Mekanik Ar |  |  | 60 | CLSD CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 112441772 | MA2-STA |  | SAPBATCH | 2026-01-30 | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-01-02 | 2026-01-02 |  | 8202238482 | 8202235030 | 8202231628#Tag 1 KV Pekerjaan Mekanik Ar |  |  | 60 | CLSD CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 90381962 | MA2-STA |  | SAPBATCH | 2026-01-30 | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 045
| K301 | 2026-02-02 | 2026-03-05 | 2026-01-02 | 2026-01-02 | 2102352175 | 8202235030 |  | 8202231627#KV Pekerjaan Mekanik Area UTL |  |  | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-14 | 2026-01-14 | 2102357289 | 8202241271 |  | 8202231626#26_[CR] penggantian bearing 1 | RU4-FOC1 | 11E50K-J/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 10798760 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-13 | 2026-01-13 | 2102357381 | 8202241270 |  | 8202231625#26_[CR] Perbaikan Mech Seal 3 | RU4-TRML | 37P102A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 6928350 | 6928350 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102357866 | 8202241269 |  | 8202231624#[CR] Perbaikan 22K-1 (packing | RU4-LOC1 | 22K1/00 | 60 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 33635202 | 16200934 | MA1-ROT |  | ABDULFM |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-07 | 2026-01-02 | 2026-01-02 |  | 8202238460 | 8202235629 | 8202231623#Tag Ke- 5 Pek Hose Handling A |  |  | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 223445046 | MA4-STA |  | SAPBATCH | 2026-05-07 | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-11 | 2026-01-02 | 2026-12-31 |  | 8202238446 | 8202234832 | 8202231621#Tag 22 TKDN Tambat Kapal SG |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 265530000 | 0 | MA4-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102355467 | 8202241267 |  | 8202231619#26_[CR] Perbaikan Pompa 11P4A | RU4-FOC1 | 11P4A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 523377257 | 5327257 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-13 | 2026-01-13 | 2102356336 | 8202241266 |  | 8202231617#26_[CR] Pompa 021P102A noise | RU4-LOC2 | 021P102A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 4830800 | 4830800 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-18 | 2026-01-02 | 2026-01-02 |  | 8202238421 |  | 8202231616#Tag 19 PM CM Rot & Elec. PT K |  |  | 60 | REL GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-10 | 2026-01-02 | 2026-01-02 | 2102352698 | 8202234414 |  | 8202231615#NR26-Pergantian Coke Valve 4" |  |  | 50 WAMA | REL CSER MSPT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 314000 | 0 | MA3-STA |  | HERDIANW |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-01-02 | 2026-01-02 |  | 8202238401 | 8202235140 | 8202231614#Tag 4 Pekerjaan Mekanik Area | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-13 | 2026-04-09 |  | 8202233511 |  | 8202231613#Penggantian Safety Relay 11-V | RU6-HSC | 11-E-112A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-13 | 2026-01-13 | 2102356494 | 8202241265 |  | 8202231612#26_[CR] 011E125K12 belt rusak | RU4-FOC2 | 011E125K12/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3209123 | 3209123 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352699 | 8202235217 |  | 8202231611#Pergantian Valve di LS-P-501B |  |  | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-13 | 2026-01-13 | 2102356491 | 8202241264 |  | 8202231610#26_[CR] 011E121K11 Belt rusak | RU4-FOC2 | 011E121K11/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765778 | 1765778 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-13 | 2026-02-11 |  | 8202233729 |  | 8202231609#Penggantian 052-PSLL-912B Boi | RU6-UTL | 052-B-101B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2772 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102356448 | 8202241263 |  | 8202231608#26_[CR] 011E116K04 belt rusak | RU4-FOC2 | 011E116K04/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-13 | 2026-01-13 | 2102356445 | 8202241262 |  | 8202231607#26_[CR] 011E110K33 Belt Rusak | RU4-FOC2 | 011E110K33/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3525956 | 3525956 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-07 | 2026-01-02 | 2026-01-02 |  | 8202238186 | 8202235126 | 8202231606#Tag 5 Mekanik Area Utara OM |  |  | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 102680000 | MA4-STA |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 |  | 3 | 2026-05-07 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-13 | 2026-01-13 | 2102356443 | 8202241261 |  | 8202231605#26_[CR] 011E110K06 belt rusak | RU4-FOC2 | 011E110K06/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765778 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-07 | 2026-01-02 | 2026-01-02 |  | 8202238385 | 8202234908 | 8202231604#Tag 31 Termin TKDN Pemlhrn Se | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 159188595 | WS-SG |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 |  | 3 | 2026-05-07 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102355802 | 8202241260 |  | 8202231603#26_[CR] Perbaikan Motor MLOP, | RU4-TRML | 63P101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-12 | 2026-01-12 | 2102361575 | 8202234049 |  | 8202231602#4" #150 line PSV 31-E-101ABC | RU6-HSC | 31-E-101A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102355488 | 8202241259 |  | 8202231600#26_Matl Perbaikan Line Suctio | RU4-RFCC | 101P501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 3162744 | 0 | MA6-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-13 | 2026-04-10 | 2102351289 | 8202232343 |  | 8202231597#211-PT-75A Turbin Rusak | RU2-HCC | 211-PT-75A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 3564 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-13 | 2026-01-13 | 2102354921 | 8202241258 |  | 8202231596#26_[CR] Penggantian Bearing 8 | RU4-KPC | 80E201B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-05 | 2026-01-13 | 2026-01-13 | 2102356592 | 8202241257 |  | 8202231595#26_[CR] Penggantian Mech Seal | RU4-KPC | 48P201B/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 101916698 | 101916698 | MA4-ROT |  | SAPBATCH | 2026-05-05 | 2026-03-10 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-13 | 2026-01-22 | 2102352167 | 8202232363 |  | 8202231594#Pompa Jammed | RU2-HCC | 211-P-14A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 8508505 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-12 | 2026-01-13 | 2026-01-13 | 2102357715 | 8202241256 |  | 8202231588#26_[CR] Penggantian LubeOil F | RU4-RFCUTL | 154P505A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 9962000 | 0 | MA5-ROT |  | TONNYADI | 2026-06-02 | 2026-03-10 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-13 | 2026-01-13 | 2102355176 | 8202241255 |  | 8202231587#26_[PV] Penggantian Pompa Inj | RU4-TRML | 46P2AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-07 | 2026-01-19 | 2026-01-19 | 2102351722 | 8202238102 |  | 8202231586#Pengerjaan Elevator 140 – DCU | RU2-HOC | 140-PX-53/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 42000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-13 | 2026-01-13 | 2102357639 | 8202241254 |  | 8202231585#25_[CR] perbaikan pompa 51P2A | RU4-UTL | 51P2A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-13 | 2026-01-13 | 2102355429 | 8202238587 |  | 8202231584#Pengadaan Motor 021P107B | RU4-LOC2 | 021P107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-09 | 2026-06-04 |  | 8202237772 | 8202232778 | 8202231582#Penyelesaian Pek. PM PDM EI M | RU6-UTL | SS-01/00 | 60 | REL GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 3960 | 91424300 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-09 | 2026-06-04 | 2102361500 | 8202236676 |  | 8202231581#SPKR Refacing Gasket Thp 8 24 | RU6-HSC | 24-E-201A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 84400000 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-01-09 | 2026-12-08 | 2102361507 | 8202232778 |  | 8202231580#PM Electric dan Instrument Ar | RU6-UTL | SS-01/00 | 50 | REL GMCO NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 29040 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-12 | 2026-06-05 | 2102361545 | 8202236680 |  | 8202231579#SPKR Refacing Gasket Thp 6 PO | RU6-POC | 37-V-101/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 409100000 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-08 | 2026-01-02 | 2026-01-02 |  | 8202238384 | 8202234749 | 8202231578#Tag 5 LTSA Online Partial Dis |  |  | 60 | CLSD CNF GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 0 | 78077600 | MA2-LIS |  | SAPBATCH | 2026-03-05 | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-08 | 2026-01-02 | 2026-01-02 |  | 8202238376 | 8202234749 | 8202231577#Tag 4 LTSA Online Partial Dis |  |  | 60 | CLSD CNF GMPS NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 0 | 95757600 | MA2-LIS |  | SAPBATCH | 2026-02-03 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-27 | 2026-01-02 | 2026-12-31 |  | 8202234749 |  | 8202231576#LTSA Online Partial Discharge |  |  | 50 | CRTD GMCO NMAT PRC | 3ER | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-LIS |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-11 | 2026-01-12 | 2026-02-25 | 2102360314 | 8202237977 |  | 8202231575#UR. BORDES MA-2 (2) | RU5-E15111 | 09-PV-104/00 | 60 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 0 | 390424000 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-12 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-01-02 | 2026-01-02 |  | 8202238063 | 8202235151 | 8202231574#Tag 18 KV Cleaning & Ganti Ca | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-09 | 2026-04-02 | 2102361468 | 8202233598 |  | 8202231573#Penggantian Level Switch EDG | RU6-UTL | 51-G-102/00 | 50 WAMA | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 6864 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-11 | 2026-01-02 | 2026-01-02 | 2102358138 | 8202234911 |  | 8202231571#Fabrikasi Spool Pipe & Chambe | RU7-CRU | 3-LT-108/00 | 60 | REL PRC SETC | 7RT | D17/26/B6/RT-3-D3H | 0 | 0 | MA-LINT |  | YAYANHER |  | 2026-03-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-05-07 | 2026-01-12 | 2026-12-30 | 2102352548 | 8202234291 |  | 8202231570#Pemasangan/Perbaikan Fire Pro | RU2S-KIL | GDG-KTR-CDU/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 1250000000 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-12 | 2026-01-12 | 2102353843 | 8202241253 |  | 8202231569#26_Mtl. Pilot Burner 12F1 | RU4-FOC1 | 12F1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-12 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-12 | 2026-02-04 | 2102361424 | 8202233640 |  | 8202231565#Penggantian Flow Transmitter | RU6-UTL | 052-FT-901A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2244 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K201 | 2026-02-04 | 2026-04-23 | 2026-03-03 | 2026-03-03 | 2102351105 | 8202238146 |  | 8202231564#Perbaikan Mobile Crane 160T R | RU2-WS | CMH-03/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 843570000 | 0 | WS-KAB |  | MDSYAHPUTRA |  | 2026-04-23 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-12 | 2026-03-03 | 2102361442 | 8202233594 |  | 8202231562#Penggantian Level Transmitter | RU6-HSC | 33-LT-015/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-12 | 2026-01-12 | 2102357604 | 8202237911 |  | 8202231558#TGH1_25_POND_TANKI_MA3 |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 358268000 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-12 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-12 | 2026-02-09 | 2102361549 | 8202233129 |  | 8202231555#Perbaikan kompressor 63-K-401 | RU6-ITP | 63-K-401B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2640 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-12 | 2026-04-06 | 2102362439 | 8202238577 |  | 8202231554#Penggantian Flow Transmitter | RU6-DHC | 12-FT-889/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-12 | 2026-01-12 | 2102362562 | 8202233986 |  | 8202231553#Lift line catalyst | RU6-HSC | 32-R-101-UP6/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-03-06 | 2026-03-06 | 2102351660 | 8202232232 |  | 8202231552#Motor Rusak | RU2-HCC | 211-EM-5E/00 | 01 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-08-03 | 2026-09-15 | 2102360787 | 8202235268 |  | 8202231551#Perbaikan Water Meter Deepwel | RU5-UTL | P-9PAMPANCUR/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 15100000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-08-03 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360473 | 8202235277 |  | 8202231550#PERB.LINE 21-P235-12" LGP DI | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 54670646 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360317 | 8202235271 |  | 8202231549#Perbaikan Motor GM-5-09B | RU5-E15111 | GM-5-09B/00 | 50 | REL CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360316 | 8202235274 |  | 8202231548#Perbaikan Motor Fin-Fan EM-5- | RU5-E15111 | EM-5-09A/00 | 50 | REL CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 003
| K201 | 2026-02-01 | 2026-05-29 | 2026-03-06 | 2026-03-06 | 2102351389 | 8202232405 |  | 8202231545#Vibrasi Tinggi | RU2-HCC | 701-PM-7B/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ER | D12/26/B6/RT-D2H | 68472000 | 66692000 | MA2-LIS |  | NURFADHILLA |  | 2026-05-21 | PT02 |  | 3 | 2026-03-06 | PM |  | 004
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-12 | 2026-03-17 | 2102363116 | 8202238576 |  | 8202231544#Penggantian Level Switch 37-P | RU6-POC | 37-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-02 | 2026-01-12 | 2026-06-22 | 2102361509 | 8202236582 |  | 8202231543#Tgh ke 6 Volume Stat MA 1 | RU6-RCC | 15-R-103/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-STA |  | SHELFIANCBP |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-09 | 2026-03-11 | 2102361502 | 8202233028 |  | 8202231542#Perbaikan Motor 57-E-507H | RU6-DHC | 57-E-401H-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-12 | 2026-03-13 | 2102363063 | 8202238575 |  | 8202231540#Penggantian Temp Indicator 11 | RU6-HSC | 11-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-12 | 2026-03-13 | 2102363065 | 8202238574 |  | 8202231538#Penggantian Temp Indicator 11 | RU6-HSC | 11-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-05 | 2026-01-12 | 2026-01-12 | 2102355615 | 8202241252 |  | 8202231537#26_[CR] 87P204A Mech seal boc | RU4-KPC | 87P204A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 23461200 | 23461200 | MA4-ROT |  | SAPBATCH | 2026-05-05 | 2026-03-10 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-12 | 2026-03-17 | 2102363456 | 8202238569 |  | 8202231536#Perbaikan Positioner 52-TV-21 | RU6-UTL | 52-TV-219C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 5808 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-14 | 2026-01-14 | 2102355529 | 8202237895 |  | 8202231535#TGH1_25_SCAFFOLD_REJUV_ISOLAS |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 850803250 | MA2-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-14 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-20 | 2026-02-20 | 2026-03-13 | 2102362560 | 8202232962 |  | 8202231534#Perbaikan Pompa 42-P-101B | RU6-ITP | 42-P-101B/00 | 50 WAMA | REL CSER MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 14460980 | 0 | MA4-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-20 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-07-01 | 2026-08-27 | 2102360699 | 8202235282 |  | 8202231533#Pengadaan Material AIS | RU5-TBL | SAMPLER-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 574050000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-07-01 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-05 | 2026-01-12 | 2026-01-12 | 2102354415 | 8202241251 |  | 8202231532#26_[CR] Mechanical seal bocor | RU4-LOC3 | 220P103A/00 | 60 | TECO CNF CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 324624650 | 166371400 | MA4-ROT |  | SAPBATCH | 2026-05-05 | 2026-03-10 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-12 | 2026-01-12 | 2102355484 | 8202241250 |  | 8202231531#26_[CR] High vibrasi pada pom | RU4-TRML | 041P302A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-12-02 | 2026-12-02 | 2102360815 | 8202235251 |  | 8202231530#G-5-16B PERBAIKAN VIBRASI TIN | RU5-E15111 | G-5-16B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 2160940 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-06-02 | PT02 |  | 3 | 2026-12-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-03 | 2026-06-08 | 2026-06-08 | 2102360692 | 8202235255 |  | 8202231529#EA-1-21Q V-BELT PUTUS | RU5-E15111 | EA-1-21Q/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-09 | 2026-01-09 | 2102351783 | 8202232634 |  | 8202231528#Pengambilan material gasket 9 | RU2-ITP | 8-P-94650-A2A1/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-09 | 2026-06-09 | 2102360471 | 8202235249 |  | 8202231527#GT-3-30A vibrasi tinggi | RU5-E15112 | GT-3-30A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-09 | 2026-01-09 | 2102354780 | 8202237879 |  | 8202231526#TGH1_24 UP Penyehatan SRU | RU4-SRU | 93E405/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-09 | 2026-01-09 | 2102357865 | 8202241249 |  | 8202231525#26_Pengadaan speed indikator | RU4-FOC1 | 14P607A/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 32000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-09 | 2026-04-20 | 2102361504 | 8202232860 |  | 8202231524#Perbaikan Trafo 14A-PTR1-01A | RU6-RCC | 14A-PTR1-01A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 4750000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-09 | 2026-01-09 | 2102356497 | 8202241248 |  | 8202231523#26_011TI091 putus | RU4-FOC2 | 011TI091/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 24000000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-08 | 2026-01-13 | 2026-01-13 | 2102350268 | 8202232218 |  | 8202231522#Perbaikan Motor 220 PM-5A | RU2-HOC | 220-PM-5A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 3110000 | 0 | MA1-LIS |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360366 | 8202235248 |  | 8202231521#pengantian kabel LV SS 32 |  |  | 50 | REL CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-09 | 2026-01-09 | 2102357166 | 8202241247 |  | 8202231520#26_valve recycle 260K101/102 | RU4-LOC3 | LN260-1152HK/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 0 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-09 | 2026-01-09 | 2102356977 | 8202241246 |  | 8202231519#26_Valve 1" SS Needle Valve F | RU4-LOC3 | LN240-1326A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 0 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-09 | 2026-01-09 | 2102357611 | 8202241245 |  | 8202231518#26_Penggantian PSV 70PSV004/0 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-09 | 2026-01-09 | 2102357383 | 8202241244 |  | 8202231517#26_[CR] Perbaikan Turbin 52P2 | RU4-UTL | 52P2B-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 17448314 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-12 | 2026-01-09 | 2026-01-09 | 2102357387 | 8202241243 |  | 8202231515#26_[CR] Perbaikan pompa 54P20 | RU4-UTL | 54P204B/00 | 60 | TECO CNF CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 2741934 | 0 | MA5-ROT |  | TONNYADI | 2026-03-30 | 2026-03-10 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-12-01 | 2026-12-01 | 2102360572 | 8202238620 |  | 8202231514#FASILITAS REGREASING EA-31-21 | RU5-E15112 | EA-31-21C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-01 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-09 | 2026-01-09 | 2102355445 | 8202237877 |  | 8202231513#Amend_25 UP Loading Unloading | RU4-RFCGTO | 106S502/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-09 | 2026-04-23 | 2102361491 | 8202233485 |  | 8202231512#Penggantian Temp Switch 052-T | RU6-UTL | 052-B-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 8712 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-09 | 2026-01-09 | 2102357862 | 8202241242 |  | 8202231510#26_[CR] Perbaikan Bocoran Pel | RU4-RFCC | 103P508A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 2327500 | 0 | MA6-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-09 | 2026-01-30 | 2102361465 | 8202232984 |  | 8202231509#Perbaikan Pompa 15-P-109B | RU6-RCC | 15-P-109B/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-08-03 | 2026-08-03 | 2102351889 | 8202232702 |  | 8202231508#perbaikan 300-C-2 A silinder | RU2-HSC | 300-C-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-08-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-09 | 2026-01-09 | 2102357385 | 8202241241 |  | 8202231507#26_[CR] Perbaikan LO Filter P | RU4-UTL | 54P1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 500000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-11-20 | 2025-11-20 | 2102351847 | 8202232578 |  | 8202231506#Penggantian Check Valve 8 inc | RU2-ITP | 930-P-5BN/00 | 01 | CRTD NMAT PRC | 2MR | D12/XX/B6/RT-D2NH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-20 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-05 | 2026-01-09 | 2026-01-09 | 2102357339 | 8202241240 |  | 8202231505#26_[CR] Bocoran pelumas crank | RU4-LOC3 | 220K101/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 7253368 | 11396736 | MA4-ROT |  | SAPBATCH | 2026-05-05 | 2026-03-10 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351761 | 8202232522 |  | 8202231504#[Br.down] Mechanical Seal Lea | RU2-HCC | 702-P-9B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351667 | 8202232519 |  | 8202231503#[Br.down] Mechanical Seal Lea | RU2-HCC | 211-P-75B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351589 | 8202232516 |  | 8202231502#[Br.down] Mechanical Seal Lea | RU2-HCC | 840-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 3565626 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351588 | 8202232514 |  | 8202231501#[Br.down] Mechanical Seal Lea | RU2-HCC | 702-P-7B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 3565626 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351580 | 8202232503 |  | 8202231500#Abnormal Noise | RU2-HCC | 211-EF-4D/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 35253000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351474 | 8202232512 |  | 8202231499#[Br.down] Mechanical Seal Lea | RU2-HCC | 212-P-18A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 1715235 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-01-09 | 2026-01-09 |  | 8202238456 | 8202237680 | 8202231498#Amandemen_25 UP Load Unload M | RU4-GTO | 106S502/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/25/B6/RTC-14-C2H | 200000000 | 0 | MA7-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-09 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351475 | 8202232272 |  | 8202231497#Material PM Oil Purifier 301- | RU2-HSC | 301-CT-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-12 | 2026-01-12 | 2102358316 | 8202237347 |  | 8202231496#85E206-bocor tube side di int | RU4-KPC | 85E206/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-06 | 2026-05-29 | 2102361327 | 8202236678 |  | 8202231495#SPKR Refacing Gasket Thp 7 CO | RU6-DHC | 14-E-101A/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 255600000 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-22 | 2026-01-22 | 2102354614 | 8202241239 |  | 8202231494#26_Stopper pulley motor 240E1 | RU4-LOC3 | 240E125M2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-22 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-08 | 2026-01-08 | 2102351282 | 8202232347 |  | 8202231493#211-PM 76A Motor Rusal | RU2-HCC | 211-P-76A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-24 | 2026-01-08 | 2026-01-08 | 2102351313 | 8202232277 |  | 8202231492#Perbaikan Kerusakan Pompa Slo | RU2-UTL | 510-P-1/00 | 60 | REL PRT MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | MSADLI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-09 | 2026-02-06 | 2102361467 | 8202233712 |  | 8202231491#Penggantian Air Filter 58-K-1 | RU6-UTL | 58-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2640 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-08 | 2026-01-08 | 2102352156 | 8202232222 |  | 8202231490#Perbaikan Motor 140-PM-4 A | RU2-HOC | 140-PM-4A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-05-18 | 2026-01-08 | 2026-01-08 | 2102351969 | 8202232206 |  | 8202231489#Perbaikan motor 930-PM-4A | RU2-ITP | 930-PM-5AN/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA4-STA |  | DEDISUKMANA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-08 | 2026-01-08 | 2102351488 | 8202232280 |  | 8202231488#Perbaikan Kerusakan Major 580 | RU2-UTL | 580-P-303A/00 | 50 | REL MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-09 | 2026-01-30 | 2102361373 | 8202233646 |  | 8202231487#Penggantian Filter LO 56-P-10 | RU6-UTL | 56-P-101A-T/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 1980 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-02 | 2026-06-04 | 2102362152 | 8202238583 |  | 8202231486#Indikasi passing 61-FV-302 | RU6-POC | 61-P-303A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-06 | 2026-03-09 | 2026-04-13 | 2102361422 | 8202232155 |  | 8202231485#Perbaikan Mech Seal Pompa 33- | RU6-HSC | 33-P-108A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 2431295 | 0 | MA3-ROT |  | ABDULAZIZ70 |  | 2026-02-07 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360614 | 8202235143 |  | 8202231484#Perbaikan Motor EM-2-12F | RU5-E15112 | EM-2-12F/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 747900 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K501 | 2026-02-03 | 2026-03-06 | 2026-01-19 | 2026-04-22 | 1102329017 | 8202237976 |  | 8202231483#TSA Maint. & Service AC dalam | RU5-UTL | 41-AC-CR-PP2/00 | 60 | CLSD NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 731077000 | 0 | WS-INT |  | RUDIEKO |  | 2026-03-06 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-25 | 2026-01-01 | 2026-12-31 | 2102352108 | 8202235463 |  | 8202231482#Pekerjaan Pipa box cooler 4-1 | RU3-CDGP |  | 60 | REL CSER GMPS MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 94041034 | 94041034 | MA1-STA |  | ALEPDALITAN |  | 2026-03-09 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K401 | 2026-02-04 | 2026-02-13 | 2026-01-08 | 2026-01-08 |  | 8202238455 | 8202237635 | 8202231481#TGH2_25 UP Cleaning HE Cooler | RU4-UTL | 54E1/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/25/B6/RTC-5-C2H | 275928000 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-08 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-08 | 2026-03-09 | 2102362492 | 8202233410 |  | 8202231480#Perbaikan 12-A-501 P1B | RU6-DHC | 12-A-501/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-04-09 |  | 8202236746 | 8202234040 | 8202231479#SPK 29 LTSA Transformator RU | RU6-RCC | 14A-PTR1-01A/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-08 | 2026-01-29 | 2102361325 | 8202233167 |  | 8202231478#Perbaikan Finfan 31-E-105A1 | RU6-HSC | 31-E-105A1/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 16015404 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-08 | 2026-03-03 | 2102361268 | 8202233865 |  | 8202231477#Pemasangan Duct Seal di OS-15 | RU6-HSC | OS-15/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-01-08 | 2026-04-14 | 2102361285 | 8202234000 |  | 8202231476#Kebutuhan Material COC 20-R-1 | RU6-RCC | 20-R-101C/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 1041661 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 004
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-08 | 2026-10-12 | 2102361338 | 8202238570 |  | 8202231475#Perbaikan pompa 055-A-101-P4B | RU6-UTL | 055-A-101-P4B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-08 | 2026-06-18 | 2102361321 | 8202233150 |  | 8202231474#Perbaikan IR Low Burner 52-B- | RU6-UTL | 52-B-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 13200 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-09 | 2026-02-02 | 2026-12-30 |  | 8202237875 |  | 8202231473#TGH5_24 Perbaikan dan Pemelih | RU4-FOC2 | 011P127B/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 64172450 | 64172450 | WS-PMP |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-08 | 2026-01-08 | 2102357872 | 8202241238 |  | 8202231471#26_Motor 024P-102A high vibra | RU4-LOC2 | 024P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 888150 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-08 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-08 | 2026-01-08 | 2102355531 | 8202241237 |  | 8202231470#26_[CR] Bocoran Mech Seal 180 | RU4-GTO | 180T602P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-08 | 2026-01-08 | 2102356335 | 8202241236 |  | 8202231467#26_Motor CPI 002P101B vibrasi | RU4-LOC2 | 002P101B/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 493600 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-08 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-30 | 2026-12-30 | 2102360610 | 8202235149 |  | 8202231466#Pengadaan Relay proteksi KM-1 |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 8 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-08 | 2026-01-08 | 2102357827 | 8202236529 |  | 8202231465#D_26 022P104A motor noise | RU4-LOC2 | 022P104A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-08 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-08 | 2026-01-08 | 2102356540 | 8202241235 |  | 8202231464#26_Perbaikan Motor 021P102B | RU4-LOC2 | 021P102B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 676550 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-08 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-07 | 2026-04-13 | 2102361374 | 8202237770 |  | 8202231462#LTSA Scaffolding 2025-2027 Ta | RU6-POC | 37-E-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 0 | 112948350 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-07 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2025-12-22 | 2026-12-30 | 2102354243 | 8202237873 |  | 8202231461#TGH_SIP_UP CPI ME 2 Tahun 202 | RU4-GTO | 140FE020/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 0 | 1817171000 | MA7-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2025-12-22 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-08 | 2026-06-08 | 2102360693 | 8202235131 |  | 8202231460#Ea-8-15B Vbelt Defect | RU5-E15112 | EA-8-15B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-06 | 2026-12-30 |  | 8202235128 |  | 8202231459#Perbaikan Cover Condenser STG | RU5-UTL | VAP-FAN-TG2-PP2/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-05 | 2026-06-05 | 2102360760 | 8202235133 |  | 8202231458#Ea-3-09B High Vibration | RU5-E15112 | EA-3-09B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-05 | 2026-06-05 | 2102360739 | 8202235134 |  | 8202231456#Ea-3-09A High Vibration | RU5-E15112 | EA-3-09A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-18 | 2026-01-07 | 2026-12-30 | 2102356348 | 8202236220 |  | 8202231455#TGH13_22 TSA 11 Unit DCS Exis | RU4-FOC2 | DCS-FOC2/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 2533589000 | 2533589000 | MA2-INT |  | FARIZSETYANA |  | 2026-03-09 | PT02 |  | 3 | 2026-01-07 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-05 | 2026-01-05 | 2102355535 | 8202241234 |  | 8202231452#26_[CR] Perbaikan turbin FD F | RU4-UTL | 520B601K-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-02 | 2026-06-02 | 2102360616 | 8202235137 |  | 8202231451#CASING BOOSTER PUMP B BOCOR | RU5-UTL | VM-32-03-GM1B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-19 | 2026-01-19 | 2102361266 | 8202238452 |  | 8202231449#SPKR Service Fire Water Tahap | RU6-UTL | 54SW0103MS0124N/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 1 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-16 | 2026-01-07 | 2026-01-21 | 2102361372 | 8202232978 |  | 8202231448#Perbaikan Pompa 20-P-103A | RU6-RCC | 20-P-103A/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 211541199 | 889800 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-01-07 | PM |  | 003
| K202 | 2026-02-02 |  | 2025-12-24 | 2025-12-24 | 2102352383 | 8202234290 |  | 8202231447#LOW PERFOMANCE 101-P-9B | RU2S-KIL | 101-P-9B/00 | 01 | CRTD NMAT PRC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  |  |  |  | PT02 |  | 2 | 2025-12-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-02 | 2026-01-29 | 2026-02-20 | 2102361284 | 8202232154 |  | 8202231446#Penggantian Toothbelt 3150-14 | RU6-HSC | 33-E-101A1/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C3H | 64888585 | 49288585 | MA3-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-07 | 2026-01-07 | 2102355599 | 8202241233 |  | 8202231443#26_[CR] 011E-124-K4 pulley go | RU4-FOC2 | 011E124K04/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 17796500 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-07 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-07 | 2026-01-07 | 2102355598 | 8202241232 |  | 8202231442#26_[CR] 011E-117 K5 pulley go | RU4-FOC2 | 011E117K05/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 21431969 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-07 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-07 | 2026-02-04 | 2102362284 | 8202234111 |  | 8202231441#11-E-131D | RU6-HSC | 11-E-131D/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-07 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-06 | 2026-01-06 | 2102357188 | 8202237872 |  | 8202231440#TGH_TKDN_SIP_UP Fire Proofing | RU4-UTL | 05PS163/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-06 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-06 | 2026-03-04 | 2102361269 | 8202232741 |  | 8202231438#Rewinding Motor 14-P-601B | RU6-DHC | 14-P-601B/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-06 | 2026-02-20 | 2102362799 | 8202237768 |  | 8202231437#LTSA Online Leak Sealing Taha | RU6-UTL | 50HS-8103MS138H/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 15816000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-30 | 2026-07-30 | 2102360695 | 8202235111 |  | 8202231436#Perbaikan kabel lampu F-8-01A | RU5-E15112 | F-8-01A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 28800000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-30 | 2026-12-30 | 2102360694 | 8202235115 |  | 8202231435#Perbaikan Cover fin fan Em-8- | RU5-E15112 | EM-8-10M/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 18525387 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-30 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-06 | 2026-02-27 | 2102362693 | 8202237766 |  | 8202231434#LTSA Online Leak Sealing Taha | RU6-DHC | 22-E-102/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-06 | 2026-04-10 | 2102361305 | 8202236813 |  | 8202231433#PM mekanikal MA 3 Thp 1 | RU6-HSC | 32-R-102/00 | 50 | REL GMCO NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-13 | 2026-02-03 | 2102362241 | 8202233001 |  | 8202231432#Perbaikan Pompa 11-P-114 Body | RU6-HSC | 11-P-114B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-06 | 2026-01-27 | 2102361328 | 8202232951 |  | 8202231431#Perbaikan Pompa 51-P-101E (Pe | RU6-UTL | 51-P-101E/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 1980 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 004
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-07 | 2026-01-07 | 2102357425 | 8202237870 |  | 8202231426#Tagihan Termin 1-Perb. PT Sin |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 872139000 | MA5-ROT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-07 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-04-10 |  | 8202236811 | 8202232772 | 8202231425#PM PDM Elect Inst Area MA-2 D | RU6-DHC | 09-13-PSW2-01B/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-04-10 |  | 8202236807 | 8202232772 | 8202231424#PM PDM Elect Inst Area MA2-DH | RU6-DHC | 09-13-PSW2-01B/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-23 | 2026-01-05 | 2026-04-10 |  | 8202236809 | 8202232772 | 8202231423#PM PDM Elect Inst Area MA2 DH | RU6-DHC | 09-13-PSW2-01B/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | DINDINS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-01-05 | 2026-12-03 | 2102361306 | 8202232772 |  | 8202231422#PM PDM Elect Inst Area DHC Ta | RU6-DHC | 09-13-PSW2-01B/00 | 01 | CRTD CSER GMCO NMAT PRC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-11 | 2026-01-05 | 2026-01-05 | 2102354785 | 8202236744 |  | 8202231421#Penggantian Level Transmitter | RU4-TRML | 73LT001/00 | 01 | CRTD CSER MACM PRC | 4IR |  | 1 | 0 | MA3-INT |  | FATAHALFI |  |  | PT02 |  | 2 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-02 | 2026-04-08 | 2102362437 | 8202237764 |  | 8202231418#LTSA Scaffolding 2025-2027 Ta | RU6-ITP | 42-T-101E/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 115195050 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-04-10 | 2026-01-02 | 2026-04-08 | 2102361813 | 8202237762 |  | 8202231417#Pekerjaan COA 32-V-106 B Taha | RU6-HSC | 32-V-106B/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 20763000 | MA3-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-06 | 2026-02-19 | 2102362036 | 8202233424 |  | 8202231414#Perbaikan 12-P-504A | RU6-DHC | 12-P-504A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-06 | 2026-03-03 | 2102361323 | 8202233025 |  | 8202231412#Perbaikan Motor auxl LO | RU6-UTL | 056-P-101B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 152903 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-06 | 2026-01-06 | 2026-01-06 | 2102351380 | 8202232671 |  | 8202231411#Winding Motor Short | RU2-HCC | 702-PM-7B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 1780000 | 0 | MA2-LIS |  | AZIZFATONI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-06 | 2026-01-06 | 2102351712 | 8202232526 |  | 8202231409#penyediaan Power Supply#Trafo | RU2-UTL | 925-AND-24/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355841 | 8202241231 |  | 8202231408#26_[CR] penggantian fan blade | RU4-FOC1 | 11E52K-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-05 | 2026-05-29 | 2102361304 | 8202233349 |  | 8202231407#Perbaikan 15-LC-003 | RU6-RCC | 15-LT-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K501 | 2026-02-05 | 2026-06-17 | 2026-06-17 | 2026-07-01 | 2102364390 | 8202238608 |  | 8202231406#Perbaikan Modul IO DCS SWD 1 | RU5-UTL | SWD1-DCS-INST/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/26/B6/RT-C2H | 2 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-06 | 2026-07-16 | 2102362143 | 8202233117 |  | 8202231405#Perbaikan Limit Switch SB 11- | RU6-RCC | 15-B-101-SB19/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-04-10 | 2102361303 | 8202237760 |  | 8202231404#LTSA ConMon PLC TKDN Thp 4 | RU6-RCC | 16-JKX-004/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-04-10 | 2102361307 | 8202237758 |  | 8202231403#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | 20-JS-007/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-25 | 2102361301 | 8202237756 |  | 8202231402#LTSA Online Leak Sealing Taha | RU6-RCC | 15-E-110/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 0 | 139060000 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-04-10 | 2026-01-05 | 2026-02-19 | 2102362498 | 8202237754 |  | 8202231401#LTSA Online Leak Sealing Taha | RU6-HSC | 32PG4803PR366H/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 16392450 | MA3-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-12 | 2102362467 | 8202237752 |  | 8202231400#LTSA Online Leak Sealing Taha | RU6-DHC | 22-E-102/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 0 | 233295000 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-05 | 2026-01-08 | 2102362566 | 8202233172 |  | 8202231399#Perbaikan Fin Fan 31-E-103A1 | RU6-HSC | 31-E-103A1/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-13 | 2026-01-13 |  | 8202237854 | 8202237592 | 8202231398#Perbaikan Pompa 70P3 dan 70P3 | RU4-K3LL | 70P2A/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 0 | 1270495000 | WS-PMP |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-13 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-10 | 2025-11-10 | 2102358108 | 8202236041 |  | 8202231397#Klem pipa conduit rusak & ber |  |  | 50 WENG | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-10 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102354787 | 8202237853 |  | 8202231396#TGH7-9_24 TSA AC Split di Are | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 0 | 200120000 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-05-26 |  | 8202236613 | 8202238735 | 8202231395#SWO Sewa Barge Tahap 5 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-05-26 |  | 8202236614 | 8202238735 | 8202231394#SWO Sewa Barge Tahap 4 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-08 | 2026-02-10 | 2026-01-05 | 2026-05-26 |  | 8202238737 |  | 8202231393#SWO Sewa Barge Tahap 3 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 40000000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354084 | 8202236248 |  | 8202231392#Perbaikan 005PV003D | RU4-UTL | 005PV003D/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-05 | 2026-01-05 | 2102354512 | 8202241230 |  | 8202231391#26_019P-124BM visual motor no | RU4-FOC2 | 019P124BM/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 125600 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354082 | 8202236250 |  | 8202231390#Perbaikan 005PV003C | RU4-UTL | 005PV003C/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-08 | 2026-02-10 | 2026-01-05 | 2026-05-26 |  | 8202238736 |  | 8202231389#SWO Sewa Barge Tahap 2 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 40000000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-27 | 2025-11-27 | 2102355824 | 8202236244 |  | 8202231388#Perbaikan 520FI_407 Boiler 52 | RU4-UTL | 520B401/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-27 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-05 | 2026-01-05 | 2102356937 | 8202241229 |  | 8202231387#26_Motor 021P-106A vibrasi | RU4-LOC2 | 021P106A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 2712239 | 2712005 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-05 | 2026-01-05 | 2102358297 | 8202241228 |  | 8202231386#26_Motor 021P-107B short | RU4-LOC2 | 021P107B/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102357891 | 8202236543 |  | 8202231384#D_26 013P104 A M motor panas | RU4-FOC2 | 013P104AM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102357521 | 8202236519 |  | 8202231383#D_26 Pengambilan kawat wiring | RU4-LOC2 | 021P102AM-CB/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K601 | 2026-02-08 | 2026-02-10 | 2026-01-02 | 2026-05-25 |  | 8202238735 |  | 8202231382#LTSA Floating Crane SPM 165.0 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 40000000 | 0 | MA4-STA |  | T_FATAHY |  | 2026-02-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102354996 | 8202236532 |  | 8202231381#D_26 021P113A Motor High Temp | RU4-LOC2 | 021P113A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-05 | 2026-01-05 | 2102357966 | 8202241226 |  | 8202231380#26_hub kopling 011P103CM rusa | RU4-FOC2 | 011P103C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-05 | 2026-01-05 | 2102361444 | 8202238582 |  | 8202231379#Indikasi rusak valve 34-LG-03 | RU6-POC | 34-V-106/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/NR-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102357427 | 8202236522 |  | 8202231378#D_26 Pengambilan kawat rewind | RU4-LOC2 | 021P107B/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102356962 | 8202236526 |  | 8202231377#D_26 023P107A motor noise | RU4-LOC2 | 023P107A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102355461 | 8202236524 |  | 8202231376#D_26 Motor 024P-121A Noise | RU4-LOC2 | 024P121A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-05 | 2026-01-05 | 2102355840 | 8202241225 |  | 8202231375#26_017P103AM vibrasi | RU4-FOC2 | 017P103AM/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 12175000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102355597 | 8202237851 |  | 8202231374#TGH9_25 UP MON&INSP PERALATN | RU4-RFCUTL |  | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-17 | 2026-07-01 | 2026-11-20 |  | 8202235103 | 8202236165 | 8202231373#NRK_Retrofit Kontrol Sump Pum | RU5-E15111 | GM-34-63A/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/NR-C3H | 1178000000 | 0 | MA2-INT |  | FAUZANR |  | 2026-06-03 | PT02 |  | 3 | 2026-07-01 | PM |  | 004
| K401 | 2026-02-02 | 2026-04-08 | 2026-04-07 | 2026-12-07 | 2102354812 | 8202236245 |  | 8202231370#26_Perbaikan 054 LT 023 | RU4-UTL | 054LT023/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-08 | PT02 |  | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-08 | 2026-05-08 | 2026-12-22 | 2102354810 | 8202236246 |  | 8202231369#26_Perbaikan 054 LT 022 | RU4-UTL | 054LT022/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-05-08 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-08 | 2026-04-07 | 2026-12-07 | 2102354768 | 8202236247 |  | 8202231368#26_Perbaikan 054 LT 019 | RU4-UTL | 054LT019/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-08 | PT02 |  | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-21 | 2026-06-19 | 2026-12-30 | 2102356489 | 8202237304 |  | 8202231367#26_BV14 bocor | RU4-KPC | 84BV81B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-06-19 | PT02 |  | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-11 | 2026-03-10 | 2026-11-09 | 2102357830 | 8202236325 |  | 8202231366#26_Penunjunan Nan 004FT701 | RU4-TRML | 004FT701/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-11 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-11 | 2026-03-10 | 2026-11-09 | 2102357044 | 8202236326 |  | 8202231365#26_Penunjukkan Tidak Sesuai 1 | RU4-GTO | 180FT601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 11744430 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-11 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102356964 | 8202236289 |  | 8202231364#D26_025AI001 Penunjukkan erro | RU4-LOC2 | 025F101/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356337 | 8202241224 |  | 8202231362#26_Penunjukan 024FT037 kadang | RU4-LOC2 | 024FT037/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 64035663 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-14 | 2026-02-10 | 2026-12-01 | 2102355846 | 8202237310 |  | 8202231358#Body control valve korosi 260 | RU4-LOC3 | 260PV064/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-13 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102355842 | 8202236287 |  | 8202231357#D26_Perbaikan Dryer 14D650 | RU4-FOC1 | 14D650/00 | 50 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-04-15 | 2026-01-02 | 2026-05-25 | 2102361267 | 8202237751 |  | 8202231356#Penagihan LTSA PM Tangki Taha | RU6-ITP | 42-T-101A/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 200957000 | MA4-STA |  | MARSHAL |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-08 | 2026-01-08 | 2102355463 | 8202241223 |  | 8202231355#26_Perbaikan TST COB 101-TXI- | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 47400000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355181 | 8202241221 |  | 8202231353#26_021FT-001 penunjukan error | RU4-LOC2 | 021FT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 42690442 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102357964 | 8202241219 |  | 8202231352#26_[CR] Penggantian Belt 14K6 | RU4-FOC1 | 14K621B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1565000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355109 | 8202241217 |  | 8202231349#26_018LT030 penunjukan error | RU4-FOC2 | 018LT030/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 42690442 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-06 | 2026-01-06 | 2102355929 | 8202241215 |  | 8202231348#26_Mtl. Perbaikan Bocoran Roo | RU4-FOC1 | 13F1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 35077500 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-17 | 2026-03-09 | 2026-04-28 |  | 8202234901 |  | 8202231347#NRK_Perbaikan FO FGDS SS65-67 |  | CONTROLLERFGDS/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/NR-C3H | 89000000 | 0 | MA4-INT |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-03-09 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-01-19 | 2102361300 | 8202233373 |  | 8202231346#Perbaikan 13-K-101 | RU6-DHC | 13-K-101/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-06-02 | 2026-06-30 |  | 8202238612 |  | 8202231345#Penggantian Tabung FM-200 PP- | RU5-TBL | FM-2/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | ENG-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-11 | 2026-03-03 | 2026-12-30 | 2102356333 | 8202241213 |  | 8202231344#26_[CR] Penggantian mech seal | RU4-FOC1 | 11P7A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 142661000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-25 | 2102361560 | 8202233499 |  | 8202231343#Penggantian solenoid & positi | RU6-DHC | 22-V-109B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-02-11 | 2102362734 | 8202233826 |  | 8202231340#Pengadaan consumable material | RU6-UTL | 62-P-201D/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 3696 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102357480 | 8202241209 |  | 8202231339#26_[CR] Pompa 47P-507D macet | LOC1-UP4 | 47P507B/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 470853 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354916 | 8202241207 |  | 8202231338#26_[CR] Penggantian sight gla | RU4-FOC1 | 11P4A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-02 | 2026-01-02 |  | 8202237837 | 8202237810 | 8202231337#TGH23_23 TSA ConMon Instrumen | RU4-RFCC | 101FJB001/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 321310000 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-02 | 2026-04-02 | 2102360788 | 8202234683 |  | 8202231336#Pergantian Pintu hydraulic RP | RU5-E15112 | 41-AC-RPPK-BPP2/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 225000000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-02 | PM |  | 005
| K501 | 2026-02-03 | 2026-04-22 | 2026-01-02 | 2026-12-30 | 2102360813 | 8202237975 |  | 8202231335#Retubing E-202-04&Ganti Tube | RU5-D&W | E-202-04/00 | 60 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/NR-C2H | 495000000 | 420750000 | MA1-STA |  | BERNANDOP |  | 2026-02-11 | PT02 | 1 | 3 | 2026-01-02 | PM |  | 004
| K501 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-12-30 | 2102360830 | 8202237974 |  | 8202231334#Jasa Eddy Current Test E-202- | RU5-D&W | E-202-04/00 | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/25/B6/NR-C2H | 140000000 | 140000000 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102351288 | 8202232306 |  | 8202231333#PENGADAAN GASKET KEBUTUHAN SA | RU2-HOC | 140-H-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K501 | 2026-02-03 | 2026-05-08 | 2026-10-02 | 2026-10-16 | 2102360854 | 8202237973 |  | 8202231332#Sewa Crane 220 Ton pd Stop Un | RU5-D&W | E-202-04/00 | 60 | CLSD NMAT PRC SETC | 5MR | D15/25/B6/NR-C2H | 1 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357917 | 8202241205 |  | 8202231331#25_[CR] Pengadaan Pompa Assy | RU4-TRML | 30P107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-31 | 2026-01-09 | 2102352015 | 8202232705 |  | 8202231328#Suara Kasar | RU2-HCC | 212-EF-18A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 2034817 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-24 | 2026-01-06 | 2102350925 | 8202232360 |  | 8202231327#211-P-24B High Vibrasi | RU2-HCC | 211-P-24B/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 1715504 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-24 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-12-24 | 2026-05-19 | 2102350926 | 8202232356 |  | 8202231326#211-PG-6AR Perbaikan Gearbox | RU2-HCC | 211-PG-6/00 | 01 | CRTD CSER MACM PRC | 2RR | D12/25/B6/RT-D2H | 3456 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-24 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102355421 | 8202237834 |  | 8202231325#TGH1_25 UP Pipa GTO KLBC | RU4-RFCC | 106-ACF0004-4/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-03-09 | 2026-01-05 | 2026-01-20 | 2102362661 | 8202233288 |  | 8202231324#Perbaikan 32-PDI-092 | RU6-HSC | 32-PDT-092/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 23326900 | 23326900 | MA3-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-05 | 2026-01-20 | 2102361698 | 8202233404 |  | 8202231323#Perbaikan 12-FT-536A | RU6-DHC | 12-FT-536/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-05 | 2026-01-20 | 2102361777 | 8202233384 |  | 8202231322#Perbaikan 12-PT-756 | RU6-DHC | 12-PT-756/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-05 | 2026-01-20 | 2102361856 | 8202233391 |  | 8202231321#Perbaikan 12-PI-752 | RU6-DHC | 12-PT-752/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 13957143 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-30 | 2025-12-31 | 2102362617 | 8202233905 |  | 8202231320#MOC No. 735/HSC/X2014 | RU6-HSC | 23-LT-005/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 18 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-11 | 2026-01-06 | 2026-06-04 | 2102361280 | 8202233125 |  | 8202231319#Perbaikan lampu SBNP | RU6-ITP | 41-A-103/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 79087276 | 79075000 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-31 | 2025-12-31 | 2102362669 | 8202233227 |  | 8202231318#Perbaikan Bearing OB Pompa 15 | RU6-RCC | 15-P-102C/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 13 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-01-02 | 2026-12-31 |  | 8202238064 | 8202234908 | 8202231317#Tag 30 Pemeliharaan Sepeda Ki | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF GMPS NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 26295288 | 26295288 | WS-SG |  | MHAMDIBRD | 2026-06-09 | 2026-03-04 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2025-12-29 | 2025-12-29 |  | 8202238370 | 8202234916 | 8202231316#Tag 22 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-27 | 2025-12-27 |  | 8202238361 | 8202234972 | 8202231315#Tag 6 Pemb Ceceran Minyak & T |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-27 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-29 | 2025-12-29 |  | 8202238065 | 8202235501 | 8202231314#Tag 3 Pengerukan Lumpur Area | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238345 | 8202235092 | 8202231313#Tag 9 Sup Teknisi dan Operato | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-10-28 | 2025-10-28 |  | 8202238066 | 8202235318 | 8202231312#Tag 3 KV Listrik Area Oil Mov |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238343 | 8202234515 | 8202231311#Tag 17 Pemeliharaan Fire Exti | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-17 | 2102362667 | 8202233960 |  | 8202231310#Make Up Rocksalt 21-V-108 | RU6-DHC | 21-V-108/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 221830 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238330 | 8202234515 | 8202231309#Tag 16 Pemeliharaan Fire Exti | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238315 | 8202234515 | 8202231308#Tag 15 Pemeliharaan Fire Exti | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-03 | 2026-06-17 | 2026-01-02 | 2026-12-30 | 2102354609 | 8202237832 |  | 8202231307#Penggantian kabel receptacle | LOC1-UP4 | 47M509A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 100000 | 0 | MA1-LIS |  | WAHYUCATUR |  | 2026-03-30 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357429 | 8202241203 |  | 8202231306#25_[CR] 024E102C searpin no.5 | RU4-LOC2 | 024E102C/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1273080 | 1273080 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102354692 | 8202241201 |  | 8202231304#26_Pengg. piping inlet tanki | RU4-TRML | LN71-25A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-11 | 2026-03-30 | 2026-03-30 |  | 8202237972 | 8202236161 | 8202231303#Perbaikan Mechanical Seal Are | RU5-TBL | G-20-08A/00 | 60 | REL GMPS NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 32810000 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-10 | 2026-01-26 | 2026-01-26 | 2102355734 | 8202235387 |  | 8202231302#26_Perbaikan Transmitter 101L | RU4-RFCC | 101V521/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 149189625 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102355593 | 8202237830 |  | 8202231301#TGH7_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-30 | 2026-01-02 | 2026-12-30 | 2102355596 | 8202237828 |  | 8202231300#TGH9_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER GMCO NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102355594 | 8202237826 |  | 8202231299#TGH8_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102355595 | 8202237824 |  | 8202231298#TGH6_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102362615 | 8202233690 |  | 8202231296#Penggantian bearing pompa 055 | RU6-UTL | 055-A-101-P4A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 147900 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102362663 | 8202233039 |  | 8202231295#Perbaikan motor 23-P-901A | RU6-HSC | 23-P-901A-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 13 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2026-05-21 | 2102351751 | 8202232650 |  | 8202231294#Pengadaan Sight Glass Area HC | RU2-HCC | 212-P-9B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 3456 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102356486 | 8202241199 |  | 8202231293#25_[CR] Penggantian V-Belt XP | RU4-KPC | 81XV201A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 420000 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102357321 | 8202237821 |  | 8202231292#TGH6_25 UP PERB LIGHTING SYST | RU4-KPC | 80EE0032F-PNL/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 216484442 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102357325 | 8202237819 |  | 8202231291#TGH5_25 UP PERB LIGHTING SYST | RU4-KPC | 80EE0032F-PNL/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 189671940 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102355574 | 8202241197 |  | 8202231290#25_[CR] 012P102B - Noise pomp | RU4-FOC2 | 012P102/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 23940725 | 0 | MA2-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102357322 | 8202237817 |  | 8202231289#TGH4_25 UP PERB LIGHTING SYST | RU4-KPC | 80EE0032F-PNL/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 141408447 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102357326 | 8202237814 |  | 8202231288#TGH3_25 UP PERB LIGHTING SYST | RU4-KPC | 80EE0032F-PNL/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 173480991 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102357323 | 8202237812 |  | 8202231287#TGH2_25 UP PERB LIGHTING SYST | RU4-KPC | 80EE0032F-PNL/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 183788954 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-11 | 2025-12-11 | 2102358328 | 8202236050 |  | 8202231286#Kerusakan 93TI-098 INST-MA1 | RU4-SRU | 93TIT091/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-11 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-11 | 2025-12-11 | 2102358326 | 8202236047 |  | 8202231285#Kerusakan 93TI-099 INST-MA1 | RU4-SRU | 93TIT091/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-11 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-23 | 2025-12-23 | 2102357423 | 8202234952 |  | 8202231284#PSA Metering System Termin 20 |  |  | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-23 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357040 | 8202241195 |  | 8202231283#25_Perbaikan 14TI-524 | RU4-FOC1 | 14TT524/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-02 | 2026-01-02 | 2102356961 | 8202237810 |  | 8202231282#TGH22_23 TSA ConMon Instrumen | RU4-RFCC | 101FJB001/00 | 50 | REL CSER GMCO NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 258068000 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-29 | 2026-04-07 | 2102362496 | 8202234040 |  | 8202231281#Bocoran Lube Oil Trafo 14A-PT | RU6-RCC | 14A-PTR1-01A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 42726768 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-11 | 2025-11-19 | 2025-11-19 | 2102352524 | 8202234289 |  | 8202231280#Pengecatan Eksternal Tangki 9 | RU2S-KIL | 946-TK-06/00 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-19 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-02 | 2027-01-04 | 2102356909 | 8202237808 |  | 8202231279#TGH4_24 TSA Online Analyzer T | RU4-RFCC | 102FT049/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 2492800000 | MA6-INT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-02 | 2027-01-04 | 2102356907 | 8202237806 |  | 8202231278#TGH8_24 TSA DCS Honeywell RFC | RU4-RFCC | 101FJB001/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 715052000 | MA6-INT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102356905 | 8202237804 |  | 8202231277#TGH5_24 PM Field Instr ME II | RU4-RFCGTO | 105FT072/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 372827000 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-05 | 2026-01-05 | 2102361528 | 8202234008 |  | 8202231275#Indikasi rusak check valve ar | RU6-POC | 34-A-104-P101A-M/0 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/NR-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2026-01-02 | 2026-04-22 | 2102362401 | 8202238579 |  | 8202231274#Pengadaan Pompa 33-P-107B | RU6-HSC | 33-P-107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-15 | 2026-01-15 | 2102354859 | 8202237802 |  | 8202231271#Tagihan termin 17 - Perb. Eqp |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 47465700 | 47465700 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-15 | 2026-01-15 | 2102354855 | 8202237781 |  | 8202231269#Tagihan termin 16 - Perb. Eqp |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 62748700 | 62748700 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-15 | 2026-01-15 | 2102354910 | 8202237748 |  | 8202231268#Tagihan termin 15 - Perb. Eqp |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 53274600 | 53274600 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-23 | 2026-02-23 |  | 8202234620 |  | 8202231267#CHARGER BATTERAI SS V RPAL RU | RU5-UTL | RPALU/00 | 01 | CRTD CSER NMAT PRC | 5ER | D15/10/B6/RT1-P1NH | 0 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-23 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-11 | 2026-02-11 | 2102360060 | 8202234616 |  | 8202231266#CHARGER SSV RPAL RUSAK | RU5-UTL | 1AL/00 | 01 | CRTD CSER NMAT PRC | 5ER | D15/10/B6/RT1-SSNH | 0 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-11 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-29 | 2025-12-29 |  | 8202238295 | 8202235817 | 8202231265#Tag 7 Con Mon Peralatan Rotat |  |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-29 | 2025-12-29 |  | 8202238282 | 8202235817 | 8202231264#Tag 6 Con Mon Peralatan Rotat |  |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-17 | 2026-01-01 | 2026-12-31 |  | 8202238154 | 8202235152 | 8202231263#Tag 3 KV Sipil Area Selatan | RU3-ITP | 36-RJ-DER-10/00 | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 748182750 | 0 | GEN-STA |  | APUGUHA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-05 | 2026-05-06 | 2026-05-06 | 2102360927 | 8202235152 |  | 8202231262#Kontrak Volume Sipil Area Sel | RU3-ITP | 36-RJ-DER-10/00 | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-05-06 | PM |  | 045
| K701 | 2026-02-02 | 2026-03-08 | 2025-12-29 | 2025-12-29 | 2102358139 | 8202234910 |  | 8202231261#Pengadaan Gas Argon Ultra Hig |  |  | 50 | REL MACM PRC SETC | 7RT | D17/25/B6/RT-2-D1H | 43529420 | 0 | MA-ROT |  | YAYANHER |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K301 | 2026-02-04 | 2026-06-09 | 2025-12-23 | 2025-12-23 |  | 8202238273 | 8202234391 | 8202231260#Tag 3 TSA O2 Analyzer CDGP | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-07 | 2025-12-23 | 2025-12-23 |  | 8202238255 | 8202235263 | 8202231259#Tag TKDN Perb Jln Kilang PL S |  |  | 60 | TECO CNF PRT NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 045
| K301 | 2026-02-04 | 2026-04-27 | 2025-12-23 | 2025-12-23 |  | 8202238251 | 8202235502 | 8202231258#Tag TKDN KV Sipil Area Utara | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-04-27 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-10 | 2026-12-01 | 2102355520 | 8202235454 |  | 8202231257#26_Perbaikan Level Indikator | RU4-TRML | 31T7/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-02-13 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-22 | 2026-01-26 | 2026-01-26 | 2102354331 | 8202235492 |  | 8202231256#26_Penggantian Horen FGDS are | RU4-RFCGTO | 47AA-U47/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-10 | 2026-12-01 | 2102357915 | 8202235878 |  | 8202231255#Perbaikan Level Transmitter 1 | RU4-RFCGTO | 107LT-U107/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 4898274 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-02-13 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-23 | 2025-12-23 | 2102357421 | 8202234986 |  | 8202231254#Sewa CCTV Area Tanki 41,47 & | RU4-RFCGTO | 47T511A/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-23 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-14 | 2025-12-23 | 2025-12-23 | 2102357420 | 8202237735 |  | 8202231253#TGH37-38_22 Sewa CCTV Tanki 4 | RU4-RFCGTO | 47T511A/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 116661000 | 116661000 | MA3-INT |  | TYFFANIM |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-04 | 2025-11-04 | 2102352453 | 8202234288 |  | 8202231252#Perbaikan Isolasi Pipa 18 Inc | RU2S-KIL | 12PL946Y23-A1A1/00 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-24 | 2025-12-24 | 2102350923 | 8202232635 |  | 8202231251#Pengambilan Material Flexible | RU2-HOC | 140-V-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-24 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-12-24 | 2025-12-24 | 2102352257 | 8202234287 |  | 8202231250#101-P-5B indikasi high vibrat | RU2S-KIL | 101-P-5B/00 | 50 | REL NMAT PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-24 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2025-12-24 | 2025-12-24 | 2102352896 | 8202235352 |  | 8202231249#Penggantian kerangan butterly | RU3-CDL | 14-FCV-025/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-24 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-05-29 | 2102362494 | 8202233670 |  | 8202231248#Penggantian Control Valve 16- | RU6-RCC | 16-XV-501/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-10 | 2026-12-01 | 2102354572 | 8202236230 |  | 8202231247#TI untuk temp. cooler pompa p | RU4-KPC | 84P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-02-13 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-04 | 2026-01-02 | 2026-12-22 | 2102357422 | 8202237734 |  | 8202231246#TGH9_22 TSA ATG Endress Hause | RU4-TRML | 31LT-U31/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 0 | 0 | WS-INT |  | FATAHALFI |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-14 | 2026-02-26 | 2026-12-30 | 2102357329 | 8202237733 |  | 8202231245#TGH20-21_23 PSA Metering Syst | RU4-TRML | 004FT002/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 370681000 | 370681000 | MA3-INT |  | WAHYUCATUR |  | 2026-04-14 | PT02 |  | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-02 | 2026-12-30 | 2102357328 | 8202237732 |  | 8202231244#TGH18-19_23 PSA Metering Syst | RU4-TRML | 004FT002/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1015387000 | 1015387000 | MA3-INT |  | FARIZSETYANA |  | 2026-03-03 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102357320 | 8202237731 |  | 8202231243#TGH9_23 Tagihan TSA Fire Supp | RU4-FOC1 | 11FT001/00 | 50 | REL GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 60681000 | 60681000 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-02-03 | 2102362690 | 8202233593 |  | 8202231242#Penggantian Level Transmitter | RU6-HSC | 64-LT-002/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-12-31 | 2102354857 | 8202237730 |  | 8202231241#Tagihan termin 14 - Perb. Eqp | RU4-UTL | 055P101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 55416600 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-12-31 | 2102354853 | 8202237729 |  | 8202231240#Tagihan termin 13 - Perb. Eqp | RU4-UTL | 051E101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 53295000 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-01-02 | 2026-12-31 | 2102352082 | 8202238248 |  | 8202231236#Tag 7 Pem IPAL Domestik RU II | RU3-LKKK | 33-SH-IPAL/00 | 60 | REL GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-23 | 2025-12-23 | 2102352085 | 8202238247 |  | 8202231235#Tag 6 Pem IPAL Domestik RU II | RU3-LKKK | 33-SH-IPAL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-23 | 2025-12-23 | 2102352081 | 8202238067 |  | 8202231234#Tag 5 Pem IPAL Domestik RU II | RU3-LKKK | 33-SH-IPAL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-23 | 2025-12-23 | 2102352083 | 8202238246 |  | 8202231233#Tag 4 Pem IPAL Domestik RU II | RU3-LKKK | 33-SH-IPAL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-23 | 2025-12-23 | 2102352087 | 8202238068 |  | 8202231232#Tag 3 Pem IPAL Domestik RU II | RU3-LKKK | 33-SH-IPAL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-23 | 2025-12-23 | 2102352086 | 8202238069 |  | 8202231231#Tag 2 Pem IPAL Domestik RU II | RU3-LKKK | 33-SH-IPAL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-23 | 2025-12-23 | 2102352084 | 8202238070 |  | 8202231230#Tag 1 Pem IPAL Domestik RU II | RU3-LKKK | 33-SH-IPAL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-22 | 2025-12-30 |  | 8202232194 | 8202233926 | 8202231228#Tambahan Material Pipa Pernai | RU6-ITP | 42-PIPE/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 64 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-22 | PM |  | 005
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238245 | 8202234942 | 8202231227#Tag 18 TKDN PM Pre Heater Reb | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354626 | 8202241193 |  | 8202231226#25_PI fuel gas 89F201 rusak | RU4-KPC | 89F201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2256987 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354504 | 8202241191 |  | 8202231225#25_PI automizing steam 84F203 | RU4-KPC | 84F203/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1355534 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-01-05 | 2102362431 | 8202236682 |  | 8202231224#SPKR LTSA Patching Pipa Tahap | RU6-ITP | 42-PIPE/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 220341000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354579 | 8202241189 |  | 8202231223#25_PI fuel oil 87F201 cell A | RU4-KPC | 87F201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1203448 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-19 | 2025-12-02 | 2025-12-02 | 2102353126 | 8202234476 |  | 8202231222#NR_26 P-12 CDU III | RU3-CDGP | CD3-P-012/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | PASRILARIF |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354621 | 8202241187 |  | 8202231221#25_PI automizing staem 87F201 | RU4-KPC | 87F201/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2711068 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354623 | 8202241185 |  | 8202231220#25_PI fuel oil 87F201 cell C | RU4-KPC | 87F201/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 4813793 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354576 | 8202241183 |  | 8202231219#25_PI automizing steam di 85F | RU4-KPC | 85F201/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 5422136 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354574 | 8202241181 |  | 8202231217#25_PI Fuel oil di 85F201 rusa | RU4-KPC | 85F201/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 3610345 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-08 | 2026-01-08 | 2102357965 | 8202237728 |  | 8202231216#TGH1-2_24 TSA FGDS Sieger Hon | RU4-SRU | 90GD17/00 | 50 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-08 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-02 | 2027-01-04 | 2102357424 | 8202237727 |  | 8202231215#TGH27_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER GMCO NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 307214000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356832 | 8202241179 |  | 8202231214#25_[CR] Penggantian V-Belt 82 | RU4-KPC | 82E202KA/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 3375000 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-04 |  | 2025-12-23 | 2025-12-23 |  | 8202238563 |  | 8202231213#TGH25_Sewa Crane 50 Ton WS | RU4-WS | 037BD101/00 | 50 | CRTD NMAT PRC | 4MR | D14/25/B6/RTC-15-C2H | 125895000 | 0 | WS-KAB |  |  |  |  | PT02 |  | 2 | 2025-12-23 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-12-31 | 2102358131 | 8202237726 |  | 8202231212#PM Reciprocating Kompresor FO | RU4-FOC2 | 011K101A/01 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 54216400 | 54216400 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-23 | 2025-12-23 | 2102351382 | 8202232430 |  | 8202231209#Perbaikan 940 P 1B | RU2-UTL | 940-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 2513167 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-23 | 2025-12-23 |  | 8202233914 |  | 8202231208#Matl Slowmoving 11-P-109A | RU6-HSC | 11-P-109A-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2025-12-16 |  | 8202233913 | 8202234034 | 8202231207#Matl Slowmoving 15-P-102A | RU6-RCC | 15-P-102A/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-20 | 2025-11-19 | 2025-11-19 | 2102353230 | 8202238581 |  | 8202231206#N_Penggantian Local Display 2 | RU3-PP | 22-LT-1108/00 | 50 WAMA | CRTD CSER MACM PRC | 3IR |  | 0 | 0 | MA2-INT |  | ALEPDALITAN |  |  | PT02 |  | 2 | 2025-11-19 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-23 | 2025-12-30 | 2102362335 | 8202233026 |  | 8202231205#Perbaikan motor aerasi 63-A-3 | RU6-ITP | 63-A-301A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 41 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357507 | 8202241177 |  | 8202231204#25_Mtl. Gasket HE 14K1E1 dan |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-12 | 2026-01-12 | 2102362435 | 8202234073 |  | 8202231203#21-S-103A | RU6-DHC | 21-S-103A/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102357508 | 8202236410 |  | 8202231201#Penggantian Valve 16” 71T2 li | RU4-TRML | 71T2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-01 | 2026-07-30 |  | 8202234513 |  | 8202231200#PERBAIKAN LEVEL INDICATOR 202 | RU5-D&W | 202-LT-022/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-01 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102357509 | 8202237724 |  | 8202231199#TGH1_25_SCAFFOLD_REJUV_ISOLAS | RU4-RFCC | 104-WT0824-3-4/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 0 | 208858350 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-04-27 | 2025-12-18 | 2025-12-18 |  | 8202238071 | 8202235145 | 8202231198#Tagihan Ke- 17 KV Cleaning Co | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-04-27 | PM |  | 045
| K301 | 2026-02-06 | 2026-05-19 | 2025-12-23 | 2025-12-23 | 1102326359 | 8202238694 |  | 8202231197#Penggantian Battery Bank UPS | RU3-UTL | 62PL-UPS1-127-1/00 | 50 WAMA | CRTD MACM PRC | 3ER |  | 350000000 | 0 | MA2-LIS |  | MULYONO701 |  |  | PT02 |  | 2 | 2025-12-23 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-22 | 2025-12-30 | 2102362337 | 8202233926 |  | 8202231196#Material Pipa Pernaikan Dyes | RU6-ITP | 42-PIPE/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 64 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-22 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356766 | 8202241164 |  | 8202231195#25_24LT046 penunjukkan NaN | RU4-LOC1 | 24LT046/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 19250000 | 18950000 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354570 | 8202241162 |  | 8202231194#25_PI tandem seal pompa pada | RU4-KPC | 84P202A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1355534 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354471 | 8202241160 |  | 8202231193#25_PI fuel gas 84F201 CH rusa | RU4-KPC | 84F201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 11284933 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354474 | 8202241158 |  | 8202231192#25_PI fuel gas 84F201 IH-3 ru | RU4-KPC | 84F201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 9027947 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354477 | 8202241156 |  | 8202231191#25_PI fuel gas 84F201 IH-1 ru | RU4-KPC | 84F201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 6770960 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354501 | 8202241154 |  | 8202231190#25_PI fuel gas 84F201 IH-2 ru | RU4-KPC | 84F201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 11284933 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102354409 | 8202241151 |  | 8202231189#25_PI Fuel Gas di 82F202 rusa | RU4-KPC | 82F202/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1219906 | 0 | MA4-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-22 | 2025-12-22 | 2102362189 | 8202234100 |  | 8202231188#12-J-501ABCDE & 12-J-550ABCDE | RU6-DHC | 12-J-501/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-22 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-07 | 2025-12-17 | 2025-12-17 |  | 8202236728 | 8202235263 | 8202231187#Tagihan Ke-8 Pekerjaan Perbai |  |  | 60 | TECO CNF PRT NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-20 | 2026-01-02 | 2026-01-02 | 2102364375 | 8202235341 |  | 8202231185#Kontrak vol pekerjaan sipil L | RU3-LAB |  | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-04 | 2026-02-13 | 2025-12-22 | 2025-12-22 |  | 8202238562 | 8202238643 | 8202231179#TGH9_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | CRTD NMAT PRC | 4IR | D14/25/B6/RTC-10-C2H | 518699000 | 0 | MA6-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-22 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2025-12-22 | 2025-12-22 |  | 8202238561 | 8202238643 | 8202231178#TGH8_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | CRTD NMAT PRC | 4IR | D14/25/B6/RTC-10-C2H | 128302000 | 0 | MA6-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-22 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2025-12-22 | 2025-12-22 |  | 8202238560 | 8202238643 | 8202231177#TGH7_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | CRTD NMAT PRC | 4IR | D14/25/B6/RTC-10-C2H | 507993000 | 0 | MA6-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-22 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2025-12-22 | 2025-12-22 |  | 8202238559 | 8202238643 | 8202231174#TGH6_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | CRTD NMAT PRC | 4IR | D14/25/B6/RTC-10-C2H | 174048000 | 0 | MA6-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-22 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102356769 | 8202241148 |  | 8202231173#25_[PV] Belt fin fan putus 26 | RU4-LOC3 | 260E122BK/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 1200000 | 1170000 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102355808 | 8202241145 |  | 8202231168#25_[CR] Penggantian Filter Pe | RU4-KPC | 82K201B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2798172 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355141 | 8202241143 |  | 8202231160#25_[CR] Perbaikan Turbin 53P1 | RU4-UTL | 53P1B-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 56349808 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102354629 | 8202241140 |  | 8202231159#26_Pengg. piping inlet tanki | RU4-TRML | LN71-24A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2025-12-16 | 2102352391 | 8202234286 |  | 8202231158#PENGECEKAN GATE VALVE 101-T-1 | RU2S-KIL | 101-T-1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-10 | 2026-01-02 | 2026-08-26 | 2102362286 | 8202233197 |  | 8202231157#Perbaikan Control ijeksi Poly | RU6-UTL | 53-A-202B/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 977932 | 0 | MA4-LIS |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-19 | 2026-01-02 | 2026-01-02 | 2102354249 | 8202241136 |  | 8202231149#26_Perbaikan Perpipaan & Bord |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102358132 | 8202241120 |  | 8202231148#25_Control Room KPC dan 80SS2 | RU4-KPC | 80S201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 631896 | 0 | GEN-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-12-31 | 2102358186 | 8202237723 |  | 8202231143#Tagihan termin 3 Unit Price P | RU4-UTL | 052B102/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-22 | 2025-12-31 | 2102362246 | 8202233745 |  | 8202231142#Pengadaan Transmitter 58-PT-2 | RU6-UTL | 58-PT-202D/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 67 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-22 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102356307 | 8202237722 |  | 8202231141#TGH3_CIV_UP INSULASI EQUIPMEN | RU4-FOC2 | 011E109C1/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 0 | 1170779000 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102358134 | 8202237721 |  | 8202231140#TGH1_25_SCAFFOLD_REJUV_ISOLAS | RU4-RFCC | 101E523A/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-13 | 2026-01-13 | 2102357679 | 8202237720 |  | 8202231137#TGH1_SIP_UP Pagar Tahun 2025 | RU4-UTL | 050JL08/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 775018000 | GEN-SIP |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-13 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102356600 | 8202237719 |  | 8202231136#TGH1_REJUV_ISOLASI_PIP_MA7 | RU4-RFCC | 105-AM0002-2/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-04 | 2026-06-18 | 2026-03-06 | 2026-12-30 | 2102357676 | 8202238558 |  | 8202231135#TGH1_Unit Price UTL Camp Tahu | RU4-UTL | 050JL08/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 1244078000 | 1057466300 | GEN-SIP |  | FARIZSETYANA |  | 2026-03-06 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-04 |  | 2025-12-10 | 2025-12-10 |  | 8202238557 | 8202237691 | 8202231134#TGH19_Building Management Ser | RU4-K3LL | FT34/00 | 50 | CRTD NMAT PRC | 4MR | D14/25/B6/RTC-15-C2H | 4056190 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2025-12-10 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-01-02 | 2102356864 | 8202241117 |  | 8202231133#25_85P205B Motor Noise | RU4-KPC | 85P205B/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 403950 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102353976 | 8202236558 |  | 8202231132#D_25 Shoot blower macet 260ME | RU4-LOC3 | 260ME151-SBL-M1/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-04 | 2026-02-13 | 2025-11-21 | 2025-11-21 |  | 8202238556 | 8202237557 | 8202231131#TGH1&2_OLLS 2025 |  |  | 50 | CRTD NMAT PRC | 4MR |  | 16837344 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-21 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357354 | 8202241115 |  | 8202231130#25_Pengadaan Kontaktor 47P502 | RU4-RFCGTO | 47P502B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355399 | 8202241113 |  | 8202231129#25_Pengadaan kontaktor 47P511 | RU4-RFCGTO | 47P511BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355398 | 8202241110 |  | 8202231128#25_Pengadaan kontaktor 47P501 | RU4-RFCGTO | 47P501AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356084 | 8202241107 |  | 8202231127#25_Penggantian Breaker Loadin | RU4-TRML | 70CIB1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-6-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-04-27 | 2025-12-17 | 2025-12-17 |  | 8202238240 | 8202235145 | 8202231125#Tagihan Ke- 18 Termin TKDN Pe | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-04-27 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238072 | 8202234972 | 8202231123#Tag 5 Pemb Ceceran Minyak & T |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-03 | 2026-06-05 | 2026-01-13 | 2026-01-13 | 2102353895 | 8202237718 |  | 8202231122#TGH1_RT LOADING UNLOADING COL |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA4-STA |  | HERIOBM |  | 2026-02-11 | PT02 |  | 3 | 2026-01-13 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355173 | 8202241104 |  | 8202231121#25_[PV] Pengadaan Lubricator | RU4-FOC1 | 14K602AMP5/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-06-12 |  | 8202236686 | 8202238734 | 8202231120#SPKR 6 Table Volume Tanki | RU6-ITP | 42-T-206/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 54670000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-06-12 |  | 8202236688 | 8202238734 | 8202231119#SPKR 5 Table Volume Tanki | RU6-ITP | 42-T-206/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 66665000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-05-25 | 2026-05-25 |  | 8202238073 | 8202234908 | 8202231118#Tag 29 Pemeliharaan Sepeda Ki | RU3-WS | BEN-TOOL/00 | 60 | CLSD NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-19 | 2025-12-19 | 2102351795 | 8202232464 |  | 8202231117#Perbaikan 310-CM-3 | RU2-HSC | 310-C-3A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 4109000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-19 | PM |  | 003
| K401 | 2026-02-03 | 2026-05-21 | 2026-01-02 | 2027-01-04 | 2102358184 | 8202237716 |  | 8202231116#TGH#5_CAT_MA2 | RU4-LOC2 | LN21-1001C/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 0 | 172058000 | MA2-STA |  | ALFIANRH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357718 | 8202241101 |  | 8202231113#25_[CR] Perbaikan Pompa 54WS2 | RU4-UTL | 54WS201P1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 265959800 | 265959800 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102354939 | 8202237715 |  | 8202231112#TGH1_REJUV_ISOLASI_PIP_MA2 | RU4-FOC2 | LN11-1001C/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 327733000 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-06-19 | 2026-02-02 | 2026-12-30 |  | 8202237714 | 8202234792 | 8202231111#TGH1_25_SCAFFOLD_REJUV_ISOLAS | RU4-KPC | 82E201A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 646637000 | MA4-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-02-05 | 2026-06-10 | 2026-12-21 | 2026-12-21 | 2102351251 | 8202238654 |  | 8202231110#Perbaikan panel SWGR SWS#5, 6 | RU2-UTL | 560-SWG-5BB12/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 2783200 | 0 | MA3-LIS |  | DEDISUKMANA |  | 2026-02-07 | PT02 |  | 3 | 2026-12-21 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-19 | 2025-11-19 | 2102351849 | 8202232275 |  | 8202231109#kebutuhan material listrik MA | RU2-ITP | 690-PX-2/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-19 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-18 | 2025-12-18 |  | 8202238236 | 8202235364 | 8202231108#Tagihan Ke- 1 Pekerjaan Perba |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 |  | 3 | 2025-12-18 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-07 | 2026-01-01 | 2026-01-01 | 2102352739 | 8202235364 |  | 8202231107#Kontr.Vol.Perb.Bocoran Dindin |  |  | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-07 | 2025-12-17 | 2025-12-17 |  | 8202238074 | 8202235318 | 8202231106#Tagihan Ke- 2 Pekerjaan Kontr |  |  | 60 | TECO CNF PRT NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-01-02 |  | 8202237708 |  | 8202231105#Perbaikan FD Fan 52B3K1 | RU4-UTL | 52B3K/00 | 50 WAMA | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 550000000 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102358512 | 8202238007 |  | 8202231104#LTSA Electrical Instrument |  |  | 50 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D2H | 1 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2025-12-18 | 2025-12-18 | 2102356883 | 8202241098 |  | 8202231103#25_[CR] Perbaikan bocoran pom | RU4-TRML | 46P1B-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 1050003 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-18 | 2025-12-18 |  | 8202237707 | 8202237636 | 8202231102#TGH2_25 UP Pipa & Acc UTL RFC | RU4-RFCC | 151-FG0003-8/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 045
| K601 | 2026-02-08 | 2026-02-10 | 2026-01-02 | 2026-06-12 |  | 8202238734 |  | 8202231101#SPKR 4 Table Volume Tanki | RU6-ITP | 42-T-206/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 88824000 | 88824000 | MA4-STA |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354999 | 8202241095 |  | 8202231100#25_[CR] Perbaikan Pompa 103P5 | RU4-RFCC | 103P514B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102358210 | 8202241092 |  | 8202231099#26_Penggantian Insulation Gas | RU4-TRML | 32T103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 65650125 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-05 | 2026-01-02 | 2026-01-02 | 2102353891 | 8202234792 |  | 8202231098#RK_26-RT scafolding untuk aks | RU4-KPC | 82C201/00 | 50 | REL CSER GMCO NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | SAMSUDINH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355168 | 8202241089 |  | 8202231096#26_Perb. Valve DBB Bypass Met |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102356836 | 8202241069 |  | 8202231095#25_belt 82E202AM 5V-2000 3 ja | RU4-KPC | 82E202KA/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2891761 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-20 | 2026-05-18 | 2026-12-30 | 2102351051 | 8202238449 |  | 8202231094#RK0132 PENGADAAN PORTABLE SUB | RU2-UTL | 560-SW33-INC-TY/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SATRIAAGUNG |  | 2026-02-10 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-18 | 2025-12-30 | 2102362083 | 8202233582 |  | 8202231089#Penggantian Microfilter 21-S- | RU6-DHC | 21-S-103B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 90 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-18 | 2025-12-30 | 2102361974 | 8202233849 |  | 8202231088#Pembuatan Bak Sampel Avtur | RU6-DHC | 21-S-103B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 90 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K202 | 2026-02-02 |  | 2025-12-12 | 2025-12-12 | 2102352400 | 8202234285 |  | 8202231087#KEBOCORAN MECH SEAL 946-P1A | RU2S-KIL | 946-P-1A/00 | 01 | CRTD NMAT PRC | 2RS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  |  |  |  | PT02 |  | 2 | 2025-12-12 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-18 | 2025-12-18 |  | 8202237706 | 8202237519 | 8202231086#TGH3 UP Int Cleaning Tank A70 | RU4-TRML | 71T6/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-29 | 2025-12-29 | 2102351478 | 8202232596 |  | 8202231085#Penggantian Bearing 100-P-5B | RU2-HSC | 100-P-5B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 3315500 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2025-12-29 | 2102361694 | 8202232169 |  | 8202231084#Upgrade lampu PJU area Oil Mo | RU6-ITP | 42-T-404E/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 193 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-18 | 2025-12-18 | 2102351233 | 8202232324 |  | 8202231083#212-F1 Rusak | RU2-HCC | 212-F-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-17 | 2026-01-05 | 2102362149 | 8202233899 |  | 8202231082#Normalisasi lampu sorot area | RU6-ITP | 63-A-310D/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 260 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102357637 | 8202237705 |  | 8202231081#TGH2_23 Penyehatan Metering S | RU4-RFCGTO | 47MP012/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355753 | 8202241067 |  | 8202231080#25_Kerusakan Horn FGDS 47AA01 | RU4-RFCGTO | 47AA-U47/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 19600000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356959 | 8202241065 |  | 8202231077#25_[CR] 048P-104A/B mech seal | RU4-FOC2 | 019P122A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 8418812 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2025-12-17 | 2025-12-17 | 2102358513 | 8202234892 |  | 8202231076#Non Rutin Maintenance Desembe |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/NR-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-17 | 2025-12-17 | 2102351237 | 8202232231 |  | 8202231075#Line Cold Bottom ke CBA Bocor | RU2-HCC | 212-E-12A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K202 | 2026-02-02 |  | 2025-12-12 | 2025-12-12 | 2102352396 | 8202234284 |  | 8202231073#POMPA TIDAK BERFUNGSI 101-P4C | RU2S-KIL | 101-P-4C/00 | 01 | CRTD NMAT PRC | 2RS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  |  |  |  | PT02 |  | 2 | 2025-12-12 | PM |  | 003
| K202 | 2026-02-02 |  | 2025-12-12 | 2025-12-12 | 2102352395 | 8202234283 |  | 8202231072#KEBOCORAN MECH SEAL 101-P4B | RU2S-KIL | 101-P-4B/00 | 50 | CRTD CSER MACM PRC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  |  |  |  | PT02 |  | 2 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-26 | 2102361696 | 8202233522 |  | 8202231071#Penggantian Pressure Switch 5 | RU6-UTL | 52-B-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 6864 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-10 | 2026-01-02 | 2026-04-08 | 2102361819 | 8202233535 |  | 8202231070#Penggantian Press Gauge 15-SL | RU6-RCC | 15-SLV-102/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 5 | 0 | MA1-INT |  | AHMADAKHYAR |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-30 | 2102362141 | 8202233715 |  | 8202231069#Penggantian Actuator 22-PV-80 | RU6-DHC | 22-PV-803/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2025-12-30 | 2102362030 | 8202233480 |  | 8202231068#Penggantian thermocouple 32-A | RU6-HSC | 32-F-104/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 115 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-05 | 2026-01-05 | 2102353588 | 8202237704 |  | 8202231065#TGH1_Pemeliharaan Peralatan K | RU4-TRML | 70AR1/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-17 | 2025-12-17 | 2102355072 | 8202234463 |  | 8202231064#Pengadaan proteksi relay 11P2 | RU4-FOC1 | 11P2BM/00 | 50 WAMA | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2025-12-23 | 2102362039 | 8202233468 |  | 8202231061#Penggantian Transmitter 16-PI | RU6-RCC | 16-K-102A/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 78 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-04 | 2026-02-02 | 2026-12-30 |  | 8202237703 | 8202237603 | 8202231060#TGH7_24 Jasa LTSA Fire Truck | RU4-WS | FL51/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 18238799 | 15502979 | WS-KAB |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-10 | 2025-12-17 | 2025-12-17 | 2102356602 | 8202237702 |  | 8202231059#TGH1_SIP_UP Parit 2024 | RU4-TRML | 70AR1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 896198000 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2025-12-17 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2025-12-30 | 2102362032 | 8202234034 |  | 8202231056#Cons Mat Penggantian Pompa 15 | RU6-RCC | 15-P-102A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 115 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356955 | 8202241062 |  | 8202231055#25_[CR] 011P103BT Bearing def | RU4-FOC2 | 011P103B-T/00 | 60 WAMA | REL CSER GMCO GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 135000000 | 135000000 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-26 | 2026-03-26 | 2026-03-03 | 2026-10-05 |  | 8202241885 | 8202241062 | 8202231055#25_[CR] 011P103BT Bearing def | RU4-FOC2 | 011P103B-T/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 56136529 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-26 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-02-03 | 2026-05-12 | 2026-01-15 | 2026-01-15 |  | 8202237971 | 8202238445 | 8202231054#Fabrikasi Suction Bell Sump P | RU5-D&W | G-34-53/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 25500000 | 25500000 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K201 | 2026-02-01 | 2026-05-19 | 2026-01-02 | 2026-01-02 | 2102351927 | 8202232652 |  | 8202231052#Pengadaan rubber hose Area Je | RU2-ITP | 990-PX-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 216068160 | 0 | MA4-STA |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-04 | 2026-06-18 | 2025-12-16 | 2026-12-30 | 2102357673 | 8202238031 |  | 8202231051#TGH1_SIP_Stripping Area 70 | RU4-TRML | 70AR1/00 | 50 | REL GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 801636000 | 801636000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-05 | PT02 |  | 3 | 2025-12-16 | PM |  | 045
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-02 | 2026-12-30 | 2102357588 | 8202237701 |  | 8202231049#TGH7_SIP_Pemotongan Rumput 20 | RU4-TRML | 30P108B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 807596000 | MA3-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-03-03 | 2102362786 | 8202233145 |  | 8202231044#Perbaikan Junction Box All Ar | RU6-UTL | 53-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1924680 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-09 | 2026-01-02 | 2026-07-13 | 2102361632 | 8202238447 |  | 8202231043#Perbaikan Trafo TR-18 | RU6-UTL | GROUNDSYS-57/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/NR-C2H | 300000001 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-09 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-03 | 2026-02-07 | 2026-01-02 | 2027-01-20 | 2102359401 | 8202237970 |  | 8202231042#Jasa Perhitungan RLA Boiler H |  |  | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/NR-C2H | 299970000 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-06 |  | 8202233578 |  | 8202231040#Penggantian Module Bentley Nv | RU6-HSC | 32-K-102B-A1-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-25 | 2026-05-19 | 2026-12-30 | 2102356951 | 8202234984 |  | 8202231039#Power Supply Metering Pertama | RU4-TRML | 65BD1OU1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-05-25 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-18 | 2026-02-18 | 2026-11-26 | 2102358104 | 8202238590 |  | 8202231038#26_perbaikan Transmitter 90PI | RU4-SRU | 90PIT105/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-01-02 | 2027-01-04 | 2102358083 | 8202237700 |  | 8202231037#TGH6_24 PM Field Instrument M | RU4-KPC | 80FT205/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-05 | 2026-05-26 | 2026-12-02 | 2026-12-02 | 2102351269 | 8202238629 |  | 8202231034#RK0106 TSA ALAT UV VIS SPECTR | RU2-LAB | LAB-GAS-21/00 | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 110000000 | 0 | WS-IN1 |  | DONITGN |  | 2026-05-06 | PT02 |  | 3 | 2026-12-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-29 | 2026-02-03 | 2026-12-30 | 2102353896 | 8202237699 |  | 8202231032#RK_25-RT FIRE PROOFING | RU4-KPC | LN82FCR8001MS01/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 847861000 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2025-12-16 | 2102361942 | 8202233944 |  | 8202231031#Material Catridge Filter 21-S | RU6-DHC | 21-S-103A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-18 | 2026-01-02 | 2026-12-31 |  | 8202234394 | 8202237713 | 8202231030#Mat'l Rejuvenate Line UTL Wat | RU5-UTL | PIPA-WTP-PCR/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/NR-C2H | 360246336 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 001
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2025-12-16 | 2102351888 | 8202232371 |  | 8202231029#Pompa High Vibrasi | RU2-HSC | 200-P-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 334219 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2025-12-16 | 2102351982 | 8202232557 |  | 8202231028#Penggantian Filter KOF DGS | RU2-HSC | 300-C-1/00 | 60 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-05 | 2025-12-05 |  | 8202238231 | 8202235105 | 8202231027#Tag 8 Mekanik CDL, OM, UTL SG |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102353128 | 8202234440 |  | 8202231026#NR26_P-62-904A Bocor Mech Sea | RU3-CDGP | P-62-904A/00 | 50 WAMA | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102353129 | 8202234435 |  | 8202231025#NR26_P-62-905B Bocor Mech Sea | RU3-CDGP | P-62-905B/00 | 50 WAMA | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355332 | 8202241060 |  | 8202231024#25_Penggantian Bearing 33M4 | RU4-TRML | 33M4M/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 261750 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355193 | 8202241058 |  | 8202231023#25_Perbaikan bearing motor po |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 27016002 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102357657 | 8202241031 |  | 8202231022#25_Perbaikan motor border 73M | RU4-TRML | 73MD5M/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 693300 | 0 | MA3-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102357654 | 8202241028 |  | 8202231021#25_Perbaikan motor border 73B | RU4-TRML | 73BD6M/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 693300 | 0 | MA3-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2025-12-01 | 2025-12-01 | 2102358107 | 8202241025 |  | 8202231020#25_[CR] Ganti Catridge Filter | RU4-SRU | 91K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 48489000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102357487 | 8202241022 |  | 8202231019#25_Perbaikan motor border 72M |  |  | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 693300 | 0 | MA3-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-15 | 2025-12-29 | 2102361940 | 8202233061 |  | 8202231018#Perbaikan motor 14-P-601A | RU6-DHC | 14-P-601A/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 108 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102357486 | 8202240997 |  | 8202231017#25_Perbaikan motor border 72B |  |  | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 693300 | 0 | MA3-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354767 | 8202240981 |  | 8202231016#25_Penggantian bearing motor |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 2375383 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-15 | 2025-12-30 | 2102361976 | 8202233002 |  | 8202231015#Perbaikan Pompa 11-P-109B | RU6-HSC | 11-P-109B/01 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 128 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2025-12-29 | 2102361978 | 8202233419 |  | 8202231014#Perbaikan 11-FT-402 | RU6-HSC | 11-FT-402/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 103 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102358324 | 8202240955 |  | 8202231013#25_[CR] Kerusakan Coupling 91 | RU4-SRU | 91P403B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238229 | 8202235263 | 8202231012#Tag 7 Perbaikan Jalan Kilang |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102358322 | 8202240952 |  | 8202231011#25_[CR] Kerusakan Coupling 91 | RU4-SRU | 91P403A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-29 | 2025-12-29 | 2102351525 | 8202232253 |  | 8202231010#Perbaikan Mechanical Seal | RU2-HSC | 300-P-3A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 3454126 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-17 | 2026-03-17 | 2026-12-30 | 2102354879 | 8202240949 |  | 8202231009#25_[CR] Perbaikan mechanical | RU4-FOC1 | 10P2/00 | 60 | CLSD CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA1-ROT |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102358072 | 8202240946 |  | 8202231006#25_Pengadaan Coupling Assy 13 | RU4-FOC1 | 13P4A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102354450 | 8202240943 |  | 8202231005#25_Perbaikan Jalur kabel lamp |  |  | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 5325000 | 0 | MA3-LIS |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2025-12-05 | 2025-12-05 |  | 8202238030 | 8202234916 | 8202231004#Tag 21 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-11 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-05 | 2026-02-11 | 2025-12-05 | 2025-12-05 |  | 8202238648 | 8202235629 | 8202231003#Tagihan Ke- 4 Pekerjaan Hose |  |  | 60 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-15 | 2025-12-15 | 2102354889 | 8202237698 |  | 8202231000#TGH 1_25 UP Cleaning SWD Jetp | RU4-UTL | 054FE219/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-15 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-01 | 2102361484 | 8202233461 |  | 8202230999#Penggantian Transmitter 37-PI | RU6-POC | 37-F-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-11 | 2102361334 | 8202233460 |  | 8202230998#Penggantian Transmitter 37-PT | RU6-POC | 37-PT-021A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238075 | 8202234908 | 8202230997#Tag 28 Pemeliharaan Sepeda Ki | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K601 | 2026-02-02 | 2026-03-03 | 2026-03-03 | 2026-07-24 |  | 8202233823 | 8202233866 | 8202230995#Pengadaan CSS & LBS SS 01 (DC | RU6-UTL | SS-01/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-15 | 2025-12-15 |  | 8202237697 | 8202237657 | 8202230994#TGH2_SIP_Pengecetan MA 1 2024 | RU4-FOC1 | LN12-1055LA/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 100 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-15 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-08-24 | 2102361972 | 8202233866 |  | 8202230992#Pemanfaatan Listrik PLN untuk | RU6-UTL | SS-01/00 | 01 | CRTD NMAT PRC | 6ER | D16/26/B6/RT-C2H | 19800 | 0 | MA4-LIS |  | T_FATAHY |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 004
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-05 | 2025-12-05 |  | 8202238222 |  | 8202230990#Tag 18 PM CM Rot & Elec. PT K |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-07 | 2025-11-17 | 2025-11-17 |  | 8202237696 | 8202237676 | 8202230989#TGH_TKDN_UP Rejuv Isolasi MA | RU4-RFCC | 105-WT0827-3-4/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 100 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-01-01 | 2026-12-30 |  | 8202238062 |  | 8202230988#Tag 59 Sewa Beli 20 Unit ATG | RU3-ITP | LT-A-003/00 | 60 | REL GMCO NMAT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 139666666 | 0 | MA4-INT |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-01-01 | 2026-12-31 |  | 8202238061 |  | 8202230987#Tag 58 Sewa Beli 20 Unit ATG | RU3-ITP | LT-A-003/00 | 60 | REL NMAT PRC SETC | 3IR | D13/26/B6/NR-2-D2H | 139666666 | 0 | MA4-INT |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2025-12-02 | 2025-12-02 | 2102354815 | 8202240919 |  | 8202230985#25_[CR] Shim coupling 22P4B p | RU4-LOC1 | 22P4B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 9000000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-03-26 | 2026-03-12 | 2026-09-17 | 2102361293 | 8202238444 |  | 8202230984#Pemasangan Fire Damper di SS- | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 300000001 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-03-12 | PT02 |  | 3 | 2026-03-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102354813 | 8202240916 |  | 8202230983#25_[CR] Shim coupling 21P10B | RU4-LOC1 | 21P10/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 5594772 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-04 | 2025-12-23 | 2102361635 | 8202233230 |  | 8202230982#Perbaikan bearing motor 42-P- | RU6-ITP | 42-P-903-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 179 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-27 | 2025-12-22 | 2102361405 | 8202233046 |  | 8202230981#Perbaikan Motor 19P112A | RU6-RCC | 19-P-112A-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 230 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K601 | 2026-02-02 | 2026-03-09 | 2026-03-09 | 2026-06-03 | 2102361449 | 8202234050 |  | 8202230980#39-FV-003 indikasi positioner | RU6-POC | 39-FV-011/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 48236464 | 48236464 | MA3-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-13 | 2026-01-02 | 2026-01-02 | 2102356645 | 8202240913 |  | 8202230979#25_[CR] Perbaikan Pompa 38P11 | RU4-TRML | 38P113B/00 | 50 | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 12162350 | 12162350 | MA3-ROT |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-03-11 | 2026-03-11 | 2026-04-30 | 2102361521 | 8202233501 |  | 8202230978#Penggantian smart positioner | RU6-HSC | 33-FV-032/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 144709392 | 144709392 | MA3-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-11 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238218 | 8202234972 | 8202230977#Tag 4 Pemb Ceceran Minyak & T |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238213 | 8202235140 | 8202230976#Tag 3 Pekerjaan Mekanik Area | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K601 | 2026-02-02 | 2026-03-09 | 2026-01-02 | 2026-02-13 | 2102361661 | 8202233821 |  | 8202230975#Pengadaan dan penggantian 33- | RU6-HSC | 33-FT-032/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 16888382 | 16888382 | MA3-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-04-15 | 2102361732 | 8202233243 |  | 8202230974#Perbaikan Analog Output | RU6-RCC | 15-A-107A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1024 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-01-29 | 2102361888 | 8202232850 |  | 8202230973#Perbaikan Transmitter 15-FSLL | RU6-RCC | 15-FT-591A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 384 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-29 | 2025-12-29 | 2102351333 | 8202232666 |  | 8202230971#Pengadaan Membrane Coupling | RU2-HCC | 702-P-4B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K401 | 2026-02-05 | 2026-06-18 | 2026-02-03 | 2026-12-30 | 2102358087 | 8202238653 |  | 8202230970#TGH1_25 TSA CEMS UTL II & GT | RU4-UTL | 520B601/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1516695000 | 1516695000 | MA5-INT |  | FARIZSETYANA |  | 2026-03-02 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-13 | 2026-04-28 | 2026-12-15 | 2102357013 | 8202234757 |  | 8202230969#Temperature 024TE-113B alarm | RU4-LOC2 | 024K102/00 | 50 WENG | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-13 | PT02 |  | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102358259 | 8202240910 |  | 8202230968#25_022TV-131 status INIT | RU4-LOC2 | 022TV131/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2025-12-12 | 2025-12-30 | 2102361523 | 8202237749 |  | 8202230967#Maintenance Bawah Air SPM & J | RU6-UTL | 56-CT-101A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356389 | 8202240907 |  | 8202230966#25_[CR] Perbaikan pompa injec | RU4-RFCUTL | 154A503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-09 | 2025-12-09 | 2102356087 | 8202237695 |  | 8202230964#TGH4_24 TSA Mercury Analyzer | RU4-FOC2 | 30BD12EE0012C/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K601 | 2026-02-03 |  | 2025-12-12 | 2026-01-13 | 2102361738 | 8202237746 |  | 8202230961#Pemb LTSA DCS Centum VP&ESD T | RU6-ITP | DCSOFFSITE/00 | 50 | CRTD NMAT PRC | 6IR | D16/25/B6/NR-C2H | 531887500 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-12-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-02 | 2026-06-30 |  | 8202234350 |  | 8202230959#Perbaikan Water Meter Apartem | RU5-UTL | WTP1-INT/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 15100000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355081 | 8202240905 |  | 8202230958#25_[CR] Perbaikan 13P7 | RU4-FOC1 | 13P7/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 22158600 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355018 | 8202240902 |  | 8202230957#25_[CR] Perbaikan 13P3 | RU4-FOC1 | 13P3/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 55862887 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-29 | 2026-01-13 | 2102361851 | 8202233170 |  | 8202230955#Perbaikan Fin Fan 36-E-101-J2 | RU6-POC | 36-E-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C3H | 141 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-20 | 2025-12-12 | 2025-12-15 | 2102357055 | 8202240899 |  | 8202230953#25_Penggantian mechanical sea | RU4-FOC1 | 11P22A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 15 | 0 | MA1-ROT |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357945 | 8202240896 |  | 8202230952#25_[PV] Pengadaan sight glass | RU4-FOC1 | 11P3/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 11067692 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357847 | 8202240893 |  | 8202230950#25_[CR] 011K101A pompa lubric | RU4-FOC2 | 011K101A/01 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 160000000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354031 | 8202240890 |  | 8202230949#25_[CR]Ganti gelas pelumas ti | RU4-SRU | 94P402A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357059 | 8202240887 |  | 8202230948#25_Kerusakan 90PI-105 INST-MA | RU4-SRU | 90PIT105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-09 | 2025-12-24 |  | 8202233788 | 8202233789 | 8202230946#Pengadaan Material Nataru Uni | RU6-HSC | 32-K-101/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 154 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355821 | 8202240884 |  | 8202230945#25_[CR] Membran coupling ront | RU4-LOC3 | 260P151A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 13920000 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-03-26 | 2102362354 | 8202233476 |  | 8202230943#Penggantian Thermometer Dial | RU6-HSC | 31-K-101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-11 | 2025-12-11 | 2102358266 | 8202240881 |  | 8202230942#25_Pengadaan Block Vlv bypass | RU4-RFCGTO | 105FI-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-11 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-03-30 | 2102362352 | 8202233477 |  | 8202230941#Penggantian Thermometer Dial | RU6-HSC | 31-K-101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-26 | 2102362307 | 8202233736 |  | 8202230940#Pengantian Thermometer Dial 3 | RU6-HSC | 31-K-101B-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-03 | 2025-12-03 | 2102354329 | 8202237344 |  | 8202230939#86C202 isolasi rusak total - | RU4-KPC | 86C202/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 29660632 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 045
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-02 | 2027-01-21 |  | 8202238659 |  | 8202230938#Modifikasi Line Produksi LPG | RU4-TRML | LN47-1001CC/00 | 50 | CRTD NMAT PRC | 4MR |  | 2020000000 | 0 | MA7-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-09 | 2025-12-09 |  | 8202237694 | 8202238259 | 8202230937#TGH1_REJUV_ISOLASI_PIP_MA4 | RU4-KPC | LN39-DW8001MS24/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-09 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-11 | 2025-12-11 | 2102351387 | 8202232641 |  | 8202230936#Pengambilam material press ga | RU2-ITP | 945-T-32/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-23 | 2026-02-23 | 2102351792 | 8202232697 |  | 8202230934#Perbaikan 940 -B - 3 | RU2-UTL | 940-B-3/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/NR-D2H | 597849 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-05 | 2025-11-05 | 2102355169 | 8202237693 |  | 8202230933#TGH1_25 TSA CEMS UTL II dan S | RU4-UTL | 052B101-1/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-10 | 2025-12-30 | 2102361407 | 8202232754 |  | 8202230932#Readiness Filter Lube Oil RCC | RU6-RCC | 15-K-101/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 166 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-10 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-05 | 2025-12-05 |  | 8202238209 | 8202235817 | 8202230931#Tag 5 Con Mon Peralatan Rotat |  |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-11 | 2025-12-11 | 2025-12-11 |  | 8202234282 | 8202234177 | 8202230930#Penggantian Pipa Raw Water Se | RU2S-KIL | 946-LK3-PIPING/00 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102355650 | 8202240878 |  | 8202230929#25_[CR] Penggantian LO Sight | RU4-FOC1 | 11P2A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 5533846 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2025-12-24 | 2102361524 | 8202233235 |  | 8202230928#Perbaikan Bearing Blade 33-E- | RU6-HSC | 33-E-118I1/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C3H | 166 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-10 | 2025-12-10 | 2102351520 | 8202232463 |  | 8202230925#Perbaikan 310-FR-382 | RU2-HSC | 310-CM-2A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-10 | PM |  | 001
| K202 | 2026-02-02 | 2026-02-20 | 2025-12-10 | 2025-12-10 |  | 8202234281 | 8202234209 | 8202230924#Pemeliharaan Pompa di Kilang | RU2S-KIL | 101-P-6B/00 | 60 | REL NMAT PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 750000000 | 0 | MAS-ME1 |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2025-12-10 | PM |  | 001
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-02-13 | 2102361817 | 8202233589 |  | 8202230922#Penggantian LO Filter 56-P-10 | RU6-UTL | 56-P-101A-S1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 3960 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357029 | 8202240876 |  | 8202230921#25_Mtl. Body Mixer Oil Gun 01 | RU4-FOC2 | 018F102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357027 | 8202240873 |  | 8202230920#25_Mtl. Body Mixer Oil Gun 01 | RU4-FOC2 | 018F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357023 | 8202240870 |  | 8202230918#25_Mtl. Body Mixer Oil Gun 01 | RU4-FOC2 | 013F102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357021 | 8202240867 |  | 8202230917#25_Mtl. Body Mixer Oil Gun 01 | RU4-FOC2 | 013F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-02-09 | 2102363177 | 8202233526 |  | 8202230916#Penggantian Pressure Gauge di | RU6-UTL | 53-P-102A-EN/01 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 3432 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-03 | 2025-12-03 | 2102354231 | 8202237201 |  | 8202230915#control valve 85FC225 passhin | RU4-KPC | 85FV225/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-17 | 2102361669 | 8202233635 |  | 8202230911#Penggantian Gasket all Cont.V | RU6-UTL | 059-FV-784A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 6600 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-03 | 2025-12-03 | 2102354232 | 8202237692 |  | 8202230910#TGH 8 Pemutahiran master data | RU4-SRU | 90V401/00 | 50 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K301 | 2026-02-05 | 2026-05-12 | 2025-12-05 | 2025-12-05 |  | 8202238646 |  | 8202230909#Tagihan Ke- 17 Pekerjaan Prev |  |  | 60 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | RAMADENY |  |  | PT02 | 3 | 2 | 2025-12-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-12 | 2025-12-05 | 2025-12-05 |  | 8202238207 | 8202234942 | 8202230907#Tagihan Ke- 17 Pekerjaan PM C | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-09 | 2025-12-09 | 2102351737 | 8202232632 |  | 8202230906#Pengambilan material modul di | RU2-ITP | RTU01A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2025-12-10 | 2025-12-10 |  | 8202237691 |  | 8202230905#TGH18_Building Management Ser | RU4-K3LL | FT34/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-15-C2H | 424090000 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-10 | PM |  | 045
| K201 | 2026-02-04 | 2026-06-18 | 2025-12-08 | 2026-01-22 | 2102351477 | 8202238552 |  | 8202230904#pekerjaan LTSA Steam Leak Non | RU2-ITP | DPN-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 400000000 | 0 | MA4-STA |  | AHILMANSYAH |  | 2026-06-18 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-03 | 2025-12-03 | 2102351614 | 8202232576 |  | 8202230902#Perbaikan temporary plate roo | RU2-HSC | 100-H-1/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 1195567 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-30 | 2102363060 | 8202233530 |  | 8202230900#Penggantian Pressure Gauge 13 | RU6-DHC | 13-R-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102354119 | 8202240865 |  | 8202230898#25_[CR] Perbaikan Pompa 16P-2 | RU4-FOC1 | 16P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-09 | 2025-12-24 |  | 8202233524 |  | 8202230897#Penggantian Pressure Gauuge d | RU6-UTL | 58-D-101A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 154 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102358220 | 8202240862 |  | 8202230895#25_Penggantian LSH tanki 70T2 | RU4-TRML | 70T2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-21 | 2026-02-09 | 2102361779 | 8202233691 |  | 8202230894#Penggantian Bearing Pompa 052 | RU6-UTL | 052-P-101C/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 223678 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-01-02 | 2102356564 | 8202240859 |  | 8202230892#25_Perbaikan Sensor Conductiv | RU4-UTL | 052AT002/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 20017650 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-17 | 2025-12-17 | 2102356720 | 8202236389 |  | 8202230891#D25_Kerusakan probe sensor 24 | RU4-LOC3 | 240K101/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-03 | 2025-12-03 | 2102351613 | 8202232294 |  | 8202230890#Perbaikan kabel power supply | RU2-UTL | 560-TRF-AS1/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102358071 | 8202240856 |  | 8202230888#25_[CR] Membran Rusak 120P601 | RU4-GTO | 120P601B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-09 | 2025-12-24 | 2102362055 | 8202233789 |  | 8202230887#Pengadaan Material Nataru Uni | RU6-HSC | 32-K-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1774797 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102356773 | 8202238586 |  | 8202230885#RKAP 2026 PENGGANTIAN MAINLIN |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102356125 | 8202234444 |  | 8202230884#Pengadaan Pulley Motor Finfan | RU4-RFCUTL | 30BD12EE0102A/00 | 60 | REL CNF CSER MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 58500000 | 0 | MA6-LIS |  | SAPBATCH | 2026-03-05 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102356122 | 8202234448 |  | 8202230883#Pengadaan Pulley Motor Finfan | RU4-RFCUTL | 30BD12EE0102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102356123 | 8202234452 |  | 8202230882#Pengadaan Pulley Motor Finfan | RU4-RFCUTL | 30BD12EE0102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355086 | 8202240853 |  | 8202230880#25_[CR] Penggantian Belt 16K1 | RU4-FOC1 | 16K1/01 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 210600 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357003 | 8202240850 |  | 8202230878#25_[CR] Perbaikan Pump Grease |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | GEN-MEK |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-07 | 2026-02-05 | 2026-07-02 | 2102361614 | 8202238573 |  | 8202230877#Perbaikan 11-P-101 B | RU6-HSC | 11-P-101B/01 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354618 | 8202240825 |  | 8202230876#25_[CR] Perbaikan Lubrication | RU4-TRML | 33P2B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-10 | 2026-01-02 | 2026-05-08 | 2102362477 | 8202238571 |  | 8202230875#Perbaikan Lampu Indicator Pan | RU6-RCC | 16-K-101/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-09 | 2102362557 | 8202233464 |  | 8202230874#Penggantian Transmitter 33-FT | RU6-HSC | 33-FT-022/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 | 2102352184 | 8202234280 |  | 8202230873#Pemeriksaan Tangki 946-Tk-7 | RU2S-KIL | 946-TK-07/00 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2025-12-08 | 2102351523 | 8202232599 |  | 8202230871#Perbaikan pressure gauge 940- | RU2-UTL | 940-P-2C/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-03-17 | 2102361077 | 8202233489 |  | 8202230870#Penggantian Switch IHLA 42T10 | RU6-ITP | 42-T-101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 6600 | 0 | MA4-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102357952 | 8202240822 |  | 8202230869#25_Vibrasi, high temp disch 2 | RU4-LOC3 | 220K101/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 41038000 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2025-12-08 | 2025-12-08 |  | 8202237690 | 8202238635 | 8202230868#TGH26_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 278407000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2025-12-23 | 2102362109 | 8202233787 |  | 8202230867#Pengadaan Material Nataru Uni | RU6-POC | 39-K-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 154 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102351337 | 8202232659 |  | 8202230866#Pengadaan Part PC Engine CFR | RU2-LAB | LAB-GAS-22/00 | 50 | REL MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | WS-IN1 |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2025-12-08 | 2025-12-08 | 2102357012 | 8202240819 |  | 8202230865#25_Mtl. MOC Strainer Tail Gas | RU4-LOC2 | 025F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 130083354 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2025-12-08 | 2102351522 | 8202232601 |  | 8202230864#Perbaikan pressure gauge 940- | RU2-UTL | 940-P-2B/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102353978 | 8202240817 |  | 8202230863#25_[CR] Perbaikan pompa 30P10 | RU4-TRML | 30P108A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2025-12-08 | 2102351521 | 8202232603 |  | 8202230862#Perbaikan pressure gauge 940- | RU2-UTL | 940-P-2A/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-02-18 | 2102361730 | 8202233693 |  | 8202230860#Penggantian bearing motor 58- | RU6-UTL | 58-K-101E-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 4229819 | 0 | MA4-LIS |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-28 | 2102362864 | 8202233528 |  | 8202230859#Penggantian Pressure Gauge ar | RU6-DHC | 14-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2025-12-29 | 2102361734 | 8202233023 |  | 8202230858#Perbaikan motor hoist 12-A-60 | RU6-DHC | 12-A-602-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 173 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238201 | 8202234925 | 8202230857#Tagihan Ke- 5 Pekerjaan Pemel |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354941 | 8202240815 |  | 8202230856#25_Penggantian Motor 054WS105 | RU4-UTL | 054WS105P1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K301 | 2026-02-02 | 2026-05-08 | 2025-12-12 | 2025-12-12 | 2102353065 | 8202235305 |  | 8202230855#Perbaikan Furnace F1 CD 5 | RU3-CDGP | CD5-F-1/00 | 60 | CLSD CNF CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-STA |  | PASRILARIF | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-08 | 2025-12-09 | 2025-12-09 | 2102353067 | 8202235353 |  | 8202230853#Penggantian insulasi pipe sta | RU3-CDGP | STA-1-1C/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-07 | 2025-12-09 | 2025-12-09 | 2102353066 | 8202235320 |  | 8202230852#Penggantian Torque Multipler | RU3-CDL | FLRS-C-101/00 | 60 | REL CNF PRT NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | HANGGAO | 2026-01-02 | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2025-12-09 | 2025-12-09 | 2102353062 | 8202235357 |  | 8202230851#Penggantian belt conveyor ZB2 | RU3-PP | 23-ZB-2611Z3/00 | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-08 | 2025-12-09 | 2025-12-09 | 2102353064 | 8202235225 |  | 8202230850#Perbaikan Pompa 1 CD 3 | RU3-CDGP | CD3-P-001/00 | 60 | TECO CNF NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | MULYONO701 | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-08 | PM |  | 004
| K301 | 2026-02-02 | 2026-05-08 | 2025-12-09 | 2025-12-09 | 2102353063 | 8202235315 |  | 8202230849#Perbaikan ALK-E-5-6/00 | RU3-CDGP | ALK-E-5-6/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-08 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-04-16 | 2102361399 | 8202233669 |  | 8202230848#Penggantian Control Valve 31- | RU6-HSC | 31-FV-001/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-05-06 | 2026-01-02 | 2026-09-09 | 2102361835 | 8202237745 |  | 8202230847#Pengadaan Oil Cooler 15K103E3 | RU6-RCC | 15-K-103-E3B/00 | 50 | REL PRC SETC | 6MR | D16/26/B6/NR-C2H | 204000001 | 0 | MA1-STA |  | DANDARWANI |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-08 | 2025-12-08 | 2102355131 | 8202236470 |  | 8202230846#Penggantian Support JB Motor | RU4-LOC2 | 40LTW08/00 | 60 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-01 | 2025-12-01 | 2102358028 | 8202240814 |  | 8202230845#25_[CR] Perbaikan pompa 10P4 | RU4-FOC1 | 10P2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 600000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2025-12-05 | 2025-12-05 |  | 8202237689 | 8202238641 | 8202230843#TGH10_22 TSA FGDS Gastron RFC | RU4-RFCC | 102TG005/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1063683000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102355752 | 8202240812 |  | 8202230841#25_[CR] Penggantian Belt 14E6 | RU4-FOC1 | 14E6K-A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 4454130 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-05 | 2025-12-05 | 2102357542 | 8202240810 |  | 8202230837#25_[CR] Penggantian Belt 12E2 | RU4-FOC1 | 12E2K-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2025-12-22 | 2102361633 | 8202233579 |  | 8202230835#Penggantian Modul TDI 3 BN TC | RU6-UTL | 51-G-101B-LP/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357545 | 8202240808 |  | 8202230834#25_[CR] Penggantian Belt 16K2 | RU4-FOC1 | 16K2/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 70200 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102358141 | 8202240806 |  | 8202230833#25_[CR] Penggantian Belt 11E5 | RU4-FOC1 | 11E53AK-A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1740000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-01-12 | 2026-02-24 | 2102361440 | 8202238442 |  | 8202230832#PEM. SACRIFICIAL CATHODIC SUP | RU6-ITP | 41-LA-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 1 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-01-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-04 | 2025-12-04 | 2102357658 | 8202240804 |  | 8202230830#25_[CR] Penggantian Filter Lu | RU4-FOC1 | 16K1/01 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-04 | 2025-12-04 | 2102357700 | 8202240802 |  | 8202230829#25_[CR} Penggantian Filter Ud | RU4-FOC1 | 16K1/01 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354328 | 8202240800 |  | 8202230817#25_[CR] Penggantian Filter LO | RU4-UTL | 520B601K-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 17100666 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-27 | 2102361763 | 8202233599 |  | 8202230815#Penggantian Level Switch 42-L | RU6-ITP | 42-P-919/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 6996 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-04 | 2025-12-04 | 2102351529 | 8202232412 |  | 8202230814#High vibration 140 EM-23B | RU2-HOC | 140-EM-23B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 3419093 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356945 | 8202240797 |  | 8202230813#25_Mtl. kerangan HFO manifold |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 3858334 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-04 | 2025-12-04 | 2102351584 | 8202232625 |  | 8202230811#Perbaikan panel listrik area | RU2-UTL | 510-DG-CAT01/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/NR-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-04 | 2025-12-04 | 2102351611 | 8202232410 |  | 8202230809#Perbaikan 940-PM-58A | RU2-UTL | 940-P-58A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/NR-D2H | 508400 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-04 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-20 | 2025-11-20 | 2102357854 | 8202237688 |  | 8202230808#TGH 1_Sky Lift Gen Maint 25/2 | RU4-K3LL | FT27/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-15-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-20 | PM |  | 045
| K201 | 2026-02-04 | 2026-04-16 | 2026-04-23 | 2026-12-29 | 2102351401 | 8202238551 |  | 8202230806#LTSA Perbaikan Dan Penggantia | RU2-HOC | 140-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | ERLANGGA |  | 2026-04-16 | PT02 |  | 3 | 2026-04-23 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-02 | 2026-03-04 | 2102362396 | 8202237742 |  | 8202230805#LTSA Prbkan 15-P-102 Body E T | RU6-RCC | 15-P-102A/01 | 50 | REL CSER GMPS NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 122740000 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-02 | 2026-02-18 | 2102362318 | 8202237740 |  | 8202230804#LTSA Prbkan 15-P-102 Body D T | RU6-RCC | 15-P-102A/01 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-04-22 | 2102361866 | 8202233543 |  | 8202230802#Penggantian Positioner 33-FV- | RU6-HSC | 33-FV-026/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2026-01-02 | 2026-04-08 | 2102361667 | 8202238441 |  | 8202230798#Perbaikan impeller pompa 42-P | RU6-ITP | 42-P-501B/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 117000000 | 0 | MA4-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K201 | 2026-02-01 |  | 2025-12-31 | 2025-12-31 | 2102351609 | 8202232581 |  | 8202230797#perbaikan tanki HCl | RU2-UTL | 940-ME-3/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2025-12-31 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-20 | 2026-02-26 |  | 8202232153 | 8202232152 | 8202230796#Gasket dan Baut Butterly Valv | RU6-ITP | 43-SPM-01/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 660 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-20 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-30 |  | 8202233529 |  | 8202230795#Penggantian pressure gauge ar | RU6-DHC | 12-F-101/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 3387588 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-06 | 2102361079 | 8202233597 |  | 8202230794#Penggantian Level Switch IHLA | RU6-ITP | 42-T-301A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 7656 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-05 | 2026-06-15 | 2025-12-04 | 2025-12-29 | 2102364344 | 8202238618 |  | 8202230792#Mat. Isolasi Cementlining E-3 | RU5-E15112 | 03B-FCV-105/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-D1H | 205 | 0 | MA3-STA |  | SAPBATCH | 2026-06-15 | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 045
| K601 | 2026-02-01 | 2026-03-16 | 2026-01-02 | 2026-01-15 | 2102361568 | 8202232966 |  | 8202230791#Perbaikan Pompa 34-A-102-P-10 | RU6-POC | 34-A-102-P-101A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 26874000 | 22450000 | MA3-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2025-12-18 | 2102361590 | 8202232965 |  | 8202230790#Perbaikan Pompa 34-P-104A | RU6-POC | 34-P-104A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C2H | 128 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-05 | 2026-02-07 | 2026-01-02 | 2027-01-20 |  | 8202238617 |  | 8202230789#Material Relokasi Tank HCl da | RU5-UTL | 2UA05A001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-05-06 | 2026-01-02 | 2026-01-02 | 2102356419 | 8202240768 |  | 8202230788#25_Perbaikan cooling water 71 | RU4-TRML | 71T17/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102356560 | 8202240765 |  | 8202230787#25_Perbaikan cooling water 71 | RU4-TRML | 71T11/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-14 | 2026-01-02 | 2026-07-24 | 2102361639 | 8202238439 |  | 8202230786#Compsite Repair 11-V-104 | RU6-HSC | 11-V-104/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 122000000 | 103700000 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102355471 | 8202240762 |  | 8202230784#25_[CR] 84P206B Low Performan | RU4-KPC | 84P206B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 31286359 | 28980000 | MA4-ROT |  | SAMSUDINH |  | 2026-03-10 | PT02 |  | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357279 | 8202240759 |  | 8202230782#25_Penggantian positioner azb | RU4-LOC1 | 21PV008/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 2 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-01 | 2102362750 | 8202233614 |  | 8202230781#Penggantian Lampu Annunciator | RU6-ITP | 42-P-503E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 7392 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-27 | 2025-11-27 | 2102355037 | 8202236328 |  | 8202230779#Penunjukkan 21TIC710 NaN | RU4-LOC1 | 21TT710/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-27 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2025-12-15 | 2025-12-15 |  | 8202241439 | 8202241222 | 8202230778#TGH12_24 Kontrak Peformance M | RU4-KPC | 87P204A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 145123900 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-12-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-03 | 2025-12-22 | 2102361406 | 8202233463 |  | 8202230777#Penggantian Transmitter 33-FT | RU6-HSC | 33-FT-024/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 180 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-19 | 2026-01-06 | 2026-01-27 | 2102361393 | 8202232941 |  | 8202230776#Perbaikan Pompa 63-P-111A (WA | RU6-ITP | 63-P-111A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 102001980 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-03 | 2025-12-22 | 2102361408 | 8202233735 |  | 8202230775#Penggaantian Transmitter 33-P | RU6-HSC | 33-E-108/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 180 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-22 | 2026-02-04 | 2102361596 | 8202232985 |  | 8202230773#Perbaikan Pompa 15-P-107B | RU6-RCC | 15-P-107B/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2027-02-12 | 2102361520 | 8202234103 |  | 8202230772#11-P-121 B | RU6-HSC | 11-P-121B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-04 | 2026-05-07 | 2026-01-19 | 2026-06-03 | 2102360124 | 8202238550 |  | 8202230771#PERB.PIPING PROGRAM CLAMP MGT | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 2700000000 | 0 | MA4-STA |  | YUSUFM |  | 2026-05-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102354884 | 8202237687 |  | 8202230770#TGH8_25 UP MON&INSP PERALATN |  |  | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102354886 | 8202237686 |  | 8202230769#TGH7_25 UP MON&INSP PERALATN |  |  | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-30 | 2102362914 | 8202233459 |  | 8202230768#Penggantian Transmitter 38-PD | RU6-POC | 38-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-12 | 2025-12-12 |  | 8202238185 | 8202235701 | 8202230767#Tagihan Ke- 2 Pekerjaan Kontr |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-12-12 | 2025-12-12 |  | 8202238107 | 8202235701 | 8202230766#Tag 1 Pek.KV Mekanik area Sel |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 045
| K301 | 2026-02-02 | 2026-03-12 | 2026-01-01 | 2026-01-01 | 2102353123 | 8202235701 |  | 8202230765#Pek.KV Mekanik area Selatan O |  |  | 01 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-01-01 | 2026-01-01 | 2102353124 | 8202235665 |  | 8202230764#Pek.KV Mekanik area Utara OM |  |  | 01 | CRTD NMAT PRC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 045
| K601 | 2026-02-04 | 2026-03-03 | 2026-03-03 | 2026-05-25 | 2102361566 | 8202238548 |  | 8202230763#FABRIKASI PART POMPA 32-A-101 | RU6-HSC | 32-A-101-P1B/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 189000000 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-03-03 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102361594 | 8202232936 |  | 8202230762#Perbaikan Pompa 66-P-101D | RU6-UTL | 66-P-101D/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C1H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-03 | 2025-12-22 | 2102363472 | 8202233864 |  | 8202230761#Pemasangan Level Trasnmitter | RU6-HSC | 11-V-103/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 180 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-03 | 2025-12-22 | 2102362815 | 8202233466 |  | 8202230759#Penggantian Transmitter 23-LT | RU6-HSC | 23-T-101/00 | 50 | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 180 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2025-12-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-03 | 2025-12-03 | 2102356648 | 8202235784 |  | 8202230757#Perbaikan motor 41P-4BM | RU4-TRML | 41P4BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 045
| K201 | 2026-02-04 | 2026-03-11 | 2026-03-02 | 2026-03-02 | 2102352049 | 8202238032 |  | 8202230754#Perbaikan Trafo T 3-12 | RU2-UTL | 905-TRF-3-12/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 778900000 | 0 | MA3-LIS |  | ADEMULYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-03-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102351332 | 8202232547 |  | 8202230753#Mechanical Seal Bocor | RU2-HCC | 702-P-4B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 9552698 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102351244 | 8202232487 |  | 8202230752#oil seal bocor | RU2-HCC | 211-P-61A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 9552698 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102351760 | 8202232712 |  | 8202230751#Service Venturi Tube | RU2-HSC | 300-FT-69A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-01 | 2025-12-01 | 2102355174 | 8202240756 |  | 8202230750#25_[PV] Pengadaan Suction dan | RU4-FOC1 | 14K602B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 181649282 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-08-19 | 2102362232 | 8202236856 |  | 8202230749#Perbaikan Transformator RU VI | RU6-RCC | 15-K-102A-VFD/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/26/B6/RT-C2H | 111138000 | 94467300 | MA1-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102351769 | 8202232668 |  | 8202230748#Pengadaan Material PRV 560-GT | RU2-UTL | 560-GT-3/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA3-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-03 | 2025-12-18 | 2102361846 | 8202233469 |  | 8202230747#Penggantian Transmitter 11-FT | RU6-HSC | 11-V-101A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354795 | 8202240753 |  | 8202230746#25_Perbaikan modul 94TIC156 | RU4-SRU | 94TIT156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-02 | 2025-12-10 | 2102361482 | 8202234065 |  | 8202230745#24-P-302 A | RU6-HSC | 24-P-302A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C2H | 269 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-18 | 2026-02-18 | 2026-12-22 | 2102357450 | 8202238593 |  | 8202230744#26_Penggantian PSL Lube Oil F | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357394 | 8202240750 |  | 8202230743#25_Penggantian flow transmitt | RU4-LOC1 | 21FT001/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 111000000 | 18875000 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355737 | 8202240747 |  | 8202230742#25_Penggantian TG 105-TG-944B | RU4-RFCGTO | 105TG-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 3 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355738 | 8202240744 |  | 8202230741#25_Penggantian TG 105-TG-944A | RU4-RFCGTO | 105TG-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 3 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-18 | 2026-02-18 | 2026-11-26 | 2102355736 | 8202238594 |  | 8202230740#26_Pengadaan Modul VMS Kompre | RU4-RFCGTO | 105K501/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 4 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-18 | 2026-02-18 | 2026-11-26 | 2102355635 | 8202238595 |  | 8202230739#26_Pengadaan Modul VMS Kompre | RU4-RFCC | 108-CWS0009-1/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 2 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-18 | 2026-02-18 | 2026-11-26 | 2102355634 | 8202238596 |  | 8202230738#26_Pengadaan Modul VMS Kompre | RU4-RFCGTO | 108PV005/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-16 | 2025-12-01 | 2025-12-01 | 2102354944 | 8202236305 |  | 8202230737#D25_Perbaikan Solenoid 140-KV | RU4-GTO | 140KV015/00 | 60 | CLSD CNF NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH | 2026-04-16 | 2026-02-07 | PT02 |  | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-01 | 2025-12-01 | 2102354763 | 8202234826 |  | 8202230736#Tagihan TSA O2 analyzer termi | RU4-FOC2 | 012AT001/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-01 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-01 | 2025-12-01 | 2102354762 | 8202234830 |  | 8202230735#Tagihan TSA O2 analyzer termi | RU4-FOC2 | 011AT324/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-01 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-01 | 2025-12-01 | 2102354761 | 8202234833 |  | 8202230734#Tagihan TSA O2 analyzer termi | RU4-FOC2 | 011AT323/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-03 | 2025-11-18 | 2102361874 | 8202233507 |  | 8202230732#Penggantian Sensor Temperatur | RU6-ITP | 42-T-107B/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K201 | 2026-02-05 | 2026-05-25 | 2026-12-02 | 2026-12-02 | 2102351509 | 8202238649 |  | 8202230731#RK0065 TSA LAMPU PENERANGAN J | RU2-UTL | 905-LPN-OSBLES5/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 57000000 | 0 | MA4-LIS |  | DEDISUKMANA |  | 2026-02-07 | PT02 |  | 3 | 2026-12-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-22 | 2026-01-02 | 2026-08-31 | 2102352424 | 8202234279 |  | 8202230730#Perbaikan Motor Pompa 946-P9- | RU2S-KIL | 946-P-9B-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 2068507 | 591002 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-02 | 2026-03-03 |  | 8202236575 | 8202236586 | 8202230729#Tgh ke4 TKDN LTSA 11E116 (15% | RU6-HSC | 11-E-116A/00 | 50 | CRTD NMAT PRC | 6MR | D16/24/B6/RT-C3H | 15872400 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-12-02 | PM |  | 004
| K202 | 2026-02-02 | 2026-03-31 | 2026-03-17 | 2026-08-31 | 2102352421 | 8202234278 |  | 8202230728#Perbaikan vibrasi motor 101-P | RU2S-KIL | 101-P-8C-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 260000 | 260000 | MAS-LIS |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-03-17 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-17 | 2026-02-02 | 2026-02-02 | 2102352474 | 8202234277 |  | 8202230726#PENGECEKAN KONDISI JETTY 1 SP | RU2S-KIL | 18PL90001B-A1A1/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 519700 | 519700 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102351661 | 8202232279 |  | 8202230725#Kebutuhan material 410 E-2 | RU2-HCC | 410-E-2/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102358160 | 8202240741 |  | 8202230724#25_[CR] Penggantian Membran C | RU4-GTO | 180A601K1A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 45000000 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-11 | 2025-12-02 | 2025-12-02 | 2102356165 | 8202237685 |  | 8202230723#Tagihan PM IAS termin 25 | RU4-FOC2 | 011P106A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 478800000 | 478800000 | MA2-ROT |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102354790 | 8202236202 |  | 8202230721#ganti cartridge filter 91K-40 | RU4-SRU | 91K401B/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 045
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102353926 | 8202236206 |  | 8202230720#Perbaikan bocoran steam 91E-4 | RU4-SRU | 91E403/00 | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-12-02 | 2025-12-02 | 2102356973 | 8202237334 |  | 8202230719#91S-404 Penggantian catridge | RU4-SRU | 91S404/00 | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-12-02 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-10-29 | 2025-10-29 | 2102354140 | 8202237312 |  | 8202230718#Bocoran di 91C-403 | RU4-SRU | 91C403/00 | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-10-29 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354457 | 8202240738 |  | 8202230715#013P-113B : line suction pomp | RU4-FOC2 | 013P113B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355665 | 8202240735 |  | 8202230713#25_Mtl. Check Valve 011P127A | RU4-FOC2 | 011P127A/01 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238196 | 8202235502 | 8202230712#Tagihan Ke- 11 Pekerjaan Sipi | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102357551 | 8202236224 |  | 8202230711#Fin fan 023E-108M4 bocor | RU4-LOC2 | 023E108/00 | 01 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102357241 | 8202234963 |  | 8202230710#Soot blower 021F101/F102 no.1 | RU4-LOC2 | 021F101/00 | 01 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2025-12-02 | 2025-12-02 | 2102357359 | 8202240731 |  | 8202230709#25_Butt. Valve cooler 025P-10 | RU4-LOC2 | 025P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2025-12-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202236795 | 8202235092 | 8202230708#Tagihan Ke- 8 Pekerjaan Suppo | RU3-WS | BEN-TOOL/00 | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-05-19 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-01 | 2025-12-01 | 2102357455 | 8202240729 |  | 8202230707#25_[CR] Penggantian Belt 11 E | RU4-FOC1 | 11E57K-G/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3350000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-18 | 2026-02-04 | 2026-02-04 |  | 8202238123 | 8202238402 | 8202230706#Tagihan Ke- 17 Pekerjaan Clea | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102355607 | 8202237259 |  | 8202230704#Cleaning strainer 024P-119 | RU4-LOC2 | 024P119/00 | 01 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-12-02 | 2025-12-02 | 2102353729 | 8202236086 |  | 8202230703#Heater 24E-5 indikasi bocor | RU4-LOC1 | 24E5/00 | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-12-02 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-12-02 | 2025-12-02 | 2102354966 | 8202236089 |  | 8202230702#Gland packing 24E1A patah | RU4-LOC1 | 24E1A/00 | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-12-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-12 | 2102361488 | 8202233314 |  | 8202230701#Perbaikan 19PC012 | RU6-RCC | 19-PV-012/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 112 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-02 | 2025-12-17 | 2102362745 | 8202233558 |  | 8202230699#Penggantian PI Vessel Anion D | RU6-UTL | 055-A-101-V2/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-10 | 2026-03-10 | 2026-04-14 | 2102361448 | 8202232977 |  | 8202230698#Perbaikan Pompa 20-P-103A | RU6-RCC | 20-P-103A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/NR-C2H | 1018885018 | 507600000 | MA1-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-01 | 2025-12-16 | 2102363450 | 8202233527 |  | 8202230697#Penggantian Pressure Gauge di | RU6-HSC | 11-P-102B-P1/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102351668 | 8202232533 |  | 8202230696#Penggantian Transmiter 300-FT | RU2-HSC | 300-FT-176/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K401 | 2026-02-02 |  | 2025-12-01 | 2025-12-01 | 2102353546 | 8202237319 |  | 8202230695#Aux boiler 151B501B | RU4-RFCUTL | 151B501B/00 | 50 | CRTD CSER MACM PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-STA |  |  |  |  | PT02 |  | 2 | 2025-12-01 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2025-12-01 | 2025-12-01 | 2102354764 | 8202240725 |  | 8202230694#25_Mtl. Perbaikan Bocoran 023 | RU4-LOC2 | 023E108/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 1447800 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2025-12-01 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-01 | 2025-12-01 | 2102355639 | 8202237088 |  | 8202230692#Pengambilan Material Pinjam S | RU4-RFCGTO | 108K501A-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-01 | 2025-12-01 | 2102354766 | 8202240723 |  | 8202230691#25_Mtl. Perbaikan Bocoran 024 | RU4-LOC2 | 024E105/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 4618571 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-01 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-20 | 2026-02-20 |  | 8202232148 | 8202232152 | 8202230690#Pick-up Rope Mooring Hawser S | RU6-ITP | 43-SPM-01/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-20 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2025-12-01 | 2025-12-01 | 2102358061 | 8202237684 |  | 8202230689#Tagihan Termin 11, 12 Perbaik | RU4-UTL | 051G101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 163049550 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 045
| K601 | 2026-02-06 | 2026-03-26 | 2026-02-06 | 2026-09-29 | 2102361331 | 8202238689 |  | 8202230688#Perbaikan boom crane TMC | RU6-WS | 00-A-452/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 85000000 | 0 | WS-KAB |  | DANDARWANI |  | 2026-03-04 | PT02 | 5 | 3 | 2026-02-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102351873 | 8202232480 |  | 8202230687#Perbaikan 211 V-26 | RU2-HCC | 211-V-26/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 756900 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-05-11 | 2102361997 | 8202233734 |  | 8202230686#Pengganntian TE/TW di 15-B-10 | RU6-RCC | 15-B-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-01 | 2025-12-30 | 2102361447 | 8202233910 |  | 8202230685#Matrial Tambahan Line Fire | RU6-UTL | 66-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 256 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2025-11-18 | 2102351910 | 8202232605 |  | 8202230683#Perbaikan press transmitter 5 | RU2-UTL | 550-MHI-PT-101/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102351171 | 8202232273 |  | 8202230681#Perbaikan Lampu Area Utilitie | RU2-UTL | 550-TRF-BMHI/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-14 | 2025-11-14 | 2102351938 | 8202232518 |  | 8202230680#Penyelesaian Bon Pinjam Mater | RU2-WS | OHC-2/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 8060000 | WS-LI2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-01 | 2025-12-16 |  | 8202233533 |  | 8202230679#Penggantian Press Gauge di 11 | RU6-HSC | 11-P-103A-E1/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102351846 | 8202232546 |  | 8202230678#Penggantian Membrane Coupling | RU2-HOC | 220-P-3A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 25260000 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-12-02 | 2025-12-02 | 2102351880 | 8202232200 |  | 8202230677#Perbaikan Oil Pump 140-P-51A | RU2-HOC | 140-P-51A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102351988 | 8202232620 |  | 8202230676#Perbaikan Pompa 140 P-14B | RU2-HOC | 140-P-14B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 399926 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-12-02 | 2025-12-02 | 2102351164 | 8202232615 |  | 8202230675#Perbaikan Pompa 140 P-8B | RU2-HOC | 140-P-8B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102351558 | 8202232341 |  | 8202230674#Perbaikan FDF 110 C-52 BN | RU2-HOC | 110-C-52BN/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 1174830 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102351459 | 8202232305 |  | 8202230673#Perbaikan IDF 110 C-51N | RU2-HOC | 110-C-51N/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2025-12-01 | 2025-12-01 | 2102357896 | 8202240719 |  | 8202230672#25_[CR] 014K102P3B Mech Seal | RU4-FOC2 | 014K102P3B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102362805 | 8202233506 |  | 8202230671#Penggantian Sensor Vibrasi 56 | RU6-UTL | 56-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 12012 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102361683 | 8202233119 |  | 8202230670#Perbaikan Level Switch | RU6-ITP | 42-P-910/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 12012 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-05-07 | 2102361548 | 8202233577 |  | 8202230669#Penggantian MTL BRC 39-TI-901 | RU6-POC | 39-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102358300 | 8202234854 |  | 8202230668#Ganti Check Valve & Butterfly | RU7-UTL | 10-4-FW390-A1F/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/25/B6/RT-5-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 005
| K601 | 2026-02-04 | 2026-03-03 | 2025-11-28 | 2026-06-09 | 2102361445 | 8202238470 |  | 8202230667#Perbaikan bocoran tube Boiler | RU6-UTL | 52-B-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 209270000 | 0 | MA4-STA |  | HARSARIZANO |  | 2026-02-24 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K201 | 2026-02-01 | 2026-05-13 | 2026-01-28 | 2026-01-28 | 2102352116 | 8202232718 |  | 8202230665#Pengadaan Pompa Retention Pon | RU2-HSC | 301-ONP-3A/00 | 60 | REL GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 210000000 | MA2-ROT |  | ERLANGGA |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-17 | 2026-01-02 | 2026-08-31 | 2102352202 | 8202234276 |  | 8202230664#PERBAIKAN 900-06-GE-7 | RU2S-KIL | 900-06GE-7-SWGR/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C3H | 13350000 | 13350000 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-15 | 2026-04-30 | 2026-12-31 | 2102351602 | 8202238566 |  | 8202230663#PERAWATAN PEMBERSIHAN/ CLEANI | RU2-UTL | 940-B-1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1225000000 | 0 | MA3-STA |  | AHILMANSYAH |  | 2026-03-31 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357457 | 8202240716 |  | 8202230662#25_[CR] Perbaikan fin fan 14E | RU4-FOC1 | 14E610A-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357458 | 8202240714 |  | 8202230661#25_[CR] Perbaikan fin fan 14E | RU4-FOC1 | 14E610A-B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-14 | 2102361311 | 8202233452 |  | 8202230660#Penggantian TW/TT 15-TI-164 | RU6-RCC | 15-B-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-14 | 2102361297 | 8202233453 |  | 8202230659#Penggantian TW/TT 15-TI-152 | RU6-RCC | 15-B-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-28 | 2025-12-15 | 2102361404 | 8202233521 |  | 8202230658#Penggantian Pressure Transmit | RU6-RCC | 15-A-102/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354887 | 8202240710 |  | 8202230656#25_Pengadaan Ring Burner 52B1 | RU4-UTL | 52B1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355820 | 8202240708 |  | 8202230654#25_Penunjukan 260TT506 tinggi | RU4-LOC3 | 260F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-27 | 2025-12-29 | 2102361446 | 8202233438 |  | 8202230653#Penggantian vavle dan gasket | RU6-UTL | 53-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 269 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2025-12-24 | 2102361318 | 8202233385 |  | 8202230649#Perbaikan 12-PT-697 | RU6-DHC | 12-PT-697/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 295 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-01-02 | 2026-02-19 |  | 8202233532 |  | 8202230648#Penggantian Press Gauge di OS | RU6-ITP | 42-P-966A/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/26/B6/RT-C2H | 4224 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102357937 | 8202235316 |  | 8202230647#Panel sootblower 85F201 | RU4-KPC | 85F201J1-PNL/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-05-12 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102354019 | 8202236060 |  | 8202230646#Kabel Jumper panel 80SS21 Rus | RU4-KPC | 80SS21/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-05-12 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102355795 | 8202236096 |  | 8202230645#perbaikan control heater 39P2 | RU4-TRML | 39P202AM/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-05-12 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102353930 | 8202237346 |  | 8202230644#85F201J1-PNL/00 malfunction | RU4-KPC | 85F201J1-PNL/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-05-12 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102353977 | 8202236555 |  | 8202230643#D_25 Shoot blower macet 260ME | RU4-LOC3 | 260ME151-SBL-M2/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102356261 | 8202236713 |  | 8202230642#D_25 0ibrasi pada motor 041P0 | RU4-TRML | 041P304AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102357705 | 8202236685 |  | 8202230641#D_25 Cover fan motor 260P157A | RU4-LOC3 | 260P157AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 045
| K701 | 2026-02-02 |  | 2025-11-28 | 2025-11-28 | 2102358308 | 8202234852 |  | 8202230639#Pengecekan Lampu penerangan d |  |  | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-2-D2H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 005
| K701 | 2026-02-02 |  | 2025-11-28 | 2025-11-28 | 2102358330 | 8202234816 |  | 8202230638#Perbaikan Tanggul Rered |  |  | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-5-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 005
| K701 | 2026-02-02 |  | 2025-11-28 | 2025-11-28 | 2102358309 | 8202234788 |  | 8202230637#pengecekan lampu penerangan d |  |  | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 005
| K701 | 2026-02-02 |  | 2025-11-28 | 2025-11-28 | 2102358307 | 8202234754 |  | 8202230636#Ganti kerangan 3-V-02 |  |  | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-3-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 005
| K701 | 2026-02-02 |  | 2025-11-27 | 2025-11-27 | 2102358306 | 8202234729 |  | 8202230635#Pengecekan Lampu di 2-f-01 |  |  | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-2-D2H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2025-11-27 | PM |  | 005
| K701 | 2026-02-02 |  | 2025-11-27 | 2025-11-27 | 2102358331 | 8202234695 |  | 8202230634#Perbaikan Regulator 3-E-01 |  |  | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-3-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2025-11-27 | PM |  | 005
| K201 | 2026-02-04 | 2026-05-26 | 2026-11-27 | 2026-11-27 | 2102351987 | 8202238564 |  | 8202230633#Perbaikan jalan rusak area WT | RU2-UTL | 510-PIPING/00 | 60 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 3582250000 | 3570000000 | MA3-STA |  | ADEMULYADI |  | 2026-03-02 | PT02 |  | 3 | 2026-11-27 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351675 | 8202232494 |  | 8202230632#Motor Vibrasi | RU2-HCC | 211-PM-15B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 453119 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351950 | 8202232233 |  | 8202230631#Perbaikan Motor 140 PM-21A | RU2-HOC | 140-PM-21A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 890000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351951 | 8202232293 |  | 8202230630#702 P-2 Danger Vibration | RU2-HCC | 702-P-2/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 890000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351958 | 8202232229 |  | 8202230629#Perbaikan Motor 140 PM-22A | RU2-HOC | 140-PM-22A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 1178000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-27 | 2025-11-27 | 2102351092 | 8202232594 |  | 8202230628#Penggantian Bearing 200-PM-6A | RU2-HSC | 200-PM-6A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-12-30 | 2102361401 | 8202233351 |  | 8202230627#Perbaikan 15-FT-591 | RU6-RCC | 15-FT-591A/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 295 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2025-11-27 | 2025-11-27 | 2102357629 | 8202240706 |  | 8202230626#25_Penggantian Valve Bundwall | RU4-TRML | 46PSH304/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 40291217 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2025-11-27 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-05 |  | 8202233531 |  | 8202230625#Penggantian Press Gauge di Po | RU6-ITP | 42-P-206A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 5544 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-06-02 | 2026-06-02 | 2026-12-31 | 2102361441 | 8202238467 |  | 8202230623#Pemasangan cathodic SPL 35 da | RU6-ITP | 41-A-102/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 1129000000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-02-13 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-05 |  | 8202233525 |  | 8202230622#Penggantian Pressure Gauge OS | RU6-ITP | 42-P-960/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 5544 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-24 | 2025-12-22 | 2102361319 | 8202234007 |  | 8202230621#Instalasi ATG 42-T-101D | RU6-ITP | 42-T-101D/00 | 50 WAMA | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 269 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-27 | 2025-12-29 | 2102361333 | 8202233999 |  | 8202230620#Kebutuhan Spare Part IHLA | RU6-ITP | 42-T-101D/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 269 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-05 |  | 8202233536 |  | 8202230617#Penggantian Press Gauge 0-60 | RU6-ITP | 42-P-304A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 5544 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-10 | 2026-01-02 | 2027-02-12 | 2102361443 | 8202233331 |  | 8202230616#Perbaikan 16-P-107B | RU6-RCC | 16-P-107B/00 | 50 WAMA | CRTD CSER MACM PRC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | T_FATAHY |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-14 | 2102361739 | 8202233470 |  | 8202230615#Penggantian Transmitter 059-P | RU6-UTL | 059-PT-500/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 8448 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-14 | 2025-11-14 | 2102351966 | 8202232340 |  | 8202230614#Pressure switch rusak | RU2-HCC | 211-P-2A/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357815 | 8202241152 |  | 8202230612#25_[BP] 011K101C valve passin | RU4-FOC2 | 011K101C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 9864000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-01-02 | 2026-04-09 | 2102361402 | 8202238465 |  | 8202230611#Perbaikan Struktur Area Jetty | RU6-ITP | 41-A-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 1 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102362541 | 8202233541 |  | 8202230610#Penggantian Positioner 52-FV- | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 12012 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102362304 | 8202233505 |  | 8202230609#Penggantian Sensor Vibrasi 58 | RU6-UTL | 58-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 12012 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-27 | 2025-11-27 | 2102354967 | 8202235789 |  | 8202230608#Perbaikan motor 24S1CM2M | RU4-LOC1 | 24S1CM2M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 045
| K501 | 2026-02-03 | 2026-06-04 | 2026-06-04 | 2027-06-07 | 2102360376 | 8202237725 |  | 8202230607#Jasa Resertifikasi Boiler HHP |  |  | 50 | REL NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 197450000 | 0 | ENG-STA |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-06-04 | PM |  | 045
| K601 | 2026-02-02 |  | 2026-01-02 | 2026-04-01 | 2102363346 | 8202233498 |  | 8202230606#Penggantian Solenoid 058 XV 5 | RU6-UTL | 058-D-101A/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/26/B6/RT-C2H | 7392 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-25 | 2102363345 | 8202233497 |  | 8202230605#Penggantian solenoid 52-XV-20 | RU6-UTL | 52-XV-209A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 6732 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-15 | 2026-04-15 | 2026-05-29 | 2102351165 | 8202232540 |  | 8202230604#Penggantian Press Gauge | RU2-HSC | 301-FCV-241/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 1984600 | 0 | MA2-INT |  | DONITGN |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-21 | 2026-05-25 | 2026-09-14 | 2102351736 | 8202238555 |  | 8202230602#Jasa Inspeksi NDT & RBI RU II |  |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 200000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-05-21 | PT02 |  | 3 | 2026-05-25 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351142 | 8202232400 |  | 8202230601# pengambilan material untuk | RU2-ITP | 110-P-1A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-01 | 2026-03-12 | 2026-04-09 | 2102361361 | 8202232976 |  | 8202230600#Perbaikan Pompa 23-P-101B | RU6-HSC | 23-P-101B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/NR-C2H | 1386425 | 1312481 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-03-12 | PM |  | 003
| K201 | 2026-02-01 | 2026-03-11 | 2026-03-04 | 2026-06-29 | 2102352043 | 8202232689 |  | 8202230599#Tube 212 E-26 bocor | RU2-HCC | 212-E-26/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MR | D12/26/B6/RT-D2H | 6566000 | 4526000 | MA2-STA |  | STEVANEKOPP |  | 2026-02-07 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-11-04 | 2102351141 | 8202232583 |  | 8202230598#Perbaikan sounder valve Filtr | RU2-UTL | 925-HY-1185/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-15 | 2026-04-15 | 2026-12-29 | 2102351140 | 8202232604 |  | 8202230597#perbaikan pressure gauge 560- | RU2-UTL | 560-GT-3/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 1984600 | 0 | MA3-INT |  | DONITGN |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-11-04 | 2102351109 | 8202232256 |  | 8202230596#Perbaikan limit switch IDF 55 | RU2-UTL | 550-STK-ZS-17/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-17 | 2025-11-17 | 2102351935 | 8202232598 |  | 8202230595#Penggantian Bearing | RU2-HSC | 300-PM-3B/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-27 | 2025-11-27 | 2102357568 | 8202241150 |  | 8202230594#25_Flange Tapping Point 87TI2 | RU4-KPC | 87TV209/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 3818137 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-28 | 2025-11-28 | 2102356737 | 8202241147 |  | 8202230593#25_Penggantian Temp Indikator | RU4-TRML | 43T101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-28 | 2025-11-28 | 2102356417 | 8202241144 |  | 8202230591#25_Penggantian Temp Indikator | RU4-TRML | 36T106/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-12 | 2025-11-26 | 2102362604 | 8202233832 |  | 8202230590#Pengadaan baru motor 15-K-101 | RU6-RCC | 15-K-101-K2B-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 141 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-10 | 2025-11-10 | 2102352441 | 8202234275 |  | 8202230589#PENGECEKAN MECH SEAL 101-P3B | RU2S-KIL | 101-P-3B/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351190 | 8202232590 |  | 8202230582#Penggantian Bearing 310-CM-4 | RU2-HSC | 310-CM-4/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 616350 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351158 | 8202232239 |  | 8202230581#Perbaikan Motor 140 - PM 16A | RU2-HOC | 140-PM-16A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357060 | 8202241141 |  | 8202230580#25_166P553B, mech seal bocor | RU4-RFCGTO | 166P553B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351800 | 8202232396 |  | 8202230579# 930-PM-201A (Service & Ganti | RU2-ITP | 930-PM-201A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357064 | 8202241138 |  | 8202230578#25_[CR] Mech seal 41P-4B boco | RU4-TRML | 41P4B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351834 | 8202232225 |  | 8202230576#perbaikan motor 140-PM-26 A | RU2-ITP | 140-PM-26A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-11-26 | 2025-12-30 |  | 8202236584 | 8202236570 | 8202230574#Tgh ke 5 Kont. RT Vol MA1 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351275 | 8202232496 |  | 8202230573#Perbaikan 140 EM-23B | RU2-HOC | 140-EM-23B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 2859838 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-01 | 2025-11-26 | 2025-11-26 | 2102351484 | 8202232208 |  | 8202230572#perbaikan motor 930-PM-3A | RU2-ITP | 930-PM-3A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 350670 | 350670 | MA4-LIS |  | AZIZFATONI |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351413 | 8202232204 |  | 8202230571#Perbaikan Motor 945-PM-7B | RU2-ITP | 945-PM-7B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 2349660 | 2349660 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102351977 | 8202232674 |  | 8202230570#Vibrasi Motor | RU2-HCC | 840-PM-3A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-26 | 2025-11-26 |  | 8202238192 |  | 8202230569#Add. Pek. Perbaikan Pos Secur | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 045
| K201 | 2026-02-01 |  | 2025-11-25 | 2025-11-25 | 2102351798 | 8202232478 |  | 8202230568#Perbaikan 211/212 F-1 | RU2-HCC | 211-BV-F1A/00 | 01 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2025-11-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356809 | 8202241135 |  | 8202230567#25_Penggantian PD Meter 30P10 | RU4-TRML | 30P105B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-17 | 2025-12-01 | 2025-12-01 | 2102354639 | 8202236369 |  | 8202230566#D25_PENGGANTIAN 510 PCV 128 - | RU4-UTL | 510G301/00 | 60 | CLSD CNF NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-INT |  | SAPBATCH | 2026-04-18 | 2026-02-07 | PT02 |  | 3 | 2026-04-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-17 | 2025-12-01 | 2025-12-01 | 2102354682 | 8202236368 |  | 8202230565#D25_PENGGANTIAN 510 PCV 129 - | RU4-UTL | 510G301/00 | 60 | CLSD CNF NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-INT |  | SAPBATCH | 2026-04-17 | 2026-02-07 | PT02 |  | 3 | 2026-04-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-01 | 2025-12-01 | 2102355479 | 8202236342 |  | 8202230564#D25_Perbaikan FGDS 71T21 | RU4-TRML | 71T21/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102358315 | 8202241134 |  | 8202230563#25_Perbaikan Box Panel Instru | RU4-UTL | 51G1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357992 | 8202241133 |  | 8202230561#25_51G201 Perbaikan Diff PG F | RU4-UTL | 51G201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357949 | 8202241132 |  | 8202230560#25_Flame rod burner 21F-2 pat | RU4-LOC1 | 21F2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 2 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357948 | 8202241131 |  | 8202230559#25_Flame rod burner 21F-1 pat | RU4-LOC1 | 21F1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102357481 | 8202241130 |  | 8202230558#25_Penggantian PG 510G301 [NE | RU4-UTL | 510G301/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 15487519 | 0 | MA5-INT |  | REHANR |  | 2026-03-10 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357483 | 8202241129 |  | 8202230557#25_(BON PINJAM) Penggantian T | RU4-UTL | 510G301/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 14693578 | 0 | MA5-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357271 | 8202241128 |  | 8202230555#25_Penggantian safety relay K | RU4-UTL | 510G601T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357149 | 8202241127 |  | 8202230554#25_Penggantian LCP ESD Push B | RU4-UTL | 510G601T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 10 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357067 | 8202241126 |  | 8202230552#25_(BON PINJAM) 89LV508 erro | RU4-KPC | 89LV508/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 23454546 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-11 | 2026-11-25 | 2026-11-25 | 2102351340 | 8202238546 |  | 8202230551# KONTRAK VOLUME PERBAIKAN DAN | RU2-HCC | 8-V-21338-MS11/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA2-STA |  | DJOKOTRIONO |  | 2026-05-06 | PT02 |  | 3 | 2026-11-25 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-11-04 | 2102351101 | 8202232631 |  | 8202230550#Pengambilan Material Thermal | RU2-ITP | 990-HVM-1018/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-14 | 2025-11-14 | 2102351964 | 8202232448 |  | 8202230549#Perbaikan 610-PM-203A | RU2-ITP | 610-P-203A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-15 | 2025-12-19 |  | 8202233929 | 8202238464 | 8202230548#Material Perbaikan 63-Z-202B | RU6-ITP | 63-Z-202B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 64 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-15 | PM |  | 005
| K601 | 2026-02-04 | 2026-02-22 | 2026-01-06 | 2026-08-27 | 2102362554 | 8202238464 |  | 8202230547#Perbaikan 63-Z-202B dan 63-P- | RU6-ITP | 63-Z-202B/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 4000000 | 400000000 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-06 | PM |  | 005
| K202 | 2026-02-02 | 2026-05-25 | 2026-04-27 | 2026-10-30 | 2102352576 | 8202234274 |  | 8202230546#Perbaikan Kebocoran Cooler 10 | RU2S-KIL | 101-E-9/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 26633000 | 26633000 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-04-27 | PM |  | 003
| K202 | 2026-02-02 | 2026-05-25 | 2026-05-18 | 2026-10-30 | 2102352575 | 8202234272 |  | 8202230545#Perbaikan Kebocoran Cooler 10 | RU2S-KIL | 101-E-8/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 153526 | 153526 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-05 | 2025-11-05 | 2102351100 | 8202232452 |  | 8202230544#Perbaikan 550-IDF-101C | RU2-UTL | 550-IDF-101C/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354792 | 8202241125 |  | 8202230543#25_Mtl. Ganti Cartridge Filte | RU4-SRU | 91S403/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 52080000 | 52080000 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-05 | 2025-11-05 | 2102351079 | 8202232216 |  | 8202230542#Perbaikan motor 550-FDF-101A | RU2-UTL | 550-FDF-101A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2025-11-17 | 2025-12-30 | 2102362658 | 8202237938 |  | 8202230541#Pemb. PM/PDM Control Valve Ta | RU6-DHC | 22-A-101/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-25 | 2025-11-25 | 2025-11-25 | 2102357946 | 8202235828 |  | 8202230540#Perbaikan motor 11P8B | RU4-FOC1 | 11P8BM/00 | 60 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | AGUNGSN |  | 2026-02-07 | PT02 |  | 3 | 2025-11-25 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-24 | 2025-11-24 |  | 8202237683 | 8202237681 | 8202230539#TGH3_25 Instalasi dan Konfi D | RU4-FOC2 | DCS-FOC2/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2025-11-25 | 2025-11-25 |  | 8202237682 |  | 8202230538#TGH10_24 Kontrak Peformance M | RU4-LOC1 | 21P9B/00 | 50 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 43018500 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-25 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-24 | 2025-11-24 | 2102356739 | 8202237681 |  | 8202230537#TGH2_25 Instalasi dan Konfi D | RU4-FOC2 | DCS-FOC2/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-11-24 | 2025-12-30 | 2102361314 | 8202236787 |  | 8202230535#Rebagging Catalyst Tahap 1 | RU6-LOG | OO-S-102/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-24 | 2025-12-24 | 2102351894 | 8202232326 |  | 8202230531#Pengadaan Flexible Joint Burn | RU2-HOC | 170-WHB-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-24 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-04-20 | 2102361396 | 8202233455 |  | 8202230529#Penggantian Transmitter 58-TT | RU6-UTL | 58-D-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 8976 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-03-09 | 2102362803 | 8202233458 |  | 8202230528#Penggantian transmitter 50-LT | RU6-UTL | 50-LT-006/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 5808 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-21 | 2025-12-12 | 2102361310 | 8202234024 |  | 8202230527#Fasilitas power listrik new b | RU6-ITP | 42-LA-401A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/25/B6/NR-C2H | 205 | 14000000 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-21 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-17 | 2025-11-17 | 2102352436 | 8202234270 |  | 8202230525#Kebocoran di gland packing 90 | RU2S-KIL | 900-08P-1C/01 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-17 | 2025-11-17 | 2102352435 | 8202234269 |  | 8202230524#Kebocoran di gland packing 90 | RU2S-KIL | 900-08P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356169 | 8202241124 |  | 8202230523#25_Kerusakan membran coupling | RU4-TRML | 041P304A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 22100000 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-17 | 2025-11-17 | 2102352434 | 8202234268 |  | 8202230522#Perbaikan vibrasi pompa 900-0 | RU2S-KIL | 900-08-P-4D/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-16 | 2026-01-02 | 2026-08-31 | 2102352439 | 8202234267 |  | 8202230521#indikasi motor trip 101-P7B | RU2S-KIL | 101-P-7B-M/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 834000 | 504000 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102355083 | 8202241123 |  | 8202230519#25_[PV] Pengadaan belt 14E6A | RU4-FOC1 | 14E6K-A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 66811956 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-16 | 2026-03-27 | 2026-08-31 | 2102352438 | 8202234266 |  | 8202230518#indikasi motor trip 101-E-6E | RU2S-KIL | 101-E-6E-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-D2H | 2616578 | 884945 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-03-27 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-19 | 2025-11-19 | 2102352431 | 8202234265 |  | 8202230516#PENGECEKAN MOTOR POMPA 101-P5 | RU2S-KIL | 101-P-5A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-24 | 2025-12-09 | 2102361348 | 8202233457 |  | 8202230515#Penggantian Transmitter 54-LT | RU6-UTL | 54-LT-001A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 154 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-24 | 2025-11-24 | 2102361229 | 8202237680 |  | 8202230512#TGH1_25 UP Load Unload ME-2 | RU4-GTO | 106S502/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-24 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-20 | 2026-01-02 |  | 8202237679 | 8202237674 | 8202230511#TGH3_24 UP OLLS ME-2 | RU4-RFCC | 101-CS0015-1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-20 | PM |  | 004
| K401 | 2026-02-04 |  | 2025-11-24 | 2025-11-24 |  | 8202238543 |  | 8202230510#Perbaikan Kompresor 048K101C | RU4-TRML | 048K101C/00 | 50 WASR | CRTD NMAT PRC | 4RR | D14/25/B6/RTC-2-C2H | 10000000 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2025-12-22 | 2102361649 | 8202232957 |  | 8202230509#Perbaikan pompa 42-P-501A | RU6-ITP | 42-P-501A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C2H | 1536 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-12 | 2025-11-12 | 2102351980 | 8202232585 |  | 8202230508#Penggantian Bearing Motor 211 | RU2-HCC | 211-PM-11A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 112171 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2025-11-24 | 2025-11-24 | 2102354584 | 8202236351 |  | 8202230507#D25_Perbaikan Alarm HMI MAB 1 | RU4-RFCC | 101K501/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-09-30 | 2026-11-24 |  | 8202236195 |  | 8202230505#Perbaikan metering sytem LPG | RU5-TBL | METER-7841/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-09-30 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-18 | 2026-05-04 | 2026-12-10 |  | 8202236199 |  | 8202230504#NRK_Perbaikan LPG PDN-PKBBM | RU5-TBL | 22-X2-X2-793/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 4180000000 | 0 | MA4-INT |  | YUSUFM |  | 2026-06-18 | PT02 |  | 3 | 2026-05-04 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-21 | 2025-11-21 | 2102351071 | 8202232328 |  | 8202230499#Perbaikan Gearbox 170-GG-58 | RU2-HOC | 170-GG-58/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-21 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351674 | 8202232212 |  | 8202230498#Perbaikan motor 580-PM-301 A | RU2-UTL | 580-PM-301A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-21 | 2026-02-24 | 2102361416 | 8202233482 |  | 8202230497#Penggantian TG di 36-E-105 | RU6-POC | 36-E-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-21 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-20 | 2026-02-26 | 2102362558 | 8202232152 |  | 8202230496#Material Camlock Coupling SPM | RU6-ITP | 43-SPM-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 660 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-20 | PM |  | 005
| K301 | 2026-02-04 | 2026-05-15 | 2025-11-20 | 2025-11-20 |  | 8202238022 | 8202235439 | 8202230495#Tagihan Ke- 1 Pekerjaan Pemel |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354748 | 8202241122 |  | 8202230494#25_87FT213 rusak | RU4-KPC | 87FT213/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357702 | 8202241121 |  | 8202230493#25_Limit switch SOV 21P17 rus | RU4-LOC1 | 21P17/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2025-11-20 | 2025-11-20 | 2102358367 | 8202234667 |  | 8202230484#MATERIAL SUPPORT MAINTENANCE | RU7-OFF | 5-PM-01B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-5-D1H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2025-11-20 | 2025-11-20 | 2102358366 | 8202234664 |  | 8202230483#MATERIAL SUPPORT MAINTENANCE | RU7-OFF | 5-PM-01A/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/25/B6/RT-5-D1H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-14 | 2025-11-14 | 2102351963 | 8202232515 |  | 8202230482#Penyelesaian Bon Pinjam Mater | RU2-HCC | 212-EM-18A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 34700029 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2025-10-28 | 2102351204 | 8202232367 |  | 8202230481#211-EM-5E Motor Rusak | RU2-HCC | 211-EM-5E/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-11-11 | 2102351989 | 8202232228 |  | 8202230480#Perbaikan Motor 140 PM-8B | RU2-HOC | 140-PM-8B/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-20 | 2025-12-22 | 2102361299 | 8202232749 |  | 8202230479#Repair 34-A-103-P-101 A-M | RU6-POC | 34-A-103-P-101AM/0 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/NR-C2H | 148181 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-11 | 2026-01-02 | 2026-01-02 |  | 8202235439 |  | 8202230478#Kontr.Vol Online leak Sealing |  |  | 50 | REL GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | MULYONO701 |  | 2026-05-08 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-04-28 | 2026-04-27 | 2026-12-10 | 2102358140 | 8202236331 |  | 8202230477#Penunjukan 84TI205 A&C | RU4-KPC | TEMP-U84/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-28 | PT02 |  | 3 | 2026-04-27 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2025-12-04 | 2025-12-04 | 2102358109 | 8202241119 |  | 8202230476#25_PI Pelumas Pompa Sundyne A | RU4-KPC | 84P201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 50 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-12-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-20 | 2026-04-13 | 2102361890 | 8202233009 |  | 8202230475#Perbaikan Pilot Lamp Alarm 05 | RU6-UTL | 056-K-101-B1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1284 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-20 | 2026-04-13 | 2102361891 | 8202233520 |  | 8202230474#Penggantian Presure Switch 51 | RU6-UTL | 51-G-102-K1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1284 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-20 | 2025-11-20 | 2102357245 | 8202236695 |  | 8202230473#D_25 Control LPS Sootblower 0 | RU4-LOC2 | 025F101/00 | 60 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-20 | 2025-11-20 | 2102357246 | 8202236691 |  | 8202230472#D_25 Control MPS Sootblower 0 | RU4-LOC2 | 025F101/00 | 60 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-20 | 2025-11-20 | 2102356774 | 8202236651 |  | 8202230471#D_25 Motor 024P-113A Noise | RU4-LOC2 | 024P113A/00 | 60 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356128 | 8202241116 |  | 8202230469#25_[CR] 048P101BT throttle va | RU4-TRML | 48P101B-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 129354508 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-20 | 2025-11-20 | 2102351936 | 8202232536 |  | 8202230466#Penggantian Pressure Transmit | RU2-HSC | 301-PCV-206/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-02-23 | 2102363204 | 8202233364 |  | 8202230465#Perbaikan 13-TI-928A | RU6-DHC | 13-K-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 640 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-06-23 | 2102361727 | 8202234066 |  | 8202230462#24-P-205 A | RU6-HSC | 24-P-205A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 3456 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-19 | 2026-01-02 | 2102354729 | 8202237678 |  | 8202230461#TGH1_REJUV_ISOLASI_PIP_MA3 | RU4-TRML | LN38-1001AJ/00 | 60 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-19 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357994 | 8202241112 |  | 8202230460#25_[CR] Perbaikan turbin 51P2 | RU4-UTL | 51P2A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 6158617 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-20 | 2025-12-31 | 2102362556 | 8202233603 |  | 8202230458#Penggantian LCS Tag 12-E-105 | RU6-DHC | 12-E-105/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 359 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366094 | 8202241109 |  | 8202230457#25_[CR] Perbaikan Fin Fan 104 | RU4-RFCC | 104E509C-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 52085732 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-22 | 2026-06-22 | 2026-12-30 | 2102357941 | 8202241106 |  | 8202230456#25_[PV] Perbaikan Pompa 103P5 | RU4-RFCC | 103P501B/00 | 60 | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 100992500 | 0 | MA6-ROT |  | LUQMANULH |  | 2026-03-10 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102365809 | 8202241103 |  | 8202230455#25_penggantian belt 16K1 | RU4-FOC1 | 16K1/01 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2027-01-20 |  | 8202236191 |  | 8202230453#Ganti Valve dan Line Pendingi | RU5-UTL | GM-32-05A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 |  | 8202236864 | 8202234582 | 8202230452#Tagihan Ke- 7 Termin Masa Pem |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-19 | 2025-11-19 | 2102352430 | 8202234264 |  | 8202230451#PENGECEKAN POMPA 101-P4 CDU S | RU2S-KIL | 101-P-4A-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-19 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-08 | 2025-11-20 | 2025-11-20 | 2102352159 | 8202234263 |  | 8202230450#Kendala Sinkron ATS 900-06-GE | RU2S-KIL | 900-06GE-6-GT/00 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-C3H | 0 | 0 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-19 | 2025-12-09 | 2102361295 | 8202233991 |  | 8202230449#Lamp MCC400V SS15 dan SS16 | RU6-HSC | 15-PMC3-01A/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 193 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2025-12-05 | 2102362751 | 8202232945 |  | 8202230447#Perbaikan pompa 55-A-101B-P1 | RU6-UTL | 55-A-101B/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C1H | 179 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-17 | 2025-11-19 | 2025-12-30 |  | 8202236547 | 8202237896 | 8202230444#Welder Pipe Fitter Tahap 10 | RU6-HSC | 11-E-110A/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-06 | 2025-11-06 | 2102354676 | 8202236467 |  | 8202230443#D25_011FV-049 indikasi passin | RU4-FOC2 | 011FV049/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-17 | 2025-11-19 | 2025-12-30 |  | 8202236530 | 8202237896 | 8202230442#Welder Pipe Fitter Tahap 9 | RU6-HSC | 11-E-110A/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354960 | 8202241100 |  | 8202230440#25_[CR] Perbaikan coupling 21 | RU4-LOC1 | 21P7B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-17 | 2025-11-19 | 2025-12-30 |  | 8202236533 | 8202237896 | 8202230439#Welder Pipe Fitter Tahap 8 | RU6-HSC | 11-E-110A/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 004
| K601 | 2026-02-02 | 2026-06-17 | 2025-11-19 | 2025-12-30 |  | 8202236534 | 8202237896 | 8202230438#Welder Pipe Fitter Tahap 7 | RU6-HSC | 11-E-110A/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 004
| K601 | 2026-02-02 | 2026-06-17 | 2025-11-19 | 2025-12-30 |  | 8202236537 | 8202237896 | 8202230437#Welder Pipe Fitter Tahap 6 | RU6-HSC | 11-E-110A/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355393 | 8202241097 |  | 8202230436#25_[CR] Perbaikan Loader Valv | RU4-FOC1 | 14K602A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351702 | 8202232344 |  | 8202230435#Perbaikan fan 945-PM-30A | RU2-ITP | 945-PM-3A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102356804 | 8202241094 |  | 8202230434#25_[CR] Penggantian pompa pel | RU4-SRU | 91K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 48489000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238191 | 8202235438 | 8202230433#Tagihan Ke- 6 Termin TKDN Pek |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238190 | 8202234832 | 8202230431#Tag 21 Sarana Tambat Kapal Su |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238189 | 8202235085 | 8202230430#Tagihan Ke- 10 Termin TKDN Pe |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-18 | 2025-12-17 | 2102362692 | 8202233828 |  | 8202230429#Pengadaan consumable material | RU6-UTL | 52-B-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 4596384 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102354047 | 8202241091 |  | 8202230427#25_[CR] Perbaikan turbin FDF | RU4-UTL | 52B3K-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 57611606 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355669 | 8202241088 |  | 8202230426#25_[NP] 048P101A mech seal bo | RU4-TRML | 048P101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 114565800 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-10-28 | 2025-10-28 |  | 8202234261 | 8202234202 | 8202230423#Material Calcium Silicate (BA | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-D3H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-13 | 2025-11-12 | 2025-11-12 | 2102357409 | 8202235943 |  | 8202230422#Perbaikan Lamp test flame det |  |  | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | FATAHALFI |  |  | PT02 |  | 2 | 2025-11-12 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357714 | 8202241084 |  | 8202230420#25_Pemasangan TI area tanki 4 | RU4-TRML | TEMP-U42/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 100648120 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357991 | 8202241082 |  | 8202230419#25_Perbaikan Instrumentasi Po | RU4-TRML | 36P101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 12 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357213 | 8202241080 |  | 8202230418#25_Penggantian thermo gauge 1 | RU4-RFCC | 101TI-U101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 3062169 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-04 | 2025-12-17 | 2025-12-17 | 2102357571 | 8202236306 |  | 8202230417#D25_Perbaikan Leak Connector | RU4-RFCC | 101K501/00 | 60 | CLSD CNF NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH | 2026-03-04 | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354262 | 8202241078 |  | 8202230416#25_Perbaikan Feedback 101UV00 | RU4-RFCC | 101UV007/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2026-02-02 |  | 8202232915 |  | 8202230415#Perbaikan Press Gauge 64-P-10 | RU6-HSC | 64-P-102A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 640 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2025-12-17 | 2025-12-17 | 2102354587 | 8202236307 |  | 8202230414#D25_Perbaikan HMI WGC LAR 1 ( | RU4-RFCC | 102K501/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2026-02-02 |  | 8202232917 |  | 8202230413#Perbaikan Press Gauge 24-P-30 | RU6-HSC | 24-P-302B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 640 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2026-04-09 |  | 8202232918 |  | 8202230412#Perbaikan Press Gauge 24-P-30 | RU6-HSC | 24-P-302A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2026-04-09 |  | 8202232914 |  | 8202230411#Perbaikan Press Gauge 64-P-10 | RU6-HSC | 64-P-103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2025-11-18 | 2025-12-31 | 2102361474 | 8202237936 |  | 8202230410#Major Repair Fin Fan SPKR 3 | RU6-POC | 36-K-101-A1/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2026-04-09 |  | 8202232920 |  | 8202230409#Perbaikan Press Gauge 24-P-10 | RU6-HSC | 24-P-103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2026-04-09 |  | 8202232921 |  | 8202230408#Perbaikan Press Gauge 23-P-60 | RU6-HSC | 23-P-601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102362565 | 8202232752 |  | 8202230407#Reciever Gauge 24-PDI-054 | RU6-HSC | 24-S-202/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-19 | 2026-06-02 | 2026-11-30 | 2102352440 | 8202234259 |  | 8202230406#Pengecekan line ADO 946-TK-20 | RU2S-KIL | 10PL94601A-A1A1/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C2H | 4936025 | 1298235 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-06 | 2026-01-02 | 2026-05-26 | 2102361980 | 8202233374 |  | 8202230405#Perbaikan 13-FV-219 | RU6-DHC | 13-FV-219/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 564900000 | 178250000 | MA2-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2026-04-09 | 2102361982 | 8202233392 |  | 8202230404#Perbaikan 12-PCV-948 | RU6-DHC | 13-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355013 | 8202241076 |  | 8202230401#25_Rejuvenate Isolasi area OM | RU4-TRML | LN60-1216-A-10/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 5009100 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-03 |  | 2025-11-18 | 2026-01-02 |  | 8202237935 | 8202233981 | 8202230400#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | ES-B14-01/00 | 50 | CRTD CSER NMAT PRC | 6ER | D16/25/B6/RT-C2H | 1 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2025-11-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354302 | 8202241075 |  | 8202230397#25_[CR] 011P112A mech seal IB | RU4-FOC2 | 011P112A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102356682 | 8202241074 |  | 8202230395#25_[CR]Pelumas Turbin 025P-10 | RU4-LOC2 | 025P101A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 6531000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-17 | 2026-01-13 | 2102361239 | 8202233067 |  | 8202230394#Perbaikan Motor 11-P-107A | RU6-HSC | 11-P-107A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/NR-C2H | 486 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2025-12-16 | 2102361291 | 8202233402 |  | 8202230391#Perbaikan 12-FV-219 | RU6-DHC | 12-FV-219/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 269 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2025-12-16 | 2102362694 | 8202233396 |  | 8202230390#Perbaikan 12-LV-212 | RU6-DHC | 12-LV-212A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 269 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2025-11-18 | 2025-11-18 |  | 8202237677 | 8202237512 | 8202230389#TGH21_23 TSA ConMon Instrumen | RU4-RFCC | 101FJB001/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 278079000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355649 | 8202241073 |  | 8202230387#25_Mechanical seal pompa 025P | RU4-LOC2 | 025P101B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 |  | 8202241438 | 8202240911 | 8202230386#TGH12_24 Kontrak Peformance M | RU4-UTL | 54P5A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 83198850 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2025-11-18 | 2025-11-18 |  | 8202238463 |  | 8202230384#Inspeksi Peralatan Elect & In | RU2-HSC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1780000000 | 306540566 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2025-11-18 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102351934 | 8202232311 |  | 8202230382#212-V-103 CBA Jenuh | RU2-HCC | 212-V-103/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-25 |  | 8202236174 | 8202237117 | 8202230380#MAT.PERB.PIPING FOAM TANK 101 | RU5-TBL | 101-5-T-01B/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-17 | 2025-11-17 | 2102363618 | 8202232354 |  | 8202230379#Pengadaan check valve lubrica | RU2-HCC | 211-P-5A/01 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-09 |  | 8202233915 |  | 8202230377#Matl Slow Moving 35-P-101B | RU6-POC | 35-P-101A/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/NR-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-17 | 2025-11-17 | 2102355132 | 8202236800 |  | 8202230376#Penggantian kabel LPS area OM | RU4-TRML | 65BD1IU1/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355253 | 8202241072 |  | 8202230375#25_[CR] 87P202B Sisi OB Mech | RU4-KPC | 87P202B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356156 | 8202241071 |  | 8202230373#25_[CR] Blower 66K201 High Vi | RU4-TRML | 66K201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357940 | 8202241070 |  | 8202230371#25_[CR] Perbaikan Pompa 101F5 | RU4-RFCC | 101F503P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-20 | 2026-05-20 | 2026-12-31 | 2102355668 | 8202241068 |  | 8202230370#25_[CR] 014P107A mech seal bo | RU4-FOC2 | 014P107A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 2 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354043 | 8202241066 |  | 8202230363#25_perbaikan Ignitor boiler 5 | RU4-UTL | 520B301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356289 | 8202241064 |  | 8202230362#25_Penggantian Valve Fire Pum | RU4-K3LL | 70P2A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356801 | 8202241063 |  | 8202230359#25_Ganti belt 91E409B2 | RU4-SRU | 91E409B2M/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 32855000 | 3285500 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102356807 | 8202241061 |  | 8202230358#25_Ganti belt 91K401BE | RU4-SRU | 91K401BEM/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 282000 | 282000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2025-11-17 | 2025-11-17 |  | 8202237676 |  | 8202230352#TGH3_SIP_UP Rejuv Isolasi MA | RU4-RFCC | 105-WT0827-3-4/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-17 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102354341 | 8202241059 |  | 8202230350#25_[CR]Ganti belt 91E-409 A1 | RU4-SRU | 91E409A1M/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 1045000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102354343 | 8202241057 |  | 8202230349#25_[CR]Ganti belt 91E-409 A2 | RU4-SRU | 91E409A2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 3285500 | 3285500 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2025-11-12 | 2025-12-30 | 2102362504 | 8202237934 |  | 8202230347#Pengosongan Tangki Thp 5 | RU6-ITP | 42-T-301C/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-17 | 2025-12-15 | 2102362652 | 8202233153 |  | 8202230346#Perbaikan Instrumentasi Area | RU6-DHC | 12-LV-264A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 269 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2025-11-28 | 2025-11-28 | 2102354347 | 8202241055 |  | 8202230345#25_[CR]Ganti belt 94E-403 B | RU4-SRU | 94E403BM/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 1045000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102358466 | 8202234661 |  | 8202230344#PENGADAAN GATE VALVE 6" 150 |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-12 | 2102363347 | 8202233639 |  | 8202230343#Penggantian FTxPositionerConn | RU6-RCC | 15-K-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-17 | 2025-12-15 | 2102362650 | 8202232869 |  | 8202230342#Perbaikan Switch ZS-905 12-K- | RU6-DHC | 12-K-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 269 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-17 | 2025-12-01 | 2102362696 | 8202233405 |  | 8202230341#Perbaikan 12-FT-310 | RU6-DHC | 12-FT-310/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 141 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2025-11-17 | 2025-12-30 |  | 8202238435 | 8202237859 | 8202230340#SWO Pemeriksaan Bawah Air Kem | RU6-ITP | 41-A-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-12 | 2025-11-12 | 2102351985 | 8202232416 |  | 8202230339#Perbaikan 940-PM-1A | RU2-UTL | 940-PM-1A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351066 | 8202232334 |  | 8202230338#Preventive Maintenance Trafo | RU2-UTL | 560-TRF-CLINIC/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351708 | 8202232296 |  | 8202230337#Perbaikan kabel NYRGbY | RU2-UTL | 925-PM-7D/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351391 | 8202232460 |  | 8202230336#Pemasangan Kontaktor &Timer 5 | RU2-UTL | 520-PM-608C/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351394 | 8202232485 |  | 8202230335#Perbaikan 140 PM-27B | RU2-HOC | 140-PM-27B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 224342 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-06 | 2025-11-06 | 2102354678 | 8202236448 |  | 8202230330#D25_014PI-114 : failure, 014F | RU4-FOC2 | 014F101/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-12-09 | 2025-12-09 | 2102358147 | 8202241054 |  | 8202230329#25_Perbaikan 14PDT543 | RU4-FOC1 | 14PDT543/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-27 | 2025-11-27 | 2102357712 | 8202241052 |  | 8202230328#25_94PDIT-108 | RU4-SRU | 94PDIT108/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-12-04 | 2025-12-04 | 2102357710 | 8202241050 |  | 8202230327#25_92PI-112, ganti transmiter | RU4-SRU | 92PIT112/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-12-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102356930 | 8202241048 |  | 8202230326#25_[Upgrd] API Plan 87P202A | RU4-KPC | 87P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-27 | 2025-11-27 | 2102357677 | 8202241046 |  | 8202230325#25_92PDIT-113, ganti transmit | RU4-SRU | 92PDIT113/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-28 | 2026-04-27 | 2026-12-10 | 2102354968 | 8202235376 |  | 8202230324#perbaikan TST 84F203 | RU4-KPC | 84F203/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-28 | PT02 |  | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357470 | 8202241044 |  | 8202230322#25_Pengadaan Ring Burner & Ka | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 39900000 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-11 | 2025-11-10 | 2026-01-02 |  | 8202237675 | 8202237597 | 8202230321#TGH5_24 UP Perpipaan & Acc UT | RU4-UTL | LN52-104VA/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-10 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357581 | 8202241042 |  | 8202230320#[CR] SV dan gearbox SV 24S1C | RU4-LOC1 | 24S1C-G/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-10 | 2026-01-02 | 2102353962 | 8202237674 |  | 8202230319#TGH2_24 UP OLLS ME-2 | RU4-RFCC | 101-CS0015-1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-10 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-14 | 2025-11-14 | 2102354965 | 8202235793 |  | 8202230317#Perbaikan motor 24E12B | RU4-LOC1 | 24E12BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-14 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-14 | 2025-12-29 | 2102362550 | 8202233553 |  | 8202230316#Penggantian Pompa 15-P-102C | RU6-RCC | 15-P-102C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 384 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-17 | 2026-07-01 | 2026-08-27 | 2102364111 | 8202236165 |  | 8202230315#Perbaikan Instrumentasi Sump | RU5-E15111 | GM-34-63A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/NR-C3H | 475932006 | 0 | MA2-INT |  | FAUZANR |  | 2026-02-11 | PT02 |  | 3 | 2026-07-01 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-14 | 2026-01-02 | 2026-08-26 | 2102362608 | 8202238153 |  | 8202230314#Perbaikan Jalur Pipa Salamdar | RU6-UTL | 53-RW-0401-MS23/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 580000000 | 580000000 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357340 | 8202241040 |  | 8202230313#25_[CR] Membran Coupling 11P8 | RU4-FOC1 | 11P8B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2025-10-28 | 2102351207 | 8202232654 |  | 8202230312#Pengadaan Push Button Switch | RU2-ITP | 945-PM-7A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 35700000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K201 | 2026-02-01 | 2026-03-26 | 2025-11-13 | 2025-11-21 | 2102351245 | 8202232607 |  | 8202230311#Perbaikan Pompa Bak Sedimenta | RU2-UTL | 520-P-601A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 1410269 | 0 | MA3-ROT |  | ERLANGGA |  | 2026-02-07 | PT02 |  | 3 | 2025-11-13 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-26 | 2026-04-06 | 2026-12-28 | 2102351378 | 8202238542 |  | 8202230310#Penyediaan Scaffolding All Ar | RU2-HOC | 140-V-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 2000000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-04-02 | PT02 |  | 3 | 2026-04-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-13 | 2025-12-24 | 2102362654 | 8202232990 |  | 8202230308#Perbaikan Pompa 15-P-102A | RU6-RCC | 15-P-102A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/NR-C2H | 222214 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-13 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237673 | 8202237661 | 8202230307#TGH6_25 UP MON&INSP PERALATN | RU4-FOC1 | 11P10AM-CB/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-27 | 2025-12-01 | 2102361643 | 8202233610 |  | 8202230306#Penggantian Lampu Penerangan | RU6-RCC | 15-R-REGEN/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/NR-C2H | 333 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237672 | 8202237620 | 8202230305#TGH6_24 TSA LIGHTNING PROT SY | RU4-TRML | 30EE101A-50GS/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102361865 | 8202233245 |  | 8202230303#Perbaikan Aktuator 42-XV-511 | RU6-ITP | 42-T-404E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12012 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-11 | 2026-04-01 | 2102362458 | 8202233467 |  | 8202230302#penggantian transmitter 21-FT | RU6-DHC | 21-FT-012/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-11 | 2025-12-02 | 2102362454 | 8202233566 |  | 8202230301#Penggantian Part Positioner 3 | RU6-HSC | 33-FV-032/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 205 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-13 | 2025-11-21 | 2102351107 | 8202232359 |  | 8202230300#Pompa Jammed | RU2-HCC | 410-P-3B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 3347395 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-13 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-13 | 2025-12-16 | 2102362683 | 8202233569 |  | 8202230299#Penggantian Part 31-AT-003/00 | RU6-HSC | 31-V-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 297 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-13 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-13 | 2025-11-13 | 2102355664 | 8202236892 |  | 8202230298#D_25 011P112AM : hasil meger | RU4-FOC2 | 011P112AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-13 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-13 | 2025-11-13 | 2102354677 | 8202236919 |  | 8202230297#D_25 011P-109A, STOP. High vi | RU4-FOC2 | 011P109AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-11-30 | 2026-12-29 | 2102358887 | 8202236160 |  | 8202230296#Penggantian Fuse HRC MV 100A | RU5-UTL | 41-R-SS-66-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/NR-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-11-30 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-12-22 | 2102362390 | 8202233393 |  | 8202230295#Perbaikan 12-P-902 | RU6-DHC | 12-P-902/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/NR-C2H | 1152 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-11-13 | 2025-12-30 |  | 8202236858 | 8202238420 | 8202230293#Perbaikan Pompa Sump Pit | RU6-ITP | 42-P-902/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-13 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-12 | 2025-12-05 | 2102362500 | 8202232746 |  | 8202230292#Repair Motor 34-P-103 B | RU6-POC | 34-P-103B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 148118 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-04 | 2025-12-31 | 2102362158 | 8202233425 |  | 8202230291#Perbaikaan Motor 53-P-201C | RU6-UTL | 53-P-201C-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 148399 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-07 | 2026-01-09 | 2026-04-08 | 2102362452 | 8202234052 |  | 8202230290#33-P-112 A | RU6-HSC | 33-P-112A/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 559874252 | 1597992 | MA3-ROT |  | ABDULAZIZ70 |  | 2026-02-07 | PT02 |  | 3 | 2026-01-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-12-30 | 2102362106 | 8202233032 |  | 8202230289#Perbaikan motor 53-P-201A | RU6-UTL | 53-P-201A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 500 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-29 | 2102361963 | 8202233332 |  | 8202230288#Perbaikan 16-E-120 P | RU6-RCC | 16-E-120P-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 497 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-29 | 2102362058 | 8202233333 |  | 8202230287#Perbaikan 16-E-119 G | RU6-RCC | 16-E-119G-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 499 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-29 | 2102362004 | 8202233334 |  | 8202230286#Perbaikan 16-E-119 A | RU6-RCC | 16-E-119A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 499 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-24 | 2102362054 | 8202233336 |  | 8202230285#Perbaikan 16-E-117 M | RU6-RCC | 16-E-117M-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 485 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-24 | 2102361927 | 8202233353 |  | 8202230284#Perbaikan 15-E-110 Y | RU6-RCC | 15-E-110Y-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 487 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-24 | 2102362056 | 8202233354 |  | 8202230283#Perbaikan 15-E-110 AF | RU6-RCC | 15-E-110AF-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 487 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-18 | 2102362052 | 8202233341 |  | 8202230282#Perbaikan 15E110 AE | RU6-RCC | 15-E-110AE-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 435 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102363066 | 8202233415 |  | 8202230280#Perbaikan 11-TI-235 | RU6-HSC | 11-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102363128 | 8202233406 |  | 8202230279#Perbaikan 12-FT-279 | RU6-DHC | 12-FT-279/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2025-12-19 | 2102363314 | 8202233403 |  | 8202230278#Perbaikan 12-FT-809 | RU6-DHC | 12-FT-809/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 141 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-05-26 | 2102361938 | 8202233389 |  | 8202230277#Perbaikan 12-PSLL-457 | RU6-DHC | 12-PCV-449/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-12 | 2026-01-07 | 2102362506 | 8202233217 |  | 8202230276#Perbaikan bocoran Oil Trafo 5 | RU6-UTL | 51-PTR-101B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/NR-C2H | 249235606 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357996 | 8202241038 |  | 8202230274#25_Ganti transmitter 94PDIT-0 | RU4-SRU | 94PDIT082/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357995 | 8202241037 |  | 8202230273#25_Ganti Transmitter 94PDIT- | RU4-SRU | 94PDIT071/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-10 | 2025-11-10 | 2102352040 | 8202232244 |  | 8202230271#Lampu area HCC banyak yang ma | RU2-HCC | HCC-AC-MCR/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355183 | 8202241035 |  | 8202230265#25_[CR]Penggantian shim coupl | RU4-SRU | 91P406/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-26 | 2025-11-26 | 2102357570 | 8202241030 |  | 8202230263#25_PG Discharge Rusak 100P602 | RU4-GTO | 100PI603A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356257 | 8202241027 |  | 8202230262#25_Pressure draft Furnace 520 | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356258 | 8202241024 |  | 8202230261#25_Pressure Flue Gas to Stack | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356255 | 8202241021 |  | 8202230260#25_Pressure Flue Gas to Econo | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356256 | 8202241019 |  | 8202230259#25_Pressure draft Furnace 520 | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102365808 | 8202241017 |  | 8202230258#25_penggantian belt 14E605A | RU4-FOC1 | 14E605/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3525956 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356253 | 8202241015 |  | 8202230257#25_Pressure Furnace 520B401 | RU4-UTL | 520B401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356252 | 8202241013 |  | 8202230256#25_Pressure draft Furnace 520 | RU4-UTL | 520B401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356254 | 8202241011 |  | 8202230255#25_Pressure draft Furnace 520 | RU4-UTL | 520B401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356251 | 8202241009 |  | 8202230254#25_Pressure draft Furnace 520 | RU4-UTL | 520B301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356250 | 8202241007 |  | 8202230253#25_Pressure Furnace 520B301 | RU4-UTL | 520B301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-11 | 2026-01-06 | 2102362502 | 8202233863 |  | 8202230252#Pemasangan VSD | RU6-UTL | 70-P-101A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 606 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356129 | 8202241005 |  | 8202230251#25_Pressure draft Furnace 520 | RU4-UTL | 520B301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356127 | 8202241003 |  | 8202230250#25_Penggantian Power Supply | LOC1-UP4 | 47S506A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355889 | 8202241002 |  | 8202230249#25_Pressure Economizer Draft | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355887 | 8202241000 |  | 8202230248#25_Pressure Stack Draft 052B1 | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355888 | 8202240999 |  | 8202230247#25_Pressure Furnace Draft 052 | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355886 | 8202240998 |  | 8202230245#25_Pressure draft Furnace 052 | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356000 | 8202240996 |  | 8202230244#25_Pressure Flue Gas to Stack | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355881 | 8202240995 |  | 8202230243#25_Pressure Flue Gas to Stack | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355883 | 8202240994 |  | 8202230242#25_Pressure Stack Draft 052B1 | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355885 | 8202240993 |  | 8202230241#25_Pressure Furnace Draft 052 | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355884 | 8202240992 |  | 8202230240#25_Pressure Economizer Draft | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355882 | 8202240991 |  | 8202230239#25_Pressure draft Furnace 052 | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-11-12 | 2026-01-26 |  | 8202236663 | 8202233859 | 8202230238#SWO Pemb. LTSA ATG Termin 8 | RU6-ITP | 42-T-403A/00 | 50 | CRTD NMAT PRC | 6IR | D16/25/B6/RT-C2H | 1116600000 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355769 | 8202240990 |  | 8202230237#25_Pressure Economizer Draft | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355880 | 8202240989 |  | 8202230236#25_Pressure Stack Draft 052B1 | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355766 | 8202240988 |  | 8202230235#25_Pressure Flue Gas to Stack | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355767 | 8202240987 |  | 8202230234#25_Pressure Furnace Draft 052 | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355768 | 8202240986 |  | 8202230233#25_Pressure draft Furnace 052 | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355762 | 8202240985 |  | 8202230232#25_Pressure draft Furnace 052 | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-10 | 2025-12-19 | 2102362398 | 8202232991 |  | 8202230231#Perbaikan Pompa 15-P-102 Body | RU6-RCC | 15-P-102A/01 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 384 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2025-12-10 | 2102361767 | 8202233109 |  | 8202230230#Perbaikan Mech Seal 18-P-104A | RU6-RCC | 18-P-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 384 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-11 | 2025-12-11 | 2102351156 | 8202232696 |  | 8202230229#Tie In Pipa Raw Water KM 11-1 | RU2-UTL | 510-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 3579408 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-11 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-04 | 2026-05-04 | 2026-06-30 | 2102362344 | 8202233110 |  | 8202230227#Perbaikan Mech Seal 16-P-111B | RU6-RCC | 16-P-111B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 77754662 | 77754662 | MA1-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357990 | 8202240983 |  | 8202230226#25_[CR] Mech seal 23P-8 bocor | RU4-LOC1 | 23P8/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-11-12 | 2025-11-12 | 2102351006 | 8202232629 |  | 8202230224#pengambilan sw gasket 24’’ 15 | RU2-ITP | METER-SKID031/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-11-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355763 | 8202240980 |  | 8202230223#25_Pressure Flue Gas to Stack | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355761 | 8202240978 |  | 8202230222#25_Pressure Furnace Draft 052 | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355764 | 8202240976 |  | 8202230221#25_Pressure Stack Draft 052B1 | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355765 | 8202240974 |  | 8202230220#25_Pressure Economizer Draft | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354304 | 8202240972 |  | 8202230219#25_Penggantian 105VI601 RGC R | RU4-RFCGTO | 105VT-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 70 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102358144 | 8202240970 |  | 8202230216#25_Perbaikan Potensiometer 11 | RU4-FOC1 | 11K401A/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 55680000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-01-02 | 2026-01-02 | 2102351009 | 8202238111 |  | 8202230215#Pemasangan FGDS Area HCC | RU2-HCC | 212-H-1/00 | 50 | CRTD NMAT PRC SETC | 2IR | D12/26/B6/NR-D2H | 5000000 | 0 | MA2-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-03 | 2026-05-26 | 2026-01-02 | 2026-01-02 | 2102351083 | 8202237470 |  | 8202230214#RK0062 Control valve All Area | RU2-HCC | 211-PIPING/00 | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 500000000 | 0 | MA2-INT |  | DONITGN |  | 2026-04-28 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-11 | 2025-11-11 | 2102357849 | 8202237671 |  | 8202230213#TGH_TKDN_24 UP SCAFFOLD REJUV | RU4-FOC2 | 012V101/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 045
| K401 | 2026-02-04 | 2026-02-13 | 2025-11-11 | 2025-11-11 | 2102354095 | 8202238541 |  | 8202230212#Perbaikan ICCP LOC I | RU4-LOC1 | 40LTW03/00 | 50 | CRTD NMAT PRC | 4ER |  | 50000000 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-11 | PM |  | 045
| K201 | 2026-02-04 | 2026-03-05 | 2026-11-11 | 2026-11-11 | 2102351241 | 8202238540 |  | 8202230211#Doubling Pipa RWI KM 14 WPS S | RU2-UTL | 510-PIPING/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 3651324000 | 2738493000 | MA3-STA |  | AHILMANSYAH |  | 2026-02-11 | PT02 |  | 3 | 2026-11-11 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2025-11-11 | 2025-11-11 | 2102351169 | 8202238553 |  | 8202230210#Perbaikan Jalan dan Sarfas Pi | RU2-ITP |  | 50 | CRTD NMAT PRC RELR SETC | 2MR | D12/25/B6/NR-D2H | 3582250000 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-11 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-03 | 2025-12-03 | 2102351148 | 8202232317 |  | 8202230209#Pengadaan Gasket 220 E-8 | RU2-HOC | 220-E-8/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-11 | 2025-11-11 |  | 8202238187 | 8202234391 | 8202230208#Tag 2 TSA O2 Analyzer CDGP | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-11 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2027-01-20 | 2102358783 | 8202237717 |  | 8202230207#Pekerjaan Sewa Alat Berat pad | RU5-E15112 |  | 50 | REL NMAT PRC SETC | 5MR | D15/25/B6/NR-C2H | 1700000000 | 0 | WS-KAB |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-11-11 | 2102351243 | 8202232267 |  | 8202230206#abnormal noise | RU2-HCC | 211-P-16A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 28637253 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K401 | 2026-02-03 | 2026-05-07 | 2025-11-06 | 2025-11-06 | 2102354675 | 8202237670 |  | 8202230205#Tagihan Termin I UP Bordes OM | RU4-TRML | LN60-1216-A-10/00 | 60 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | ANGGIKAW |  | 2026-02-11 | PT02 |  | 3 | 2025-11-06 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-11-11 | 2102351330 | 8202232417 |  | 8202230204#High Vibration | RU2-HCC | 212-EF-22B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-06-18 | 2025-12-11 | 2025-12-11 | 2102363684 | 8202232429 |  | 8202230201#penambahan line pertadex dari | RU2-HCC | 212-P-15A/00 | 50 | REL CSER MANC PRC SETC | 2MR | D12/25/B6/NR-D2H | 20330269 | 0 | MA2-STA |  | MDSYAHPUTRA |  | 2026-02-07 | PT02 |  | 3 | 2025-12-11 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-11 | 2025-11-11 | 2102354964 | 8202235796 |  | 8202230200#Perbaikan motor 23E8AM | RU4-LOC1 | 23E8AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-11 | 2025-11-11 | 2102354961 | 8202235799 |  | 8202230199#Perbaikan motor 23E1M | RU4-LOC1 | 23E1M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-11 | 2025-11-11 | 2102354962 | 8202235797 |  | 8202230197#Perbaikan motor 23E4AM | RU4-LOC1 | 23E4AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-11-11 | 2102352119 | 8202232403 |  | 8202230196#CONMON High Vibrasi 520-P-608 | RU2-UTL | 520-P-608F/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-11-11 | 2102352118 | 8202232587 |  | 8202230195#MATERIAL Penyeharan 520-P-406 | RU2-UTL | 520-P-601A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 589000 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-11-11 | 2102351246 | 8202232453 |  | 8202230193#Perbaikan 550-B-1 | RU2-UTL | 550-B-1/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-11 | 2025-11-11 | 2102351298 | 8202232408 |  | 8202230192#High Vibration Gearbox | RU2-HCC | 211-EG-15A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 9687512 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-22 | 2026-01-13 | 2026-09-03 |  | 8202238497 | 8202232733 | 8202230190#SWO Cleaning 42-T-503 | RU6-ITP | 42-T-503/00 | 60 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 2787500 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-06 | 2025-11-06 | 2102352444 | 8202234258 |  | 8202230188#KEBOCORAN MECH SEAL 101-P6C | RU2S-KIL | 101-P-6C/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-10 | 2025-11-10 |  | 8202238496 | 8202235105 | 8202230187#Tag 7 Mekanik CDL, OM, UTL SG |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-10 | 2025-11-10 |  | 8202238490 | 8202234925 | 8202230186#Tag 4 Pemeliharaan RPA 1-5 & |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 045
| K201 | 2026-02-04 | 2026-04-15 | 2026-11-10 | 2026-11-10 | 2102351130 | 8202238549 |  | 8202230185#Doubling Pipa RWI KM 13 WPS S | RU2-UTL | 510-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 2300000000 | 0 | MA3-STA |  | AHILMANSYAH |  | 2026-04-15 | PT02 | 5 | 3 | 2026-11-10 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-21 | 2026-01-02 | 2026-01-02 | 2102358168 | 8202237669 |  | 8202230184#Pekerjaan Instalasi Lampu LED | RU4-TRML | 43P5A/00 | 50 | CRTD NMAT PRC RELR SETC | 4ER | D14/26/B6/RT-3-C2H | 100000 | 0 | MA4-LIS |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355266 | 8202240968 |  | 8202230183#25_Perbaikan 052TV277 Control | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356746 | 8202240966 |  | 8202230182#25_Perbaikan 151ZL691-791-891 | RU4-RFCUTL | 154FY-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 3 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357478 | 8202240964 |  | 8202230181#25_Perbaikan T. Gauge Flue Ga | RU4-RFCUTL | 151A501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 3 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356053 | 8202240962 |  | 8202230180#25_Perb Temp Superheater 520T | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-27 | 2025-10-27 | 2102354688 | 8202237024 |  | 8202230179#PENGGANTIAN 51 PCV 301 - 51G | RU4-UTL | 51G3/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-10-27 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354603 | 8202240960 |  | 8202230176#25_Penggantian Analyzer<(>&<) | RU4-RFCUTL | 152AT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-27 | 2025-10-27 | 2102354452 | 8202236983 |  | 8202230174#PENGGANTIAN 51PCV330 LP SEAL- |  |  | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-10-27 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-28 | 2025-10-28 | 2102354146 | 8202235924 |  | 8202230173#Membran Rusak 180LV601B | RU4-GTO |  | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-10-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-30 | 2102357576 | 8202240958 |  | 8202230172#25_PG Discharge Rusak 140P603 | RU4-GTO | 140PI045A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1328614 | 0 | MA7-INT |  | YOHANESMVIS |  | 2026-03-10 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356358 | 8202240956 |  | 8202230170#25_Boiler Skin Pressure 52B3 | RU4-UTL | 52B3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12867300 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356356 | 8202240953 |  | 8202230169#25_Pressure Furnace Draft 52B | RU4-UTL | 52B3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356450 | 8202240950 |  | 8202230168#25_Forced Draft Fan Pressure | RU4-UTL | 52B3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12867300 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356355 | 8202240947 |  | 8202230167#25_Pressure Flue Gas to Econo | RU4-UTL | 52B201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12867300 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356353 | 8202240944 |  | 8202230166#25_Boiler Skin Pressure 52B2 | RU4-UTL | 52B2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12867300 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356354 | 8202240941 |  | 8202230165#25_Forced Draft Fan Pressure | RU4-UTL | 52B2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12867300 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356352 | 8202240939 |  | 8202230164#25_Pressure Furnace Draft 52B | RU4-UTL | 52B2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356351 | 8202240937 |  | 8202230163#25_Boiler Skin Pressure 52B1 | RU4-UTL | 52B1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12867300 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356259 | 8202240935 |  | 8202230162#25_Forced Draft Fan Pressure | RU4-UTL | 52B1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 12867300 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356350 | 8202240933 |  | 8202230161#25_Pressure Furnace Draft 52B | RU4-UTL | 52B1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-10 | 2025-11-10 |  | 8202238184 | 8202235126 | 8202230160#Tag 4 Mekanik Area Utara OM |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-10 | 2025-11-10 |  | 8202238486 | 8302404613 | 8202230159#Tag 11 Supp. Teknisi Rope Acc | RU3-UTL | RPA3-P-001/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-10 | 2025-12-30 | 2102362392 | 8202233939 |  | 8202230156#Material Consumable Perbaikan | RU6-UTL | 53-P-102A-EN/01 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C2H | 448 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-20 | 2026-01-19 | 2026-01-19 | 2102356329 | 8202236081 |  | 8202230155#UP_26 Pekerjaan Wrapping di K |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | AKHMADRIZAL |  | 2026-02-07 | PT02 |  | 3 | 2026-01-19 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-01-23 |  | 8202232737 | 8202232733 | 8202230152#Spool Piece Pigging Line SPL | RU6-ITP | 42-T-503/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 1980 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355391 | 8202240931 |  | 8202230151#25_[CR] 011P105B excessive ax | RU4-FOC2 | 011P105B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 1860000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-10 | 2026-02-05 | 2102363281 | 8202233833 |  | 8202230150#Pengadaan Baru assy Pompa 34- | RU6-POC | 34-P-108A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 768 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2025-11-10 | 2025-11-10 |  | 8202237668 | 8202237537 | 8202230149#TGH3_CIV_CPS |  |  | 60 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-10 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-09 | 2026-07-01 | 2026-08-27 |  | 8202236112 |  | 8202230148#Upgrade LG kaca C-3-19AB ke L | RU5-E15112 | 03A-LT-464/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 8457372 | 0 | MA3-INT |  | RIANDAADI |  | 2026-02-07 | PT02 |  | 3 | 2026-07-01 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-01 | 2026-08-27 |  | 8202236114 |  | 8202230147#Upgrade LG kaca C-3-15AB ke L | RU5-E15112 | 03A-LT-345/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 8457372 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-01 | PM |  | 004
| K401 | 2026-02-02 | 2026-05-20 | 2025-11-10 | 2025-11-10 | 2102353521 | 8202234790 |  | 8202230143#RK_26-RT UP PENGECATAN MA-4 |  |  | 50 | CRTD NMAT PRC | 4MR | D14/09/B6/RTNH | 0 | 0 | MA4-STA |  | AKHMADRIZAL |  |  | PT02 |  | 2 | 2025-11-10 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-11-10 | 2025-11-10 | 2102355478 | 8202236204 |  | 8202230139#Perbaikan bocoran thermowell |  |  | 01 | CRTD NMAT PRC | 4MR | D14/09/B6/RT1-101-S0NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-11-10 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354427 | 8202240929 |  | 8202230138#25_Mtl. Bocoran Line Overhead | RU4-SRU | 92C402/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 14730480 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356770 | 8202240927 |  | 8202230137#25_Mtl. Cleaning HE 11E18 | RU4-FOC1 | 11E18A/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 8940532 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | 8202236131 | 8202238855 | 8202230136#MATERIAL PIPING PLANT HVU2&HP | RU5-E15112 | 2-SPW05-3-B6/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 158476824 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-27 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102354101 | 8202240925 |  | 8202230131#25_[CR] 84P211A Seal leak | RU4-KPC | 84P211A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2025-10-29 | 2102351200 | 8202232392 |  | 8202230126#Perbaikan Bearing 140 EM - 5F | RU2-HOC | 140-EM-5F/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351295 | 8202232236 |  | 8202230125#Perbaikan Motor 140 PM-1B | RU2-HOC | 140-PM-1B/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-11-03 | 2102351149 | 8202232459 |  | 8202230124#Perbaikan 520 PM 606 J | RU2-UTL | 520-P-606J/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2102357077 | 8202236299 |  | 8202230123#D25_Perbaikan Vibrasi 158VT60 | RU4-RFCUTL | 158VT-U158/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-INT |  | REHANR |  | 2026-02-07 | PT02 |  | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356051 | 8202240923 |  | 8202230122#25_Penggantian Snaplock Limit | RU4-UTL | 51G2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 4 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357512 | 8202240921 |  | 8202230120#25_[BON PNJM] Perb speed tach | RU4-RFCUTL | 154P507A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 53031638 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357510 | 8202240918 |  | 8202230117#25_[BON PNJM] Perb speed Aux | RU4-RFCUTL | 151B501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 79547457 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-05-25 | 2026-12-31 | 2102357219 | 8202240915 |  | 8202230114#25_[CR] Perbaikan Pompa 47P10 | RU4-TRML | 47P102B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-30 | 2025-10-28 | 2026-01-02 | 2102354396 | 8202237667 |  | 8202230113#Tagihan I Pekerjaan Perpipaan | RU4-KPC | LN81LP8001MS11/00 | 60 | REL GMCO NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | HERIOBM |  | 2026-02-11 | PT02 |  | 3 | 2025-10-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356717 | 8202240912 |  | 8202230112#25_80E202F house bearing noi | RU4-KPC | 80E202KF/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 10405503 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102356755 | 8202240909 |  | 8202230110#25_87P201B bila stand by mech | RU4-KPC | 87P201B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 10967700 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-12-15 | 2102362214 | 8202233178 |  | 8202230108#Perbaikan FDF Boiler 52-B-101 | RU6-UTL | 52-B-101B-K1-T/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/NR-C2H | 384 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-07 | 2025-11-07 |  | 8202238485 | 8202235263 | 8202230106#Tag 6 Perbaikan Jalan Kilang |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-07 | 2025-11-07 |  | 8202238476 | 8202234515 | 8202230105#Tag 14 Pemeliharaan Fire Exti | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-07 | 2025-11-07 |  | 8202238462 | 8202234515 | 8202230104#Tag 13 Pemeliharaan Fire Exti | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-07 | 2025-11-07 |  | 8202238451 | 8202235539 | 8202230102#Tag 1 Kontrak Volume Mekanik |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 045
| K301 | 2026-02-02 |  | 2025-11-07 | 2025-11-07 | 2102353237 | 8202235539 |  | 8202230101#Pekerjaan Kontrak Volume Meka |  |  | 50 | CRTD NMAT PRC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2025-11-07 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238432 | 8202234908 | 8202230099#Tag 27 Pemeliharaan Sepeda Ki | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-11-07 | 2025-11-07 |  | 8202238430 | 8202235629 | 8202230098#Tag 3 Hose Handling Area Derm |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-21 | 2025-11-07 | 2026-03-30 | 2102362397 | 8202238416 |  | 8202230097#Pekerjaan Sertifikasi LPS & E | RU6-ITP | GROUNDSYS42T402/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 1230000 | 0 | MA4-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 | 2102354663 | 8202238547 |  | 8202230095#Upgrade PLC N2 Plant 590 | RU4-UTL | 590A301K1/00 | 50 | CRTD CSER NMAT PRC | 4IR |  | 100000000 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-04 | 2026-05-04 | 2026-05-04 | 2026-07-02 | 2102362314 | 8202238414 |  | 8202230094#PERBAIKAN ATAP 21-K-101A & 21 | RU6-DHC | 21-K-101A-E1/00 | 50 | REL CSER NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 718000000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-05-04 | PT02 |  | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-06 | 2026-01-05 | 2102362108 | 8202233094 |  | 8202230093#Perbaikan Mech Seal Pompa 19- | RU6-RCC | 19-P-112A/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 512 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-17 | 2026-06-17 | 2102359881 | 8202236093 |  | 8202230092#Per Box lampu penerangan area | RU5-UTL | 1NV00DOO1-S1/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 51440000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357513 | 8202240906 |  | 8202230091#25_Penggantian Press Indikato | RU4-TRML | 32UV013A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 51917743 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-06 | 2025-11-06 | 2102356935 | 8202236656 |  | 8202230090#D_25 Motor 021P-104 noise | RU4-LOC2 | 021P104/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-06 | 2025-11-06 | 2102357515 | 8202236887 |  | 8202230089#D_25 011P117AM trip dengan k | RU4-FOC2 | 011P117AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357085 | 8202240903 |  | 8202230088#25_Pengadaan Material Meterin | RU4-TRML | 39PSV230A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 3 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-06 | 2025-11-06 | 2102356810 | 8202236896 |  | 8202230087#D_25 011P102AM: Pelumas motor | RU4-FOC2 | 011P102AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102355397 | 8202236392 |  | 8202230086#D25_HC masuk ke conduit 1st s | RU4-LOC3 | 260K101A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-02 | 2026-11-19 | 2102359138 | 8202236085 |  | 8202230084#Perbaikan Sensor Rod Drop K-3 | RU5-E15112 | K-3-02A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 107880000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 004
| K601 | 2026-02-02 |  | 2025-11-06 | 2025-11-06 |  | 8202236673 | 8202237825 | 8202230083#SWO LTSA PM Tangki 2025 Tghn | RU6-ITP | 42-T-101D/00 | 50 | CRTD NMAT PRC | 6MR | D16/25/B6/RT-C2H | 200957000 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355440 | 8202240900 |  | 8202230082#25_Central flange 024S-101B i | RU4-LOC2 | 024S101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102356456 | 8202240898 |  | 8202230080#25_[CR] Lube Oil Filter High | RU4-UTL | 560K601A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 53933334 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-07-09 | 2102358786 | 8202238545 |  | 8202230078#NRK_PenyehatanParit Piperack |  |  | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/25/B6/RT-D1H | 18346140 | 366922800 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357873 | 8202240895 |  | 8202230077#25_[CR] Perbaikan Turbin 051P | RU4-UTL | 051P101A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357950 | 8202240892 |  | 8202230076#25_[CR] PerbaikanTurbin 154P5 | RU4-RFCUTL | 154P507B-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 8933076 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-05 | 2026-03-06 | 2026-03-06 | 2102354260 | 8202240889 |  | 8202230075#25_[CR] 054P105C MS leak | RU4-UTL | 054P105C/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 2 | 0 | MA5-ROT |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357216 | 8202240886 |  | 8202230073#25_[CR] Pulley blade fan goya | RU4-LOC3 | 240E125K1/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 20475000 | 19091667 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352473 | 8202234257 |  | 8202230072#KEBOCORAN BOTTOM FLARE SPK | RU2S-KIL | 101-SK-001/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-06 | 2025-11-06 | 2102362312 | 8202233963 |  | 8202230070#Make Up Rocksalt 14-V-108 | RU6-DHC | 14-V-108/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-11-06 | 2025-11-06 | 2102352621 | 8202234256 |  | 8202230069#Pemeriksaan Temuan Scaling 90 | RU2S-KIL | 900-08B-2/01 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-19 | 2102361610 | 8202233462 |  | 8202230067#penggantian transmitter 33-PT | RU6-HSC | 33-PV-030/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-25 | 2026-01-02 | 2026-11-30 | 2102352467 | 8202234255 |  | 8202230066#KERUSAKAN EXPANSION JOINT TK- | RU2S-KIL | 10PL94601A-A1A1/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 0 | 82190000 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-30 | 2102361588 | 8202233214 |  | 8202230064#Perbaikan Bocoran Pompa 34-P- | RU6-POC | 34-P-110A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 512 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-12-15 | 2102362212 | 8202232963 |  | 8202230063#Perbaikan Pompa 39-K-101-P2 | RU6-POC | 39-K-101-P2/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/NR-C2H | 384 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-05 | 2025-11-05 | 2102357296 | 8202236677 |  | 8202230062#D_25 Kerusakan cover fan moto | RU4-LOC3 | 240K101M/00 | 50 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-05 | PM |  | 045
| K202 | 2026-02-02 | 2026-04-23 | 2026-01-02 | 2026-08-31 | 2102352463 | 8202234254 |  | 8202230061#Pengecekan Line Naptha 946-TK | RU2S-KIL | 6PL900001B-A1A1/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 5438228 | 4462082 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-05 | 2025-11-05 | 2102357953 | 8202236643 |  | 8202230060#D_25 Motor noise & vibrasi 24 | RU4-LOC3 | 240E116CM/00 | 50 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-05 | 2025-11-05 | 2102356121 | 8202236683 |  | 8202230059#D_25 Fan motor fin fan lepas | RU4-LOC3 | 260E172M3/00 | 50 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102356812 | 8202240883 |  | 8202230057#25_[PdM] 011P106A high vibras | RU4-FOC2 | 011P106A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 92250000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354617 | 8202240880 |  | 8202230056#25_[CR] Perbaikan mech seal 2 | RU4-LOC1 | 24P2A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-07 | 2025-11-03 | 2025-11-03 | 2102358373 | 8202238006 |  | 8202230055#Pengadaan material tools TA R |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 1 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-07 | 2025-11-07 | 2102351758 | 8202232612 |  | 8202230051#Perbaikan Pompa 220 P-1B | RU2-HOC | 220-P-1B/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 3347126 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-07 | 2025-11-07 | 2102351959 | 8202232475 |  | 8202230050#Perbaikan 220 E-11 | RU2-HOC | 220-E-11/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 1719526 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-07 | 2025-11-07 | 2102351138 | 8202232497 |  | 8202230049#Perbaikan 140 EF-23 | RU2-HOC | 140-EF-23A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 11574466 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-02 | 2026-03-31 | 2026-12-30 | 2102351392 | 8202238410 |  | 8202230048#Kontrak Semenisasi All Area R | RU2-HOC | 3-MS-11025-A2A2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 700000000 | 0 | MA1-STA |  | ERLANGGA |  | 2026-03-31 | PT02 |  | 3 | 2026-03-31 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-04-15 | 2026-10-13 | 2102362767 | 8202232733 |  | 8202230047#Superior Order Aktivasi Line | RU6-ITP | 42-T-503/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 15840 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-26 | 2025-11-07 | 2026-12-21 |  | 8202238537 |  | 8202230046#LTSA Gantry,Clamshell&Decokin | RU2-HOC | 140-PC-51/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA1-ROT |  | ADEMULYADI |  | 2026-03-10 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-19 | 2026-02-02 | 2026-02-02 | 2102352477 | 8202234253 |  | 8202230044#Pemasangan Press Gauge Disch | RU2S-KIL | 946-P-8A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 7200000 | 7200000 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-09 | 2026-01-02 | 2026-08-31 | 2102352450 | 8202234252 |  | 8202230043#KEBOCORAN POMPA 101-P-11 | RU2S-KIL | 101-P-11/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RS | D12/26/B6/NRZ-C1H | 1620000 | 1620000 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2102354148 | 8202237666 |  | 8202230042#Tagihan termin 8,9,10 Perbaik | RU4-UTL | 051G101/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | EDWINK |  | 2026-02-11 | PT02 |  | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-02-03 | 2026-06-18 | 2026-01-02 | 2026-01-02 | 2102356124 | 8202237665 |  | 8202230040#Repeat Order Elevator RFCC | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 1610000000 | 563500000 | MA6-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-05 | 2025-11-05 | 2102356814 | 8202236450 |  | 8202230038#D25_014BV-42 selenoid rusak | RU4-FOC2 | 014BV42/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-05 | 2025-11-05 | 2102355027 | 8202236443 |  | 8202230037#D25_048K102C SOV seal water t | RU4-FOC2 | 019K102C/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355026 | 8202240877 |  | 8202230036#25_018PIC-023 Penunjukan mera | RU4-FOC2 | 018PV023/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 15000000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-12 | 2102361744 | 8202233465 |  | 8202230035#penggantian Transmitter 32-PI | RU6-HSC | 32-A-110/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-17 | 2025-12-17 | 2102354459 | 8202236452 |  | 8202230034#D25_014 FIC-021 ( pass 2 014 | RU4-FOC2 | 014FT021/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-29 | 2025-10-29 | 2102357871 | 8202235317 |  | 8202230033#Panel lokal 022K-101 korosif | RU4-LOC2 | 022K101/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-10-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-17 | 2025-12-17 | 2102357814 | 8202236471 |  | 8202230032#D25_011FIC-018 & 011PDIC-701 | RU4-FOC2 | 011FI018/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-17 | 2025-12-17 | 2102357813 | 8202236465 |  | 8202230031#D25_011TI031 Putus | RU4-FOC2 | 011F101B/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355001 | 8202240875 |  | 8202230030#25_CV inlet dan drain sootblo | RU4-KPC | 84F201LMP/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355004 | 8202240872 |  | 8202230029#25_CV inlet dan drain sootblo | RU4-KPC | 87F201LMP/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-29 | 2025-10-29 | 2102354269 | 8202236092 |  | 8202230028#Perbaikan Control Valve 120FV | RU4-GTO | 120FV022/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-10-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2025-11-05 | 2025-11-05 | 2102357572 | 8202236304 |  | 8202230027#D25_Perbaikan Spike 101XV638 | RU4-RFCC | 101PV638/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2025-12-01 | 2025-12-01 | 2102357177 | 8202240869 |  | 8202230026#25_(BON PINJAM) Penggantian G | RU4-RFCC | 101A525A/00 | 60 | CLSD MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 682503 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355007 | 8202240866 |  | 8202230025#25_CV inlet dan drain sootblo | RU4-KPC | 85F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-05 | 2025-11-05 | 2102356856 | 8202236391 |  | 8202230024#D25_Kerusakan penunjukan 240S | RU4-LOC3 | 240S101A/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-05 | 2025-11-05 | 2102351679 | 8202232289 |  | 8202230023#702-EF-13E bearing dan pulley | RU2-HCC | 702-EF-13E/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102352032 | 8202232545 |  | 8202230022#Mechanical Seal Bocor | RU2-HCC | 211-P-14A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-18 | 2025-11-03 | 2026-01-29 | 2102361928 | 8202233763 |  | 8202230021#Pengadaan pompa 53-P-203A | RU6-UTL | 53-P-203A-M/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 768 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-02-18 | PT02 |  | 3 | 2025-11-03 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2026-01-30 | 2102361584 | 8202232905 |  | 8202230020#Perbaikan PSA | RU6-DHC | 22-A-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-03 | 2102362632 | 8202232926 |  | 8202230019#Perbaikan Positioner 33PV030 | RU6-HSC | 33-PV-030/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-12 | 2026-03-12 | 2026-12-30 |  | 8202237664 | 8202238635 | 8202230018#TGH25_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 228509000 | 0 | MA5-INT |  | REHANR |  | 2026-02-07 | PT02 |  | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2025-11-04 | 2025-11-04 |  | 8202237663 |  | 8202230016#TGH11_22 TSA FGDS GM & Deluge | RU4-FOC2 | 011AT323/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 1361133000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237662 |  | 8202230015#TGH21-25_23 TSA 11 Unit GC KP | RU4-KPC | DCS-KPC/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 |  | 2025-11-04 | 2025-11-04 | 2102354045 | 8202235408 |  | 8202230012#NRKAP 2025, Mat' Fitting & Va | RU4-UTL | 520B301/00 | 01 | CRTD CSER MACM PRC | 4MO | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-STA |  |  |  |  | PT02 |  | 2 | 2025-11-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356800 | 8202240863 |  | 8202230011#2025_Penggantian Motor 14P5B | RU4-FOC1 | 14P5BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-11-13 | 2102362250 | 8202233318 |  | 8202230009#Perbaikan 19-FT-002 | RU6-RCC | 19-FT-002/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 90 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354534 | 8202240860 |  | 8202230008#26_56K3A ganti cooler | RU4-UTL | 56K3A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354532 | 8202240858 |  | 8202230005#26_56K3B ganti cooler | RU4-UTL | 56K3B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-04 | 2025-12-24 | 2102362104 | 8202233173 |  | 8202230004#Perbaikan Fin Fan 20-E-104A | RU6-RCC | 20-E-104A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 474 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356818 | 8202240855 |  | 8202230003#25_[CR] Perbaikan Stroke 103P | RU4-RFCC | 103P501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-19 | 2025-11-04 | 2025-11-04 | 2102353312 | 8202234877 |  | 8202230000#Pompa 2005 JB Mech Seal Bocor | RU3-UTL | 2005-JB/00 | 60 | CLSD CNF CSER MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 160089927 | 0 | MA2-ROT |  | SAPBATCH | 2025-11-04 | 2026-02-07 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357229 | 8202237661 |  | 8202229999#TGH6_25 UP MON&INSP PERALATN | RU4-FOC1 | 11P10AM-CB/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2026-01-30 | 2102361920 | 8202232908 |  | 8202229993#Perbaikan Pressure Gauge Area | RU6-DHC | 14-PV-015A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-05 | 2025-11-05 | 2102351296 | 8202232282 |  | 8202229992#Pengadaan Governor 140 PT-51 | RU2-HOC | 140-PT-51A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-05 | 2025-11-05 | 2102351393 | 8202232637 |  | 8202229991#Pengambilan Material 110-PT-3 | RU2-HOC | 110-PT-3B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 188791 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-11-17 | 2102361960 | 8202233152 |  | 8202229990#Perbaikan Instrumentasi Feed | RU6-DHC | 12-J-501/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 141 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-05 | 2025-11-05 | 2102351297 | 8202232636 |  | 8202229989#Pengambilan Material 140 PT-5 | RU2-HOC | 140-PT-51A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-05 | 2025-11-05 | 2102351292 | 8202232619 |  | 8202229988#Perbaikan Pompa 140 P-1B | RU2-HOC | 140-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 334219 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-12 | 2102362100 | 8202232841 |  | 8202229987#Perbaikan tubing 52-FT-206 da | RU6-UTL | 52-FT-206A/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 384 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-03 | 2025-12-12 | 2102362102 | 8202233627 |  | 8202229986#Penggantian I to P 058-PV-503 | RU6-UTL | 058-PV-503A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 384 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-11-03 | 2102351160 | 8202232492 |  | 8202229985#Motor Vibrasi | RU2-HCC | 840-PM-4B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 898119 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-31 | 2025-10-31 | 2102351167 | 8202232255 |  | 8202229984#Perbaikan Main Breaker MCC 21 | RU2-UTL | 212-EM-C-20C/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-05-04 | 2026-05-04 | 2102358836 | 8202236015 |  | 8202229983#Pergantian Altenator DEG 2 | RU5-UTL | 2AL1010/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-05-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-27 | 2025-12-11 | 2102361629 | 8202233053 |  | 8202229982#Perbaikan Motor 15SLV101M1 | RU6-RCC | 15-SLV-101/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 435 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-31 | 2025-12-15 | 2102361878 | 8202233246 |  | 8202229981#Perbaikan aksesoris Instrumen | RU6-UTL | 52-B-101F/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 410 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-01-28 | 2026-01-28 | 2102351806 | 8202232432 |  | 8202229980#TOOLS IRSM DAN THERMAL IMAGIN | RU2-UTL | 925-P-7C/00 | 50 | REL GMPS MACM PRC SETC | 2RR | D12/26/B6/NR-D2H | 0 | 1270000000 | MA3-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-28 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-30 | 2025-12-10 | 2102361791 | 8202233436 |  | 8202229979#Penggatian Air inlet filter 0 | RU6-UTL | 059-A-101B-K1/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 384 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-30 | 2025-12-10 | 2102361797 | 8202233645 |  | 8202229978#Penggantian filter LO pompa 5 | RU6-UTL | 56-P-101A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 384 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-31 | 2025-12-17 | 2102361837 | 8202233442 |  | 8202229977#Penggantian valve Desuperheat | RU6-UTL | 52-TV-219E/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 435 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-03 | 2025-12-18 | 2102362000 | 8202233695 |  | 8202229976#Penggantian bearing motor 52- | RU6-UTL | 52-B-101A-K1-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 148322 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-03 | 2025-11-03 | 2102354606 | 8202235809 |  | 8202229975#Perbaikan motor 21P-3A | RU4-LOC1 | 21P3AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 045
| K201 | 2026-02-04 |  | 2025-10-31 | 2025-10-31 | 2102351162 | 8202238536 |  | 8202229973#Pengadaan Test Bench 3,3kV ut | RU2-WS | PC-01/00 | 01 | CRTD NMAT PRC | 2ER | D12/25/B6/NR-D2H | 3000000000 | 0 | WS-LI2 |  |  |  |  | PT02 |  | 2 | 2025-10-31 | PM |  | 001
| K202 | 2026-02-02 | 2026-06-03 | 2026-01-11 | 2026-11-30 | 2102352186 | 8202234251 |  | 8202229969#FIRE TRUCK AFT 2 | RU2S-LKKK | 946-PIPING-F-CH/00 | 50 | REL PRC SETC | 2MS | D12/26/B6/RTZ-C2H | 0 | 0 | MAS-ME2 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-11 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2025-10-27 | 2025-10-27 | 2102353266 | 8202235506 |  | 8202229964#Kerusakan Level Glass di Deae | RU3-UTL | 54-LCV-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354893 | 8202240852 |  | 8202229961#25_[BD] Perbaikan Turbin 52P2 | RU4-UTL | 52P2B-T/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 11571300 | 11571300 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355380 | 8202240849 |  | 8202229960#25_[RP] 014K102P3A Penggantia | RU4-FOC2 | 014K102P3A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2025-11-03 | 2025-12-31 |  | 8202237933 |  | 8202229959#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-09 | 2025-10-29 | 2026-01-05 |  | 8202237932 | 8202232767 | 8202229958#Penyelesaian PMPDM Elect&Inst | RU6-POC | GROUNDSYS-39/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-09 | 2025-10-29 | 2025-10-29 | 2102361729 | 8202232767 |  | 8202229957#PM/PDM Electrical & Instrumen | RU6-POC | GROUNDSYS-39/00 | 01 | CLSD NCMP NMAT PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-08-07 | 2026-08-07 | 2102360145 | 8202236029 |  | 8202229956#Perbaikaan Junction Box Ban S | RU5-UTL | GM-34-130A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 51440000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-08-07 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2025-11-03 | 2025-11-03 | 2102358374 | 8202234630 |  | 8202229954#Perbaikan Rotor & Re-Wending | RU7-CDU | 1-PM-03A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355971 | 8202240847 |  | 8202229952#25_Korosi pada chamber 260LT0 | RU4-LOC3 | 260LT072/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354891 | 8202240845 |  | 8202229950#25_Kerusakan pada 240HIC001AB | RU4-LOC3 | 240S101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-03 | 2025-11-03 | 2102353975 | 8202236396 |  | 8202229949#D25_FI Cold wash rusak 240S10 | RU4-LOC3 | 240FT012A/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 |  | 8202238535 |  | 8202229948#Pemeriksaan Peralatan Pressur | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1000000000 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-06 | 2026-02-07 | 2025-10-31 | 2025-10-31 | 2102351203 | 8202238690 |  | 8202229947#Perbaikan Roof 100-H-1 | RU2-HSC | 100-H-1/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 10 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357579 | 8202240843 |  | 8202229946#25_Penggantian Power supply P | RU4-LOC1 | 24K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357628 | 8202240841 |  | 8202229944#25_Penggantian Valve Bundwall | RU4-TRML | 43T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357626 | 8202240839 |  | 8202229941#25_Peng. Valve Bundwall Unit | RU4-TRML | 38T105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 112374445 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357625 | 8202240837 |  | 8202229940#25_Penggantian Valve Bundwall | RU4-TRML | 36T101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357624 | 8202240836 |  | 8202229939#25_Penggantian Valve Bundwall | RU4-TRML | 35T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357623 | 8202240834 |  | 8202229938#25_Penggantian Valve Bundwall | RU4-TRML | 34T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357622 | 8202240832 |  | 8202229937#25_Penggantian Valve Bundwall | RU4-TRML | 33T101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355830 | 8202240830 |  | 8202229936#25_Penggantian valve bundwall | RU4-TRML | 42T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2027-01-20 | 2102358787 | 8202235953 |  | 8202229935#Perbaikan Saluran Return TU 1 | RU5-UTL | U-11/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355832 | 8202240828 |  | 8202229933#25_Penggantian valve bundwall | RU4-TRML | 49T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 12478680 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-03 | 2026-06-08 | 2025-10-31 | 2025-12-30 |  | 8202237931 | 8202232731 | 8202229927#LTSA PEMELIHARAAN RUTIN MA 2 | RU6-DHC | 12-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354109 | 8202240826 |  | 8202229925#25_[Upgrd] API Plan 87P202C | RU4-KPC | 87P202C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-31 | 2025-10-31 |  | 8202235614 | 8202234622 | 8202229924#Perbaikan Plenum KPC | RU4-KPC | 82E201A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2025-10-27 | 2025-12-30 | 2102361622 | 8202236711 |  | 8202229923#SPK LTSA Refacing Thp 4 15-V- | RU6-RCC | 15-V-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K501 | 2026-02-03 | 2026-03-09 | 2026-01-02 | 2027-01-20 | 2102358785 | 8202237713 |  | 8202229922#Rejuvenate Line Utility Water | RU5-UTL | PIPA-WTP-PCR/00 | 50 | REL NMAT PRC SETC | 5MR | D15/25/B6/NR-C2H | 2275000000 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-11 | 2025-10-29 | 2025-12-30 | 2102361685 | 8202236712 |  | 8202229921#SPK LTSA Refacing Thp 3 | RU6-ITP | 42-PIPE/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-31 | 2026-01-29 |  | 8202232919 |  | 8202229919#Perbaikan Press Gauge 24-P-20 | RU6-HSC | 24-P-204/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-31 | 2026-01-29 |  | 8202232922 |  | 8202229918#Perbaikan Press Gauge 11-P-12 | RU6-HSC | 11-P-123/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-31 | 2026-01-14 |  | 8202232923 |  | 8202229917#Perbaikan Press Gauge 11-P-11 | RU6-HSC | 11-P-114B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 640 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-10-19 | 2026-10-19 | 2102358883 | 8202235970 |  | 8202229916#Per. Lampu Sorot LED AREA UTI |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 107225700 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-10-19 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-10-14 | 2026-10-14 | 2102360056 | 8202235955 |  | 8202229915#Perbaikan Kompresor HVAC SS 6 | RU5-UTL | 41-R-SS-66/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1208471 | 0 | WS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-10-14 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102358976 | 8202235989 |  | 8202229914#MAT.PERB.LG C-3-35A: Suct 1st | RU5-E15112 | C-3-35A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 271541894 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102358977 | 8202235987 |  | 8202229913#MAT.PERB.LG C-3-35B: Suct 1st | RU5-E15112 | C-3-35B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102358978 | 8202235985 |  | 8202229912#MAT.PERB.LG C-3-35C: Suct 1st | RU5-E15112 | C-3-35C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102358979 | 8202235984 |  | 8202229911#MAT.PERB.LG C-3-37A: Suct 2nd | RU5-E15112 | C-3-37A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102359000 | 8202235983 |  | 8202229910#MAT.PERB.LG C-3-37B: Suct 2nd | RU5-E15112 | C-3-37B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102359001 | 8202235981 |  | 8202229909#MAT.PERB.LG C-3-37C: Suct 2nd | RU5-E15112 | C-3-37C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-27 | 2026-03-26 |  | 8202235957 | 8202234940 | 8202229908#Perbaikan Actuator Backwash F | RU5-E15112 | 03-FCV-020/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 66960006 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102359002 | 8202235978 |  | 8202229907#MAT.PERB.LG C-3-39AB: Suct 3r | RU5-E15112 | C-3-39A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102359003 | 8202235976 |  | 8202229906#MAT.PERB.LG C-3-39CD: Suct 3r | RU5-E15112 | C-3-39C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-06-08 | 2102359004 | 8202235974 |  | 8202229905#MAT.PERB.LG C-3-39EF: Suct 3r | RU5-E15112 | C-3-39E/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357575 | 8202240823 |  | 8202229904#25_Noise Motor Finfan 140E607 | RU4-GTO | 140E607D-A/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 65634400 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2025-10-29 | 2102361687 | 8202233022 |  | 8202229903#Perbaikan motor mixer 42-M-10 | RU6-ITP | 42-M-101G1-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 147887 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2025-12-11 | 2102361799 | 8202233191 |  | 8202229902#Perbaikan Control Valve 62-PV | RU6-UTL | 62-PV-104B/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 397 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-28 | 2026-04-27 | 2026-12-10 | 2102357578 | 8202235839 |  | 8202229899#Perbaikan modul OST 24K2 | RU4-LOC1 | 24K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-28 | PT02 |  | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-30 | 2025-10-30 | 2102355945 | 8202236630 |  | 8202229898#D_25 Motor short 240S101AM2 | RU4-LOC3 | 240S101AM2/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102355334 | 8202236044 |  | 8202229894#Kerusakan kontaktor di 39P202 | RU4-TRML | 39P202A/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-05-12 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-15 | 2026-09-10 | 2102359898 | 8202235947 |  | 8202229892#Perbaikan Level Controller 05 | RU5-E15111 | E-5-16/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-15 | PM |  | 004
| K401 | 2026-02-03 | 2026-03-12 | 2026-01-02 | 2026-12-30 | 2102356853 | 8202237660 |  | 8202229891#RKAP 2026 Penambahan unit AC | RU4-FOC2 | 002SS11/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 100000 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-09 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354597 | 8202240820 |  | 8202229888#25_Pengadaan Ignitor 520B601 | RU4-UTL |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-30 | 2025-10-30 | 2102355894 | 8202235818 |  | 8202229884#Perbaikan motor 21FDF saat st | RU4-LOC1 | 21F1M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-30 | 2025-10-30 | 2102355899 | 8202235795 |  | 8202229883#Perbaikan motor 23E8M saat st | RU4-LOC1 | 23E8BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-30 | 2025-10-30 | 2102355897 | 8202235803 |  | 8202229882#Perbaikan motor 21P13BM saat | RU4-LOC1 | 21P13BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355365 | 8202240799 |  | 8202229881#25_[PV] Tindak Lanjut Temuan | RU4-RFCUTL | 158A501-K1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355368 | 8202240796 |  | 8202229880#25_[PV] Tindak Lanjut Temuan | RU4-RFCUTL | 158A501-K1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357879 | 8202240794 |  | 8202229879#25_[PV] Penggantian Worm Gear | RU4-FOC1 | 14K1T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2026-08-04 | 2102361795 | 8202233004 |  | 8202229878#Perbaikan pompa | RU6-ITP | 42-P-404D/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-08 | 2026-03-06 | 2026-03-06 | 2102354421 | 8202240792 |  | 8202229877#25_[CR] Tindak Lanjut Temuan | RU4-UTL | 560K301/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | ABDULFM |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-26 | 2102361937 | 8202233508 |  | 8202229876#Penggantian selenoid 51-UY-20 | RU6-UTL | 51-G-101E-GV/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 9240 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-10-27 | 2025-12-30 |  | 8202236611 | 8202236738 | 8202229874#SWO SPK LTSA NDT Thp 8 | RU6-ITP | 42-T-404H/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-10-27 | 2025-12-30 |  | 8202236612 | 8202236740 | 8202229873#SWO SPK LTSA NDT Thp 7 | RU6-ITP | 42-T-402A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2026-01-28 |  | 8202232913 |  | 8202229872#Perbaikan Press Gauge 64-P-10 | RU6-HSC | 64-P-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2026-01-28 | 2102363514 | 8202233412 |  | 8202229871#Perbaikan 11-XY-003A | RU6-HSC | 11-PDV-089/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2026-03-13 | 2102363431 | 8202233311 |  | 8202229870#Perbaikan 21-LT-013 | RU6-DHC | 57-LT-401/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1284 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K601 | 2026-02-01 |  | 2025-10-30 | 2026-03-13 | 2102361148 | 8202233377 |  | 8202229869#Perbaikan 13-FT-279 | RU6-DHC | 13-FT-279/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA2-INT |  |  |  |  | PT02 |  | 2 | 2025-10-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354124 | 8202240790 |  | 8202229868#25_Pulley motor 024E-123 M2 r | RU4-LOC2 | 024E123/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 4700000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2027-01-20 | 2102360081 | 8202235949 |  | 8202229865#Penggantian Valve Discharge R | RU5-UTL | 0UC-30-D001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 | 2102356163 | 8202238530 |  | 8202229864#Kontrak Conmon & PM Peralatan | RU4-FOC1 | 11P23BM/00 | 50 | CRTD NMAT PRC | 4ER |  | 40000000 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355246 | 8202240788 |  | 8202229863#25_85S201A Cleaning catridge | RU4-KPC | 85S201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 7200000 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 | 2102354163 | 8202238529 |  | 8202229862#Penggantian ICCP Tanki Area 7 | RU4-TRML | 70LTW6/00 | 50 | CRTD NMAT PRC | 4ER |  | 289952430 | 0 | MA3-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2026-01-27 | 2102361977 | 8202232807 |  | 8202229861#Permanent Repair Blower 55-A- | RU6-UTL | 55-A-101C-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 768 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354829 | 8202240786 |  | 8202229860#25_Modul MET Temperature Wind | RU4-RFCGTO | 105K501M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-08 | 2026-12-31 | 2026-12-31 | 2102352662 | 8202235882 |  | 8202229859#Rejuvinate PSV tahap III | RU3-CDGP | CD5-1-1/00 | 50 WAMA | REL MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 4317167000 | 0 | MA1-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-12-31 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102363184 | 8202233742 |  | 8202229857#Pengadaan Wheel Gear 19-K-101 | RU6-RCC | 19-K-101-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2025-10-29 | 2102351516 | 8202232609 |  | 8202229856#perbaikan pompa 920-P-1 B | RU2-ITP | 920-P-1B/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2025-10-29 | 2102352037 | 8202232577 |  | 8202229855#MATERIAL Re-centering Kaki Po | RU2-UTL | 905-P-58/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2025-10-29 | 2102363756 | 8202232584 |  | 8202229853#MATERIAL Penyehatan 520-CL-05 | RU2-UTL | 520-CL-05/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-19 | 2026-06-18 | 2026-09-14 | 2102361787 | 8202232996 |  | 8202229852#Perbaikan Pompa 12-P-501A | RU6-DHC | 12-P-501A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 315988640 | 0 | MA2-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355117 | 8202240784 |  | 8202229851#25_[CR] Noise dan Vibrasi 220 | RU4-LOC3 | 220K101/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 13066000 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2025-10-29 | 2025-10-29 |  | 8202237659 | 8202237512 | 8202229850#TGH20_23 TSA ConMon Instrumen | RU4-RFCC | 101FJB001/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 368432000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102361674 | 8202233644 |  | 8202229849#Penggantian Filter LO Pump 14 | RU6-DHC | 14-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2025-10-29 | 2025-10-29 |  | 8202237658 | 8202238640 | 8202229848#TGH5_24 PM Field Instrument M | RU4-KPC | 80FT205/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102362169 | 8202232980 |  | 8202229847#Perbaikan Pompa 19-P-111B | RU6-RCC | 19-P-111B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356460 | 8202240781 |  | 8202229846#25_017PT-001 rusak | RU4-FOC2 | 017PT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 21345221 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356393 | 8202240780 |  | 8202229845#25_011FT-049 rusak | RU4-FOC2 | 011FT049/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 21345221 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356391 | 8202240778 |  | 8202229844#25_011FT-009 Rusak | RU4-FOC2 | 011FT009/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102362648 | 8202233797 |  | 8202229843#Pengadaan Material 13-K-101-P | RU6-DHC | 13-K-101-P2A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102362415 | 8202232886 |  | 8202229841#Perbaikan Sighglass 12-P-503B | RU6-DHC | 12-P-503B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2026-01-26 | 2102362486 | 8202232995 |  | 8202229840#Perbaikan Pompa 12-P-507A | RU6-DHC | 12-P-507A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 768 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-15 | 2026-04-07 | 2102362624 | 8202232958 |  | 8202229839#Perbaikan Pompa 42-P-206B | RU6-ITP | 42-P-206B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 6600 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-15 | PM |  | 003
| K601 | 2026-02-04 | 2026-03-06 | 2026-03-06 | 2026-07-29 | 2102361578 | 8202238407 |  | 8202229838#Perbaikan junction box area O | RU6-ITP | 42-T-107D/00 | 50 | REL NMAT PRC SETC | 6ER | D16/26/B6/NR-C2H | 360000000 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-03-03 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102363424 | 8202233128 |  | 8202229837#Perbaikan Kopmresor 22-K-101C | RU6-DHC | 22-K-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-10-29 | 2025-10-29 |  | 8202237657 | 8202237629 | 8202229836#TGH2_SIP_Pengecetan MA 1 2024 | RU4-FOC1 | LN12-1055LA/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-10-29 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-02 | 2102361725 | 8202233448 |  | 8202229834#penggantian valve 2nd stage 3 | RU6-HSC | 32-K-102B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 576 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-15 | 2102361389 | 8202232947 |  | 8202229832#Perbaikan pompa 53-P-305A | RU6-UTL | 53-P-305A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 5940 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355197 | 8202240776 |  | 8202229830#25_[CR] Alignment Precut Shim | RU4-UTL | 54P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2025-12-23 | 2102363484 | 8202233113 |  | 8202229829#Perbaikan Loader Valve 2nd 12 | RU6-DHC | 12-K-501B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 512 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-10-27 | 2025-12-30 | 2102361647 | 8202236738 |  | 8202229827#SPK Cleaning Sp Tank Thp 7 40 | RU6-ITP | 42-T-404H/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2025-10-30 | 2025-10-30 | 2102356698 | 8202237656 |  | 8202229824#TGH1_SIP_UP Quick Release Hoo | RU4-TRML | 70CIB-BD4/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-10-30 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-26 | 2102362125 | 8202233548 |  | 8202229823#Penggantian Pompa 63-P-203B | RU6-ITP | 63-P-203B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 768 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102362238 | 8202233647 |  | 8202229822#Penggantian Filter LO 14-K-10 | RU6-DHC | 14-K-102A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-10-27 | 2025-12-30 | 2102361641 | 8202236740 |  | 8202229821#SPK Cleaning Sp Tank Thp 6 40 | RU6-ITP | 42-T-402A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K501 | 2026-02-04 | 2026-06-17 | 2026-06-11 | 2026-07-01 | 2102358789 | 8202238405 |  | 8202229820#NRK_Insp. ECT HE Plant2 Pit S | RU5-E15112 | E-2-09/00 | 50 | REL GMPS NMAT PRC SETC | 5MR | D15/26/B6/NR-C3H | 3490000 | 296650000 | ENG-STA |  | FAUZANR |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-29 | 2026-01-30 | 2102361721 | 8202233138 |  | 8202229819#Perbaikan kebocoran trafo di | RU6-ITP | 23-PTR1-01B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1296 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K501 | 2026-02-05 | 2026-05-13 | 2026-01-19 | 2026-03-03 | 2102358788 | 8202238651 |  | 8202229818#NRK_PERB. HE Plant2 & 8B Pit | RU5-E15112 | E-2-09/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 13800000 | 1173000000 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-07 | PT02 |  | 3 | 2026-05-13 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-25 | 2102361075 | 8202232930 |  | 8202229817#Perbaikan Posisioner 33-FV-03 | RU6-HSC | 33-FV-032/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-02-04 | 2102362850 | 8202233050 |  | 8202229816#Perbaikan motor 16-E-120P | RU6-RCC | 16-E-120P-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 384 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-27 | 2102361382 | 8202233344 |  | 8202229815#Perbaikan 15-PTR-01-B | RU6-HSC | 15-PTR1-01B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 42726000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357472 | 8202240774 |  | 8202229813#25_[CR] Baut Coupling Rusak 1 | RU4-RFCGTO | 105P504A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102362870 | 8202233830 |  | 8202229812#Pengadaan Belt Mixer 42-M-302 | RU6-ITP | 42-M-302B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 640 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-01-09 | 2102363090 | 8202233547 |  | 8202229811#Penggantian Pompa 63-P-302A ( | RU6-ITP | 63-P-302A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 640 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-15 | 2026-05-13 | 2102358794 | 8202235935 |  | 8202229808#Perbaikan Transmitter 02-LT-0 | RU5-E15112 | 02-LT-074/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 115393332 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-28 | 2025-12-29 | 2102363288 | 8202233584 |  | 8202229806#Penggantian Membran Coupling | RU6-HSC | 24-P-302B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 550 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K201 | 2026-02-04 | 2026-03-25 | 2026-03-17 | 2026-03-17 | 2102351202 | 8202238404 |  | 8202229805#Jasa Engineering New Pipe Rac | RU2-ITP | TRE-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 899000000 | 0 | MA4-STA |  | ERLANGGA |  | 2026-02-19 | PT02 |  | 3 | 2026-03-17 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-31 | 2102361898 | 8202233201 |  | 8202229804#Perbaikan Compressor 12-K-502 | RU6-DHC | 12-K-502A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 1280 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-10 | 2102362192 | 8202233000 |  | 8202229802#Perbaikan Pompa 11-P-114A (Bo | RU6-HSC | 11-P-114A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2025-10-28 | 2025-10-28 |  | 8202237655 | 8202237513 | 8202229801#TGH35-36_22 Sewa CCTV Tanki 4 | RU4-RFCGTO | 47T511A/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 116661000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-24 | 2026-02-02 | 2026-07-10 | 2102362722 | 8202233097 |  | 8202229799#Perbaikan Mech Seal IB 11-P-1 | RU6-HSC | 11-P-102B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 226026667 | 208050000 | MA1-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362919 | 8202233088 |  | 8202229798#Perbaikan Mechseal O/B 12-P-5 | RU6-DHC | 12-P-511B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-11 | 2102363264 | 8202233185 |  | 8202229797#Perbaikan Couple 12-A-501-P1B | RU6-DHC | 12-A-501-P1B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363313 | 8202233552 |  | 8202229796#Penggantian Pompa 15-SLV-101M | RU6-RCC | 15-SLV-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363381 | 8202233486 |  | 8202229795#Penggantian Tapper Bush Motor | RU6-UTL | 56-K-101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-28 | 2025-12-08 | 2102361580 | 8202234097 |  | 8202229794#12/13-P-101 | RU6-DHC | 12-P-101/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 384 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102361431 | 8202232997 |  | 8202229793#Perbaikan Pompa 12-A-502-P1 | RU6-DHC | 12-A-502-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K301 | 2026-02-04 | 2026-02-11 | 2025-10-28 | 2025-10-28 |  | 8202238403 | 8202235085 | 8202229792#Tag 9 Isolasi Panas Area CD&G |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-10-28 | 2025-10-28 |  | 8202238137 | 8302402794 | 8202229791#Tag 6 TSA-PM DCS Honeywell (5 | RU3-UTL | B72-LT-2/00 | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2025-10-28 | 2025-10-28 |  | 8202238480 | 8202235318 | 8202229790#Tag 1 KV Listrik Area Oil Mov |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 045
| K301 | 2026-02-02 |  | 2025-10-28 | 2025-10-28 | 2102353268 | 8202235318 |  | 8202229789#Kontrak Volume Listrik Area O |  |  | 01 | CRTD NMAT PRC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2025-10-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-28 | 2025-10-28 | 2102354581 | 8202236057 |  | 8202229788#Perbaikan Exhaust Fan Panel V | RU4-RFCC | 100UY-U100/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-28 | 2025-10-28 | 2102353961 | 8202236170 |  | 8202229787#Perbaikan bordesk di area 240 | LOC3-UP4 | GMAT-STA-LOC3/00 | 50 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-10-28 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102361438 | 8202233630 |  | 8202229786#Penggantian Gear Pump 11-P-10 | RU6-HSC | 11-P-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-07 | 2102361455 | 8202232736 |  | 8202229785#Steam Trap 33-ST-101 | RU6-HSC | 33-E-103/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-08 | 2026-02-02 | 2026-05-08 | 2102362406 | 8202233912 |  | 8202229783#MatPer.Gen. Steam Turbin 11-P | RU6-HSC | 11-P-104A-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K201 | 2026-02-01 |  | 2025-10-28 | 2025-10-28 | 2102351240 | 8202232339 |  | 8202229782#211/212 Filter rusak | RU2-HCC | 211-V-24/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102361534 | 8202233633 |  | 8202229781#Penggantian Gasket Disc Valve | RU6-HSC | 32-K-102C/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-27 | 2025-12-17 | 2102361535 | 8202233024 |  | 8202229780#Perbaikan motor finfan 12-E-5 | RU6-DHC | 12-E-505A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 487 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102355785 | 8202236343 |  | 8202229778#Penggantian/Perbaikan 14E652 | RU4-FOC1 | 14EE0336C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-03-10 | 2026-05-13 | 2102359880 | 8202235916 |  | 8202229777#Perbaikan AC SS 62 | RU5-UTL | 41-AC-SS-62/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237654 |  | 8202229776#TGH2_24 TSA 2 Unit Brand Ther | RU4-FOC2 | 30BD12EE0012B/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-15-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-10-28 | 2026-10-28 | 2102359932 | 8202235914 |  | 8202229775#Perbaikan Engine Pompa Foam T | RU5-E15500 | TSP-526/00 | 01 | CRTD NMAT PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | HSSE |  |  |  |  | PT02 |  | 2 | 2026-10-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-13 | 2026-10-06 | 2102358852 | 8202235906 |  | 8202229774#Perbaikan Temp. Sensor 3B-TI- | RU5-E15112 | F-3-03B-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 13365000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-13 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-13 | 2026-10-06 | 2102358851 | 8202235909 |  | 8202229773#Perbaikan Temp. Sensor 3A-TI- | RU5-E15112 | F-3-03A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 13365000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-13 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102361452 | 8202233613 |  | 8202229771#Penggantian Lampu area UTL | RU6-UTL | 70-P-101A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 12012 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365352 | 8202240772 |  | 8202229770#2025_Perbaikan UPS di 47SS1 | RU4-RFCGTO | 47SS1EE0021A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238473 | 8202235140 | 8202229768#Tag 2 Pekerjaan Mekanik Area | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238127 | 8202235501 | 8202229766#Tag 2 Pengerukan Lumpur Area | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356464 | 8202240770 |  | 8202229762#25_[CR] Mech Seal Bocor 180T6 | RU4-GTO | 180T602P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355025 | 8202240767 |  | 8202229760#25_[CR] 011E116K02 bearing de | RU4-FOC2 | 011E116K02/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 10798760 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238121 |  | 8202229759#Tag 24 TSA Pemeliharaan Vacuu | RU3-ITP | 039-P-007/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238458 | 8202234942 | 8202229758#Tag 16 PM Clean. PreHeater&Re | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-27 | 2102362649 | 8202232769 |  | 8202229757#PM transformator 12-PTR-501A | RU6-DHC | 12-PTR-501A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 106843791 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-27 | 2026-03-10 | 2102361538 | 8202233194 |  | 8202229753#Perbaikan Control Valve 19KV0 | RU6-RCC | 19-KV-014/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-29 | 2026-03-06 | 2026-03-06 | 2102355659 | 8202240764 |  | 8202229752#25_[CR] Perbaikan Pompa 54P1B | RU4-UTL | 54P1B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 478611429 | 0 | MA5-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-02-02 | 2026-06-26 | 2102363412 | 8202233207 |  | 8202229751#Perbaikan Catridge SO system | RU6-DHC | 13-K-101-S2A/00 | 50 | CLSD CSER NCMP NMAT PRC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-10-27 | 2025-10-27 | 2102355965 | 8202235961 |  | 8202229750#Perbaikan Kabel Motor 102P510 | RU4-RFCC | 102P510AM/00 | 50 | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-10-27 | PM |  | 045
| K601 | 2026-02-01 | 2026-06-09 | 2026-02-02 | 2026-04-09 | 2102361412 | 8202232766 |  | 8202229738#PM/PDM Electrical & Instrumen | RU6-DHC | 13-PDB3-01N/00 | 01 | CLSD CSER NCMP NMAT PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-27 | 2025-12-15 | 2102361532 | 8202233747 |  | 8202229737#Pengadaan thyristor 38-E-111 | RU6-POC | 38-TV-030/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 461 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K501 | 2026-02-04 | 2026-05-12 | 2026-01-15 | 2026-01-15 | 2102359508 | 8202238445 |  | 8202229731#PERBAIKAN SUMP PUMP G-34-53 | RU5-D&W | G-34-53/00 | 60 | TECO CNF GMCO NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-04-28 |  | 8202237653 | 8202237604 | 8202229729#TGH3_CIV_UP PENGECATAN MA7 | RU4-RFCGTO | 106E501/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-11-04 | 2025-11-04 | 2102355021 | 8202237229 |  | 8202229725#CM_Kerusakan Piping Lingkup M | RU4-GTO |  | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA7-STA |  |  |  |  | PT02 |  | 2 | 2025-11-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-05-25 | 2026-02-02 | 2026-07-10 | 2102361078 | 8202233179 |  | 8202229724#Perbaikan exhaust valve 32-A- | RU6-HSC | 32-A-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | DANDARWANI |  | 2026-05-25 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-09-30 | 2026-12-29 | 2102359697 | 8202235887 |  | 8202229722#Penggantian Lampu control roo |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-D4H | 19860000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-09-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355869 | 8202240761 |  | 8202229721#25_[CR] Perbaikan Sootblower | RU4-RFCC | 101F503/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 2255800 | 0 | MA6-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102361380 | 8202233254 |  | 8202229719#Perbaikan 54-LT-001A | RU6-UTL | 54-LT-001A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 12012 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356533 | 8202240758 |  | 8202229716#25_[CR] Penggantian Belt 11E5 | RU4-FOC1 | 11E54K-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3075463 | 3075463 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-06-04 | 2102356918 | 8202241437 |  | 8202229715#[TGH] Tagihan TSA Mech Seal 7 | RU4-TRML | 71P1C/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 74635950 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102355022 | 8202238152 |  | 8202229712#Cleaning HE, SWD, Cooler UTL | RU4-UTL | 54WS1/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 620167000 | 0 | MA5-STA |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102361530 | 8202233814 |  | 8202229711#Pengadaan gasket insulation p | RU6-LK/KK | 66-T-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 15840 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238183 | 8202235291 | 8202229710#Tag 9 TKDN Mekanik Area Selat |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361458 | 8202233120 |  | 8202229709#Perbaikan level glass 22-V-10 | RU6-DHC | 22-V-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357791 | 8202240755 |  | 8202229708#25_[CR] Tindak Lanjut Temuan | RU4-UTL | 590A301K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361495 | 8202232885 |  | 8202229707#Perbaikan sight glass 12-E-51 | RU6-DHC | 12-E-512/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361496 | 8202233220 |  | 8202229706#Perbaikan bocoran LC di 14-FV | RU6-DHC | 14-FV-071/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361387 | 8202233136 |  | 8202229705#Perbaikan kerangan venting 14 | RU6-DHC | 14-P-101B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238443 | 8202235817 | 8202229704#Tag 4 Con Mon Peralatan Rotat |  |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238425 | 8202235092 | 8202229702#Tag 7 Supporting Teknisi dan | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-30 | 2102361418 | 8202233887 |  | 8202229699#Overhaul Motor 42-P-501C | RU6-ITP | 42-P-501C-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 4488 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-30 | 2102361386 | 8202233696 |  | 8202229698#Penggantian bearing motor 42- | RU6-ITP | 42-P-911-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 4488 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-30 | 2102361531 | 8202233312 |  | 8202229697#Perbaikan 21-E-102C | RU6-DHC | 21-E-102C/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-02-03 | 2102353282 | 8202235238 |  | 8202229696#Perbaikan Line Outlet C-205 P | RU3-PP | 22-C-205/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 336000 | 0 | MA2-STA |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K202 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102352169 | 8202234250 |  | 8202229694#Kebutuhan Alat Berat (Crane) | RU2S-KIL |  | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 1880780000 | 728684000 | MAS-ME1 |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202234628 |  | 8202229692#PERBAIKAN POMPA 3-PM-01/02 A | RU7-CRU | 3-PM-01A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-3-D1H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K401 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-09-24 | 2102355009 | 8202235460 |  | 8202229691#Perbaikan push button 21HV702 | RU4-LOC1 | 25F1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354382 | 8202240751 |  | 8202229690#25_Penggantian PSV Pada Tanki | RU4-TRML | 36T102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102354860 | 8202240749 |  | 8202229689#25_[CR] Perbaikan coupling ng | RU4-LOC1 | 20P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355939 | 8202240746 |  | 8202229686#25_[CR] Membran Coupling 11P8 | RU4-FOC1 | 11P8A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102358376 | 8202234627 |  | 8202229684#PENGADAAN ASSEMBLY CONTROL PA | RU7-UTL | 4-P-04D/00 | 50 | REL MACM PRC SETC | 7RT | D17/25/B6/RT-4-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2026-05-12 | 2102361413 | 8202238424 |  | 8202229682#Cleaning External Fin Tube 15 | RU6-RCC | 15-E-110/00 | 50 | CLSD NCMP NMAT PRC RELR SETC | 6MR | D16/25/B6/RT-C3H | 300000001 | 0 | MA1-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-24 | 2102361347 | 8202233059 |  | 8202229680#Perbaikan motor 15-E-110 M | RU6-RCC | 15-E-110M-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-24 | 2102362765 | 8202233052 |  | 8202229679#Perbaikan motor 16-E-119M | RU6-RCC | 16-E-119M-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-24 | 2102361341 | 8202233051 |  | 8202229677#Perbaikan Motor 16-E-120D | RU6-RCC | 16-E-120D-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-24 | 2102361342 | 8202233313 |  | 8202229676#Perbaikan 20-E-104B | RU6-RCC | 20-E-104B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-10 | 2102361076 | 8202232813 |  | 8202229675#Perbikan 16-E-121A-K | RU6-RCC | 16-E-121A-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-24 | 2102361346 | 8202233335 |  | 8202229674#Perbaikan 16-E-117C | RU6-RCC | 16-E-117C-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355277 | 8202240743 |  | 8202229671#25_Penggantian motor ALOP Kom | RU4-FOC2 | 011K101CP2M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-17 | 2025-11-17 | 2102351336 | 8202232310 |  | 8202229669#Pengadaan Gasket Filter HCGO | RU2-HOC | 140-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361497 | 8202233013 |  | 8202229668#Perbaikan Outlet 42-T-301C | RU6-ITP | 42-PIPE/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 | 2102362180 | 8202232143 |  | 8202229667#Perawatan pembuatan jalan aks | RU6-ITP | 41PG2203A2A14NI/00 | 60 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 0 | 1084000000 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356150 | 8202236639 |  | 8202229662#D_25 Motor noise 260E125M1 | RU4-LOC3 | 260E125M1/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357475 | 8202236637 |  | 8202229661#D_25 Motor noise 260E172M2 | RU4-LOC3 | 260E172M2/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357473 | 8202236634 |  | 8202229660#D_25 Motor short 200P101B | RU4-LOC3 | 200P101BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355150 | 8202240740 |  | 8202229659#25_Motor 021P-109B hgh temper | RU4-LOC2 | 021P109B/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102353859 | 8202240737 |  | 8202229658#25_Motor 021P-109A indikasi s | RU4-LOC2 | 021P109A/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356784 | 8202236791 |  | 8202229657#D_25 014P113BM motor over loa | RU4-FOC2 | 014P113BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356432 | 8202236869 |  | 8202229656#D_25 013P-102B motor dan pomp | RU4-FOC2 | 013P102BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356377 | 8202236958 |  | 8202229655#D_25 011E124M04 trip tripan | RU4-FOC2 | 011E124M04/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355292 | 8202236868 |  | 8202229654#D_25 014 E-104 M1 : pully mot | RU4-FOC2 | 014E104M01/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357737 | 8202236899 |  | 8202229653#D_25 011P102AM trip | RU4-FOC2 | 011P102AM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357732 | 8202236672 |  | 8202229652#D_25 Lampu Lorong CCR mati |  |  | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356039 | 8202240734 |  | 8202229651#25_[CR] Perbaikan Spring Link | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357692 | 8202236937 |  | 8202229650#D_25 011F-101B SB No. 1 dan 3 | RU4-FOC2 | 011F101B/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357358 | 8202236735 |  | 8202229649#D_25 018E106M2 motor short | RU4-FOC2 | 018E106M02/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356398 | 8202236874 |  | 8202229647#D_25 013E-107 M5 indikasi sho | RU4-FOC2 | 013E107M05/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356308 | 8202237016 |  | 8202229646#D_25 011E-110 M 24 : PELINDUN | RU4-FOC2 | 011E110M24/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357346 | 8202240732 |  | 8202229645#25_[CR] Perbaikan Mixer 36M10 | RU4-TRML | 36M102CM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 3298167 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-23 | 2026-01-02 | 2026-01-02 |  | 8202237652 |  | 8202229644#Penggantian Transformer 80EE2 | RU4-KPC | 80EE2112F/00 | 50 | CRTD CSER NMAT PRC RELR SETC | 4ER | D14/26/B6/RT-10-C2H | 100000 | 0 | MA4-LIS |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361494 | 8202233213 |  | 8202229643#Perbaikan Bocoran Steam Trace | RU6-DHC | 22-F-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361493 | 8202233407 |  | 8202229642#Perbaikan 12-E-516 | RU6-DHC | 12-E-516/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352271 | 8202234246 |  | 8202229641#Pompa Chemical Area Boiler | RU2S-KIL | 900-08P-6F/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356174 | 8202240728 |  | 8202229640#25_Penggantian Temp Indikator | RU4-TRML | 43T101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356172 | 8202240726 |  | 8202229639#25_Penggantian Temp Indikator | RU4-TRML | 37T102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-04-10 |  | 8202237930 | 8202233981 | 8202229638#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | ES-B14-01/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355158 | 8202240722 |  | 8202229636#25_[CR] Mechanical seal bocor | RU4-LOC3 | 240P116A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-12 | 2026-01-02 | 2026-01-02 | 2102356965 | 8202240720 |  | 8202229635#25_[CR] Pengadaan pompa 054WS | RU4-UTL | 054WS105P1/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | TONNYADI | 2026-06-11 | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356214 | 8202240717 |  | 8202229634#25_[CR] Perbaikan bearing 14K | RU4-FOC1 | 14K1P2A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 186724495 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-12-31 | 2025-12-31 | 2102351450 | 8202232466 |  | 8202229633#pekerjaan Penggantian gate va | RU2-ITP | 2-P-94675-A1A1/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-12-31 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-09 | 2102361453 | 8202233557 |  | 8202229632#Penggantian PI yang rusak di | RU6-RCC | 15-K-103/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2025-12-05 | 2026-04-28 |  | 8202237929 | 8202233430 | 8202229630#Penyelesaian Pek. PM PDM EI M | RU6-ITP | 42-T-101A/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-10 | 2102361450 | 8202233750 |  | 8202229627#Pengadaan spare contactor 58- | RU6-UTL | 58-D-101A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 5544 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-20 | 2102361454 | 8202233339 |  | 8202229626#Perbaikan 15K103P1B | RU6-RCC | 15-K-103-P1B-M/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357107 | 8202240713 |  | 8202229625#[PV] Mechanical Seal Pompa 84 | RU4-KPC | 84P203A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102353734 | 8202240712 |  | 8202229624#25_[CR]Plunger sebelah timur | RU4-LOC3 | 260P104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354476 | 8202240709 |  | 8202229622#[CR] Penggantian gelas peluma | RU4-LOC1 | 25P1A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 323687767 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-16 |  | 8202236586 |  | 8202229619#Tgh ke 4 85% LTSA Cleaning 11 | RU6-HSC | 11-E-116A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/24/B6/RT-C3H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-02-26 | 2026-03-02 | 2026-03-02 | 2026-12-30 | 2102357482 | 8202239183 |  | 8202229618#[CR] Perbaikan pompa 38P-11 | RU4-TRML | 38P111D/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 82110000 | 82110000 | WS-PMP |  | WAHYUCATUR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102354945 | 8202240705 |  | 8202229617#25_[CR] Perbaikan Coupling Va | RU4-LOC1 | 24S1C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 12175000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-23 | 2026-04-27 | 2026-01-02 | 2026-12-30 | 2102357536 | 8202239050 |  | 8202229613#014E102AM02 kabel control sho | RU4-FOC2 | 014E102AM02/00 | 50 | CRTD CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 100000 | 0 | MA2-LIS |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-05-25 |  | 8202238423 | 8202235565 | 8202229612#Tag. 19 Operator & Pem. Alat | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-25 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K401 | 2026-02-03 | 2026-04-23 | 2026-04-15 | 2026-12-30 | 2102355276 | 8202237651 |  | 8202229610#Rejuvenate kabel motor ALOP K | RU4-FOC2 | 011K101AP2M/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 978000000 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-04-22 | PT02 |  | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-02-03 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356777 | 8202237650 |  | 8202229609#RKAP 2026 PENGGANTIAN LEAK GA | RU4-TRML | 70CIB1/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 100000 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361270 | 8202237649 |  | 8202229608#TGH7_24 TSA DCS Honeywell RFC | RU4-RFCC | 101FJB001/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357477 | 8202241222 |  | 8202229604#[CR] Mech.Seal 87P204A Bocor | RU4-KPC | 87P204A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-01-02 | 2102352217 | 8202234245 |  | 8202229600#Fabrikasi Blade FinFan 101-E- | RU2S-KIL | 101-E-9/00 | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/26/B6/NRZ-C2H | 0 | 210000000 | MAS-ME1 |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356239 | 8202241220 |  | 8202229597#25_penujukan 85FT244 tidak ak | RU4-KPC | 85FT244/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356213 | 8202241218 |  | 8202229596#25_[CR] Pompa 011P132 jammed | RU4-FOC2 | 011V109/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 120281700 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356301 | 8202241216 |  | 8202229595#25_penujukan 84PT280 tidak ak | RU4-KPC | 84PT280/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 18000000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102357743 | 8202238604 |  | 8202229593#25_Penggantian air compressor | LOC1-UP4 | 47S506B-K/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-01-30 | 2026-01-30 | 2102357742 | 8202238605 |  | 8202229592#25_Penggantian air compressor | LOC1-UP4 | 47S506A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102357223 | 8202241214 |  | 8202229579#25_66P203B casing bocor | RU4-TRML | 66P203B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 10730178 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356438 | 8202241212 |  | 8202229578#25_[PdM] 014K101P1B high vibr | RU4-FOC2 | 014K101P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353652 | 8202237252 |  | 8202229577#CM_Kebocoran Peralatan Metode |  |  | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA6-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356588 | 8202241210 |  | 8202229576#25_[CR] Penggantian LO FIlter | RU4-TRML | 46P1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 250000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237648 | 8202237634 | 8202229574#TGH2-5_25 UP MON&INSP PERALAT | RU4-RFCGTO | 107P502A-MCC/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355329 | 8202235834 |  | 8202229571#Perbaikan motor 10P2 noise | RU4-FOC1 | 10P2/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351752 | 8202232420 |  | 8202229570#High Vibrasi (Ganti Membrane | RU2-HSC | 300-P-3B/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-14 | 2026-02-04 | 2026-11-06 |  | 8202238151 | 8202233686 | 8202229569#Fabrikasi Fan Blade 56-K-102F | RU6-UTL | 56-K-102F/00 | 50 | REL GMPS NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 5656000 | 480760000 | MA4-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102361451 | 8202233686 |  | 8202229568#Penggantian blade fin fan 56- | RU6-UTL | 56-K-102F/00 | 50 WAMA | REL CSER GMCO MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237647 |  | 8202229567#TGH3_SIP_UP Floating Hose 200 | RU4-TRML | SPM/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-06-08 | 2102361510 | 8202237928 |  | 8202229566#Penggantian Adsorbent Dryer 5 | RU6-UTL | 58-D-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-24 | 2102363099 | 8202237927 |  | 8202229565#Per.Gen. Steam Turbin 62-P-20 | RU6-UTL | 62-P-201D-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K301 | 2026-02-02 | 2026-02-24 | 2026-01-12 | 2026-01-12 | 2102360926 | 8202235355 |  | 8202229564#penggantian cable lead E-63-1 | RU3-CDL | MCC-EM-63-012A/00 | 50 WAMA | REL CSER MACM PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-LIS |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-02 | 2026-08-20 | 2026-10-30 | 2102360011 | 8202235838 |  | 8202229559#Perbaikan Flange Manhole Deae | RU5-UTL | HHP6-V-0101/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-08-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-02-02 | 2102362306 | 8202234005 |  | 8202229555#Jasa Cleaning 24-E-201 AB | RU6-HSC | 24-E-201A/00 | 01 | CLSD CSER NCMP NMAT PRC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-06 | 2026-03-31 | 2026-03-02 | 2026-04-29 | 2102351454 | 8202238680 |  | 8202229554#Overhead Crane 212 PX-52 Rusa | RU2-HCC | 212-PX-52/00 | 60 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1987000000 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-03-31 | PT02 |  | 3 | 2026-03-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233946 | 8202233301 | 8202229550#Material Blind 23-E-201 | RU6-HSC | 23-E-201/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-03-05 | 2026-02-03 | 2026-02-03 | 2102358660 | 8202234625 |  | 8202229548#Perbaikan flow Meter Gas 4-FT | RU7-UTL | 4-FT-201/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/25/B6/RT-4-D1H | 0 | 0 | MA-LINT |  | MALFANF |  | 2026-03-05 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-04 | 2026-02-04 |  | 8202238105 | 8202234916 | 8202229547#Tag 20 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-04 | 2026-02-04 |  | 8202238132 | 8202234916 | 8202229546#Tag 19 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238422 | 8202234582 | 8202229545#Tag 6 Perbaikan Korosi Atap T |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238402 | 8202235151 | 8202229544#Tag 16 Cleaning&Ganti Catalys | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356112 | 8202235825 |  | 8202229542#Perbaikan motor 13P4 | RU4-FOC1 | 13P4BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238391 |  | 8202229541#Tag 41 TSA 56 ATG Custody Tra | RU3-ITP | LT-TK-207/00 | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238389 |  | 8202229540#Tag 53 Sewa Beli 40 ATG OM | RU3-ITP | 61-FCV-304/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2026-11-06 |  | 8202238388 | 8202233892 | 8202229539#Fabrikasi Impeller 42-P-501B | RU6-ITP | 42-P-501B/00 | 50 | CLSD NCMP NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 117000000 | 0 | MA4-ROT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-07 | 2102363386 | 8202233212 |  | 8202229537#Perbaikan Bocoran Steam unit | RU6-DHC | 21-F-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102361417 | 8202232986 |  | 8202229536#Perbaikan Pompa 15-P-105B | RU6-RCC | 15-P-105B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-10-02 | 2026-10-02 | 2102351338 | 8202232719 |  | 8202229535#Pengadaan Motor 100-PM-1A (RK | RU2-HSC | 100-PM-1A/00 | 50 | REL MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA2-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-10-02 | PM |  | 004
| K401 | 2026-02-03 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102357298 | 8202237646 |  | 8202229534#Perbaikan Sistem Automasi Pom | RU4-TRML | 38P113A/00 | 50 | CRTD CSER NMAT PRC RELR SETC | 4IR | D14/26/B6/RT-3-C2H | 100 | 0 | MA3-INT |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361343 | 8202233301 |  | 8202229533#Perbaikan 23-E-201 | RU6-HSC | 23-E-201/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 739435 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357738 | 8202236460 |  | 8202229531#D25_013 AI-001 O2 analizer up | RU4-FOC2 | 013AT001/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357691 | 8202236476 |  | 8202229530#D25_011AI323 analizer menunju | RU4-FOC2 | 011F101A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-02 | 2102361415 | 8202233035 |  | 8202229528#Perbaikan Motor 39-K-101-P-10 | RU6-POC | 39-K-101-P2-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357243 | 8202236411 |  | 8202229527#D25_Control valve module FTA | RU4-LOC2 | 021FV005/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355290 | 8202236463 |  | 8202229526#D25_012F101 PRES PILOT HEADER | RU4-FOC2 | 012F101/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-27 | 2025-11-27 | 2102354365 | 8202241206 |  | 8202229525#25_Pengadaan Flow Transmitter | RU4-LOC2 | 024FE051/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357736 | 8202236469 |  | 8202229524#D25_011FIC-021A2, B3: Posisi | RU4-FOC2 | 011F101A/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-27 | 2025-11-27 | 2102357697 | 8202241204 |  | 8202229523#25_012PT008 penunjukan nol | RU4-FOC2 | 012PT008/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357696 | 8202236462 |  | 8202229522#D25_012PCV-099 press turun | RU4-FOC2 | 012PCV099/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357291 | 8202241202 |  | 8202229521#25_Perbaikan 14TT549 | RU4-FOC1 | 14TT549/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-30 | 2026-12-29 |  | 8202235811 | 8202238166 | 8202229520#Penggantian Relay Proteksi B1 | RU5-UTL | 41-R-SS-66-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-D4H | 273140000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-30 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357699 | 8202241200 |  | 8202229519#25_[CR] perbaikan bearing tur | RU4-RFCUTL | 154P507A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 3724000 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352066 | 8202232617 |  | 8202229510#Perbaikan Pompa 140 P-27B | RU2-HOC | 140-P-27B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 1022688 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352067 | 8202232616 |  | 8202229509#Perbaikan Pompa 140 P-5A | RU2-HOC | 140-P-5A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 3454126 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102346844 | 8202232532 |  | 8202229508#Membran Coupling 170-ME-103-2 | RU2-HOC | 170-ME-103-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102354423 | 8202241198 |  | 8202229507#25_[CR] Perbaikan pompa 71P1C | RU4-TRML | 71P1C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 210963367 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351871 | 8202232618 |  | 8202229506#Perbaikan Pompa 140 P-22A | RU2-HOC | 140-P-22A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-06 | 2102363208 | 8202236721 |  | 8202229505#SPK LTSA PM Assesment Motor M | RU6-DHC | 22-E-102/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-22 | 2102362460 | 8202232780 |  | 8202229504#Pernggantian Instrumentasi ST | RU6-UTL | 51-G-101C/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 6600 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-12-30 | 2026-12-30 | 2102351513 | 8202232677 |  | 8202229503#Perbaikan Steam Turbine 110-P | RU2-HOC | 110-PT-3B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/NR-D2H | 166712598 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351126 | 8202232700 |  | 8202229502#Perbaikan 520-CL-06 | RU2-UTL | 520-CL-06/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-03-03 | 2026-03-03 | 2102351125 | 8202232701 |  | 8202229501#Perbaikan 520-CL-05 | RU2-UTL | 520-CL-05/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-25 | 2102361410 | 8202233253 |  | 8202229500#Perbaikan 54-LT-001B | RU6-UTL | 54-LT-001B/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 4092 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102354363 | 8202241196 |  | 8202229499#25_[CR] Pompa 021P-104 jammed | RU4-LOC2 | 021P104/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 111904065 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353310 | 8202234459 |  | 8202229497#NR-Penggantian Bearing pompa | RU3-ITP | ITP-P-61-313A/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355362 | 8202241194 |  | 8202229496#25_14TI574 penunjukan semu (h | RU4-FOC1 | 14TE574/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-23 | 2026-04-22 | 2026-11-12 | 2102357801 | 8202236228 |  | 8202229495#Transmitter Rusak 105LI041 | RU4-RFCGTO | 105LI-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-04-23 | PT02 |  | 3 | 2026-04-22 | PM |  | 003
| K501 | 2026-02-03 | 2026-05-13 | 2026-01-02 | 2027-01-20 | 2102359883 | 8202237712 |  | 8202229494#Recoating & Ganti Insulasi Li | RU5-E15112 | 8-ACW101-3-A4/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 1925000000 | 1925000000 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 004
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-27 | 2102358679 | 8202235804 |  | 8202229493#Penggantian Flexible Hose den |  |  | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202232361 | 8202232357 | 8202229492#Pengadaan Catridge Filter 211 | RU2-HCC | 211-F-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102356118 | 8202241192 |  | 8202229490#25_[CR] membran coupling 21P1 | RU4-LOC1 | 21P13A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102357730 | 8202241190 |  | 8202229489#25_[CR] Micro Filter DGS 84k2 | RU4-KPC | 84K201/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 60491667 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-03-10 | 2102361349 | 8202233202 |  | 8202229488#Perbaikan Compresor 51-G-102- | RU6-UTL | 51-G-102-K1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 5940 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102357103 | 8202241188 |  | 8202229487#25_[CR]Penggantian membran co | RU4-LOC1 | 24K1P1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 5594772 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357357 | 8202241186 |  | 8202229484#25_[CR] 018E103K02 Bearing De | RU4-FOC2 | 018E103K02/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 10798760 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-18 | 2026-03-02 | 2026-12-30 | 2102355372 | 8202235141 |  | 8202229480#RKAP2025 UP Grouting ME-1 | RU4-TRML | LN63-DW8001MS02/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 1138924000 | 968085000 | MA4-STA |  | FARIZSETYANA |  | 2026-05-13 | PT02 |  | 3 | 2026-03-02 | PM |  | 045
| K601 | 2026-02-07 | 2026-02-10 | 2026-02-09 | 2026-04-17 |  | 8202238732 |  | 8202229479#Perbaikan cathodic Protection | RU6-UTL | 53-REC-02/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 5544 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-02-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-06 | 2026-02-02 | 2026-04-10 | 2102361782 | 8202233638 |  | 8202229478#Penggantian fuse 056-K-101A1 | RU6-UTL | 056-K-101-A1-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 5544 | 0 | MA4-LIS |  | DINDINS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102358378 | 8202234624 |  | 8202229477#Perbaikan Struktur Fin Fan 1- | RU7-CDU | 1-EA-01A/00 | 50 | CRTD CSER MACM PRC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362205 | 8202233008 |  | 8202229476#Perbaikan Piston 22-K-101B | RU6-DHC | 22-K-101B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102361344 | 8202233514 |  | 8202229474#Penggantian Reservoir 21-P-10 | RU6-DHC | 21-P-108A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-07-21 | 2102361932 | 8202233114 |  | 8202229473#Perbaikan LO 12-A-501-P1B (Pe | RU6-DHC | 12-A-501/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-08-31 | 2026-12-30 | 2102358795 | 8202235746 |  | 8202229472#Perbaikan ICCP Tanki OM | RU5-TBL | PLANT-20-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1708 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-08-31 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102356116 | 8202241184 |  | 8202229470#25_[CR] membran coupling 21P1 | RU4-LOC1 | 21P10A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 9324620 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102356824 | 8202241182 |  | 8202229469#25_[CR] Perbaikan Loader Valv | RU4-FOC1 | 12K1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1301788000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355446 | 8202241180 |  | 8202229468#25_[CR]47P-507C pompa tidak b | LOC1-UP4 | 47P507B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 12183667 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357338 | 8202241178 |  | 8202229467#25_[CR] Penggantian Filter Lu | RU4-FOC1 | 12K1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 11977768 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357380 | 8202241176 |  | 8202229466#25_[CR] Penggantian Filter Lu | RU4-FOC1 | 12K1C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 6533000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354610 | 8202241175 |  | 8202229465#25_[CR] Penggantian Membran 1 | RU4-FOC1 | 11P6/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357621 | 8202237645 |  | 8202229464#TGH10_23 KONTRAK U/P OVERHAUL | RU4-TRML | 36P101A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 1335500000 | 0 | WS-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238182 | 8202235367 | 8202229462#Tag 11 Steam Leak non Trap Ki |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-05 | 2026-02-05 |  | 8202238488 | 8202234916 | 8202229461#Tag 18 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-04 | 2026-02-04 |  | 8202238125 | 8202234916 | 8202229460#Tag 17 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-04-28 | 2102361720 | 8202237925 |  | 8202229459#LTSA Piping Tahap 6 Area UTL | RU6-UTL | 052-B-101C/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C1H | 146274000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362762 | 8202232989 |  | 8202229458#Perbaikan Pompa 15-P-102A | RU6-RCC | 15-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 1478869 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-05-06 | 2026-01-02 | 2026-11-30 | 2102352487 | 8202234244 |  | 8202229457#GV 4 inch drain box cooler E- | RU2S-KIL | 2LS900073-MS1/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/NRZ-D2H | 4520382 | 4037823 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352480 | 8202234243 |  | 8202229456#TA 2027 GV 6 inch sea water | RU2S-KIL | 101-E-10A/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102357804 | 8202241174 |  | 8202229455#25_[CR]Pengggantian catridge | RU4-SRU | 91K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 48489000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-03 | 2026-02-02 | 2026-02-02 | 2102352481 | 8202234242 |  | 8202229454#GV 3/4 ADO reflux dari 101-E- | RU2S-KIL | 101-E-5A/01 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C2H | 25775000 | 25775000 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352479 | 8202234240 |  | 8202229453#TA 2027 GV 1 inch drain 101-D | RU2S-KIL | 101-D-1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352485 | 8202234238 |  | 8202229452#TA 2027 GV 3/4 INCH VENTING P | RU2S-KIL | 101-P-10A/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-26 | 2026-02-02 | 2026-02-02 | 2102352482 | 8202234237 |  | 8202229451#BLOWDOWN 2 inch 101-E-5B | RU2S-KIL | 101-E-5B/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 2333866 | 2250057 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-28 | 2102361039 | 8202237924 |  | 8202229450#LTSA PM Grounding & Lightning | RU6-UTL | GROUNDSYS-51/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353289 | 8202234454 |  | 8202229449#NR-Perbaikan P-62-101B CD4 | RU3-CDGP | CD4-P-62-101B/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354832 | 8202241173 |  | 8202229448#25_Penggantian positioner 54C | RU4-UTL | 54WS1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 44481526 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354831 | 8202241172 |  | 8202229447#25_Perb Sol & LS Air Register | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354807 | 8202241171 |  | 8202229446#25_Perb Sol & LS Air Register | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354719 | 8202236457 |  | 8202229445#D25_013F-101 SB valve tidak m | RU4-FOC2 | 013F101/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355912 | 8202241170 |  | 8202229443#25_Tolong perbaikan 84LT433 | RU4-KPC | 84LT503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-11 | 2026-02-02 | 2026-02-02 | 2102352483 | 8202234236 |  | 8202229442#GV 6 INCH oulet steam 101-E-5 | RU2S-KIL | 101-E-5B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 49841790 | 49841790 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357041 | 8202241169 |  | 8202229441#2025_Perbaikan Coil Contactor | RU4-FOC1 | 14EE0336A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-25 | 2102362685 | 8202233296 |  | 8202229440#Perbaikan 31-FT-012A | RU6-HSC | 31-FT-012A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354008 | 8202235016 |  | 8202229437#Pompa under perform 200P101A | RU4-LOC3 | 200P101A/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238477 | 8202235629 | 8202229436#Tag 2 Hose Handling Area Derm |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238471 | 8302405757 | 8202229435#Tag 13 Pekerjaan TSA-PM Flowm | RU3-ITP | 62-FT-0308/00 | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-29 | 2102362731 | 8202237923 |  | 8202229433#LTSA Online Leak Sealing Taha | RU6-RCC | 16-E-117AD/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355294 | 8202241168 |  | 8202229432#25_[CR] 018K101B performance | RU4-FOC2 | 018K101A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 21842029 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-29 | 2102363430 | 8202237922 |  | 8202229430#LTSA Online Leak Sealing Taha | RU6-UTL | 050-FT-001A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356471 | 8202241167 |  | 8202229428#25_[CR] 018P101B Mech seal o/ | RU4-FOC2 | 018P101B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-29 | 2102362944 | 8202237920 |  | 8202229427#LTSA Online Leak Sealing Taha | RU6-RCC | 16-E-116A/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102362974 | 8202237918 |  | 8202229425#LTSA Online Leak Sealing Taha | RU6-RCC | 15-E-106A/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356110 | 8202241166 |  | 8202229423#25_[PV] Perbaikan Coupling 10 | RU4-RFCC | 101P502C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355326 | 8202241165 |  | 8202229422#25_[PV] Penggantian Coupling | RU4-RFCC | 101P503B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-29 |  | 8202236830 | 8202233979 | 8202229421#PM 8 - LTSA FGDS General Moni | RU6-ITP | 42-T-301A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351749 | 8202232630 |  | 8202229420#pengambilan stud bold w/ nut | RU2-ITP | LI-TK-201/00 | 50 | CRTD CSER MACM PRC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-29 |  | 8202236828 | 8202233867 | 8202229419#PM 8 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102361748 | 8202237916 |  | 8202229418#LTSA Online Leak Sealing Taha | RU6-UTL | 52-B-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 |  | 2026-02-04 | 2027-06-15 | 2102362519 | 8202238469 |  | 8202229417#Overhaul Elevator Unit NPU | RU6-HSC | 32-A-104/00 | 50 | CRTD CSER NMAT PRC | 6ER | D16/25/B6/RT-C2H | 1 | 0 | MA3-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-17 | 2026-04-24 | 2102363125 | 8202233414 |  | 8202229416#Perbaikan 11-TI-236 | RU6-HSC | 11-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1024 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102362260 | 8202237914 |  | 8202229414#LTSA Online Leak Sealing Taha | RU6-UTL | 52-E-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-16 | 2026-04-15 | 2026-11-11 | 2102351184 | 8202232397 |  | 8202229413#Indicator Local HOC | RU2-HOC | 110-PI-HVU/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA1-INT |  | STEVANEKOPP |  | 2026-04-16 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-04 |  | 8202237912 | 8202237910 | 8202229412#LTSA Online Leak Sealing Taha | RU6-DHC | 22-E-102H/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-16 | 2026-04-15 | 2026-11-04 | 2102351621 | 8202232230 |  | 8202229411#Pengadaan Local Control Spill | RU2-HCC | 212-P-2/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-04-16 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-04 | 2102361354 | 8202237910 |  | 8202229410#LTSA Online Leak Sealing Taha | RU6-DHC | 22-E-102H/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-06 | 2026-03-06 | 2102356154 | 8202241163 |  | 8202229408#25_[CR] Indikasi Bearing Deff | RU4-TRML | 39P202A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 9858259 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-06 | 2026-03-06 | 2102354369 | 8202241161 |  | 8202229407#25_[CR] Indikasi Bearing Deff | RU4-TRML | 39P202B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 9858259 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-01-02 | 2102355989 | 8202241159 |  | 8202229403#25_[CR] Penggantian Filter LO | RU4-UTL | 051G101T/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 46716324 | 46716321 | MA5-ROT |  | TONNYADI | 2026-05-25 | 2026-03-10 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354007 | 8202241157 |  | 8202229402#25_Perbaikan Valve Level glas | RU4-RFCUTL | 151B501C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 004
| K301 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-02-03 | 2102353311 | 8202235322 |  | 8202229399#Penggantian Strainer Pompa SB | RU3-ITP | ITP-RPA-P-005/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238466 | 8202235215 | 8202229398#Tag 13 Kontrak Volume Mekanik |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-18 | 2102359884 | 8202235709 |  | 8202229397#MAT.Perb. pipa OS-510-3-B20 | RU5-E15112 | 19-OS-503-32B20/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-03-09 | 2102354188 | 8202241436 |  | 8202229395#25_[CR] Perbaikan Mech Seal 4 | RU4-TRML | 41P3B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 86382927 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238457 | 8202235145 | 8202229394#Tag 16 PM/PDM Cleaning Cooler | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238448 | 8202235126 | 8202229393#Tag 3 Mekanik Area Utara OM |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-05-22 | 2102358819 | 8202235681 |  | 8202229390#Penggantian Valve Pipa Discha | RU5-E15500 | 33-JP-011/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | ENG-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356585 | 8202241155 |  | 8202229388#25_[CR] Perbaikan DEG 152G502 | RU4-RFCUTL | 152G502B-D/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 1784000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356582 | 8202241153 |  | 8202229387#25_[CR] Perbaikan DEG 152G502 | RU4-RFCUTL | 152G502A-D/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 705000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237644 | 8202238635 | 8202229386#TGH24_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 194893000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2027-04-27 | 2102361074 | 8202233665 |  | 8202229385#Penggantian demister breather | RU6-UTL | 58-K-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 39600 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-05 | 2026-03-16 | 2026-01-01 | 2026-12-31 | 2102353118 | 8202238647 |  | 8202229382#Perbaikan jalan dan Parit STA |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 1310000000 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-11 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354200 | 8202236087 |  | 8202229381#Handrail dan platform di area | RU4-TRML | 66HB101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-09-30 | 2026-12-29 | 2102359717 | 8202235706 |  | 8202229379#Penggantian Komponen Kontrol |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 79127811 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-09-30 | PM |  | 045
| K202 | 2026-02-02 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102352478 | 8202234235 |  | 8202229378#Perbaikan Motor Sump Pump Sep | RU2S-KIL | 946-SP-1A-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 22504000 | 17620000 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-02 | 2102359886 | 8202235677 |  | 8202229376#Perbaikan Motor P-11 WTP-1 |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 2 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-30 |  | 8202236580 | 8202236570 | 8202229375#Tgh ke-4 Kont. RT Vol MA1 | RU6-RCC | 15-R-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-18 | 2102358991 | 8202235621 |  | 8202229371#MAT.Perb. STEAM LEAK AREA HSC | RU5-E15111 | 001-FT-0899/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354311 | 8202241149 |  | 8202229370#25_Pengadaan lampu emergency | RU4-FOC2 | 011PSH026/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-17 | 2102362856 | 8202232858 |  | 8202229369#Perbaikan Trafo 14B PTR 1-01A | RU6-RCC | 14B-PTR1-01A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 42726000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-17 | 2102362760 | 8202232857 |  | 8202229368#Perbaikan Trafo 14B PTR 1-01B | RU6-RCC | 14B-PTR1-01B/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-09 | 2102362880 | 8202233386 |  | 8202229366#Perbaikan 12-PT-619 | RU6-DHC | 12-PT-619/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356633 | 8202241146 |  | 8202229365#25_perbaikan field instrument | RU4-SRU | 93K401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1128509 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-29 | 2102362858 | 8202233021 |  | 8202229364#Perbaikan motor mixer 42-M-10 | RU6-ITP | 42-M-102B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 7178 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354730 | 8202241142 |  | 8202229361#25_[CR] Perbaikan Coupling 51 | RU4-UTL | 51G201T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352287 | 8202234234 |  | 8202229358#ASAP EXHOUSE MOBIL AFT-2 | RU2S-LKKK |  | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355793 | 8202241139 |  | 8202229357#25_[CR] Hanger & bearing scro | RU4-LOC1 | 24S1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355199 | 8202241137 |  | 8202229356#25_Penggantian Valve Sirkulas |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102356597 | 8202241118 |  | 8202229354#25_[CR] Penggantian Gearset G | RU4-UTL | 053P201C-G/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 18570856 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-07-10 | 2102359885 | 8202235604 |  | 8202229353#Perbaikan Starting SOV STG 2. | RU5-UTL | TG-3-PP2-INST/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 8902000 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 004
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238426 | 8202234925 | 8202229352#Tag 3 Pemeliharaan RPA 1-5 & |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238417 | 8202235263 | 8202229349#Tag 5 Perbaikan Jalan Kilang |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351550 | 8202232213 |  | 8202229347#Casing turbin bocor | RU2-HCC | 702-CT-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351518 | 8202232425 |  | 8202229345#High Temperature Discharge St | RU2-HCC | 212-C-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 38025468 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233936 | 8202237896 | 8202229344#Material HE 11-E-110 111AB | RU6-HSC | 11-E-110A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234022 | 8202237909 | 8202229343#Ganti gasket 24-E-203 | RU6-HSC | 24-C-201/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-24 | 2025-12-08 | 2026-12-29 | 2102355227 | 8202237643 |  | 8202229341#RKAP26-Pemasangan & Retrofit | RU4-UTL | 005BD102/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-19 | 2102362207 | 8202237909 |  | 8202229340#Ganti Tray & Cleaning 24-C-20 | RU6-HSC | 24-C-201/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 |  | 8202237908 | 8202237898 | 8202229336#Penagihan Sewa SBNP Thp 9 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 |  | 8202237907 | 8202237898 | 8202229335#Penagihan Sewa SBNP Thp 8 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 |  | 8202237906 | 8202237898 | 8202229334#Penagihan Sewa SBNP Thp 7 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-04-09 |  | 8202237904 | 8202237898 | 8202229332#Penagihan Sewa SBNP Thp 6 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351517 | 8202232352 |  | 8202229331#Cleaning dan Purging Line DGS | RU2-HCC | 212-C-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 167048973 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102362545 | 8202237903 |  | 8202229330#LTSA Perbaikan pompa | RU6-ITP | 63-P-103A/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351396 | 8202232327 |  | 8202229329#212 E-9 bocor | RU2-HCC | 212-E-9/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351453 | 8202232330 |  | 8202229328#212 E-33 Tube Bocor | RU2-HCC | 212-E-33/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351452 | 8202232332 |  | 8202229327#212 E-31 Tube Bocor | RU2-HCC | 212-E-31/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102359495 | 8202235630 |  | 8202229326#Fabrikasi Part Kompresor K-3- | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-05-26 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351395 | 8202232655 |  | 8202229325#Material Gasket | RU2-HSC | 200-E-1D/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 |  | 8202237902 | 8202237898 | 8202229324#Penagihan Sewa SBNP Thp 5 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 |  | 8202237901 | 8202237898 | 8202229323#Penagihan Sewa SBNP Thp 4 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 |  | 8202237900 | 8202237898 | 8202229322#Penagihan Sewa SBNP Thp 3 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 |  | 8202237899 | 8202237898 | 8202229321#Penagihan Sewa SBNP Thp 2 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356749 | 8202236473 |  | 8202229320#D25_011F101B, control valve d | RU4-FOC2 | 011F101B/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-25 | 2025-11-25 | 2102355297 | 8202236303 |  | 8202229317#D25_Perbaikan storage pada de | RU4-FOC2 | 01CSL1/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-25 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351451 | 8202232688 |  | 8202229315#Tube Bocor | RU2-HCC | 211-E-31/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102362738 | 8202233628 |  | 8202229312#Penggantian HE 050-E-602 | RU6-UTL | 050-E-602/00 | 01 | CRTD NMAT PRC | 6MR | D16/XX/B6/RT-C2NH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355791 | 8202241114 |  | 8202229311#25_[CR] Gelas Pelumas Pecah 2 | RU4-LOC1 | 21P13A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-05-05 |  | 8202236631 | 8202233851 | 8202229310#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-27 | 2026-03-06 | 2026-03-06 | 2102356958 | 8202241111 |  | 8202229309#25_[CR] 015E107K5 Bearing Def | RU4-FOC2 | 015E107K05/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 14324714 | 0 | MA2-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-24 | 2102362643 | 8202233820 |  | 8202229308#Pengadaan diaphragm valve exh | RU6-HSC | 32-A-108/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351398 | 8202232335 |  | 8202229307#212 E-2 EFH Bocor | RU2-HCC | 212-EF2R-2/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-11-04 | 2102361780 | 8202233687 |  | 8202229306#Penggantian belt mixer OM | ITP-UP6 | 42-M-301A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102353815 | 8202241108 |  | 8202229303#25_[PV] Pengadaan material un | RU4-TRML | 63P2BD/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352522 | 8202234232 |  | 8202229302#Pemasangan New Slop Transfer | RU2S-KIL | 946-P-5A/00 | 50 | REL NMAT PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-03-16 | 2026-08-03 | 2026-08-03 | 2102351455 | 8202238400 |  | 8202229301#Pemeriksaan LRUT pipa rokan K | RU2-UTL | 510-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA3-STA |  | ADEMULYADI |  | 2026-03-16 | PT02 |  | 3 | 2026-08-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362408 | 8202233904 |  | 8202229300#Modifikasi Glikol 15FT526 | RU6-RCC | 15-FT-526/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-12 | 2026-02-02 | 2026-08-10 | 2102362068 | 8202233607 |  | 8202229299#Penggantian LCS Motor Salamda | RU6-UTL | 53-P-201A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 15972 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-12 | 2026-02-02 | 2026-08-10 | 2102362114 | 8202233606 |  | 8202229298#Penggantian LCS Motor Salamda | RU6-UTL | 53-P-101A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 15972 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-12 | 2026-02-02 | 2026-08-10 | 2102362021 | 8202233605 |  | 8202229297#Penggantian LCS Motor Salamda | RU6-UTL | 53-M-301-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 15972 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102361351 | 8202233338 |  | 8202229296#Perbaikan 15TE701 | RU6-RCC | 15-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-12 | 2026-02-02 | 2026-08-10 | 2102361908 | 8202233604 |  | 8202229295#Penggantian LCS Motor Salamda | RU6-UTL | 53-K-201A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 15906 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363324 | 8202233264 |  | 8202229294#Perbaikan 50-PV-004B | RU6-UTL | 50-PV-004B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-15 | 2102362916 | 8202233056 |  | 8202229293#Perbaikan Motor 15-SLV-105 M2 | RU6-RCC | 15-SLV-105/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-02-03 | 2102352128 | 8202235219 |  | 8202229292#Perbaikan Strainer D-2502 | RU3-PP | 23-D-2502/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-13 | 2026-03-06 | 2026-03-06 | 2102356822 | 8202241105 |  | 8202229288#[CR] Membran Kopling Rusak 12 | RU4-GTO | 120P601A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-04 | 2026-02-11 | 2025-12-31 | 2025-12-31 |  | 8202238398 | 8202235670 | 8202229285#NRK_Fabrikasi Impeller Pompa |  |  | 60 | REL NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-05-25 | 2102358838 | 8202235576 |  | 8202229284#Penggantian Line Chemical N-A | RU5-D&W |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-04 | 2102362808 | 8202232831 |  | 8202229283#Perbaikan Turbine 51-P-101C | RU6-UTL | 51-P-101C-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 7524 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-06-19 | 2026-02-02 | 2026-02-02 | 2102351120 | 8202232205 |  | 8202229278#Perbaikan Motor 945 PM-7A | RU2-ITP | 945-PM-7A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/NR-D2H | 0 | 0 | MA4-LIS |  | SUJATMIKO1 |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351312 | 8202232582 |  | 8202229277#penggantian bearing motor 945 | RU2-ITP | 1-P-94599-A1A1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-27 | 2102362730 | 8202233020 |  | 8202229276#Perbaikan motor mixer 42-M-50 | RU6-ITP | 42-M-502B-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 6930 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351551 | 8202232281 |  | 8202229275#920 E-2 bocor | RU2-HCC | 920-E-2/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-08 | 2026-01-02 | 2026-01-02 | 2102355631 | 8202237642 |  | 8202229272#kerusakan pada Switchrack 60- | RU4-KPC | 60SS21/00 | 50 WASR | CRTD CSER NMAT PRC RELR SETC | 4ER | D14/26/B6/RT-10-C2H | 100000 | 0 | MA4-LIS |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102360530 | 8202235507 |  | 8202229271#POMPA G-34-110A RUSAK | RU5-D&W | G-34-110A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351514 | 8202232422 |  | 8202229270#Penambahan silica gel di junc | RU2-HCC | 212-AR-222/00 | 50 | REL MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 700000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-09 | 2026-02-02 | 2026-02-02 | 2102351132 | 8202232393 |  | 8202229267#CONMON Perbaikan 580-P-301A | RU2-UTL | 580-P-301A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 572229804 | 0 | MA3-ROT |  | T_YUDIPRAS |  | 2026-02-09 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354809 | 8202241102 |  | 8202229264#25_Penggantian Proximity Swit | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357559 | 8202241099 |  | 8202229263#25_Kerusakan Limit Switch 140 | RU4-GTO | 140KV028A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357348 | 8202241096 |  | 8202229262#25_Perbaikan PT Draft Gauge 8 | RU4-KPC | 84F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 4 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356828 | 8202241093 |  | 8202229260#25_Perb Modbus 156K501A Mdl & | RU4-RFCUTL | 156UCPS501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-15 | 2026-02-03 | 2026-02-03 | 2102356820 | 8202236382 |  | 8202229259#D25_O-ring bocor 105FV647 | RU4-RFCGTO | 105FY-U105/00 | 60 | TECO CNF CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | HKHUSNANTO | 2026-06-15 | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2025-12-17 | 2025-12-17 | 2102356786 | 8202236346 |  | 8202229258#D25_Perbaikan Cable Rack Inst | RU4-RFCC | 103V510/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356743 | 8202241090 |  | 8202229257#25_Perbaikan Fan Cab Relics 1 | RU4-RFCUTL | 150SS1EE0131ASC/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 10 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356474 | 8202241087 |  | 8202229255#25_Penggantian Modul Komunika | RU4-RFCC | 101A510B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-25 | 2026-02-05 | 2026-02-05 | 2102352660 | 8202238387 |  | 8202229252#Penggantian Refrigerant 23-K- | RU3-PP | 23-K-2911/01 | 60 | REL GMPS NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 445000000 | 445000000 | MA2-ROT |  | ALEPDALITAN |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-05-22 | 2102358831 | 8202235535 |  | 8202229249#Penggantian Valve Outlet Cond |  |  | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-28 | 2102362525 | 8202233045 |  | 8202229248#Perbaikan Motor 20-E-107F | RU6-RCC | 20-E-107F-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-28 | 2102362598 | 8202233044 |  | 8202229247#Perbaikan motor 20-E-108D | RU6-RCC | 20-E-108D/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 739435 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363664 | 8202232406 |  | 8202229246#Perbaikan 940-PT-1B | RU2-UTL | 940-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 2907240 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-09-30 | 2026-12-29 | 2102358793 | 8202235537 |  | 8202229243#Penggantian Thermal Overload | RU5-E15112 | GM-34-56/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 20 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-09-30 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-05 | 2026-03-02 | 2102362681 | 8202237898 |  | 8202229242#Penagihan Sewa SBNP Thp 1 | RU6-ITP | 43-SPM-01/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351089 | 8202232450 |  | 8202229241#Perbaikan 580-P-304B | RU2-UTL | 580-P-304B/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356840 | 8202241085 |  | 8202229240#25_89P208A Mech Seal Rembes | RU4-KPC | 89P208A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356841 | 8202241083 |  | 8202229239#25_[CR] 89P208B tidak mau men | RU4-KPC | 89P208B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102360531 | 8202235512 |  | 8202229238#Perbaikan GM-17-03B | RU5-E15112 | GM-17-03B/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 185673 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-19 | 2026-03-06 | 2026-03-06 | 2102355675 | 8202241081 |  | 8202229236#25_[CR] 011E124K03 Bearing de | RU4-FOC2 | 011E124K03/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 14434228 | 0 | MA2-ROT |  | MALBARSN |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-07 | 2026-03-06 | 2026-03-06 | 2102355410 | 8202241079 |  | 8202229235#25_[CR] 013P103A mechseal boc | RU4-FOC2 | 013P103A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 40034833 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355101 | 8202241077 |  | 8202229234#25_Penggantian Valve Bunker 8 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102362645 | 8202237897 |  | 8202229229#LTSA Scaffolding 2024-2026 Ta | RU6-HSC | 32-V-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362462 | 8202232992 |  | 8202229228#Perbaikan Pompa 15-P-101C (Ma | RU6-RCC | 15-P-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 739435 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-06 | 2026-01-06 | 2102353853 | 8202241056 |  | 8202229227#25_[CR] 011P117B mech seal bo | RU4-FOC2 | 011P117B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 186117 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-06 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353159 | 8202234539 |  | 8202229226#N_Penggantian press gauge coa | RU3-CDL | PDT-63-001/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357025 | 8202241053 |  | 8202229221#25_[CR] 014P113B flexible cou | RU4-FOC2 | 014P113B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 650000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2025-12-29 | 2025-12-29 | 2102359776 | 8202235510 |  | 8202229220#PERBAIKAN KABEL POWER MOV 423 | RU5-TBL | 022-R-RP-PSAP/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 5 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-05-19 |  | 8202237641 | 8202237560 | 8202229219#TGH3_24 UP Scaff.Rejuve Isol | RU4-TRML | LN71-026A/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-18 | 2102359331 | 8202235538 |  | 8202229218#MAT.PERB.LINE FLARE 12" DHP | RU5-D&W | OC-104/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353855 | 8202236835 |  | 8202229217#D_25 014K102B meger 1,2 Meg | RU4-FOC2 | 014K102BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238386 |  | 8202229216#Tag 23 TSA Pemeliharaan Vacuu | RU3-ITP | 039-P-007/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238475 |  | 8202229215#Tag 22 TSA Pemeliharaan Vacuu | RU3-ITP | 039-P-007/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238474 |  | 8202229214#Tag 16 Pekerjaan PM & CM RU I |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238459 | 8202235817 | 8202229213#Tag 3 Con Mon Peralatan Rotat |  |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238450 | 8202235817 | 8202229212#Tag 2 Con Mon Peralatan Rotat |  |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238428 | 8202235817 | 8202229211#Tag 1 Con Mon Peralatan Rotat |  |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-25 | 2026-01-02 | 2026-01-02 | 2102352661 | 8202235817 |  | 8202229210#Condition Monitoring Peralata |  |  | 01 | CRTD GMCO NMAT PRC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361081 | 8202236398 |  | 8202229208#D25_Fan Motor Rontok 120P602B | RU4-GTO | 120P602B/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA7-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354092 | 8202236399 |  | 8202229204#D25_Cover Fan Motor Rusak 140 | RU4-GTO | 140E611A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102354756 | 8202241051 |  | 8202229203#25_[PV] Perbaikan Pompa 101P5 | RU4-RFCC | 101P501C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354759 | 8202241049 |  | 8202229202#25_[CR] Perbaikan Pompa 30P10 | RU4-TRML | 30P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102362590 | 8202234054 |  | 8202229193#33-P-108 B | RU6-HSC | 33-P-108B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355991 | 8202241047 |  | 8202229191#25_[CR]92E409 A bearing ronto | RU4-SRU | 92E409AM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 20475000 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353980 | 8202236927 |  | 8202229190#penggantian bearing 47S508BM | LOC1-UP4 | 47S508B/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354220 | 8202235779 |  | 8202229189#perbaikan motor 47P-504A | LOC1-UP4 | 47P504A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-06-08 | 2026-02-02 | 2026-11-04 | 2102362468 | 8202234107 |  | 8202229186#11-P-104 A | RU6-HSC | 11-P-104A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-05 | 2026-05-21 | 2026-12-07 | 2026-12-07 | 2102352113 | 8202238676 |  | 8202229184#Penambahan dan Perbaikan Hand | RU2-HSC | 100-E-14A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-12-07 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102351305 | 8202232662 |  | 8202229183#Pengadaan Motor 550-PM-102 | RU2-UTL | 550-PM-102/00 | 50 | REL MACM PRC SETC | 2ER | D12/25/B6/NR-D2H | 0 | 0 | MA3-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351631 | 8202232369 |  | 8202229182#Perbaikan Cooler | RU2-HSC | 300-E-3/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 378035 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351555 | 8202232638 |  | 8202229181#Pengambilan Material 100-E-14 | RU2-HSC | 100-E-14B/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 756900 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-18 | 2102358792 | 8202235497 |  | 8202229180#MAT.Perb.pipa snuffing steam | RU5-E15112 | F-2-01B/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-18 | 2102359055 | 8202235500 |  | 8202229179#MAT.Perb. Valve LP Drain G-3- | RU5-E15112 | G-3-01B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-26 | 2102362647 | 8202233843 |  | 8202229178#Penambahan Power MCB 12-K-501 | RU6-DHC | 12-K-501A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-03-07 | 2026-02-03 | 2026-02-03 | 2102358391 | 8202234618 |  | 8202229177#Penggantian PI 1-P-02 | RU7-CDU | 1-P-02A/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH | 2025-10-07 | 2026-02-07 | PT02 |  | 3 | 2025-10-07 | PM |  | 005
| K701 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 | 2102358390 | 8202234611 |  | 8202229176#Penggantian PI 1-P-12 | RU7-CDU | 1-P-12A/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH | 2026-02-03 | 2026-02-07 | PT02 |  | 3 | 2026-03-09 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353944 | 8202241043 |  | 8202229168#25_Penggantian Positioner 240 | RU4-LOC3 | 240FV024/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102361673 | 8202232954 |  | 8202229167#Perbaikan Pompa 42-P-503A | RU6-ITP | 42-P-503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-09 | 2102359887 | 8202235489 |  | 8202229166#Perbaikan Control Valve AGV 5 | RU5-TBL | 101-PT-01A-INST/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 658000000 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 004
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-03-25 | 2102358880 | 8202235483 |  | 8202229165#Perbaikan PI Lokal Area 201-P | RU5-D&W | 201-PCV-118/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1145882 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-25 | 2026-02-04 | 2026-02-04 | 2102351329 | 8202238139 |  | 8202229163#RK0125 LTSA SPRING SUP | RU2-HCC | 2NAL21135A1A2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1661370000 | 0 | MA2-STA |  | DEDISUKMANA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355092 | 8202234929 |  | 8202229162#penambahan level di reservoir | RU4-FOC2 | 014K101T1/00 | 01 | CRTD CSER MACM PRC | 4IR |  | 14612942 | 0 | MA2-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354184 | 8202241041 |  | 8202229161#25_200LT051 Level CPI Selatan | RU4-LOC3 | 200LT051/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-10-05 | 2026-12-30 | 2102359442 | 8202235486 |  | 8202229160#Perbaikan Oil Cooler Bawah ST | RU5-UTL | TG-5A-OIL-COOLR/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-10-05 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102353940 | 8202241039 |  | 8202229159#25_Transmitter Rusak 140TI069 | RU4-GTO | 140TT069/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-29 | 2026-12-29 | 2102358999 | 8202235493 |  | 8202229158#Komponen Kontrol Heater P-5-2 | RU5-E15111 | P-5-20/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102353888 | 8202241036 |  | 8202229157#25_Sensor Rusak 140TI025A di | RU4-GTO | 140TE025A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353886 | 8202241034 |  | 8202229155#25_Display Rusak 120PT612 A | RU4-GTO | 120PT612A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-02 | 2026-06-30 | 2102359714 | 8202235480 |  | 8202229151#Perbaikan Solenoid Horn K-4-0 | RU5-E15111 | K-4-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 81496800 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102362517 | 8202233121 |  | 8202229149#Perbaikan LCS area STG C | RU6-UTL | 51-G-101C/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 7920 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355152 | 8202241032 |  | 8202229148#25_Motor noise 041P309M | RU4-TRML | 041P309M/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102353946 | 8202241029 |  | 8202229145#25_[CR] Shearpin chiller 24E1 | RU4-LOC1 | 24E1A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 4320000 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354182 | 8202241026 |  | 8202229134#25_[CR] Penggantian Seal Oil | RU4-FOC1 | 14K1F1B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 15572108 | 15572107 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-03 | 2026-02-11 | 2026-09-28 | 2026-11-26 | 2102358796 | 8202237711 |  | 8202229132#Tag-1 UR. Perbaikan Bundwall | RU5-TBL | 022-R-RP9/00 | 60 | REL NMAT PRC SETC | 5MR | D15/25/B6/RT-D1H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-09-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102357788 | 8202235469 |  | 8202229129#Perbaikan Em-17-03D & GM-3-19 | RU5-E15112 | EM-17-03D/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 661264 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K701 | 2026-02-02 | 2026-03-09 | 2026-01-02 | 2026-01-02 | 2102358394 | 8202234608 |  | 8202229128#Kebocoran HE 1-E-30 | RU7-CDU | 1-E-30/00 | 60 | REL CSER MANC PRC SETC | 7RT | D17/26/B6/RT-1-D1H | 4822006 | 0 | MA-STA |  | YAYANHER |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357288 | 8202235284 |  | 8202229126#PCV FG BOILER 104 052PCV492 | RU4-UTL | 052B104/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357286 | 8202241023 |  | 8202229125#25_PCV PILOT BOILER 104 052PC | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357282 | 8202235289 |  | 8202229124#PCV FG BOILER 103 052PCV392 | RU4-UTL | 052B103/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357284 | 8202241020 |  | 8202229123#25_PCV PILOT BOILER 103 052PC | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357237 | 8202241018 |  | 8202229122#25_PCV PILOT BOILER 102 052PC | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357280 | 8202235293 |  | 8202229121#PCV FG BOILER 102 052PCV292 | RU4-UTL | 052B102/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357233 | 8202241016 |  | 8202229120#25_PCV PILOT BOILER 101 052PC | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357235 | 8202235296 |  | 8202229119#PCV FG BOILER 101 052PCV092 | RU4-UTL | 052B101/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354954 | 8202241014 |  | 8202229118#25_Penggantian Temp Indicator | RU4-TRML | 33PSV306/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354087 | 8202241012 |  | 8202229117#25_025FT_008 penunjukan rusak | RU4-LOC2 | 025FT008/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353881 | 8202241010 |  | 8202229116#25_Penunjukkan 022FT-002 NaN | RU4-LOC2 | 022FT002/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-17 | 2025-12-17 | 2102353857 | 8202236449 |  | 8202229115#D25_014LT26 (014V126 ) ngacau | RU4-FOC2 | 014V126/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357557 | 8202241008 |  | 8202229107#25_[CR] Perbaikan Cooler Mech | RU4-RFCC | 102P507B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K701 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102358398 | 8202234607 |  | 8202229106#Perbaikan motor 1-PM-13A ( MO | RU7-CDU | 1-PM-13A/00 | 50 | CRTD NMAT PRC | 7RT | D17/10/B6/RT1-CDUNH | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 005
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358397 | 8202234605 |  | 8202229105#Perbaikan motor 1-PM-12A ( Be | RU7-CDU | 1-PM-12A/00 | 50 | CRTD NMAT PRC | 7RT | D17/10/B6/RT1-CDUNH | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K202 | 2026-02-02 | 2026-04-16 | 2026-01-02 | 2026-01-02 | 2102352501 | 8202234231 |  | 8202229104#ELECTRICAL CONSUMABLE PA | RU2S-KIL |  | 50 | REL CSER MANC PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 49067330 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354180 | 8202241006 |  | 8202229103#25_[CR] Penggantian Lubricato | RU4-FOC1 | 13K1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-04-09 | 2102358815 | 8202235373 |  | 8202229101#PERBAIKAN TRANSMITTER 01-FT-3 | RU5-E15111 | 01-FT-327/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 21948149 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102355182 | 8202241004 |  | 8202229099#25_[CR]Penggantian shim coupl | RU4-SRU | 91P401A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 733649 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362403 | 8202232982 |  | 8202229097#Perbaikan Pompa 16-P-108B | RU6-RCC | 16-P-108B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2026-08-28 |  | 8202238418 |  | 8202229096#Upgrade PLC Dryer 58-D-101C & | RU6-UTL | 58-D-101C/00 | 50 | REL NMAT PRC SETC | 6IR | D16/26/B6/NR-C2H | 1321 | 0 | MA4-INT |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238415 | 8302404613 | 8202229094#Tag 10 Supp. Teknisi Rope Acc | RU3-UTL | RPA3-P-001/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357646 | 8202241001 |  | 8202229092#25_perbaikan LCS di area foc2 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 2827804500 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102357049 | 8202240984 |  | 8202229089#25_[CR] Penggantian membran c | RU4-LOC1 | 22P2B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 17607576 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-05-13 | 2102359888 | 8202235475 |  | 8202229088#Cleaning ACW Cooler E-232-01A | RU5-D&W | E-232-01/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102357047 | 8202240982 |  | 8202229087#25_[CR] Penggantian membran c | RU4-LOC1 | 21P10/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 11189544 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-02-03 | 2102352875 | 8202235721 |  | 8202229086#ARC Valve pada discharge 2008 | RU3-UTL | 2008-JA/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-07-07 |  | 8202236657 | 8202233858 | 8202229085#SWO Pemb. LTSA CV Masoneila T | RU6-RCC | 16-FV-018/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-06-29 |  | 8202236660 | 8202233858 | 8202229084#SWO Pemb. LTSA CV Masoneila T | RU6-RCC | 16-FV-018/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-05-11 |  | 8202236747 | 8202232770 | 8202229083#SPK 26 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-18 | 2102362510 | 8202233542 |  | 8202229082#Penggantian positioner 52-FV- | RU6-UTL | 52-B-101E/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 1320 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102352488 | 8202234229 |  | 8202229081#Perbaikan Coupling 717-JP-1B | RU2S-LKKK | 717-JP-1B/00 | 01 | CRTD NMAT PRC | 2RS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | JUNIANTO |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351556 | 8202232249 |  | 8202229080#Perbaikan modul AI 905-TG-02 | RU2-UTL | 905-G-2/00 | 50 | REL CSER NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-12-30 | 2102357787 | 8202235370 |  | 8202229077#Perbaikan Line Seal LEG 1,5 I | RU5-D&W | 202-P038-2/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351639 | 8202232593 |  | 8202229076#perbaikan selenoid valve boil | RU2-UTL | 550-B-2/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354096 | 8202240979 |  | 8202229072#25_Perbaikan control valve 54 | RU4-UTL | 54WS201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2025-11-28 | 2025-11-28 | 2102353929 | 8202240977 |  | 8202229071#25_Penggantian 156PT668A | RU4-RFCUTL | 156PT-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357412 | 8202240975 |  | 8202229070#25_Penggantian PCV L.O STG 51 | RU4-UTL | 51G201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357414 | 8202236528 |  | 8202229069#Penggantian PCV L.O STG 51TCV | RU4-UTL | 51G201/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357388 | 8202240973 |  | 8202229068#25_Penggantian PCV L.O STG 51 | RU4-UTL | 510G301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357410 | 8202240971 |  | 8202229067#25_Penggantian PCV L.O STG 51 | RU4-UTL | 510G301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-02-26 | 2026-12-30 | 2102357334 | 8202236521 |  | 8202229065#26_Penggantian PCV PUMP 054PC | RU4-UTL | 054P101C/00 | 50 WAMA | REL CSER PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | DWIHIZZKI |  | 2026-02-26 | PT02 |  | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-03-09 | 2102354505 | 8202241435 |  | 8202229064#[CR] Perbaikan Pompa 54WS2P2 | RU4-UTL | 54WS2P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 70869100 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-02-26 | 2026-12-30 | 2102357332 | 8202236523 |  | 8202229063#26_Penggantian PCV LO PUMP BF | RU4-UTL | 054P101B/00 | 50 WAMA | REL CSER PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | DWIHIZZKI |  | 2026-02-26 | PT02 |  | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-06 | 2026-02-26 | 2026-12-30 | 2102357330 | 8202236525 |  | 8202229062#26_Penggantian PCV LO PUMP BF | RU4-UTL | 054P101A/00 | 50 WAMA | REL CSER PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | DWIHIZZKI |  | 2026-02-26 | PT02 |  | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237640 | 8202237615 | 8202229061#TGH5_24 UP scaff rejuve MA-4 | RU4-KPC | 84C204/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237639 | 8202237616 | 8202229060#TGH4_24 UP Pipa MA-7 | RU4-RFCC | 106-ACF0015-4/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356372 | 8202236094 |  | 8202229059#UP_25 pengecatan equipment di |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-06 | 2102358791 | 8202235372 |  | 8202229058#MAT. Perb. E-19-01 | RU5-E15112 | E-19-01/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351673 | 8202232479 |  | 8202229057#Overhaul Pompa | RU2-HSC | 301-P-3B/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356908 | 8202240969 |  | 8202229054#25_Mtl. Penggantian Catridge | RU4-FOC2 | 011V105/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 10860000 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355348 | 8202240967 |  | 8202229053#25_Mtl. Penggantian Catridge | RU4-FOC2 | 011V105/00 | 60 | REL CSER GMPS MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 10860000 | 10860000 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102353885 | 8202240965 |  | 8202229052#25_[PV] Perbaikan Kompresor 1 | RU4-RFCGTO | 108K501B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 689855 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102356843 | 8202240963 |  | 8202229044#25_[CR]91E-409A2, ganti pulle | RU4-SRU | 91E409A2M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102356842 | 8202240961 |  | 8202229043#25_[CR]91E-409A1, ganti pulle | RU4-SRU | 91E409A1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102353949 | 8202240959 |  | 8202229042#25_[CR] Perbaikan Pompa 41P9 | RU4-TRML | 41P9/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362302 | 8202233873 |  | 8202229040#Pekerjaan Minor Repair 37-P-1 | RU6-POC | 37-P-103B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102362353 | 8202233874 |  | 8202229038#Pekerjaan Minor Repair 36-P-1 | RU6-POC | 36-P-102B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362359 | 8202233875 |  | 8202229037#Pekerjaan Minor Repair 36-P-1 | RU6-POC | 36-P-102A-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362263 | 8202233876 |  | 8202229036#Pekerjaan Minor Repair 34-P-1 | RU6-POC | 34-P-110B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362357 | 8202233877 |  | 8202229035#Pekerjaan Minor Repair 34-P-1 | RU6-POC | 34-P-110A-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362350 | 8202233878 |  | 8202229034#Pekerjaan Minor Repair 34-P-1 | RU6-POC | 34-P-107B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362355 | 8202233879 |  | 8202229033#Pekerjaan Minor Repair 34-P-1 | RU6-POC | 34-P-107A-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-22 | 2026-10-20 | 2026-10-20 | 2102363639 | 8202232257 |  | 8202229030#MCC IPAL ES#5 dan ES#9 | RU2-UTL | 905-MCC15-SS1/00 | 50 | REL MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 229812320 | 0 | MA3-LIS |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-10-20 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364378 | 8202236378 |  | 8202229024#D25_Pembongkaran Oil Anlyzer |  |  | 50 WAMA | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357189 | 8202240957 |  | 8202229022#25_Penggantian PCV LO STG 103 | RU4-UTL | 051G103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357231 | 8202240954 |  | 8202229020#25_Penggantian PCV LO STG 103 | RU4-UTL | 051G103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357185 | 8202240951 |  | 8202229019#25_Penggantian PCV LO STG 103 | RU4-UTL | 051G103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102358811 | 8202235343 |  | 8202229017#Perbaikan lampu penerangan jl | RU5-TBL | PLANT-21-LIS/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 117375000 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357187 | 8202240948 |  | 8202229016#25_Penggantian PCV LO STG 103 | RU4-UTL | 051G103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357181 | 8202240945 |  | 8202229015#25_Penggantian PCV LO STG 102 | RU4-UTL | 051G102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357117 | 8202240942 |  | 8202229014#25_Penggantian PCV LO STG 102 | RU4-UTL | 051G102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357119 | 8202240940 |  | 8202229013#25_Penggantian PCV LO STG 102 | RU4-UTL | 051G102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-17 | 2025-12-17 | 2102355205 | 8202236432 |  | 8202229012#D25_84PS569B Purging system L | RU4-KPC | 84K202B/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354901 | 8202240938 |  | 8202229011#25_perbaikan 88LV223 | RU4-KPC | 88LV223/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-03-25 | 2026-03-25 | 2102358816 | 8202235339 |  | 8202229004#PERBAIKAN MOTOR FINFAN EAM-20 | RU5-D&W | EAM-202-05A/00 | 60 | REL CNF CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | HELDIPRANATA | 2026-03-25 | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-26 | 2026-11-24 | 2102358832 | 8202235337 |  | 8202228995#Perbaikan Pompa Jockey Pump G | RU5-E15500 | G-33-02B/01 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 7303500 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-12-28 | 2026-12-28 | 2102358830 | 8202235361 |  | 8202228993#Perbaikan Gearbox GB-33-01C |  |  | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-12-28 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102353005 | 8202234573 |  | 8202228990#N_Penggantian FGDS CDGP CDL O | RU3-CDGP | CRCD-FGDS/00 | 50 WAMA | REL GMPS MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354627 | 8202237638 |  | 8202228986#TGH1_25 UP PERB LIGHTING SYST | RU4-KPC | 80EE0032F-PNL/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354433 | 8202240936 |  | 8202228984#25_[CR] Governor turbine 025P | RU4-LOC2 | 025P101A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 21297893 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-02-03 | 2026-03-04 | 2102360100 | 8202235336 |  | 8202228983#PERBAIKAN SOLENOID LOADER VAL | RU5-E15112 | K-19-01A-INST/00 | 60 | REL CSER PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | RUDIEKO |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-03-06 | 2102358958 | 8202235368 |  | 8202228982#MAT.Perb.PIPA 8A-VF01 JALUR V | RU5-E15112 | 8A-VF1-8-B3/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102358993 | 8202235342 |  | 8202228981#Perbaikan lampu stack Boiler | RU5-UTL | HHP-5/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 63200000 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202236674 | 8202234997 | 8202228980#TKDN KV Penyediaan Jasa Hose |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102358994 | 8202235345 |  | 8202228978#Perbaikan Lampu Indikator MCC | RU5-UTL | 1AL09/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 301 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102358797 | 8202235363 |  | 8202228977#Perbaikan Fin-Fan EA-32-01S | RU5-E15112 | EA-32-01S/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102358799 | 8202235335 |  | 8202228975#Turbine GT-3-09C Reverse Engi | RU5-E15112 | GT-3-09C/00 | 01 | CRTD CSER NMAT PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-20 | 2102362203 | 8202237896 |  | 8202228973#Perbaikan 11-E-110 dan 11-E-1 | RU6-HSC | 11-E-110A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102346846 | 8202232559 |  | 8202228971#Penggantian Filter 211 F-1 | RU2-HCC | 211-BV-F1A/00 | 50 | REL MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 8142768 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102358881 | 8202235332 |  | 8202228970#GLAND PACKING POMPA G-5-09B B | RU5-E15111 | G-5-09B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 26444175 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357384 | 8202240934 |  | 8202228969#25_Low Flow 39P204A | RU4-TRML | 39P204A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102363497 | 8202237894 |  | 8202228968#Pembayaran SPK2 Unitprice OH | RU6-DHC | 12-K-501A/00 | 60 | REL CSER GMPS NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 38222250 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351756 | 8202232553 |  | 8202228967#PM 905-TRF-2-2 | RU2-UTL | 905-TRF-2-2/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 7119200 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-18 | 2102362268 | 8202232748 |  | 8202228966#Repair 34-A-103-P-101 BM | RU6-POC | 34-A-103-P-101BM/0 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-05-25 |  | 8202238412 | 8202235565 | 8202228965#Tag. 18 Operator & Pem. Alat | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-25 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-05-25 |  | 8202238409 | 8202235565 | 8202228963#Tag. 17 Operator & Pem. Alat | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-25 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102354834 | 8202234737 |  | 8202228962#RK25_Pekerjaan Isolasi Area P | RU4-KPC | 85C204/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238406 | 8202234623 | 8202228961#Tag 4 KV Isolasi Area PP |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-06-19 | 2026-02-04 | 2026-02-04 | 2102351359 | 8202238020 |  | 8202228960#Material Kit Component Conmon | RU2-HCC | 211-P-1A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 690002000 | 0 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-06-19 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 | 2102351670 | 8202238397 |  | 8202228957#Pekerjaan LTSA Trafo Area Kil | RU2-UTL | 905-TRF-1-1/01 | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 1000000000 | 402900000 | MA3-LIS |  | T_YUDIPRAS |  | 2026-02-14 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238396 | 8202235092 | 8202228955#Tag 6 Supporting Teknisi dan | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352063 | 8202232445 |  | 8202228954#Perbaikan 905-PT-58 | RU2-UTL | 905-PT-58/00 | 60 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 13 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102346848 | 8202232454 |  | 8202228952#Perbaikan 520-P608H | RU2-UTL | 520-P-608H/00 | 60 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202235334 |  | 8202228948#Fabrikasi Part Pompa G-3-13D | RU5-E15112 | G-3-13D/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | WS-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354411 | 8202240932 |  | 8202228947#25_Pengadaan Gasket Steam/Mud | RU4-RFCUTL | 151B501C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 7704000 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102358810 | 8202235197 |  | 8202228946#Perb.Pompa P.6A Putih Prtaser | RU5-TBL | P-6RP-A-PUTIH/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 2879370 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356712 | 8202236552 |  | 8202228945#D_25 tidak muncul alarm di 80 | RU4-TRML | 39P207A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355719 | 8202240930 |  | 8202228944#25_[CR] Perbaikan ALOP 053P10 | RU4-UTL | 053P101AT-P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-03 | 2102358798 | 8202235179 |  | 8202228943#Perbaikan Turbine GT-1-12B | RU5-E15111 | GT-1-12B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 158325020 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-05-19 |  | 8202236578 | 8202237799 | 8202228942#Tgh ke-4 LTSA Repair Built Up | RU6-RCC | 20-R-101C/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-29 | 2025-12-29 | 2102359505 | 8202235181 |  | 8202228936#Perbaikan Motor Em-3-16A | RU5-E15112 | EAM-3-16A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 8476351 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-05-19 |  | 8202237637 |  | 8202228934#TGH27_23 Kontrak Peformance M | RU4-KPC | 88P201A/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 25992000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-07-15 | 2102358837 | 8202235194 |  | 8202228933#Perbaikan FDF HHP Boiler 2 |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1143400 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102358834 | 8202235200 |  | 8202228929#Perb. lampu Penerangan jl.207 | RU5-TBL | PLANT-21-LIS/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 3000000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K701 | 2026-02-02 | 2026-05-08 | 2026-02-02 | 2026-02-02 | 2102358399 | 8202234603 |  | 8202228928#Perbaikan Motor 2-PM-01 B | RU7-NHT | 2-PM-01B/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D1H | 0 | 0 | MA-LINT |  | SAPBATCH | 2026-03-09 | 2026-02-07 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102352988 | 8202234563 |  | 8202228927#N_Penggantian LSHH Steam Drum | RU3-UTL | LT-20231B/00 | 50 | CRTD CSER MACM PRC | 3IR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-05-26 | 2026-02-02 | 2026-02-02 | 2102353011 | 8202234528 |  | 8202228926#N_Penggantian Solenoid CV-200 | RU3-UTL | LY-20034/00 | 50 WAMA | CRTD CSER MACM PRC | 3IR |  | 0 | 0 | MA2-INT |  | ALEPDALITAN |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102352756 | 8202234492 |  | 8202228925#N_Perbaikan Slide Valve ZCV26 | RU3-CDL | FC-SLV-303/00 | 50 WAMA | CRTD CSER MACM PRC | 3IR |  | 0 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102361930 | 8202233177 |  | 8202228924#Perbaikan FDF Boiler 52-B-101 | RU6-UTL | 52-B-101E-K1-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357183 | 8202240928 |  | 8202228923#25_Penggantian PCV LO STG 102 | RU4-UTL | 051G102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357112 | 8202240926 |  | 8202228922#25_Penggantian PCV LO STG 101 | RU4-UTL | 051G101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357111 | 8202240924 |  | 8202228921#25_Penggantian PCV LO STG 101 | RU4-UTL | 051G101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357113 | 8202240922 |  | 8202228920#25_Penggantian PCV LO STG 101 | RU4-UTL | 051G101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357115 | 8202240920 |  | 8202228919#25_Penggantian PCV LO STG 101 | RU4-UTL | 051G101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-10 | 2026-02-04 | 2026-11-17 | 2102357461 | 8202237360 |  | 8202228918#26_81KV445/00 passing | RU4-KPC | 81KV445/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-06-10 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357002 | 8202237358 |  | 8202228917#84KV441 passing |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354751 | 8202240917 |  | 8202228916#25_014K101 , 014 PSL-029 rusa | RU4-FOC2 | 014K101/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 1 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355967 | 8202240914 |  | 8202228915#25_Pengadaan Pulley Mtor Finf | RU4-GTO | 120E602A-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355799 | 8202237636 |  | 8202228914#TGH1_25 UP Pipa & Acc UTL RFC | RU4-RFCC | 151-FG0003-8/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102355787 | 8202240911 |  | 8202228913#25_[CR] Perbaikan Pompa 54P5A | RU4-UTL | 54P5A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 9347544 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-11-04 | 2102361904 | 8202233854 |  | 8202228911#Pemb. LTSA Sistem SPARING Gat | RU6-LK/KK | JALANKILANG/00 | 01 | CLSD CSER NCMP NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-12 | 2026-02-03 | 2026-12-30 | 2102355105 | 8202237635 |  | 8202228908#TGH1_25 UP Cleaning HE Cooler | RU4-UTL | 54E1/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TONNYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102363120 | 8202233418 |  | 8202228907#Perbaikan 11-PDI-191 | RU6-HSC | 11-P-102B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102363383 | 8202233327 |  | 8202228906#Perbaikan 16TE716A | RU6-RCC | 16-K-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102361439 | 8202233357 |  | 8202228905#Perbaikan 15-A-107B | RU6-RCC | 15-A-107B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-13 | 2102361435 | 8202233586 |  | 8202228903#Penggantian material 15-A-107 | RU6-RCC | 15-A-107A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102361827 | 8202232899 |  | 8202228902#Perbaikan Regulator 11-UV-004 | RU6-HSC | 11-UV-004/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354715 | 8202237013 |  | 8202228889#D_25 011E-124 M4 pully motor | RU4-FOC2 | 011E124M04/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355317 | 8202235874 |  | 8202228886#Perbaikan Line 49-24AA OM NBM |  |  | 50 WENG | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355718 | 8202240908 |  | 8202228884#25_PI Fuel Oil 025F101 rusak | RU4-LOC2 | 025F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 100 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-20 | 2102362711 | 8202237893 |  | 8202228879#Pemb. LTSA PT Spektris Termin | RU6-LAB | LABORATORIUM/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-24 | 2102361869 | 8202233362 |  | 8202228871#Perbaikan 14-P-903A | RU6-DHC | 14-P-903A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 73943 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-06 | 2026-03-06 | 2102357938 | 8202240904 |  | 8202228868#25_motor 85P205BM Noise | RU4-KPC | 85P205BM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 1224000 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-05-05 | 2026-05-05 |  | 8202235177 | 8202235113 | 8202228866#Backlog GI Rotating |  |  | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 84698246 | 0 | MA3-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356876 | 8202236704 |  | 8202228864#D_25 88P204BM Noise Up Normal | RU4-KPC | 88P204BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-29 | 2102363389 | 8202233208 |  | 8202228863#Perbaikan Catridge SO system | RU6-DHC | 12-K-101-S2A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354201 | 8202236679 |  | 8202228862#D_25 heater DGS 89K201 trip | RU4-KPC | 89K201/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353826 | 8202236626 |  | 8202228861#D_25 Motor short 260E122BM1 | RU4-LOC3 | 260E122BM1/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357463 | 8202236706 |  | 8202228860#D_25 85P205BM noise ( muncul | RU4-KPC | 85P205BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-09-28 | 2026-09-28 | 2102359113 | 8202235158 |  | 8202228859#Mat'l Refurbish Spare Unit Bl | RU5-E15111 | K-5-22/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 326686290 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-09-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356754 | 8202240901 |  | 8202228858#25_motor 86P207DM noise | RU4-KPC | 86E207DM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 2102800 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102356715 | 8202240897 |  | 8202228856#25_66P203A motor abnormal noi | RU4-TRML | 66P203AM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 170350 | 0 | MA4-LIS |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355786 | 8202236689 |  | 8202228853#D_25 Cover fan motor 240E102B | RU4-LOC3 | 240E102BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353953 | 8202240894 |  | 8202228851#25_013E107M05 Motor noise | RU4-FOC2 | 013E107M05/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 842800 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102358035 | 8202240891 |  | 8202228849#25_013E102M02 Motor Noise | RU4-FOC2 | 013E102M02/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 842800 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-02 | 2026-06-02 | 2102359112 | 8202235160 |  | 8202228848#Mat'l Refurbish Spare Unit Bl | RU5-E15111 | K-5-21/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357541 | 8202236872 |  | 8202228845#D_25 013E111M04 Pushbutton at | RU4-FOC2 | 013E111M04/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-20 | 2102363395 | 8202236802 |  | 8202228844#PM1 - LTSA UV 3900 PT INDOTEC | RU6-LAB | A-9054007000/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 5106000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-05-20 |  | 8202236635 | 8202233851 | 8202228840#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356109 | 8202240888 |  | 8202228838#25_Perbaikan motor 023E108M4 | RU4-LOC2 | 023E108/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 212400 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-06 | 2026-03-06 | 2102356107 | 8202240885 |  | 8202228834#25_Perbaikan Motor 021P-102B | RU4-LOC2 | 021P102B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 676550 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356963 | 8202236722 |  | 8202228832#D_25 018P702AM Motor noise | RU4-FOC2 | 018P102A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355717 | 8202236729 |  | 8202228830#D_25 018F101 SB no 4 Overload | RU4-FOC2 | 018F101M04/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355711 | 8202236877 |  | 8202228828#D_25 012F102 perbaikan contro | RU4-FOC2 | 012F102/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354754 | 8202236732 |  | 8202228826#D_25 018F-101 SB tidak bisa j | RU4-FOC2 | 018F101/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354752 | 8202236792 |  | 8202228825#D_25 014P102B vibrasi 5.56 s | RU4-FOC2 | 014P102BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354717 | 8202236922 |  | 8202228823#D_25 011K101A-P2 vibrasi Moto | RU4-FOC2 | 011K101AP2M/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-22 | 2026-02-03 | 2026-03-04 | 2102358818 | 8202235156 |  | 8202228821#Perbaikan Speed Sensor Turbin | RU5-E15111 | K-5-02B/00 | 60 | REL CSER PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | RUDIEKO |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355201 | 8202240882 |  | 8202228820#25_[CR] Penggantian Mech Seal | RU4-TRML | 71P9B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 3729250 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-03 | 2026-11-24 | 2102358817 | 8202235100 |  | 8202228819#POMPA G-202-08B RUSAK (RUBBER | RU5-D&W | G-202-08B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 20700000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2025-12-17 | 2025-12-17 | 2102355309 | 8202236353 |  | 8202228817#D25_Perbaikan Alarm HMI HPC R | RU4-RFCC | 104K501/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-19 | 2102362479 | 8202233590 |  | 8202228814#Penggantian limit switch 32-X | RU6-HSC | 32-XV-335/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354747 | 8202236701 |  | 8202228813#D_25 Breaker motor 041P106A r | RU4-TRML | 041P106A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354924 | 8202236963 |  | 8202228809#D_25 011E117M01 motor trip tr | RU4-FOC2 | 011E117M01/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354497 | 8202236960 |  | 8202228808#D_25 011E121M04 meger rendah | RU4-FOC2 | 011E121M04/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353822 | 8202236959 |  | 8202228806#D_25 011E124M04 Motor noise | RU4-FOC2 | 011E124M04/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357007 | 8202240879 |  | 8202228805#25_Mtl. Penyehatan Pipa di 01 | RU4-FOC2 | 011K101A/01 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 179766184 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238393 | 8202235126 | 8202228799#Tag 2 Mekanik Area Utara OM |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K202 | 2026-02-02 | 2026-04-23 | 2026-02-02 | 2026-02-02 | 2102352502 | 8202234228 |  | 8202228797#Preventive Maintenance 4000 H | RU2S-KIL | 900-06GE-7/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 40950000 | 17600000 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 |  | 8202235146 | 8202235136 | 8202228790#Perbaikan Mechanical RU V |  |  | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 496415783 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102358813 | 8202235136 |  | 8202228789#Perbaikan Mechanical RU V |  |  | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 326351681 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-29 | 2026-11-19 | 2102358814 | 8202235113 |  | 8202228786#Perbaikan Rotating RU V |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-29 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-04 | 2102358971 | 8202235153 |  | 8202228782#PERB.LINE BLEND NAPTHA PR TIM | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 94450125 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238468 | 8202234582 | 8202228778#Tag 5 Perbaikan Korosi Atap T |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355062 | 8202237634 |  | 8202228770#TGH2-5_25 UP MON&INSP PERALAT | RU4-RFCGTO | 107P502A-MCC/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-06-30 | 2102357403 | 8202237633 |  | 8202228769#TGH1_SIP_UP Fire Proofing MA | RU4-FOC1 | LN10-12A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351128 | 8202232329 |  | 8202228763#pengadaan flexible joint 945 | RU2-ITP | BLP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-09 | 2026-02-03 | 2026-07-09 |  | 8202237632 |  | 8202228762#Pekerjaan HOVF coating shaft | RU4-UTL | 54P202A/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 18346000 | 0 | MA5-ROT |  | AGHANIAKBAR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238454 | 8202235105 | 8202228760#Tag 6 Mekanik CDL, OM, UTL SG |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238124 | 8202235291 | 8202228759#Tag 8 Mekanik Area Selatan OM |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-26 | 2026-02-02 | 2026-02-02 | 2102352873 | 8202234556 |  | 8202228758#N_Penggantian module AI PLC G | RU3-UTL | XV-20250C/00 | 50 WAMA | CRTD CSER MACM PRC | 3IR |  | 0 | 0 | MA2-INT |  | ALEPDALITAN |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237631 | 8202237512 | 8202228757#TGH19_23 TSA ConMon Instrumen | RU4-RFCC | 101FJB001/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 277919000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354611 | 8202240874 |  | 8202228753#25_[CR] Membran Kopling Pecah | RU4-GTO | 140P604A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352706 | 8202234517 |  | 8202228751#Perbaikan Shaft Pompa 6 RPM R | RU3-ITP | ITP-RPR-P-006/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 |  | 8202238437 |  | 8202228745#Perbaikan PSV Passing 104PSV5 | RU4-RFCC | 104PSV502A/00 | 01 | CRTD CSER NMAT PRC | 4MR |  | 1 | 0 | MA6-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 001
| K501 | 2026-02-02 | 2026-05-25 | 2025-12-29 | 2025-12-29 | 2102360176 | 8202235088 |  | 8202228721#PERBAIKAN ELMOT P-2 SEI WAIN | RU5-UTL | P-2-S-WAIN-EM/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 45351765 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-06 | 2026-08-27 | 2026-08-27 | 2102359111 | 8202235086 |  | 8202228720#Perbaikan Motor Mixer Tanki 1 | RU5-TBL | 101-5-MI-1B2/00 | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 10066070 | 0 | MA4-LIS |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-08-27 | PM |  | 045
| K501 | 2026-02-05 | 2026-02-07 | 2026-03-02 | 2026-04-20 | 2102358957 | 8202238611 |  | 8202228710#PERBAIKAN AC SS 62 | RU5-UTL | 41-AC-SS-62/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 26890755 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 | 2102358950 | 8202235081 |  | 8202228708#INSPEKSI MOD TANK A-7 DAN R-2 | RU5-TBL | KAN-ITP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 5888000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102361706 | 8202237892 |  | 8202228706#LTSA General Purpose Line Dra | RU6-ITP | 42-T-101A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-25 | 2102363038 | 8202233502 |  | 8202228705#Penggantian smart positioner | RU6-HSC | 32-PDV-054/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102361825 | 8202233359 |  | 8202228704#Perbaikan 14-VSHH-501 | RU6-DHC | 14-K-102B/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366045 | 8202240871 |  | 8202228702#25_Penggantian solenoid 14D65 | RU4-FOC1 | 14D650/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-19 | 2102363182 | 8202233495 |  | 8202228701#Penggantian solenoid air regi | RU6-UTL | 52-B-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 8580 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362293 | 8202234112 |  | 8202228699#11-AT-401 | RU6-HSC | 11-AT-402/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355798 | 8202240868 |  | 8202228697#25_CM_Perbaikan Stack & Ducti | RU4-RFCGTO | 105A502CP945/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-31 | 2102361783 | 8202233287 |  | 8202228696#Perbaikan 32-UV-010 | RU6-HSC | 32-UV-010/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-31 | 2102361781 | 8202233295 |  | 8202228695#Perbaikan 31-FV-017 | RU6-HSC | 31-FV-017/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102361788 | 8202237891 |  | 8202228694#Pengecatan Area RCC Tahap 1 | RU6-RCC | 15-P-102A-E1/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2026-05-26 |  | 8202238436 |  | 8202228693#MOC 1982-Pembuatan Gudang Mat | RU6-ITP | SHELTER-PEM3-4/00 | 50 | CLSD NCMP NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 3000000 | 0 | MA4-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102355652 | 8202234719 |  | 8202228691#Pengadaan Material Perbaikan |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | WS-INT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-04-28 | 2026-01-02 | 2026-01-02 | 2102355914 | 8202237630 |  | 8202228688#NRKAP26L_Perbaikan Akses Jala | RU4-TRML | 70AR1/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 100000 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102363506 | 8202234098 |  | 8202228687#12-PCV-653 | RU6-DHC | 12-PCV-653/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-31 | 2102361745 | 8202233289 |  | 8202228684#Perbaikan 32-PDI-027 | RU6-HSC | 32-PDT-027/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363252 | 8202233935 |  | 8202228674#Material Louver Finfan Area 3 | RU6-POC | 36-E-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C3H | 739435 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-18 | 2102362271 | 8202233182 |  | 8202228673#Perbaikan display LCD lokal A | RU6-ITP | 42-T-404A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 8580 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-05-04 | 2026-07-06 | 2102358199 | 8202235067 |  | 8202228672#PERBAIKAN LG D-25-01A/B & C-1 | RU5-E15112 | D-25-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 485360000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-05-04 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356723 | 8202240864 |  | 8202228670#25_[CR] Perbaikan Pompa 11P2C | RU4-FOC1 | 11P2C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 4050500 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102356844 | 8202240861 |  | 8202228669#25_[CR]91E-409B2, Penggantian | RU4-SRU | 91E409B2M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-07-01 | 2102361823 | 8202238434 |  | 8202228665#Refurbishment Control Exciter | RU6-HSC | 32-K-102A/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 1610000 | 0 | MA3-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-05-13 | 2102363509 | 8202233615 |  | 8202228664#Penggantian lampu annuciator | RU6-ITP | 42-ACN-FC-1/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 8316 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-09 | 2026-02-02 | 2026-05-18 | 2102362715 | 8202232168 |  | 8202228663#Vibration Switch Sensor 37-E- | RU6-POC | 37-E-106/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 107000400 | 107000400 | MA3-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-06-22 | 2102354336 | 8202237629 |  | 8202228662#TGH1_SIP_UP Pengecetan MA 1 2 | RU4-FOC1 | LN12-1055LA/00 | 60 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102358886 | 8202235076 |  | 8202228661#Penggantian Lampu Sorot WTP |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 29985753 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-01 | 2102363143 | 8202233663 |  | 8202228660#Penggantian diff pressure 32- | RU6-HSC | 32-PDT-084/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-25 | 2102361892 | 8202232819 |  | 8202228656#Perbaikan Vib Sensor 56-K-101 | RU6-UTL | 056-K-101-A2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 9240 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102363382 | 8202233716 |  | 8202228648#Penggantian 55-PDSH-111B ACF | RU6-UTL | 55-A-101B-S1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12540 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102353828 | 8202240857 |  | 8202228647#25_[CR] Perbaikan FDFan 52B2K | RU4-UTL | 52B2K-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102354094 | 8202241434 |  | 8202228646#25_[CR] Perbaikan pompa 24P13 | RU4-LOC1 | 24P13A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 72590000 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102363413 | 8202234013 |  | 8202228645#Indikasi kerusakan 38-TI-009 | RU6-POC | 38-TT-011/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351829 | 8202232283 |  | 8202228644#Kebutuhan Material 212 Fraksi | RU2-HCC | 0-75FG21122A1A1/00 | 50 | REL MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 3640000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-09 | 2102361436 | 8202234012 |  | 8202228641#Indikasi kerusakan 39-TG-052 | RU6-POC | 39-TT-005C/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 1800000 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102361515 | 8202233484 |  | 8202228638#Penggantian temp. control 058 | RU6-UTL | 058-D-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12540 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102364263 | 8202238433 |  | 8202228633# LTSA Pemeliharaan dan Pengga | RU2-HCC | 0-75CC21132MS11/00 | 50 | CRTD NMAT PRC RELR SETC | 2MR | D12/25/B6/RT-D2H | 500000000 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-26 | 2026-02-03 | 2026-05-26 | 2102358888 | 8202235064 |  | 8202228630#Perbaikan Line Suction G-202- | RU5-D&W | G-202-07B/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 3395953 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-06-04 | 2026-02-03 | 2026-05-11 |  | 8202237890 | 8202233974 | 8202228629#LTSA Pemeliharaan Elevator Ta | RU6-HSC | 32-R-103/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-05-11 |  | 8202237889 | 8202233981 | 8202228628#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | ES-B14-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102359162 | 8202235063 |  | 8202228627#Perbaikan Purifier Plant 3C |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 475000 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356845 | 8202236884 |  | 8202228624#Penggantian dudukan 93K401A | RU4-SRU | 93K401AT/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102363676 | 8202232409 |  | 8202228623#Pengadaan 4 way Solenoid Valv | RU2-HSC | 310-AR-388/00 | 50 | REL GMPS MACM PRC SETC | 2MR | D12/26/B6/NR-D2H | 0 | 750000000 | MA2-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-05 | 2102359052 | 8202235055 |  | 8202228621#Pemasangan Line Aksesoris G-2 | RU5-D&W | G-201-02A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 3424349 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352959 | 8202234523 |  | 8202228620#N_Penggantian Temp Indicat Co | RU3-CDL | 14-TIC-016A/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353157 | 8202234525 |  | 8202228618#N_Penggantian temp gauge stac | RU3-CDL | V-14-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354782 | 8202240854 |  | 8202228617#25_Penggantian gasket 16" #15 | RU4-TRML | SPM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355107 | 8202240851 |  | 8202228612#25_[CR] Perbaikan Turbin 101P | RU4-RFCC | 101P522B-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 2639420 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-07-01 | 2102363311 | 8202238431 |  | 8202228611#Pem. Penyelesaian Kalibrasi C | RU6-RCC | 15-B-101/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238429 | 8202235629 | 8202228610#Tag 1 Hose Handling Area Derm |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 |  | 2026-01-01 | 2026-01-01 | 2102352780 | 8202235629 |  | 8202228609#Pekerjaan Hose Handling Area |  |  | 50 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-01 | PM |  | 045
| K601 | 2026-02-03 | 2026-06-08 | 2026-02-03 | 2026-06-30 |  | 8202237887 | 8202232731 | 8202228606#LTSA PEMELIHARAAN RUTIN MA 2 | RU6-DHC | 12-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 004
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238413 | 8202234972 | 8202228605#Tag 2 Pembersihan Ceceran Min |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238119 | 8202234824 | 8202228604#Tag 21 Cleaning Underground S |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-21 | 2026-05-13 | 2026-05-13 | 2102358889 | 8202235049 |  | 8202228602#Perbaikan Turbin GT-5-16A | RU5-E15111 | GT-5-16A/00 | 60 | TECO CNF CSER PRC SETC | 5RR | D15/25/B6/RT-C2H | 175490922 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-05-21 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238395 | 8202234942 | 8202228600#Tag 15 PM Clean. PreHeater&Re | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238382 |  | 8202228599#Tag 57 Sewa Beli 20 Unit ATG | RU3-ITP | LT-A-003/00 | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238381 |  | 8202228598#Tag 40 TSA 56 ATG Custody Tra | RU3-ITP | LT-TK-207/00 | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356967 | 8202240848 |  | 8202228597#25_[CR] Perbaikan 101P502A | RU4-RFCC | 101P502A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-12-07 | 2026-12-07 | 2102358992 | 8202235052 |  | 8202228594#Penggantian Membrane coupl G | RU5-TBL | G-220-01B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 34397029 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-19 | 2025-12-19 | 2102358956 | 8202235036 |  | 8202228589#POMPA 11 WTP HIGH VIBRATION | RU5-UTL | P-11PAMPANCUR/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 192600 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354784 | 8202236441 |  | 8202228586#D25_240TI060 penunjukan stuck | RU4-LOC3 | TEMP-U240/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354616 | 8202240846 |  | 8202228585#25_240TI208B Penunjukan serin | RU4-LOC3 | 240TT208B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354615 | 8202240844 |  | 8202228584#25_Penunjukan fluktuasi 240FT | RU4-LOC3 | 240FT031/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-24 | 2025-11-24 | 2102356846 | 8202236297 |  | 8202228583#D25_RAM esd foc2 maksimal 99% | RU4-FOC2 | DCS-FOC2/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2025-12-29 | 2025-12-29 | 2102358959 | 8202235038 |  | 8202228582#Pergantian lampu Sorot OC kak | RU5-TBL | PLANT-21-LIS/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 110615950 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356101 | 8202240842 |  | 8202228579#25_[CR] Penggantian Belt Mixe | RU4-UTL | 057P101A/01 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 4950000 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102357000 | 8202240840 |  | 8202228578#25_Penggantian valve manifol | RU4-TRML | 31T1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102356849 | 8202240838 |  | 8202228577#25_Penggantian Valve Bundwall | RU4-TRML | 38T102/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102354498 | 8202240835 |  | 8202228573#25_[CR] 013K101B Low flow | RU4-FOC2 | 013K101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 35506693 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365400 | 8202240833 |  | 8202228571#25_Penggantian LI Sumppit Der | RU4-TRML | LI-U70/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 3 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357006 | 8202240831 |  | 8202228569#25_011FT-041 penunjukan zero | RU4-FOC2 | 011FT041/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-05-04 | 2026-06-22 | 2102359417 | 8202235041 |  | 8202228566#Perbaikan Solenoid Oil Separa | RU5-UTL | AOP-TG2-PP2/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 9 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-05-04 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357001 | 8202240829 |  | 8202228564#25_perbaikan 81LT324 rusak | RU4-KPC | 81LT324/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 9250000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-08-13 | 2026-08-13 | 2102358954 | 8202235044 |  | 8202228563#Penggantian Membrane coupling | RU5-E15111 | G-1-31A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 42397000 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-08-13 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102358031 | 8202234861 |  | 8202228560#Rejuvinate isolasi di Area LO | RU4-LOC1 | LN21-108A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 86195270 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-25 | 2102361617 | 8202233216 |  | 8202228559#Perbaikan bocoran pipa drain | RU6-ITP | 42-T-101A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 9240 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-04 | 2026-03-17 | 2026-03-02 | 2026-03-02 | 2102359070 | 8202238380 |  | 8202228558#K-3-01A Coating Rotor | RU5-E15112 | K-3-01A/00 | 60 | CLSD NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 1 | 0 | WS-ROT |  | ANDREAYR |  | 2026-02-07 | PT02 |  | 3 | 2026-03-17 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-07-17 |  | 8202237886 | 8202233430 | 8202228554#LTSA PMPdM Electr-Instr MA4 T | RU6-ITP | 42-T-101A/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357962 | 8202240827 |  | 8202228553#25_[CR]Crankcase pompa noise | RU4-LOC3 | 260P104B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 29517920 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-02-04 | 2102351706 | 8202238144 |  | 8202228548#Perbaikan Kerusakan 970-PD-30 | RU2-PK | 970-PD-301E/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 914000000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-06-18 | 2026-01-02 | 2026-01-02 | 2102351314 | 8202232438 |  | 8202228538#Gearbox Jammed 212-EG-4 | RU2-HCC | 212-EG-4C/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2RR | D12/26/B6/RT-D2H | 556853500 | 306593750 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-02-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102359051 | 8202235023 |  | 8202228535#Perbaikan Grounding SS 70 | RU5-UTL | 1AL16/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 3092044 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102353541 | 8202240824 |  | 8202228534#25_Perbaikan leak CBD COB 101 | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-05 |  | 2026-02-06 | 2026-02-06 | 2102354923 | 8202238652 |  | 8202228533#RKU 2026 Penggantian Line Avt |  |  | 50 | CRTD NMAT PRC | 4MR | D14/09/B6/RT1-773-S0NH | 25000000 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-01 | 2102361517 | 8202233685 |  | 8202228529#Penggantian Bolt dan Gasket 3 | RU6-HSC | 31-FV-001/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-03 | 2102358996 | 8202235033 |  | 8202228528#FIN FAN EA-1-21 B | RU5-E15111 | EF-1-21B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 3259628 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-03 | 2102358998 | 8202235025 |  | 8202228527#Penggnatian v-belt FIN FAN EA | RU5-E15111 | EF-1-23A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 3259628 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-03 | 2102358997 | 8202235022 |  | 8202228526#Perbaikan in-fan EA-1-21F | RU5-E15111 | EF-1-21F/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 17712576 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-01 | 2102361514 | 8202233534 |  | 8202228523#Penggantian Press Gauge 33-PT | RU6-HSC | 33-C-103/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-18 | 2102359056 | 8202235029 |  | 8202228521#MAT.Perb. PIPA G-34-56 | RU5-D&W | G-34-56/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359549 | 8202235032 |  | 8202228519#MAT. Perb. pipa G-34-25A | RU5-D&W | GM-34-25A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 122562285 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-02-09 | 2102361556 | 8202233055 |  | 8202228518#Perbaikan motor 15E109A | RU6-RCC | 15-E-109A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 384 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-06 | 2102361558 | 8202233084 |  | 8202228517#Perbaikan mixer 42-M-102B | RU6-ITP | 42-M-102B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 152903 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102360968 | 8202236377 |  | 8202228516#Penggantian valve underground | RU4-TRML | 30P108A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-06 | 2026-02-03 | 2026-04-16 | 2102359777 | 8202235010 |  | 8202228513#Perbaikan HIS-0621 Panel Plan | RU5-E15111 | 50R-OP-01/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 6 | 0 | MA2-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355339 | 8202240821 |  | 8202228512#25_56DR302 Perbaikan Check Va | UTL-UP4 | 56K302/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 21912660 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353151 | 8202234537 |  | 8202228511#N_Penggantian Press gauge FDF | RU3-CDL | K-14-001/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353154 | 8202234535 |  | 8202228510#N_Penggantian press gauge suc | RU3-CDL | FC-BM-1E/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202233892 |  | 8202228509#Notifikasi Perbaikan Pompa 42 | RU6-ITP | 42-P-501B/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-19 | 2102361476 | 8202233829 |  | 8202228506#Pengadaan Bola Prover Meterin | RU6-ITP | 42-A-300/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 8580 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-03 |  | 8202236581 | 8202236570 | 8202228505#Tgh ke-3 Kont. RT Vol MA1 | RU6-RCC | 15-R-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-30 | 2102363062 | 8202234085 |  | 8202228504#16-E-120J | RU6-RCC | 16-E-120J-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-08 | 2102362918 | 8202233085 |  | 8202228503#Perbaikan Micrologic Feeder e | RU6-UTL | 01-PSW3-04/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 12936 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355847 | 8202240818 |  | 8202228502#25_Penggantian 51PCV313 | RU4-UTL | 51PCV313/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355103 | 8202240816 |  | 8202228501#25_Perbaikan 540LT101 Level T | RU4-UTL | 540LT111/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354479 | 8202240813 |  | 8202228500#25_[CR] Perbaikan Mixer 32M4 | RU4-TRML | 32M4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102361557 | 8202234056 |  | 8202228499#32-P-103 B | RU6-HSC | 32-P-103B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-15 | 2026-02-03 | 2026-02-03 | 2102359117 | 8202234983 |  | 8202228498#NRK_Pengadaan Pump G-232-02B | RU5-D&W | G-232-02B/00 | 50 | CLSD CSER NCMP PRC | 5RR | D15/26/B6/RT-C2H | 2030808000 | 0 | MA1-ROT |  | YONZHETG |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-12-03 | 2026-12-28 | 2102359058 | 8202235002 |  | 8202228497#Perbaikan POMPA RWP 3 POLISHE |  |  | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 21257360 | 0 | MA1-ROT |  | YONZHETG |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 045
| K601 | 2026-02-05 | 2026-04-15 | 2026-02-05 | 2027-04-30 | 2102362821 | 8202238661 |  | 8202228496#Pengadaan HE 24-E-201 AB CW T | RU6-HSC | 24-E-201A/00 | 01 | CLSD MACM NCMP PRC | 6MR |  | 300000003 | 0 | MA1-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102353317 | 8202240811 |  | 8202228495#25_Valve 6" Bottom Drain 31T1 | RU4-TRML | 31T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2027-04-30 | 2102362820 | 8202238662 |  | 8202228494#Pengadaan spare HE 24-E-102 | RU6-HSC | 24-E-102/00 | 50 | CRTD MACM PRC | 6MR |  | 300000002 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102362822 | 8202233809 |  | 8202228493#Pengadaan HE 24-E-201 AB CW T | RU6-HSC | 24-E-201B/00 | 50 | CRTD CSER MACM PRC | 6MR |  | 2 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102359119 | 8202235015 |  | 8202228492#peng pump vertical ke horizon | RU5-E15112 | G-34-60/00 | 01 | CRTD CSER NMAT PRC | 5RR | D15/10/B6/RT1-08NH | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359239 | 8202235006 |  | 8202228491#Perbaikan Pompa G-3-02C | RU5-E15112 | GM-3-02C/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 179497390 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-06-04 | 2102361554 | 8202237885 |  | 8202228490#LTSA Piping Works Tahap 15 Un | RU6-DHC | 14-V-108/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2027-04-30 | 2102362823 | 8202238663 |  | 8202228489#Pengadaan HE 24-E-101 C/W Tes | RU6-HSC | 24-E-101/00 | 50 | CRTD MACM PRC | 6MR |  | 300000003 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351755 | 8202232301 |  | 8202228488#410 CM-1A Penggantian thermod | RU2-HCC | 410-CM-1A/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-08 | 2026-05-11 | 2026-12-29 | 2026-12-29 | 2102358146 | 8202238742 |  | 8202228487#25_Perbaikan Wdward Protech G | RU4-RFCUTL | 152G501B/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/NR-13-C2H | 15000000 | 1298000000 | MA5-LIS |  | FARIZSETYANA |  | 2026-02-24 | PT02 |  | 3 | 2026-12-29 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366044 | 8202240809 |  | 8202228480#25_Perbaikan SOV dryer 56DR30 |  | 56PCV006/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365383 | 8202240807 |  | 8202228479#25_Penggantian TI tanki area |  | 33LT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 6 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365719 | 8202240805 |  | 8202228477#25_Perbaikan / Penggantian 38 | RU4-TRML | 38FT106/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102364224 | 8202237004 |  | 8202228476#Penggantian 38FIC316 |  |  | 01 | CRTD CSER NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | MA3-INT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-03-26 | 2102361029 | 8202235532 |  | 8202228475#NR_Perbaikan Support Pulley 1 | RU4-RFCC | 104E509C1/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA6-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366046 | 8202240803 |  | 8202228474#25_Penggantian PI Crane Derma | RU4-TRML | 70CIB2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 6 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102361555 | 8202237884 |  | 8202228473#LTSA Piping Tahap 12 Area 24 | RU6-HSC | 24-T-301/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354408 | 8202240801 |  | 8202228469#25_Perbaikan Deviasi Gap 101F | RU4-RFCC | 101FV041A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238568 | 8302405757 | 8202228468#Tag 12 Pekerjaan TSA-PM Flowm | RU3-ITP | 62-FT-0308/00 | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238567 | 8302405757 | 8202228467#Tag 11 Pekerjaan TSA-PM Flowm | RU3-ITP | 62-FT-0308/00 | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354732 | 8202240798 |  | 8202228466#25_Perbaikan PSUMOD PLC 520B4 | RU4-UTL | 520B401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 4 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-08 | 2102361475 | 8202233343 |  | 8202228463#Perbaikan 15-TE-151 | RU6-RCC | 15-B-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102355306 | 8202237628 |  | 8202228462#Rejuvenate kabel motor induks | RU4-FOC2 | 011K101A-P2/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238565 | 8202235215 | 8202228460#Tag 12 Kontrak Volume Mekanik |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-06 | 2026-02-07 | 2026-02-06 | 2026-02-06 | 2102351909 | 8202238691 |  | 8202228459#Pengambilan Material Motor RB | RU2-HOC | 220-PM-2A/00 | 50 | REL MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238554 | 8202235263 | 8202228458#Tag 4 Perbaikan Jalan Kilang |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238544 | 8202235263 | 8202228457#Tag 3 Perbaikan Jalan Kilang |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238534 | 8202235263 | 8202228456#Tag 2 Perbaikan Jalan Kilang |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238228 | 8202235263 | 8202228455#Tag 1 Perbaikan Jalan Kilang |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102352789 | 8202235263 |  | 8202228454#Perbaikan Jalan Kilang Plaju |  |  | 50 | CRTD NMAT PRC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-06-08 | 2102361397 | 8202237883 |  | 8202228453#LTSA Piping Tahap 14 Area EWT | RU6-ITP | 42-PIPE/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352818 | 8202234694 |  | 8202228450#Material Lighting WHRU A & B | RU3-UTL | 2010-UA/00 | 60 WAMA | REL CSER MACM PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352954 | 8202235609 |  | 8202228449#E-63-012A HIGH VIBRATION | RU3-CDL | E-63-012/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-29 | 2025-12-29 | 2025-12-29 | 2102359054 | 8202234976 |  | 8202228447#Perbaikan Motor EM-4-03B | RU5-E15111 | EM-4-03B/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 413997 | 0 | MA2-LIS |  | SAPBATCH | 2026-05-29 | 2026-02-11 | PT02 |  | 3 | 2026-05-29 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-06-08 | 2026-06-29 | 2102359057 | 8202234975 |  | 8202228445#PERBAIKAN WATER METER LINE 2 | RU5-UTL | WTP1-FIR-402/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 505080000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-06-08 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351759 | 8202232592 |  | 8202228444#Penggantian Bearing 300-PM-3B | RU2-HSC | 300-PM-3B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 1896000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-05 | 2102359053 | 8202234979 |  | 8202228442#Perbaikan E-201-20 | RU5-D&W | E-201-20/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 3344366 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351691 | 8202232548 |  | 8202228441#Penggantian Mechanical Seal 1 | RU2-HSC | 100-P-3/00 | 01 | CRTD NMAT PRC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351194 | 8202232456 |  | 8202228440#Perbaikan 520-P-601C | RU2-UTL | 520-P-601C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 589000 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-30 | 2102359116 | 8202234980 |  | 8202228438#Penggantian bearing Pompa G-2 | RU5-D&W | G-201-05B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 41903160 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K401 | 2026-02-04 |  | 2026-02-05 | 2026-02-05 |  | 8202238528 |  | 8202228437#RKAP_26L_Pedestal Crane CIB I | RU4-TRML | 72GW2M/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 99999990 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355420 | 8202240795 |  | 8202228434#25_[CR] Penggantian belt 11E5 | RU4-FOC1 | 11E50K-M/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 2960000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-25 | 2102363201 | 8202234010 |  | 8202228430#Indikasi kerusakan positioner | RU6-POC | 39-V-102/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-05 | 2026-05-25 | 2026-03-31 | 2026-12-31 | 2102351086 | 8202238628 |  | 8202228428#RK0061 LTSA PEMELIHARAAN JUNC | RU2-HSC | HSC-AC-UPS/00 | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 400000000 | 0 | MA2-INT |  | DEDISUKMANA |  | 2026-04-01 | PT02 |  | 3 | 2026-03-31 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354111 | 8202237627 |  | 8202228425#TGH1_24 UP Piping FOC I | RU4-FOC1 | LN10-26LC/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352507 | 8202234227 |  | 8202228424#Pemasangan Pressure Indicator | RU2S-KIL | 900-05P-02A/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-06-10 |  | 8202237626 | 8202237565 | 8202228423#TGH3_SIP_UP Tenaga Kerja MA 3 | RU4-TRML | 033PSV305/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-06-12 | 2026-02-02 | 2026-11-04 | 2102361471 | 8202234110 |  | 8202228421#11-P-102 A | RU6-HSC | 11-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 639314001 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-05 | 2026-05-25 | 2026-01-02 | 2026-10-06 | 2102359110 | 8202238633 |  | 8202228420#Sewa Material Scaffolding u/ |  | 8-BFW52-6-D2/00 | 60 | CLSD NCMP NMAT PRC SETC | 5MR | D16/26/B6/RT-C2H | 1208001 | 0 | MA2-STA |  | BERNANDOP |  |  | PT02 |  | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102356990 | 8202240793 |  | 8202228418#25_Penambahan Valve 4" Stompe | RU4-TRML | 31T7/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 7509550 | 0 | MA3-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356097 | 8202240791 |  | 8202228417#25_Penggantian Check Valve 38 | RU4-TRML | 38P113B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102356096 | 8202240789 |  | 8202228415#25_Penggantian Check Valve 38 | RU4-TRML | 38P113A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102356094 | 8202240787 |  | 8202228414#25_Penggantian Check Valve 38 | RU4-TRML | 38P110B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 2360166 | 0 | MA3-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102356092 | 8202240785 |  | 8202228413#25_Penggantian Check Valve 38 | RU4-TRML | 38P110A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 2360166 | 0 | MA3-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102353315 | 8202240783 |  | 8202228412#25_Penggantian Valve 4" Press | RU4-TRML | 31T1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 7509550 | 0 | MA3-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-18 | 2102361511 | 8202233739 |  | 8202228409#Pengambilan PG unit POC | RU6-POC | 39-K-101/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 29539915 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361352 | 8202236724 |  | 8202228405#SPK LTSA Pengosongan Tangki T | RU6-ITP | 42-T-104A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 31152000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351179 | 8202232481 |  | 8202228403#Perbaikan 211 PM 27 B | RU2-ITP | 211-PM-27B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-12 | 2102361390 | 8202236718 |  | 8202228402#SPK LTSA Refacing tahap 2 11- | RU6-HSC | 11-E-108/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351178 | 8202232482 |  | 8202228401#Perbaikan 211 PM 27 A | RU2-ITP | 211-PM-27A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 2349660 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-12 | 2102361355 | 8202236715 |  | 8202228399#SPK LTSA Refacing Thp 1 20-R- | RU6-RCC | 20-R-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-12-30 | 2102359336 | 8202234964 |  | 8202228394#Perbaikan E-202-06 | RU5-D&W | E-202-06/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 699312665 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-12-30 | 2102359335 | 8202234968 |  | 8202228393#Perbaikan E-202-05 | RU5-D&W | E-202-05/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 23442858 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K201 | 2026-02-01 | 2026-03-12 | 2026-02-02 | 2026-02-02 | 2102351176 | 8202232502 |  | 8202228392#Perbaikan 110 PM 1 A | RU2-ITP | 110-PM-1A/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 3123106 | 0 | MA4-LIS |  | AZIZFATONI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-26 | 2026-01-02 | 2026-12-30 | 2102359334 | 8202234970 |  | 8202228391#Perbaikan E-202-04 | RU5-D&W | E-202-04/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 596589510 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351174 | 8202232509 |  | 8202228390#Perbaikan 100 PM 10 B | RU2-ITP | 100-PM-10B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 4836603 | 4836603 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351173 | 8202232511 |  | 8202228388#Perbaikan 100 PM 10 A | RU2-ITP | 100-PM-10A/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351175 | 8202232508 |  | 8202228387#Perbaikan 100 PM 10 C | RU2-ITP | 100-PM-10C/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102346845 | 8202232201 |  | 8202228384#Perbaikan MOV 560-GT-03 | RU2-UTL | 560-GT-3/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-15 | 2102363415 | 8202233057 |  | 8202228383#Perbaikan motor 15-P-901 B | RU6-RCC | 15-P-901B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354978 | 8202237308 |  | 8202228381#BON PNJM_Perb Level Steamdrum | RU4-RFCUTL | 151LT-U151/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 12718316 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355849 | 8202236455 |  | 8202228380#D25_013F102 : O2 analizer pen | RU4-FOC2 | 013AT004/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102355185 | 8202240782 |  | 8202228379#25_penggantian modul AI PLC B | RU4-SRU | 93F401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2102360182 | 8202234951 |  | 8202228378#Pergantian SWITCH HEATER GM-3 | RU5-UTL | GM-34-130A/00 | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 140556822 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-18 | 2026-09-11 | 2026-09-11 | 2102359118 | 8202234949 |  | 8202228377#POMPA G-4-02 UNIT SPARE POMPA | RU5-E15111 | G-4-02/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354508 | 8202236924 |  | 8202228373#Penggantian bearing motor 90P | RU4-SRU | 90P405BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102352033 | 8202232389 |  | 8202228372#Instrumentasi 211-FR-1500 Rus | RU2-HCC | 211-V-32/00 | 01 | CRTD CSER MACM PRC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102359164 | 8202234953 |  | 8202228369#Penggantian filter K-35-02C | RU5-E15112 | K-35-02C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355931 | 8202236446 |  | 8202228368#D25_018LV036 passing | RU4-FOC2 | 018LV036/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-11-03 | 2102363516 | 8202232999 |  | 8202228366#Perbaikan Pompa 11-P-120B | RU6-HSC | 11-P-120B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 44500000 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-16 | 2025-12-16 | 2102359165 | 8202234956 |  | 8202228365#GANTI VALVE 24IN-150 OUTLET T | RU5-TBL | O-15/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-12-16 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102360989 | 8202234820 |  | 8202228364#RK_26 kerusakan ejector 39T20 | RU4-TRML | 39T206/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355990 | 8202240779 |  | 8202228362#25_[CR] Penggantian LO FIlter | RU4-FOC1 | 12K1C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 13066000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356952 | 8202240777 |  | 8202228361#25_Penggantian Gate Valve 16" | RU4-TRML | 71MOV7311M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351530 | 8202232552 |  | 8202228360#Penggantian Gland Packing 925 | RU2-UTL | 925-P-6A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-18 | 2102359201 | 8202234947 |  | 8202228359#MAT.Perb. Bocoran Steam G-2-0 | RU5-E15112 | G-2-04/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 20074778 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2102359542 | 8202234945 |  | 8202228356#Perbaikan Kabel & Kontrol GM3 | RU5-TBL | GM-34-86B/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 467500000 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355610 | 8202236363 |  | 8202228353#D25_Penggantian Loading Arm C | RU4-TRML | 72X201/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352955 | 8202234543 |  | 8202228352#N_Penggantian Point Type GD C | RU3-CDL | FCC-GDS/00 | 50 WAMA | REL MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353422 | 8202235375 |  | 8202228351#Perbaikan Tubing PSL 33P1B | RU4-TRML | 33P1BM/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356871 | 8202236702 |  | 8202228348#Penggantian LI Tanki 31T1, 31 | RU4-TRML | 31HS001/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355409 | 8202240775 |  | 8202228347#25_Kerusakan pada PCV214 di 3 | RU4-TRML | 39T212/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 92250000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355406 | 8202240773 |  | 8202228346#25_Kerusakan stuck open PCV20 | RU4-TRML | 39T209/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 62750000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354984 | 8202240771 |  | 8202228345#25_Kerusakan pada PCV 216 39T | RU4-TRML | 39T213/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 92250000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353119 | 8202234527 |  | 8202228344#Perbaikan pompa CTU P-53- 101 | RU3-UTL | DWP-53-P-101B/00 | 60 | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102351088 | 8202232626 |  | 8202228343#PENGANTIAN MOTOR 140-PC51-3M1 | RU2-HSC | 300-EM-10A/00 | 50 | REL MACM PRC SETC | 2ER | D12/26/B6/NR-D2H | 0 | 0 | MA2-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2102359775 | 8202234943 |  | 8202228342#Sensor pencahayaan area Bpp-1 | RU5-UTL | UPS1-DISWAX/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 15346500 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-05-20 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354850 | 8202240769 |  | 8202228341#25_Penggantian Sensor MPU 51G | RU4-UTL | 51G3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 35276000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354798 | 8202240766 |  | 8202228340#25_Penggantian Sensot MPU 51G | RU4-UTL | 51G2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 35276000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355500 | 8202240763 |  | 8202228338#25_[CR] Perbaikan Slide Valve | RU4-FOC1 | 11K401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237625 |  | 8202228336#TGH1_SIP_UP Pengecetan Lantai | RU4-LOC2 | 002BD101/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352713 | 8202234420 |  | 8202228335#NR26_Perbaikan EIV D-7 | RU3-CDL | FC-EIV-007/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238221 | 8202235085 | 8202228334#Tag 8 Isolasi Panas Area CD&G |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-22 | 2026-10-23 | 2102362728 | 8202232981 |  | 8202228332#Perbaikan Pompa 17-P-105A | RU6-RCC | 17-P-105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-22 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352006 | 8202232513 |  | 8202228330#perbaikan blower AC Central | RU2-PK | 970-FP-SS1-01/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 103839 | 0 | WS-IN2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-09 | 2026-02-05 | 2026-12-30 | 2102351908 | 8202238502 |  | 8202228328#Penggantian Carbon Aktif 211/ | RU2-HCC | 211-V-103/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 200000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-08 | 2102361394 | 8202233701 |  | 8202228326#Penggantian bearing motor 056 | RU6-UTL | 056-K-101-B2-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 160823 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102366000 | 8202240760 |  | 8202228323#25_Perbaikan flow transmitter | RU4-FOC1 | 11FT005/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 16000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356833 | 8202240757 |  | 8202228321#25_Penggantian LI Tanki 31T10 | RU4-TRML | 31T101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356559 | 8202236384 |  | 8202228320#D25_MOC_Setting 018-TALL 306- | RU4-FOC2 | 018R101/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354350 | 8202240754 |  | 8202228319#25_Press.Gauge Draft indikato | RU4-KPC | 84F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 10 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354278 | 8202240752 |  | 8202228318#25_Perbaikan Level Indikator | RU4-TRML | 37T102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-30 | 2026-02-03 | 2026-12-30 | 2102353296 | 8202234978 |  | 8202228316#TGH2_24 TSA Sparing HB 66 | RU4-TRML | 66HB101/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 44162000 | 37537700 | MA3-INT |  | FATAHALFI |  | 2026-04-17 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-13 | 2102361473 | 8202234019 |  | 8202228315#Hose Stabilizer SPM 165000 | RU6-ITP | 43-SPM-01/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 13200 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-05-20 | 2026-06-23 | 2102359237 | 8202234873 |  | 8202228314#Perbaikan Solenoid Valve 05-X | RU5-E15111 | 05-XCV-020C/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 135000000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356904 | 8202240748 |  | 8202228313#25_011K101A penggantian TI l | RU4-FOC2 | 011K101A/01 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 50 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365972 | 8202240745 |  | 8202228312#25_166AI-557, pH Analizer rus | RU4-RFCUTL | 166T554/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365971 | 8202240742 |  | 8202228311#25_166AI-554, PH Analizer rus | RU4-RFCUTL | 166T554/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365970 | 8202240739 |  | 8202228310#25_166FT003, Display redup | RU4-RFCUTL | 166T501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356218 | 8202240736 |  | 8202228309#25_pengadaan filter Dryer 56K | UTL-UP4 | 56K302/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 80000000 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365969 | 8202240733 |  | 8202228308#25_166T501 tidak ada transmit | RU4-RFCUTL | 166T501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365983 | 8202240730 |  | 8202228307#25_166LT-003B, Display mati | RU4-RFCUTL | 166T501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 14388000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102355936 | 8202240727 |  | 8202228306#25_[CR] Perbaikan mech seal 1 | RU4-FOC1 | 11P6/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 7543650 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359166 | 8202234921 |  | 8202228305#GANTI VALVE 2"-300 PASSING EJ | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 4869671 | 0 | MA4-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363123 | 8202234057 |  | 8202228303#32-K-106 | RU6-HSC | 32-K-106/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-22 | 2025-12-22 | 2102359940 | 8202234859 |  | 8202228302#POMPA G-34-117B MECH SEAL BOC | RU5-D&W | G-34-117B/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 8202234912 | 8202237296 | 8202228301#MAT.MOC(TAMBAH3) NO.11114/RUV | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2181012 | 0 | MA4-STA |  | BERNANDOP |  | 2026-05-20 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-17 | 2026-02-03 | 2102362635 | 8202232870 |  | 8202228300#Perbaikan Switch Vibrasi 16E1 | RU6-RCC | 16-E-117/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 395 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-30 | 2102359161 | 8202234909 |  | 8202228298#Perbaikan STG 1.6 B | UTL-UP5 |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 315233 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102359163 | 8202234880 |  | 8202228297#Perbaikan GM-3-07D | RU5-E15112 | GM-3-07D/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 534345 | 0 | MA3-LIS |  | SAPBATCH | 2026-06-09 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-06 | 2026-03-06 | 2102355030 | 8202240724 |  | 8202228296#25_[CR]mech seal 47P504A boco | LOC1-UP4 | 47P504A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 99623820 | 99623703 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-06-30 |  | 8202236752 | 8202232770 | 8202228295#SPK 22 LTSA Transformator RU | RU6-UTL | SS-01/00 | 50 | CRTD NMAT PRC | 6ER | D16/25/B6/RT-C2H | 146944000 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-06-09 |  | 8202237882 | 8202233431 | 8202228294#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-06-09 |  | 8202237881 | 8202233431 | 8202228293#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359458 | 8202234853 |  | 8202228292#TURBIN GT-2-05B PM | RU5-E15112 | GT-2-05B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 110381462 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-06-11 |  | 8202237880 | 8202233431 | 8202228291#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-06-08 |  | 8202237878 | 8202233431 | 8202228290#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359455 | 8202234856 |  | 8202228288#TURBIN GT-2-01A PM | RU5-E15112 | GT-2-01A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 113678679 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359452 | 8202234866 |  | 8202228287#POMPA G-2-08A PM | RU5-E15112 | G-2-08A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 42188552 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359451 | 8202234868 |  | 8202228286#POMPA G-2-05A PM | RU5-E15112 | G-2-05A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 80962106 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359450 | 8202234923 |  | 8202228285#G-3-08A PM Pit Stop | RU5-E15112 | G-2-03C/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 110381462 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359234 | 8202234881 |  | 8202228284#PERBAIKAN G-5-21B PLANT STOP | RU5-E15111 | G-5-21B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359419 | 8202234870 |  | 8202228283#POMPA G-2-02A PM | RU5-E15112 | G-2-02A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 47016666 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359453 | 8202234864 |  | 8202228282#POMPA G-2-08B PM | RU5-E15112 | G-2-08B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 42188552 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359203 | 8202234900 |  | 8202228281#PERBAIKAN G-4-01A PLANT STOP | RU5-E15111 | G-4-01A/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-04-29 | 2026-04-29 | 2102359454 | 8202234876 |  | 8202228280#Perbaikan Motor GM-4-02 | RU5-E15111 | GM-4-02A/00 | 50 | REL CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-04-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359204 | 8202234899 |  | 8202228279#PERBAIKAN G-4-01B PLANT STOP | RU5-E15111 | G-4-01B/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359456 | 8202234855 |  | 8202228278#TURBIN GT-2-03A PM | RU5-E15112 | GT-2-03A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 113678679 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359205 | 8202234898 |  | 8202228277#PERBAIKAN G-4-04A PLANT STOP | RU5-E15111 | G-4-04A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359206 | 8202234896 |  | 8202228276#PERBAIKAN G-4-04B PLANT STOP | RU5-E15111 | G-4-04B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-03 | 2026-01-02 | 2026-01-02 | 2102359207 | 8202234893 |  | 8202228275#PERBAIKAN G-5-01A PLANT STOP | RU5-E15111 | G-5-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359208 | 8202234890 |  | 8202228274#PERBAIKAN G-5-01B PLANT STOP | RU5-E15111 | G-5-01B/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-01-02 | 2026-01-02 | 2102359413 | 8202234913 |  | 8202228273#KT-8-02B PM Pit Stop 2026 | RU5-E15112 | KT-8-02B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359230 | 8202234888 |  | 8202228272#PERBAIKAN G-5-12B PLANT STOP | RU5-E15111 | G-5-12B/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359412 | 8202234915 |  | 8202228271#GT-8-05D PM Pit Stop 2026 | RU5-E15112 | GT-8-05D/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 47016666 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359411 | 8202234918 |  | 8202228270#GT-8-04D PM Pit Stop 2026 | RU5-E15112 | GT-8-04D/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359231 | 8202234887 |  | 8202228269#PERBAIKAN G-5-15A PLANT STOP | RU5-E15111 | G-5-15A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359232 | 8202234885 |  | 8202228268#PERBAIKAN G-5-15B PLANT STOP | RU5-E15111 | G-5-15B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359410 | 8202234919 |  | 8202228267#GT-8-01D PM Pit Stop 2025 | RU5-E15112 | GT-8-01D/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 90753158 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359233 | 8202234883 |  | 8202228266#PERBAIKAN G-5-21A PLANT STOP | RU5-E15111 | G-5-21A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-02-08 | 2026-03-04 | 2026-01-02 | 2026-12-30 | 2102356330 | 8202238741 |  | 8202228265#25_[CR] Blower 84K254 | RU4-KPC | 84K254/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 294000000 | 294000000 | MA4-ROT |  | SAMSUDINH |  | 2026-03-04 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102361432 | 8202237876 |  | 8202228264#Pengadaan desuperheater Boile | RU6-UTL | 52-B-101B/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 300000001 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352060 | 8202232372 |  | 8202228263#Perbaikan Control Valve 140 T | RU2-HOC | 140-TV-465/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-18 | 2102359169 | 8202234823 |  | 8202228262#MAT.Perb.Line Outlet E-35-03B | RU5-E15112 | E-35-03B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 493837 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238501 | 8302403326 | 8202228260#Tag 10 Sewa Beli Wheel Loader | RU3-WS | BEN-TOOL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238500 | 8202234908 | 8202228259#Tag 26 Pemeliharaan Sepeda Ki | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359457 | 8202234839 |  | 8202228257#GT-2-03B | RU5-E15112 | GT-2-03B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 113678679 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-01-02 | 2026-01-02 | 2102359398 | 8202234831 |  | 8202228256#GT-3-30A PM Pit Stop | RU5-E15112 | GT-3-30A/01 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 51121296 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-10 | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-01-02 | 2026-01-02 | 2102359397 | 8202234834 |  | 8202228255#GT-3-24B :PM Pit Stop | RU5-E15112 | GT-3-24B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 45936780 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-10 | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238499 | 8202234972 | 8202228254#Tag 3 Pembersihan Ceceran Min |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-04 | 2026-08-06 | 2026-08-06 | 2102359396 | 8202234840 |  | 8202228253#G-8-01C PM Pit Stop 2026 | RU5-E15112 | G-8-01C/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 96488798 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238491 | 8202234925 | 8202228252#Tag 2 Pemeliharaan RPA 1-5 & |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359395 | 8202234843 |  | 8202228251#G-3-37B PM Pit Stop | RU5-E15112 | G-3-37B/01 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 30000000 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356873 | 8202240721 |  | 8202228250#25_84PIC390 Setting Auto Hunt | RU4-KPC | 84PIC390/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 36166669 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-01-02 | 2026-01-02 | 2102359399 | 8202234828 |  | 8202228249#GT-3-37A PM Pit Stop | RU5-E15112 | GT-3-37A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 51121296 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-10 | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359394 | 8202234845 |  | 8202228247#G-3-30B PM Pit Stop | RU5-E15112 | G-3-30B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 51121296 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359392 | 8202234847 |  | 8202228245#G-3-09A PM Pit Stop | RU5-E15112 | G-3-09A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 86469809 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102358165 | 8202240718 |  | 8202228244#25_RKAP 2026 - Retrofit Relay | RU4-FOC2 | 011P102AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359391 | 8202234836 |  | 8202228243#GT-3-08B PM Pit Stop | RU5-E15112 | G-3-08B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 30466666 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359390 | 8202234849 |  | 8202228242#G-3-08A PM Pit Stop | RU5-E15112 | G-3-08A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 30466666 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359339 | 8202234837 |  | 8202228241#GT-3-05B :PM Pit Stop | RU5-E15112 | GT-3-05B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 45936780 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359338 | 8202234850 |  | 8202228240#G-3-02A :PM Pit Stop | RU5-E15112 | G-3-02A/01 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359337 | 8202234851 |  | 8202228238#G-3-01A PM Pit Stop | RU5-E15112 | G-3-01A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 108873065 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356219 | 8202236435 |  | 8202228237#D25_84BV74 Indikasi Passing | RU4-KPC | 84BV74/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102359393 | 8202234846 |  | 8202228234#G-3-24A PM Pit Stop | RU5-E15112 | G-3-24A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 51121296 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-03-04 | 2102359168 | 8202234825 |  | 8202228232#MAT.Perb.E-3-33A | RU5-E15112 | E-3-33A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 283316510 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359238 | 8202234814 |  | 8202228231#Perbaikan Pompa G-34-56 | RU5-D&W | G-34-56/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 10011869 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-18 | 2102359332 | 8202234821 |  | 8202228230#MAT.Perb.pipa Outlet C-8-17B | RU5-E15112 | C-8-17B/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 | 2102359202 | 8202234817 |  | 8202228229#Perbaikan Pompa G-3-19C | RU5-E15112 | G-3-19C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1661112 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102363711 | 8202232489 |  | 8202228228#Oil Purifier Alvalaval Damage | RU2-HSC | 301-C-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-24 | 2025-12-08 | 2026-12-29 | 2102357172 | 8202237624 |  | 8202228226#penambahan jembatan penghubun | RU4-TRML | 66HB101/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 320000000 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353933 | 8202235432 |  | 8202228222#Perbaikan Tanki 43T101 | RU4-TRML | 43T101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351139 | 8202232579 |  | 8202228220#Perbaikan temp 610 TK-205 | RU2-ITP | 610-BV-205A/00 | 01 | CRTD CSER MACM PRC | 2MR | D12/XX/B6/RT-D2NH | 0 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237623 |  | 8202228219#TGH10_24 Jasa Kontrak Peforma | RU4-LOC1 | 23P4/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 33056500 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102353152 | 8202234426 |  | 8202228218#NR26_Penggantian TSHH WHRU 20 | RU3-UTL | TT-20237B/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237622 |  | 8202228216#TGH2_24 PM Field Instr ME II | RU4-RFCGTO | 105FT072/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-18 | 2102359333 | 8202234812 |  | 8202228215#PERBAIKAN SENSOR NH3 ANALYZER | RU5-D&W | D-34-08-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 15000001 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102354543 | 8202238029 |  | 8202228214#TGH1_CIV_CLEANING SULFUR PIT | RU4-SRU | 93A404/00 | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 7870580 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352609 | 8202234226 |  | 8202228213#Kerusakan lampu penerangan ar | RU2S-KIL | 946-JT-2-PLTFM/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-16 | 2026-01-02 | 2026-01-02 | 2102352265 | 8202234225 |  | 8202228211#900-06GE-6/00 | RU2S-KIL | 900-06GE-6/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 0 | 913760 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352275 | 8202234223 |  | 8202228210#Motor compressor 900-02AC-1A | RU2S-KIL | 900-02AC-1A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352513 | 8202234222 |  | 8202228209#Perbaikan Motor Pompa 900-03P | RU2S-KIL | 900-03P-2B-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352550 | 8202234221 |  | 8202228208#NOISE PADA 101-E6A | RU2S-KIL | 101-E-6A-M/00 | 50 | REL NMAT PRC SETC | 2ES | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-03-25 | 2102359209 | 8202234804 |  | 8202228207#PERBAIKAN PRESS INDICATOR 40- | RU5-E15111 | G-5-02A/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 29175000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-10 | 2102359772 | 8202234803 |  | 8202228206#Perbaikan Transmitter 08A-PT- | RU5-E15112 | 08A-PT-156/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 20 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102359835 | 8202234808 |  | 8202228205#Penarikan Control ke DCS K-3- | RU5-E15112 | K-3-02C-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 486500000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-03 | 2026-06-12 | 2026-02-03 | 2026-12-30 | 2102356941 | 8202237621 |  | 8202228204#TGH1_SIP_UP Fire Proofing ME | RU4-UTL | 54TF4/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TONNYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-06 | 2026-02-11 | 2026-02-06 | 2026-02-06 | 2102351326 | 8202238681 |  | 8202228203# TECHNICAL SERVICE AGREEMENT | RU2-HCC | 211-P-9A/00 | 50 | CRTD NMAT PRC RELR SETC | 2RR | D12/25/B6/RT-D2H | 1450000000 | 0 | MA2-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-26 | 2102362634 | 8202232738 |  | 8202228202#Spare part PM 10 tahun 23A-UP | RU6-ITP | 23-PBC3-01A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 17292 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352860 | 8202234434 |  | 8202228201#NR26_Penggantian Module DI GT | RU3-UTL | 2015-UBG/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-04-03 | 2026-02-02 | 2026-02-02 | 2102358404 | 8202234601 |  | 8202228200#Perbaikan 2-F-01/00 | RU7-NHT | 2-F-01/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D1H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-03 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102353914 | 8202240715 |  | 8202228199#25_[CR] 011E124K01 Fin fan go | RU4-FOC2 | 011E124K01/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 21431969 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-05-25 |  | 8202238481 | 8202235565 | 8202228198#Tag. 16 Operator & Pem. Alat | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-25 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-13 | 2025-12-16 | 2025-12-16 | 2102353156 | 8202234516 |  | 8202228197#N_Penggantian Turbidity Meter | RU3-UTL | PDT-22662/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-06-29 | 2102361359 | 8202233908 |  | 8202228196#Mechanical Cleaning 24-E-203 | RU6-HSC | 24-E-203/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 739435 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102366007 | 8202240711 |  | 8202228189#25_pengadaaan flexible hose b | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353798 | 8202234775 |  | 8202228184#Pengadaan Gasket Channel Surf | RU4-UTL | 051G101/00 | 50 WENG | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 |  | 2025-12-30 | 2025-12-30 | 2102351094 | 8202232570 |  | 8202228183#Perbaikan Turbin 211-PT-86 | RU2-HCC | 211-PT-86/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356599 | 8202236819 |  | 8202228179#penggantian globe valve 1inch | RU4-UTL | 052B101/00 | 50 WENG | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-05-19 | 2026-02-02 | 2026-02-02 | 2102351690 | 8202232685 |  | 8202228176#Unloader Problem | RU2-HSC | 300-C-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 352175668 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-04-13 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-12-30 | 2026-12-30 | 2102359330 | 8202234805 |  | 8202228173#Perbaikan GM-3-19B | RU5-E15112 | GM-3-19A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 152206 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 005
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238479 | 8302405059 | 8202228171#Tag 35 LTSA 21 Unit ATG Custo | RU3-ITP | 039-P-007/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238478 | 8202235233 | 8202228170#Tag 10 TKDN Kontrak Volume Me |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238453 | 8202234832 | 8202228169#Tag 20 Sarana Tambat Kapal Su |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355632 | 8202240707 |  | 8202228168#25_pelumas new kompresor di 8 | RU4-KPC | 81A201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238159 | 8202234391 | 8202228167#Tag 1 TSA O2 Analyzer CDGP | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2102352876 | 8202234391 |  | 8202228166#TSA O2 Analyzer CDGP | RU3-CDGP |  | 50 | CRTD NMAT PRC | 3IR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-06-09 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356760 | 8202236402 |  | 8202228165#D25_Control Valve Passing 140 | RU4-GTO | 140KV021A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102354854 | 8202236434 |  | 8202228164#Penggantian Tranducer Control | RU4-UTL | 52B201/00 | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-INT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357580 | 8202236447 |  | 8202228161#D25_014PV10A passing | RU4-FOC2 | 014PV010A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355794 | 8202236322 |  | 8202228158#Penyehatan MCC-MCC Spare LV 3 | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-29 | 2026-05-13 | 2026-05-13 |  | 8202234794 | 8202238855 | 8202228156#MATERIAL PIPING PLANT HVU2&HP | RU5-E15112 | 8-ACW64-2-A4/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 221917055 | 0 | MA3-STA |  | BERNANDOP |  | 2026-05-29 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2025-12-15 | 2026-05-06 | 2102358925 | 8202234801 |  | 8202228155#Ganti Unit CV 201-FCV-004 & 2 | RU5-D&W | 201-FCV-004/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 162120576 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-15 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-08 | 2026-05-13 | 2026-05-13 |  | 8202234798 | 8202237296 | 8202228154#MAT.MOC(TAMBAH2) NO.11114/RUV | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2181012 | 0 | MA4-STA |  | BERNANDOP |  | 2026-06-08 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-18 | 2102359502 | 8202234796 |  | 8202228149#MAT.Perb. VALVE DRAIN SUCTION | RU5-E15112 | 19-ACW-501-3-A4/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 4939198 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2025-11-21 | 2026-07-16 | 2102362193 | 8202238420 |  | 8202228148#Perbaikan Pompa 42-P-503B | RU6-ITP | 42-P-503B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/NR-C2H | 348320575 | 0 | MA4-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-11-21 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-01-12 | 2026-04-16 | 2102358927 | 8202234799 |  | 8202228146#Ganti Unit CV 201-PCV-071 & 2 | RU5-D&W | 201-PCV-071/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 162120000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-12 | PM |  | 004
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238419 | 8202235501 | 8202228145#Tag 1 Pengerukan Lumpur Area | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-18 | 2026-01-02 | 2026-01-02 | 2102352877 | 8202235501 |  | 8202228144#Pekerjaan Pengerukan Lumpur A | RU3-CDGP |  | 50 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-13 | 2102359316 | 8202234791 |  | 8202228143#Penggantian Valve Air Cooler | RU5-UTL | TG-5A-PP1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353832 | 8202240704 |  | 8202228139#25_Pengadaan Material UPS dan | RU4-UTL | 05CSL1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357198 | 8202237620 |  | 8202228138#TGH5_24 TSA LIGHTNING PROT SY | RU4-TRML | 30EE101A-50GS/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102357401 | 8202240509 |  | 8202228135#25_[CR] 91K-401AEM – Suara ka | RU4-SRU | 91K401AEM/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 126200 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354161 | 8202240506 |  | 8202228134#25_Penggantian Sensor MPU 51G | RU4-UTL | 51G3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102354058 | 8202240503 |  | 8202228133#25_Penggantian Sensor MPU 51G | RU4-UTL | 51G2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355527 | 8202236426 |  | 8202228129#D25_88TI289 Penunjukan NAN | RU4-KPC | TEMP-U88/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355771 | 8202240499 |  | 8202228121#25_Mtl. Valve Suction 47P-504 | LOC1-UP4 | 47P504A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356794 | 8202240495 |  | 8202228116#25_Mtl. Perbaikan Damper 12 F | RU4-FOC1 | 12F1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 29960298 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354465 | 8202236379 |  | 8202228113#Penggantian valve middle filt | RU4-LOC1 | 24S1A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356035 | 8202237326 |  | 8202228112#94F-403, perbaikan bordes | RU4-SRU | 94F403/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357072 | 8202236929 |  | 8202228111#Penggantian Bank Finfan 11E-5 | RU4-FOC1 | 11E50GH/00 | 01 | CRTD NMAT PRC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353621 | 8202235047 |  | 8202228108#Pembuatan tangga & boarddesk | RU4-LOC1 | 21F1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353624 | 8202236482 |  | 8202228107#Penggantian spuyer pilot gun | RU4-LOC1 | 25F1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353623 | 8202236796 |  | 8202228106#Penggantian kaca peephole 25F | RU4-LOC1 | 25F1/00 | 50 WAMA | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-18 | 2025-12-30 | 2025-12-30 | 2102359540 | 8202234779 |  | 8202228104#Perbaikan Motor Gm-34-117A | RU5-D&W | GM-34-117A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 105749 | 0 | MA2-LIS |  | SAPBATCH | 2026-05-18 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102359600 | 8202234776 |  | 8202228103#Perbaikan Motor Pompa 18 | RU5-D&W | P-18-DW/00 | 60 | REL NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 11 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359501 | 8202234767 |  | 8202228102#PM K-5-22 PLANT STOP JANUARI | RU5-E15111 | K-5-22/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 21384972 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-12 | 2026-01-02 | 2026-01-02 | 2102359500 | 8202234770 |  | 8202228101#PM K-5-21 PLANT STOP JANUARI | RU5-E15111 | K-5-21/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-04-13 | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359459 | 8202234774 |  | 8202228100#PM K-5-01 PLANT STOP JANUARI | RU5-E15111 | K-5-01/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 357743400 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354695 | 8202240491 |  | 8202228097#25_[CR] 011E116K02 GANTI BELT | RU4-FOC2 | 011E116K02/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-03-11 | 2025-12-05 | 2026-09-11 |  | 8202233845 |  | 8202228095#Penambahan Material pada Supe | RU6-UTL | 056-K-101-A1/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 1902854 | 0 | MA4-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-09 | 2026-02-02 | 2026-06-25 | 2102361395 | 8202233895 |  | 8202228094#Notifikasi Perbaikan 42-PSV-1 | RU6-ITP | 42-PSV-152/00 | 60 | REL CSER GMPS MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 11616 | 17069932 | MA4-STA |  | BELLAKF |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102363385 | 8202232940 |  | 8202228093#Perbaikan Pompa 63-P-201A | RU6-ITP | 63-P-201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102361392 | 8202233083 |  | 8202228092#Perbaikan Mixer 63-M-301 | RU6-ITP | 63-M-301/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102361356 | 8202233082 |  | 8202228091#Perbaikan Mixer 63-M-403 | RU6-ITP | 63-M-403/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-09 | 2026-02-04 | 2026-02-04 | 2102363810 | 8202238116 |  | 8202228089#Perbaikan Settlement Area HCC | RU2-HCC | 6P21165A2A2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-12 | 2102363384 | 8202233413 |  | 8202228088#Perbaikan 11-XV-032 | RU6-HSC | 11-F-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-12-30 | 2102359415 | 8202234783 |  | 8202228087#Penggantian D-34-15B | RU5-D&W | Y-34-11B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 6575825 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-05 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-12-30 | 2102359418 | 8202234784 |  | 8202228086#Penggantian D-34-15A | RU5-D&W | D-34-15A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/NR-C2H | 6575825 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-05 | PM |  | 004
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-06-15 |  | 8202236751 | 8202232770 | 8202228085#SPK 22 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-08 | 2026-02-03 | 2026-06-15 |  | 8202237874 | 8202232731 | 8202228084#LTSA PEMELIHARAAN RUTIN MA 2 | RU6-DHC | 12-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-06-23 | 2102364389 | 8202238626 |  | 8202228083#TGH10_24 Monitoring Peralatan | RU4-RFCUTL | 151FT-U151/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 123686120 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352002 | 8202232642 |  | 8202228078#Pengambailan Material Tanki I | RU2-HSC | 0-75P20064A1A1/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-01 | 2026-02-01 | 2102352001 | 8202232639 |  | 8202228077#Pengambilan gasket 3" #150 | RU2-ITP | 509-M0V-1100D/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-06-12 |  | 8202236625 | 8202233857 | 8202228076#SWO Pemb. LTSA O2 Ametek Term | RU6-RCC | 15-AT-002/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-29 | 2026-06-29 | 2026-06-29 | 2102359506 | 8202234785 |  | 8202228070#Mechseal Pompa G-20-08A Leaki | RU5-TBL | G-20-08A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 11236441 | 0 | MA4-ROT |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359839 | 8202234787 |  | 8202228069#GANTI VALVE DRAIN 4" TANK A-2 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 16340293 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-05-06 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-10-13 | 2026-10-13 | 2102360090 | 8202234762 |  | 8202228068#SIGHT GLASS POMPA G-5-16 B PE | RU5-E15111 | G-5-16B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1910167 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-10-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359509 | 8202234765 |  | 8202228066#POMPA G-5-02A (GAKSET CASING) | RU5-E15111 | G-5-02A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-10 | 2026-12-15 | 2026-12-15 | 2102360051 | 8202234764 |  | 8202228065#POMPA G-5-08A VIBRASI TINGGI | RU5-E15111 | G-5-08A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352034 | 8202232473 |  | 8202228064#Perbaikan 220 EM-7B | RU2-HOC | 220-EM-7B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 2942440 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351487 | 8202232250 |  | 8202228063#Kerusakan motor 110 EM-9H | RU2-HOC | 110-EM-9H/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 2382345 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351198 | 8202232715 |  | 8202228061#Service Motor 140 EM-23B | RU2-HOC | 140-EM-23B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 3084874 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351412 | 8202232488 |  | 8202228060#Perbaikan 140 PM-16B | RU2-HOC | 140-PM-16B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 3110000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351136 | 8202232266 |  | 8202228059#Pengadaan Lampu Area HOC | RU2-HOC | 140-PX-52/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363388 | 8202232167 |  | 8202228057#WO Matl bocoran gasket 37-R-1 | RU6-POC | 37-R-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238390 | 8202234668 | 8202228056#Tag 6 TKDN Perbaikan Bocoran | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358408 | 8202234600 |  | 8202228054#Pemasangan 2-FV-101 | RU7-NHT | 2-FV-101/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/NR-1-D2H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355061 | 8202237619 |  | 8202228053#TGH1_25 UP MON&INSP PERALATN | RU4-RFCGTO | 107P501A-MCC/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-08-13 | 2102361353 | 8202238440 |  | 8202228052#Perbaikan Blower 15-K-104 | RU6-RCC | 15-K-104/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 330000000 | 280500000 | MA1-ROT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 004
| K401 | 2026-02-08 | 2026-02-27 | 2026-02-09 | 2026-02-09 | 2102353897 | 8202238740 |  | 8202228051#25_Kerusakan Pada Server DCS | RU4-FOC2 | 80OS101/00 | 50 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-02-12 | PT02 |  | 3 | 2026-02-09 | PM |  | 003
| K202 | 2026-02-04 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352504 | 8202238078 |  | 8202228050#PSA ATG di RU II Production S | RU2S-KIL | 946-TK-13-LT/00 | 50 | REL NMAT PRC SETC | 2ES | D12/26/B6/NRZ-C1H | 1 | 0 | MAS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-12 | 2026-01-02 | 2026-01-02 | 2102356017 | 8202234768 |  | 8202228049#Pengadaan Instr Line Recycle | RU4-TRML | 43P1AM-CB/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 126641602 | 122575000 | MA2-INT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-19 | 2102363414 | 8202236743 |  | 8202228047#SPK 3 LTSA Cathodic Protectio | RU6-UTL | 50-REC-01/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238438 | 8202235145 | 8202228045#Tag 15 PM/PDM Cleaning Cooler | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238411 | 8302403326 | 8202228044#Tag 9 Sewa Beli Wheel Loader | RU3-WS | BEN-TOOL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-06-23 |  | 8202237618 | 8202238635 | 8202228041#TGH23_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 211663000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102363068 | 8202233063 |  | 8202228038#Perbaikan motor 14-P-101 | RU6-DHC | 14-P-101B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-03-17 | 2102363315 | 8202233782 |  | 8202228037#Pengadaan material spare RGA | RU6-ITP | 42-T-107A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1560 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-06-15 |  | 8202236748 | 8202232770 | 8202228032#SPK 25 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102354852 | 8202240487 |  | 8202228029#25_Penggantian Baterai 51G4 | RU4-UTL | 51G4/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 15500000 | 0 | MA5-LIS |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365569 | 8202240483 |  | 8202228028#25_RKAP 2025_Penyehatan Aerat | LOC1-UP4 | 47S505-M3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365568 | 8202240479 |  | 8202228027#25_RKAP 2025_Penyehatan Aerat | LOC1-UP4 | 47S505-M2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353708 | 8202240476 |  | 8202228025#25_Membran Coupling Pompa Pec | RU4-GTO | 120P601B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354210 | 8202240472 |  | 8202228019#25_[CR] 011K101CP2 Coupling d | RU4-FOC2 | 011K101C-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102356948 | 8202240468 |  | 8202228018#25_[CR] Hub Coupling Scroll 0 | RU4-LOC2 | 024S101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-02 | 2026-05-07 | 2026-02-02 | 2026-02-02 | 2102358440 | 8202234599 |  | 8202228016#Timming belt 2 - EAM - 02 A | RU7-NHT | 2-EA-02/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH | 2026-03-08 | 2026-02-07 | PT02 |  | 3 | 2026-03-08 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-02 | 2026-04-09 | 2102359838 | 8202234750 |  | 8202228013#Perbaikan Solenoid FSS SS 63 | RU5-TBL | OFC-CRB-FIRE/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 6 | 0 | HSSE |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237617 |  | 8202228012#TGH6_24 TSA DCS Honeywell RFC | RU4-RFCC | 101FJB001/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-23 | 2025-12-29 | 2102359718 | 8202234753 |  | 8202228011#Perbaikan Motor EM-32-01G | RU5-E15112 | EA-32-01O/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 7529319 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102359496 | 8202234759 |  | 8202228010#Fabrikasi Intermediate Shaft | RU5-E15112 | KK-3-02A/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359541 | 8202234755 |  | 8202228009#Perbaikan Lampu Penerangan Ka | RU5-TBL | DER-JT-04/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 6463120 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 | 2102359548 | 8202234758 |  | 8202228008#Perbaikan Finfan Ea-17-03B | RU5-E15112 | EA-17-03B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 10007404 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2025-12-29 | 2025-12-29 | 2102359543 | 8202234752 |  | 8202228007#Perbaikan Motor Gm-8-03B | RU5-E15112 | GM-8-03B/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 152214 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-03-25 | 2102359895 | 8202234751 |  | 8202228006#Perbaikan Oksigen Analizer 05 | RU5-E15111 | 05-AIT-017/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 70884000 | 0 | WS-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-12-19 | 2025-12-29 | 2102360220 | 8202234748 |  | 8202228005#FABRIKASI STRAINER POMPA P-4 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | TECO CNF MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 16852397 | 0 | MA4-STA |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202236793 | 8202234902 | 8202228003#Tagihan Ke- 8 Termin TKDN Pek |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2025-12-31 | 2025-12-31 | 2102352794 | 8202235716 |  | 8202228002# Pengadaan Tools REIE 2025 |  |  | 50 WAMA | REL MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363318 | 8202233659 |  | 8202228001#Penggantian FH dan Aksesoris | RU6-ITP | 43-SPM-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102363411 | 8202233962 |  | 8202228000#Make Up Rocksalt 14-V-108 | RU6-DHC | 14-V-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 369717 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353788 | 8202240465 |  | 8202227999#25_PM Penggantian Filter 109M | RU4-RFCGTO | 109PSV942A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 2365200 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-09 | 2026-04-15 | 2026-03-09 | 2026-03-09 | 2102357724 | 8202241433 |  | 8202227997#[TGH] Refurbishment MechSeal | RU4-RFCC | 101P523A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-15-C2H | 118084000 | 0 | WS-PMP |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238408 | 8202234902 | 8202227996#Tag 7 Sipil Area Kilang SG |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102356689 | 8202240460 |  | 8202227995#25_[PV] 054WS102P3 Perbaikan | RU4-UTL | 054WS102P3/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 15100300 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359832 | 8202234747 |  | 8202227988#MAT.PERB. Line Gas Flare 08-P | RU5-E15112 | 08-PCV-039/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 6598533 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238392 | 8202235151 | 8202227987#Tag 15 Cleaning&Ganti Catalys | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359545 | 8202234742 |  | 8202227986#MAT.PERB.CHECK VALVE DISCHARG | RU5-E15112 | 19-ACW-501-3-A4/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 7338572 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238021 | 8202235140 | 8202227985#Tag 1 Pekerjaan Mekanik Area | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-18 | 2026-01-02 | 2026-01-05 | 2102352957 | 8202235140 |  | 8202227984#Pekerjaan Mekanik Area CDGP | RU3-CDGP |  | 60 | REL CNF PRT GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI | 2026-01-05 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359497 | 8202234745 |  | 8202227983#MAT.Perb. pipa header MS Jl.1 | RU5-D&W | 201-LLS002-2-B2/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 11592519 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-06 | 2026-02-03 | 2026-12-31 | 2102359608 | 8202234720 |  | 8202227982#Penggantian Valve Bypass 201- | RU5-D&W | 201-FCV-042/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/26/B6/NR-C2H | 236153 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355825 | 8202236401 |  | 8202227981#Penggantian Valve 6" dan 4" L |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102358908 | 8202234746 |  | 8202227977#MAT.Perb. Line Pipa 05-H27 | RU5-E15111 | 5-H27-6-C4/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 12148245 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-07-27 | 2102359546 | 8202234713 |  | 8202227975#Perbaikan System Control GCU |  | E-3-60A/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 8600022 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-08-26 | 2026-08-26 | 2102359719 | 8202234699 |  | 8202227970#Pompa Injeksi ASA Flow Tidak |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2026-08-26 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102360763 | 8202234740 |  | 8202227969#Penggantian relay proteksi&co |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 7 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-22 | 2102359601 | 8202234717 |  | 8202227968#PenggantianMCCB Panel Lampu O | RU5-TBL | PLANT-22-LIS/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 5 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102360356 | 8202234743 |  | 8202227966#MAT.Perb. Valve P-1AB | RU5-D&W | P1-B-CPI/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 22020447 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102359837 | 8202234716 |  | 8202227965#Perbaikan FAS New Laboratoriu | RU5-E15500 | LAB-DSH-004/00 | 50 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 125200000 | 0 | HSSE |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-29 | 2026-08-26 | 2026-09-24 | 2102359712 | 8202234702 |  | 8202227964#Pompa G-201-11B (Chem. Buffer | RU5-D&W | G-201-11B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 71541500 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-08-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-29 | 2026-10-29 | 2026-11-16 | 2102359711 | 8202234706 |  | 8202227963#Pompa G-201-11A (Chem. Buffer | RU5-D&W | G-201-11A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 71541500 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-29 | 2026-10-29 | 2102359710 | 8202234709 |  | 8202227962#Pompa G-201-10B (Chem. Buffer | RU5-D&W | G-201-10B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 16490460 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-29 | 2026-10-29 | 2026-11-19 | 2102359609 | 8202234712 |  | 8202227961#Pompa G-201-10A (Chem. Buffer | RU5-D&W | G-201-10A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 16490460 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359786 | 8202234670 |  | 8202227959#MAT.Perb.B.V ACW K-3-02A | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 53550000 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359729 | 8202234662 |  | 8202227958#MAT.Perb.B.V ACW K-3-02C | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 53550000 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-18 | 2026-06-18 | 2026-07-20 | 2102359728 | 8202234665 |  | 8202227957#MAT.Perb.B.V ACW K-3-02B | RU5-E15112 | K-3-02B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 36137310 | 0 | MA3-STA |  | HIMMATUSS |  | 2026-06-18 | PT02 |  | 3 | 2026-06-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359498 | 8202234674 |  | 8202227956#MAT.Perb. pipa TC-731 | RU5-E15112 | F-3-03B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 21342365 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-06 | 2102359135 | 8202234681 |  | 8202227955#Ea-3-09AA: Plug Bocor 1 pcs | RU5-E15112 | EA-3-09-AA/00 | 50 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-03-06 | 2102360357 | 8202234677 |  | 8202227954#MAT.Perb. PIPA 3B-F01-C3 | RU5-E15112 | F-3-03B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 1886310 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102360187 | 8202234672 |  | 8202227953#MAT.Perb. VALVE SUCTION G-8-0 | RU5-E15112 | GT-8-05B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 260121193 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-18 | 2026-06-18 | 2026-07-20 | 2102360089 | 8202234679 |  | 8202227952#MAT.Perb. check valve G-3-26A | RU5-E15112 | G-3-26A/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 41374194 | 0 | MA3-STA |  | HIMMATUSS |  |  | PT02 |  | 2 | 2026-06-18 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358421 | 8202234598 |  | 8202227950#Penggantian 1-LV-118 | RU7-CDU | 1-LV-118/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351099 | 8202232312 |  | 8202227944#Control 211-1672 A/B Rusak | RU2-HCC | 211-V-101/00 | 50 | CRTD MACM PRC | 2IR | D12/10/B6/RT1-211NH | 367000000 | 0 | MA2-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 | 2102359049 | 8202234633 |  | 8202227941#Perbaikan & Fabrikasi Part Po | RU5-E15112 | G-2-07A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 29098785 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-25 | 2026-02-03 | 2026-12-31 | 2102359603 | 8202234635 |  | 8202227940#Penggantian Valve Outfall P07 | RU5-UTL | P-7-RPALUTARA/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/NR-C2H | 12215630 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 | 3 | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-06-26 |  | 8202237616 |  | 8202227938#TGH3_24 UP Pipa MA-7 | RU4-RFCC | 106-ACF0015-4/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-06-26 | 2102354902 | 8202237615 |  | 8202227937#TGH4_24 UP scaff rejuve MA-4 | RU4-KPC | 84C204/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238379 |  | 8202227934#Tag 15 Pekerjaan PM & CM RU I |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238374 | 8202235092 | 8202227933#Tag 5 Supporting Teknisi dan | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238373 | 8202234515 | 8202227932#Tag 12 Pemeliharaan Fire Exti | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238364 | 8202234515 | 8202227931#Tag 11 Pemeliharaan Fire Exti | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-04 | 2026-02-20 | 2025-11-28 | 2026-02-27 | 2102359713 | 8202238348 |  | 8202227927#NRK_Perb. Motor GM-2-03C Plan | RU5-E15112 | GM-2-03C/00 | 60 | REL NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 195000000 | 0 | WS-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 005
| K501 | 2026-02-02 | 2026-04-28 | 2026-06-22 | 2026-06-22 | 2102360044 | 8202234654 |  | 8202227926#Penggantian Lampu Sorot Lawe |  |  | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-09 | 2026-05-25 | 2026-05-25 |  | 8202238346 | 8202234908 | 8202227923#Tag 25 Pemeliharaan Sepeda Ki | RU3-WS | BEN-TOOL/00 | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-06-09 | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238344 | 8202235105 | 8202227922#Tag 5 Mekanik CDL, OM, UTL SG |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365591 | 8202240457 |  | 8202227917#25_Pengadaan Sparepart 520B60 | RU4-UTL | 520B601/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357763 | 8202240454 |  | 8202227916#25_[CR] Perbaikan Coupling 10 | RU4-FOC1 | 10P1/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 975000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102354035 | 8202240451 |  | 8202227915#25_Pengadaan Oil Gun Burner 5 | RU4-UTL | 520B401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356357 | 8202240448 |  | 8202227914#25_retrofit lampu tipe konven |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102354656 | 8202240419 |  | 8202227913#25_Penggantian oil tip 151B50 | RU4-RFCUTL | 151B501B/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354654 | 8202240417 |  | 8202227912#25_Penggantian oil tip 151B50 | RU4-RFCUTL | 151B501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356270 | 8202240415 |  | 8202227911#25_Perbaikan Leak Body Valve | RU4-RFCC | 101UV770/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357263 | 8202236354 |  | 8202227910#D25_Perbaikan 024PCV-235 | RU4-LOC2 | 024PCV235/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358084 | 8202240413 |  | 8202227909#25_PDG Slide Valve 101A511 ru | RU4-RFCC | 101A511/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358082 | 8202240411 |  | 8202227908#25_PDG Slide Valve 101A510A r | RU4-RFCC | 101A510A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365340 | 8202240409 |  | 8202227907#25_Pengadaan Oil Gun 052B101 | RU4-UTL | 052B101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-03-06 | 2025-12-05 | 2026-03-06 | 2102363344 | 8202232827 |  | 8202227904#Perbaikan Valve heatingup 12- | RU6-DHC | 12-P-101A/00 | 50 WAMA | REL CSER MANC PRC SETC | 6MR | D16/25/B6/RT-C2H | 2460772 | 0 | MA2-STA |  | MARSHAL |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351411 | 8202232645 |  | 8202227903#Pengadaan UCO Pump | RU2-HOC | 220-P-2A/00 | 50 | REL MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-13 | 2102360180 | 8202234577 |  | 8202227898#Penggantian Vlv Transfr Resin | RU5-UTL | 2UA04F001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 98359960 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-13 | 2102360185 | 8202234580 |  | 8202227897#Penggantian Valve Injeksi DN2 | RU5-UTL | 2UA05D001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 493671 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-10 | 2026-02-02 | 2026-06-18 |  | 8202233426 |  | 8202227896#Perbaiikan motor pompa ultras | RU6-DHC | 12-A-603/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356504 | 8202240407 |  | 8202227895#25_[BD] perbaikan kompressor | RU4-SRU | 91K402B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-13 | 2102360186 | 8202234587 |  | 8202227894#Penggantian Valve DN50 Drain | RU5-UTL | 2UA05D001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1217315 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-13 | 2102360181 | 8202234583 |  | 8202227892#Penggantian Valve Drain DN100 | RU5-UTL | 2UA04F001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2449744 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102359778 | 8202234594 |  | 8202227891#Penggantian O-ring G-3-06D | RU5-E15112 | G-3-06D/00 | 50 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359830 | 8202234576 |  | 8202227890#Perbaikan Pompa G-2-08C | RU5-E15112 | G-2-08C/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 902967 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-31 | 2026-01-29 | 2102362079 | 8202232896 |  | 8202227889#Perbaikan Rod housing bearing | RU6-RCC | 15-SLV-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 768 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-22 | 2102363349 | 8202236570 |  | 8202227888#Thp 1&2 LTSA stationary MA1 | RU6-RCC | 15-R-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362078 | 8202232897 |  | 8202227887#Perbaikan Rod housing bearing | RU6-RCC | 15-SLV-105/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-06 | 2026-02-02 | 2026-07-13 | 2102360149 | 8202234585 |  | 8202227886#Penggantian Valve Drain DN 40 | RU5-UTL | 1UA04F001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 322448 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-13 | 2102360184 | 8202234590 |  | 8202227885#Penggantian Valve DN200 Backw | RU5-UTL | 1UA02D001/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1140176 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-03-06 | 2102359607 | 8202234574 |  | 8202227883#MAT.Perb.Check valve disch G- |  | 8-PN59-3-4-A1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 7826500 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-06-23 | 2102363387 | 8202237871 |  | 8202227881#LTSA Scaffolding 2024-2026 Ta | RU6-RCC | 15-B-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354523 | 8202236381 |  | 8202227880#Penggantian Valve DBB J/O Hea | RU4-TRML | 73JT3/00 | 50 WBUG | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355700 | 8202240405 |  | 8202227877#25_[CR] 054P101AT perbaikan g | RU4-UTL | 054P101A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357058 | 8202235827 |  | 8202227876#Perbaikan Motor 12P2A | RU4-FOC1 | 12P2AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357120 | 8202235823 |  | 8202227874#Perbaikan Motor 14P5B | RU4-FOC1 | 14P5BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-19 | 2026-02-03 | 2026-02-03 | 2102356764 | 8202237614 |  | 8202227873#Penggantian Kabel Power di CC | RU4-FOC1 | 14E650/00 | 50 WASR | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 1000 | 0 | MA1-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353636 | 8202240404 |  | 8202227870#25_[CR] 013E102K02 Bearing De | RU4-FOC2 | 013E102K02/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 4454130 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353951 | 8202240403 |  | 8202227869#25_013E107M03 Motor short | RU4-FOC2 | 013E107M03/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 842800 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-29 | 2026-06-29 | 2026-06-29 | 2102359715 | 8202234559 |  | 8202227868#Upgrade Coupling P-14 A Hitam | RU5-TBL | P-14RP-A-HITAM/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 62000000 | 0 | MA4-ROT |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102354015 | 8202234433 |  | 8202227867#RKA25 Perb Isolasi Atap 47T57 | RU4-RFCGTO | 47T572/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-16 | 2102360218 | 8202234569 |  | 8202227863#Penggantian Line Steam Trace | RU5-D&W | 220-BFW001-3-H/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 67316037 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102353002 | 8202235366 |  | 8202227862#Penambahan Valve 4 IN Separat | RU3-ITP | ITP-P-61-203/00 | 50 WAMA | CRTD CSER MACM PRC | 3MR |  | 12323661 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2025-12-29 | 2025-12-29 | 2102353004 | 8202235003 |  | 8202227861#Pemasangan Cek Valve Pompa 11 | RU3-ITP | ITP-RPR-P-011/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357765 | 8202240402 |  | 8202227860#25_[CR] Penggantian Carbon Ri | RU4-UTL | 52B201K1T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354153 | 8202240401 |  | 8202227858#25_81LISH680 rusak | RU4-KPC | 81LISH680/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358033 | 8202240399 |  | 8202227857#25_011E124M02 Motor Noise | RU4-FOC2 | 011E124M02/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 842800 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102357528 | 8202240396 |  | 8202227856#25_011E117M06 bearing motor n | RU4-FOC2 | 011E117M06/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 1044500 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354151 | 8202240393 |  | 8202227855#25_81LISH650 rusak | RU4-KPC | 81LISH650/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353916 | 8202240390 |  | 8202227851#25_011FT-003B penunjukan seri | RU4-FOC2 | 011FT003B/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-07 | 2102363317 | 8202233297 |  | 8202227843#Perbaikan 25-TE-061 | RU6-HSC | 25-F-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353700 | 8202240387 |  | 8202227841#25_018K-101B Penggantian disp | RU4-FOC2 | 018K101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358105 | 8202240385 |  | 8202227840#25_Penggantian Valve 93PCV-06 | RU4-SRU | 93PCV066/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356870 | 8202240382 |  | 8202227839#25_Penggantian PI 84PI393 di | RU4-KPC | 84K254/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 4990890 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-14 | 2026-03-13 | 2026-12-30 | 2102354218 | 8202236097 |  | 8202227837#UP_25 cleaning & perbaikan mi | RU4-TRML | 39T206/00 | 50 | REL CSER GMCO NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-03-13 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-01-02 | 2102353728 | 8202240379 |  | 8202227836#25_[PV] Penggantian inlet fil | RU4-RFCUTL | 156K502B/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 122153148 | 122153140 | MA5-ROT |  | TONNYADI | 2026-05-25 | 2026-03-10 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-29 | 2026-06-29 | 2026-06-29 |  | 8202234564 | 8202234567 | 8202227832#Perbaikan pompa P.9 WTP 1 | RU5-UTL | P-9PAMPANCUR/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-06-29 | 2026-06-29 | 2102359773 | 8202234567 |  | 8202227831#Penggantian unit pompa P.9 WT | RU5-UTL | P-9PAMPANCUR/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-03 | 2102362013 | 8202233382 |  | 8202227826#Perbaikan 12-PTR1-501B | RU6-DHC | 12-PTR1-501B/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-25 | 2102363269 | 8202234006 |  | 8202227825#Internal Cleaning Degasser 22 | RU6-DHC | 22-V-104/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-07-06 |  | 8202236661 | 8202233858 | 8202227822#SWO Pemb. LTSA CV Masoneila T | RU6-RCC | 16-FV-018/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-12-02 | 2102363069 | 8202233858 |  | 8202227821#Pemb. LTSA Control Valve Maso | RU6-RCC | 16-FV-018/00 | 01 | CLSD CSER NCMP NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357056 | 8202240376 |  | 8202227818#25_Kerusakan Pulley Motor Fin | RU4-GTO | 120E602A-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2102359716 | 8202234542 |  | 8202227817#Penggantian Lampu di PPII UTL | RU5-UTL |  | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357761 | 8202240373 |  | 8202227815#25_[CR] Penggantian Bearing 1 | RU4-RFCGTO | 106P501A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 14279500 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-05-22 | 2102359770 | 8202234545 |  | 8202227810#Penggantian Condensate Cooler |  | E-37-02/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-05 | PM |  | 004
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238326 | 8302404176 | 8202227807#Tag 9 Pemeliharaan Mini Excav | RU3-LKKK |  | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238503 | 8202234925 | 8202227805#Tag 1 Pemeliharaan RPA 1-5 & |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-10 | 2026-01-02 | 2026-01-02 | 2102353009 | 8202234925 |  | 8202227804#Pemeliharaan RPA 1-5 & TBA |  |  | 60 | REL CNF GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | HARISASEPWIJ | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-04 | 2026-02-02 | 2026-04-13 | 2102359774 | 8202234506 |  | 8202227803#Perbaikan Turbine BFW 9 |  |  | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357265 | 8202235757 |  | 8202227799#Perbaikan Motor Finfan & MV A | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-07-08 | 2102359771 | 8202234511 |  | 8202227798#Perbaikan Temp. Sensor 02-TE/ | RU5-E15112 | 02-TT-108/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/26/B6/RT-C2H | 90930000 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-03-04 | 2102359896 | 8202234509 |  | 8202227792#Perbaikan Temp. Sensor pada 3 | RU5-UTL | 37-TT-201/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 4 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-18 | 2025-12-05 | 2026-09-11 | 2102363316 | 8202234069 |  | 8202227791#23-P-101 B | RU6-HSC | 23-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102354710 | 8202234395 |  | 8202227790#Pengadaan Stud Bolt 051E101 |  |  | 50 | CRTD CSER MACM PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238498 | 8202235126 | 8202227789#Tag 1 Mekanik Area Utara OM |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-26 | 2026-01-01 | 2026-12-30 | 2102353001 | 8202235126 |  | 8202227788#Pekerjaan Mekanik Area Utara |  |  | 60 | REL GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354198 | 8202234723 |  | 8202227787#Pengadaan Material Boiler 052 | RU4-UTL | 052B102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238487 | 8202234997 | 8202227786#Tag 10 KV Penyediaan Jasa Hos |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238461 | 8302402794 | 8202227785#Tag 6 TSA-PM DCS Honeywell | RU3-UTL |  | 50 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-29 | 2102363265 | 8202233181 |  | 8202227784#Perbaikan Dryer 058-D-101 | RU6-UTL | 058-D-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 15840 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-05-07 | 2026-02-02 | 2026-02-02 | 2102358428 | 8202234597 |  | 8202227777#PEKERJAAN PEMBUATAN BOBOT PON | RU7-CDU | 1-P-12A/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/25/B6/NR-1-D2H | 0 | 0 | MA-ROT |  | SAPBATCH | 2025-08-20 | 2026-02-07 | PT02 |  | 3 | 2026-03-08 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-03-25 | 2102359831 | 8202234456 |  | 8202227775#PERB.LINE 21-P421-30" DEKAT T | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 47142299 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363203 | 8202233916 |  | 8202227774#Matl Injeksi NAOH ke 11-V-101 | RU6-HSC | 11-V-101A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102359834 | 8202234446 |  | 8202227772#POMPA G-3-30A VIBRASI TINGGI | RU5-E15112 | G-3-30A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-13 | 2102363127 | 8202233513 |  | 8202227771#Penggantian RGA di tangki 42- | RU6-ITP | 42-T-107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 13200 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359890 | 8202234477 |  | 8202227770#ISOLASI FDF TURBINE BOILER 1 | RU5-UTL | T-FDF-31-01/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359891 | 8202234475 |  | 8202227769#ISOLASI FDF TURBINE BOILER 2 | RU5-UTL | T-FDF-31-02/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359894 | 8202234466 |  | 8202227768#ISOLASI FDF TURBINE BOILER 5 | RU5-UTL | T-FDF-HHP-5/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359893 | 8202234469 |  | 8202227767#ISOLASI FDF TURBINE BOILER 4 | RU5-UTL | T-FDF-HHP-4/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359892 | 8202234473 |  | 8202227766#ISOLASI FDF TURBINE BOILER 3 | RU5-UTL | T-FDF-31-03/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2026-02-23 | 2026-02-23 | 2102359945 | 8202234442 |  | 8202227765#POMPA G-5-05 A MECHSEAL BOCOR | RU5-E15111 | G-5-05A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1995000 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-12-22 | 2025-12-22 | 2102359946 | 8202234437 |  | 8202227763#POMPA G-5-05 B MECHSEAL BOCOR | RU5-E15111 | G-5-05B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 3083076 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-09 | 1102328366 | 8202234461 |  | 8202227762#Pengadaan Dongle FAS (Softwar | RU5-LAB | BWB-316020/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 15000000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-19 | 2102362591 | 8202233007 |  | 8202227761#Perbaikan PJU Solar Cell Kila | RU6-LK/KK | JALANKILANG/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 4884 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102360213 | 8202234450 |  | 8202227759#Perbaikan Turbine GT-2-03A | RU5-E15112 | GT-2-03A/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102360188 | 8202234430 |  | 8202227756#MAT. PIPA JUMPER LINE NITROGE |  | C-35-101E/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 102693585 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-15 | 2026-03-09 | 2026-03-09 | 2102358086 | 8202241431 |  | 8202227755#[TGH] Penagihan TSA Mechseal | RU4-FOC1 | 11P22B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 234047000 | 0 | MA1-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353833 | 8202240370 |  | 8202227750#25_[CR] 048K102A Abnormal Noi | RU4-FOC2 | 019K102A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 7910519 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-04-02 | 2026-04-02 | 2102359943 | 8202234410 |  | 8202227749#Perbaikan Motor EaM-201-01F | RU5-D&W | EAM-201-01F/00 | 60 | REL CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 672478 | 0 | MA1-LIS |  | HELDIPRANATA | 2026-04-02 | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2025-12-23 | 2025-12-29 | 2102359833 | 8202234409 |  | 8202227746#Pergantian Switch Motor EM-3- | RU5-E15112 | EM-3-16A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 47 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102351308 | 8202238427 |  | 8202227745#LTSA PEMELIHARAAN PERBAIKAN F | RU2-HCC |  | 50 | CRTD NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 100000000 | 0 | MA2-CIV |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356429 | 8202240367 |  | 8202227744#25_Fan Motor 140P606A Rontok/ | RU4-GTO | 140P606A/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102358032 | 8202240364 |  | 8202227743#25_[CR] 011E124K03 puly tidak | RU4-FOC2 | 011E124K03/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 3635469 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-02 | 2026-03-06 | 2102360491 | 8202234432 |  | 8202227741#Leak manhole LTSC C-8-07 A | RU5-E15112 | C-8-07A/00 | 50 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-08NH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-03-06 | 2102358849 | 8202234422 |  | 8202227739#MAT.PERB. E-3-35C | RU5-E15112 | E-3-35C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 569873 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-02 | 2026-02-02 | 2102359899 | 8202234411 |  | 8202227738#Penggantian bearing G-31-39C | RU5-E15112 | G-31-39C/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 80981388 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102357719 | 8202237613 |  | 8202227737#TGH9_24 Monitoring Peralatan | RU4-RFCUTL | 151FT-U151/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102357721 | 8202237612 |  | 8202227736#TGH8_24 Monitoring Peralatan | RU4-RFCUTL | 151FT-U151/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356416 | 8202240361 |  | 8202227734#25_VSD 14K602A alarm Common T | RU4-FOC1 | 14K602BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-06-17 | 2026-06-17 | 2026-12-22 | 2102353426 | 8202234944 |  | 8202227733#PM_Penggantian Oil Tip 011F10 | RU4-FOC2 | 011F101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 273421152 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-06-17 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359941 | 8202234408 |  | 8202227732#Upgrade Coupling P.16 A Hita | RU5-TBL | P-16RP-A-HITAM/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 124000000 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102354238 | 8202240358 |  | 8202227731#25_[CR] Pompa Injeksi NaOCl 6 | RU4-RFCUTL | 63A502P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102353746 | 8202237611 |  | 8202227730#tagihan Upgrade Turbin Contro | RU4-FOC2 | 001SS11AH1-CB/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238399 | 8202235314 | 8202227728#Tag TKDN Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238378 | 8202235314 | 8202227727#Tag 8 Steam Leak Non Trap |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355709 | 8202240356 |  | 8202227726#25_Penggantian 14ZS312B | RU4-FOC1 | 14ZS312B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 5 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355706 | 8202240353 |  | 8202227725#25_Penggantian 14ZS12A | RU4-FOC1 | 14ZS312A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 5 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102355702 | 8202241430 |  | 8202227724#[TGH] TSA Mechseal Assy IB OB | RU4-UTL | 054P101C/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 479696000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365590 | 8202240349 |  | 8202227723#25_[CR] Perbaikan low perform | RU4-TRML | 39P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102358102 | 8202241429 |  | 8202227722#[TGH] MS OB Leak 540P401A | RU4-UTL1 | 540P401A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 126466000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353007 | 8202235579 |  | 8202227720#FLRS-P-404C Bocor Mech Seal | RU3-CDL | FLRS-P-404C/00 | 50 WAMA | REL CSER MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356412 | 8202240347 |  | 8202227719#25_[CR] Noise Pompa Oil Purif | RU4-RFCGTO | 105K501M/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 3309000 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102355956 | 8202240345 |  | 8202227717#25_Mtl. Valve drain 021E121AC | RU4-LOC2 | 021E121A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351069 | 8202232381 |  | 8202227715#Perbaikan Bocoran 100-E-13 | RU2-HSC | 100-E-13/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356421 | 8202240343 |  | 8202227713#25_Perbaikan lampu penerangan | RU4-FOC2 | 014K102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351091 | 8202232656 |  | 8202227712#Material Cooler Sealing Oil | RU2-HSC | 100-P-8A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358119 | 8202240341 |  | 8202227711#25_Penggantian Battery Bank-U | RU4-KPC | 80EE0041/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K701 | 2026-02-02 | 2026-05-07 | 2026-02-02 | 2026-02-02 | 2102358426 | 8202234596 |  | 8202227710#BEARING FEILUR DI 3-EAM-02A/0 | RU7-CRU | 3-EAM-02A/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/25/B6/RT-3-D1H | 0 | 0 | MA-LINT |  | SAPBATCH | 2025-08-21 | 2026-02-07 | PT02 |  | 3 | 2026-03-08 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354157 | 8202240339 |  | 8202227709#25_84PDI354 Rusak Penunjukan | RU4-KPC | 84PDI354/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366006 | 8202240337 |  | 8202227702#25_Perbaikan sensor temp wind | RU4-UTL | 510TE821A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 9 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354385 | 8202235468 |  | 8202227701#perbaikan probe sensor 051XE0 | RU4-UTL | 051XE006A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 14857001 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2025-11-28 | 2026-02-27 | 2102359593 | 8202234398 |  | 8202227698#Perbaikan Control Valve 35-PC | RU5-E15112 | 35-PCV-101B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 770 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-06-03 | 2102359942 | 8202234403 |  | 8202227697#MAT.Perb E-2-02B | RU5-E15112 | E-2-02B/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 107334424 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-02 | 2026-06-30 | 2102360096 | 8202234402 |  | 8202227695#Penggantian Valve Outlet Cool |  | S-37-01A/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 25989906 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 | 2 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-05 | 2026-01-26 |  | 8202234404 | 8202237414 | 8202227694#MAT. Perb. E-2-11 (REVAMPING) | RU5-E15112 | E-2-11/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 393019969 | 0 | MA3-STA |  | SAPBATCH | 2026-05-08 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354006 | 8202240335 |  | 8202227693#25_[CR] Perbaikan Packing Rod | RU4-FOC1 | 13K1B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3476461 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102363121 | 8202233016 |  | 8202227692#Perbaikan MOV 13-HV-043A | RU6-DHC | 13-V-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-10-06 |  | 8202233901 | 8202238657 | 8202227691#Mtl untuk Temporary Repair 56 | RU6-UTL | 56-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C1H | 71280 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357790 | 8202240333 |  | 8202227690#25_[CR] Penggantian cylinder | RU4-UTL | 56K3B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-08 | 2026-03-09 | 2026-02-03 | 2026-12-30 | 2102354661 | 8202238766 |  | 8202227689#25_[BK] Shaft Macet Pompa 47P | RU4-RFCGTO | 47P591A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 571098 | 57109800 | WS-PMP |  | WAHYUCATUR |  | 2026-03-09 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-06-30 |  | 8202237869 | 8202233981 | 8202227687#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | ES-B14-01/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-21 | 2026-02-03 | 2026-02-03 | 2102353704 | 8202236218 |  | 8202227685#Perbaikan Bearing Motor 102E5 | RU4-RFCC | 102E517AM1/00 | 60 WAMA | REL CNF CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | YMOHAMMAD | 2026-05-18 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-05 | 2026-05-20 | 2026-05-22 | 2102360003 | 8202234396 |  | 8202227684#Perbaikan WITCH START STOP P0 | RU5-UTL | P-6DRIVERRPA/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 21600000 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-27 | 2026-02-11 | PT02 |  | 3 | 2025-12-27 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-03-06 | 2102360098 | 8202234399 |  | 8202227683#Perb. E-1-31A | RU5-E15111 | E-1-31A/00 | 50 | REL CSER NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-03-06 | 2102358822 | 8202234405 |  | 8202227682#MAT. Perb. E-1-33 B | RU5-E15111 | E-1-33B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 10415 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-02 | 2026-03-06 | 2102358850 | 8202234406 |  | 8202227681#MAT. Perb. E-1-18 | RU5-E15111 | E-1-18A/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-25 | 2102360080 | 8202234364 |  | 8202227680#Perbaikan TI HS K-3-01A | RU5-E15112 | KT-3-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 26658000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-06-03 |  | 8202234389 | 8202237415 | 8202227679#MAT. Perb. E-2-10 (REVAMPING) | RU5-E15112 | E-2-10/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 631392553 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-24 | 2102363124 | 8202234101 |  | 8202227678#11-PI-209 | RU6-HSC | 11-P-102B/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-23 | 2102362298 | 8202232848 |  | 8202227677#Perbaikan Transmitter 24-FT-0 | RU6-HSC | 24-FT-017/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-01 | 2102358820 | 8202234368 |  | 8202227676#Perbaikan Header Steam Ejecto |  | FA-201/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 56079761 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-02-22 |  | 8202237610 |  | 8202227670#Jasa Perbaikan 014K102A | RU4-FOC2 | 014K102A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-06-30 | 2102362986 | 8202233427 |  | 8202227666#Perbaiakan UV 058-K-101C | RU6-UTL | 058-K-101C/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 12144 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102353247 | 8202234490 |  | 8202227662#N_Perbaikan Vacuum Ejector Cl | RU3-CDGP | BASIN-P-1A/00 | 50 WAMA | CRTD CSER MACM PRC | 3IR |  | 0 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-25 | 2102362076 | 8202233260 |  | 8202227660#Perbaikan 51-TI-167D STG D | RU6-UTL | 51-G-101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 9240 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-03 | 2026-02-02 | 2026-06-25 | 2102359944 | 8202234390 |  | 8202227658#F-2-01 Refractoy Damaged | RU5-E15112 | F-2-01A/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 392129685 | 0 | MA3-STA |  | DWIYUDAAM |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238369 | 8202235085 | 8202227653#Tag 7 Isolasi Panas Area CD&G |  |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356885 | 8202240331 |  | 8202227652#25_Penggantian sensor dan ana | RU4-RFCUTL | 153TT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-02 | 2102360002 | 8202234377 |  | 8202227651#Penggantian Lampu Plant Demin |  |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 111594210 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356500 | 8202240329 |  | 8202227650#25_Transmitter 140TI072 Penun | RU4-GTO | 140TT072/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 2 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356427 | 8202240327 |  | 8202227649#25_Transmitter 120PT611A Penu | RU4-GTO | 120PT611A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-06-30 | 2102363209 | 8202237867 |  | 8202227648#LTSA Hot Insulation Tahap 3 A | RU6-RCC | 15-C-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355623 | 8202240324 |  | 8202227646#25_011PDIC701 hunting | RU4-FOC2 | 011PDV701/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 21345223 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-29 | 2026-06-29 | 2026-06-29 | 2102358905 | 8202234353 |  | 8202227642#Teflon set pompa dosing pump | RU5-UTL | G-32-26A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-24 | 2026-01-23 | 2102359310 | 8202234366 |  | 8202227641#Perbaikan Temp Junction Box 0 | RU5-E15112 | F-2-01A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 386 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-24 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-10-01 | 2026-10-01 | 2102358929 | 8202234385 |  | 8202227640#Motor dan pompa booster no.2 | RU5-UTL | BOOSTER-PUMP-2/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-10-01 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 8202234378 | 8202234352 | 8202227639#Penggantian HPU LA jetty 1 OM | RU5-TBL | L-ARM-1-JT-1/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-31 | 2025-12-31 | 2102359372 | 8202234352 |  | 8202227638#Upgrade Sistem Kontrol LA jet | RU5-TBL | L-ARM-1-JT-1/00 | 01 | CRTD NMAT PRC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-12-31 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-08 | 2025-12-08 | 2102359376 | 8202234380 |  | 8202227637#Penggantian HPU control LA je | RU5-TBL | L-ARM-1-JT-5/00 | 01 | CRTD NMAT PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-08 | 2025-12-08 | 2102359374 | 8202234382 |  | 8202227636#Penggantian HPU control LA je | RU5-TBL | L-ARM-1-JT-3/00 | 01 | CRTD NMAT PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359375 | 8202234381 |  | 8202227635#Penggantian HPU Control LA je | RU5-TBL | L-ARM-1-JT-4/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359373 | 8202234384 |  | 8202227634#Penggantian HPU control LA je | RU5-TBL | L-ARM-1-JT-2/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102360178 | 8202234370 |  | 8202227633#Perbaikan FDF HHP 1 | RU5-UTL | T-FDF-31-01/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 29209980 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-02 | 2026-02-13 |  | 8202234388 | 8202238855 | 8202227632#MATERIAL PIPING PLANT HVU2&HP | RU5-E15112 | 2-SPW05-3-B6/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/26/B6/RT-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102360004 | 8202234363 |  | 8202227630#Pompa Kuning Anti Banjir (Fil |  |  | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353959 | 8202240321 |  | 8202227629#25_Mtl. Perbaikan Bocoran 024 | RU4-LOC2 | 024E103/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 3097862 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-24 | 2102363262 | 8202234064 |  | 8202227627#25-TE-061 | RU6-HSC | 25-F-102/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-06-04 | 2102360212 | 8202237429 |  | 8202227626#MAT.Perb. E-8-05B | RU5-E15112 | E-8-05B/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 38598721 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-06-04 | 2102360211 | 8202237431 |  | 8202227625#MAT.Perb. E-8-04B | RU5-E15112 | E-8-04B/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 66837779 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353957 | 8202240318 |  | 8202227622#25_Mtl. Perbaikan bocoran 023 | RU4-LOC2 | 023E112/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 7259000 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-02 | 2026-03-06 | 2102360203 | 8202234351 |  | 8202227615#Ganti Baut Flange Block Valve | RU5-E15111 | E-5-17/00 | 50 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-05NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102357318 | 8202240315 |  | 8202227613#25_[CR] 91P-403B (mech seal b | RU4-SRU | 91P403B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 2309815 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2025-11-10 | 2026-05-13 | 2102360148 | 8202237426 |  | 8202227612#Perb. JB Pressure Switch STG | RU5-UTL | TG-6-PP1-INST/00 | 60 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 29345136 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-12 | 2026-02-27 | 2026-11-26 | 2102353789 | 8202234614 |  | 8202227611#Pengadaan Material Water Sepa |  |  | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 1168795953 | 1168795953 | MA3-STA |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-06-12 | 2102359213 | 8202237425 |  | 8202227609#Perbaikan Flow Meter Demin Pl | RU5-UTL | OUA41D002/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 136416004 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102357315 | 8202240312 |  | 8202227608#25_[CR] mech seal bocor pompa | RU4-SRU | 91P402A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 2555650 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355501 | 8202240309 |  | 8202227607#25_[CR] Penggantian battray 1 | RU4-RFCUTL | 155P501B-EN/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362836 | 8202232946 |  | 8202227605#Perbaikan Pompa 54-P-103A | RU6-UTL | 54-P-103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 71280 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359267 | 8202234349 |  | 8202227604#K-19-01B Oil Filter Wire Mesh | RU5-E15112 | K-19-01B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-08 | 2026-01-20 | 2026-01-20 | 2102359768 | 8202237423 |  | 8202227603#Rubber coupling Pompa Diesel | RU5-UTL | DIESEL-P1-SW/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH | 2026-05-06 | 2026-02-07 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-14 | 2026-02-02 | 2026-06-26 | 2102363122 | 8202233105 |  | 8202227602#Perbaikan Mech Seal 37-P-103A | RU6-POC | 37-P-103A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 5558917 | 5279240 | MA3-ROT |  | ABDULAZIZ70 |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355630 | 8202240306 |  | 8202227601#25_perbaikan control motor 56 | RU4-UTL | 560K301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102361037 | 8202232764 |  | 8202227600#PMPdm electrical motor 13-P-1 | RU6-DHC | 13-P-101-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 19743000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102361749 | 8202233871 |  | 8202227598#Pekerjaan Overhaul Motor LV 1 | RU6-HSC | 11-E-114C-M/01 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102361821 | 8202233064 |  | 8202227597#Perbaikan Motor 14-E-109C | RU6-DHC | 14-E-109C-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-21 | 2102360097 | 8202237428 |  | 8202227596#Pemasangan Socket listrik di | RU5-UTL | 0VG02D001/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 683300000 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102358021 | 8202241428 |  | 8202227594#[TGH] 21P7B–Penggantian Mech | RU4-LOC1 | 21P7B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 152074000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357749 | 8202240301 |  | 8202227593#25_[CR] Penggantian Condensat | UTL-UP4 | 56K302/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357748 | 8202240297 |  | 8202227592#25_[CR] Penggantian hose set | RU4-UTL | 56K201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238353 | 8202235291 | 8202227589#Tag 7 Mekanik Area Selatan OM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238329 | 8202235291 | 8202227588#Tag 6 Mekanik Area Selatan OM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238394 | 8202234582 | 8202227585#Tag 4 Perbaikan Korosi Atap T |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238158 | 8202234515 | 8202227584#Tag 10 Pemeliharaan Fire Exti | RU3-LKKK |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102354289 | 8202240293 |  | 8202227583#25_[CR] Mechanical seal bocor | RU4-TRML | 041P309/00 | 60 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 6928350 | 6928350 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237609 | 8202237607 | 8202227582#TGH11_23 Jasa LTSA Mech Seal | RU4-FOC2 | 011P104A/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 31530000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-08 | 2102358928 | 8202237424 |  | 8202227581#Perbaikan PI Line 934 Jetty 2 | RU5-TBL | 22-GANGWAY-5BC/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 30885220 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102356195 | 8202241427 |  | 8202227580#[TGH] Penggantian basic seal | RU4-LOC2 | 023P109A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 193703000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102355621 | 8202241426 |  | 8202227579#[TGH] penagihan Kontrak perfo | RU4-FOC2 | 011P109A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 145319000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-01-02 | 2026-08-26 | 2102363205 | 8202237866 |  | 8202227577#LTSA Reposisi Underground Cab | RU6-HSC | 17-PDB3-01/00 | 50 | REL CSER GMPS NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 274023000 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2025-11-11 | 2025-11-11 | 2102360143 | 8202237422 |  | 8202227576#Perbaikan Pompa P4A Putih RPA | RU5-TBL | P-4RP-A-PUTIH/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356887 | 8202240287 |  | 8202227572#25_Penggantian Transmitter 15 | RU4-RFCUTL | 154LI012B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 14388000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102356197 | 8202241425 |  | 8202227568#25_[TGH] Penggantian basic se | RU4-TRML | 041P106B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 98200000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-06-03 | 2026-06-03 | 2102360147 | 8202237419 |  | 8202227567#Perbaikan Kompresor K-5-02A | RU5-E15111 | K-5-02A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 2142325808 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102356191 | 8202241424 |  | 8202227566#25_[TGH] Penggantian basic se | RU4-LOC2 | 021P110A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 85989000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-03 | 2102360144 | 8202237420 |  | 8202227564#Perbaikan Blower K-5-22 | RU5-E15111 | K-5-22/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 15027486 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 | 2102360091 | 8202237417 |  | 8202227563#Perbaikan Pompa GT-5-16A | RU5-E15111 | GT-5-16A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-03 | 2102360050 | 8202237418 |  | 8202227562#Perbaikan POMPA G-4-10B | RU5-E15111 | G-4-10B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 566930 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2025-12-01 | 2026-06-10 | 2102358055 | 8202237421 |  | 8202227559#Perb. Tx 19-LIC-510 & 19-LIC- | RU5-E15112 | C-19-05/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 120554740 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 004
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358465 | 8202234591 |  | 8202227558#Penggantian 6-PM-06A | RU7-UTL | 6-PM-06A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-5-D1H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-11 | 2026-06-11 | 2026-06-11 | 2026-07-23 |  | 8202238855 |  | 8202227555#ANEKA RGM PIPING,COLUMN,&FURN | RU5-E15112 | 2-SPW05-3-B6/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 3825000000 | 3251250000 | MA3-STA |  | BERNANDOP |  | 2026-05-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351536 | 8202232621 |  | 8202227551#Perbaikan Pompa 140 P-14 | RU2-HOC | 140-P-14A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 399926 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351355 | 8202232297 |  | 8202227550#Fabrikasi Oil Deflector 140-P | RU2-HOC | 140-P-22B/00 | 50 | REL NMAT PRC SETC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351922 | 8202232490 |  | 8202227548#Perbaikan 140 P-6A | RU2-HOC | 140-P-6A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 334219 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102351945 | 8202235574 |  | 8202227543#Gate Valve 3/4" Daytank Acid | RU3-UTL | 2000-U5/00 | 60 | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351943 | 8202232348 |  | 8202227542#Pengadaan coupling 945 P-30 A | RU2-ITP | 945-P-3B/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 261848 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351191 | 8202232614 |  | 8202227541#Perbaikan Pompa 140 PT-21B | RU2-HOC | 140-PT-21B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102361785 | 8202233870 |  | 8202227535#Pekerjaan Overhaul Motor LV 2 | RU6-HSC | 23-P-601B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357275 | 8202235767 |  | 8202227531#Motor 21P-17 Noise | RU4-LOC1 | 21P17M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-10 | 2102360057 | 8202237415 |  | 8202227528#MAT. Tube Bundle E-2-10 | RU5-E15112 | E-2-10/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-05-08 | 2026-06-05 | 2102360058 | 8202237414 |  | 8202227527#MAT.Tube Bundle E-2-11 | RU5-E15112 | E-2-11/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/26/B6/RT-C2H | 1 | 0 | MA3-STA |  | HIMMATUSS |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-10 | 2102360352 | 8202237416 |  | 8202227526#MAT. Tube Bundle E-2-09 | RU5-E15112 | E-2-09/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357977 | 8202240280 |  | 8202227524#25_Retrofit bearing 021P-103 | RU4-LOC2 | 021P103/00 | 60 WAMA | REL CSER MANC PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 3666150 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102358118 | 8202240276 |  | 8202227523#25_Penggantian coupling 71P1C | RU4-TRML | 71P1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357562 | 8202240273 |  | 8202227522#25_[CR] Penggantian Coupling | RU4-UTL | 054WS103P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 13800000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357270 | 8202240269 |  | 8202227521#25_[CR] 018POP101A mechseal b | RU4-FOC2 | 018P101A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 55855633 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-24 | 2025-12-29 | 2102360146 | 8202237398 |  | 8202227518#Rewinding Motor GM 8-03D | RU5-E15112 | GM-8-03D/00 | 60 | CLSD CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 22 | 0 | MA3-LIS |  | MKASPUDDIN | 2025-12-25 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-07 | 2102358059 | 8202237411 |  | 8202227517#Penggantian Block Valve Blowd |  | FA-201/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 67846378 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-07-30 | 2102359076 | 8202237401 |  | 8202227515#Perbaikan PI Pompa G-225-01A/ | RU5-D&W | G-225-01A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 80 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-07-07 |  | 8202236754 | 8202232770 | 8202227514#SPK 21LTSA Transformator RU V | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-09 | 2102359263 | 8202237409 |  | 8202227510#Perb. PI Line 17Bar, 3,5Bar d | RU5-UTL | BFW-P-9-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 35170000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-01 | 2026-04-02 | 2026-04-06 | 2102360085 | 8202237404 |  | 8202227506#Perbaikan Motor EAM 201-01E | RU5-D&W | EAM-201-01E/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1481800 | 0 | MA1-LIS |  | SAPBATCH | 2026-04-02 | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2026-06-03 | 2026-06-04 | 2102360086 | 8202237403 |  | 8202227504#Perbaikan Motor EAM 231-01A | RU5-D&W | EAM-231-01A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 672478 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-29 | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2026-06-03 | 2026-06-04 | 2102360087 | 8202237402 |  | 8202227503#Perbaikan Motor EAM 231-01B | RU5-D&W | EAM-231-01B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 672478 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-29 | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-09 | 2102358853 | 8202237405 |  | 8202227502#Perbaikan FI Fire Pump G-33-0 | RU5-E15500 | G-33-01B/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 120000000 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-23 | 2026-05-22 | 2102358924 | 8202237400 |  | 8202227500#Perbaikan Sistem DCS Centum B | RU5-D&W | DCS-HVU-III/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 40000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-08-10 | 2102359134 | 8202237407 |  | 8202227499#Perbaikan 05-TW/TE-367 di P-5 | RU5-E15111 | P-5-20/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 11569838 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362720 | 8202233955 |  | 8202227496#Mat Perb Turbine 51-P-101A-T | RU6-UTL | 51-P-101A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356046 | 8202240265 |  | 8202227495#25_[CR] 41P-3A bearing pompa | RU4-TRML | 41P3A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 8148927 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2102360140 | 8202237391 |  | 8202227492#Perbaikan Kompresor K-3-02C | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 598349916 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-07-08 | 2102358057 | 8202237397 |  | 8202227489#Cleaning Strainer SWD 2 |  | FA-201/00 | 50 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-30 | 2102360093 | 8202237387 |  | 8202227488#Perbaikan Timer LP Area OM Se | RU5-TBL | PLANT-20-LIS/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 9277522 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362727 | 8202233728 |  | 8202227484#Penggantian 12-LT-613 | RU6-DHC | 12-LT-613/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353711 | 8202240261 |  | 8202227479#25_Pengadaan Check Valve Rec | RU4-FOC1 | 13K1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357125 | 8202240258 |  | 8202227478#25_[CR] Perbaikan Turbine 54P | RU4-UTL | 54P202C-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 27632440 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-08-03 | 2026-08-03 | 2102360088 | 8202237388 |  | 8202227477#Perbaikan Pompa G-3-10A | RU5-E15112 | G-3-10A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 11977003 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-08-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356501 | 8202236439 |  | 8202227475#D25_260FI054 H2 To LOC3 Flow | RU4-LOC3 | 260FI054/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360084 | 8202237392 |  | 8202227474#Perbaikan Grounding Body Traf | RU5-UTL | 41-R-SS-68-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 46350000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356274 | 8202240254 |  | 8202227473#25_84PV515 Underperfm Pres Td | RU4-KPC | 84PV515/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-03-02 | 2026-07-01 | 2102360083 | 8202237395 |  | 8202227472#Penggantian Kabel, Lampu, Soc | RU5-TBL | 101-5-T-01C/00 | 50 | REL CSER GMPS MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 136257459 | 1050000 | MA4-LIS |  | AGUSHIDAYAT |  | 2026-02-07 | PT02 |  | 3 | 2026-03-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-06-29 | 2102358054 | 8202237393 |  | 8202227469#Perb. Tx 19-LIC-671 & 19-FIT- | RU5-E15112 | 19-LIC-671/00 | 50 | REL CSER MANC PRC SETC | 5IR | D15/25/B6/RT-C2H | 117816750 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-07 | 2102361924 | 8202233379 |  | 8202227465#Perbaikan 12-TX-194 | RU6-DHC | 12-R-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-07 | 2102361965 | 8202233363 |  | 8202227463#Perbaikan 13-TX-186 | RU6-DHC | 13-R-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-10 | 2026-02-02 | 2026-07-31 |  | 8202232948 |  | 8202227462#Perbaikan Pompa 53-P-303A | RU6-UTL | 53-P-303A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 18198760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353779 | 8202240250 |  | 8202227461#[CR] Perbaikan Pompa 104P502B | RU4-RFCC | 104P502B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 121261171 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2026-06-03 | 2026-06-04 | 2102360094 | 8202237390 |  | 8202227460#Perbaikan Motor Degassaer Ven | RU5-UTL | OUA-12-D001/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 282998 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-30 | 2026-02-11 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353719 | 8202236806 |  | 8202227459#Penggantian Kabel Kontrol 38P | RU4-TRML | 38P101A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 214940000 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-24 | 2025-12-29 | 2102360092 | 8202237389 |  | 8202227458#Perbaikan Motor G-20-19A ST 1 | RU5-TBL | GM-20-19A/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 697367 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-24 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-24 | 2102363129 | 8202234070 |  | 8202227457#22-V-109C | RU6-DHC | 22-V-109C/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-06 |  | 8202236834 | 8202233979 | 8202227455#PM 7 - LTSA FGDS General Moni | RU6-ITP | 42-T-301A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353117 | 8202234640 |  | 8202227450#Perbaikan Expans Joint Pomp D | RU3-CDGP | 85-P-201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102358022 | 8202241423 |  | 8202227449#Penagihan kontrak mech seal 2 | RU4-LOC3 | 220P104A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 177729000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102358094 | 8202236301 |  | 8202227444#D25_Perbaikan timbangan 50 to | RU4-TRML | 49HS001/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102358063 | 8202237608 |  | 8202227443#Analizer PH, condativity blow | RU4-LOC2 | 002PDT021/00 | 50 | CRTD CSER NMAT PRC RELR SETC | 4IR | D14/26/B6/RT-8-C2H | 100000 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356206 | 8202240244 |  | 8202227442#25_Penggantian Temperature In | RU4-TRML | 32PSV001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 33880000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-14 | 2026-03-09 | 2026-03-09 | 2102357979 | 8202241422 |  | 8202227433#[TGH] Penagihan LTSA Mechseal | RU4-UTL | 054P101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 202331000 | 0 | WS-PMP |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237607 |  | 8202227432#Penggantian Mechanical Seal I | RU4-FOC2 | 011P104A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 413143000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102357975 | 8202241421 |  | 8202227431#[TGH] Kontrak Performance Mec | RU4-FOC2 | 011P104A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 339569000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102363067 | 8202233796 |  | 8202227428#Pengadaan Material 15-P-101AB | RU6-RCC | 15-P-101A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-19 | 2102360183 | 8202237385 |  | 8202227427#Perbaikan Solenoid Valve 05-X | RU5-E15111 | 05-XCV-254C/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 400 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353770 | 8202236803 |  | 8202227426#Penggantian Kabel Kontrol DCS | RU4-LOC2 | 40LTW08/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 1085088000 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-11 | 2026-02-05 | 2026-10-29 | 2102356798 | 8202234374 |  | 8202227425#Pengadaan tip gas burner 14F- | RU4-FOC1 | 14F603/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-09 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354305 | 8202240240 |  | 8202227424#25_Mtl. Pilot Assy & Flame Ho | RU4-FOC1 |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-06-03 | 2026-02-03 | 2026-02-03 | 2102353775 | 8202235744 |  | 8202227420#MTL_Fire Ground | RU4-TRML | 30P104BM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | GEN-MEK |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-07 | 2026-02-03 | 2026-02-03 | 2102360358 | 8202237386 |  | 8202227418#Perbaikan Pompa G-35-03B | RU5-E15112 | G-35-03B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 86500 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102358027 | 8202240196 |  | 8202227417#25_Mtl. Bocoran Line Discharg | RU4-SRU | 93P402B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 26783977 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102355165 | 8202240192 |  | 8202227416#25_[CR] Perbaikan coupling 22 | RU4-LOC1 | 22P4A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 1500000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353710 | 8202240188 |  | 8202227415#25_[CR] Penggantian Sim Coupl | RU4-FOC1 | 11P22B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 6077882 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237605 | 8302417241 | 8202227412#TGH4_24 UP Scaffold Rejuve MA | RU4-FOC2 | 012C101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357976 | 8202240184 |  | 8202227411#25_[CR] 014K106A high temp Ca | RU4-FOC2 | 014K106A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361931 | 8202234060 |  | 8202227409#31-PSV-501 ABC untuk 31-E-101 | RU6-HSC | 31-E-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352685 | 8202234795 |  | 8202227408#Penggantian kerangan pangkal | RU3-CDL | FC-D-3/00 | 50 WAMA | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-07-15 | 2102357595 | 8202237604 |  | 8202227405#TGH1_CIV_UP PENGECATAN MA7 | RU4-RFCGTO | 106E501/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-08 |  | 2026-01-02 | 2026-01-02 | 2102355741 | 8202238753 |  | 8202227403#25_Perbaikan ACB 05EE1128B | RU4-UTL | 05EE1128B/00 | 50 | CRTD NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 8400000 | 0 | MA5-LIS |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362989 | 8202234076 |  | 8202227401#20-PSV-003A | RU6-RCC | 20-PSV-003A/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362981 | 8202234080 |  | 8202227400#19-PSV-015A | RU6-RCC | 19-PSV-015A/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362983 | 8202234078 |  | 8202227398#20-E-102A | RU6-RCC | 20-E-102A/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362988 | 8202234079 |  | 8202227397#20-E-101A | RU6-RCC | 20-E-101A/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362984 | 8202234074 |  | 8202227396#20-S-102A | RU6-RCC | 20-S-102A/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362913 | 8202234075 |  | 8202227395#20-R-101 A | RU6-RCC | 20-R-101A/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102357978 | 8202240181 |  | 8202227393#25_Retrofit bearing 021P-105 | RU4-LOC2 | 021P105/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 6928350 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-10 | 2102360095 | 8202237381 |  | 8202227390#Penggantian Valve Hidrolik G- | RU5-UTL | G-32-05A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 733726 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238383 |  | 8202227387#Tag 21 TSA Pemeliharaan Vacuu |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-03 | 2026-03-04 | 2026-02-02 | 2026-12-30 | 2102353754 | 8202237603 |  | 8202227386#Penggantian ban cadangan FT-4 | RU4-WS | FL49/00 | 60 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 7668265 | 6518025 | WS-KAB |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-06-30 |  | 8202237865 |  | 8202227380#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237602 | 8202237513 | 8202227379#TGH33-34_22 Sewa CCTV Tanki 4 | RU4-RFCGTO | 47T511A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 116661000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-10 | 2102363232 | 8202237864 |  | 8202227376#LTSA Boiler Thp 1 | RU6-UTL | 52-B-101C/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-16 | 2102360214 | 8202237383 |  | 8202227375#Penggantian Line SCW RPAL Uta | RU5-UTL | P-7-RPALUTARA/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1776488 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-08-31 | 2026-11-30 | 2102360216 | 8202237384 |  | 8202227373#Penggantian Fuse Knife LV MCC | RU5-UTL | P-30-MC61LAB/00 | 50 | REL CSER GMPS MANC PRC SETC | 5ER | D15/26/B6/RT-C2H | 18795720 | 117000000 | MA3-LIS |  | AGUSHIDAYAT |  | 2026-02-11 | PT02 | 4 | 3 | 2026-08-31 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102363500 | 8202233047 |  | 8202227371#Perbaikan Motor 19-P-109A | RU6-RCC | 19-P-109A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102363491 | 8202233048 |  | 8202227370#Perbaikan Motor 17-P-104B | RU6-RCC | 17-P-104B-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102362633 | 8202233038 |  | 8202227369#Perbaikan Motor 24-E-106 B | RU6-HSC | 24-E-106B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-05-19 | 2102362912 | 8202233058 |  | 8202227368#Perbaikan Motor 15-E-110H | RU6-RCC | 15-E-110H-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1152 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-01-02 | 2026-01-02 | 2102351316 | 8202232472 |  | 8202227362#Packing Seat Gearbox | RU2-HOC | 140-PX-51C/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/NR-D2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-11 | 2102362980 | 8202233487 |  | 8202227361#Penggantian Tali Mooring Rope | RU6-ITP | 43-SPM-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 924 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-06-04 | 2102360210 | 8202237379 |  | 8202227357#MAT.Perb. E-8-03B | RU5-E15112 | E-8-03B/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 151268159 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-11 | 2102363061 | 8202233617 |  | 8202227356#Penggantian kontaktor heater | RU6-UTL | 58-D-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 16104 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102358025 | 8202236437 |  | 8202227354#D25_39PSL251 malfunction | RU4-TRML | 39PSL251/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354118 | 8202240177 |  | 8202227353#25_[CR] Pompa Make Up Chemica | RU4-RFCC | 63-WS0011-32/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-01 | 2025-12-31 | 2102360253 | 8202237378 |  | 8202227352#Perbaikan Motor EM 32 01P | HCC-E5144 |  | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 386 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-20 | 2102362825 | 8202233261 |  | 8202227350#Perbaikan 51-PT-002D | RU6-UTL | 51-PT-002D/00 | 60 | REL MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1128614 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-28 | 2102362985 | 8202233684 |  | 8202227347#Penggantian Bushing Trafo STG | RU6-UTL | 51-PTR-101D/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 20328 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-03 |  | 2025-12-31 | 2025-12-31 | 2102351657 | 8202237468 |  | 8202227342#TSA wrapping roof tank | RU2-ITP | 945-T-20-FA-1/00 | 01 | CRTD NMAT PRC | 2MR | D12/XX/B6/RT-D2NH | 5000000000 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-12-31 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356207 | 8202240173 |  | 8202227339#25_Penggantian LSH Tanki OM 6 | RU4-TRML | 33HS302/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 15 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202237601 | 8202238643 | 8202227338#TGH5_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352519 | 8202234220 |  | 8202227337#Perbaikan Pompa 900-03P-2B WD | RU2S-KIL | 900-03P-2B/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2025-12-08 | 2102362421 | 8202232847 |  | 8202227336#Perbaikan Transmitter 24-PDT- | RU6-HSC | 24-PDT-056/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 141 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354817 | 8202236504 |  | 8202227334#Penggantian Pulley Finfan 101 | RU4-RFCC | 101E532C1/00 | 50 | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-07 | 2102363390 | 8202233340 |  | 8202227333#Perbaikan 15FV800 | RU6-RCC | 15-K-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-04 | 2102351195 | 8202238138 |  | 8202227331#Pemasangan FAS Warehouse & FS | RU2-LAB | 970-FP-LAB-01/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 165292500 | 0 | WS-IN1 |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357454 | 8202240169 |  | 8202227330#25_Mtl. Perbaikan Bocoran 93E | RU4-SRU | 93E405/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 3338964 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2025-12-05 |  | 8202232193 | 8202233906 | 8202227329#Tambahan Matl MOC 1342 | RU6-UTL | 055-A-101-V2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-02-08 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102353902 | 8202238763 |  | 8202227327#25_Penggantian Rly Inc Trf 30 | RU4-TRML | 30EE3101A/00 | 50 | CRTD NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 100000 | 0 | MA3-LIS |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-17 | 2026-04-23 | 2102363097 | 8202232849 |  | 8202227325#Perbaikan Transmitter 20FI054 | RU6-RCC | 20-FT-054/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1024 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-08 | 2102362042 | 8202234095 |  | 8202227324#15-AT-901/902 Perbaikan Analy | RU6-RCC | 15-R-102/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 317888269 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102354569 | 8202240165 |  | 8202227323#25_[CR] Penggantian flexible | RU4-UTL | 52P2B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238375 | 8202234902 | 8202227322#Tag 6 Sipil Area Kilang SG |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-15 | 2026-02-07 | 2026-02-27 |  | 8202238371 | 8202234942 | 8202227321#Tag 14 PM Clean. PreHeater&Re | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-15 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102352919 | 8202234548 |  | 8202227320#N_Penggantian Module PLC ESD | RU3-CDL | EGT-CAB-PLC/00 | 50 WAMA | CRTD CSER MACM PRC | 3IR |  | 0 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-04 | 2026-02-04 |  | 8202238135 | 8202235215 | 8202227319#Tag 11 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-24 | 2026-02-12 | 2026-12-29 | 2102362915 | 8202238023 |  | 8202227317#Retubing 31-E-103A1 & B2 | RU6-HSC | 31-E-103/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C3H | 0 | 0 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355382 | 8202240161 |  | 8202227313#25_Pengadaan Tube Bundle 024E | RU4-LOC2 | 024E103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-01-08 | 2102361822 | 8202232810 |  | 8202227311#Pergantian transmitter 11FT00 | RU6-HSC | 11-FT-002/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 384 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237600 | 8202237496 | 8202227310#TGH6_24 UP Clean SWD Jet Pres | RU4-UTL | 54FIC304/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355271 | 8202240157 |  | 8202227309#25_Mtl. Cleaning Heater 023E- | RU4-LOC2 | 023E105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 84770842 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238117 | 8202235423 | 8202227299#Tag 5 Cleaning Tangki Minyak |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354322 | 8202240153 |  | 8202227298#25_[CR]011K101B cylinder 1 da | RU4-FOC2 | 011K101B/01 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102354237 | 8202240149 |  | 8202227295#25_[CR] Perbaikan Pompa 21P13 | RU4-LOC1 | 21P13B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 189000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102354016 | 8202240145 |  | 8202227294#25_[CR] Perbaikan Pompa 54P1B | RU4-UTL | 54P1B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 1369685463 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354947 | 8202236681 |  | 8202227293#D_25 Fan motor rusak 260E172M | RU4-LOC3 | 260E172M3/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353773 | 8202240141 |  | 8202227291#25_[PV] Penggantian Grease Ge |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102357851 | 8202240098 |  | 8202227290#25_RKAP 2026 RETROFIT LAMPU | RU4-FOC2 | 011E101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-05 | 2026-06-08 | 2026-02-02 | 2026-02-02 | 2102351218 | 8202238666 |  | 8202227289#Long Term Service Agreement ( | RU2-HOC | 140-V-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | NURFADHILLA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102358823 | 8202237373 |  | 8202227288#MAT.GANTI CHECK VALVE POMPA G | RU5-D&W | G-34-91B/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 54238906 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102358825 | 8202237372 |  | 8202227287#MAT.PERB.LINE 947-10" DI JL. | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 103601922 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354536 | 8202240094 |  | 8202227284#25_[CR]014K101F1A Filter Elem | RU4-FOC2 | 014K101F1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 31144216 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-05-19 | 2026-07-17 |  | 8202237363 |  | 8202227283#Rejuvenate DBB Valve Metering | RU5-TBL | METER-4541/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 24840000000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-13 | 2102362987 | 8202233228 |  | 8202227282#Perbaikan bearing motor 61-P- | RU6-HSC | 61-P-301A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 73943 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356561 | 8202240090 |  | 8202227281#25_14TXI530 penunjukan NaN | RU4-FOC1 | 14TXE530/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-21 | 2102362824 | 8202237863 |  | 8202227280#LTSA Cleaning Internal Tangki | RU6-ITP | 42-T-404F/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355166 | 8202240086 |  | 8202227279#25_Control valve 88FV217 dan | RU4-KPC | 88FV212/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-21 | 2102362826 | 8202237862 |  | 8202227278# LTSA Cleaning Internal Tangk | RU6-ITP | 42-T-401A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360259 | 8202237366 |  | 8202227276#PERBAIKAN KABEL POWER MOV 425 | RU5-TBL | PLANT-20-LIS/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-02 | 2102360350 | 8202237364 |  | 8202227275#Perbaikan Power Air Comp. 110 | RU5-UTL | WTP-I-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 651321000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360254 | 8202237370 |  | 8202227274#Penggantian HMI DC Charger AE | RU5-UTL | 41-R-SS-38-LIS/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353051 | 8202234508 |  | 8202227273#N_Perbaikan Flowmeter Pet-Set | RU3-CDGP | CD2-FT-8201/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355696 | 8202240082 |  | 8202227271#25_Mtl. Filter Dust Collector | RU4-FOC2 | 014S111/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354214 | 8202240079 |  | 8202227270#25_Mtl. Ganti Filter Separato | RU4-FOC1 | 11K401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353153 | 8202234558 |  | 8202227269#N_Penggantian Material INT Ba | RU3-PP | 23-ZB-2601Z1/00 | 60 | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102360353 | 8202237368 |  | 8202227268#Perb. Power Supply Modul PLC | RU5-UTL | HHP-6-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 39152500 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353693 | 8202240075 |  | 8202227267#25_Mtl. Ganti Filter Separato | RU4-FOC1 | 11K401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102358826 | 8202237371 |  | 8202227266#MAT.PERB.LINE 968/963-10" MFO | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 105352979 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362876 | 8202233106 |  | 8202227265#Perbaikan Mech Seal 34-P-108 | RU6-POC | 34-P-108B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353158 | 8202234565 |  | 8202227264#N_Penggantian Level Sump Pit | RU3-CDL | 14-XT-501/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362874 | 8202233107 |  | 8202227263#Perbaikan Mech Seal 34-P-108 | RU6-POC | 34-P-108A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-04 | 2102362077 | 8202237861 |  | 8202227262#LTSA Patching, Wrapping Th 9 | RU6-UTL | 55-T-101C/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-19 | 2026-01-01 | 2026-12-30 | 2102353155 | 8202234904 |  | 8202227261#Pengadaan Breaker Feeder Pomp |  |  | 60 | REL CSER GMPS MACM PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 17745000 | 17745000 | MA4-LIS |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362827 | 8202232988 |  | 8202227259#Perbaikan Pompa 15-P-102C | RU6-RCC | 15-P-102C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 741739 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-14 |  | 8202236749 | 8202232770 | 8202227257#SPK 24 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 | 2102360189 | 8202237367 |  | 8202227256#Perbaikan 05-XCV-253C | RU5-E15111 | 05-XCV-253C/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 13500000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-04 | 2026-02-07 | 2026-09-30 | 2026-12-29 | 2102359780 | 8202238188 |  | 8202227255#Peng.Trafo DC Charger 125VDC |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/NR-C3H | 1 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-09-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354665 | 8202240071 |  | 8202227252#25_[CR] 63P1C penggantian cou | RU4-TRML | 63P1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-20 | 2102362726 | 8202237860 |  | 8202227251#lWO Pemb On Call Termin 2 LTS | RU6-RCC | 15-B-101/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-07-17 | 2102362829 | 8202236670 |  | 8202227250#SWO Pemb LTSA CEMS Termin 9 | RU6-RCC | 15-B-101/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354013 | 8202240067 |  | 8202227245#25_[CR] Perbaikan Valve 13K1B | RU4-FOC1 | 13K1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3100000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2026-12-31 | 2026-12-31 | 2102358824 | 8202237369 |  | 8202227243#Penyediaan spare rubber coupl | RU5-UTL | P-12PAMPANCUR/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 28863040 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-31 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102362917 | 8202233236 |  | 8202227242#Perbaikan bearing 34-A-103-P- | RU6-POC | 34-A-103-P-102BM/0 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 147887 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352911 | 8202234982 |  | 8202227241#Pemasangan PV Vent tangki 160 | RU3-ITP | ITP-PVV01-T-160/00 | 50 WAMA | REL NMAT PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-04 |  | 8202233030 |  | 8202227240#Perbaikan motor 57-E-401E | RU6-DHC | 57-E-401E-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353574 | 8202240063 |  | 8202227234#25_[CR] Perbaikan Coupling Ge | RU4-RFCUTL | 154P505A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358111 | 8202240058 |  | 8202227233#25_Penggantian 024PCV222 di 0 | RU4-LOC2 | 024PCV222/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357850 | 8202240054 |  | 8202227230#25_valve drain dan selenoid s | RU4-KPC | 87PSV213/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357489 | 8202240051 |  | 8202227229#25_Mechanical seal 024P-109B | RU4-LOC2 | 024P109B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 66731450 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356418 | 8202240047 |  | 8202227228#25_14TIC543 penunjukan NaN | RU4-FOC1 | 14TV543/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-06-24 | 2102355732 | 8202236393 |  | 8202227227#D25_H2 analyzer 89AI202 | RU4-KPC | 89AT202/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-06-24 | 2102355730 | 8202236394 |  | 8202227226#D25_H2 analyzer 86AI202 | RU4-KPC | 86AT202/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-06-26 | 2102355633 | 8202236395 |  | 8202227225#D25_H2 analyzer 84AI202 | RU4-KPC | 84AT202/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355387 | 8202240043 |  | 8202227224#25_[CR] Penggantian Mechseal | RU4-RFCC | 104P502B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 11442182 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-06-08 | 2102354014 | 8202236355 |  | 8202227220#D25_Penunjukan LI lambat 240L | RU4-LOC3 | 240LI002/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354883 | 8202240039 |  | 8202227219#25_[CR] Perbaikan pompa 13P5A | RU4-FOC1 | 13P5A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 2148236 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-07-10 | 2102358056 | 8202237356 |  | 8202227217#MAT.Perb. Header steam trace | RU5-E15112 | 03-DIV-001/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 6126058 | 0 | MA3-STA |  | BERNANDOP |  | 2026-05-06 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102354882 | 8202240036 |  | 8202227216#25_Perbaikan kopling 12P2A | RU4-FOC1 | 12P2A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-07-10 | 2102360219 | 8202237357 |  | 8202227215#MAT. Perb. Pipa SCW E-35-04A | RU5-E15112 | E-35-04A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 57789252 | 0 | MA3-STA |  | HIMMATUSS |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-11-03 | 2025-11-21 | 2102359696 | 8202237353 |  | 8202227214#Perbaikan Indicator LG Magnet | RU5-E15111 | C-4-01-INST/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 195 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102353907 | 8202240032 |  | 8202227213#25_88P215 Mech seal Rusak | RU4-KPC | 88P215/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 3692998 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237599 | 8202238643 | 8202227212#TGH4_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237598 | 8202238635 | 8202227211#TGH22_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 147651000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102355504 | 8202240028 |  | 8202227206#25_[CR] Penggantian LO Filter | RU4-LOC1 | 24K2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 31144216 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102353576 | 8202241420 |  | 8202227205#25_[CR] Perbaikan mech seal 4 | RU4-TRML | 43P1A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 78240800 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-17 | 2026-04-24 | 2102362910 | 8202233420 |  | 8202227204#Perbaikan 11-AT-002 | RU6-HSC | 11-AT-002/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1024 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352795 | 8202235513 |  | 8202227203#PSV Blower 2300-U5JAM RWC 2 | RU3-UTL | 2300-U5JAM/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-13 | 2102362911 | 8202233643 |  | 8202227202#Penggantian filter LO Purifie | RU6-UTL | UTL-CHEM-BUILD/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 13200 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354880 | 8202240022 |  | 8202227200#25_[CR] Perbaikan kopling 11P | RU4-FOC1 | 11P24B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2102358053 | 8202237351 |  | 8202227199#Perbaikan KK,K-3-02C | RU5-E15112 | KT-3-02C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 577421669 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-04 | 2026-05-04 | 2102360240 | 8202237352 |  | 8202227194#Perbaikan kabel Power EM 31-2 | RU5-E15112 | PLANT-31-LIS/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 160142500 | 0 | MA3-LIS |  | AGUSHIDAYAT |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2025-12-30 | 2026-06-29 | 2102358821 | 8202237355 |  | 8202227192#Penggantian MOV-501 (Plant 19 | RU5-E15111 | PLANT-19-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2305 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237597 | 8202237489 | 8202227191#TGH4_24 UP Perpipaan & Akseso | RU4-UTL | LN52-104VA/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102360256 | 8202237350 |  | 8202227189#Perbaikan Pompa G-3-34C | RU5-E15112 | G-3-34C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 5682000 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352990 | 8202234561 |  | 8202227187#N_Penggantian LV-20231B | RU3-UTL | LT-20231B/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355386 | 8202240019 |  | 8202227186#25_[CR] Penggantian Mechseal | RU4-RFCC | 103P514B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 2760821 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102357399 | 8202240596 |  | 8202227184#25_perbaikan 91E-409B1 | RU4-SRU | 91E409B1M/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 10798760 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102354662 | 8202240593 |  | 8202227181#25_[CR] 51P2AT penggantian sp | RU4-UTL | 51P2A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 94509091 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 |  | 2026-03-05 | 2026-03-05 |  | 8202240590 | 8202241419 | 8202227180#25_[BD] Pompa 63P601A Jammed | RU4-UTL | 63P601A/00 | 50 | CRTD CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 3719000 | 0 | MA5-ROT |  |  |  |  | PT02 |  | 2 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-09 | 2025-12-30 | 2102360217 | 8202237332 |  | 8202227178#Perbaiakan Motor EM 32-01G | RU5-E15112 | EA-32-01O/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1417629 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238365 | 8202235502 | 8202227177#Tagihan Ke- 10 Pekerjaan Sipi | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351830 | 8202232221 |  | 8202227176#Pengadaan Material Alat ICP O | RU2-LAB | LAB-GAS-21/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | WS-IN1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238357 | 8202235314 | 8202227175#Tagihan Ke- 7 Pekerjaan Steam |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352680 | 8202234541 |  | 8202227173#Perbaikan P-1 CDU V | RU3-CDGP | CD5-P-001/00 | 60 | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2025-12-15 | 2025-12-15 |  | 8202237337 | 8202237339 | 8202227172#Main Metal & Brg Large K-19-0 | RU5-E15112 | K-19-01A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2025-12-15 | 2025-12-15 | 2102359266 | 8202237339 |  | 8202227169#K-19-01A Perbaikan | RU5-E15112 | K-19-01A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 4652600 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-23 | 2102358058 | 8202237349 |  | 8202227162#Cleaning Final Condensor SWD |  |  | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 56422658 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-18 | 2102362721 | 8202233694 |  | 8202227161#Penggantian Bearing motor 53- | RU6-UTL | 53-P-101A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 164519 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-18 | 2102362723 | 8202233682 |  | 8202227160#Penggantian cable gland di ew | RU6-ITP | 42-P-930A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 16632 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-15 | 2025-12-30 | 2102360257 | 8202237328 |  | 8202227159#Perbaikan Motor GM 3 49A & GM | RU5-E15112 | GM-3-49D/00 | 60 | CLSD CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 128 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-20 | 2102362427 | 8202233037 |  | 8202227158#Perbaikan Motor 32-K-105 | RU6-HSC | 32-K-105-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-11 | 2102362424 | 8202233198 |  | 8202227157#Perbaikan Control 32-K-102 A | RU6-HSC | 32-K-102A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-20 | 2102362292 | 8202233180 |  | 8202227156#Perbaikan electrical motor 13 | RU6-DHC | 13-HV-302-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-27 | 2102362526 | 8202232853 |  | 8202227155#Perbaikan Trafo Workshop | RU6-HSC | WS-PTR2-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 14242000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102360359 | 8202237330 |  | 8202227154#Perbaikan Kabel Solenoid K-3- | RU5-E15112 | K-3-02C-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 110588000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-05 | 2026-06-09 | 2026-02-05 | 2026-02-05 | 2102364385 | 8202238627 |  | 8202227153#Pengecatan Area HCC | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1500000000 | 0 | MA2-STA |  | AHILMANSYAH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356415 | 8202240586 |  | 8202227152#25_14FI570 penunjukan NaN | RU4-FOC1 | 14FT570/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 18083334 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-06-03 | 2102360351 | 8202237314 |  | 8202227150#MAT.Retubing E-2-09 Unit Baru | RU5-E15112 | E-2-09/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 1046190631 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355179 | 8202236356 |  | 8202227149#D25_penunjukan flow 260FI054 | RU4-KPC | 82FIC205/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102357889 | 8202240584 |  | 8202227148#25_[CR] Penggantian coupling | RU4-LOC1 | 24P13B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357934 | 8202240582 |  | 8202227144#25_solenoid rusak dan valve d | RU4-KPC | 84D251/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 31125004 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354940 | 8202236359 |  | 8202227143#D25_Penunjukan error 200LI051 | RU4-LOC3 | 200LI051/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-23 | 2102360355 | 8202237313 |  | 8202227139#Perbaikan Slip Ring TG 2.2 | RU5-UTL | TG-2-PP2/00 | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 96160952 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362295 | 8202232937 |  | 8202227138#Perbaikan Pompa 64-P-104 A | RU6-HSC | 64-P-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355385 | 8202240580 |  | 8202227131#25_[CR] Penggantian Mechseal | RU4-RFCC | 103P514A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 175383811 | 175383811 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357563 | 8202240578 |  | 8202227130#25_Pulley Finfan Tidak Seimba | RU4-GTO | 120E605A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 4900712 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355503 | 8202236357 |  | 8202227129#D25_Penunjukan error 240LTC05 | RU4-LOC3 | 240LTC057/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354942 | 8202236400 |  | 8202227128#D25_Control valve rusak 240LV | RU4-LOC3 | 240LV057/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238337 | 8202234972 | 8202227127#Tag 1 Pembersihan Ceceran Min |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-03 | 2026-01-01 | 2026-01-01 | 2102351946 | 8202234972 |  | 8202227126#KV Pembersihan Ceceran Minyak |  |  | 60 | REL CNF PRT GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RAMADENY | 2026-06-08 | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-09 | 2102364190 | 8202237309 |  | 8202227123#Perb. MOV Conv. 60/17 Luar Si | RU5-UTL | INT-HHP-BOILER/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 11931000 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102362630 | 8202233560 |  | 8202227120#Penggantian PI range 0-3kg/cm | RU6-UTL | 55-A-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12540 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102359215 | 8202237311 |  | 8202227118#GT-2-03A refurbish rotor | RU5-E15112 | GT-2-03A/00 | 01 | CRTD CSER NMAT PRC | 5RR | D15/10/B6/RT1-02NH | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-25 | 2025-11-25 | 2025-11-25 | 2102351468 | 8202238320 |  | 8202227116#RK0060 KONTRAK ASISTEN PMC | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 303000000 | 0 | MA2-ROT |  | DEDISUKMANA |  | 2026-02-11 | PT02 |  | 3 | 2025-11-25 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356565 | 8202236423 |  | 8202227111#D25_AC Split bocor 200BD2 | RU4-LOC3 | 200BD2/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355638 | 8202236429 |  | 8202227110#D25_85FC210 Mode Auto , Outpu | RU4-KPC | 85FV210/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355175 | 8202236295 |  | 8202227109#D25_swicht power 36P201B berm | RU4-TRML | 36P201B/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102356047 | 8202240576 |  | 8202227108#25_perbaikan mechanical seal | RU4-KPC | 86P203A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 70466667 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352551 | 8202234219 |  | 8202227105#Kebocoran Pipa 8" di Tk 8-Tk | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C3H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-30 | 2102362637 | 8202233015 |  | 8202227103#Perbaikan noise 63-P-202B | RU6-ITP | 63-P-202B-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 12078 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102362638 | 8202233034 |  | 8202227102#Perbaikan motor 42-P-101D | RU6-ITP | 42-P-101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 160295 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-08-10 | 2102362528 | 8202233430 |  | 8202227098#Penyelesaian PM EI MA4 tahun | RU6-ITP | 42-T-101A/00 | 01 | CLSD NCMP NMAT PRC | 6ER | D16/25/B6/RT-C2H | 15840 | 0 | MA4-LIS |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-14 | 2026-02-04 | 2026-07-24 |  | 8202238297 | 8202232753 | 8202227097#Pekerjaan Reaktivasi Load She | RU6-UTL | 51-G-101A-LP/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 115000000 | 0 | MA4-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-21 |  | 8202233779 | 8202232753 | 8202227096#Pengadaan Matl Arrester Load | RU6-UTL | 51-G-101A-LP/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 16896 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-02-02 | 2026-08-07 | 2102362636 | 8202232753 |  | 8202227095#Reaktivasi Load Shedding RU V | RU6-UTL | 51-G-101A-LP/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 15840 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-09 | 2026-02-02 | 2026-02-02 | 2102363591 | 8202232262 |  | 8202227094#Pengadaan Lampu Emergency Are | RU2-HSC | 100-H-1/00 | 50 | CRTD MACM PRC | 2ER | D12/10/B6/RT1-100NH | 501420000 | 0 | MA2-LIS |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-10 | 2026-12-30 | 2026-12-30 | 2102360391 | 8202237307 |  | 8202227093#NRK_Pembelian Motor Baru 5 Un | RU5-UTL | 0PE00D002/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | AGUSHIDAYAT |  | 2026-02-10 | PT02 |  | 3 | 2026-12-30 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352547 | 8202234218 |  | 8202227091#Kerusakan Pipa Outlet Box Coo | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/NRZ-D4H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356411 | 8202240574 |  | 8202227084#25_Transmitter 025FT-013 rusa | RU4-LOC2 | 025FT013/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-03-05 | 2026-03-05 | 2102356203 | 8202240572 |  | 8202227083#25_Pengadaan Process Calibrat | RU4-WS | 037BD101-6795Z2/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-15-C2H | 2 | 0 | WS-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-05 |  | 2026-03-05 | 2026-08-31 |  | 8202240570 | 8202241459 | 8202227077#25_[BK] 84P203B Jammed | RU4-KPC | 84P203B/00 | 50 | CRTD CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102363659 | 8202232395 |  | 8202227076#Perbaikan ATG 920-TK-02 | RU2-UTL | 920-Y-53/00 | 60 | CLSD CNF NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA3-INT |  | SAPBATCH | 2025-12-09 | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-06 |  | 8202236605 | 8202232773 | 8202227074#Tagihan 2 PM MA 1 2025 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 81897534 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-06 |  | 8202236609 | 8202232773 | 8202227073#Tagihan 1 PM MA 1 2025 | RU6-RCC | 15-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 141670501 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102362521 | 8202232773 |  | 8202227072#PM MA 1 2025 | RU6-RCC | 15-R-101/00 | 01 | CRTD CSER NMAT PRC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355511 | 8202240568 |  | 8202227062#25_Perbaikan fin-fan 91E405 | RU4-SRU | 91E405AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-23 | 2102359078 | 8202237303 |  | 8202227061#Perbaikan kabel power motor G | RU5-D&W | GM-201-05A/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 280500000 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352863 | 8202234889 |  | 8202227060#Pengadaan Coupling Rubber 62- | RU3-CDGP | P-62-902B/00 | 50 WAMA | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102358827 | 8202237305 |  | 8202227059#Penggantian RGA Tangki A31 | RU5-TBL | PLANT-20-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1116000000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359073 | 8202237291 |  | 8202227056#Pemasangan Socket Listrik Jet | RU5-TBL | PLANT-22-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 118921000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-03 | 2025-12-05 | 2026-09-11 | 2102362527 | 8202233176 |  | 8202227055#Perbaikan FDF Vane & Turbine | RU6-UTL | 052-B-101B-K-101/0 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 3644767 | 0 | MA4-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-09 | 2102363147 | 8202233800 |  | 8202227049#Pengadaan Level Transmiter 31 | RU6-HSC | 31-LT-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102361989 | 8202233233 |  | 8202227047#Perbaikan Bearing Motor 11-P- | RU6-HSC | 11-P-119A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-05 | 2102361988 | 8202233761 |  | 8202227046#Pengadaan Pompa Sumpit Assy 2 | RU6-HSC | 23-P-901B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-30 | 2026-03-05 | 2026-03-05 | 2102354068 | 8202240566 |  | 8202227045#25_PENGGANTIAN DISPLAY ANALY | RU4-RFCUTL | 152AT002/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 5 | 0 | MA5-INT |  | TYFFANIM |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353573 | 8202240564 |  | 8202227044#25_Penggantian control valve | RU4-RFCUTL | 151TV600/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353831 | 8202240563 |  | 8202227043#25_Penggantian LT sump pit Je |  | 73LT002/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353759 | 8202240562 |  | 8202227042#25_Penggantian LIC sump pit C | RU4-TRML | 72P103B-D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 2 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352864 | 8202235786 |  | 8202227041#engPerbaikan P-62-902B | RU3-CDGP | P-62-902B/00 | 50 WAMA | CRTD CSER MACM PRC | 3RR |  | 0 | 0 | MA1-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353830 | 8202240560 |  | 8202227040#25_Penggantian LIC sump pit C | RU4-TRML | 72P103B-D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 2 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352917 | 8202235236 |  | 8202227039#Perbaikan P-62-906B Pet Set | RU3-CDGP | P-62-906B/00 | 50 WAMA | CRTD CSER MACM PRC | 3RR |  | 0 | 0 | MA1-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358158 | 8202240559 |  | 8202227038#25_PI Discharger Pompa 57P2 T | RU4-UTL | 57P2/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1370895 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102358155 | 8202234725 |  | 8202227037#Pengadaan Material (MOC) Pena | RU4-FOC1 | 16T3/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 57303384 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238358 | 8202235367 | 8202227035#Tag 10 Steam Leak non Trap Ki |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358069 | 8202240558 |  | 8202227034#25_Penggantian 154_AI775C | RU4-RFCUTL | 154XA-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358092 | 8202240557 |  | 8202227033#25_Penggantian 154_AI775B | RU4-RFCUTL | 154XA-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357936 | 8202236361 |  | 8202227032#D25_Penunjukan 84FI362 0 Nm3/ | RU4-KPC | 84FI362/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357659 | 8202236479 |  | 8202227031#D25_ Orifice 88FT242 rembes | RU4-KPC | 88FT242/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357564 | 8202240556 |  | 8202227030#25_14TT567 rusak/fault | RU4-FOC1 | 14TT567/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-08 | 2026-06-02 | 2026-12-30 | 2102357560 | 8202240555 |  | 8202227029#25_Display level 024S-101ABCD | RU4-LOC2 | 024S101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 95860000 | 0 | MA2-INT |  | TYFFANIM |  | 2026-03-10 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357272 | 8202240554 |  | 8202227028#25_018POT101B LT penunjukan N | RU4-FOC2 | 018V101/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102352799 | 8202234570 |  | 8202227027#N_Penggantian Flowcomp Meteri | RU3-ITP | ITP-MS-1000-EQP/00 | 50 WAMA | REL GMPS MACM PRC SETC | 3IR | D13/25/B6/NR-4-C2H | 0 | 181680000 | MA4-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357274 | 8202240552 |  | 8202227026#25_[PV] Perbaikan Pompa 101P5 | RU4-RFCC | 101P523A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 148566500 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-13 | 2102358922 | 8202237296 |  | 8202227022#MAT.MOC(TAMBAH) NO.11114/RUV | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 70641113 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-18 | 2102363172 | 8202233748 |  | 8202227018#Pengadaan Stud Bold PRV 63-RV | RU6-ITP | 63-Z-202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1320 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-11-30 | 2026-12-18 | 2102358828 | 8202237288 |  | 8202227017#Rubber Coupling Degasser Pump | RU5-UTL | 1UA-03-D002/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 5000000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-11-30 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-28 | 2102362523 | 8202237859 |  | 8202227013#Perbaikan Boogey Wheel & grea | RU6-ITP | 41-A-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-07-29 | 2102362522 | 8202238167 |  | 8202227012#Perbaikan DBB Valve metering | RU6-ITP | 42-A-313/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-09 | 2026-06-22 | 2026-03-09 | 2026-12-22 | 2102354670 | 8202241419 |  | 8202227009#25_[CR] Perbaikan pompa 53P20 | RU4-UTL | 53P201/00 | 50 | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 3248291 | 0 | MA5-ROT |  | SAMSUDINH |  | 2026-06-22 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-13 | 2102359433 | 8202237294 |  | 8202227007#MAT.PERB.LINE 8" OUTLET TANK | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 642168990 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362299 | 8202232971 |  | 8202227006#Perbaikan Pompa 31-P-107 A | RU6-HSC | 31-P-107A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 83804000 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-10-26 |  | 8202237596 | 8202238642 | 8202227005#TGH2_24 TSA Online Analyzer T | RU4-RFCC | 102FT049/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-28 | 2102362425 | 8202237858 |  | 8202227000#LTSA Scaffolding 2024-2026 Ta | RU6-RCC | 16-E-116A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237595 | 8202238641 | 8202226999#TGH8_22 TSA FGDS Gastron RFCC | RU4-RFCC | 102TG005/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237593 | 8202238640 | 8202226998#TGH4_24 PM Field Instrument M | RU4-KPC | 80FT205/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362428 | 8202233743 |  | 8202226995#Pengadaan Valve Suction 33-P- | RU6-HSC | 33-P-108A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352539 | 8202234217 |  | 8202226994#Pembuatan Pondasi Pompa 946-P | RU2S-KIL | 946-P-8B/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352560 | 8202234216 |  | 8202226992#Kebocoran Pipa Crude Oil 18'' | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/NRZ-D2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359499 | 8202237287 |  | 8202226991# M Pompa RWP Polisher demin 5 |  |  | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 10000000 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-23 | 2102359189 | 8202237284 |  | 8202226990#MAT.PERB.LINE COOLING WATER D | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 359772430 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-29 |  | 8202237591 | 8202237482 | 8202226984#Pasang MCC & power 47P507C | LOC1-UP4 | 47P507A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/NR-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102353816 | 8202240551 |  | 8202226983#25_[CR] Penggantian panel con | RU4-TRML | 63P2BD/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-04 | 2102359139 | 8202237282 |  | 8202226981#Penggantian Meter Kerja MS Bu | RU5-TBL | 22-716B/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 59400002 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355777 | 8202236545 |  | 8202226980#Penggantian Motor Pompa 71P10 | RU4-TRML | 71P10AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2026-12-01 | 2026-12-30 | 1102327457 | 8202237280 |  | 8202226979#Perb Sensor EE Bearing Temp 1 | RU5-TBL | 101-GT-01A-INST/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 97500000 | 97500000 | MA4-INT |  | SAPBATCH | 2026-03-13 | 2026-02-11 | PT02 | 8 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357887 | 8202240550 |  | 8202226965#25_Perbaikan 14TXI561 | RU4-FOC1 | 14TXT561/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359218 | 8202237271 |  | 8202226964#Perbaikan T-BFW 12 | RU5-UTL | T-BFW-P-0101B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 47361000 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-03 | 2026-11-24 | 2102359195 | 8202237273 |  | 8202226963#Perbaikan pompa G-202-08B | RU5-D&W | G-202-08B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1430999 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359072 | 8202237275 |  | 8202226962#Pengadaan Spare Parts K-3-02C | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 267746974 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359133 | 8202237272 |  | 8202226961#Perbaikan pompa G-3-19D | RU5-E15112 | G-3-19D/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 3390000 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238342 | 8202235085 | 8202226960#Tag 6 Isolasi Panas Area CD&G |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352993 | 8202234520 |  | 8202226957#N_Penggantian Temperatur Cont | RU3-PP | 23-K-2203/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-05 | 2026-02-22 | 2026-01-13 | 2026-12-29 | 2102362971 | 8202238657 |  | 8202226955#Perbaikan Pompa 56-P-101ABD | RU6-UTL | 56-P-101A/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C1H | 38900000 | 0 | MA4-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357884 | 8202240549 |  | 8202226952#25_[CR] Pompa 140P601A Noise | RU4-GTO | 140P601A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 7714200 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-01-13 | 2102361895 | 8202232852 |  | 8202226949#Perbaikan transmiter 13-LT-22 | RU6-DHC | 13-LT-228/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 256 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-31 | 2102363286 | 8202233251 |  | 8202226948#Perbaikan 58-D-101C | RU6-UTL | 58-D-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-11 | 2102361894 | 8202233376 |  | 8202226947#Perbaikan 13-FT-760 | RU6-DHC | 13-FT-760/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-18 | 2102361899 | 8202233187 |  | 8202226946#Perbaikan Controller 13-PDIC- | RU6-DHC | 13-PDC-929/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353692 | 8202240548 |  | 8202226945#25_[CR] 012E102K04 Belt rusak | RU4-FOC2 | 012E102K04/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 1275000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353691 | 8202240546 |  | 8202226944#25_[CR] 012E102K01 Belt rusak | RU4-FOC2 | 012E102K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 1275000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-14 | 2026-04-14 | 2026-11-23 | 2102362423 | 8202232933 |  | 8202226937#Perbaikan Pompa Jockey 66-P-1 | RU6-UTL | 66-P-102/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 1522032 | 1502232 | MA4-ROT |  | DANDARWANI |  | 2026-04-14 | PT02 |  | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102352899 | 8202240544 |  | 8202226935#25_Ganti Check Valve Dryer IA | RU4-RFCUTL | 156A501A-V1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 14608440 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-19 | 2026-12-30 | 2026-12-30 | 2102358923 | 8202237274 |  | 8202226931#Pengg.Lampu penerangan diarea | RU5-UTL | WTP-I-LIS/00 | 60 | REL CSER MSPT PRC SETC | 5ER | D15/26/B6/RT-C2H | 155720741 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-11 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353684 | 8202240543 |  | 8202226930#25_011P123BM ampere lokal rus | RU4-FOC2 | 011P123BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-11 | 2026-02-03 | 2026-02-03 | 2102357019 | 8202235120 |  | 8202226929#RKAP2026_Penggantian Pilot 10 | RU4-RFCC | 101F504/00 | 60 | TECO CNF CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH | 2026-05-11 | 2026-02-07 | PT02 |  | 3 | 2026-05-11 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353683 | 8202240541 |  | 8202226928#25_011P123AM ampere lokal rus | RU4-FOC2 | 011P123AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102357017 | 8202234894 |  | 8202226927#RAKP2026_Penggantian Pilot DF | RU4-RFCC | 101F501/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358098 | 8202240540 |  | 8202226922#25_Perbaikan 56AT1 Dew Point | RU4-UTL | 56PSV005/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 5 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-04-14 | 2102359079 | 8202237264 |  | 8202226921#MAT. Perb. Check Valve G-35-1 |  | G-35-02C/01 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 13000000 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102358937 | 8202237262 |  | 8202226920#Perbaikan IHLA Tanki V16, V17 | D&W-E5110 | V-16/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 3 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-12 | 2025-12-29 | 2102358857 | 8202237260 |  | 8202226919#Perbaikan motor GM 3 33C | RU5-E15112 | GM-3-33C/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 370985 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-24 | 2025-12-24 | 2102358920 | 8202237253 |  | 8202226917#PM Pompa P17 WTP | RU5-UTL | P-17-WTP/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 4494720 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-26 | 2102358854 | 8202237255 |  | 8202226916#Perbaikan Transmitter 19-FT-5 | RU5-E15112 | 19-FIT-518/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 28611990 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2026-12-28 | 2026-12-28 | 2102358859 | 8202237268 |  | 8202226915#Coupling Pompa 11 WTP 1 | RU5-UTL | P-11PAMPANCUR/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 28496040 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2026-12-28 | 2026-12-28 | 2102358921 | 8202237267 |  | 8202226914#Coupling Pompa 9 WTP 1 | RU5-UTL | P-9PAMPANCUR/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 28688640 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2026-12-28 | 2026-12-28 | 2102358858 | 8202237270 |  | 8202226913#Coupling Pompa 10 rusak | RU5-UTL | P-10PAMPANCUR/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 28496040 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2102358855 | 8202237258 |  | 8202226912#Perbaikan pompa G-34-113 A | RU5-D&W | G-34-113A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 1911934 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-05 | 2102362074 | 8202237857 |  | 8202226910#LTSA Pengosongan Tngki Thp 4 | RU6-ITP | 42-T-104A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-08 | 2026-04-20 | 2026-01-02 | 2027-01-21 |  | 8202238762 | 8202238767 | 8202226909#25_[CR] Perbaikan Pompa 054P1 | RU4-UTL | 054P101A/00 | 50 | CRTD NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 100000 | 0 | MA5-ROT |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-04 | 2102362190 | 8202237856 |  | 8202226908#LTSA Maintenance Bawah Air Th | RU6-ITP | 41-A-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-08-18 | 2102354216 | 8202241418 |  | 8202226906#25_[CR] Perbaikan pompa 21P-3 | RU4-LOC1 | 21P3/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 98520266 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355518 | 8202240539 |  | 8202226904#25_94E403 B, Penggantian gear | RU4-SRU | 94E403BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-04 | 2102362075 | 8202236684 |  | 8202226903#SPKR LTSA N2 Tahap 11 (COC 13 | RU6-DHC | 13-R-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-04 | 2102362194 | 8202236727 |  | 8202226902#SPK LTSA N2 Tahap 10 (22-R-10 | RU6-DHC | 22-R-102A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102363050 | 8202237855 |  | 8202226901#Per.Gen. Steam Turbin 56-P-10 | RU6-UTL | 56-P-101H-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353811 | 8202237230 |  | 8202226900#CM_Kerusakan Coating Piping 1 | RU4-GTO | 105-PL0130-8/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-07-22 | 2102362420 | 8202238328 |  | 8202226895#Amandemen 33-PG-1801-R1A1-3" | RU6-HSC | 33-C-104/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 196520000 | 0 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352938 | 8202234872 |  | 8202226892#Pompa 2434 JA Netral Basin De | RU3-UTL | 2434-JA/00 | 01 | CRTD CSER MACM PRC | 3RR |  | 0 | 0 | MA2-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354306 | 8202240538 |  | 8202226891#25_Penggantian kabel LCS |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358110 | 8202240527 |  | 8202226887#25_Transmitter 024FT-011 rusa | RU4-LOC2 | 024FT011/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 21345221 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362296 | 8202233909 |  | 8202226886#Matrial valve gasoline transf | RU6-ITP | 42-PIPE/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358006 | 8202237589 |  | 8202226884#TGH1_25 Instalasi dan Konfi D | RU4-FOC2 | DCS-FOC2/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354909 | 8202240526 |  | 8202226883#25_CM_Kebocoran Valve MPC BL | RU4-GTO | 107-MPC0001-6/00 | 50 WAMA | REL CSER GMCO GMPS MANC PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 22645990 | 22012896 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353838 | 8202240525 |  | 8202226880#25_Perbaikan Level Transmitte | RU4-FOC1 | 14V623B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102356056 | 8202240524 |  | 8202226879#25_[CR] Perbaikan FIn Fan 23E | RU4-LOC1 | 23E4K-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360969 | 8202236380 |  | 8202226875#D25_Pembacaan HS emergency tr | RU4-LOC2 | 021F101/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355127 | 8202236421 |  | 8202226874#D25_Belum ada Cover di Push B |  |  | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355162 | 8202240523 |  | 8202226873#25_[CR] Perbaikan 12K1C Flow | RU4-FOC1 | 12K1C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 83430000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353694 | 8202235801 |  | 8202226872#Perbaikan motor 22P-4AM | RU4-LOC1 | 22P4AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238016 | 8202234515 | 8202226871#Tag 9 Pemeliharaan Fire Extin | RU3-LKKK |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-04 | 2026-06-04 | 2026-12-29 | 2026-12-29 | 2102351697 | 8202238327 |  | 8202226870#Permintaan Perbaikan Wrapping | RU2-HCC | 0-75FG21122A1A1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 100000000 | 0 | MA2-STA |  | NURFADHILLA |  | 2026-03-25 | PT02 |  | 3 | 2026-12-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355153 | 8202240522 |  | 8202226866#25_[CR] Perbaikan Pompa 46P2 | RU4-TRML | 46P2AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-28 | 2025-11-28 | 2102354062 | 8202236415 |  | 8202226864#D25_CM Leak Tubing Regulator | RU4-GTO | 140PSV010BA/00 | 60 | REL CNF NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH | 2026-04-16 | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353839 | 8202240521 |  | 8202226863#25_Perbaikan 14XV561 | RU4-FOC1 | 14XV561/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 148500000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-04 | 2026-02-04 |  | 8202238122 | 8202234916 | 8202226859#Tag 16 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238325 | 8202235145 | 8202226857#Tag 14 PM/PDM Cleaning Cooler | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238130 | 8202234824 | 8202226856#Tag 20 Cleaning Underground S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358152 | 8202240520 |  | 8202226853#25_Manifold 84PDT343 rusak | RU4-FOC2 | 80OS302/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102358151 | 8202240519 |  | 8202226852#25_Pengadaan Rotameter Worksh | RU4-WS | 037BD101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-15-C2H | 10 | 0 | WS-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-11 | 2026-01-02 | 2026-01-02 | 2102352561 | 8202234215 |  | 8202226849#Kebocoran Pipa Kerosene 10" d | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-D3H | 97005854 | 1352734 | MAS-ME2 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353642 | 8202236496 |  | 8202226848#Penggantian pulley motor 94E4 | RU4-SRU | 94E403BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-23 | 2026-12-07 | 2102359132 | 8202237244 |  | 8202226847#Perbaikan Heat Exchanger E-20 | RU5-D&W | E-201-22B/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-23 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353606 | 8202236501 |  | 8202226846#Penggantian pulley motor 91E4 | RU4-SRU | 91E404AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-07-28 |  | 8202237852 | 8202233981 | 8202226845#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | ES-B14-01/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353641 | 8202237331 |  | 8202226843#92E409, Penggantian pulley mo | RU4-SRU | 92E409AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-30 | 2102362197 | 8202232859 |  | 8202226841#Perbaikan Trafo 14A-PTR1-01B | RU6-RCC | 14A-PTR1-01B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 28484000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353640 | 8202237333 |  | 8202226840#92E407, Penggantian pulley mo | RU4-SRU | 92E407A1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-23 | 2026-12-07 | 2102359131 | 8202237245 |  | 8202226839#Perbaikan Heat Exchanger E-20 | RU5-D&W | E-201-22A/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-23 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353643 | 8202240518 |  | 8202226838#5E401, Penggantian pulley | RU4-SRU | 95E401A1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K202 | 2026-02-02 | 2026-03-06 | 2026-01-02 | 2026-01-02 | 2102352538 | 8202234214 |  | 8202226837#LTSA FGDS DAN IHLA IRKAP 2025 | RU2S-LKKK | 946-OPGD-03R/00 | 50 | REL GMPS NMAT PRC SETC | 2ES | D12/26/B6/NRZ-C2H | 1000000000 | 114457000 | MAS-INT |  | JUNAIDIT |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353609 | 8202237340 |  | 8202226836#91E409, penggantian pulley | RU4-SRU | 91E409B1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353608 | 8202237341 |  | 8202226835#91E408, Penggantian pulley mo | RU4-SRU | 91E408B1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351658 | 8202232506 |  | 8202226834#Perbaikan 110 EM-12A | RU2-HOC | 110-EM-12A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 445000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353607 | 8202240517 |  | 8202226832#25_Penggantian pulley motor 9 | RU4-SRU | 91E405AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353605 | 8202237342 |  | 8202226831#91E-402, penggantian pulley | RU4-SRU | 91E402BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362580 | 8202233317 |  | 8202226830#Perbaikan 19-P-101A | RU6-RCC | 19-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-21 | 2026-01-02 | 2026-01-02 | 2102352688 | 8202238157 |  | 8202226829#Penyusunan Corrosion Control | RU3-CDGP |  | 50 | REL GMPS NMAT PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 606400000 | 212240000 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-08-03 | 2102362297 | 8202238311 |  | 8202226827#Pekerjaan Repair & Rewinding | RU6-RCC | 20-P-103A-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102351019 | 8202232537 |  | 8202226825#Mechseal pompa rusak | RU2-HCC | 300-P-81/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354219 | 8202240516 |  | 8202226824#25_[PV] PM 560K601A | RU4-UTL | 560K601A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 53933334 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102359438 | 8202237243 |  | 8202226823#Perbaikan Pompa G-8-01B | RU5-E15112 | G-8-01B/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102354300 | 8202240514 |  | 8202226822#25_[PV] PM 560K601B | RU4-UTL | 560K601B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 53933334 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-29 | 2102359268 | 8202237247 |  | 8202226817#Perbaikan Control Valve 04-PC | RU5-E15111 | 04-PCV-179/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 312623010 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-28 | 2102359210 | 8202237248 |  | 8202226815#Pengadaan O-ring BFW 3 | RU5-UTL | 2RL-20-D001/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 4700000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-10 | 2102359190 | 8202237236 |  | 8202226814#Perbaikan pompa G-201-05A | RU5-D&W | G-201-05A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 13000000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-07-20 | 2026-12-08 | 2102359137 | 8202237234 |  | 8202226813#Perbaikan pompa G-201-08B | RU5-D&W | G-201-08B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 93387498 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-07-20 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2025-12-05 | 2026-04-28 | 2102362196 | 8202238309 |  | 8202226803#Retrofit Relay Protection Gen | RU6-UTL | 51-G-101D/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/NR-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238307 | 8202235092 | 8202226802#Tag 4 Supporting Teknisi dan | RU3-WS | BEN-TOOL/00 | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-05-19 | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-03-10 | 2026-02-02 | 2026-08-26 | 2102363054 | 8202233815 |  | 8202226801#Pengadaan Flowmeter MOC1989 F | RU6-ITP | 42-T-203B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 580017160 | 580000000 | MA4-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-02 | 2026-03-05 | 2026-03-05 | 2102352898 | 8202240513 |  | 8202226796#25_[CR] Perbaikan Mechseal 10 | RU4-RFCC | 102P503A/00 | 60 | CLSD CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | LUQMANULH |  | 2026-03-10 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-06-08 | 2026-07-08 |  | 8202237241 | 8202238853 | 8202226795#Bearing FDF HHP 1 | RU5-UTL | T-FDF-31-01/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 29209980 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353904 | 8202240511 |  | 8202226794#25_[CR] Perbaikan Turbin 530P | RU4-UTL | 530P601A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-05 | 2026-05-25 | 2026-01-02 | 2026-01-02 | 2102351085 | 8202238673 |  | 8202226792#RK0061 LTSA LIGHTING SYSTEM & | RU2-HSC | 100-PM-6A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 700000000 | 0 | MA2-LIS |  | DEDISUKMANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102357178 | 8202237588 |  | 8202226791#Perbaikan PC IPAL | RU4-SRU | 90-DCS1-SRU/00 | 50 | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 770000000 | 0 | MA1-INT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2025-10-30 | 2026-06-29 | 2102360227 | 8202237239 |  | 8202226787#Penggantian MOV inlet & Outle | RU5-TBL | 21-MOV-107/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 3074 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102359592 | 8202237238 |  | 8202226786#Perbaikan Display Temp. ACW K | RU5-E15112 | K-3-02A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2025-12-23 | 2025-12-30 | 2102359136 | 8202237237 |  | 8202226785#Perbaikan EM-1-28B | RU5-E15111 | EM-1-28B/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 727542 | 0 | MA2-LIS |  | SAPBATCH | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-15 | 2025-12-15 | 2102359217 | 8202237240 |  | 8202226784#Pekerjaan PM. Rotating Equipm | RU5-TBL | P-20RP-A-HITAM/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 890905617 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102359314 | 8202237222 |  | 8202226783#Perbaikan Motor EM 32 01Q | RU5-E15112 |  | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 256883 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102357140 | 8202237587 |  | 8202226781#TGH1-3_24 TSA AC Split di Are | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362071 | 8202234053 |  | 8202226780#33-P-108A | RU6-HSC | 33-P-108A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-11 | 2026-02-02 | 2026-07-31 | 2102361987 | 8202232932 |  | 8202226779#Perbaikan Pompa spare 32A101- | RU6-HSC | 32-A-101-P1A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6RR | D16/25/B6/RT-C2H | 31000000 | 0 | MA3-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354631 | 8202240508 |  | 8202226777#25_[CR] Perbaikan Pompa Well | RU4-TRML | 30P107A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 3054452 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-03 | 2102359199 | 8202237218 |  | 8202226770#Perbaikan Transmitter 04-FT-1 | RU5-E15111 | 04-FT-115/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 63000000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-04 |  | 8202237850 |  | 8202226768#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353903 | 8202240505 |  | 8202226765#25_Mech Seal Pompa bocor besa | LOC1-UP4 | 47S506A-P5/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-04 | 2102359493 | 8202237225 |  | 8202226763#Penggantian CT&Hub Coup. moto | RU5-E15112 | GM-3-01A/00 | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 66656671 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-07-02 | 2102359260 | 8202237232 |  | 8202226761#Peng. contactor thermal motor |  |  | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 24864004 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-27 | 2102359431 | 8202237226 |  | 8202226758#Pengadaan Sparepart Non OEM K | RU5-E15112 | K-3-02B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 136213461 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353905 | 8202240502 |  | 8202226757#[CR] Perbaikan Pompa 54P5B Le | RU4-UTL | 54P5B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 6300000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355067 | 8202240498 |  | 8202226754#25_[CR] 014K102C high tempera | RU4-FOC2 | 014K102C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 82262440 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355066 | 8202240493 |  | 8202226753#25_[CR] 014K102A high temp 2n | RU4-FOC2 | 014K102A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 443422360 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102359216 | 8202237233 |  | 8202226752#Penambahan Panel Power AC Gd. | RU5-E15500 | KAN-FS-LL/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 7316000 | 0 | GM-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238306 | 8202235423 | 8202226751#Tag 4 Cleaning Tangki Minyak |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-04 |  | 2026-06-30 | 2026-12-29 | 2102358936 | 8202238166 |  | 8202226750#NRK_Peng. Relay Proteksi B12& | RU5-UTL | 41-R-SS-66-LIS/00 | 01 | CRTD NMAT PRC | 5ER | D15/25/B6/RT-C2H | 5000000 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-06-30 | PM |  | 005
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238367 | 8202234997 | 8202226748#Tag 9 KV Penyediaan Jasa Hose |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238363 | 8202234623 | 8202226747#Tag 3 KV Isolasi Area PP |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K202 | 2026-02-02 | 2026-04-23 | 2026-01-02 | 2026-11-30 | 2102352537 | 8202234213 |  | 8202226742#KEBOCORAN MECH SEAL 946-P-1B | RU2S-KIL | 946-P-1B/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 391642675 | 102597886 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352545 | 8202234212 |  | 8202226739#Perbaikan FinFan CDU Pasca Pl | RU2S-KIL | 101-E-6A-FF/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102359371 | 8202237224 |  | 8202226738#perbaikan Cylinder 6 K-3-02C | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 254891896 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359370 | 8202237223 |  | 8202226737#Perbaikan Kompresor K-3-02B | RU5-E15112 | K-3-02B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 1143419380 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354673 | 8202236541 |  | 8202226736#Penggantian motor pompa 71P2- | RU4-TRML | 71P2AM/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2025-12-16 | 2025-12-16 | 2102359196 | 8202237207 |  | 8202226729#Perbaikan Mech Seal G-5-02A | RU5-E15111 | G-5-02A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 2521519 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355196 | 8202240489 |  | 8202226728#25_Dew Point Analyzer Dryer I | RU4-RFCC | 156-IA0001-4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 4 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354211 | 8202240485 |  | 8202226727#25_Transmiter 041FT-314 rusak |  | 041FT314/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354560 | 8202240481 |  | 8202226718#25_[CR] 012E102K02 belt rusak | RU4-FOC2 | 012E102K02/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 1275000 | 1275000 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351693 | 8202232673 |  | 8202226717#VIBRASI MOTOR 220 PM-1B | RU2-HOC | 220-PM-1B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/NR-D2H | 2407738 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102353756 | 8202237586 |  | 8202226715#TGH6_24 Monitoring Peralatan | RU4-RFCC | 101FT-U101/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-08-05 |  | 8202237849 | 8202233853 | 8202226712#Pemb. LTSA Slide Valve Unit R | RU6-RCC | 15-SLV-105/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237585 | 8202238640 | 8202226711#TGH2_24 PM Field Instrument M | RU4-KPC | 80FT205/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353525 | 8202240477 |  | 8202226710#25_[CR] 011E110K40 Blade,hub& | RU4-FOC2 | 011E110K38/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 243125956 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-15 | 2026-12-15 | 2102359212 | 8202237208 |  | 8202226706#K-3-02C : Valve Stage 3 (Bran | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-04 | 2102362072 | 8202233891 |  | 8202226702#Notifikasi Perbaikan Pompa 63 | RU6-ITP | 63-P-110A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 15312 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102353490 | 8202237584 |  | 8202226701#Pemeliharaan Rotating Equipme | RU4-LOC1 | 22K1/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102359193 | 8202237192 |  | 8202226700#Perbaikan GM-35-03B |  |  | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 105741 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355068 | 8202240473 |  | 8202226697#25_[CR] 018K101B low flow | RU4-FOC2 | 018K101B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 49323634 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355160 | 8202235471 |  | 8202226694#Perbaikan Press Gauge Purging | RU4-RFCC | 101A513/00 | 50 WENG | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-05-25 |  | 8202238354 | 8202235565 | 8202226693#Tag. 15 Operator & Pem. Alat | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-25 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-02 | 2102362379 | 8202237848 |  | 8202226690#23-P-201 A | RU6-HSC | 23-P-201A/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-26 | 2102363369 | 8202237847 |  | 8202226688#LTSA PM Tahap 8 | RU6-UTL | 056-P-101B-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-05-19 |  | 8202238351 | 8202234908 | 8202226687#Tag 24 Pemeliharaan Sepeda Ki | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-19 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360528 | 8202237206 |  | 8202226685#Penggantian Low Cap Charger S | RU5-UTL | S-WAIN-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 4000002 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-05 |  | 8202236638 | 8202233851 | 8202226680#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102359194 | 8202237196 |  | 8202226679#Penggantian Pulley Em-2-12E | RU5-E15112 | EM-2-12A/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 16450000 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-02-02 | 2102362208 | 8202233860 |  | 8202226676#Pemb. LTSA 14 Unit Lab | RU6-LAB | LABORATORIUM/00 | 01 | CLSD CSER NCMP NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-04 | 2102359437 | 8202237180 |  | 8202226675#Perbaikan Online Analyzer RU | RU5-E15111 | 05-AIT-120/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 194800000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-26 | 2102363368 | 8202237846 |  | 8202226674#LTSA PM Tahap 6 | RU6-UTL | 51-P-101D-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-26 | 2102363366 | 8202237845 |  | 8202226673#LTSA PM Tahap 5 | RU6-UTL | 52-P-103B-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-11 | 2102363360 | 8202237844 |  | 8202226671#LTSA PM Tahap 4 | RU6-UTL | 58-K-101C-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-26 | 2102363367 | 8202237843 |  | 8202226670#LTSA PM Tahap 3 | RU6-UTL | 51-P-101A-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-22 | 2102362831 | 8202233677 |  | 8202226669#Penggantian Contactor Droper | RU6-HSC | 01A-PBC3-01C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1800 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-19 | 2025-12-08 | 2026-12-29 | 2102354565 | 8202237583 |  | 8202226668#pemasangan penerangan impound | RU4-RFCUTL | 166M512BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238350 | 8202235105 | 8202226661#Tag 4 Mekanik CDL, OM, UTL SG |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-21 | 2102362733 | 8202233071 |  | 8202226659#Perbaikan motor 11-E-112 B | RU6-HSC | 11-E-112B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 1102328106 | 8202237194 |  | 8202226657#Perbaikan Diff. Press. Switch | RU5-TBL | 101-GT-01A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-08-13 | 2102361896 | 8202238338 |  | 8202226656#Repair & Rewinding Motor 42-P | RU6-ITP | 42-P-404D-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102360344 | 8202237204 |  | 8202226654#Penggantian PowerSupply STG 2 |  |  | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 64459200 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-04-28 | 2025-12-08 | 2026-12-29 | 2102354674 | 8202237582 |  | 8202226651#Perbaikan MOV area OM 60 & NB | RU4-TRML | POSITIONER-U041/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 1 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357083 | 8202240469 |  | 8202226649#25_Perbaikan 180TI641 A/B | RU4-GTO | 180TI641A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 2 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352931 | 8202234552 |  | 8202226648#N_Penggantian Module AO PLC R | RU3-CDL | FLRS-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/NR-5-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-31 | 2025-12-29 | 2025-12-29 | 2102359928 | 8202237168 |  | 8202226640#GANTI CAMLOCK & BFLY VALVE SP | RU5-TBL | PIPE-ON-SHORE/00 | 60 | CLSD CNF MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 557735384 | 0 | MA4-STA |  | SAPBATCH | 2026-04-01 | 2026-02-11 | PT02 |  | 3 | 2026-04-01 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2102359211 | 8202237166 |  | 8202226627#Perbaikan Bearing Rusak EA-1- | RU5-E15111 | EA-1-24B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 19060642 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102354845 | 8202237581 |  | 8202226625#TGH1_CIV_UP INSULASI EQUIPMEN | RU4-FOC2 | 018K101A/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354108 | 8202240464 |  | 8202226624#25_Pompa 93P-403B ( Gland Sea | RU4-SRU | 93P403B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-02-18 | 2026-02-18 | 2102359261 | 8202237164 |  | 8202226622#Perbaikan pompa P-2B CPI DHP | RU5-D&W | P-2B-CPI/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 18573311 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363284 | 8202233634 |  | 8202226621#Penggantian Gasket Casing 14- | RU6-DHC | 14-P-106A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238118 | 8202235423 | 8202226618#Tag 3 Cleaning Tanki Minyak R |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202236753 | 8202235502 | 8202226617#Tagihan Ke- 9 Pekerjaan Sipil | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-09 | 2102359265 | 8202237165 |  | 8202226615#Perbaikan Motor GM 3 16A | RU5-E15112 | GM-3-16A/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 2 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356451 | 8202236829 |  | 8202226612#Penggantian foam maker tanki | RU4-K3LL | FT27/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-08 | 2026-12-08 | 2102359319 | 8202237167 |  | 8202226609#K-3-02B: Upgrade Valve Kompre | RU5-E15112 | K-3-02B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-01 | 2102362017 | 8202233381 |  | 8202226607#Perbaikan 12-PTR1-501C | RU6-DHC | 12-PTR1-501C/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 142420000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-06-15 | 2026-06-30 | 2102359219 | 8202237169 |  | 8202226606#Filter lube oil STG 1.5 | RU5-UTL | TG-5A-OIL-FLTR/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/NR-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355245 | 8202240461 |  | 8202226604#25_[CR] 011K101BP2 membran ko | RU4-FOC2 | 011K101B-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102353577 | 8202240458 |  | 8202226552#25_[CR] Penggantian Coupling | RU4-UTL | 53P1A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 58562000 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354076 | 8202240455 |  | 8202226551#25_CM_Steam Trap 140ST6001 Ma | RU4-GTO | 140FV017/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 390000000 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102354399 | 8202234735 |  | 8202226549#RK25_Rejuvenate isolasi equip | RU4-RFCC | 101-ATM0006-28/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102355774 | 8202240452 |  | 8202226529#[CR] PerbaikanTurbin 52P2AT | RU4-UTL | 52P2A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355698 | 8202240449 |  | 8202226526#25_[CR] 017E105K17 Blade, Brg | RU4-FOC2 | 017E105K17/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 321495068 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-11-27 | 2102363451 | 8202238669 |  | 8202226525#Repair & Rewinding Motor 12-K | RU6-DHC | 12-K-501A/00 | 50 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 005
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-02-02 | 2102362040 | 8202233861 |  | 8202226522#Pemb. LTSA 11-AT-401 CEMS | RU6-HSC | 11-AT-401/00 | 01 | CLSD CSER NCMP NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357210 | 8202240446 |  | 8202226521#25_91V-403 Penambahan control | RU4-SRU | 91V403/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 11899341 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-08 | 2102359782 | 8202237160 |  | 8202226520#Perbaikan Transmitter 02-LT-1 | RU5-E15112 | 02-LT-146/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 60276986 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-04 | 2026-08-20 | 2102354342 | 8202238104 |  | 8202226518#Refurbishment Mech seal 23P-1 | RU4-LOC1 | 23P14/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 87079000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353524 | 8202240444 |  | 8202226517#25_MOC 0168 line flushing 47T | RU4-RFCGTO | 47T511A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 1990139 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351742 | 8202232714 |  | 8202226516#Service Switching Valve 140-V | RU2-HOC | 140-V-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352916 | 8202235613 |  | 8202226514#Coupling Failure P-61-252B | RU3-UTL | P-61-252B/00 | 50 WAMA | REL CSER MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-11 |  | 2025-12-08 | 2025-12-08 |  | 8202238853 |  | 8202226512#HVOF Shaft FDF Turbine Boiler | RU5-UTL | T-FDF-31-01/00 | 01 | CRTD NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 53000000 | 0 | WS-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102359691 | 8202237161 |  | 8202226510#Penggantian Gland Kabel ATG A | RU5-D&W | 13-LT-D20-05D/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 10506949 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2026-12-30 | 2026-12-30 | 2102359649 | 8202237158 |  | 8202226506#Valve kompressor K-201-01 | RU5-D&W | K-201-01/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-07 | PT02 |  | 3 | 2026-04-24 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359761 | 8202237163 |  | 8202226505#Gland packing P7 RPAL Rusak | RU5-UTL | P-7-RPALUTARA/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 5000000 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-20 | 2102362756 | 8202233611 |  | 8202226501#Penggantian lampu padam area | RU6-ITP | 42-T-505A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 16896 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-07-01 | 2102363494 | 8202233337 |  | 8202226500#Perbaikan 16-E-117 AB | RU6-RCC | 16-E-117AB-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1536 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-08-12 | 2102362963 | 8202233070 |  | 8202226498#Perbaikan Motor 11-E-112 C | RU6-HSC | 11-E-112C-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357082 | 8202240442 |  | 8202226497#25_Penggantian Pressure Gauge | RU4-GTO | 180PI636A/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2406896 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2025-10-27 | 2026-01-22 | 2102358845 | 8202237156 |  | 8202226494#Perbaikan Control Valve 8A/B- | RU5-E15112 | 08B-FCV-105/00 | 60 | TECO CNF NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 768 | 0 | MA3-INT |  | SAPBATCH | 2026-05-18 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353570 | 8202240440 |  | 8202226491#25_022PV-003 stuck max 40% | RU4-LOC2 | 022PV003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-12-11 | 2026-12-11 | 2102359629 | 8202237153 |  | 8202226490#Pergerakan Abnormal LA No.1 J | RU5-TBL | L-ARM-1-JT-3/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352912 | 8202234878 |  | 8202226489#Pengadaan Material Cat | RU3-LKKK |  | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-08-11 |  | 8202236756 | 8202232770 | 8202226488#SPK 20 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360019 | 8202237157 |  | 8202226486#PERB.LINE DRAIN SUCTION POMPA | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 5675385 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351807 | 8202232261 |  | 8202226485#Perbaikan Level Displacer 100 | RU2-HSC | 100-LT-102/00 | 01 | CRTD CSER MACM PRC | 2IR | D12/XX/B6/RT-D2NH | 0 | 0 | MA2-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102355513 | 8202240438 |  | 8202226483#25_91E408, perbaikan fin-fan | RU4-SRU | 91E408/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 18296354 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357297 | 8202235474 |  | 8202226482#Perbaikan power motor 72P-102 | RU4-TRML | 30P104AM-CB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353973 | 8202236293 |  | 8202226480#D25_Thermocouple 140TI068E Re | RU4-GTO | 140TE068E/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102354102 | 8202240436 |  | 8202226479#25_[CR] 260P104B Check valve | RU4-LOC3 | 260P104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353972 | 8202236291 |  | 8202226478#D25_Transmitter 120TI042 Rusa | RU4-GTO | 120TE042/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102352542 | 8202238335 |  | 8202226477#Dokumen Izin Lingkungan | RU2S-LKKK |  | 50 | CRTD NMAT PRC SETC | 2MS | D12/25/B6/NRZ-D2H | 1 | 0 | MAS-ME2 |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-08-20 | 2102354588 | 8202237580 |  | 8202226476#Tagihan Pek. Refurb Mechseal | RU4-RFCC | 101P502A/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 322293000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-02-18 | 2102354601 | 8202237579 |  | 8202226475#Tagihan Pek. Refurb Mechseal | RU4-RFCC | 101P502A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 214862000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-08-20 | 2102354608 | 8202237576 |  | 8202226474#Tagihan Pek. Refurbish Mechse | RU4-RFCC | 101P522B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 48389000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-08-20 | 2102354605 | 8202237574 |  | 8202226473#Tagihan Pek. Refurbish Mechse | RU4-RFCC | 101P522A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 47382000 | 0 | WS-PMP |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354046 | 8202240434 |  | 8202226471#25_041FT714 penunjukan semu | RU4-TRML | 041FT714/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-08 | 2026-02-27 | 2026-02-26 | 2026-12-30 | 2102353575 | 8202238752 |  | 8202226469#25_Perbaikan server DCS LOC I | RU4-LOC3 | 200CSL7/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-02-27 | PT02 |  | 3 | 2026-02-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102359494 | 8202237147 |  | 8202226467#Perbaikan motor gm-34-56 | RU5-E15112 | GM-34-56/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 3311376 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-12 | 2026-03-04 | 2026-03-06 | 2102360465 | 8202237151 |  | 8202226466#GANTI BFLY VALVE SPM 150.000 | RU5-TBL | PIPE-ON-SHORE/00 | 60 | CLSD CNF CSER PRC SETC | 5MR | D15/25/B6/RT-C2H | 77735384 | 0 | MA4-STA |  | SAPBATCH | 2026-03-13 | 2026-02-11 | PT02 |  | 3 | 2026-03-13 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-02 | 2102363438 | 8202233148 |  | 8202226465#Perbaikan JB Lampu All Area O | RU6-ITP | 42-T-101A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1496821 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102359491 | 8202237150 |  | 8202226464#Perb Elmot Booster Pump No. 2 | RU5-UTL | BOOSTER-PUMP-2/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2226950 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-04-22 | 2026-12-22 | 2026-12-30 | 2102359312 | 8202237145 |  | 8202226463#Pergantian Lampu TL area Perk | RU5-TBL | PLANT-22-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 12530500 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-11 | PT02 | 8 | 3 | 2026-12-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-09 | 2102360171 | 8202237148 |  | 8202226462#Perb. Pompa Booster No. 1&2 W | RU5-UTL | BOOSTER-PUMP-1/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 6424844 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-03-12 | 2026-02-02 | 2026-02-02 | 2102351177 | 8202232501 |  | 8202226458#Perbaikan 110 PM 1 B | RU2-ITP | 110-PM-1B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/25/B6/NR-D2H | 3123106 | 3123106 | MA4-LIS |  | AZIZFATONI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-10 | 2102363459 | 8202232888 |  | 8202226450#Perbaikan selenoid clarifier | RU6-UTL | 53-XV-506E/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 13200 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-04 | 2102359311 | 8202237146 |  | 8202226449#Perbaikan PI Range 60 Kg/sqcm | RU5-E15111 | G-1-35B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 11670000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102356302 | 8202240432 |  | 8202226448#25_[CR] Perbaikan 24K2P1A-T | RU4-LOC1 | 24K2P1A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 22141649 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-02-05 | 2102363434 | 8202232811 |  | 8202226447#Pergantian Press Gauge 23-P-1 | RU6-HSC | 23-P-101A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 640 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-05-08 | 2102362927 | 8202234113 |  | 8202226446# Penggantian Pressure Gauge 2 | RU6-HSC | 24-P-302B/00 | 01 | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-17 | 2026-05-11 | 2102362585 | 8202233423 |  | 8202226445#Perbaikan Pressure Gauge 11- | RU6-HSC | 11-P-101B/01 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360025 | 8202237144 |  | 8202226444#MAT.PERB.PIPING FOAM&COOL TAN | RU5-E15500 | FOAM-CMBR/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 570157009 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354346 | 8202240430 |  | 8202226442#25_Penggantian FSL Pompa 71P2 | RU4-TRML | 71P2B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 28000000 | 72000000 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354268 | 8202240428 |  | 8202226441#25_Penggantian 011FT052 | RU4-FOC2 | 011FT052/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 21345221 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-10-29 | 2025-12-24 | 2102359269 | 8202237143 |  | 8202226440#Penggantian Kabel Power & Sig | RU5-D&W | 13-LT-D20-05D/00 | 60 | TECO CNF GMPS MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 577610668 | 88020000 | MA4-INT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354266 | 8202240425 |  | 8202226439#25_Penggantian 011FT025D4 | RU4-FOC2 | 011FT025D4/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102360499 | 8202240422 |  | 8202226438#25_Penggantian Connector Tubi | RU4-GTO |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 37648488 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102354585 | 8202240398 |  | 8202226437#25_[CR] Perbaikan Linkage Soo | RU4-RFCC | 101F503/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 168486 | 168486 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 1102328035 | 8202237139 |  | 8202226436#Perbaikan motor Eam-201-01F | RU5-D&W | EAM-201-01F/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 1102328034 | 8202237141 |  | 8202226435#Perbaikan motor Eam-201-01A | RU5-D&W | EAM-201-01A/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 761275 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353507 | 8202240395 |  | 8202226433#25_Refill Stock Gasket Cover | RU4-GTO | 140D601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 35000000 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-11 | 2026-02-03 | 2026-03-25 | 2102359317 | 8202237142 |  | 8202226432#Perbaikan Level Switch P-2 A/ | RU5-E15112 | DHP-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 118034051 | 0 | MA2-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-11 | 2102363476 | 8202233091 |  | 8202226430#Perbaikan Mech. Seal Pompa 11 | RU6-HSC | 11-P-111B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355008 | 8202240392 |  | 8202226428#25_[PV] Penyehatan RWI 63P601 | RU4-UTL | 63P601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238324 | 8202234832 | 8202226426#Tag 19 Sarana Tambat Kapal Su |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238129 | 8202234832 | 8202226425#Tag 18 Sarana Tambat Kapal Su |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-04 | 2102359046 | 8202237138 |  | 8202226420#Perbaikan Speed Sensor 101-PT | RU5-TBL | 101-PT-01A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 43200000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-29 | 2102355944 | 8202240389 |  | 8202226416#25_Pengadaan QCV MAB 101K501 | RU4-RFCC | 101K501/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | FATAHALFI |  | 2026-03-10 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-09-14 | 2102354843 | 8202237573 |  | 8202226412#TGH2_24Modifikasi Ln. Recycle | RU4-TRML | LN04-3002N/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102354931 | 8202240386 |  | 8202226408#25_[CR] Baut central flange 0 | RU4-LOC2 | 024S101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 15916667 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355681 | 8202240383 |  | 8202226407#25_[CR] 011E110K38 Bearing de | RU4-FOC2 | 011E110K38/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 14324716 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354899 | 8202240380 |  | 8202226406#25_[PV] Kompresor 022K-101 kn | RU4-LOC2 | 022K101/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-05 | 2102359315 | 8202237135 |  | 8202226400#Perbaikan HMI GM-32-05C | RU5-UTL | GM-32-05C/00 | 50 | REL CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353685 | 8202240377 |  | 8202226399#25_[CR] 017E105K03 Bearing de | RU4-FOC2 | 017E105K05/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 14007883 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2026-10-27 | 2026-10-27 | 2102359642 | 8202237137 |  | 8202226391#G-19-03A | RU5-E15112 | G-19-03A/00 | 60 | TECO CNF CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-25 | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-14 | 2102362814 | 8202236694 |  | 8202226388#SPK1 Unitprice OH & Rewinding | RU6-UTL | 58-K-101A-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238316 | 8302403326 | 8202226385#Tag 8 Sewa Beli Wheel Loader | RU3-WS | BEN-TOOL/00 | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238313 | 8302404176 | 8202226384#Tag 8 Pemeliharaan Mini Excav | RU3-LKKK | LK-CT155/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238312 | 8202235438 | 8202226383#Tag 5 KV Cleaning Minyak Bera |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-15 | 2026-02-02 | 2026-02-27 |  | 8202238299 | 8202234942 | 8202226382#Tag 13 PM Clean. PreHeater&Re | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-15 | PM |  | 045
| K301 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238625 | 8202235291 | 8202226381#Tag 5 Mekanik Area Selatan OM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-09 |  | 2025-12-04 | 2025-12-04 |  | 8202241490 |  | 8202226372#[BD] Pompa 63P601A Jammed | RU4-UTL | 63P601A/00 | 01 | CRTD NMAT PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 1260000000 | 0 | MA5-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-04 | PM |  | 003
| K201 | 2026-02-05 | 2026-02-07 | 2026-02-06 | 2026-02-06 | 2102351050 | 8202238665 |  | 8202226371#Perbaikan Bocoran CFE 200-E-1 | RU2-HSC | 200-E-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 100000000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-06-04 | 2102362289 | 8202233894 |  | 8202226370#Notifikasi perbaikan 63-P-110 | RU6-ITP | 63-P-110A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 004
| K501 | 2026-02-04 |  | 2026-01-19 | 2027-01-29 | 2102359278 | 8202238052 |  | 8202226369#Pembuatan Water Pond Area New | RU5-E15500 | KAN-FS-LL/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-K3NH | 1 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-19 | PM |  | 001
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363453 | 8202232747 |  | 8202226368#Repair Kebocoran line LSL | RU6-POC | 61-P-303A/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-04 |  | 2026-01-07 | 2027-01-20 |  | 8202238051 |  | 8202226367#Revitalisasi Sarfas Fire Grou | RU5-E15500 | KAN-FS-LL/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-K3NH | 1 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-01-07 | PM |  | 001
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-08 | 2025-12-08 | 2102359377 | 8202237131 |  | 8202226364#P16 WTP 1 vibrasi tinggi |  |  | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 87187320 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-11 | 2026-03-05 | 2026-03-05 | 2102353604 | 8202240375 |  | 8202226363#25_Perbaikan blade 91E402 | RU4-SRU | 91E402/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 22011364 | 0 | MA1-ROT |  | ABDULFM |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238632 |  | 8202226361#Tag 20 TSA Pemeliharaan Vacuu | RU3-ITP | 039-P-007/00 | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-04 | 2026-05-25 |  | 8202238126 | 8202235565 | 8202226360#Tag. 14 Operator & Pem. Alat | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-25 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-04 | 2026-05-25 |  | 8202238110 | 8202235565 | 8202226359#Tag. 13 Operator & Pem. Alat | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-25 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238134 | 8202234824 | 8202226358#Tag 19 Cleaning Underground S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238630 | 8202235085 | 8202226357#Tag 5 Isolasi Panas Area CD&G |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-06 | 2026-02-06 | 2102354292 | 8202238672 |  | 8202226356#Sewa Elevator Temporary 1 Cab | RU4-RFCC | 102A502-1B-MCC/00 | 50 | CRTD NMAT PRC | 4ER |  | 50000000 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355280 | 8202240372 |  | 8202226354#25_[CR] Mechanical seal 023P- | RU4-LOC2 | 023P105A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356157 | 8202240369 |  | 8202226353#25_Ganti Bypass Check Valve 1 | RU4-RFCC | 101P523C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 004
| K601 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-11-09 | 2102363433 | 8202238668 |  | 8202226352#Permintaan tenaga aneka ragam | RU6-DHC | 12-R-101/00 | 01 | CRTD NMAT PRC | 6MO |  | 300000001 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 004
| K601 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-11-09 | 2102363436 | 8202238667 |  | 8202226351#Permintaan tenaga aneka ragam | RU6-DHC | 12-R-101/00 | 50 WAMA | CRTD NMAT PRC | 6MO |  | 300000001 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-04 | 2102360341 | 8202237124 |  | 8202226350#Perbaikan Temp. Transmitter B | RU5-D&W | 201-TT-031/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 114106340 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-08 | 2026-12-21 | 2026-12-21 | 2102359430 | 8202237133 |  | 8202226345#K-19-01B | RU5-E15112 | K-19-01B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 910553894 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-21 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-08-14 | 2102362759 | 8202238291 |  | 8202226341#PENYEHATAN 63-Z-305 A/B EWTP | RU6-ITP | 63-Z-305A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 215000000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K701 | 2026-02-02 | 2026-05-07 | 2026-02-02 | 2026-02-02 | 2102358531 | 8202234588 |  | 8202226338#Line Disch Flare 1-PF-182-A1 |  |  | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-03-08 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2025-11-21 | 2026-09-25 | 2102362757 | 8202238290 |  | 8202226337#perbaikan tangga concrete bun | RU6-ITP | 42-T-103A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 237650000 | 202002500 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-11-21 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357155 | 8202240366 |  | 8202226336#25_Perbaikan Passive Filter V | RU4-RFCC | 102E518AM2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-14 | 2026-03-03 | 2026-03-03 | 2102351111 | 8202232365 |  | 8202226332#Low performance 550-P-02 | RU2-UTL | 550-P-02/00 | 50 | REL GMPS MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 766500000 | MA3-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-15 | 2026-02-02 | 2026-08-13 | 2102363187 | 8202232777 |  | 8202226331#PM Electrical dan Instrument | RU6-DHC | SS-12/00 | 01 | CLSD CSER NCMP NMAT PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353868 | 8202240363 |  | 8202226329#25_260ROV-002 indikasi semu c | RU4-LOC3 | 260HS012B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355002 | 8202240360 |  | 8202226328#25_220PDI401 penunjukan hunti | RU4-LOC3 | 220PDT401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355286 | 8202240357 |  | 8202226322#25_166 P 562A pompa rusak tid | RU4-RFCGTO | 166P562A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 13361750 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355284 | 8202240355 |  | 8202226321#25_166 P 561A, pompa tidak bi | RU4-RFCGTO | 166P561A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 13361750 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102363432 | 8202233744 |  | 8202226320#pengadaan tube glass 19-LG-02 | RU6-RCC | 19-V-109/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102360029 | 8202237117 |  | 8202226317#MAT.PERB.PIPING FOAM&COOL TAN | RU5-TBL | 101-5-T-01B/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 715362949 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-19 | 2102362362 | 8202237842 |  | 8202226316#LTSA Online Leak Sealing Taha | RU6-HSC | 11-E-114B/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354847 | 8202240352 |  | 8202226314#25_Flame 120F601 C Tidak Terd | RU4-GTO | 120LCPSF6011/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 2 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363398 | 8202233945 |  | 8202226309#Material Butterfly valve 32-A | RU6-HSC | 32-A-101-E4/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-24 | 2102363391 | 8202237841 |  | 8202226308#LTSA Scaffolding 2024-2026 Ta | RU6-HSC | 24-E-107/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-20 | 2102363220 | 8202237840 |  | 8202226307#LTSA Scaffolding 2024-2026 ta | RU6-DHC | 12-E-111/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-16 | 2026-04-16 | 2026-08-18 | 2102362931 | 8202234094 |  | 8202226306#15-K-103 Tambahan Material pe | RU6-RCC | 15-K-103/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6IR | D16/26/B6/RT-C2H | 28800000 | 7200000 | MA1-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-16 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351921 | 8202232571 |  | 8202226305#Penggantian Coupling 100-P-7 | RU2-HSC | 100-P-7/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-20 | 2025-11-20 | 2102351357 | 8202232374 |  | 8202226303#Perbaikan Control Valve | RU2-HSC | 300-TV-46/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363174 | 8202234105 |  | 8202226302#11-P-114 A | RU6-HSC | 11-P-114A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357095 | 8202240350 |  | 8202226298#25_[CR] 013K101BP1 MLOP Low P | RU4-FOC2 | 013K101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 11977768 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-04 | 2026-03-03 | 2026-02-03 | 2026-08-19 | 2102363362 | 8202238288 |  | 8202226296#Perbaikan Pondasi 17-V-101, 1 | RU6-RCC | 17-V-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/NR-C2H | 458000000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-03-03 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-06 | 2102355893 | 8202240348 |  | 8202226294#25_Service Mixer 041T-122 | RU4-TRML | 041M122M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-02-25 | 2102360466 | 8202237119 |  | 8202226286#MAT.Perb. line MP Steam Jl.10 | RU5-D&W | OC-104/00 | 50 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2773014 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-07-03 | 2026-07-03 | 2102359304 | 8202237114 |  | 8202226285#NEUTRALIZATION PUMP DEMIN-5 | RU5-UTL | DM-5-P13/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2026-12-01 | 2026-12-01 | 2102359561 | 8202237123 |  | 8202226284#Impeller blower FDF turb Boil |  |  | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3832220 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-01 | PM |  | 045
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358530 | 8202234553 |  | 8202226278#Cleaning HE 2-e-01 a,b,c | RU7-NHT | 2-E-01A/00 | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-2-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356058 | 8202240346 |  | 8202226276#25_Penggantian Flow Transmitt | RU4-LOC1 | 24FT038/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 19250000 | 18950000 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-02 | 2026-02-03 | 2026-02-25 | 2102359565 | 8202237108 |  | 8202226275#PERB.LINE L221-12" KERO KEPAL | RU5-TBL | DER-JT-5-ABC/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 83783429 | 0 | MA4-STA |  | OCTARIOHS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356394 | 8202240344 |  | 8202226273#25_Kerusakan pada 85FT210 | RU4-KPC | 85FT210/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355970 | 8202240342 |  | 8202226272#25_Penggantian Level Transmit | RU4-RFCC | 101LT206/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355947 | 8202240340 |  | 8202226271#25_Pengadaan Material Hot Spa | RU4-RFCC | 101K501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 103526010 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102363222 | 8202233837 |  | 8202226270#Pengadaan 19-PSV-014B | RU6-RCC | 19-P-110B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355745 | 8202240338 |  | 8202226267#25_Perbaikan Transmitter 101P | RU4-RFCC | 101PT214/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355743 | 8202240336 |  | 8202226266#25_Perbaikan Temperatur Gauge | RU4-RFCC | 101P523C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-11 | 2025-12-11 | 2102359566 | 8202237111 |  | 8202226265#PERB.LINE 20" CRUDE BELAKANG | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-12-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355655 | 8202240334 |  | 8202226264#25_Perbaikan Level Transmitte | RU4-RFCC | 101LT-U101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 114700625 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-25 | 2102359569 | 8202237109 |  | 8202226262#PERB.LINE 960 & 962 - 10" MFO | RU5-TBL | DER-JT-5-ABC/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 54581513 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-08 | 2026-04-27 | 2026-02-09 | 2027-02-26 | 2102355609 | 8202238751 |  | 8202226261#25_Perbaikan Blower Workshop- | RU4-WS | 037BD101-6795Z2/00 | 50 | CRTD CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-15-C2H | 100000 | 0 | WS-TLS |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-02-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102357295 | 8202240332 |  | 8202226260#25_260P155A mech seal bocor | RU4-LOC3 | 260P155A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 58905000 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-19 | 2026-12-30 | 2026-12-30 | 2102360179 | 8202237106 |  | 8202226256#PERBAIKAN KONTROL LAMPU AREA | RU5-UTL | WTP-I-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 18555000 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-11 | PT02 | 8 | 3 | 2026-12-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-19 | 2026-12-30 | 2026-12-30 | 2102359560 | 8202237112 |  | 8202226255#PenggantTimer lampu Peneranga | RU5-UTL | WTP-I-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 18555000 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-11 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102360443 | 8202237107 |  | 8202226253#Perbaikan FGDS Tangki Balikpa | RU5-E15112 | 019-GC-001A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 13 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-21 |  | 8202236750 | 8202232770 | 8202226252#SPK 23 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360925 | 8202235099 |  | 8202226251#Scrapper RWC 1 Plaju | RU3-UTL | 2200-U1G1/00 | 60 | REL CSER MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102356897 | 8202240330 |  | 8202226250#25_[CR] Perbaikan pompa bocor | RU4-LOC3 | 260P104A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 12701044 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-08-26 |  | 8202237570 | 8202238635 | 8202226249#TGH21_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 158547000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102356867 | 8202237568 |  | 8202226248#TGH2_24 UP Cleaning Tanki LOC | RU4-LOC1 | 40LTW03/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356461 | 8202240328 |  | 8202226246#25_[CR] 011P117A Vibrasi ting | RU4-FOC2 | 011P117A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 42750000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354029 | 8202240325 |  | 8202226244#25_Pengadaan Bearing Workshop | RU4-WS | 037BD101/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-15-C2H | 0 | 0 | WS-TLS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-19 | 2025-12-19 | 2102359567 | 8202237113 |  | 8202226243#Booster pump no.1 WTP gn.4 vi | RU5-UTL | BOOSTER-PUMP-1/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 697345 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-08-21 |  | 8202236665 | 8202233968 | 8202226242#SWO Pemb. LTSA AC Termin 12 | RU6-RCC | SHELTER-PEM1/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102362965 | 8202233784 |  | 8202226241#Pengadaan Material PRV 63-RV- | RU6-ITP | 63-Z-202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12540 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357039 | 8202240322 |  | 8202226238#25_Penggantian Solenoid SOV 5 | RU4-UTL | 56PSV016/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 7 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356792 | 8202240319 |  | 8202226237#25_Transmitter 105LT600 Rusak | RU4-RFCGTO | 105LT600/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-09 | 2026-04-07 | 2026-04-29 | 2102356699 | 8202240316 |  | 8202226234#25_Penggantian pressure gauge | RU4-LOC1 | 21J1A/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 52041378 | 32650078 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356392 | 8202240313 |  | 8202226232#25_Penggantian Flow Transmitt | RU4-LOC1 | 21FT021/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356390 | 8202240310 |  | 8202226231#25_Penggantian Flow Transmitt | RU4-LOC1 | 21FT020/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356052 | 8202240307 |  | 8202226230#25_Penggantian Flow Transmitt | RU4-LOC1 | 22FT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356050 | 8202240303 |  | 8202226229#25_Penggantian Flow Transmitt | RU4-LOC1 | 21FT048/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355978 | 8202240299 |  | 8202226227#25_Penggantian Flow Transmitt | RU4-LOC1 | 21FT047/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102356790 | 8202240295 |  | 8202226226#25_[CR] 014K102B-P2 coupling | RU4-FOC2 | 014K102B-P2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 901200 | 901200 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355976 | 8202240291 |  | 8202226225#25_Penggantian Flow Transmitt | RU4-LOC1 | 21FT046/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355974 | 8202240288 |  | 8202226223#25_Penggantian Flow Transmitt | RU4-LOC1 | 21FT045/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355861 | 8202240284 |  | 8202226219#25_Penggantian Card Prover Me | RU4-TRML | PI-U70/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-08-24 |  | 8202237839 | 8202233981 | 8202226218#LTSA PLC/MMS Tagihan TKDN Tah | RU6-RCC | ES-B14-01/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-27 | 2026-01-02 | 2026-12-30 | 2102352554 | 8202234211 |  | 8202226215#Sertifikasi dan Resertifikasi | RU2S-KIL | 101-H-1/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 800000000 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102352555 | 8202234210 |  | 8202226214#KONFIRMASI D-S TK-F132, TK-F1 | RU2S-KIL | 946-FI-501/00 | 60 | REL GMPS NMAT PRC SETC | 2ES | D12/25/B6/NRZ-C2H | 202500000 | 202500000 | MAS-INT |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356793 | 8202240281 |  | 8202226208#25_[CR] Penggantian Belt 11E- | RU4-FOC1 | 11E54AM-CB/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 2300000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-08-26 | 2102353207 | 8202237566 |  | 8202226199#Tgh Termin 2 UP Perb Bordes & | RU4-TRML | LN70-1001LB/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102356465 | 8202234562 |  | 8202226189#Pengadaan Motor 101P521BM | RU4-RFCC | 101P521BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2102359930 | 8202237105 |  | 8202226186#Penggantian Isolator Terminal | RU5-TBL | P-A2-HITAM/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 6626250 | 0 | MA4-LIS |  | ILHAMNAHRU |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352557 | 8202234209 |  | 8202226184#Perbaikan Kebocoran Casing Po | RU2S-KIL | 101-P-6B/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-02-03 | 2026-04-02 | 2102359999 | 8202237104 |  | 8202226183#Perb Motor Fire Monitor No.4 | RU5-E15500 | JT2-WFM-1200-03/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 1 | 0 | HSSE |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-04-02 | 2102360016 | 8202237103 |  | 8202226182#Perbaikan FSS & FAS Power Pla | RU5-TBL | AF-11/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 11 | 0 | HSSE |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-06 | 2102363304 | 8202233770 |  | 8202226181#Pengadaan motor baru 19-P-102 | RU6-RCC | 19-P-102B-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-07-10 | 2102354557 | 8202236062 |  | 8202226177#Interkoneksi Suction 43T001 t | RU4-TRML | 35T2/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-31 | 2102363364 | 8202233754 |  | 8202226174#Pengadaan Rotor Spare FDF 52- | RU6-UTL | 52-B-101C-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-30 | 2102362777 | 8202233115 |  | 8202226170#Perbaikan Line MakeUp Caustic | RU6-UTL | 055-A-101-V4/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 11880 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238287 | 8302404176 | 8202226169#Tag 7 Pemeliharaan Mini Excav | RU3-LKKK | LK-CT155/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2025-12-31 | 2025-12-31 | 2102352936 | 8202234575 |  | 8202226167#N_Penggantian Fan Motor HVAC | RU3-UTL | SS16-PL/00 | 50 WAMA | REL GMPS MACM PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 322200000 | MA1-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-03-04 | 2102362929 | 8202233906 |  | 8202226165#MOC Injeksi Caustic #055 | RU6-UTL | 055-A-101-V2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 1152 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353861 | 8202236736 |  | 8202226160#D_25 017E105M 2 motor noise | RU4-FOC2 | 017E105M02/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-17 | 2102362378 | 8202237838 |  | 8202226155#Per. Gen. Steam Turbin 11-P-1 | RU6-HSC | 11-P-104A-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102359599 | 8202237101 |  | 8202226153#Perbaikan motor P9 WTP 1 | RU5-UTL | P-9-WTP/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 993600 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-04 | 2026-11-30 | 2026-12-23 | 2102359562 | 8202237102 |  | 8202226152#Perbaikan G-201-12A | RU5-D&W | G-201-12A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 49000000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2025-12-29 | 2025-12-29 | 2102359648 | 8202237076 |  | 8202226150#Perbaikan Motor Gm-3-13A | RU5-E15112 | GM-3-13A/00 | 60 | CLSD CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102359361 | 8202237077 |  | 8202226149#Perb. Motor GM34-93B Sump pum | RU5-TBL | GM-34-93B/00 | 60 | TECO CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH | 2026-06-09 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-30 | 2025-12-30 | 2102359646 | 8202237054 |  | 8202226147#PM Rutin G-220-01D | RU5-TBL | G-220-01D/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 30466666 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-09-30 | 2026-09-30 | 2102359644 | 8202237056 |  | 8202226146#PM Rutin G-220-01B | RU5-TBL | G-220-01B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-09-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-06-30 | 2026-06-30 | 2102359645 | 8202237055 |  | 8202226145#PM Rutin G-220-01C | RU5-TBL | G-220-01C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 73768612 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-06-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-31 | 2025-12-31 | 2102359643 | 8202237059 |  | 8202226144#PM Rutin G-220-01A | RU5-TBL | G-220-01A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 73217400 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2025-12-24 | 2025-12-24 | 2102359641 | 8202237075 |  | 8202226142#Penggantian MS dan Bearing G- | RU5-E15111 | G-1-06C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 4494288 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359694 | 8202237062 |  | 8202226141#Perbaikan pump no.1 STG 2.4 | RU5-UTL | 4RM-01-D001/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 26136366 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359695 | 8202237063 |  | 8202226140#Perbaikan Pump No 2 STG 2.4 | RU5-UTL | 4RM-02-D001/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 26231760 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-27 | 2026-10-27 | 2102359693 | 8202237060 |  | 8202226139#perbaikan T-FDF-31-01 | RU5-UTL | T-FDF-31-01/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-27 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102357290 | 8202240278 |  | 8202226132#25_[CR] Penggantian shim coup | RU4-LOC1 | 21P3A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 13801693 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 1102329133 | 8202232600 |  | 8202226131#Penggantian 1 Unit Pompa | RU2-HSC | 301-ONP-2A/00 | 50 | REL MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 0 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2102359699 | 8202237043 |  | 8202226129#Perbaikan Pompa G-19-02A | RU5-E15112 | G-19-02A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 1317042 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238377 | 8202235105 | 8202226127#Tag 3 Mekanik CDL, OM, UTL SG |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238372 | 8202235367 | 8202226126#Tag 9 Steam Leak non Trap Kil |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238366 | 8202235367 | 8202226125#Tag 8 Steam Leak non Trap Kil |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-24 | 2025-12-24 | 2102359698 | 8202237052 |  | 8202226122#penggantian bearing dan V bel | RU5-E15112 | EA-3-03-BB/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 12741068 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-04 | 2026-02-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238359 | 8202235291 | 8202226118#Tag 4 Mekanik Area Selatan OM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238347 | 8202235291 | 8202226117#Tag 3 Mekanik Area Selatan OM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238333 | 8202235291 | 8202226116#Tag 2 Mekanik Area Selatan OM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238322 | 8202235291 | 8202226115#Tag 1 Mekanik Area Selatan OM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352932 | 8202235253 |  | 8202226114#Kontrak Volume Mekanik Area S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-27 | 2102363365 | 8202236600 |  | 8202226113#Tagihan TKDN Tahap 6 | RU6-ITP | 42-LT-001/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238308 | 8202235151 | 8202226112#Tagihan Ke- 14 Pekerjaan Clea | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238294 | 8202235314 | 8202226110#Tagihan Ke- 6 Pekerjaan Steam |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238284 | 8202235085 | 8202226109#Tagihan Ke- 6 Pekerjaan Isola |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-01 | 2102363249 | 8202237836 |  | 8202226108#LTSA sweepblasting tahap 2 | RU6-UTL | 52-B-101A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-10-13 | 2102355040 | 8202241417 |  | 8202226107#25_[CR] Perbaikan pompa 71P3B | RU4-TRML | 71P3B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 49400000 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 | 2102353842 | 8202234895 |  | 8202226106#Penambahan VSD 14E6B | RU4-FOC1 | 14E6BM/00 | 50 WENG | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | BANYUPUTEWA |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-08-27 | 2102362899 | 8202237835 |  | 8202226105#Pemeriksaan pipa stream feed | RU6-HSC | 31-C-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 455000000 | 455000000 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354416 | 8202234727 |  | 8202226104#Pengadaan Lampu Penerangan RF | RU4-RFCUTL | 30BD12EE0102A/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA5-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353802 | 8202235815 |  | 8202226102#Perbaikan motor 21P-16A | RU4-LOC1 | 21P16AM/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353765 | 8202235837 |  | 8202226101#Perbaikan Module SCR 104E511 | RU4-RFCC | 104E511/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353675 | 8202236023 |  | 8202226100#Perbaikan Genset 30 DEG 101 3 | RU4-FOC2 | 001SS11AH1-CB/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-08 |  | 2026-01-02 | 2027-01-21 | 2102353803 | 8202238750 |  | 8202226099#25_Perb Ctrl ATS dan Pnl DEG3 | RU4-TRML | 30EE3106A/00 | 50 | CRTD NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 13750000 | 0 | MA3-LIS |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-05-07 | 2025-12-08 | 2026-12-29 | 2102353676 | 8202237564 |  | 8202226098#Perbaikan Batt Charger 30SS31 | RU4-FOC2 | 001SS11AH1-CB/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 1 | 0 | MA2-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 | 2102356863 | 8202235748 |  | 8202226097#Perbaikan Motor Mixer 33M1 | RU4-TRML | 33M1M/00 | 50 WENG | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA3-LIS |  | DHANANGDH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 | 2102356861 | 8202235288 |  | 8202226096#Perbaikan/penggantian motor s | RU4-LOC1 | 24S1CM2M/00 | 50 WENG | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | BANYUPUTEWA |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 | 2102356225 | 8202235750 |  | 8202226095#Perbaikan Motor Lube Oil 33P1 | RU4-TRML | 33P1CP1M-CB/00 | 50 WENG | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA3-LIS |  | DHANANGDH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355324 | 8202236059 |  | 8202226094#perbaikan electric heater 14E | RU4-FOC1 | 14E654/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354846 | 8202235436 |  | 8202226093#Perbaikan Sootblower Overload | RU4-RFCC | 101F503A7/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354468 | 8202235752 |  | 8202226092#Perbaikan motor finfan 260E12 | RU4-LOC3 | 260E122AM1/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354179 | 8202236886 |  | 8202226091#Penggantian Cooling Fan Motor | RU4-RFCC | 102P508AM/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354178 | 8202236888 |  | 8202226090#Penggantian Cooling Fan Motor | RU4-RFCC | 102P507AM/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354177 | 8202236889 |  | 8202226089#Penggantian Cooling Fan Motor | RU4-RFCC | 102P506M/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354176 | 8202236893 |  | 8202226088#Penggantian Cooling Fan Motor | RU4-RFCC | 102P504AM/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354175 | 8202236897 |  | 8202226087#Penggantian Cooling Fan Motor | RU4-RFCC | 101P529AM/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354174 | 8202236901 |  | 8202226086#Penggantian Cooling Fan Motor | RU4-RFCC | 101P527AM/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351210 | 8202232469 |  | 8202226085#Perbaikan 220 V-8 | RU2-HOC | 220-V-8/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-08-31 | 2102353812 | 8202240272 |  | 8202226084#25_[CR] Perbaikan pelumasan p | RU4-LOC1 | 25P1A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 1478 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-31 |  | 8202237562 | 8202237487 | 8202226083#TGH6_24 UP Clean HE Utl | RU4-UTL | 51E3/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-08-31 |  | 8202237560 | 8202237547 | 8202226082#TGH2_24 UP Scaff.Rejuve Isol | RU4-TRML | LN71-026A/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354173 | 8202236902 |  | 8202226081#Penggantian Cooling Fan Motor | RU4-RFCC | 101P525AM/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354172 | 8202236904 |  | 8202226080#Penggantian Cooling Fan Motor | RU4-RFCC | 101P521AM/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354171 | 8202236906 |  | 8202226078#Penggantian Cooling Fan Motor | RU4-RFCC | 101P501BM/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-08-11 | 2102356910 | 8202240268 |  | 8202226077#25_[CR] Perbaikan scraper 63A | RU4-RFCUTL | 63A501C-S1/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 399200000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-21 | 2026-06-02 | 2026-12-30 | 2102354277 | 8202237558 |  | 8202226072#Pengadaan UPS 3 Phase Gd. Lab | RU4-FOC2 | 30BD12EE0012A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-11-C2H | 100000 | 0 | MA2-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-24 | 2102359690 | 8202237042 |  | 8202226070#Perbaikan Transmitter 19-PT-5 | RU5-E15112 | 19-PIT-503/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 10974075 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351047 | 8202232623 |  | 8202226068#Perbaikan pipa distribusi raw | RU2-UTL | 510-PIPING/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-07-28 | 2102353545 | 8202240264 |  | 8202226067#25_[CR] Perbaikan 14P650 Indi | RU4-FOC1 | 14P650A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 52801188 | 52800000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2025-11-21 | 2026-11-20 | 2102363306 | 8202234025 |  | 8202226066#Fabrikasi tube bundle (upgrad | RU6-RCC | 20-E-102A/00 | 50 | REL MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 3072 | 0 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-11-21 | PM |  | 005
| K601 | 2026-02-03 | 2026-04-15 | 2026-02-03 | 2026-08-27 | 2102363308 | 8202237833 |  | 8202226065#LTSA COCA & COA Utilities | RU6-UTL | 55-A-101A-S1/00 | 50 | CLSD NCMP NMAT PRC | 6MR | D16/25/B6/RT-C2H | 1 | 0 | MA4-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363243 | 8202233937 |  | 8202226064#Material Gasket & Bolt Flange | RU6-HSC | 31-R-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-03 | 2102355589 | 8202236921 |  | 8202226063#Penggantian Blade Fan Motor 1 | RU4-RFCC | 101P521BM/00 | 60 | TECO CNF CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH | 2026-05-18 | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353208 | 8202240260 |  | 8202226062#25_013PT016B | RU4-FOC2 | 013PT016/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-08-21 | 2102362586 | 8202238356 |  | 8202226061#Repair & Rewinding Motor 19-P | RU6-RCC | 19-P-102B/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 004
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351592 | 8202232591 |  | 8202226053#Perbaikan sensor vibrasi 905- | UTL-UP2 | 905-XE-1165B/00 | 50 | CRTD CSER MACM PRC | 2IR | D12/22/B6/RT-D2H | 0 | 0 | MA3-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102358970 | 8202237041 |  | 8202226045#GT-3-25C Sentinel Valve Rusak | RU5-E15112 | GT-3-25C/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 463344 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353140 | 8202234538 |  | 8202226043#Perbaikan P-16 C4 Polymerisas | RU3-CDGP | C4P-P-16/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-05 | 2026-06-17 | 2026-06-30 | 2026-12-29 | 2102358846 | 8202238671 |  | 8202226039#NRK_Perbaikan HoistCrane | RU5-TBL | 101-5-P-10A/00 | 50 | REL NMAT PRC SETC | 5ER | D15/26/B6/NR-C3H | 300000000 | 0 | MA4-LIS |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-06-30 | PM |  | 005
| K401 | 2026-02-08 | 2026-04-27 | 2026-01-02 | 2026-01-02 | 2102354253 | 8202238761 |  | 8202226036#25_Pengadaan Kabel & LCS 166P | RU4-RFCUTL | 166P505M/00 | 50 | CRTD NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 100000 | 0 | MA7-LIS |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-07-15 | 2102359158 | 8202237032 |  | 8202226034#PERB.LINE BALLAST 16" BARAT T | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 379059300 | 0 | MA4-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363282 | 8202233882 |  | 8202226032#pekerjaan bor tape line gas o | RU6-ITP | 42-PIPE/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102351642 | 8202238355 |  | 8202226031#BUKA/ PASANG SOROKAN NOZZLE & | RU2-HOC | 140-V-1A/00 | 60 | CRTD NMAT PRC SETC | 2MR | D12/22/B6/RT-D2H | 1 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353817 | 8202240257 |  | 8202226029#25_88FT252 rusak | RU4-KPC | 88FT252/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 21345221 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353810 | 8202240253 |  | 8202226027#25_Perbaikan Transmitter 100L | RU4-GTO | 100CPI601B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353742 | 8202240248 |  | 8202226025#25_Perbaikan Wire Drum Bearin | RU4-RFCGTO | 47T573/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353741 | 8202240245 |  | 8202226024#25_Perbaikan Wire Drum Bearin | RU4-RFCGTO | 47T571/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238352 | 8202235145 | 8202226023#Tag 13 PM/PDM Cleaning Cooler | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353688 | 8202240241 |  | 8202226022#25_Perbaikan Level Indikator | RU4-GTO | 100CPI601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238332 | 8202234515 | 8202226020#Tag 8 Pemeliharaan Fire Extin | RU3-LKKK |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 1102328045 | 8202237031 |  | 8202226018#Perbaikan MOV Prover Meter 12 | RU5-TBL | 22-MOV-510A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 2261772841 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359760 | 8202237040 |  | 8202226017#PERB.LINE 4" SLOP DEKAT TANK | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 3433410 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363814 | 8202238143 |  | 8202226016#Perbaikan Gearbox 930-ME-13 | RU2-UTL | 930-ME-13/00 | 50 | CRTD NMAT PRC SETC | 2RR | D12/24/B6/NR-D2H | 900000000 | 0 | MA4-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 004
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-02 | 2026-01-02 | 2102356979 | 8202237556 |  | 8202226015#Study SIL KPC | RU4-KPC | DCS-KPC/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1305000000 | 1097095000 | MA4-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-09-03 | 2102363228 | 8202238319 |  | 8202226014#JasaPerbaikan Kompressor 22-K | RU6-DHC | 22-K-101A/00 | 50 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 115000000 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102356404 | 8202240238 |  | 8202226012#25_[CR] Perbaikan Bocoran JW | RU4-FOC1 | 13K1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3476461 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238318 | 8202235423 | 8202226010#Tag 2 Cleaning Tangki Minyak |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353549 | 8202240235 |  | 8202226008#25_[CR] Penggantian air intak | RU4-UTL | 560K601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353600 | 8202240232 |  | 8202226007#25_[CR] Penggantian air intak | RU4-UTL | 560K601B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354199 | 8202240229 |  | 8202226004#25_[CR] Perbaikan 101-F-503-K | RU4-RFCC | 101F503K2T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-01 | 2102363149 | 8202233163 |  | 8202225996#Perbaikan Gasket Pompa 56-P-1 | RU6-UTL | 56-P-101A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 7920 | 34320000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353058 | 8202234518 |  | 8202225993#N_Penggantian Temperature Gau | RU3-PP | 23-K2911B-TG-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351644 | 8202232500 |  | 8202225992#Perbaikan 110-EF-7N No. 3 | RU2-HOC | 110-EF-7N-3/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-01 |  | 8202237831 |  | 8202225989#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-12-28 | 2026-12-28 | 2102359763 | 8202237021 |  | 8202225988#Perbaikan pompa 101-P-8B |  |  | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-09 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-26 | 2026-11-23 | 2102359762 | 8202237030 |  | 8202225987#FDF motor Boiler 2 |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1143400 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-26 | PM |  | 045
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-09-01 |  | 8202236760 | 8202232770 | 8202225986#SPK 19 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-09-01 |  | 8202236762 | 8202232770 | 8202225984#SPK 18 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353866 | 8202240226 |  | 8202225983#25_[CR] Stage 1 kompresor noi | RU4-LOC3 | 220K101/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 3423918 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 1102328309 | 8202237003 |  | 8202225982#Perbaikan Valve 05-KV-504 | RU5-E15111 | 05-KV-504/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 177428730 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-09-01 |  | 8202236764 | 8202232770 | 8202225981#SPK 17 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-11 | 2102359764 | 8202237026 |  | 8202225980#Perbaikan AC Switchgear PP 1 | RU5-UTL | CCR-HVAC-01/00 | 50 | REL CSER MANC PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | WS-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102359767 | 8202237025 |  | 8202225979#Perbaikan K-35-02B | RU5-E15112 | K-35-02B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 97901136 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351942 | 8202232563 |  | 8202225977#Penggantian Drillstem Chamber | RU2-HOC | 140-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-09-01 |  | 8202237829 | 8202233981 | 8202225974#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | ES-B14-01/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-31 |  | 8202236640 | 8202233851 | 8202225972#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-31 |  | 8202236641 | 8202233851 | 8202225971#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-06 | 2102354772 | 8202240223 |  | 8202225970#25_[CR] 240P105 Vibrasi dan m | RU4-LOC3 | 240P105/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 20701800 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351353 | 8202232538 |  | 8202225969#Penggantian Press Gauge Furna | RU2-UTL | 940-B-3/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/22/B6/RT-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102354310 | 8202240221 |  | 8202225967#25_Perbaikan kompresor 91K-40 | RU4-SRU | 91K402B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 499227998 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363759 | 8202232589 |  | 8202225966#Perbaikan solenoid 940 XY 145 | RU2-UTL | 940-B-1/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-06 | 2102354250 | 8202240219 |  | 8202225965#25_[CR] 14K652 Mech Seal Boco | RU4-FOC1 | 14K652/00 | 60 | REL MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 9397006 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363763 | 8202232606 |  | 8202225964#Perbaikan Press Gauge Furnac | RU2-UTL | 940-B-1/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355363 | 8202235794 |  | 8202225962#Perbaikan motor 24E-23BM | RU4-LOC1 | 24E23BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-07 | 2026-03-05 | 2026-03-05 | 2102353966 | 8202240216 |  | 8202225961#25_[CR] 013P103B Mech Seal Bo | RU4-FOC2 | 013P103B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 40034833 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2025-11-24 | 2102363692 | 8202232441 |  | 8202225959#Perbaikan 905-TG-4 | RU2-UTL | 905-G-4/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102356407 | 8202240213 |  | 8202225958#25_Perbaikan pompa 240P114 | RU4-LOC3 | 240P114/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360226 | 8202237027 |  | 8202225957#PERB.LINE 508-6" HVGO DI JL.1 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 17576516 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238015 | 8202235438 | 8202225955#Tag 4 KV Cleaning Minyak Bera |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238296 | 8202235151 | 8202225954#Tag. 13 Pek. Cleaning dan Gan | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238283 | 8202235215 | 8202225952#Tag 10 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102354556 | 8202237555 |  | 8202225949#RKAP24_Jasa Block Mode MOC No | RU4-TRML | LN31-1001AA/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-11 | 2102363224 | 8202232861 |  | 8202225947#Perbaikan Thyristor 059 A | RU6-UTL | 059-A-101A-E9/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 16038 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353749 | 8202240210 |  | 8202225945#25_Penunjukkan 025FT-013 berm | RU4-LOC2 | 025FT013/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102360229 | 8202237002 |  | 8202225942#Perbaikan Fan Door FCS 203 | RU5-E15112 | 50RC-CC-13/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 12 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238360 | 8202234582 | 8202225939#Tag 3 Perbaikan Korosi Atap T |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-01 |  | 8202236832 | 8202233867 | 8202225938#PM 7 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-01 |  | 8202236836 | 8202233867 | 8202225937#PM 6 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-01 |  | 8202236841 | 8202233867 | 8202225936#PM 5 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-01 |  | 8202236844 | 8202233867 | 8202225935#PM 4 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-01 |  | 8202236848 | 8202233867 | 8202225934#PM 3 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351059 | 8202232336 |  | 8202225933#Pengadaan Fastener Belt Conve | RU2-HOC | 170-ME-103-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-01 |  | 8202236851 | 8202233867 | 8202225932#PM 2 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354981 | 8202240207 |  | 8202225929#25_Perbaikan Shut-off Valve 1 | RU4-RFCUTL | 154XV733B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 24 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354980 | 8202240204 |  | 8202225928#25_Perbaikan Shut-off Valve 1 | RU4-RFCUTL | 154XV733A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 24 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354848 | 8202240202 |  | 8202225927#25_Perbaikan Lock-up Valve 14 | RU4-FOC1 | 14HV203/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 23754525 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354841 | 8202240199 |  | 8202225926#25_Perbaikan 154XV735B | RU4-RFCUTL | 154XV736B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 24 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354842 | 8202240195 |  | 8202225924#25_Perbaikan 154XV735A | RU4-RFCUTL | 154XV736A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 24 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355435 | 8202240191 |  | 8202225920#25_47P503A mechanical seal bo | LOC1-UP4 | 47P503A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-06-03 | 2026-06-03 | 2102360013 | 8202236991 |  | 8202225918#Perbaikan P-18 RP A Hitam - | RU5-TBL | P-18/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/26/B6/RT-C2H | 12519390 | 0 | MA4-ROT |  | ANDREAYR |  |  | PT02 |  | 2 | 2026-06-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 1102326220 | 8202234613 |  | 8202225917#Modifikasi Line Buffer 9-1 | RU3-CDGP | SRM-9-1A/00 | 60 | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-09 | 2025-11-20 | 2025-11-20 | 2102351087 | 8202232292 |  | 8202225915#Filter DGS 300-C-1 | RU2-HSC | 300-C-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 906174400 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-09 | PT02 |  | 3 | 2025-11-20 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354424 | 8202240187 |  | 8202225912#25_Float meter 021LT-010 rusa | RU4-LOC2 | 021LT010/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 2 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355919 | 8202240183 |  | 8202225911#25_[CR] 014P107B Coupling Def | RU4-FOC2 | 014P107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354422 | 8202240179 |  | 8202225910#25_Float meter 021LT-009 rusa | RU4-LOC2 | 021LT009/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 2 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354420 | 8202240175 |  | 8202225909#25_Float meter 021LT-004 rusa | RU4-LOC2 | 021LT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 2 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354368 | 8202240171 |  | 8202225908#25_Float meter 021LT-003 rusa | RU4-LOC2 | 021LT003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 2 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356037 | 8202240167 |  | 8202225907#25_Draft gauge 260F151 rusak | RU4-LOC3 | PI-U260/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354849 | 8202240163 |  | 8202225906#25_Perbaikan Positioner 14TV- | RU4-FOC1 | 14TV543/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354256 | 8202240159 |  | 8202225903#25_240PT-026 Penunjukan Hunti | RU4-LOC3 | 240PI026/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 4 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363018 | 8202234071 |  | 8202225899#22-K-105A Pengadaan Blower Ba | RU6-DHC | 22-K-105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237554 | 8202237543 | 8202225897#TGH22-24_22 PSA TRANSFORMATOR | RU4-TRML | 30EE3101A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238341 | 8202235233 | 8202225896#Tag 9 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-05 | 2026-02-05 |  | 8202238323 | 8202238120 | 8202225895#Tag 11 Sarana Tambat Kapal Pl |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K501 | 2026-02-02 |  | 2025-12-19 | 2025-12-19 | 2102360012 | 8202236992 |  | 8202225892#Perbaikan P-17 RP A Hitam - | RU5-D&W | P-17-DW/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-19 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353818 | 8202235921 |  | 8202225891#Perbaikan Lampu Sorot Worksho | RU4-WS | 037BD101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-15-C2H | 0 | 0 | WS-TLS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354127 | 8202240155 |  | 8202225888#25_[CR] 014E108K02 bearing fi | RU4-FOC2 | 014E108K02/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 117766 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-06 | 2102358906 | 8202236994 |  | 8202225884#MAT.Perb. line DEW CDU V to E | RU5-D&W | GHDC/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-EWNH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353864 | 8202240151 |  | 8202225883#25_[CR] Penggantian Filter LO | RU4-FOC1 | 12K1B-P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 5988884 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353865 | 8202240147 |  | 8202225882#25_[CR] Penggantian LO filter | RU4-FOC1 | 12K1B-P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 5988884 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102358844 | 8202236993 |  | 8202225878#PERB.LINE 145-18" LOADING ADO | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 282246566 | 0 | MA4-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360386 | 8202236987 |  | 8202225875#PERB.LINE 508-6" HVGO HVU III | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 48816293 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-09-11 | 2102354775 | 8202237553 |  | 8202225872#TGH_Inspeksi kabel underwater | RU4-TRML | 70BD1IU1/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102353867 | 8202240143 |  | 8202225870#[CR] Perbaikan 24K2P1AT | RU4-LOC1 | 24K2P1A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 15000000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-10-21 | 2102353511 | 8202237552 |  | 8202225867#TGH2_24 UP Boardesk MA 2 | RU4-FOC2 | 012V101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-07-02 | 2102358975 | 8202236981 |  | 8202225861#Perbaikan Sparepart EIV C-1-1 | RU5-E15111 | C-1-11/00 | 50 | REL CSER MANC PRC SETC | 5IR | D15/25/B6/RT-C2H | 474603 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-06-19 | 2102359666 | 8202236988 |  | 8202225859#Perb Transmitter dan Module 0 | RU5-E15111 | C-5-01A/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 338847278 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-02 | 2102360420 | 8202236984 |  | 8202225858#Perbaikan Meter Naphtha PKBBM | RU5-TBL | 22-DPIT-660A/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 437603907 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102354742 | 8202240140 |  | 8202225857#25_[CR] Penggantian Coupling | RU4-TRML | 71P4A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-05 | 2026-05-04 | 2026-11-17 | 2102355327 | 8202240136 |  | 8202225856#25_[PV]Pengadaan Parts Overha | RU4-RFCUTL | 152G502D-D/00 | 50 | REL CSER MACM PRC SETC | 4RO | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-06 | 2102354770 | 8202240131 |  | 8202225854#25_[CR] 017E105K3 Bearing Def | RU4-FOC2 | 017E105K03/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 14007883 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102351056 | 8202238165 |  | 8202225849#LTSA Spring Hanger dan Spring | RU2-HSC | 0-5-C-117-AF/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102360383 | 8202236982 |  | 8202225848#Perbaikan Pompa G-3-34A | RU5-E15112 | G-3-34A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 2070811 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 | 2102360382 | 8202236990 |  | 8202225847#Penggantian Bearing dan MS G- | RU5-E15112 | G-3-11B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 6013563 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102354024 | 8202237551 |  | 8202225846#Penggantian Kabel Power Heate | RU4-LOC2 | 40LTW08/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 399616000 | 0 | MA2-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 | 2102360384 | 8202236989 |  | 8202225845#Penggantian MS Pompa G-8-05B | RU5-E15112 | G-8-05B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 2309866 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-16 | 2102360247 | 8202236985 |  | 8202225841#Perbaikan 04-TE-405A/B,408A/B | RU5-E15111 | K-4-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 4 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-09 | 2102359591 | 8202236979 |  | 8202225840#Perbaikan Tubing Airbank | RU5-E15500 | HALON-RPPK/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 8636726 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360223 | 8202236976 |  | 8202225839#NRK_PenambahanRantaiPengikatF | RU5-TBL | DER-JT-01-02/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 4527482 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-31 | 2026-02-03 | 2026-09-15 | 2102355222 | 8202237550 |  | 8202225837#Pekerjaan Perbaikan Peralatan | RU4-UTL | 51G4/00 | 60 | CLSD CNF NMAT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TONNYADI | 2026-03-25 | 2026-02-07 | PT02 |  | 3 | 2026-03-31 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102360018 | 8202236973 |  | 8202225834#Pengadaan Mechseal G-5-05 A | RU5-E15111 | G-5-05A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363016 | 8202232970 |  | 8202225833#Perbaikan Pompa 32-P-104 B | RU6-HSC | 32-P-104B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-21 | 2026-05-05 | 2102360022 | 8202236978 |  | 8202225832#MAT.Perb. pipa outlet CPI 16" | RU5-D&W | P-2A-CPI/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1028578559 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102354077 | 8202237549 |  | 8202225831#RKA24_Interior Extend MCB RFC | RU4-RFCUTL | 150BD1MMP001/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 1688569000 | 0 | GEN-MEK |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-31 | 2102362334 | 8202233549 |  | 8202225814#Penggantian Pompa 63-P-203A | RU6-ITP | 63-P-203A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-02-02 | 2026-03-07 | 2026-03-06 | 2026-06-29 | 2102353489 | 8202235763 |  | 8202225812#25_[CR] Penggantian Filter 14 | RU4-FOC1 | 14K653/00 | 60 | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 133266954 | 0 | MA1-ROT |  | BADIPUTRO |  | 2026-02-07 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-06 | 2102359153 | 8202236977 |  | 8202225811#MAT.Perb. Roto Hammer G-1-14A | RU5-E15111 | G-1-14A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-11 | 2102359279 | 8202236971 |  | 8202225810#Perbaikan Pressure Controller | RU5-E15112 | 08B-PIC-227/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 169000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237827 |  | 8202225807#LTSA Cleaning Mnyak Rngan 42- | RU6-ITP | 42-T-202A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359594 | 8202236975 |  | 8202225805#Pengadaan FI PI spillback G-1 | RU5-E15111 | G-1-22A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 20 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-09-09 | 2102355871 | 8202237548 |  | 8202225803#TGH1_24 UP Perb.Sub stdr RWI | RU4-RFCUTL | 63MP001/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-09-08 | 2102361275 | 8202237547 |  | 8202225802#TGH1_24 UP Scaffold Rejuve Is | RU4-TRML | LN71-026A/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355904 | 8202240128 |  | 8202225796#25_[CR] 91K401B, Penggantian | RU4-SRU | 91K401B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357549 | 8202240125 |  | 8202225795#25_[CR] Penggantian membran k | RU4-FOC1 | 11P7/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365825 | 8202240122 |  | 8202225794#25_[CR] 21P-9A Shim Coupling | RU4-LOC1 | 21P9A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-18 | 2026-02-02 | 2026-09-23 | 2102363051 | 8202233546 |  | 8202225793#Penggantian Positioner | RU6-RCC | 17-FV-003/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 60875000 | 60875000 | MA1-INT |  | AHMADAKHYAR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-10-07 | 2102362872 | 8202234058 |  | 8202225791#32-FT-055 | RU6-HSC | 32-FT-055/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-05-19 | 2102359380 | 8202236948 |  | 8202225790#MAT.Perb/Clean. Diverter V-3- | RU5-E15112 | V-3-01B/01 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 119018630 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 | 2102359098 | 8202236949 |  | 8202225789#MAT.Perb. V-32-13A | RU5-E15112 | 32-XCV-398/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 10105519 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-21 | 2026-01-27 | 2102359090 | 8202236951 |  | 8202225788#MAT. Perb. valve suct disch K | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 564 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-21 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-04-06 | 2102360021 | 8202236952 |  | 8202225785#MAT. Perb. pipa inlet CPI 16" | RU5-D&W | P-2A-CPI/00 | 50 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 698899817 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102358901 | 8202236895 |  | 8202225784#Perbaikan Floater 08B-LC-157 | RU5-E15112 | C-8-05B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 2 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102355293 | 8202237546 |  | 8202225783#Termin 20 Kontrak PM Rot Elec | RU4-FOC2 | 018P101AM/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 411000000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102358195 | 8202236917 |  | 8202225782#Perbaikan dan rewinding motor | RU5-E15112 |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 11324551 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102355291 | 8202237545 |  | 8202225781#Termin 19 Kontrak PM Rot Elec | RU4-FOC2 | 014P101AM/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 429200000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354464 | 8202240119 |  | 8202225780#25_RKAP26 Perbaikan 154XV001/ | RU4-RFCUTL | 154XY-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-04 | 2102358973 | 8202236950 |  | 8202225778#MAT.Perb. Kaca peep hole burn | RU5-UTL | HHP-1/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-S3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102362923 | 8202234023 |  | 8202225776#Ganti bearing motor/OH 12-P-5 | RU6-DHC | 12-P-507A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363549 | 8202232211 |  | 8202225772#Perbaikan motor 930-MEM-16 | RU2-ITP | 930-ME-15/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 1007321 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2025-12-29 | 2025-12-29 | 2102360342 | 8202236878 |  | 8202225768#Perbaikan Motor GM-4-11B | RU5-E15111 | GM-4-11B/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 120466 | 0 | MA2-LIS |  | SAPBATCH | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2102360485 | 8202236947 |  | 8202225766#Pengadaan spare module relay |  |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1107704000 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359009 | 8202236930 |  | 8202225764#Perbaikan Battery Dry Cell SP |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 2 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102355228 | 8202237544 |  | 8202225763#Termin 18 PM Rot elect | RU4-FOC2 | 013P101AM/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 521200000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-14 | 2026-12-29 | 2026-12-29 | 2102359788 | 8202236876 |  | 8202225757#Perbaikan Sentrifuge Y-34-12B | RU5-D&W | Y-34-12B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360228 | 8202236953 |  | 8202225756#GANTI VALVE DRAIN VESSEL 02D | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 5208976 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-06-29 | 2102360348 | 8202236891 |  | 8202225754#Perbaikan IHLA Tanki A33, A20 | RU5-TBL | IHLA-RP-A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 76164000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-27 | 2026-02-02 | 2026-02-02 | 2102363421 | 8202233556 |  | 8202225749#Penggantian pipa aeration 63- | RU6-ITP | 63-Z-305A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 311460000 | 0 | MA4-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2025-11-17 | 2025-11-17 | 2102363642 | 8202232358 |  | 8202225748#Perbaikan Draft Gauge Heater | RU2-HSC | 100-BH-9/00 | 50 | REL GMPS MACM PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 451030000 | MA2-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-05 | 2102358848 | 8202236831 |  | 8202225743#Perbaikan Modul T7 101-PT-01A | RU5-TBL | 101-PT-01C-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 255729900 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-29 | 2026-12-29 | 2102359447 | 8202236867 |  | 8202225739#Pengadaan Tiang-JB-Lampu Lawe |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 82108646 | 0 | MA4-LIS |  | AGUSHIDAYAT |  | 2026-02-11 | PT02 |  | 3 | 2026-12-29 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102358867 | 8202236833 |  | 8202225737#perbaikan mixer TM-20-04 E&F | RU5-TBL | TM-20-04E/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 520600 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-25 | 2102360346 | 8202236827 |  | 8202225735#Perbaikan Transmitter 01-FT-1 | RU5-E15111 | 01-FT-106/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 10974075 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-20 | 2026-02-20 | 2026-06-02 | 2102362470 | 8202232931 |  | 8202225734#Perbaikan pompa turbine 42-P- | RU6-ITP | 42-P-502B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6RR | D16/26/B6/RT-C2 | 236485074 | 0 | MA4-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-20 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-12-09 | 2025-12-30 | 2102362922 | 8202236805 |  | 8202225733#PM UPS dan DC Charger Brand G | RU6-RCC | 14X-UPS3-01A/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355366 | 8202240117 |  | 8202225730#25_[CR] Perbaikan 24K-2P1A | RU4-LOC1 | 24K2P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238302 | 8202234582 | 8202225728#Tag 2 Perbaikan Korosi Atap T |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238286 | 8202234997 | 8202225727#Tag 8 KV Penyediaan Jasa Hose |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102356117 | 8202240114 |  | 8202225726#25_Kebutuhan Material Cyber S | RU4-RFCC | 100SS1CN001/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 393400000 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102360493 | 8202236780 |  | 8202225724#Perbaikan G-201-12A | RU5-D&W | G-201-12A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 2179957 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352802 | 8202234637 |  | 8202225722#Perbaikan Feld Inst. Gas Plan | RU3-CDGP |  | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351129 | 8202232608 |  | 8202225720#Perbaikan pompa 945-P-15 | RU2-ITP | 945-T-30/00 | 50 | REL NMAT PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351590 | 8202232707 |  | 8202225719#Steam tracing bocor | RU2-HCC | 211-V-26/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-10-23 |  | 8202237825 |  | 8202225717#LTSA PM Tangki 2025 Tahap 1 | RU6-ITP | 42-T-101D/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355438 | 8202240111 |  | 8202225716#25_Pembacaan Tidak Akurat 87F | RU4-KPC | 87FT202/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355369 | 8202240108 |  | 8202225714#25_260LT004 Penunjukan level | RU4-LOC3 | 260LT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353195 | 8202234532 |  | 8202225712#N_Penggantian Selang Pneumati | RU3-UTL | PV-20420A/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-1-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355321 | 8202240105 |  | 8202225711#25_penggantian TI deal 2nd st | RU4-FOC1 | 13K1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 15 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360380 | 8202236824 |  | 8202225710#Material Cleaning Condensor S | RU5-UTL | TG-4-PP2/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-P2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-12-21 | 2026-12-29 | 2102360423 | 8202236820 |  | 8202225709#Penggantian Bearing Deaerato |  |  | 60 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-21 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-20 | 2026-10-20 | 2102360425 | 8202236783 |  | 8202225708#Perbaikan dan inspeksi pompa | RU5-D&W | G-201-09A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1802388 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-20 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102353094 | 8202235362 |  | 8202225707#Pengadaan Membran Coupling P- | RU3-CDGP | CD2-P-002/00 | 50 WAMA | CRTD CSER MACM PRC | 3MR |  | 0 | 0 | MA1-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363661 | 8202232399 |  | 8202225706#Pengadaan bearing dan seal HC | RU2-HCC | 702-PT-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 2111420 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-28 | 2026-11-26 | 2102360424 | 8202236781 |  | 8202225704#Perbaikan G-201-08B | RU5-D&W | G-201-08B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-02 | 2026-01-02 | 2026-06-30 | 2102355721 | 8202240102 |  | 8202225703#25_[PV] Perbaikan Mechseal 10 | RU4-RFCC | 102P502A/00 | 60 | CLSD CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 124160900 | 0 | MA6-ROT |  | LUQMANULH |  | 2026-03-10 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-06-02 | 2026-11-09 | 2102355720 | 8202235760 |  | 8202225702#25_[PV] Perbaikan Mechseal 10 | RU4-RFCC | 101P526A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362320 | 8202233394 |  | 8202225699#Perbaikan 12-P-510 | RU6-DHC | 12-P-510/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-09-23 |  | 8202236669 | 8202233856 | 8202225698#SWO Pemb LTSA Oksigen Analyze | RU6-UTL | 52-B-101B/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-11-04 | 2102362016 | 8202233856 |  | 8202225697#Pemb. LTSA Oksigen Analyzer | RU6-UTL | 52-B-101B/00 | 01 | CLSD NCMP NMAT PRC | 6IR | D16/25/B6/RT-C2H | 23760 | 0 | WS-ROT |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-09-15 | 2102362920 | 8202238272 |  | 8202225696#Jasa Perbaikan 52-B-101C-K1 | RU6-UTL | 52-B-101C-K1/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 200000001 | 0 | MA4-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-18 | 2025-12-22 | 2102360381 | 8202236785 |  | 8202225695#Penggantian PI di G-5-07 | RU5-E15111 | G-5-07/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1022038 | 0 | MA2-INT |  | SAPBATCH | 2026-06-04 | 2026-02-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2025-11-19 | 2025-12-17 | 2102360421 | 8202236692 |  | 8202225694#Perbaikan Oksigen Analizer 8A | RU5-E15112 | 08B-AIT-121/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 67870269 | 0 | MA3-INT |  | SAPBATCH | 2026-05-26 | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2026-04-02 | 2026-04-02 | 2102360389 | 8202236733 |  | 8202225693#Perbaikan motor GM-201-09A | RU5-D&W |  | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH | 2026-04-06 | 2026-02-11 | PT02 |  | 3 | 2026-04-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-04 | 2026-06-03 | 2026-06-03 | 2102360388 | 8202236757 |  | 8202225692#Perbaikan motor GM-201-02B | RU5-D&W |  | 60 | CLSD CNF CSER PRC SETC | 5ER | D15/25/B6/RT-C2H | 1841200 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-30 | 2026-02-11 | PT02 |  | 3 | 2025-12-30 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238270 | 8202235092 | 8202225686#Tag 3 Supporting Teknisi dan | RU3-WS | BEN-TOOL/00 | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | WS-SG |  | SAPBATCH | 2026-05-19 | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363809 | 8202238115 |  | 8202225684#Push button P 140 P 26 B OPT | RU2-ITP | P-208A-DMI/00 | 50 | CRTD NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 10000000 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 004
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238028 | 8202238038 | 8202225683#Tag 9 KV Pengecatan Pipa dan |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-09-28 | 2102353486 | 8202237543 |  | 8202225682#TGH19-21_22 PSA TRANSFORMATOR | RU4-TRML | 30EE3101A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-09-14 |  | 8202237542 | 8202238635 | 8202225677#TGH20_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 161068000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202236816 | 8202235502 | 8202225675#Tagihan Ke- 8 Pekerjaan Sipil | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357020 | 8202240100 |  | 8202225671#25_[CR] perbaikan blade 11E52 | RU4-FOC1 | 11E52AB/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 53592308 | 53592308 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362771 | 8202232758 |  | 8202225670#Pnggntian Rider Ring 22-K-101 | RU6-DHC | 22-K-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363278 | 8202232956 |  | 8202225669#Perbaikan Pompa 42-P-501A | RU6-ITP | 42-P-501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-10 | 2026-06-10 | 2026-12-31 | 2102352992 | 8202238142 |  | 8202225668#Perbaikan Vibration Monitorin | RU3-UTL | 53-GB-101A/00 | 50 | REL NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 894999600 | 0 | MA3-ROT |  | RRAMADHANI |  | 2026-06-10 | PT02 |  | 3 | 2026-06-10 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102360467 | 8202236659 |  | 8202225666#Perbaikan Pompa |  |  | 60 | CLSD CNF NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102358861 | 8202236662 |  | 8202225665#Penggantian bearing dan Ms G- | RU5-E15112 | G-8-01C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 5735640 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355952 | 8202240097 |  | 8202225664#25_Perbaikan 014 S 111 | RU4-FOC2 | 014S111/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-20 | 2026-02-24 | 2026-02-24 | 2102360429 | 8202236633 |  | 8202225663#Perbaikan Pompa G-5-03A | RU5-E15111 | G-5-03A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 3788200 | 0 | MA2-ROT |  | BAMBANGSS | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-02-08 | 2026-03-09 | 2026-02-02 | 2026-12-30 | 2102355724 | 8202238749 |  | 8202225659#25_Perbaikan pompa 166P-513 | RU4-RFCGTO | 166P513/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 67174650 | 67174650 | WS-PMP |  | WAHYUCATUR |  | 2026-03-09 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362719 | 8202232895 |  | 8202225658#Perbaikan Rotor Assembly 52-B | RU6-UTL | 52-B-101C-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 6912 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355982 | 8202240093 |  | 8202225657#25_166P-551B, Mech seal bocor | RU4-RFCGTO | 166P552B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102363489 | 8202233066 |  | 8202225652#Perbaikan Motor 11-P-114 B | RU6-HSC | 11-P-114B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-10-19 | 2102356547 | 8202237541 |  | 8202225646#TGH1_SIP_UP Isolasi ME 2 Tahu | RU4-UTL | LN57-1446R/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-04-10 | 2026-02-02 | 2026-07-10 |  | 8202232727 | 8202233791 | 8202225644#SWO Kebutuhan Material PM SLV | RU6-RCC | 15-R-REGEN/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6IR | D16/25/B6/RT-C2H | 10 | 0 | MA1-INT |  | AHMADAKHYAR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352994 | 8202234544 |  | 8202225642#Perbaikan P-1 CDU III | RU3-CDGP | CD3-P-001/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-09-16 | 2102362581 | 8202238340 |  | 8202225641#kalibrasi CGA/RCA untuk CEMS | RU6-RCC | 15-B-101/00 | 50 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102356946 | 8202240089 |  | 8202225640#25_[CR] Penggantian belt finf | RU4-LOC2 | 021E130/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 1494840 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102356475 | 8202240085 |  | 8202225637#25_Ganti belt fin-fan 91E-409 | RU4-SRU | 91E409A1M/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1045000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-05-13 | 2026-05-13 | 2102352582 | 8202234208 |  | 8202225633#Pemeriksaan H Beam Support De | RU2S-KIL | 900-08F-02/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-08-10 | 2102356323 | 8202240081 |  | 8202225624#25_Penggantian H2S Detector 2 | RU4-LOC3 | PLC-U260/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 13215994 | 0 | MA4-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-14 | 2102362714 | 8202237823 |  | 8202225620#LTSA Piping Tahap 11 Area HTU | RU6-DHC | 22-F-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 69419500 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354086 | 8202235705 |  | 8202225607#Perbaikan perpipaan fire wate |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102354907 | 8202236666 |  | 8202225606#Penggantian line flaring jett |  |  | 50 WAMA | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102354906 | 8202238339 |  | 8202225605#Penambahan Line Produksi Avtu | RU4-TRML | 32T103/00 | 50 | CRTD NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102360427 | 8202236512 |  | 8202225603#Perbaikan Motor GM-8-04C | RU5-E15112 | GM-8-04C/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 9167491 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357400 | 8202236154 |  | 8202225598#Gasket insulasi 041T118 bocor | RU4-TRML | 041T118/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359383 | 8202236624 |  | 8202225596#Penggantian Go Switch Loading | RU5-TBL | L-ARM-1-JT-5B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 685900000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361046 | 8202236012 |  | 8202225595#Valve Stripping Steam to 023C | RU4-LOC2 | 023C107/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359045 | 8202236546 |  | 8202225594#Perb PI Loader Valve di K-5-0 | RU5-E15111 | K-5-02A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 15 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359095 | 8202236536 |  | 8202225593#Perbaikan Lampu Local Panel K | RU5-E15111 | K-4-01A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 100000000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360995 | 8202234939 |  | 8202225591#PSV 024PSV-065 passing | RU4-LOC2 | 024PSV065/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360468 | 8202236542 |  | 8202225590#Perbaikan 05-KV-555 | RU5-E15111 | 05-KV-555/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 262422150 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102358902 | 8202236539 |  | 8202225588#Perbaikan Fan Panel DCS BPP I | RU5-D&W | DCS-HVU-III/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 26000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359817 | 8202236606 |  | 8202225587#Perb Flowmeter Polisher 1,2,3 |  |  | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 4 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359956 | 8202236577 |  | 8202225586#Perb Line Sampling dan Monito |  |  | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1543499 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359955 | 8202236621 |  | 8202225585#Perb Analyzer AT-164 & AT-105 |  |  | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 2 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-04-30 | 2026-12-29 | 2102360035 | 8202236629 |  | 8202225584#NRK_Pengadaan Motor FDF HHP 4 | RU5-UTL | 4M-FDF-HHP-4/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-13 | 2026-06-10 | 2026-06-10 | 2102360469 | 8202236511 |  | 8202225578#Perbaikan unit motor starter | RU5-TBL | 101-PT-1C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3780000 | 0 | MA4-ROT |  | YONZHETG |  | 2026-02-07 | PT02 |  | 3 | 2026-06-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102360461 | 8202236509 |  | 8202225577#Perbaikan Blower FDF Turbine |  |  | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 4624220 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358552 | 8202234550 |  | 8202225576#Pengantian baru Mech Seal 1 - |  |  | 50 | CRTD NMAT PRC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360460 | 8202236488 |  | 8202225575#PERB.LINE 9-10"SHORTRESIDU BP | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 26827783 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233989 | 8202233612 | 8202225574#Lampu Kebutuhan Bumi Patra | RU6-UTL | SS-01/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 15840 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351315 | 8202232269 |  | 8202225568#Kebutuhan Material Perbaikan | RU2-LAB | LAB-GAS-21/00 | 50 | REL MACM PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | WS-IN1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-02 | 2026-02-03 | 2026-04-30 | 2102359325 | 8202236436 |  | 8202225565#Penggantian LCS GM-3-12C | RU5-E15112 | GM-3-12C/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 10 | 0 | MA3-LIS |  | GHAGASP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-01 | 2102361569 | 8202233127 |  | 8202225564#Perbaikan lampu di area tanki | RU6-ITP | 63-A-101-V1/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 17820 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354189 | 8202236440 |  | 8202225562#Penggantian Tip Burner 14F602 | RU4-FOC1 | 14F602B1FA/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354083 | 8202235242 |  | 8202225561#Pekerjaan Cleaning Burner di |  |  | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354716 | 8202236414 |  | 8202225560#penggantian valve 14V621 | RU4-FOC1 | 14V621/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355155 | 8202235813 |  | 8202225558#Modifikasi pondasi pompa baru | LOC1-UP4 | 47S506B-P4/00 | 50 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355202 | 8202236006 |  | 8202225557#perbaikan isolasi area FOC 1 |  |  | 50 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355878 | 8202236438 |  | 8202225556#Penggantian Tip Burner 14F602 | RU4-FOC1 | 14F602/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355080 | 8202236881 |  | 8202225551#Penggantian Filter 14D650 | RU4-FOC1 | 14D650/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366035 | 8202240077 |  | 8202225550#25_Pengadaan L. Loading Gaske | RU4-LOC2 | 022E113/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 621791500 | 621791500 | MA2-STA |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102353557 | 8202237539 |  | 8202225548#TGH1-2_24 TSA LIGHTNING PROT | RU4-TRML | 38LT306/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-10-05 | 2026-10-05 | 2102358860 | 8202236427 |  | 8202225547#Perbaikan Pompa G-34-112 B | RU5-D&W | G-34-112B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 612379 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-10-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102360463 | 8202236424 |  | 8202225546#Perbaikan Pulley Motor Eam-20 | RU5-D&W |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 14573000 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-21 | 2026-01-02 | 2026-11-17 | 2102362133 | 8202238174 |  | 8202225542#Perb. Tangga Beton SS-11,12,1 | RU6-DHC | SS-12/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 453000000 | 385050000 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354904 | 8202240073 |  | 8202225541#25_perbaikan pH analyzer Clar | RU4-RFCUTL | 63AA001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 4 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356866 | 8202240069 |  | 8202225540#25_91TI-532, Layar Transmitt | RU4-SRU | 91E409/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356865 | 8202240065 |  | 8202225539#25_91FT-205 , Transmitter rus | RU4-SRU | 91E402AM/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 19250000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238336 | 8202235145 | 8202225538#Tagihan Ke- 12 Pekerjaan PM/P | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-05 | 2026-02-05 |  | 8202238310 | 8202238120 | 8202225537#Tagihan Ke- 13 Pekerjaan Perb |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102356829 | 8202240059 |  | 8202225536#25_Penggantian limit switch 2 | RU4-LOC1 | 21HV037/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102356827 | 8202240056 |  | 8202225535#25_Penggantian limit switch 2 | RU4-LOC1 | 21HV036/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238289 | 8202235367 | 8202225534#Tagihan Ke- 7 Pekerjaan Kontr |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102356825 | 8202240052 |  | 8202225533#25_Penggantian limit switch 2 | RU4-LOC1 | 21HV035/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102356744 | 8202240049 |  | 8202225532#25_Penggantian limit switch 2 | RU4-LOC1 | 21HV038/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356706 | 8202240045 |  | 8202225531#25_011FT034 rusak | RU4-FOC2 | 011FT034/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360814 | 8202236433 |  | 8202225524#Perb. lampu Penerangan Jetty | RU5-TBL | DER-JT-05/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/NR-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2025-12-29 | 2025-12-29 | 2102359907 | 8202236485 |  | 8202225523#Penggantian kabel grounding P |  |  | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 57988000 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362478 | 8202234084 |  | 8202225522#16P107B Perbaikan Mech seal | RU6-RCC | 16-P-107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-07 | 2102363485 | 8202233222 |  | 8202225521#Perbaikan bocoran 37-XV-073 | RU6-POC | 37-R-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-01-12 |  | 8202237822 |  | 8202225519#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-23 | 2026-12-01 | 2026-12-30 | 2102358196 | 8202236459 |  | 8202225518#Penggantian lampu penerangan |  |  | 60 | REL CSER MSPT PRC SETC | 5ER | D15/26/B6/RT-C2H | 270250000 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-11 | PT02 | 8 | 3 | 2026-12-01 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102358840 | 8202236430 |  | 8202225516#Perbaikan Motor EM-1-21B | RU5-E15111 | EA-1-21B/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 296800 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102356587 | 8202240041 |  | 8202225515#25_017E104M3 Motor Short | RU4-FOC2 | 017E104M03/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 1044500 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351486 | 8202232670 |  | 8202225510#Pengadaan Material Overhaul E | RU2-LAB | LAB-GAS-21/00 | 50 | REL NMAT PRC SETC | 2IR | D12/22/B6/RT-D2H | 0 | 0 | WS-IN1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353661 | 8202240037 |  | 8202225505#25_Penggantian Expansion Join | RU4-KPC | 88P201B/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 2424000000 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102358843 | 8202236417 |  | 8202225504#Perbaikan motor Gm-34-61 | RU5-E15112 | GM-34-61/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 112980 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102358842 | 8202236418 |  | 8202225503#Perbaikan motor Gm-34-100 | RU5-E15112 | GM-34-100A/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 112980 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102358197 | 8202236413 |  | 8202225502#Perbaikan panel listrik deep |  |  | 60 | REL NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238269 |  | 8202225501#Tag 19 TSA Pemeliharaan Vacuu | RU3-ITP | 039-P-007/00 | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2102359044 | 8202236390 |  | 8202225500#Perbaikan Pompa G-319-01A |  | G-319-01A/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 827000 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-12-04 | 2026-12-04 |  | 8202238173 |  | 8202225499#CLEANING INSIDE SEA WATER COL | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 440000000 | 0 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-12-04 | PM |  | 045
| K202 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102352572 | 8202234207 |  | 8202225496#Perbaikan Pondasi Flokulator | RU2S-KIL | GDG-WTP/00 | 50 | CRTD NMAT PRC | 2MS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362582 | 8202232935 |  | 8202225494#Perbaikan Pompa 70-P-102 | RU6-UTL | 54-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-22 | 2025-12-30 | 2102358847 | 8202236419 |  | 8202225489#Cleaning Condensor STG 1.6 | RU5-UTL | TG-6-PP1/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-P2NH | 64 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-12-22 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-05-22 | 2102362474 | 8202233031 |  | 8202225485#Perbaikan motor 54-P-102A | RU6-UTL | 54-P-102A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2072 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353558 | 8202237537 |  | 8202225477#TGH1_CIV_CPS |  |  | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353551 | 8202240033 |  | 8202225475#25_Perbaikan bocoran pompa 26 | RU4-LOC3 | 260P104B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 1930714 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-11-26 | 2025-12-04 | 2102359322 | 8202236388 |  | 8202225473#Perbaikan TI Flushing Oil G-1 | RU5-E15111 | G-1-20A/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 4360090 | 0 | MA2-INT |  | SAPBATCH | 2026-06-04 | 2026-02-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362236 | 8202233961 |  | 8202225469#Make Up Rocksalt 14-V-108 | RU6-DHC | 14-V-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 369717 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-09-18 |  | 8202237523 | 8202237513 | 8202225468#TGH31-32_22 Sewa CCTV Tanki 4 | RU4-RFCGTO | 47T511A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 116661000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-04 | 2026-04-17 | 2026-02-19 | 2026-12-30 | 2102363968 | 8202238267 |  | 8202225467#Instalasi Switchgear SWS#2 | RU2-UTL | 560-SWG-BTE/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1665000000 | 0 | MA3-LIS |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-19 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359099 | 8202236370 |  | 8202225466#Pengecetan Body motor pompa b |  |  | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 18478320 | 0 | WS-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356823 | 8202240029 |  | 8202225464#25_Selisih Penunjukkan 105PDI | RU4-RFCGTO | 105PDT-U105/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 25700000 | 27000000 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 |  | 8202236352 | 8202235132 | 8202225463#Penggantian Modul MOV Rotork | RU5-TBL | PLANT-24-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 66 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-04 | 2025-11-26 | 2025-12-04 | 2102359321 | 8202236347 |  | 8202225461#Perbaikan TI Flushing Oil G-1 | RU5-E15111 | G-1-04C/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 4360090 | 0 | MA2-INT |  | SAPBATCH | 2026-06-04 | 2026-02-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356821 | 8202240025 |  | 8202225459#25_Pengadaan Power Supply 105 | RU4-RFCGTO | 105FT-U105/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 10000000 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356789 | 8202240021 |  | 8202225458#25_Selisih Penunjukkan 105FI0 | RU4-RFCGTO | 105FI-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 11744430 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362373 | 8202233608 |  | 8202225457#Penggantian LBS CSS Managemen | RU6-UTL | MSS-31/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 15840 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-20 | 2026-03-05 | 2026-03-05 | 2102356702 | 8202240017 |  | 8202225455#25_RKAP25 Penggantian CV DI 1 | RU4-RFCUTL | 154LV605A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 15 | 0 | MA5-INT |  | SAMSUDINH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356704 | 8202240686 |  | 8202225454#25_RKAP25 Penggantian 63LV002 | RU4-RFCC | 63-WS0011-32/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 3 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356433 | 8202240684 |  | 8202225450#25_Perbaikan Instrumentasi 26 | RU4-LOC3 | 260K101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 10289340 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-31 | 2025-12-31 | 2102358866 | 8202236345 |  | 8202225449#Perbaikan Turbine GT-2-05B | RU5-E15112 | GT-2-05B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 16601923 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-15 | 2102359043 | 8202236383 |  | 8202225448#MAT.Cleaning/Perb. E-202-06 | RU5-D&W | E-202-06/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 62898688 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362376 | 8202233632 |  | 8202225443#Penggantian Gasket Pompa 35-P | RU6-POC | 35-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362235 | 8202232944 |  | 8202225442#Perbaikan Pompa 61-P-201B | RU6-HSC | 61-P-201B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 40000000 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-15 | 2102359042 | 8202236385 |  | 8202225440#MAT.Cleaning/Perb. E-202-05 | RU5-D&W | E-202-05/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 61030998 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102353494 | 8202240682 |  | 8202225439#25_Penggantian Valve Tanki Un | RU4-TRML | 030PSV301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 110307480 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-03 | 2026-04-07 | 2026-01-02 | 2026-12-31 | 2102353840 | 8202237520 |  | 8202225435#Penambahan VSD 14E6A | RU4-FOC1 | 14E6AM/00 | 50 | CRTD NMAT PRC RELR SETC | 4ER | D14/26/B6/RT-1-C2H | 100000 | 0 | MA1-LIS |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2025-12-29 | 2025-12-29 | 2102358865 | 8202236350 |  | 8202225433#Perbaikan Motor GM-5-12A | RU5-E15111 | GM-5-12A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2057976 | 0 | MA2-LIS |  | SAPBATCH | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351645 | 8202232664 |  | 8202225430#Pengadaan Modul PLC 211/212 m | RU2-HCC | 211-C-2A/00 | 50 | REL NMAT PRC SETC | 2IR | D12/22/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356637 | 8202240680 |  | 8202225429#25_Penggantian Limit Switch 2 | RU4-LOC3 | 260XV355/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 9 | 99000000 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-03 | 2025-12-03 | 2102363608 | 8202232322 |  | 8202225425#Pengadaan FT dan Orifice Line | RU2-HCC | 4-TMW-21216-MS1/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102359274 | 8202236341 |  | 8202225424#Pekerjaan Kalibrasi CEMS | RU5-E15500 | CEMS-SYSTEM-INT/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 79500000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-11-03 | 2102362368 | 8202232755 |  | 8202225420#Reactor Filter 20-S-102 B | RU6-RCC | 20-S-102C/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102359008 | 8202236344 |  | 8202225419#Mat'l Resetting PSV Releasabl | RU5-D&W | 201-PSV-002C/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 37178965 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-01-02 | 2026-01-02 | 2102355208 | 8202237518 |  | 8202225415#Perbaikan HVAC Sistem PLC Gd | RU4-FOC2 | 30BD12EE0012B/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 5100000000 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362237 | 8202232759 |  | 8202225412#Pnggntian Carbon Ring-Mech Se | RU6-RCC | 15-P-118A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-06 | 2026-03-06 | 2102353482 | 8202240678 |  | 8202225409#25_Penggantian Filter MAC 180 | RU4-GTO | 180A601K1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-09 | 2026-01-02 | 2026-01-02 | 2102352999 | 8202235092 |  | 8202225406#Supporting Teknisi dan Operat | RU3-WS | BEN-TOOL/00 | 60 | REL CNF GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | SUHARTADI | 2026-05-07 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362372 | 8202232987 |  | 8202225402#Perbaikan Pompa 15-P-102C | RU6-RCC | 15-P-102C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351278 | 8202232290 |  | 8202225400#Pengadaan Gasket Vapour 18'' | RU2-HOC | 140-V-1A/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354227 | 8202240676 |  | 8202225399#25_Perbaikan 14PCV-3 | RU4-FOC1 | 14PCV3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102359155 | 8202236337 |  | 8202225397#Perbaikan Piston Hidrolik GM- | RU5-UTL | G-32-22A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 795000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2102359329 | 8202236338 |  | 8202225396#Perbaikan Penerangan Lampu Ja | RU5-TBL | PLANT-22-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1084409225 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359720 | 8202236339 |  | 8202225394#Perb Pres Transmitter Skid Me | RU5-TBL | METER-4521/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 10 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102358868 | 8202236335 |  | 8202225393#perbaikan motor Gm-2-01B | RU5-E15112 |  | 60 | CLSD CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-11 | 2025-12-29 | 2025-12-29 | 2102358869 | 8202236330 |  | 8202225392#Perbaikan motor GM-31-39C |  |  | 60 | CLSD MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1161899 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-31 | 2025-12-31 | 2102359510 | 8202236323 |  | 8202225389#Perbaikan Cylinder 6 K-3-02A | RU5-E15112 | K-3-02A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 49578962 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102358904 | 8202236324 |  | 8202225388#Penggantian bearing dan V bel | RU5-E15112 | EA-3-11C/00 | 60 | CLSD CNF NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351356 | 8202232298 |  | 8202225384#Kebutuhan Gland Packing Switc | RU2-HOC | 140-V-1C/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365943 | 8202240674 |  | 8202225383#25_Penggantian Transmitter 63 | RU4-RFCC | 101FD001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-10-21 | 2102353469 | 8202237516 |  | 8202225382#TGH2_23 UP Penyehatan HE MA 2 | RU4-FOC2 | 011E109C2/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-11-24 | 2102361248 | 8202237514 |  | 8202225381#TGH1_24 UP Plenum FOC II | RU4-FOC2 | 013V101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-03-04 | 2026-02-02 | 2026-12-30 |  | 8202237511 | 8202238638 | 8202225380#Perbaikan Line Brake System F | RU4-WS | FL44/00 | 60 | REL CSER GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 73378000 | 62371300 | WS-KAB |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-06 | 2026-04-24 | 2026-04-24 | 2102353090 | 8202234593 |  | 8202225378#Perbaikan Kabel Pompa 4D RPM | RU3-ITP | ITP-RPR-MC-004/00 | 60 | REL CSER GMPS MACM PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 640349100 | 640349100 | MA4-LIS |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-04-24 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102358972 | 8202236320 |  | 8202225372#Perbaikan Flow Transmitter 31 | RU5-UTL | TG-2-PP2-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 13967883 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357164 | 8202240672 |  | 8202225369#25_Mtl. Perbaikan Line Sulfur | RU4-SRU | 93A404/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 57876524 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-21 | 2026-01-02 | 2026-01-02 | 2102363822 | 8202238171 |  | 8202225368#Service System-1 Vibration Mo | RU2-UTL | 905-DEG-01/00 | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/NR-D2H | 500000000 | 0 | MA3-INT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-07-28 | 2102361142 | 8202236912 |  | 8202225366#Penggantian Check Valve 46P10 | RU4-TRML | 46P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102362231 | 8202233183 |  | 8202225365#Perbaikan dan PM-3 12-PTR2-01 | RU6-DHC | 12-PTR2-01B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 28484000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2102359007 | 8202236319 |  | 8202225354#Impeller pompa P7 rusak WTP 1 | RU5-UTL | P-7PAMPANCUR/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | NSUCIPTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362018 | 8202233160 |  | 8202225351#Perbaikan Genral Turbin 11-P- | RU6-HSC | 11-P-104A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351319 | 8202232499 |  | 8202225350#Perbaikan 140 E-11AB | RU2-HOC | 140-E-11A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-04-15 | 2026-02-03 | 2026-11-05 | 2102362234 | 8202237820 |  | 8202225348#Penggantian/Perbaikan Coalesc | RU6-DHC | 14-S-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 300000001 | 0 | MA2-STA |  | HARSARIZANO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2025-12-05 | 2102362233 | 8202233959 |  | 8202225347#Make Up Rocksalt 21-V-108 | RU6-DHC | 21-V-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 221830 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-02-08 | 2026-06-18 | 2026-03-09 | 2026-12-30 | 2102353324 | 8202238748 |  | 8202225344#25_Perbaikan Electrical Unit | RU4-LOC2 | 024C102/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/NR-8-C2H | 1003575000 | 1003575000 | MA2-LIS |  | WAHYUCATUR |  | 2026-03-09 | PT02 |  | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-02-08 | 2026-06-19 | 2026-03-09 | 2026-12-30 | 2102357221 | 8202238747 |  | 8202225343#25_Perbaikan Electrical Unit | RU4-LOC2 | 022C101/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 701865000 | 701865000 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-02-08 | 2026-06-18 | 2026-03-09 | 2026-12-30 | 2102357169 | 8202238746 |  | 8202225338#25_Perbaikan Electrical Unit | RU4-LOC2 | 021C101/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 1576252000 | 1576252000 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353497 | 8202240670 |  | 8202225336#25_Perbaikan Bocoran Bodi 140 | RU4-GTO | 140PV019/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102359559 | 8202236314 |  | 8202225332#Penggantian Bearing Pompa G-2 | RU5-E15112 | G-2-10A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 2264000 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359273 | 8202236298 |  | 8202225330#Perbaikan Temp Transmitter 20 | RU5-D&W | 201-TT-071/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 10 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-29 | 2026-11-27 | 2102359005 | 8202236296 |  | 8202225328#RWP no.2 Polisher | UTL-UP5 | DP-5-RWP-2/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-10-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359097 | 8202236312 |  | 8202225323#Perb PI Tangki W-7 Demin |  |  | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 61904775 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-09-24 |  | 8202237509 | 8202237513 | 8202225317#TGH29-30_22 Sewa CCTV Tanki 4 | RU4-RFCGTO | 47T511A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 172256000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-08 |  | 2026-02-09 | 2026-02-09 | 2102354658 | 8202238760 |  | 8202225316#25_Pengadaan fire hose 12 inc | RU4-K3LL | FT29/00 | 50 | CRTD CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | TRCK-FRE |  |  |  |  | PT02 |  | 2 | 2026-02-09 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-18 | 2102359048 | 8202236317 |  | 8202225306#MAT. Perbaikan scrapper D-34- | RU5-D&W | D-34-07A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 12150000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-05-20 | 2026-05-20 | 2102352577 | 8202234205 |  | 8202225300#Perbaikan Motor Pompa 101-P4- | RU2S-KIL | 101-P-4A-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-16 | 2026-05-20 | 2026-05-20 | 2102352578 | 8202234204 |  | 8202225299#Perbaikan Motor Aerator A IPA | RU2S-KIL | 946-M-1A-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 4687 | 4687 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-23 | 2026-02-02 | 2026-02-02 | 2102352574 | 8202234203 |  | 8202225298#Perbaikan Motor Fin Fan Coole | RU2S-KIL | 101-E-7B-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 2141501 | 836501 | MAS-LIS |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202235297 | 8202238631 | 8202225290#RKAP-Material LP Tangga Tanki |  |  | 50 WAMA | REL CSER MACM PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K301 | 2026-02-05 | 2026-03-12 | 2026-01-01 | 2026-12-30 | 2102352731 | 8202238631 |  | 8202225289#NR26-Pemasangan Lighting Tank |  |  | 50 | REL NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 1800000000 | 0 | MA4-LIS |  | RRAMADHANI |  | 2026-02-11 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353145 | 8202234526 |  | 8202225288#Perbaikan Pompa LS-P-501B (Hi | RU3-CDL | LS-P-501B/00 | 60 | REL CSER MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237507 | 8202237503 | 8202225287#TGH8_23 Tagihan TSA Fire Supp | RU4-FOC1 | 11FT001/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-08-10 | 2102365681 | 8202240668 |  | 8202225286#25_Perbaikan Polisher 154-A-5 | RU4-RFCUTL | 154A503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 4559175 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102354038 | 8202240666 |  | 8202225285#25_Mtl. Perbaikan bocoran 91K | RU4-SRU | 91K401AEM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 2605681 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-04 | 2102359783 | 8202236294 |  | 8202225281#Pengadaan PI Range 0-60Kg G-5 | RU5-E15111 | G-5-01A/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 7780000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202237504 | 8202236915 | 8202225274#Penggantian Cable under groun | LOC1-UP4 | 47S506A-P4/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 526602000 | 0 | MA1-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-25 | 2102362011 | 8202237818 |  | 8202225269#LTSA Steam Leak Tahap 14 Area | RU6-RCC | 15-R-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362120 | 8202233184 |  | 8202225265#Perbaikan Coupling 056-P-101C | RU6-UTL | 056-P-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353804 | 8202240664 |  | 8202225264#25_Perbaikan FSL 31P1C | RU4-TRML | 31P1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 28000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-24 | 2102362015 | 8202237816 |  | 8202225263#LTSA Oksigen Analyzer Termin | RU6-UTL | 52-B-101A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102354032 | 8202240662 |  | 8202225260#25_Penggantian sensor flowmet | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353622 | 8202240660 |  | 8202225259#25_Penggantian positioner 24H | RU4-LOC1 | 24K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360248 | 8202236275 |  | 8202225257#Perbaikan Probe dan Sensor O2 | RU5-E15111 |  | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359519 | 8202236292 |  | 8202225256#Perb Thermocouple w/Thermowel | RU5-E15112 | K-3-02A-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 20 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102359092 | 8202236288 |  | 8202225250#Perbaikan Kabel Pompa Sump 19 |  |  | 60 | REL NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361210 | 8202237327 |  | 8202225249#93HV-183, perbaikan stationar | RU4-SRU | 93HV183/00 | 50 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361100 | 8202236497 |  | 8202225248#Penggantian Pulley Motor 92E4 | RU4-SRU | 92E409BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361101 | 8202236498 |  | 8202225247#Penggantian Pulley Motor 92E4 | RU4-SRU | 92E409AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361105 | 8202236503 |  | 8202225245#Penggantian Pulley Motor 91E- | RU4-SRU | 91E404BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361103 | 8202236500 |  | 8202225243#Penggantian Pulley Motor 91E4 | RU4-SRU | 91E404AM/00 | 50 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354757 | 8202240658 |  | 8202225242#25_penggantian gasket 85S201 | RU4-KPC | 85S201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 14400000 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-05-05 | 2026-02-02 | 2026-09-23 | 2102362019 | 8202233689 |  | 8202225238#Penggantian Bearing Pompa 11- | RU6-HSC | 11-P-120A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361022 | 8202235283 |  | 8202225236#Perbaikan/Penggantian MOV Pre | RU4-TRML | 36P101A-P1/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-08 | 2026-03-09 | 2026-02-03 | 2026-12-29 | 2102353801 | 8202238759 |  | 8202225235#25_[CR]Pompa CPI 200P104 B bo | RU4-LOC3 | 200P104B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 65080250 | 65080250 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-09 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361144 | 8202236923 |  | 8202225232#Penggantian bearing motor 91E | RU4-SRU | 91E409A1M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360825 | 8202234995 |  | 8202225231#Service Busduct 70SS11 | RU4-TRML | 70SS11/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360826 | 8202234996 |  | 8202225229#Service Busduct 70SS1 | RU4-TRML | 70SS1/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360827 | 8202234998 |  | 8202225228#Service Busduct 40SS11 | RU4-TRML | 40SS11/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361000 | 8202234999 |  | 8202225227#Service Busduct 30SService Bu | RU4-TRML | 30SS2/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361002 | 8202235005 |  | 8202225225#Service Busduct 30SS12 | RU4-TRML | 30SS12/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354033 | 8202240656 |  | 8202225223#25_Penggantian sensor flowmet | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361003 | 8202235007 |  | 8202225220#Service Busduct 30SS11 | RU4-TRML | 30SS11/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361001 | 8202235001 |  | 8202225219#Service Busduct 30SS31 | RU4-TRML | 30EE3101A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353956 | 8202235753 |  | 8202225218#Motor pelumasan 24S1A rusak | RU4-LOC1 | 24S1AM3M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353475 | 8202235765 |  | 8202225217#Perbaikan Motor Clause Blower | RU4-SRU | 93K401BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-08-13 | 2102353442 | 8202236914 |  | 8202225216#Penggantian Cable under groun | LOC1-UP4 | 47S506A-P5/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 1624 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2027-01-21 | 2102353441 | 8202236915 |  | 8202225215#Penggantian Cable under groun | LOC1-UP4 | 47S506A-P4/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 3353 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353440 | 8202235788 |  | 8202225214#Perbaikan Motor 33M2 | RU4-TRML | 33M4M/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357543 | 8202236009 |  | 8202225213#Perbaikan instalasi listrik d | RU4-FOC1 | 11P23AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2025-12-31 | 2026-03-30 | 2102359550 | 8202236262 |  | 8202225212#Perb PI Disch Stage 1,2,3 K-3 | RU5-E15112 | K-3-02B-INST/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 24541152 | 0 | MA3-INT |  | SAPBATCH | 2026-05-26 | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357139 | 8202235791 |  | 8202225211#Perbaikan motor 24S1AM3 | RU4-LOC1 | 24S1AM3M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-21 | 2026-02-03 | 2026-02-03 | 2102356984 | 8202236885 |  | 8202225210#Penggantian Cooling Fan Motor | RU4-RFCC | 104P503AM/00 | 60 WAMA | REL CNF CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | YMOHAMMAD | 2026-05-18 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 1102326224 | 8202235148 |  | 8202225209#Overhaul Pompa LS-P-1B | RU3-CDL | LS-P-1B/00 | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356980 | 8202236535 |  | 8202225208#Penggantian Over Current Rela | RU4-RFCC | 101F503/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-25 | 2102362184 | 8202237815 |  | 8202225207#LTSA Online Leak Sealing Taha | RU6-RCC | 15-V-101/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-25 | 2102361941 | 8202237813 |  | 8202225206#LTSA Online Leak Sealing Taha | RU6-RCC | 15-B-101/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-25 | 2102362785 | 8202237811 |  | 8202225204#LTSA Online Leak Sealing Taha | RU6-RCC | 15-E-113C/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356761 | 8202236487 |  | 8202225203#penggantian relay multilin 36 |  | 46P1BM-135PB/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356725 | 8202234763 |  | 8202225202#pengadaan kabel power 46P1B |  | 46P1BM-135PB/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356721 | 8202234766 |  | 8202225200#pengadaan kabel power 46P-1A |  | 46P1AM-135PA/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 | 2102356105 | 8202235735 |  | 8202225199#Perbaikan MOV Press 32P101B | RU4-TRML | 32P101B/00 | 50 WENG | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA3-LIS |  | DHANANGDH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-03-07 | 2026-02-03 | 2026-02-03 | 2102353938 | 8202236495 |  | 8202225197#Penggantian pulley motor area | RU4-SRU | 91E408A1M/00 | 01 | CLSD NCMP NMAT PRC | 4RR |  | 0 | 0 | MA1-ROT |  | BADIPUTRO |  |  | PT02 |  | 2 | 2026-03-07 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353662 | 8202235836 |  | 8202225196#Perbaikan motor 92E409B | RU4-SRU | 92E409BM/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353518 | 8202235739 |  | 8202225195#Perbaikan Motor Short Winding | RU4-RFCC | 104E509AM2/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353517 | 8202235737 |  | 8202225194#Perbaikan Motor Short Winding | RU4-RFCC | 104E509AM2/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-11 | 2025-10-27 | 2025-10-27 | 2102352588 | 8202234202 |  | 8202225193#LTSA Thermal Insulation & Ste | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-D3H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 | 2102353464 | 8202234987 |  | 8202225192#Service motor 42P4A | RU4-TRML | 42P4AM/00 | 50 WENG | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | BANYUPUTEWA |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356711 | 8202236810 |  | 8202225191#Penggantian hub coupling moto | RU4-LOC1 | 24P7AM/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356247 | 8202235792 |  | 8202225190#Perbaikan motor 24P-7A | RU4-LOC1 | 24P7AM/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356184 | 8202236090 |  | 8202225189#Perbaikan Cover Fan Motor 102 | RU4-RFCC | 102P509AM/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 | 2102354596 | 8202235772 |  | 8202225188#Perbaikan motor 91K401BM | RU4-SRU | 91K401BM/00 | 50 | CRTD CSER MACM PRC | 4ER |  | 75196000 | 0 | MA1-LIS |  | BANYUPUTEWA |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102354595 | 8202235775 |  | 8202225187#Perbaikan motor 91K401AM | RU4-SRU | 91K401A/00 | 50 WAMA | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-04-06 | 2026-01-02 | 2026-12-30 | 2102352587 | 8202234201 |  | 8202225186#Pekerjaan Non Destructive Tes | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 850000000 | 0 | MAS-ME2 |  | JUNIANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 | 2102354419 | 8202235782 |  | 8202225185#Perbaikan motor 42P-4A | RU4-TRML | 42P4AM/00 | 50 WENG | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | BANYUPUTEWA |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-09-28 |  | 8202237502 | 8202238635 | 8202225184#TGH19_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 246962000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354413 | 8202235806 |  | 8202225183#Perbaikan motor 21P-4 | RU4-LOC1 | 21P4M/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353596 | 8202236710 |  | 8202225182#D_25 166A553 cvr mtr Scap td | RU4-RFCUTL | 166A553/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-13-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102360949 | 8202237500 |  | 8202225177#Perbaikan Panel Control Motor | RU4-TRML | 30P105A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 733500000 | 0 | MA3-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-26 | 2026-02-02 | 2026-02-02 | 2102353059 | 8202234551 |  | 8202225175#Perbaikan Motor Pompa 5 RPM A | RU3-ITP | ITP-RPA-PM-005/00 | 60 | CLSD CNF CSER MACM PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 369000 | 0 | MA4-LIS |  | SAPBATCH | 2026-03-27 | 2026-02-07 | PT02 |  | 3 | 2026-03-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354410 | 8202236219 |  | 8202225172#Perbaikan Bearing Motor 101P5 | RU4-RFCC | 101P524BM/00 | 50 | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353628 | 8202240654 |  | 8202225168#25_Penggantian Transmitter 54 | RU4-UTL | 54WS201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353854 | 8202240652 |  | 8202225162#25_[CR]011P112B sight glass b | RU4-FOC2 | 011P112B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-05 | 2026-02-14 | 2026-02-18 | 2026-02-18 | 2102351187 | 8202238675 |  | 8202225154#kontrak LTSA Seal John Crane | RU2-HSC | 100-P-1A/00 | 50 | REL GMPS NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 1000000000 | 384746000 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353768 | 8202240650 |  | 8202225153#25_[CR] Penggantian filter LO | RU4-FOC1 | 14K602B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3334091 | 3334091 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353678 | 8202240648 |  | 8202225152#25_[CR] 011P105A Mech Seal OB | RU4-FOC2 | 011P105A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 6913496 | 6913496 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238368 | 8202235085 | 8202225151#Tagihan Ke- 5 Pekerjaan Isola |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238362 | 8202235215 | 8202225150#Tag 9 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-23 |  | 8202236617 | 8202233975 | 8202225147#SWO Pemb. PM/PDM Control Valv | RU6-DHC | 22-V-109A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353098 | 8202234427 |  | 8202225146#Pompa Lumpur P-2300 JA RWC2 | RU3-UTL | 2300-U2JA/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-05 | 2026-02-14 | 2026-02-05 | 2026-12-08 | 2102361640 | 8202238660 |  | 8202225145#Instalasi Lampu PJU Jl.16, Ar | RU6-ITP | 42-P-930A-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 18795083 | 0 | MA4-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-08-28 | 2102353629 | 8202240646 |  | 8202225143#25_[CR] Replace piston rod 2n | RU4-UTL | 56K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 198697974 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353626 | 8202240644 |  | 8202225138#25_Kerusakan 260PDT184 di Kom | RU4-LOC3 | 260PDT184/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353625 | 8202240642 |  | 8202225137#25_Penggantian Control valve | RU4-LOC1 | 25PV006/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238349 | 8202235105 | 8202225135#Tag 2 Mekanik CDL, OM, UTL SG |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353463 | 8202236028 |  | 8202225131#Konsumable material saat pit | RU4-TRML | 41FSL006/00 | 60 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-08-10 | 2102362091 | 8202233708 |  | 8202225127#Penggantian ATS 42-T-305A | RU6-ITP | 42-T-305A/00 | 01 | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 15840 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238331 | 8202234582 | 8202225126#Tag 1 Perbaikan Korosi Atap T |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-03 | 2026-01-01 | 2026-01-01 | 2102353057 | 8202234582 |  | 8202225125#Perbaikan Korosi Atap Tangki |  |  | 60 | REL CNF PRT GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RAMADENY | 2026-06-08 | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357266 | 8202240640 |  | 8202225124#25_[CR] 012P103A indikasi coo | RU4-FOC2 | 012P103A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 65000000 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-08-28 | 2102355907 | 8202240638 |  | 8202225122#25_[CR] Perbaikan Power Foam | RU4-K3LL | FT35/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-15-C2H | 0 | 0 | WS-KAB |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355528 | 8202236520 |  | 8202225120#Penggantian Pre&After Filter | RU4-RFCUTL | 156A501A/00 | 50 WENG | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-25 | 2026-03-25 | 2026-03-30 | 2102359157 | 8202236259 |  | 8202225119#perbaikan motor vent degaser | RU5-UTL | DEMIN-123-LIS/00 | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 738181 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102360947 | 8202237498 |  | 8202225117#Perbaikan DC Charger ELOP 510 | RU4-UTL | 510G601P3M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1379454000 | 0 | MA5-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353948 | 8202240635 |  | 8202225114#25_Perbaikan Pompa 38P112B | RU4-TRML | 38P112B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 83841100 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353945 | 8202240633 |  | 8202225113#25_Perbaikan Pompa 38P112A | RU4-TRML | 38P112A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 83841100 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102354800 | 8202240631 |  | 8202225112#25_[CR] Cover MLOP 022K101 Bo | RU4-LOC2 | 022K101/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 1501000 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-24 | 2026-03-25 | 2026-03-30 | 2102359152 | 8202236260 |  | 8202225111#Perbaikan EaM-202-05B | RU5-D&W | EAM-202-05B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 683200 | 0 | MA1-LIS |  | SAPBATCH | 2026-03-25 | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-09 | 2025-12-09 | 2102359441 | 8202236261 |  | 8202225109#GT-3-17B: Turbine rusak | RU5-E15112 | GT-3-17B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 26707923 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-04 | 2026-02-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-11 | 2026-03-05 | 2026-03-05 | 2102354051 | 8202240629 |  | 8202225107#25_[CR] 92E409B, Penggantian | RU4-SRU | 92E409BM/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 1681501 | 0 | MA1-ROT |  | ABDULFM |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353092 | 8202234536 |  | 8202225106#Perbaikan P-33 CD II | RU3-CDGP | CD2-P-033/00 | 50 WAMA | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359440 | 8202236257 |  | 8202225104#PERB.LINE 19-18" ADO BWH BADN | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 164379490 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102359159 | 8202236256 |  | 8202225101#PERB.LINE 751-12" PIPERACK BA | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 161894169 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-06 | 2102353887 | 8202240627 |  | 8202225099#[CR] 011E121K09 Bearing defec | RU4-FOC2 | 011E121K09/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 13014829 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353880 | 8202236788 |  | 8202225097#D_25 015P102AM push button st | RU4-FOC2 | 015P102AM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102353769 | 8202240625 |  | 8202225094#25_KOPKIT 166 P 561B rusak (R | RU4-RFCGTO | 166P561B/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 210000 | 0 | MA7-ROT |  | FARIZSETYANA | 2026-05-21 | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238106 | 8202234623 | 8202225092#Tagihan Ke- 2 Pekerjaan Kontr |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-28 | 2102359819 | 8202236240 |  | 8202225085#Sparepart Sarana Tambat Jetty |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2040957067 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354271 | 8202240623 |  | 8202225082#25_Perbaikan 14TI-254 | RU4-FOC1 | 14TT254/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354229 | 8202240622 |  | 8202225081#25_Perbaikan 14TI-253 | RU4-FOC1 | 14TT253/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-08-31 | 2102353858 | 8202240620 |  | 8202225080#25_[CR] 015E107K01 Belt putus | RU4-FOC2 | 015E107K01/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354223 | 8202240618 |  | 8202225079#25_Perbaikan PSU PLC 14K602A | RU4-FOC1 | 14K602A/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 20176000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354034 | 8202240616 |  | 8202225078#25_Rotameter LT CPI selatan 2 | RU4-LOC3 | 200LT051/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 5 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353988 | 8202240614 |  | 8202225077#25_Perbaikan Level Varec 054T | RU4-UTL | 054LI004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-05-18 | 2026-05-18 | 2102351485 | 8202238156 |  | 8202225075#Penarikan Kabel auxilary pump | RU2-HOC | 140-FV-569/00 | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/NR-D2H | 725000000 | 688750000 | MA1-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 004
| K501 | 2026-02-02 | 2026-03-05 | 2026-02-03 | 2026-08-10 | 2102360416 | 8202236241 |  | 8202225069#Perbaikan Level Radiasi 05-LT | RU5-E15111 | 05-LT-349/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 120475278 | 0 | MA2-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102354950 | 8202240612 |  | 8202225067#25_[CR} Perbaikan coupling (n | RU4-LOC1 | 20P2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-10-29 | 2026-11-27 | 2102359381 | 8202236258 |  | 8202225061#Material drain dan venting Co | RU5-UTL | HHP-3/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 8105191 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-10-15 | 2026-11-05 | 2102359382 | 8202236255 |  | 8202225060#Perbaikan Gearbox GB-33-01 D |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 9925000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-15 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351410 | 8202232402 |  | 8202225057#Hydraulic Pump&gearbox FM Jet | RU2-PK | 970-P-3B/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-28 | 2102363511 | 8202233042 |  | 8202225051#Perbaikan Motor 20E108 | RU6-RCC | 20-E-108A-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102351649 | 8202232274 |  | 8202225050#970-P-3B Rusak | RU2-PK | 970-P-3B/00 | 50 | CRTD CSER NMAT PRC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102366037 | 8202240608 |  | 8202225049#25_Valve drain line BFW bocor | RU4-LOC3 | LN200-3004R/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-09 | 2026-01-23 | 2102359751 | 8202236223 |  | 8202225047#MAT. Perb. valve discharge 10 | RU5-E15112 | G-2-03C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 93072000 | 0 | MA3-STA |  | SAPBATCH | 2026-05-08 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-11-04 | 2102363503 | 8202233975 |  | 8202225046#LTSA Pemb. PSA 22-V-109A | RU6-DHC | 22-V-109A/00 | 01 | CRTD CSER NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354352 | 8202240606 |  | 8202225036#25_[CR] 011E116K01 belt putus | RU4-FOC2 | 011E116K01/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354187 | 8202240604 |  | 8202225034#25_[CR] Penggantian Belt 11E5 | RU4-FOC1 | 11E50K-G/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3171368 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354225 | 8202240602 |  | 8202225033#25_Perbaikan PSU PLC 14K602B | RU4-FOC1 | 14K602B/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 20176000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-08 | 2026-02-02 | 2026-09-29 |  | 8202236540 | 8202232730 | 8202225032#Welder Pipe Fitter Tahap 5 | RU6-RCC | 15-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-08 | 2026-02-02 | 2026-11-13 |  | 8202236544 | 8202232730 | 8202225031#Welder Pipe Fitter Tahap 4 | RU6-RCC | 15-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102354437 | 8202240600 |  | 8202225030#25_Perbaikan Sen Temp Cont 56 | UTL-UP4 | 56K302/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 3 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356622 | 8202240598 |  | 8202225029#25_Perbaikan 052TI401 Flue Ga | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 12358041 | 13336863 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354598 | 8202236918 |  | 8202225027#D_25 011P-111AM motor noise | RU4-FOC2 | 011P111AM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353852 | 8202236961 |  | 8202225024#D_25 011E117M04 motor noise | RU4-FOC2 | 011E117M04/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365535 | 8202240595 |  | 8202225023#25_[PV] Pengadaan Pompa Neutr | RU4-FOC1 | 11V7B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-03-31 | 2026-06-08 | 2102359276 | 8202236235 |  | 8202225022#Impeller degasser pump no.3 d | RU5-UTL | 3UA-03-D002/00 | 60 | TECO CNF CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 5515666 | 0 | MA1-ROT |  | SAPBATCH | 2026-06-02 | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365279 | 8202240592 |  | 8202225018#25_[CR] Perbaikan Ex Run GB F | RU4-RFCUTL | 153A501E/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 2 | 0 | MA5-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102354435 | 8202240589 |  | 8202225017#25_Perbaikan Sen Temp Cont 56 | RU4-UTL | 56DR201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 3 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358556 | 8202234514 |  | 8202225016#Mechanical Spreder Flange CDU |  |  | 60 WAMA | REL MACM PRC SETC | 7RT | D17/25/B6/NR-1-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-10-02 | 2102363508 | 8202233159 |  | 8202225013#Perbaikan Governor 15-K-102B- | RU6-RCC | 15-K-102B-T/01 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363663 | 8202232404 |  | 8202225011#Pengadaan Bare Compressor 560 | RU2-UTL | 560-GT-3/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359271 | 8202236208 |  | 8202225008#PENAMBAHAN FAS G/V 4" LINE SL | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 25476543 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102359389 | 8202236203 |  | 8202225006#K-3-02C: Perbaikan Cyl 1,4,6 | RU5-E15112 | K-3-02C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 399831077 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102359320 | 8202236205 |  | 8202225005#Ea-3-08A: V-Belt putus | RU5-E15112 | EA-3-08A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2374396 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102359323 | 8202236201 |  | 8202225004#Penggantian filter G-3-09C | RU5-E15112 | G-3-09C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 29493065 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354131 | 8202236397 |  | 8202225000#D25_FGDS SYSTEM FAULT | RU4-FOC2 | 001GD001/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-03 | 2026-01-05 | 2026-08-30 | 2102359326 | 8202236193 |  | 8202224998#Perbaikan Turbine GT-8-01B | RU5-E15112 | GT-8-01B/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359328 | 8202236196 |  | 8202224997#PERB.LINE 8" LPG PADA LDP 1/2 | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 33061018 | 0 | MA4-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237496 | 8202238634 | 8202224996#TGH5_24 UP Clean SWD Jet Pres | RU4-UTL | 54FIC304/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102359388 | 8202236200 |  | 8202224995#penggantian v belt fin-fan Ea | RU5-E15112 | EA-3-08B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2374396 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102359443 | 8202236194 |  | 8202224993#perbaikan fin-fan EA-8-11D | RU5-E15112 | EM-8-11D/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 7973484 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102359385 | 8202236197 |  | 8202224991#Perb Kabel Power ATG SS68 ke | RU5-D&W | 13-LT-D20-05D/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 8250594 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354185 | 8202240587 |  | 8202224987#25_Perbaikan 10LI-010A |  | 10LT010A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 2 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355344 | 8202240585 |  | 8202224986#25_Perbaikan 166FT-008 | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 4898274 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355343 | 8202240583 |  | 8202224985#25_perbaikan 166FT-007 | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 4898274 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-15 | 2026-02-03 | 2026-12-18 |  | 8202237809 | 8202233981 | 8202224982#Conmon dan PM/PdM PLC & MMS T | RU6-RCC | ES-B14-01/00 | 60 | TECO CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354165 | 8202240581 |  | 8202224981#25_[CR] Penggantian Silica Ge | RU4-FOC1 | 14K602B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354164 | 8202240579 |  | 8202224980#25_[CR] Penggantian Silica Ge | RU4-FOC1 | 14K602A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-17 | 2026-05-11 | 2102363513 | 8202233664 |  | 8202224977#Penggantian Dessicant Filter | RU6-RCC | 15-R-REGEN/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-24 | 2025-12-12 | 2026-12-29 | 2102356162 | 8202237493 |  | 8202224975#pemindahan panel 91K-402A | RU4-SRU | 91K402A/00 | 50 | REL GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 0 | 58500000 | MA1-INT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-05-06 | 2102359468 | 8202236189 |  | 8202224973#Cleaning Strainer SWD 2 |  |  | 50 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-05 | 2102359993 | 8202236190 |  | 8202224972#Bocor pada line converting 17 | RU5-UTL | TG2-PP2-2RF04-S/00 | 50 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-03-04 | 2102359667 | 8202236176 |  | 8202224969#GANTI NOZZLE FILTER POLISHER | RU5-UTL | D5-BV-2-1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102351539 | 8202232672 |  | 8202224967#Vibrasi tinggi | RU2-HCC | 211-EF-20C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 51600000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354594 | 8202240577 |  | 8202224965#25_Kerusakan 260PDT096 di Kom | RU4-LOC3 | 260PDT096/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354528 | 8202240575 |  | 8202224964#25_84FV222 pengikat glandpack | RU4-KPC | 84FV222/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238314 | 8202235233 | 8202224963#Tag 8 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-15 | 2026-02-02 | 2026-02-27 |  | 8202238293 | 8202234942 | 8202224962#Tag 12 PM Clean. PreHeater&Re | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-15 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233940 | 8202237800 | 8202224959#Material Consumable 22-R-102A | RU6-DHC | 22-R-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363504 | 8202233581 |  | 8202224957#Penggantian Microfilter 21-S- | RU6-DHC | 21-S-103B/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 |  | 8202236173 |  | 8202224956#Perbaikan pintu air OC R | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1869376 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102354353 | 8202237491 |  | 8202224954#TGH_1-2 Rejuvenate Kabel Moto | RU4-FOC2 | 014K102A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353091 | 8202234800 |  | 8202224953#Penggantian Expand Joint P-85 | RU3-CDGP | 85-P-201B/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355341 | 8202235743 |  | 8202224947#Perbaikan Motor Seal Air Fan | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-09-15 | 2102354137 | 8202240573 |  | 8202224946#25_[CR] Penggantian Shear Pin | RU4-LOC2 | 024E102B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 1273080 | 1273080 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238279 | 8202235151 | 8202224942#Tag. 12 Pek. Cleaning dan Gan | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238278 | 8302404176 | 8202224941#Tag 6 Pemeliharaan Mini Excav | RU3-LKKK | LK-CT155/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-09-03 | 2026-10-15 | 2102359387 | 8202236172 |  | 8202224936#Casing & Stuffing Box Pompa G | RU5-D&W | G-202-07A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 218000000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-09-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102359557 | 8202236168 |  | 8202224933#Reposisi OPGD Tangki A23 dan | RU5-E15112 | 019-GC-001A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 16050000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237489 | 8202237508 | 8202224928#TGH3_24 UP Perpipaan & Akseso | RU4-UTL | LN52-104VA/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237487 | 8202237527 | 8202224927#TGH5_24 UP Clean HE Utl | RU4-UTL | 51E3/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356982 | 8202240571 |  | 8202224925#25_[CR] Perbaikan Bearing Hou | RU4-RFCC | 101P501A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355674 | 8202236340 |  | 8202224922#D25_Perbaikan flame ignitor | RU4-RFCUTL |  | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355619 | 8202236327 |  | 8202224919#D25_Perbaikan flame ignitor 1 | RU4-RFCUTL |  | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355671 | 8202236332 |  | 8202224918#D25_Perbaikan flame ignitor | RU4-RFCUTL |  | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354908 | 8202236654 |  | 8202224917#D_25 Motor 021P-115 noise | RU4-LOC2 | 021P115/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102355267 | 8202240569 |  | 8202224916#25_Perbaikan Solenoid Dryer 5 | RU4-UTL | 560DR301/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 124500000 | 0 | MA5-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355059 | 8202240567 |  | 8202224915#25_011PDT010B rusak | RU4-FOC2 | 011PDT010B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355053 | 8202240565 |  | 8202224914#25_Perbaikan TSH 63-P101A/P10 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K202 | 2026-02-02 | 2026-06-03 | 2026-06-11 | 2026-11-30 | 2102352615 | 8202234200 |  | 8202224913#Kebocoran Stuffing Box 101-P- | RU2S-KIL | 101-P-6C/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2RS | D12/26/B6/RTZ-C2H | 5355969 | 5355969 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355051 | 8202240542 |  | 8202224912#25_Perbaikan TSH 63-P201 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354959 | 8202240529 |  | 8202224911#25_Perbaikan TSH 63-P1/P2/P3 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 3 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355268 | 8202236466 |  | 8202224910#D25_011HV004 ground fault | RU4-FOC2 | 011F101A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355151 | 8202236300 |  | 8202224909#D25_Perbaikan Turbine Flow Me | RU4-RFCGTO | 105FI-U105/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354900 | 8202240500 |  | 8202224908#25_Perbaikan analyzer cond ou | RU4-RFCUTL | 154A503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354714 | 8202240496 |  | 8202224904#25_Perbaikan Diaprahma 101PCV | RFCC-UP4 | 101K501T-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354712 | 8202240492 |  | 8202224903#25_Penggantian Assy 101PCV-60 | RFCC-UP4 | 101K501T-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102359598 | 8202236167 |  | 8202224894#Fabrikasi Bushing Crosshead K | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358557 | 8202234485 |  | 8202224892#Pengadaan V-belt Kompresor 2- | RU7-NHT | 2-K-01-02/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-02-04 | 2102363796 | 8202238027 |  | 8202224878#Cleaning Bak OPT (Off Product | RU2-ITP | SPRT-1/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 842700000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2027-06-24 | 2102354830 | 8202241416 |  | 8202224877#25_Perbaikan pompa 91P-408 | RU4-SRU | 91P408/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 65947107 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354804 | 8202240488 |  | 8202224875#25_[CR] penggantian belt 16K2 | RU4-FOC1 | 16K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355345 | 8202240484 |  | 8202224874#25_[CR] Penggantian belt 16K2 | RU4-FOC1 | 16K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102355093 | 8202240480 |  | 8202224873#25_[CR] 012K101B Valve Defect | RU4-FOC2 | 012K101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 498666949 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-15 | 2026-03-09 | 2026-03-09 | 2102354802 | 8202241415 |  | 8202224872#25_[CR] Penggantian mechseal | RU4-FOC1 | 11K401A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 122749350 | 0 | MA1-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K301 | 2026-02-05 | 2026-02-14 | 2026-02-06 | 2026-02-06 | 2102353095 | 8202238656 |  | 8202224869#Perbaikan Pompa P-54-005A BFW | RU3-UTL | 54-P-005A/00 | 50 | REL NMAT PRC SETC | 3RR | D13/25/B6/NR-5-D2H | 29500000 | 0 | MA3-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-06 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102359444 | 8202236143 |  | 8202224867#Perbaikan pompa G-202-02B | RU5-D&W | G-202-02B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 2636520 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102355487 | 8202240474 |  | 8202224861#25_[CR] 011E111K3 Belt putus | RU4-FOC2 | 011E111K03/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 1275000 | 1275000 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356983 | 8202240470 |  | 8202224856#25_[CR] Perbaikan Cooler Mech | RU4-RFCC | 102P507A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2025-10-29 | 2102352586 | 8202234199 |  | 8202224854#Perbaikan Residue Loading Pum | RU2S-KIL | 946-P-3A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 |  | 8202236794 |  | 8202224853#penggantian kerangan rack H2 |  |  | 50 WAMA | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363704 | 8202232468 |  | 8202224851#pekerjaan insulasi tipe perso | RU2-HCC | 211-PIPING/00 | 01 | CRTD NMAT PRC | 2MR | D12/10/B6/RT1-211NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102366038 | 8202240466 |  | 8202224850#25_Kebuntuan Vacum Ejector HE | RU4-LOC3 | 240E140A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-9-C2H | 2245766 | 0 | MA4-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-08-28 | 2102355097 | 8202240462 |  | 8202224836#25_[CR] Bearing 054P105AT Hea | RU4-UTL | 054P105A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 74194942 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-17 | 2102361747 | 8202232806 |  | 8202224835#Permanent Repair FDF 052-B-10 | RU6-UTL | 052-B-101B-K-101/0 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 27984 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-09-15 | 2102355413 | 8202240459 |  | 8202224831#25_[CR] Perbaikan turbine 54P | RU4-UTL | 54P1A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 206902 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-01 | 2026-02-01 | 2102351533 | 8202232667 |  | 8202224827#Pengadaan material sarfas ADO | RU2-ITP | 990-P-52/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/10/B6/RT1-JSRNH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-01 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-03-16 | 2102363498 | 8202232875 |  | 8202224826#Perbaikan Soot Blower 052-B-1 | RU6-UTL | 052-B-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1362 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353737 | 8202240456 |  | 8202224824#25_Penggantian Transmitter 91 | RU4-SRU | 91FIT109/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356291 | 8202240453 |  | 8202224822#25_48LT201 rusak | RU4-TRML | 48LT201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356075 | 8202240450 |  | 8202224821#25_88PSL Hydolik Rotary valve | RU4-KPC | DCS-KPC/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 2 | 81388000 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352590 | 8202234198 |  | 8202224819#Pengecekan Relay Protection 1 | RU2S-KIL | 101-PI-018B/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355206 | 8202240447 |  | 8202224818#25_Pembacaan indikator speed | RU4-KPC | 81A201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 3 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-03 | 2026-05-05 | 2026-10-30 | 2102352591 | 8202234197 |  | 8202224817#Error Breaker Relay Protectio | RU2S-KIL | 900-06TR-H-01/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 101000000 | 101000000 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355095 | 8202240445 |  | 8202224816#25_Penggantian 014LT-014 | RU4-FOC2 | 014LT014/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355057 | 8202240443 |  | 8202224815#25_Penggantian 011FT-012 | RU4-FOC2 | 011FT012/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355262 | 8202236249 |  | 8202224814#Fasilitas hose steam untuk ar |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238277 | 8202234832 | 8202224813#Tagihan Ke- 17 Pekerjaan Perb |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-03 | 2026-02-20 | 2026-02-03 | 2026-02-03 | 2102363830 | 8202237469 |  | 8202224810#TSA MECH SEAL JOHN CRANE HCC | RU2-HCC | 211-P-1A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 200000000 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-18 | 2026-02-18 | 2102364377 | 8202238260 |  | 8202224809#Line MPA & Gas Bocor | RU2-HSC | 8-SW-210-NA/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1852000001 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-14 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102362849 | 8202233791 |  | 8202224808#Pengadaan Material Kebutuhan | RU6-RCC | 15-R-REGEN/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355055 | 8202240441 |  | 8202224807#25_Perbaikan motor 063P101BM | RU4-UTL | 63P101BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 24162556 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359553 | 8202236133 |  | 8202224799#Perb JB/Kabel Penerangan area | RU5-TBL | PLANT-22-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 36538914 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-03-30 | 2026-02-03 | 2026-08-18 | 2102360440 | 8202236129 |  | 8202224798#Perb. Temp. Switch TSHH K-5-0 | RU5-E15111 | 05-TCV-729A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/09/B6/RT1-05NH | 50925000 | 0 | MA2-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-23 | 2102360286 | 8202236130 |  | 8202224797#Perb. Temp Switch 05-TSH-881, | RU5-E15111 | K-5-01/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 16975000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359514 | 8202236123 |  | 8202224796#Perbaikan Selenoid tripping F | RU5-UTL | 1NV00S100/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 45000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353420 | 8202240439 |  | 8202224794#25_Perbaikan Bocoran Tube 157 | RU4-RFCUTL | 157E501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 004
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-10 |  | 8202236132 |  | 8202224793#Perb. Line discharge pompa V | RU5-UTL | 32-ACW-117-A7/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 78844168 | 0 | MA1-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-04-30 | 2026-12-29 | 2102359513 | 8202236134 |  | 8202224792#Penggantian ACB di SS 67 | RU5-UTL | 41-R-SS-67-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 1800000000 | 0 | MA4-LIS |  | AGUSHIDAYAT |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360980 | 8202234622 |  | 8202224783#RKA2025_Perbaikan Plenum Finf | RU4-KPC | 82E201A/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-06-19 | 2026-02-03 | 2026-02-03 |  | 8202235096 |  | 8202224781#RKAP25_pengg clay 85C206B,87C | RU4-KPC | 89C201/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | AKHMADRIZAL |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 | 2102364374 | 8202238259 |  | 8202224780#TGH1_REJUV_ISOLASI_PIP_MA4 | RU4-KPC | LN39-DW8001MS24/00 | 50 | CRTD NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-10-07 | 2102359555 | 8202236124 |  | 8202224775#Perbaikan PLC pompa G-32-05 C | RU5-E15112 | 32-FT-008/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-10-07 | 2102363495 | 8202232972 |  | 8202224771#Perbaikan Pompa 24-P-305 B (S | RU6-HSC | 24-P-305B/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 6400000 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359255 | 8202236126 |  | 8202224770#Perbaikan Clarifier no.1 & 2 | RU5-UTL | CHEM-P2-WTP-IV/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 4887488 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2027-01-06 | 2027-01-06 | 2102359517 | 8202236128 |  | 8202224768#Perbaikan Bearing Guillotine | RU5-E15111 | F-1-01B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2027-01-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359661 | 8202236135 |  | 8202224767#MAT.PERB.LINE BALLAST 16" DPN | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 184510057 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102359725 | 8202236136 |  | 8202224766#MAT.PERB.LINE 21-P914-10"-B20 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 94386072 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-28 | 2102359554 | 8202236139 |  | 8202224763#Journal Bearing FDF 4 Turbin | RU5-UTL | T-FDF-HHP-4/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 147185634 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K201 | 2026-02-05 |  | 2026-02-05 | 2026-02-05 | 2102351538 | 8202238624 |  | 8202224762#Sertifikasi Persetujuan Layak | RU2-HSC |  | 50 | CRTD NMAT PRC | 2MR | D12/22/B6/RT-D2H | 2768715000 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-04 | 2026-02-04 |  | 8202238120 | 8202234916 | 8202224760#Tagihan Ke- 12 Pekerjaan Perb |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-18 | 2026-02-04 | 2026-02-04 |  | 8202238131 | 8202234916 | 8202224759#Tagihan Ke- 10 Pekerjaan Perb |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-18 | 2026-02-03 | 2026-02-03 |  | 8202236777 | 8202234916 | 8202224758#Tagihan Ke- 9 Pekerjaan Perba |  |  | 60 | CLSD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-18 | 2026-02-03 | 2026-02-03 |  | 8202236846 | 8202234916 | 8202224757#Tagihan Ke- 8 Pekerjaan Perba |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-11 |  | 8202236554 | 8202232770 | 8202224755#TKDN LTSA Transformator Tahap | RU6-UTL | SS-01/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 49295700 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-11 |  | 8202236557 | 8202232770 | 8202224754#TKDN LTSA Transformator Tahap | RU6-UTL | SS-01/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 36464700 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-11 |  | 8202236559 | 8202232770 | 8202224753#TKDN LTSA Transformator Tahap | RU6-UTL | SS-01/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 27331200 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-12-11 |  | 8202236562 | 8202232770 | 8202224752#TKDN LTSA Transformator Tahap | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-12-11 |  | 8202236564 | 8202232770 | 8202224751#TKDN LTSA Transformator Tahap | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-12-11 |  | 8202236551 | 8202232770 | 8202224749#TKDN LTSA Transformator Tahap | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-12-11 |  | 8202236553 | 8202232770 | 8202224748#TKDN LTSA Transformator Tahap | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-27 | 2025-12-29 | 2102359515 | 8202236121 |  | 8202224740#Ganti Valve Distribusi Area G | RU5-UTL | PIPA-WTP-PCR/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 13068873 | 0 | GM-SIP |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-18 | 2102359866 | 8202236118 |  | 8202224739#Perbaikan DS PKBBM & TL TSA | RU5-TBL | 22-DPIT-505A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 112 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-09 | 2102362269 | 8202237807 |  | 8202224736#Pemb. LTSA Sparing Termin 1 N | RU6-LAB | LABORATORIUM/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102363467 | 8202233154 |  | 8202224735#Perbaikan instrumentasi 12-PT | RU6-DHC | 12-PT-751/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363652 | 8202232384 |  | 8202224734#Perbaikan belting HVAC ES#1 | RU2-UTL | 905-LPN-ES1/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351641 | 8202232444 |  | 8202224733#Perbaikan 905-TG-01 | RU2-UTL | 905-ME-56/00 | 60 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102363499 | 8202233126 |  | 8202224732#Perbaikan Lampu Penerangan Ar | RU6-DHC | 14-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-10 | 2026-04-02 | 2026-12-30 | 2102353931 | 8202237485 |  | 8202224731#Penambahan UPS 1 Phase Metrin | RU4-TRML | POSITIONER-U041/00 | 60 | REL GMPS NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 376000000 | 75200000 | MA3-INT |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102359558 | 8202236120 |  | 8202224728#Penggantian Kabel Feeder Jett | RU5-TBL | DER-JT-05/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1380000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102359781 | 8202236117 |  | 8202224727#Perbaikan Kabel Feeder Meter | RU5-TBL | 22-DPIT-01-501/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 200400000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-24 | 2025-12-24 | 2102359665 | 8202236095 |  | 8202224725#Pengadaan PortablePump Diesel | RU5-E15112 |  | 60 | CLSD CNF NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-10 | 2026-02-04 | 2026-02-04 | 2102353220 | 8202238026 |  | 8202224722#Pekerjaan Perbaikan Kantor PP |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 850000000 | 0 | GEN-STA |  | HARISASEPWIJ |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-10-01 | 2102363493 | 8202233131 |  | 8202224720#Perbaikan kompresor 63-K-401B | RU6-ITP | 63-K-401B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 95040 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-12-07 |  | 8202236622 | 8202233855 | 8202224719#SWO Pemb. LTSA Sparing Termin | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-09 | 2102362301 | 8202237805 |  | 8202224717#Pemb. LTSA Sparing Termin 2 N | RU6-LAB | LABORATORIUM/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-09 |  | 8202237803 | 8202233855 | 8202224713#Pemb. TKDN LTSA Sparing Termi | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-09 |  | 8202237801 | 8202233855 | 8202224712#Pemb. TKDN LTSA Sparing Termi | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359724 | 8202236101 |  | 8202224710#MAT.PERB.LINE 963- 10" MFO AR | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 144827979 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353738 | 8202236699 |  | 8202224707#Penggantian Line 30" Press 38 |  |  | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360177 | 8202236102 |  | 8202224706#MAT.PERB.LINE 617-4" HVGO(SLO | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 12443955 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361141 | 8202236911 |  | 8202224705#Penggantian Check Valve 46P10 | RU4-TRML | 46P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361140 | 8202236909 |  | 8202224704#Penggantian Check Valve 46P10 | RU4-TRML | 46P101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356262 | 8202236125 |  | 8202224701#Perbaikan Check Valve 40P2 |  |  | 50 WENG | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360131 | 8202236104 |  | 8202224700#MAT.MOC NO.11114/RUV LINE SF0 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 29227211 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356343 | 8202240437 |  | 8202224699#25_87FV204A positioner rusak | RU4-KPC | 87FV204A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355964 | 8202240435 |  | 8202224698#25_Perbaikan 14PDT-504 | RU4-FOC1 | 14PDT504/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 35333333 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355962 | 8202240433 |  | 8202224697#25_Perbaikan 14PDT-503 | RU4-FOC1 | 14PDT503/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 35333334 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355960 | 8202240431 |  | 8202224696#25_Perbaikan Flow Transmitter | RU4-FOC1 | 14FT507/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 35333333 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355714 | 8202240429 |  | 8202224695#25_87FT222 rusak | RU4-KPC | 87FT222/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355264 | 8202237483 |  | 8202224694#Pengadaan Nitrogen untuk area |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 100000 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355419 | 8202240426 |  | 8202224693#25_Perbaikan Kerusakan 92TIC- | RU4-SRU | 92TIT159/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 28000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355416 | 8202240423 |  | 8202224692#25_Perbaikan Kerusakan 92TIC- | RU4-SRU | 92TIT154/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 28000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102362763 | 8202236734 |  | 8202224690#SPK LTSA Maintenance Bawah Ai | RU6-ITP | 41-A-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102362795 | 8202236731 |  | 8202224688#SPK LTSA Maintenance Bawah Ai | RU6-UTL | 56-CT-101A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360130 | 8202236103 |  | 8202224687#MAT.PERB.LINE 22P20-10"-B20 A | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 6148061 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-02-08 | 2026-04-17 | 2026-01-02 | 2026-01-02 | 2102363718 | 8202238744 |  | 8202224685#25L_Peremajaan WWT | RU4-SRU | 166A563A/00 | 50 | CRTD CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 100 | 0 | MA7-STA |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-30 | 2025-12-30 | 2102359597 | 8202236074 |  | 8202224684#Perbaikan Motor GM-8-04C | RU5-E15112 | GM-8-04C/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 3424966 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102355561 | 8202236608 |  | 8202224683#Penggantian motor 46P1BM | RU4-TRML | 46P1BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353456 | 8202240421 |  | 8202224682#25_Penggantian Damper 1 Set A | RU4-RFCC | 101F504/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-19 | 2025-12-05 | 2026-09-11 | 2102363486 | 8202233928 |  | 8202224681#Material Perbaikan PM Y1 15-P | RU6-RCC | 15-P-101C-T/00 | 50 WAMA | REL CSER MANC PRC SETC | 6RR | D16/25/B6/RT-C2H | 10661049 | 0 | MA1-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356625 | 8202240420 |  | 8202224680#25_PCV Tank 106T501 Tidak Bek | RU4-RFCGTO | 106T501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356496 | 8202240418 |  | 8202224679#25_Perbaikan 56TI385A/B | RU4-UTL | 056TT385A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 2264502 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356341 | 8202240416 |  | 8202224676#25_87FT202 rusak | RU4-KPC | 87FT202/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356297 | 8202240414 |  | 8202224674#25_82PDT238 rusak | RU4-KPC | 82PDT238/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356590 | 8202235599 |  | 8202224673#Perbaikan pondasi 011P103B | RU4-FOC2 | 011P103B/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102356065 | 8202240412 |  | 8202224672#25_Pressure Transmitter N2 88 | RU4-KPC | 88T201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 57500000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356029 | 8202240410 |  | 8202224671#25_82PT265 rusak | RU4-KPC | 82PT265/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356026 | 8202240408 |  | 8202224670#25_82PT251 rusak | RU4-KPC | 82PT251/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355137 | 8202237231 |  | 8202224666#CM_Kebocoran Sour Water Line | RU4-FOC2 | 017V101/00 | 50 WAMA WENG | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102360173 | 8202236108 |  | 8202224665#Ganti filter L/O G-3-35 EF: | RU5-E15112 | G-3-35F/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 28066000 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360307 | 8202236115 |  | 8202224661# Perb. CV & BV Pompa Sump OC | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 4290384 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360304 | 8202236106 |  | 8202224660#Ganti Valve 10" Bypass Pengis | RU5-UTL | PIPA-WTP-PCR/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 54827230 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-18 | 2102359785 | 8202236099 |  | 8202224658#MAT.PERB.PIPING PEMADAM DI JE | RU5-E15500 | JT5B-FWLB-006/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 922774 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353141 | 8202234547 |  | 8202224656#Perbaikan P-1 CDU 2 | RU3-CDGP | CD2-P-001/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353309 | 8202234533 |  | 8202224655#Perbaikan P-36 CDU IV | RU3-CDGP | CD4-P-036/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354197 | 8202236152 |  | 8202224654#Gasket insulasi 041T119 bocor | RU4-TRML | 041T119/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354196 | 8202236156 |  | 8202224653#Gasket insulasi 041T116 bocor | RU4-TRML | 041T116/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353459 | 8202234990 |  | 8202224652#Service motor 24P13A | RU4-LOC1 | 24P13AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102354506 | 8202240406 |  | 8202224651#25_Pengadaan Consumable Mater | RU4-REL |  | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 10440097 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353461 | 8202234988 |  | 8202224650#Service motor 24P9A | RU4-LOC1 | 24P9AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354192 | 8202236162 |  | 8202224649#Gasket insulasi 041T113 bocor | RU4-TRML | 041T113/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353199 | 8202234471 |  | 8202224648#NR_Perbaikan P-7 Stab C | RU3-CDGP | STA-P-007/00 | 60 | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354194 | 8202236158 |  | 8202224645#Gasket insulasi 041T114 bocor | RU4-TRML | 041T114/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353460 | 8202234989 |  | 8202224644#Service motor 24P2B | RU4-LOC1 | 24P2BM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362948 | 8202232743 |  | 8202224643#Resertifikasi 52-B-101A | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 221830 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353458 | 8202234992 |  | 8202224641#Service motor 23P8 | RU4-LOC1 | 23P8M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361191 | 8202237256 |  | 8202224640#CM_011P106C Lasan Check Valve | RU4-FOC2 | 011P106C/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-05-07 | 2026-01-02 | 2026-12-30 | 2102355909 | 8202237606 |  | 8202224639#Penggantian push button LOC I |  |  | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 100 | 0 | MA2-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361192 | 8202237257 |  | 8202224638#CM_011P103B Flange Check Valv | RU4-FOC2 | 011P103B/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353457 | 8202234994 |  | 8202224635#Service motor 22P2A | RU4-LOC1 | 22P2AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102359814 | 8202236105 |  | 8202224634#MAT.GANTI GATE VALVE TANK WAT | RU5-UTL | PIPA-WTP-PCR/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 53763032 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361206 | 8202237317 |  | 8202224633#Battery Limit 011 Bocoran lin | RU4-FOC2 | 011V111/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 001
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355873 | 8202237014 |  | 8202224632#D_25 011E-121M7 meger rendah | RU4-FOC2 | 011E121M07/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-30 | 2102360200 | 8202236077 |  | 8202224631#Perbaikan Converting 60/17A P | RU5-UTL | TG4-PP1-AV-101/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 75000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355310 | 8202236648 |  | 8202224630#D_25 Motor finfan 240E116B ru | RU4-LOC3 | 240E116M2/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-18 | 2102360201 | 8202236079 |  | 8202224628#PERBAIKAN converting 17/3.5 n | RU5-UTL | 0RA00P001/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 25000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102360287 | 8202236075 |  | 8202224627#PERBAIKAN LEVEL TRANSMITTER 0 | RU5-E15112 | 03A-LT-402/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 30000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-02-03 | 2026-08-10 | 2102360242 | 8202236071 |  | 8202224626#Perbaikan Sample Cooler 05-AI | RU5-E15111 | 05-AIT-120/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 95800000 | 0 | MA2-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353733 | 8202236646 |  | 8202224625#D_25 Motor finfan 260E122 AM1 | RU4-LOC3 | 260E122AM1/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355712 | 8202236708 |  | 8202224624#D_25 82E202AM rusak | RU4-KPC | 82E202A/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102355677 | 8202240354 |  | 8202224623#25_Pengadaan bearing motor 24 | RU4-LOC3 | 240P102BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 4597200 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-06-30 | 2102363488 | 8202237800 |  | 8202224621#Penggantian Katalis 22-R-102A | RU6-DHC | 22-R-102A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 95000000 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102355789 | 8202240351 |  | 8202224619#25_[CR] Penggantian battray N |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102355676 | 8202240305 |  | 8202224618#25_[CR] Penggantian Filter Lu | RU4-FOC1 | 14K602BM-S1S2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3335556 | 3334091 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102355648 | 8202240302 |  | 8202224613#25_[CR] Penggantian Filter Lu | RU4-FOC1 | 14K602BM-S1S2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3334091 | 3334091 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-11-12 | 2102363235 | 8202233417 |  | 8202224606#Perbaikan 11-PTR1-01A | RU6-HSC | 11-PTR1-01A/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-04 | 2102359669 | 8202236068 |  | 8202224604#MAT.MOC Jalur Spillback G-1-2 | RU5-E15111 | G-1-22A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 39275266 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-11-02 | 2102362841 | 8202237799 |  | 8202224602#BUILT UP 20-R-101C - Tahap 3 | RU6-RCC | 20-R-101C/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-08 | 2026-03-14 | 2026-01-02 | 2026-01-02 | 2102356493 | 8202238758 |  | 8202224601#25_Penggantian Valve Manual K |  |  | 50 | CRTD CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 100000 | 0 | MA3-LIS |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-08 | 2026-04-17 | 2026-01-02 | 2026-01-02 | 2102356490 | 8202238745 |  | 8202224600#25_Penggantian Valve Manual K |  |  | 50 | CRTD CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 100 | 0 | MA3-LIS |  | FARIZSETYANA |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-10-13 |  | 8202237798 |  | 8202224595#Penyelesaian Pek. PM PDM EI M | RU6-UTL | 01-PSW2-01A-006/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-11-04 | 2102362303 | 8202233855 |  | 8202224592#Pemb. LTSA Sistem SPARING Gat | RU6-LAB | LABORATORIUM/00 | 01 | CRTD CSER NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-09-15 | 2102353513 | 8202240298 |  | 8202224589#25_[PV] Penyehatan Turbin MLO | RU4-UTL | 051G101P1T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 3747455 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102360172 | 8202236065 |  | 8202224587#Perbaikan Motor Em-8-10A | RU5-E15112 | EM-8-10A/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 8809948 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K401 | 2026-02-08 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102355966 | 8202238757 |  | 8202224586#25_166K-551AM, penggantian dr | RU4-RFCUTL | 166M551/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 100000 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-04-23 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-07-30 | 2102356182 | 8202240294 |  | 8202224585#25_[CR] Perbaikan Pompa 101P5 | RU4-RFCC | 101P522B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2025-12-29 | 2025-12-29 | 2102359722 | 8202236063 |  | 8202224583#Perbaikan Motor GM-2-07A | RU5-E15112 |  | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 305464 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-09-15 | 2102356714 | 8202240290 |  | 8202224582#25_[CR] Perbaikan pompa 54P20 | RU4-UTL | 54P203A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 1026950000 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-03-26 | 2102363468 | 8202233544 |  | 8202224577#Penggantian positioner 22-V-1 | RU6-DHC | 22-V-109C/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-05 | 2026-03-04 | 2026-02-02 | 2026-12-31 | 2102356442 | 8202238638 |  | 8202224576#[CR] Perbaikan brake system F | RU4-WS | FL45/00 | 50 | REL CSER GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 58518758 | 49740944 | WS-KAB |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353619 | 8202236321 |  | 8202224575#Penyehatan Stationary IPAL 47 | LOC1-UP4 | 47S507A-M1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353731 | 8202235182 |  | 8202224574#Pipa 8 inch 11V2 ke SRU bocor | RU4-FOC1 | 11V2/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354503 | 8202237246 |  | 8202224573#CM_Kebocoran Piping 106LPC090 | RU4-GTO |  | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-10-12 |  | 8202236839 | 8202233979 | 8202224572#PM 6 - LTSA FGDS General Moni | RU6-ITP | 42-T-301A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-10-12 |  | 8202236644 | 8202233851 | 8202224571#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-10-12 |  | 8202236647 | 8202233851 | 8202224570#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102355572 | 8202235615 |  | 8202224569#Perbaikan plenum finfan 91K-4 | RU4-SRU | 91K401AEM/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102357776 | 8202234771 |  | 8202224567#Pengadaan gland packing chill | RU4-LOC1 | 24E2A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353632 | 8202235211 |  | 8202224566#Perpanjangan kontrak cleaning | RU4-FOC1 | 11E25/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102356133 | 8202240285 |  | 8202224565#25_[NP] 048P104B Mech Seal bo | RU4-FOC2 | 019P122B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 65909405 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361134 | 8202236815 |  | 8202224563#Penggantian HE Assy 93E402B | RU4-SRU | 93E402B/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361211 | 8202237329 |  | 8202224562#93E-402A, Penggantian HE assy | RU4-SRU | 93E402A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102365684 | 8202240282 |  | 8202224560#25_[CR] Perbaikan Pompa 14P65 | RU4-FOC1 | 14P650B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 52801465 | 52800000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365956 | 8202240277 |  | 8202224558#25_Penggantian LEVEL TRANSMIT | RU4-RFCUTL | 110LT-U110/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356674 | 8202240274 |  | 8202224557#25_pengadaan transmitter 14FT | RU4-FOC1 | 14FT376/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353508 | 8202235979 |  | 8202224552#Line drain 23C5 to sewer boco | RU4-LOC1 | 23C5/00 | 50 WENG | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353477 | 8202235247 |  | 8202224551#Perbaikkan Line CW 14E613 | RU4-FOC1 | 14E613/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102353476 | 8202234760 |  | 8202224549#Pengadaan Kontrak OLLS di FOC |  |  | 50 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356061 | 8202240270 |  | 8202224548#25_Pressure Gauge 84F201 rusa | RU4-KPC | 84F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 20 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361010 | 8202235171 |  | 8202224547#Pemasangan olls di11TI013 | RU4-FOC1 | 11F1DS1B/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102356023 | 8202240266 |  | 8202224546#25_Pressure Gauge N2 Tanki 39 | RU4-TRML | 39T201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 20 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361067 | 8202236209 |  | 8202224545#Perbaikan boardesk Unit 95 | RU4-SRU | 95V403/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361068 | 8202236210 |  | 8202224544#Perbaikan boardesk Unit 94 | RU4-SRU | 94R401/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361069 | 8202236211 |  | 8202224543#Perbaikan boardesk Unit 93 | RU4-SRU | 93V402/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102355877 | 8202236366 |  | 8202224542#D25_Penggantian actuator 048P | RU4-TRML | 048PT001/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-26 | 2025-11-26 | 2102355875 | 8202236367 |  | 8202224541#D25_Penggantian Actuator 014K | RU4-FOC2 | 014K101/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102356186 | 8202240262 |  | 8202224540#25_[CR] Bocoran Mech Seal 107 | RU4-RFCGTO | 107P503A/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 8244450 | 0 | MA7-ROT |  | FARIZSETYANA | 2026-05-21 | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238256 |  | 8202224538#Tag 18 TSA Pemeliharaan Vacuu | RU3-ITP | 039-P-007/00 | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2102360281 | 8202236070 |  | 8202224537#Indikasi Slipring STG 2.3 abn | RU5-UTL | PP-2-LIS/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 82130076 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-12 | 2102362855 | 8202233352 |  | 8202224536#Perbaikan 15-E-110AP | RU6-RCC | 15-E-110AP-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-12 | 2102362673 | 8202233383 |  | 8202224533#Perbaikan 12-PTR1-01A | RU6-DHC | 12-PTR1-01A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 28484000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-06-05 | 2102359864 | 8202236066 |  | 8202224532#pelumasan Exciter STG 2.1 | RU5-UTL | TG-1-PP2/00 | 60 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 63690188 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102356020 | 8202241414 |  | 8202224531#25_[CR] Perbaikan Mech seal ( | RU4-LOC1 | 24P10/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 99016500 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-03-04 | 2102360417 | 8202236069 |  | 8202224530#MAT. Perb. Deluge Valve Plant | RU5-E15500 | 3B-DV-150B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 14439834 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102356246 | 8202240255 |  | 8202224527#25_[CR] Perbaikan 24K-1P1AT | RU4-LOC1 | 24K1P1A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 186048500 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-13 | 2102363006 | 8202233054 |  | 8202224526#Perbaikan Motor 15E110B | RU6-RCC | 15-E-110B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-03-30 | 2102363445 | 8202233060 |  | 8202224518#Perbaikan Motor 15-E-110 H | RU6-RCC | 15-E-110H-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 74711 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-03-30 | 2102363426 | 8202233237 |  | 8202224515#Perbaikan Bearing 16-E-117AB | RU6-RCC | 16-E-117AB/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 74711 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 |  | 8202236043 |  | 8202224510#MAT.GANTI BUTRFLY VALVE 12" S | RU5-TBL | PIPE-ON-SHORE/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 27995200 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363821 | 8202238170 |  | 8202224509#thermograph | RU2-HSC | 100-H-1/00 | 50 | CRTD NMAT PRC RELR SETC | 2MR | D12/25/B6/RT-D2H | 500000000 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353443 | 8202240251 |  | 8202224506#25_[NP] 47S506B-P1, Perbaikan | LOC1-UP4 | 47S506B-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-10-19 | 2102356447 | 8202237594 |  | 8202224503#Mstr Data Peralatan & Prog Pe | RU4-TRML | 31P2A/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-03-25 | 2102361889 | 8202233299 |  | 8202224500#Perbaikan 23-PI-011 | RU6-HSC | 23-V-101/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2025-12-12 | 2026-05-06 | 2102362935 | 8202233010 |  | 8202224499#Perbaikan PI discharge 16-K-1 | RU6-RCC | 16-K-102-P1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353438 | 8202240247 |  | 8202224498#25_Perbaikan VSD 14P611M & 14 | RU4-FOC1 | 14P611M/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 179828000 | 179828000 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-13 | 2025-12-12 | 2026-05-06 | 2102362898 | 8202233075 |  | 8202224497#Perbaikan Modul converter 15P | RU6-RCC | 15-S-103-S2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-29 | 2025-12-29 | 2102359723 | 8202236011 |  | 8202224495#Perbaikan Motor Gm-3-02C | RU5-E15112 | GM-3-02C/00 | 60 | CLSD CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-23 | 2102359991 | 8202236038 |  | 8202224492#Perbaikan Control Valve Area | RU5-E15112 | 08-FCV-013/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1522462224 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-06 | 2102360489 | 8202236036 |  | 8202224491#Perbaikan Level Tangki Solar |  |  | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 400348 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102366034 | 8202240243 |  | 8202224489#25_Pengadaan gun burner 021F1 | RU4-LOC2 | 021F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-09 | 2026-06-11 | 2026-03-09 | 2026-09-02 | 2102353395 | 8202241405 |  | 8202224488#25_Perbaikan Pompa 80P201B | RU4-KPC | 80P201B/00 | 60 | TECO CNF CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 83944000 | 0 | MA4-ROT |  | SAPBATCH | 2026-06-11 | 2026-03-10 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-08-28 | 2102356628 | 8202240237 |  | 8202224487#25_[CR] Fin Fan 11E52KA Blade | RU4-FOC1 | 11E52K-A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 113675225 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102365687 | 8202240234 |  | 8202224486#25_[CR] Troubleshoot Filter K | RU4-FOC1 | 14K602B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1465 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-15 | 2026-01-30 | 2026-12-29 | 2102359813 | 8202236039 |  | 8202224484#Pengadaan MCC DegasserFan K-3 | RU5-UTL | K-32-01B/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 268424000 | 0 | MA4-LIS |  | MAYRAALFAR |  | 2026-02-07 | PT02 |  | 3 | 2026-01-30 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359867 | 8202236026 |  | 8202224482#Perbaikan motor Eam-201-01F | RU5-D&W | EAM-201-01F/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 880000 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102359721 | 8202236042 |  | 8202224481#Material Perb. Line Outlet TU | RU5-UTL | FUEL-OIL-P3/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 79165260 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357368 | 8202236698 |  | 8202224480#D_25 Breaker motor 041P106A r | RU4-TRML | 041P106A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-06-19 | 2026-01-02 | 2026-12-31 | 2102361271 | 8202237592 |  | 8202224473#Low press dan Low Flow pompa | RU4-K3LL | 70P2A/00 | 60 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 716252500 | WS-PMP |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-05 | 2102363469 | 8202237797 |  | 8202224470#LTSA COA 32V106 | RU6-HSC | 32-V-106A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355900 | 8202240231 |  | 8202224468#25_[CR] 30P101A, Perbaikan Po | RU4-TRML | 30P101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 195000 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-06-03 | 2026-06-03 | 2102359938 | 8202236005 |  | 8202224464#Perbaikan motor Eam-201-01A | RU5-D&W | EAM-201-01A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1097514 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-29 | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102359812 | 8202236010 |  | 8202224463#Motor Degasser K-32-01A WTP 2 | RU5-UTL | K-32-01A/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 566595 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-06 | 2026-06-11 | 2102359784 | 8202236008 |  | 8202224461#Perbaikan GS-201-08B (Tambaha | RU5-D&W | GS-201-08B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 197469976 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361070 | 8202236213 |  | 8202224458#Perbaikan boardesk Unit 92 | RU4-SRU | 92V402/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361071 | 8202236215 |  | 8202224457#Perbaikan boardesk Unit 91 | RU4-SRU | 91V413/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361055 | 8202236054 |  | 8202224456#Kebutuhan connector union 3/4 | RU4-SRU | 93E405/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361212 | 8202237335 |  | 8202224455#91P409, Penggantian suction s | RU4-SRU | 91P409/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361213 | 8202237338 |  | 8202224454#91P408, penggantian suction s | RU4-SRU | 91P408/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361088 | 8202236472 |  | 8202224453#Penggantian suction strainer | RU4-SRU | 91P401A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365807 | 8202240228 |  | 8202224452#25_Mtl. Penggantian Filter 16 | RU4-FOC1 | 16WS101/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 7490000 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361091 | 8202236480 |  | 8202224451#penggantian steam coil 93A40 | RU4-SRU | 93A404/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361094 | 8202236484 |  | 8202224450#Penggantian Sight Port (Stat- | RU4-SRU | 93F401/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361084 | 8202236406 |  | 8202224449#Penggantian valve 4'150 | RU4-FOC1 | 14K1E1B/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361058 | 8202236058 |  | 8202224448#kebutuhan conector reducer | RU4-SRU | 91V410/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361054 | 8202236053 |  | 8202224447#kebutuhan konektor a/l Plug, | RU4-SRU | 91V410/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361057 | 8202236056 |  | 8202224444#kebutuhan conector reducer | RU4-SRU | 91E409/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354330 | 8202241452 |  | 8202224442#25_[CR] Perbaikan 54A204-P1A | RU4-UTL | 54A204P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102354248 | 8202240225 |  | 8202224441#25_[CR] Perbaikan 54A203-P1C | RU4-UTL | 54A203P1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354246 | 8202241451 |  | 8202224440#25_[CR] Perbaikan 54A203-P1B | RU4-UTL | 54A203P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354244 | 8202241450 |  | 8202224439#25_[CR] Perbaikan 54A203-P1A | RU4-UTL | 54A203P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354242 | 8202241449 |  | 8202224438#25_[CR] Perbaikan 54A202-P1B | RU4-UTL | 54A202P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354241 | 8202241448 |  | 8202224437#25_[CR] Perbaikan 54A202-P1A | RU4-UTL | 54A202P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354240 | 8202241447 |  | 8202224436#25_[CR] Perbaikan 54A201-P1B | RU4-UTL | 54A201P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354169 | 8202241446 |  | 8202224434#25_[CR] Perbaikan 54A201-P1A | RU4-UTL | 54A201P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354334 | 8202241445 |  | 8202224433#25_[CR] Perbaikan 54A3P1 | RU4-UTL | 54A3P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354332 | 8202241444 |  | 8202224432#25_[CR] Perbaikan 54A2P1 | RU4-UTL | 54A2P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354168 | 8202241443 |  | 8202224431#25_[CR] Perbaikan 54A1P1 | RU4-UTL | 54A1P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354379 | 8202241442 |  | 8202224430#25_[CR] Perbaikan pompa 54WS2 | RU4-UTL | 54WS201P5B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-03 | 2102362992 | 8202233709 |  | 8202224429#Penggantian Analyzer STG | RU6-UTL | 51-AT-001A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12408 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353146 | 8202234780 |  | 8202224428#Penggantian Manual Call Point |  |  | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354376 | 8202241404 |  | 8202224427#25_[CR] Perbaikan pompa 54WS2 | RU4-UTL | 54WS201P5A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354372 | 8202241403 |  | 8202224426#25_[CR] Perbaikan pompa 54WS2 | RU4-UTL | 54WS201P4B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354370 | 8202241402 |  | 8202224425#25_[CR] Perbaikan pompa 54WS2 | RU4-UTL | 54WS201P4A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353147 | 8202234572 |  | 8202224424#N_Penggantian Flame Sensor WH | RU3-UTL | BE-20236C/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-1-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-03-09 | 2102354337 | 8202241401 |  | 8202224423#25_[CR] Perbaikan 54WS1P-4A | RU4-UTL | 54WS1P4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352659 | 8202234581 |  | 8202224422#N_Penggantian Axial Vibration | RU3-UTL | 2027-JC/01 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-02 | 2102363465 | 8202233839 |  | 8202224421#Pengadaan & Penggantian solen | RU6-UTL | 53-A-202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12276 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102357135 | 8202240218 |  | 8202224417#25_Penggantian belt 16K2 | RU4-FOC1 | 16K2/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1465 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102357137 | 8202240215 |  | 8202224416#25_penggantian belt 16K2 | RU4-FOC1 | 16K2/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1465 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357131 | 8202240211 |  | 8202224415#25_Penggantian belt 16K1 | RU4-FOC1 | 16K1/01 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102357133 | 8202240208 |  | 8202224413#25_Penggantian belt 16K1 | RU4-FOC1 | 16K1/01 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1465 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-06 | 2026-02-14 | 2026-02-06 | 2026-02-06 |  | 8202238683 |  | 8202224412#LTSA VALVE RECRIPOCATING COMP | RU2-HCC | 211-C-2A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 20000000 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-22 | 2025-12-30 | 2102359810 | 8202236002 |  | 8202224411#Perbaikan motor Em-17-03C | RU5-E15112 | EM-17-03C/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 521969 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-19 | 2025-12-30 | 2102359811 | 8202236000 |  | 8202224410#Perbaikan Motor Em-17-04A | RU5-E15112 | EM-17-04A/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 521982 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-11-16 | 2102353915 | 8202237590 |  | 8202224408#RKA23L_Perbaikan Gedung Labor |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-11-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-10-19 | 2102353911 | 8202237578 |  | 8202224405#RKA24_Pagar Gate 3 s/d Brass | RU4-K3LL | ZG01/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-09-15 | 2102353879 | 8202240206 |  | 8202224402#25_[CR] 90P404A, Perbaikan Po | RU4-SRU | 90P404A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 1624 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2026-11-27 | 2026-12-30 | 2102360138 | 8202235998 |  | 8202224398#Mat. Modifikasi line Booster | RU5-UTL | 1VF-01-D001/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/NR-C2H | 19619171 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-27 | PM |  | 001
| K501 | 2026-02-02 | 2026-06-04 | 2026-06-03 | 2026-06-03 | 2102359789 | 8202235975 |  | 8202224395#Perbaikan motor degasser pump | RU5-UTL | DM-4-P103/00 | 60 | CLSD CNF PRT CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 640600 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-29 | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-19 | 2026-07-24 | 2102359865 | 8202235972 |  | 8202224394#Perbaikn HMI Flocomp Meter PD | RU5-TBL | 22-716B/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-09-17 | 2102356927 | 8202241399 |  | 8202224392#25_Mechanical seal 023P-116B | RU4-LOC2 | 023P116B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 75703526 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-09-15 | 2102356651 | 8202240201 |  | 8202224388#25_[CR[ Perbaika Fin Fan 14E2 | RU4-FOC1 | 14E2K-F/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 12719684 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102354160 | 8202238642 |  | 8202224387#TGH1_24 TSA Online Analyzer T | RU4-RFCC | 102FT049/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-09-30 | 2102356100 | 8202240198 |  | 8202224386#25_[CR] Penggantian Filter LO | RU4-FOC1 | 14K602AM-S1S2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3335860 | 3334091 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102353730 | 8202240194 |  | 8202224385#25_Penggantian Tachometer 101 | RU4-RFCC | 101P522B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 57638000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-09-15 | 2102356103 | 8202240190 |  | 8202224384#25_[CR] Penggantian Filter LO | RU4-FOC1 | 14K602BM-S1A/B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3335715 | 3334091 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353669 | 8202240186 |  | 8202224383#25_Penggantian Tachometer 101 | RU4-RFCC | 101P522A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 17638000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353668 | 8202240182 |  | 8202224382#25_kerusakan level indicator | RU4-GTO | 100LT605/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353617 | 8202240180 |  | 8202224380#25_Penggantian Tachometer 104 | RU4-RFCC | 104P505A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-10-19 | 2102353462 | 8202237577 |  | 8202224379#Repeat Order Sewa Elevator Te | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353611 | 8202240176 |  | 8202224378#25_85FV210 rusak | RU4-KPC | 85FV210/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353451 | 8202240172 |  | 8202224377#25_Pengadaan Horn Tag No 154- | RU4-RFCC | 153FG003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 19600000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-16 | 2026-03-05 | 2026-03-06 | 2102353514 | 8202240168 |  | 8202224375#25_[PV] Penyehatan 051P101AT | RU4-UTL | 051P101A-T/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 5702692 | 5701982 | MA5-ROT |  | ABDULFM |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-09-14 | 2102353510 | 8202240164 |  | 8202224374#25_[CR] 011K101B cylinder 1 n | RU4-FOC2 | 011K101B/01 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353399 | 8202240160 |  | 8202224369#25_Pengadaan Horn Tag No 154- | RU4-RFCC | 153FG003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 19600000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353452 | 8202240156 |  | 8202224368#25_Pengadaan Horn Tag No 153- | RU4-RFCC | 153FG003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 19600000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353397 | 8202240152 |  | 8202224367#25_Pengadaan Horn Tag No 154- | RU4-RFCC | 153FG003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 19600000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353450 | 8202240148 |  | 8202224364#25_Pengadaan Horn Tag No 154- | RU4-RFCC | 153FG003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 19600000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353398 | 8202240144 |  | 8202224362#25_Pengadaan Horn Tag No 153- | RU4-RFCC | 153FG003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 19600000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-15 | 2026-02-03 | 2026-04-30 | 2102359726 | 8202235977 |  | 8202224354#Perbaikan Mec. Selenoid FDFT | RU5-UTL | 1NV00S100/00 | 60 | CLSD CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 45000000 | 0 | MA1-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102354628 | 8202237575 |  | 8202224349#RKAP25 Instal HMI SWD 154 di | RU4-RFCUTL | 154XA-U154/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 3299000000 | 0 | MA5-INT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2102359103 | 8202235996 |  | 8202224348#Perbaikan Lampu di Area Boile |  |  | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 165254500 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359816 | 8202235973 |  | 8202224347#Perbaikankabel incoming SS 38 | RU5-UTL | 41-R-SS-38-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 37083600 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102358596 | 8202234483 |  | 8202224346#Pemasangan Flow Meter | RU7-CDU | 1-P-03B/00 | 60 | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353321 | 8202234451 |  | 8202224343#Pompa 2200 JA Feed Demin | RU3-UTL | MCC-2200-JAM/00 | 60 | REL CSER MACM PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-10-14 | 2102361864 | 8202236782 |  | 8202224337#Repetitive Crack pada 052-V-1 | RU6-UTL | 052-V-101A/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102353455 | 8202240138 |  | 8202224334#25_015E107M1 Puly motor rusak | RU4-FOC2 | 015E107M01/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234571 | 8202238101 | 8202224333#tagihan 2025 Pek Perawatan da | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-04 | 2102363448 | 8202233898 |  | 8202224332#Notif Penggantian Flange Unde | RU6-ITP | 42-PIPE/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 2640 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351774 | 8202232252 |  | 8202224330#Kerusakan belting finfan area | RU2-HSC | 200-E-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 1620000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-06-26 | 2102363460 | 8202233186 |  | 8202224329#Perbaikan Cooler Dan Lampu di | RU6-UTL | 51-G-101D-E5B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2328 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102360207 | 8202235971 |  | 8202224328#NRK_Pengadaan Motor P-17 & P- | RU5-UTL | P-17-WTP/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238136 | 8202234824 | 8202224327#Tag 18 Cleaning Underground S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238317 | 8202235233 | 8202224326#Tag 7 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238181 | 8202235438 | 8202224324#Tag 3 KV Cleaning Minyak Bera |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238304 | 8202235438 | 8202224323#Tag 2 KV Cleaning Minyak Bera |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238292 | 8202234997 | 8202224322#Tag 6 KV Penyediaan Jasa Hose |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238280 | 8202235215 | 8202224321#Tag 8 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102351772 | 8202232569 |  | 8202224312#Penggantian Coupling 100-P-8A | RU2-HSC | 100-P-8A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353515 | 8202240135 |  | 8202224310#25_Penggantian Motor Lube Oil | RU4-UTL | 054P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102360246 | 8202235952 |  | 8202224309#Perbaikan Instalasi Kabel GM- | RU5-TBL | G-220-01C/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 22201600 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-10-16 | 2102363428 | 8202237796 |  | 8202224307#Assessment Motor MV 3 kV Taha | RU6-UTL | 052-P-101A-M/00 | 50 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-03-05 | 2026-03-05 | 2102359862 | 8202235950 |  | 8202224304#Perbaikan Motor Gm-3-26C | RU5-E15112 | GM-3-26C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1517002 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-02 | 2026-08-13 | 2026-08-13 | 2102359868 | 8202235946 |  | 8202224295#perbaikan fin-fan EA-4-05 B | RU5-E15111 | EF-4-05B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3289837 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-08-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102355312 | 8202240133 |  | 8202224291#25_Belt finfan putus 260E120 | RU4-LOC3 | 260E120A-K1/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 42911597 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2102360134 | 8202235942 |  | 8202224290#Perbaikan Y-34-06B | RU5-D&W | Y-34-06B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 1804476 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102353618 | 8202240130 |  | 8202224289#25_[CR] Perbaikan 12K1B-P1 | RU4-FOC1 | 12K1B-P1/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 004
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-03-09 | 2102353614 | 8202241397 |  | 8202224288#25_[TSA]011P104B mechseal IB | RU4-FOC2 | 011P104B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 443390950 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102361949 | 8202233298 |  | 8202224285#Perbaikan 25-PI-010 | RU6-HSC | 25-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-16 | 2102359863 | 8202235944 |  | 8202224283#Perbaikan Kabel Power Upgrade | RU5-E15112 | 17-LG-002/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 4000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-12 | 2026-01-20 | 2026-02-19 | 2102359869 | 8202235948 |  | 8202224282#Perbaikan ATG IHLA D-20-11 | RU5-TBL | IHLA-STTN-VII/00 | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 10949780 | 0 | MA4-INT |  | SAPBATCH | 2026-06-12 | 2026-02-11 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102353519 | 8202240127 |  | 8202224280#25_Mtl. Retube FinFan 91K-401 | RU4-SRU | 91K401BEM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 4812194 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-02 | 2102362447 | 8202234099 |  | 8202224278#12-K-501B P2 | RU6-DHC | 12-K-501B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 1102328049 | 8202235945 |  | 8202224274#Perbaikan Kabel Power AC Stan |  | 341-AC-2F-5-94/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 2 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353434 | 8202240124 |  | 8202224272#25_Perbaikan Alarm Axial Comp | RU4-RFCC | 101XV007A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 3940000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-01 | 2025-12-01 | 2102357407 | 8202234494 |  | 8202224271#Pengadaan panel board 11K401B | RU4-FOC1 | 11K401B/00 | 50 WENG | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-01 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102356987 | 8202234496 |  | 8202224270#pengadaan panel board 11K-401 | RU4-FOC1 | 11K401B/00 | 50 WENG | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-08 | 2026-04-17 | 2026-01-02 | 2026-01-02 |  | 8202238767 |  | 8202224269#25_[CR] Perbaikan Pompa 054P1 | RU4-UTL | 054P101A/00 | 01 | CRTD CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 100000 | 0 | MA5-ROT |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351863 | 8202232471 |  | 8202224265#Perbaikan 220 P-3A | RU2-HOC | 220-P-3A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362547 | 8202233248 |  | 8202224264#Perbaikan 63-Z-202A | RU6-ITP | 63-Z-202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-10-21 | 2102355906 | 8202237572 |  | 8202224263#RKA22L_Cleaning Clarifier Tah | RU4-RFCUTL | 63A501A-P1/01 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-04 | 2026-04-22 | 2026-12-30 | 2026-12-30 | 2102351180 | 8202238275 |  | 8202224262#Steam leak | RU2-HSC | 0-5-FO-090-GAB/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 800000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363635 | 8202232357 |  | 8202224258#Pengadaan Catridge Filter 211 | RU2-HCC | 211-F-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-11-04 | 2102363443 | 8202233727 |  | 8202224254#Penggantian 15-LG-029 (15-V-1 | RU6-RCC | 15-LG-029/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354405 | 8202240121 |  | 8202224251#25_Kerusakan booster 88PV203 | RU4-KPC | 88PV203/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 4 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355314 | 8202240118 |  | 8202224250#25_Multipoint Thermocuple 39T | RU4-TRML | 39T206/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2025-11-20 | 2026-04-10 | 2102359860 | 8202235911 |  | 8202224247#perbaikan instrumentasi Plant | RU5-E15112 | 31-PCV-009/00 | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 485699976 | 0 | MA3-INT |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-12 | 2026-02-02 | 2026-11-04 | 2102363236 | 8202233801 |  | 8202224246#Pengadaan LCS type ZE5AM1S1P2 | RU6-UTL | 50-P-201B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 23892 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-12 | 2026-02-02 | 2026-11-04 | 2102363272 | 8202233802 |  | 8202224245#Pengadaan LCS Type ZE3AS1P2WX | RU6-UTL | 56-P-101A-P1B-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 23892 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-18 | 2102363210 | 8202233803 |  | 8202224244#Pengadaan LCS 51-G-101B-S1 | RU6-UTL | 51-G-101B-S1-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 30360 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359995 | 8202235915 |  | 8202224239#Penggantian Lampu TL di F-1-0 | RU5-E15111 | F-1-01A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 9200000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360137 | 8202235937 |  | 8202224238#Grounding body Trafo SS-7/64/ |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 115250000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2025-10-27 | 2025-10-27 | 2102352610 | 8202234196 |  | 8202224237#Vibrasi tinggi pada pompa 946 | RU2S-KIL | 946-P-5B/00 | 60 | REL NMAT PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102363442 | 8202234055 |  | 8202224236#32K101 P1A | RU6-HSC | 32-K-101-P1-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102353794 | 8202240115 |  | 8202224230#25_Mtl. Stok MicroFilter 013M | RU4-FOC2 | 013C101/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 107000000 | 38520000 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102359997 | 8202235900 |  | 8202224228#Perbaikan Motor GM-34-54 | RU5-E15112 | GM-34-54/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1870800 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-11 | 2025-12-01 | 2025-12-01 | 2102359994 | 8202235904 |  | 8202224227#Perbaikan Motor em-2-12B | RU5-E15112 | EM-2-12A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 664554 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-06-09 | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 005
| K501 | 2026-02-02 | 2026-04-21 | 2026-06-30 | 2026-09-29 | 2102360028 | 8202235917 |  | 8202224226#kabel support tanki OM | RU5-TBL | PLANT-20-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 19285710 | 0 | MA4-LIS |  | AGUSHIDAYAT |  | 2026-02-11 | PT02 |  | 3 | 2026-06-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360027 | 8202235908 |  | 8202224225#perbaikan kabel sump pump 34- | RU5-TBL | GM-34-91B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 90127600 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-01 | 2025-12-01 | 2102360026 | 8202235940 |  | 8202224224# Perbaikan Elmot GM-20-21A | RU5-TBL | GM-20-21/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 341660 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-01 | PM |  | 005
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102360414 | 8202235913 |  | 8202224223#Perb. Fan Motor GM-20-18A RP | RU5-TBL | GM-20-18A/00 | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 5652000 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353423 | 8202240112 |  | 8202224217#25_Pengadaan Amperemeter Untu | RU4-RFCUTL | 150BD1PDP001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-13-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-10-22 | 2102363446 | 8202236697 |  | 8202224216#SPK#18 LTSA Pompa Sump (42-P- | RU6-ITP | 42-P-701/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351776 | 8202232653 |  | 8202224214#Pengadaan Ring Joint 140 V-1 | RU2-HOC | 140-V-1A/00 | 60 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102357364 | 8202240109 |  | 8202224212#25_Cooler 021P109A bocor | RU4-LOC2 | 021P109A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 65000000 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355377 | 8202240106 |  | 8202224203#25_[PV] Perbaikan Pompa 101P5 | RU4-RFCC | 101P522B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 45340000 | 84000000 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365553 | 8202240103 |  | 8202224201#25_Pengadaan tube 54E2 dan 54 | RU4-UTL | 54E2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 2175000000 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-09-23 | 2102360514 | 8202235897 |  | 8202224199#NRK_Perbaikan CCTV Boiler Are | RU5-UTL | B1-1SV-612/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-04 | 2026-02-02 | 2026-12-30 | 2102361272 | 8202237571 |  | 8202224198#Perbaikan hydraulic & Flow Me | RU4-WS | FL48/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 74307305 | 63161209 | WS-KAB |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-30 | 2102360202 | 8202235895 |  | 8202224197#Penggantian Part Inner Valve | RU5-E15111 | 05-KV-504/00 | 01 | CRTD CSER MACM PRC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA2-INT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363404 | 8202233347 |  | 8202224195#Perbaikan 15-P-111C-T | RU6-RCC | 15-P-111C-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-09 | 2026-01-02 | 2027-01-22 | 2102354575 | 8202237569 |  | 8202224194#RKA25L_Gedung Operator UTL 50 | RU4-UTL | 50BD1/00 | 50 | CRTD CSER NMAT PRC RELR SETC | 4MR | D14/26/B6/RT-9-C2H | 100000 | 0 | MA5-STA |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-10-21 | 2102363155 | 8202234059 |  | 8202224193#32-E-103 A1 | RU6-HSC | 32-E-103A1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-10-21 | 2102363153 | 8202234062 |  | 8202224192#31-E-105 C2 | RU6-HSC | 31-E-105C2/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-10-26 | 2102363105 | 8202238169 |  | 8202224191#Jasa Perbaikan Ducting area 1 | RU6-RCC | 15-B-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-10-21 | 2102363330 | 8202234063 |  | 8202224190#31-E-105 B2 | RU6-HSC | 31-E-105B2/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-19 |  | 8202233835 |  | 8202224189#Pengadaan AC Analyzer House 3 | RU6-POC | 35-GDF-001/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-10-20 | 2102363332 | 8202233171 |  | 8202224188#Perbaikan Fin Fan 31-E-105 B1 | RU6-HSC | 31-E-105B1/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102359951 | 8202235889 |  | 8202224186#Perbaikan Temp. Out. FO Heate | RU5-UTL | HHP-4-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 38600000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102359936 | 8202235892 |  | 8202224185#Perb. Flow Meter Mixedbed cha | RU5-UTL | 0UA-20-F001/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 15375000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-17 | 2102363440 | 8202232873 |  | 8202224182#Perbaikan steam trap tangki 4 | RU6-ITP | 42-T-101G/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 3960 | 4768715 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-04 | 2026-02-02 | 2026-12-30 | 2102361273 | 8202237567 |  | 8202224177#Penggantian gate valve FT-28 | RU4-WS | FL54/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 70923836 | 60285261 | WS-KAB |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-08-13 | 2102355564 | 8202236489 |  | 8202224176#Penggantian RELAY Motor Prote | RU4-TRML | 46P1BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-03-10 | 2102354402 | 8202241395 |  | 8202224171#25_87P206A Overload | RU4-KPC | 87P206A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 88137756 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-11-04 |  | 8202237565 | 8202238639 | 8202224170#TGH3_SIP_UP Tenaga Kerja MA 3 | RU4-TRML | 033PSV305/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102354167 | 8202241393 |  | 8202224169#25_[CR] Mech seal 23P4 bocor | RU4-LOC1 | 23P4/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 139904905 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102354158 | 8202237563 |  | 8202224167#TGH3_SIP_UP Rejuv Isolasi MA | RU4-FOC2 | 014K102C/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365908 | 8202240096 |  | 8202224166#25_Penggantian Switch Limit P | RU4-TRML | 36P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 26 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355251 | 8202240091 |  | 8202224165#25_108PV642 Positioner & Akse | RU4-RFCGTO | 108A501V4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-09-30 | 2102355218 | 8202240087 |  | 8202224164#25_108PV622 Positioner Rusak | RU4-RFCGTO | 108A501V2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-03-04 | 2026-02-02 | 2026-12-30 | 2102361274 | 8202237561 |  | 8202224156#Penggantian klakson FT-29 | RU4-WS | FL48/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 49050439 | 41692873 | WS-KAB |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363593 | 8202232265 |  | 8202224155#Revitalisasi fix foam monitor | RU2-ITP | DPN-PIPING/00 | 01 | CRTD NMAT PRC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102356012 | 8202240084 |  | 8202224153#25_011E110 pengadaan pulley m | RU4-FOC2 | 011E110-01/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 59250000 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102351861 | 8202232574 |  | 8202224150#Perbaikan thermodial 945 T-02 | RU2-ITP | 945-T-02/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-05-22 | 2102360020 | 8202235883 |  | 8202224149#perbaikan bordes rumah pompa | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 14935840 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354500 | 8202235990 |  | 8202224148#Perbaikan isolasi di Kilang R | RU4-RFCC | 103-AM0002-1-1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 91219165 | MA6-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-18 | 2025-11-18 | 1102328555 | 8202235885 |  | 8202224146#Penggantian Kabel Komunikasi | RU5-LAB | BWB-316020/00 | 60 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 5000000 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102360564 | 8202235879 |  | 8202224145#GT-2-05B | RU5-E15112 | GT-2-05B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 4098257 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102358599 | 8202234481 |  | 8202224140#Ganti Bearing Pompa 6-PM-201 |  |  | 60 | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-4-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353148 | 8202234555 |  | 8202224139#Perbaikan MCC Motor Fire Pump | RU3-UTL | RPA2-P-2BF/00 | 50 WAMA | REL CSER MACM PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-12-11 |  | 8202236767 | 8202232770 | 8202224132#SPK 16 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-09 | 2026-04-10 | 2026-08-31 | 2102352600 | 8202234195 |  | 8202224131#Auto drain valve bak sediment | RU2S-KIL | 900-02AC-1A/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 36402432 | 36394645 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364227 | 8202234669 |  | 8202224130#Pengadaan Material Perbaikan |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | WS-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356835 | 8202236149 |  | 8202224129#Perbaikan Carbon in Catalyst |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | WS-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102356160 | 8202236907 |  | 8202224127#Penggantian Control 85P215B | RU4-KPC | 85P215B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-15 | 2026-06-15 | 2026-12-31 | 2102355374 | 8202236348 |  | 8202224125#D25_Perbaikan Analyzer Pada U | RU4-GTO | 120FE006/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-INT |  | YOHANESMVIS |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102355376 | 8202240080 |  | 8202224122#25_Perbaikan Deviasi 101TI637 | RU4-RFCC | 101K501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102355378 | 8202240076 |  | 8202224121#25_[CR] Penggantian Filter Lu | RU4-FOC1 | 11K401B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 73602000 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354625 | 8202240072 |  | 8202224120#25_[CR] Perbaikan MSeal 14P60 | RU4-FOC1 | 14P607C/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353505 | 8202240068 |  | 8202224118#25_Fake Alarm H2S Detector 12 | RU4-GTO | 120E606/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360951 | 8202236934 |  | 8202224110#D_25 011K-101B motor short | RU4-FOC2 | 011K101BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-10-22 |  | 8202237795 | 8202233431 | 8202224107#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-10-22 |  | 8202237793 | 8202233431 | 8202224106#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-10-22 |  | 8202237791 | 8202233431 | 8202224104#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-14 | 2026-02-03 | 2026-10-22 |  | 8202237789 | 8202233431 | 8202224103#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-10-21 | 2102363040 | 8202233431 |  | 8202224102#Penyelesaian Pekerjaan EI MA1 | RU6-RCC | 09-14B-PSW2-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352601 | 8202234194 |  | 8202224101#Kerusakan Motor Compressor Ai | RU2S-KIL | 900-02AC-1B-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-08 | 2102362737 | 8202233239 |  | 8202224096#Perbaikan Battery FCS/SCS DCS | RU6-HSC | PC-B15-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/XX/B6/RT-C2NH | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362907 | 8202233758 |  | 8202224095#Pengadaan Pressure Gauge N2 B | RU6-ITP | 42-T-504/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 11963 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360280 | 8202235876 |  | 8202224093#Line chain 4 bocor | RU5-UTL | D4-XSV-402/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-24 | 2026-02-27 | 2102360132 | 8202235868 |  | 8202224091#Perbaikan Motor P-2B CPI DHP | RU5-D&W | PM-2B-CPI/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | WS-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-24 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-03-25 | 2026-04-16 | 2102360282 | 8202235872 |  | 8202224089#Penggantian 202-FT-033 | RU5-D&W | 202-FT-033/00 | 60 | REL CNF CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | HELDIPRANATA | 2026-03-25 | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K301 | 2026-02-04 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 8202238274 | 8202235151 | 8202224081#Tag. 11 Pek. Cleaning dan Gan | RU3-CDGP |  | 60 | TECO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357766 | 8202236567 |  | 8202224079#D_25 Perbaikan Sootblower No. | RU4-RFCC | 101F503A19/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102355902 | 8202240064 |  | 8202224078#25_[CR] 30P101B, Perbaikan Po | RU4-TRML | 30P101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 195000 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238262 | 8202234832 | 8202224077#Tag 16 KV Tambat Kapal Area S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238334 | 8202235502 | 8202224076#Tagihan Ke- 6 Pekerjaan Sipil | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238321 | 8202235314 | 8202224074#Tag 4 KV Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K202 | 2026-02-02 | 2026-03-30 | 2026-02-02 | 2026-02-02 | 2102352166 | 8202234193 |  | 8202224069#Pemeriksaan Pembangkit Listri | RU2S-KIL | 900-06GE-6/00 | 50 | REL CSER MSPT PRC SETC | 2RS | D12/26/B6/RTZ-C2H | 6 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-04-16 | 2026-04-16 | 2102351975 | 8202238305 |  | 8202224064#Pelaksanaan COA 300-V-14 | RU2-HSC | 300-V-14/00 | 50 | CRTD NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 152997000 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-04-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102363004 | 8202232868 |  | 8202224061#Perbaikan Tachometer 52-B-101 | RU6-UTL | 52-B-101C-K1-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353149 | 8202234530 |  | 8202224059#N_Penggantian Sensor COD Spar | RU3-ITP | 61-PT-005/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365380 | 8202240060 |  | 8202224055#25_017E103 M1 puly motor anjl | RU4-FOC2 | 017E103M01/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-11 | 2025-12-12 | 2025-12-12 | 2102358238 | 8202235841 |  | 8202224051#Perbaikan T-34-05D (Gear Set) | RU5-D&W | T-34-05D/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 151330700 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-02-08 |  | 2026-01-02 | 2027-01-21 | 2102363930 | 8202238756 |  | 8202224047#25_Penggantian ACB 51G4 | RU4-UTL | 51G4/00 | 50 | CRTD NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 145000000 | 0 | MA5-LIS |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 005
| K401 | 2026-02-08 | 2026-06-18 | 2026-01-02 | 2027-01-21 | 2102357197 | 8202238755 |  | 8202224046#25_Penggantian kabel Feeder 6 | RU4-TRML | 63SS11/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 4700000000 | 3800000000 | MA5-LIS |  | FARIZSETYANA |  | 2026-02-24 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-26 | 2026-06-19 | 2102360175 | 8202235768 |  | 8202224043#Perbaikan transmitter 201-TI- | RU5-D&W | INT-CDU-V/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-26 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353194 | 8202234578 |  | 8202224042#N_Penggantian Battery CPM DCS | RU3-UTL | UTL-DCS/00 | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-10-30 | 2102355858 | 8202240055 |  | 8202224040#25_[CR] Pompa 106P501B Under | RU4-RFCGTO | 106P501B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 14279500 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-03-09 | 2102356386 | 8202241391 |  | 8202224039#25_012P103A indikasi mechseal | RU4-FOC2 | 012P103A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 407550650 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-10-20 | 2102356684 | 8202241389 |  | 8202224038#25_[CR] Mech seal 24P8 bocor | RU4-LOC1 | 24P8/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 184152722 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-10-30 | 2102353444 | 8202240048 |  | 8202224036#25_[CR] Perbaikan Pompa Clari | RU4-RFCUTL | 63P502C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 |  | 8202238303 |  | 8202224034#Perbaikan kerusakan & Perawat | RU2-PK | 970-PIPING/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 250000000 | 250000000 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102356382 | 8202240044 |  | 8202224033#25_[CR] 011E111K4 Bearing Def | RU4-FOC2 | 011E111K04/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 6650551 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-08-28 | 2102356106 | 8202240040 |  | 8202224027#25_[CR] Perbaikan Turbine 57P | RU4-UTL | 57P102AT/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-09 | 2026-06-09 | 2026-10-30 | 2102362942 | 8202233346 |  | 8202224026#Perbaikan 15-P-111F | RU6-RCC | 15-P-111F/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 31210893 | 87893760 | MA1-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102355375 | 8202241382 |  | 8202224025#[NP] Penggantian Mech Seal 02 | RU4-LOC2 | 024P121B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 71123000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K202 | 2026-02-02 | 2026-05-25 | 2026-05-18 | 2026-10-30 | 2102352614 | 8202234192 |  | 8202224020#Kebocoran pipa discharge Tk 0 | RU2S-KIL | 946-TK-09/00 | 50 | REL PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-10-28 | 2102362441 | 8202237787 |  | 8202224018#LTSA Steam Trap SPK 2 TKDN | RU6-RCC | 15-R-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102360306 | 8202235802 |  | 8202224017#Perb BV Manifold Transmitter | RU5-E15111 | 01-FT-159/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 78750000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-01-15 | 2026-01-15 | 2102360305 | 8202235800 |  | 8202224016#Perbaikan solenoid Air dryer | RU5-HSC |  | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 70430800 | 0 | MA2-INT |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360562 | 8202235814 |  | 8202224015#Penggantian Actuator 08A-HCV- | RU5-E15112 | 08A-HCV-270/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 39500001 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-23 | 2102360507 | 8202235805 |  | 8202224014#Penggantian Control Valve 03- | RU5-E15112 | 03-PCV-167A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-23 | 2102360506 | 8202235808 |  | 8202224013#Penggantian Control Valve 03- | RU5-E15112 | 03-PCV-120A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102360249 | 8202235762 |  | 8202224005#G-3-02D: Gland Packing Selata | RU5-E15112 | G-3-02D/01 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 590012880 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102362538 | 8202233957 |  | 8202224001#Mat Per Gen Steam Turbine 62- | RU6-UTL | 62-P-201A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-10-22 | 2102362940 | 8202236773 |  | 8202224000#SPK #17 LTSA Pompa Sump (42-P | RU6-ITP | 42-P-903/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362901 | 8202233132 |  | 8202223995#Perbaikan Kompresor 63-K-401A | RU6-ITP | 63-K-401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-30 | 2026-02-02 | 2026-09-23 | 2102361699 | 8202233668 |  | 8202223994#Penggantian Control Valve Ass | RU6-RCC | 17-LV-010/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-04-30 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-09-23 | 2102362276 | 8202233667 |  | 8202223993#Penggantian Control Valve Ass | RU6-RCC | 19-FV-017/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-11-20 |  | 8202236667 | 8202233968 | 8202223992#SWO Pemb. LTSA AC Termin 11 | RU6-RCC | SHELTER-PEM1/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363600 | 8202232215 |  | 8202223990#Perbaikan motor 580-EM-301 | RU2-UTL | 580-CT-301/00 | 50 | REL MACM PRC SETC | 2ER | D12/25/B6/NR-D2H | 0 | 0 | MA3-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356923 | 8202236725 |  | 8202223989#D_25 018F102 soot blower ov | RU4-FOC2 | 018F102/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356877 | 8202236870 |  | 8202223988#D_25 013F102 panel soot blowe | RU4-FOC2 | 013F102/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356319 | 8202237017 |  | 8202223987#D_25 011C-101 pintu elivator | RU4-FOC2 | 011C101/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-26 | 2102362532 | 8202233817 |  | 8202223985#Pengadaan Filter LO 15SLV101/ | RU6-RCC | 15-SLV-101/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360418 | 8202235751 |  | 8202223984#Perbaikan/cleaning I/S Cooler | RU5-D&W | E-235-03B/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-D5NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102356018 | 8202240034 |  | 8202223983#25_[CR] perbaikan 14E610 | RU4-FOC1 | 14E610A-B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-15 | 2025-12-15 | 2102360206 | 8202235749 |  | 8202223976#Pompa P05 WTP 1 vibrasi tingg |  |  | 60 | CLSD CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 045
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-11-04 | 2102355908 | 8202238640 |  | 8202223974#TGH1_24 PM Field Instrument M | RU4-KPC | 80FT205/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357527 | 8202240030 |  | 8202223971#25_[CR] 018K101A Low Flow | RU4-FOC2 | 018K101A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/NR-2-C2H | 4774144 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357540 | 8202240026 |  | 8202223970#25_[CR] Penggantian Mech Seal | RU4-LOC2 | 023P116B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357546 | 8202240023 |  | 8202223968#25_[CR] Penggantian membran k | RU4-FOC1 | 11P6A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-26 | 2026-04-16 | 2102360505 | 8202235754 |  | 8202223967#Pemasangan flow transmitter H | RU5-E15112 | 02-FT-189/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 35001152 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-10 | 2026-06-10 | 2102360245 | 8202235759 |  | 8202223965#kebocoran flexible hose G-1-2 | RU5-E15111 | G-1-22A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3375000 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-06-10 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102358484 | 8202234428 |  | 8202223964#TSA PLTS |  |  | 01 | CRTD NMAT PRC | 7RT |  | 0 | 0 | MA-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-03-25 | 2102358179 | 8202238005 |  | 8202223963#Perbaikan 1-E-20B | RU7-CDU | 1-E-20B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D4H | 1 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-11-05 | 2102357360 | 8202237559 |  | 8202223961#perbaikan 46P1B | RU4-TRML | 46P1BM-CB/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-07-31 | 2102362845 | 8202233998 |  | 8202223952#Kebutuhan Spare part LPS | RU6-ITP | 42-T-107A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 5628 | 62820000 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-05 | 2026-02-05 | 2102351116 | 8202238524 |  | 8202223951#Pengadaan VSD 110-PM3A | RU2-HOC | 110-PM-3A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 2900000000 | 0 | MA1-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362675 | 8202232998 |  | 8202223949#Perbaikan Pompa 11-P-122 | RU6-HSC | 11-P-122/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362671 | 8202232973 |  | 8202223946#Perbaikan Pompa 24-P-203B | RU6-HSC | 24-P-203B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102363706 | 8202232474 |  | 8202223945#Packing seat 140 PX-51 | RU2-HOC | 140-PX-51A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363710 | 8202232486 |  | 8202223943#Perbaikan 140 PM-23A | RU2-HOC | 140-PM-23A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 906237 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-10-28 | 2102362797 | 8202233751 |  | 8202223937#Pengadaan Spare Assy Pompa 32 | RU6-HSC | 32-A-101-P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102356381 | 8202237015 |  | 8202223936#D_25 011E-110 M20 indikasi mo | RU4-FOC2 | 011E110M20/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2102359100 | 8202235693 |  | 8202223931#Pengadaan Rider & Piston Ring | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 55384068 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-03-13 | 2026-08-04 |  | 8202235695 | 8202234646 | 8202223924#Pem.PT dan TT pada HS HeaderB | RU5-E15112 | 03-PG-5211/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 23508000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-03-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102360308 | 8202235726 |  | 8202223923#Filter lube oil BFW Pump 2 ko | RU5-UTL | T-BFW2-PP2/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 1430999 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-13 | 2102362843 | 8202233702 |  | 8202223921#Penggantian bearing motor 056 | RU6-UTL | 056-K-101-A1-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 8448 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102357195 | 8202240018 |  | 8202223919#25_Penggantian gasket 30in 43 | RU4-TRML | 47T103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 719572 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-04 |  | 2026-02-05 | 2026-02-05 |  | 8202238301 |  | 8202223915#PERAWATAN PEMBERSIHAN INSIDE | RU2-UTL | 940-B-1/00 | 01 | CRTD NMAT PRC | 2MR | D12/25/B6/RT-D2H | 1000 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353435 | 8202240015 |  | 8202223912#25_Perbaikan 102TI603B | RU4-RFCC | 102TE-U102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353436 | 8202240692 |  | 8202223911#25_Perbaikan 102TI620A | RU4-RFCC | 102TE-U102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102356266 | 8202240691 |  | 8202223910#25_Modul SVPM ACCS rusak | RU4-KPC | 84FE313/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102357262 | 8202240690 |  | 8202223907#25_Pengadaan Hot Spare SPD RF | RU4-RFCGTO | 108K502AM/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 409555800 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102360244 | 8202235692 |  | 8202223906#MAT. Cleaning bank EA-1-25C | RU5-E15111 | EA-1-25C/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 21655861 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102362977 | 8202233704 |  | 8202223903#penggantian bearing 34-A-102- | RU6-POC | 34-A-102-P-101A/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-05-07 | 2102362660 | 8202233883 |  | 8202223901#Pegadaan new Motor 53-P-201A | RU6-UTL | 53-P-201A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 39600 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102360283 | 8202235689 |  | 8202223899#MAT. Perb. Bocoran pipeline L | RU5-E15111 | 6-P05-6-C18/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 9027034 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-06 | 2026-03-06 | 2102357193 | 8202240689 |  | 8202223894#25_Mtl. Perbaikan Handreel ar | LOC1-UP4 | 47S507B-M3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 29958000 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-26 | 2026-04-16 | 2102360508 | 8202235685 |  | 8202223893#Penambahan Surge Arrester pad |  | 341-FGDS-F18-5/00 | 60 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 19201152 | 0 | HSSE |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-01-12 |  | 8202237785 |  | 8202223890#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-08-10 | 2026-09-09 | 2102360285 | 8202235682 |  | 8202223882#Perbaikan G-202-01B | RU5-D&W | G-202-01B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 84741609 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-08-10 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-10-30 | 2102362747 | 8202233330 |  | 8202223880#Perbaikan 16-P-108B | RU6-RCC | 16-P-108B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-12 | 2102362791 | 8202233321 |  | 8202223877#Perbaikan 17-PTR2-02A | RU6-HSC | 17-PTR2-02A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366049 | 8202240688 |  | 8202223876#25_[CR] Sprocket 24E-2B sudah | RU4-LOC1 | 24E2B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 81000000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102363978 | 8202240687 |  | 8202223875#25_Mtl. Perbaikan Crane CCR 0 | RU4-FOC2 | 014R101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366050 | 8202240685 |  | 8202223874#25_[CR] Sprocket 24E-2A aus | RU4-LOC1 | 24E2A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 67500000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361008 | 8202235155 |  | 8202223871#Plug box fin fan 014E102B1 da | RU4-FOC2 | 014E102-B1/00 | 50 WAMA WENG | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 001
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354150 | 8202240683 |  | 8202223868#25_[CR] 41P12A, Perbaikan Pom | RU4-TRML | 41FT012/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 6380800 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-06 | 2026-03-06 | 2102354152 | 8202240681 |  | 8202223867#25_[CR] 41P12B, Perbaikan Pom | RU4-TRML | FI-U41/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 6380800 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-08-14 | 2102357774 | 8202240679 |  | 8202223860#25_[CR] Cooler 21P-7A Bocor | RU4-LOC1 | 21P7A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 65001914 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-10-01 | 2102357406 | 8202240677 |  | 8202223859#25_[CR] Mechanical Seal 24P-2 | RU4-LOC1 | 24P2B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 1775 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365385 | 8202240675 |  | 8202223852#25_Penggantian Li Mekanis 71T | RU4-TRML | 71T14/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102365384 | 8202240673 |  | 8202223851#25_Penggantian Li Mekanis 71T | RU4-TRML | 71T13/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361132 | 8202236739 |  | 8202223848#D_25 017E104M4 trip tripan | RU4-FOC2 | 017E104M01/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361129 | 8202236675 |  | 8202223846#D_25 kontrak baru perbaikan o | RU4-FOC2 | 012K101BM/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102360300 | 8202235678 |  | 8202223845#Perbaikan Intrumentasi pump G | RU5-TBL | P-10-RP-R/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 2287542240 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238639 | 8202237533 | 8202223833#TGH2_SIP_UP Tenaga Kerja MA 3 | RU4-TRML | 033PSV305/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-12-31 | 2026-12-31 | 2102358239 | 8202235670 |  | 8202223832#Perbaikan Pompa Fire Truck TS |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-12-31 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 |  | 8202238300 |  | 8202223831#fabrikasi shaft blower | RU2-HSC | 310-C-1/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/RT-D2H | 100000000 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362629 | 8202234093 |  | 8202223830#15-K-104 Indikasi High Vibras | RU6-RCC | 15-K-104/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357678 | 8202240671 |  | 8202223826#25_88LT202 Rusak | RU4-KPC | 88LT202/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 22500000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357674 | 8202240669 |  | 8202223825#25_88FT252 Rusak | RU4-KPC | 88FT252/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102353445 | 8202240667 |  | 8202223824#25_88FT249 Rusak | RU4-KPC | 88FT249/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357671 | 8202240665 |  | 8202223822#25_88FT234 Rusak | RU4-KPC | 88FT234/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 16650000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357638 | 8202240663 |  | 8202223820#25_88FT223 Rusak | RU4-KPC | 88FT223/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 16650000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102357630 | 8202240661 |  | 8202223819#25_87FT201 Rusak | RU4-KPC | 87FT201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357617 | 8202240659 |  | 8202223817#25_86FT204 Rusak | RU4-KPC | 86FT204/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 16650000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357614 | 8202240657 |  | 8202223816#25_85FT214 Rusak | RU4-KPC | 85FT214/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 16650000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357610 | 8202240655 |  | 8202223815#25_85FT203 Rusak | RU4-KPC | 85FT203/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360303 | 8202235675 |  | 8202223814#Ganti Valve drain suction GM |  | FA-201/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357586 | 8202240653 |  | 8202223813#25_85FT201 Rusak | RU4-KPC | 85FT201/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357582 | 8202240651 |  | 8202223812#25_84FT264 Rusak | RU4-KPC | 84FT264/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 18500000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353509 | 8202240649 |  | 8202223811#25_Transmiter 24K2 (24TT033) | RU4-LOC1 | 24K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102360498 | 8202240647 |  | 8202223810#25_Kerusakan 180KV602A | RU4-GTO | 180KV602A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102360497 | 8202240645 |  | 8202223809#25_Kerusakan Selenoid Level V | RU4-GTO | 180A601/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-02 | 2026-03-05 | 2026-03-05 | 2102353503 | 8202240643 |  | 8202223803#25_Perbaikan Toxic Gas Detect | RU4-RFCC | 101TG015/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-02 | 2026-03-05 | 2026-03-05 | 2102353502 | 8202240641 |  | 8202223802#25_Perbaikan Toxic Gas Detect | RU4-RFCC | 101TG014/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-02 | 2026-03-05 | 2026-03-05 | 2102353501 | 8202240639 |  | 8202223801#25_Perbaikan Toxic Gas Detect | RU4-RFCC | 101TG002/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353479 | 8202240637 |  | 8202223796#25_Perbaikan 152TT028 | RU4-RFCUTL | 152TT-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102353478 | 8202240636 |  | 8202223795#25_Perbaikan Solenoid+Limit S | RU4-RFCUTL | 151ZS-U151/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 8000001 | 0 | MA5-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102357525 | 8202240634 |  | 8202223792#25_88FT219 Rusak | RU4-KPC | 88FT218/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 18500000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102362627 | 8202233221 |  | 8202223791#Perbaikan bocoran L.O 12-PTR1 | RU6-DHC | 12-PTR1-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360301 | 8202235673 |  | 8202223789#MAT.PERB.LINE 21-P143-6" CDU | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 6088430 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102359903 | 8202235586 |  | 8202223780#MAT.PERB.21-P958-6" ADO RP.A | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 49208542 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202235588 |  | 8202223779#MAT.PERB.21-P918-12" KEROSEN | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 257774073 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202235590 |  | 8202223778#MAT.PERB.21-P910-12"-B20 BLKG | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 134446380 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359292 | 8202235562 |  | 8202223777#MAT.PERB.LINE 22-P922-924-12" | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 13254085 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-02 | 2026-11-30 | 2102359296 | 8202235577 |  | 8202223776#MAT.PERB.LINE 21-P918-12" KER | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 49050260 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359615 | 8202235573 |  | 8202223775#MAT.PERB.LINE 21-P934-12" PER | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 65654406 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359617 | 8202235560 |  | 8202223774#MAT.PERB.LINE HEADER LOADNG A | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 41904578 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359980 | 8202235571 |  | 8202223773#MAT.PERB.LINE 21-P957-10"-B20 | RU5-TBL | 022-R-RP-PSA/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 7004228 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202235581 |  | 8202223772#MAT.PERB.LINE 21-P905-16"-B20 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 135340729 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202235583 |  | 8202223771#MAT.PERB.LINE 21-P901-20" HVG | RU5-TBL | 220-P-XXX/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 282377993 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102360867 | 8202235567 |  | 8202223770#MAT.PERB.LINE 21-P974-10" IDO | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 34431562 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359534 | 8202235554 |  | 8202223769#MAT.PERB.LINE TSV NO. 371 PUT | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 6720056 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102360444 | 8202235543 |  | 8202223768#Perb Solenoid 04-XCV-215 dan | RU5-E15111 | 04-XCV-215/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-08-14 | 2102353425 | 8202240632 |  | 8202223767#25_[CR] 011E117K2 Bearing & B | RU4-FOC2 | 011E117K02/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 66607137 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-10-15 | 2102353428 | 8202240630 |  | 8202223766#25_[CR] 017E104K06 Bearing de | RU4-FOC2 | 017E104K06/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 13014829 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-02 | 2026-02-03 | 2026-06-02 | 2102360413 | 8202235546 |  | 8202223765#Penggantian LCS Finfan HCC | RU5-E15112 | EM-3-11A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 15 | 0 | MA3-LIS |  | GHAGASP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357722 | 8202235730 |  | 8202223761#Perbaikan Peep Hole Boiler 15 | RU4-RFCUTL | 151B501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357725 | 8202236217 |  | 8202223760#Perbaikan Blowdown Boiler 151 | RU4-RFCUTL | 151B501C/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357762 | 8202236183 |  | 8202223759#Perbaikan Bordes Clarifier&Ar | RU4-RFCUTL |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353433 | 8202236589 |  | 8202223756#D_25 Perbaikan Fan Motor 101A | RU4-RFCC | 101A520P5/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362535 | 8202232757 |  | 8202223754#Prbaikn Genral Steam Turbin 5 | RU6-UTL | 56-P-101B-T/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 3600000 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-06-18 | 2026-02-02 | 2026-12-30 | 2102357728 | 8202237557 |  | 8202223752#UP_25 Activity OLLS KPC | RU4-KPC | 82K201A/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 1683734400 | MA4-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-21 | 2025-11-21 | 2102357760 | 8202236119 |  | 8202223750#UP_25 Activity Wrapping Area |  |  | 50 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-21 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-13 | 2026-04-06 | 2026-09-29 | 2102353630 | 8202236908 |  | 8202223742#Penggantian Contactor Motor L | RU4-RFCC | 102P505AM/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 50 | 0 | MA6-LIS |  | WAHYUCATUR |  | 2026-04-06 | PT02 |  | 3 | 2026-04-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353568 | 8202236944 |  | 8202223741#Penggantian Accesories Motor | RU4-RFCC | 101E531AM2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-03-14 | 2026-01-02 | 2027-01-21 | 2102353424 | 8202237540 |  | 8202223739#Penggantian Cathodic Protect | RU4-TRML | 004FT002/00 | 50 | CRTD NMAT PRC RELR SETC | 4ER | D14/26/B6/RT-8-C2H | 100000 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-13 | 2026-02-13 | 2102352157 | 8202234191 |  | 8202223737#perbaikan Line 10 Inch I&TY | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-D3H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102360590 | 8202235527 |  | 8202223735#Perbaikan Pompa G-31-46A | RU5-E15112 | G-31-46A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 472500 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238298 | 8202235145 | 8202223729#Tag 10 KV Cleaning Cooler & C | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-23 |  | 8202235526 | 8202236745 | 8202223728#Perbaikan Seal DBB Valve Mete | RU5-TBL | 22-716B/00 | 50 | REL CSER MANC PRC SETC | 5IR | D15/25/B6/RT-C2H | 668130010 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-04-24 |  | 8202235524 | 8202236745 | 8202223727#Perbaikan Seal DBB Valve Mete | RU5-TBL | 22-716B/00 | 50 | REL CSER MANC PRC SETC | 5IR | D15/25/B6/RT-C2H | 1336260020 | 0 | MA4-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-17 | 2102360447 | 8202235529 |  | 8202223724#Perbaikan pompa G-202-07A | RU5-D&W | G-202-07A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 7992500 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238285 | 8202235145 | 8202223723#Tag 9 KV Cleaning Cooler&Cond | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-09-30 | 2102353421 | 8202240628 |  | 8202223719#25_Penggantian gasket HE LPG | RU4-RFCUTL | 157E501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 6200000 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-08-28 | 2102365702 | 8202240626 |  | 8202223714#25_[NP] 47S506B-P6, Perbaikan | LOC1-UP4 | 47S506B-P6/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-6-C2H | 2074915 | 2073450 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102363699 | 8202232457 |  | 8202223710#Pembelian Governor Baru | RU2-HCC | 211-PT-75A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362575 | 8202233798 |  | 8202223709#Pengadaan material 13-FT-751A | RU6-DHC | 13-FT-751A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-23 |  | 8202236649 | 8202233851 | 8202223708#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352196 | 8202234190 |  | 8202223706#Health Check 900-06GE-05 & 07 | RU2S-KIL | 900-06GE-5/00 | 50 | REL NMAT PRC SETC | 2RS | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-02 | 2102360500 | 8202235517 |  | 8202223703#Perbaikan Exciter STG 2.3 | RU5-UTL | 3SR10/00 | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 2368880 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102353565 | 8202240624 |  | 8202223700#25_Perbaikan 102 TG 632 | RU4-RFCC | 102TG-U102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 15 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102360415 | 8202235522 |  | 8202223694#Penggantian Solenoid K-3-02C | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 6 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-15 | 2026-03-09 | 2026-12-08 | 2102353504 | 8202241378 |  | 8202223693#25_[CR] Perbaikan Mseal DE 11 | RU4-FOC1 | 11P4A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 351315826 | 0 | MA1-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102351119 | 8202232238 |  | 8202223691#Leakage pada Casing Cover 200 | RU2-HSC | 200-P-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-11-17 |  | 8202237538 | 8202238637 | 8202223690#TGH3_SIP_CPI MA 3 Tahun 2022 | RU4-TRML | 70HB1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-11-19 | 2102354154 | 8202238637 |  | 8202223689#TGH2_SIP_CPI MA 3 Tahun 2022 | RU4-TRML | 66HB101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102359622 | 8202235520 |  | 8202223687#Perbaikan 3B-LT-530 di C-3-24 | RU5-E15112 | 03B-LT-530/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102359855 | 8202235491 |  | 8202223685#Perbaikan Transmitter 202-TT- | RU5-D&W | 202-TT-055/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-12-28 |  | 8202237536 | 8202237513 | 8202223683#TGH27-28_22 Sewa CCTV Tanki 4 | RU4-RFCGTO | 47T511A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 116661000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352618 | 8202234188 |  | 8202223678#Kebocoran Line Disch dan Load | RU2S-KIL | 946-TK-08/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-30 |  | 8202232739 |  | 8202223677#Solenoid 52XV002B antisipasi | RU6-UTL | 52-XV-002B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 12144 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-11 | 2026-01-02 | 2026-11-30 | 2102352616 | 8202234187 |  | 8202223676#Demolish Unused Pipe 18" 946- | RU2S-KIL | 946-ITP-PIPING/00 | 60 | REL CSER GMPS MANC PRC SETC | 2MS | D12/25/B6/NRZ-C1H | 3958582 | 3268428 | MAS-ME2 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-03-16 | 2102362026 | 8202233818 |  | 8202223675#Pengadaan FGDS General Monito | RU6-LK/KK | 66-FS-408/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1428 | 450000000 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-03-13 | 2102362571 | 8202233252 |  | 8202223671#Perbaikan 55-A-101C-P3-M | RU6-UTL | 55-A-101C-P3-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1296 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-01 | 2025-12-01 | 2102360449 | 8202235430 |  | 8202223670#Perbaikan motor Gm-3-16C | RU5-E15112 | GM-3-16C/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1417450 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-30 | 2025-12-30 |  | 8202235428 | 8202235321 | 8202223668#Reroute Kabel Kontrol MOV5A&5 |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 55294000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-16 | 2102365343 | 8202240621 |  | 8202223664#25_[RP] Pompa Make Up Chemica | RU4-GTO | 100WSA601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102358232 | 8202235484 |  | 8202223660#Perbaikan Grounding Transform |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 115600000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-01 | 2025-12-01 | 2102359753 | 8202235441 |  | 8202223659#Perbaikan motor Gm-17-03B | RU5-HSC |  | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 534345 | 0 | MA3-LIS |  | SAPBATCH | 2026-06-09 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-21 | 2025-12-24 | 2025-12-24 | 2102351113 | 8202238276 |  | 8202223658#LTSA Alat Ukur Pemantauan Lim | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2IR | D12/24/B6/RT-D2H | 100000000 | 84801000 | MA3-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-12-24 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-15 | 2026-02-02 | 2026-02-27 |  | 8202238257 | 8202234942 | 8202223657#Tag 11 PM Clean. PreHeater&Re | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-15 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-05 | 2026-01-05 | 2102352619 | 8202234186 |  | 8202223651#Pembutan Lubang Sampling | RU2S-LKKK | 900-06GS-3-D/01 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-13 | 2102361264 | 8202237535 |  | 8202223642#TGH2_23 UP Penyehatan SRU tah | RU4-SRU | 94C401/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-09 | 2026-12-01 | 2026-12-30 | 2102360441 | 8202235321 |  | 8202223640#Perbaikan MOV 4D, 4G, 5G, 3F, |  |  | 60 | REL CNF CSER GMCO GMPS MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 31907500 | 13647500 | MA4-LIS |  | GHAGASP | 2026-03-13 | 2026-02-11 | PT02 | 8 | 3 | 2026-12-01 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-09-18 | 2102366054 | 8202240619 |  | 8202223638#25_[CR] 013P104A Cooler Plan | RU4-FOC2 | 013P104A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353631 | 8202236636 |  | 8202223633#Penggantian LTMR Motor LV 102 | RU4-RFCC | 102P506M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-11-16 | 2102365342 | 8202240617 |  | 8202223632#25_[CR]Penggantian Bearing Ch | RU4-LOC2 | 024E102C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 247008 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365736 | 8202240615 |  | 8202223630#25_[CR] Perbaikan fan 52B201K | RU4-UTL | 52B201K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-03-09 | 2102366033 | 8202241376 |  | 8202223627#25_[CR] Penggantian Mech Seal | RU4-LOC2 | 024P107A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 102526433 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365455 | 8202240613 |  | 8202223623#25_Penggantian FSL Pompa 71P7 | RU4-TRML | 71P7C/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 28000000 | 144000000 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2102359258 | 8202235399 |  | 8202223622#Pengadaan Material K-3-02A | RU5-E15112 | K-3-02A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 1370709130 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365454 | 8202240611 |  | 8202223621#25_Penggantian FSL Pompa 71P7 | RU4-TRML | 71P7B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 28000000 | 144000000 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365453 | 8202240609 |  | 8202223619#25_Penggantian FSL Pompa 71P7 | RU4-TRML | 71P7A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 28000000 | 72000000 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-31 | 2025-12-31 | 2102359177 | 8202235350 |  | 8202223615#Perbaikan Fin-fan Ea-3-02N | RU5-E15112 | EF-3-02N/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 5818445 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-02 | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102358872 | 8202235298 |  | 8202223614#Perbaikan Transmitter 3B-FT-6 | RU5-E15112 | 3B-FT-641B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 11979990 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102358962 | 8202235392 |  | 8202223613#Penggantian PI Balancing BFW | RU5-UTL | 2RL-10D001-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1920000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2102360560 | 8202235390 |  | 8202223612#Perb Level Alarm Switch Separ | RU5-E15111 |  | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 312000000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102354282 | 8202240607 |  | 8202223609#25_Body Control Valve 120FV02 | RU4-GTO | 120FV022/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102360591 | 8202235299 |  | 8202223608#Perbaikan Pompa G-35-101F | RU5-E15112 | G-35-101F/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 182196 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361060 | 8202236098 |  | 8202223603#Perbaikan Contl Panel Heater | RU4-KPC | 89P201A/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361061 | 8202236100 |  | 8202223600#Perbaikan Contl Panel Heater | RU4-KPC | 84K201/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2025-12-01 | 2026-03-31 | 2102359102 | 8202235396 |  | 8202223593#Penggantian 313-LT-801 Steam | RU5-UTL | HHP-3-INST/00 | 60 | REL NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 1536 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-10 | 2026-03-05 | 2026-03-05 | 2102359675 | 8202235347 |  | 8202223590#Perbaikan Motor Gm-3-11B | RU5-E15112 |  | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1297419 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-03-10 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238281 | 8202235068 | 8202223586#Tagihan Ke- 4 Pekerjaan Isola |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365875 | 8202240605 |  | 8202223585#25_Penggantian Catridge Filte | RU4-GTO | 105A501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-09-24 | 2102365669 | 8202240603 |  | 8202223583#25_Butterfly Valve H2 140D602 | RU4-GTO | 140D602A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363683 | 8202232428 |  | 8202223580#Governor Hunting | RU2-HCC | 212-PT-4B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363617 | 8202232353 |  | 8202223577#Perbaikan Fan | RU2-HCC | 211-EF-20E/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 30100000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-23 | 2026-07-22 | 2102360504 | 8202235292 |  | 8202223575#Pengambilan LT D-31-14 dan D- | RU5-E15112 | 32-LT-303/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 71921194 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-23 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-12-17 | 2102366043 | 8202241375 |  | 8202223574#25_[CR] Mech seal 21P10A nete | RU4-LOC1 | 21P10A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 108068150 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102363979 | 8202240601 |  | 8202223561#25_013E107M1 puly motor rusak | RU4-FOC2 | 013E107M01/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 8550000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-04-28 | 2026-04-01 | 2026-12-29 | 2102361263 | 8202237534 |  | 8202223557#Penambahan atap permanen 13K- | RU4-FOC1 | 13K1A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102362178 | 8202233848 |  | 8202223555#Pembuatan IBC kultivasi bakte | RU6-ITP | 63-A-301A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 7920 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-11-13 | 2102362365 | 8202236700 |  | 8202223551#SPK#14 LTSA Pompa Sump (64-P- | RU6-HSC | 64-P-101A/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-12-29 | 2102361670 | 8202236703 |  | 8202223549#SPK#12 LTSA Pompa Sump (42-P- | RU6-ITP | 42-P-907/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-07-09 | 2102360561 | 8202235294 |  | 8202223546#Material Perbaikan E-3-35B | RU5-E15112 | K-3-02B/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-10 | 2026-07-14 | 2102358913 | 8202235190 |  | 8202223545#PM Equipment G-202-05A | RU5-D&W | G-202-05A/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 23820334 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-10 | 2026-07-14 | 2102358912 | 8202235192 |  | 8202223544#PM Equipment G-202-03B | RU5-D&W | G-202-03B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 23820334 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-07-15 | 2102358911 | 8202235195 |  | 8202223543#PM Equipment G-202-03A | RU5-D&W | G-202-03A/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 23820334 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-08-28 | 2102358871 | 8202235218 |  | 8202223542#PM All Fin-fan Area HVU 3 |  |  | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 136706521 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-08-28 | 2102358870 | 8202235227 |  | 8202223541#PM All Fin-fan Area CDU V |  |  | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 17319630 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-08-28 | 2102358875 | 8202235208 |  | 8202223540#PM Equipment G-201-01A | RU5-D&W | G-201-01A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 40487000 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-08-28 | 2102358876 | 8202235206 |  | 8202223539#PM Equipment G-201-01B | RU5-D&W | G-201-01B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 40487000 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-07-15 | 2102358877 | 8202235204 |  | 8202223535#PM Equipment G-201-08A | RU5-D&W | G-201-08A/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 23820334 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-08-28 | 2102358878 | 8202235202 |  | 8202223534#PM Equipment G-201-08B | RU5-D&W | G-201-08B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 23820334 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-11-04 | 2102362221 | 8202236861 |  | 8202223533#Perbaikan Pompa 15-P-101 Body | RU6-RCC | 15-P-101A/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-08-28 | 2102358879 | 8202235201 |  | 8202223532#PM Equipment G-202-01A | RU5-D&W | G-202-01A/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 21820334 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-07-15 | 2102358910 | 8202235198 |  | 8202223531#PM Equipment G-202-01B | RU5-D&W | G-202-01B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 21820334 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-07-15 | 2102358918 | 8202235185 |  | 8202223529#PM Equipment GS-202-03B | RU5-D&W | GS-202-03B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 141661309 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238271 | 8202235105 | 8202223527#Tag 1 Mekanik CDL, OM, UTL SG |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-07 | 2026-01-02 | 2026-01-02 | 2102353241 | 8202235105 |  | 8202223526#Pekerjaan Mekanik CDL, OM, UT |  |  | 60 | REL CNF PRT GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | HANGGAO | 2026-03-06 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102361013 | 8202235295 |  | 8202223525#Perbaikan VSD Finfan 101E532B | RU4-RFCC | 101E532BM2/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-10 | 2026-07-14 | 2102358915 | 8202235188 |  | 8202223524#PM Equipment GS-201-01B | RU5-D&W | GS-201-01B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 141661309 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-07-15 | 2102358916 | 8202235187 |  | 8202223523#PM Equipment GS-201-08B | RU5-D&W | GS-201-08B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 137840975 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-12-01 | 2025-12-01 | 2102361023 | 8202235301 |  | 8202223522#Perbaikan VSD 102E520B2M | RU4-RFCC | 102E520BM2/00 | 50 WAMA | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-01 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-13 | 2026-04-13 | 2026-07-15 | 2102358917 | 8202235186 |  | 8202223521#PM Equipment GS-202-01B | RU5-D&W | GS-202-01B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 141661309 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-02 | 2026-01-02 | 2026-05-29 | 2102361024 | 8202235303 |  | 8202223520#Perbaikan VSD 102E518AM2 | RU4-RFCC | 102E518AM2/00 | 60 | TECO CNF CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 78906240 | 0 | MA6-LIS |  | SAPBATCH | 2026-06-02 | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360535 | 8202235745 |  | 8202223519#Perbaikan motor pompa 103P512 | RU4-RFCC | 103P512BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361028 | 8202235509 |  | 8202223518#Perbaikan Power 102P505A | RU4-RFCC | 102P505AM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-03 | 2025-12-12 | 2025-12-12 | 2102358960 | 8202235184 |  | 8202223516#PM Equipment K-235-01B | RU5-D&W | K-235-01B/00 | 60 | CLSD NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361040 | 8202235840 |  | 8202223515#Perbaikan local ampere 102P50 | RU4-RFCC | 102P503BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361056 | 8202236055 |  | 8202223514#Perbaikan fan trip 101F503K3M | RU4-RFCC | 101F503K3MCC/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360964 | 8202236253 |  | 8202223512#Fan Motor 140P603A/B Rusak | RU4-GTO | 140P603B/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102359461 | 8202235272 |  | 8202223510#Penggantian Hose Lube Oil 101 | RU5-TBL | 101-PT-1A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-12-18 | 2026-12-18 | 2102359460 | 8202235275 |  | 8202223509#Penggantian hose fuel gas Gen | RU5-TBL | 101-GT-1A/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102351188 | 8202232314 |  | 8202223507#Kebutuhan Constant Level Oile | RU2-UTL | 925-P-7A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-12-01 | 2102365820 | 8202240599 |  | 8202223503#25_Mtl. Penggantian bocoran l | RU4-SRU | 91V405A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 6577150 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2027-01-04 | 2102363033 | 8202236790 |  | 8202223502#Re Routing Line Condensate MO | RU6-ITP | 42-PIPE/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 656000000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238258 | 8202234668 | 8202223497#Tag 5 Perbaikan Bocoran Onlin | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-03-03 | 2026-06-17 | 2026-01-02 | 2026-06-08 | 2102359301 | 8202239375 |  | 8202223495#NRK_Perbaikan Permanen tanggu | RU5-UTL | DAM-SEIWAIN/00 | 50 | REL NMAT PRC SETC | 5MR | D15/26/B6/RT-C2H | 36490000 | 0 | MA4-STA |  | FAUZANR |  | 2026-06-17 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 | 2102360102 | 8202235244 |  | 8202223491#Perbaikan Cation 4 Demin Plan |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-19 | 2026-06-19 | 2102360517 | 8202235183 |  | 8202223490#Pompa chemical untuk area WTP | RU5-UTL | G-32-26A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-29 | 2026-10-06 | 2026-12-01 | 2102359254 | 8202235269 |  | 8202223489#Penggantian Lateral Filter Di |  |  | 60 | REL CNF CSER MANC PRC SETC | 5MR | D15/25/B6/NR-C2H | 1702834 | 0 | MA1-STA |  | JOYOPRATIKN | 2026-05-29 | 2026-05-06 | PT02 |  | 3 | 2026-10-06 | PM |  | 045
| K501 | 2026-02-02 |  | 2025-11-28 | 2025-12-30 | 2102359028 | 8202235245 |  | 8202223488#Perb. Line pendingin ke pompa | RU5-UTL | P-4PAMPANCUR/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-W1NH | 269 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102359101 | 8202235232 |  | 8202223486#Perbaikan Line Pendingin G-32 | RU5-E15112 | 32-FT-009/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SCNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102359960 | 8202235229 |  | 8202223485#Perbaikan Saluran pendingin G | RU5-UTL | G-32-05C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 33214802 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-18 | 2102359750 | 8202235228 |  | 8202223484#Perbaikan Sample Point Water | RU5-UTL | HHP-4/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1367500 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354004 | 8202237023 |  | 8202223483#Penggantian motor 91K-402APM | RU4-SRU | 91K402APM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360150 | 8202235281 |  | 8202223482#Ganti Valve Suction GM 37 201 |  | FA-201/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-01NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-24 | 2102362044 | 8202237783 |  | 8202223480#LTSA Perbaikan Bocoran Fire W | RU6-UTL | 66-FF-8101-MS01/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 402633100 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359021 | 8202235287 |  | 8202223474#Ganti Material Valve pompa P6 | RU5-UTL | P-6PAMPANCUR/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/NR-C2H | 1874306 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-02-06 |  | 2026-02-06 | 2026-02-06 |  | 8202238682 |  | 8202223466#RKAP25L_Atap & Overhead 24S1A | RU4-LOC1 | 24S1A/00 | 50 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 70000000 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-09-25 | 2026-09-25 | 2102359857 | 8202235174 |  | 8202223464#Perbaikan K-34-01B | RU5-D&W | K-34-01B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 48450000 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-09-25 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-29 | 2102362048 | 8202237780 |  | 8202223459#LTSA Scaffolding 2024-2026 Ta | RU6-POC | 34-V-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C1H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362172 | 8202233130 |  | 8202223458#Perbaikan Kompressor | RU6-ITP | 63-K-401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 171647 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-03-15 | 2102362888 | 8202233749 |  | 8202223457#Pengadaan spare parts turbine | RU6-UTL | 51-G-101E-P2A-T/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 35640 | 5625000 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366023 | 8202240597 |  | 8202223452#25_Perbaikn limit switch trip | RU4-UTL | 510G601T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 3900000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365955 | 8202240594 |  | 8202223451#25_Perbaikan 154LT602B | RU4-RFCUTL | 154LT602B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366018 | 8202240591 |  | 8202223449#25_Perbaikan Level Varec 054T | RU4-UTL | 054T103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366020 | 8202240588 |  | 8202223448#25_Penggantian solenoid valve |  |  | 60 | REL CNF CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 9848000 | 9848000 | MA5-INT |  | SAPBATCH | 2026-04-09 | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366019 | 8202240561 |  | 8202223447#25_Penggantian solenoid valve |  |  | 60 | REL CNF CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 9848000 | 9848000 | MA5-INT |  | SAPBATCH | 2026-04-09 | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365964 | 8202240547 |  | 8202223446#25_PENGGANTIAN 157PT005 | RU4-RFCUTL | 157PT-U157/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 12249320 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365954 | 8202240545 |  | 8202223444#25_PENGGANTIAN SOLENOID 154XV | RU4-RFCUTL |  | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-09 | 2026-02-02 | 2026-02-02 | 2102351189 | 8202232259 |  | 8202223442#Kebutuhan re-lagging pulley 1 | RU2-HOC | 170-ME-103-2/00 | 50 | CRTD NMAT PRC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA1-ROT |  | ADEMULYADI |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363786 | 8202232691 |  | 8202223437#Tindak lanjut pasca breakdown | RU2-HOC | 220-C-1B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-25 | 2026-05-29 | 2102358873 | 8202235176 |  | 8202223436#Perbaikan Grounding Trafo di | RU5-UTL | 41-R-SS-73/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 5615380 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102354000 | 8202236610 |  | 8202223435#Penggantian Motor 43P2AM | RU4-TRML | 43P2AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-07 | 2026-07-30 | 2026-08-03 | 2102359364 | 8202235178 |  | 8202223434#Modul MOV outlet TU 14 Rusak | RU5-TBL | U-14/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 129800000 | 0 | MA1-LIS |  | AGUSHIDAYAT |  | 2026-02-11 | PT02 |  | 3 | 2026-07-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-10-30 | 2102365703 | 8202240537 |  | 8202223433#25_[CR] Perbaikan Bearing 101 | RU4-RFCC | 101P522B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102363622 | 8202232355 |  | 8202223432#Pompa rusak | RU2-HCC | 410-P-52A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-11 | 2026-02-03 | 2026-02-03 | 2102353950 | 8202235658 |  | 8202223429#Perbaikan Pilot 101-F-504 | RU4-RFCC | 101F504/00 | 60 | TECO CNF CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH | 2026-05-11 | 2026-02-07 | PT02 |  | 3 | 2026-05-11 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102365688 | 8202240536 |  | 8202223427#25_[CR] Perbaikan pompa 30P10 | RU4-TRML | 30P105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102366029 | 8202240535 |  | 8202223425#25_[NP] 47S511, perbaikan Gea | LOC1-UP4 | 47S511-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 145650 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102354002 | 8202237061 |  | 8202223423#Pengantian Motor 54WS2P3 | RU4-UTL | 54WS2P3M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362323 | 8202233250 |  | 8202223420#Perbaikan 62-P-201D-T | RU6-UTL | 62-P-201D-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-20 | 2102361955 | 8202233642 |  | 8202223414#Penggantian flame detector UV | RU6-UTL | 52-B-101C/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1584 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238254 | 8202234515 | 8202223407#Tag 7 Pemeliharaan Fire Extin | RU3-LKKK |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238250 | 8202234515 | 8202223406#Tag 6 Pemeliharaan Fire Extin | RU3-LKKK |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238155 | 8202234515 | 8202223404#Tag 5 Pemeliharaan Fire Extin | RU3-LKKK |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102358664 | 8202234423 |  | 8202223403#Penggantian Timing Belt 2-EA- |  |  | 60 | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-06-08 | 2026-02-02 | 2026-02-02 | 1102329625 | 8202232730 |  | 8202223402#Superior Order Welder Pipe Fi | RU6-RCC | 15-R-101/00 | 01 | CLSD CSER NCMP NMAT PRC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365982 | 8202240534 |  | 8202223401#25_Perbaikan 102 LT 020 A B C | RU4-RFCC | 102V502/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 3 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-11-12 | 2102365313 | 8202240533 |  | 8202223399#25_[CR] Perbaikan Line Lube O | RU4-UTL | 56K201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365952 | 8202240532 |  | 8202223398#25_Penggantian PG Sealing 101 | RU4-RFCC | 101P523C/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 6017241 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365951 | 8202240531 |  | 8202223397#25_Penggantian PG discharge r | RU4-RFCC | 101P501A/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 6309835 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365950 | 8202240530 |  | 8202223394#25_Penggantian PG Line HPS Pr | RU4-RFCC | 101F503/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 6309835 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362132 | 8202233165 |  | 8202223391#Perbaikan Flow Transmitter 32 | RU6-HSC | 32-FT-039/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365948 | 8202240528 |  | 8202223388#25_Perbaikan Pressure Gauge A | RU4-RFCC |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 103152450 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-01 | 2102362136 | 8202233265 |  | 8202223381#Perbaikan 50-P-201A | RU6-UTL | 50-P-201A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 160163 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361170 | 8202237081 |  | 8202223379#Pengambilan Sealent (K3009001 | RU4-LOC2 | 40LTW09/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-04-23 | 2026-02-03 | 2026-02-03 | 2102361155 | 8202237082 |  | 8202223377#Pengambilan Scoth Tape 33 (J6 | RU4-LOC2 | 40LTW08/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361156 | 8202237083 |  | 8202223376#Pengambilan Scoth Tape 23 (J6 | RU4-LOC2 | 40LTW08/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360539 | 8202235821 |  | 8202223375#Perbaikan motor 16A1P1AM | RU4-FOC1 | 16A1P1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-08-10 | 2102362319 | 8202232879 |  | 8202223373#Perbaikan solenoid dan Positi | RU6-HSC | 33-FV-027/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-08 | 2102362807 | 8202233225 |  | 8202223372#Perbaikan Bearing Pompa 15-P- | RU6-RCC | 15-P-102A/00 | 60 | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 2363898 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-03-31 | 2026-03-16 | 2026-12-30 |  | 8202238264 |  | 8202223371#Perbaikan struktur jetty area | RU2-ITP | DPN-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 700000000 | 0 | MA4-STA |  | NURFADHILLA |  | 2026-03-30 | PT02 |  | 3 | 2026-03-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102361999 | 8202233219 |  | 8202223370#Perbaikan Bocoran Mechseal 17 | RU6-RCC | 17-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362811 | 8202232862 |  | 8202223369#Perbaikan Thermocouple 32-TI- | RU6-HSC | 32-A-101-E6/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-02 | 2026-12-31 | 2026-12-31 | 2102363527 | 8202238263 |  | 8202223368#Pekerjaan Piping Bordes Area | RU2-HCC | 0-75CC21133MS11/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 200000000 | 0 | MA2-STA |  | ERLANGGA |  | 2026-05-20 | PT02 |  | 3 | 2026-12-31 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-21 | 2102361262 | 8202237533 |  | 8202223367#TGH1_SIP_UP Tenaga Kerja MA 3 | RU4-TRML | 033PSV305/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352058 | 8202234671 |  | 8202223364#Material utama Perbaikan DA22 | RU3-PP | 23-DA-2203/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102365683 | 8202240515 |  | 8202223363#25_[NP] 017E103K2 Bearing Def | RU4-FOC2 | 017E103K02/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 12645694 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102360569 | 8202235164 |  | 8202223361#Perbaikan Pompa G-3-16D | RU5-E15112 | G-3-16D/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 893036 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102361041 | 8202235888 |  | 8202223360#Meremajakan Block Valve Line | RU4-TRML | 72FMMOV101AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-04-15 | 2026-04-15 | 2026-07-17 | 2102362130 | 8202233218 |  | 8202223357#Perbaikan Bocoran Mechseal O/ | RU6-RCC | 15-P-108B/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 149735628 | 149735628 | MA1-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-11-10 | 2102366042 | 8202241366 |  | 8202223356#25_[CR] Mech seal 22P2A netes | RU4-LOC1 | 22P2A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 51838100 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-09-23 | 2102361828 | 8202232900 |  | 8202223355#Perbaikan Red Lion 15-A-107 | RU6-RCC | 15-A-107A/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102359250 | 8202235165 |  | 8202223352#Perbaikan Pompa G-3-08A | RU5-E15112 | G-3-08A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 30466666 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-25 | 2026-02-25 | 2102352146 | 8202234185 |  | 8202223351#Kebutuhan Material Grease Bea | RU2S-KIL | 900-06GE-6-G/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 40343166 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-25 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102360563 | 8202235168 |  | 8202223350#Penggantian Filter L/O Turbin | RU5-E15112 | GT-2-03A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 3297217 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-22 | 2102359466 | 8202235170 |  | 8202223339#Material Perbaikan Ejector SW | RU5-UTL | 32-PSV-393/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362175 | 8202233554 |  | 8202223333#Penggantian Pipa Fire All Are | RU6-HSC | 66-FW-8701-MS20/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102361261 | 8202237532 |  | 8202223332#Tagihan Assesment Elevator RF | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-13-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-21 | 2102361994 | 8202233795 |  | 8202223330#Pengadaan Material 32-TXI-329 | RU6-HSC | 32-A-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-10 | 2026-01-02 | 2026-01-02 | 2102352246 | 8202234184 |  | 8202223329#101-PCV042 indikasi passing | RU2S-KIL | 101-FCV-042/00 | 50 | REL CSER MANC PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 18876002 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-14 | 2026-07-28 | 2102362182 | 8202233780 |  | 8202223328#Pengadaan Material Vibrasi di | RU6-HSC | 31-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-03 | 2026-01-01 | 2026-01-01 | 2102353323 | 8202235056 |  | 8202223327#KV Listrik Area Oil Movement |  |  | 60 | REL CNF PRT GMCO NMAT PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-LIS |  | RAMADENY | 2026-06-08 | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361131 | 8202236719 |  | 8202223326#D_25 048K101A motor short | RU4-TRML | 048K101AM/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363547 | 8202232203 |  | 8202223325#Perbaikan Motor Gantry Crane | RU2-HOC | 140-PC-51/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 564000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361115 | 8202236561 |  | 8202223323#D_25 push bottom finfan FOC I | RU4-FOC2 | 017E105M02/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-20 | 2102359027 | 8202235162 |  | 8202223322#Penggantian Level Glass Polis | RU5-UTL | D5-BV-2-2/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 11 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365905 | 8202240512 |  | 8202223320#25_014BV075 rusak | RU4-FOC2 | 014BV75/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-05 | 2026-06-12 | 2026-02-05 | 2026-12-30 | 2102364384 | 8202238634 |  | 8202223317#TGH4_24 UP Clean SWD Jet Pres | RU4-UTL | 54FIC304/00 | 60 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TONNYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-11-11 | 2102359300 | 8202235159 |  | 8202223316#Perbaikan Control Valve 31-PC | RU5-E15112 | GCP-PIC-101/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 150000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359026 | 8202235163 |  | 8202223315#MAT.GANTI BEARING VALVE OUTLT | RU5-TBL | 101-5-T-01G/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 2866200 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-08-18 | 2102358967 | 8202235147 |  | 8202223314#Perbaikan Level Transmitter 0 | RU5-E15111 | 05-LT-107/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202236263 |  | 8202223310#perbaikan / penggantian tutup |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365552 | 8202240510 |  | 8202223306#25_Penggantian After Cooler 5 | RU4-UTL | 56K3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102363776 | 8202232651 |  | 8202223300#Pengadaan Seal Nippon Pillar | RU2-HSC | 301-P-1A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 184115600 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365531 | 8202240507 |  | 8202223297#25_Perbaikan Levelglass 151-B | RU4-RFCUTL | 151B501B/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 127800000 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365458 | 8202240504 |  | 8202223294#25_Kerusakan Solenoid Valve d | RU4-LOC3 | 240KV178A/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 336324000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-07-06 | 2102358665 | 8202234413 |  | 8202223289#Perbaikan Line P 116 Area CDU |  |  | 50 | CRTD CSER NMAT PRC | 7RT | D17/25/B6/RT-1-D4H | 0 | 0 | MA-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102358666 | 8202234400 |  | 8202223287#PERBAIKAN RUTIN |  |  | 60 | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D4H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352144 | 8202234183 |  | 8202223281#Pemeriksaan Pipa Fresh Water | RU2S-KIL | 900-03P-6D/01 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-11-17 | 2025-11-17 | 2102363670 | 8202232419 |  | 8202223280#Perbaikan 940-LIC-14 | RU2-UTL | 940-LT-14/00 | 50 | CRTD CSER MACM PRC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA3-INT |  |  |  |  | PT02 |  | 2 | 2025-11-17 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361087 | 8202236454 |  | 8202223278#D25_013K-101B ALOP Penunjukka | RU4-FOC2 | 013K101B/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238261 | 8202234997 | 8202223277#Tag 5 KV Penyediaan Jasa Hose |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238168 | 8202238038 | 8202223275#Tag 8 KV Pengecatan Pipa dan |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365913 | 8202240501 |  | 8202223274#25_Penggantian 520LT104 (For | RU4-UTL | 520LT104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-05 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238623 | 8202238038 | 8202223273#Tag 7 KV Pengecatan Pipa dan |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238252 | 8202235215 | 8202223270#Tag 7 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238244 | 8202235367 | 8202223269#Tag 6 Steam Leak non Trap Kil |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365539 | 8202240497 |  | 8202223267#25_[CR] Penggantian Coupling | RU4-TRML | 63P201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-02 | 2102360566 | 8202235157 |  | 8202223264#Perbaikan Lampu Jalan Lawe-la |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 131411500 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-05 | 2026-02-14 | 2026-02-05 | 2026-11-05 | 2102359624 | 8202238670 |  | 8202223262#NRK_Peng. Battery&Charger Law | RU5-TBL | 101-PT-01A-INST/00 | 50 | REL NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 18000000 | 0 | MA4-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365912 | 8202240494 |  | 8202223261#25_Perbaikan SOV MP Steam 051 | RU4-UTL | 051P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102358965 | 8202235161 |  | 8202223258#Perb Heater Assy O2 Analizer | RU5-UTL | B4-AR-501/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 73856000 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-08-21 | 2102362546 | 8202234031 |  | 8202223257#Cons Perbaikan bushing Motor | RU6-POC | 37-P-101A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 271735 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-28 | 2102361789 | 8202232829 |  | 8202223256#Perbaikan UPS DC Quint 11-P-1 | RU6-HSC | 11-P-109B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-25 | 2102362954 | 8202233707 |  | 8202223255#Penggantian Aux Relay MCC SS | RU6-HSC | 17-PMC2-02B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2019 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-08-10 | 2102362885 | 8202233576 |  | 8202223254#Penggantian Mtl Elect Boiler | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2844 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-25 | 2102363020 | 8202233255 |  | 8202223253#Perbaikan 53-P-101AM | RU6-UTL | 53-P-101A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 20196 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-07-31 | 2102362953 | 8202233834 |  | 8202223252#Pengadaan Air Filter Motor 58 | RU6-UTL | 58-K-101A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2052 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-24 | 2102362952 | 8202233822 |  | 8202223251#Pengadaan CT untuk Motor Tosh | RU6-UTL | SS-01/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 290020062 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-12 | 2026-02-02 | 2026-11-04 | 2102363025 | 8202233122 |  | 8202223250#Perbaikan LCS 51-G-101A-S1 | RU6-UTL | 51-G-101A-S1-M/00 | 50 WAMA | REL MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 127953672 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-12 | 2026-02-02 | 2026-11-04 | 2102362887 | 8202233123 |  | 8202223249#Perbaikan LCS 51-G-101A-K1 | RU6-UTL | 51-G-101A-K1-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 23892 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-12 | 2026-02-02 | 2026-11-04 | 2102363082 | 8202233124 |  | 8202223248#Perbaikan LCS 50-P-901A | RU6-UTL | 50-P-901A-M/00 | 50 WAMA | REL MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 41637548 | 0 | MA4-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-05-29 | 2102358961 | 8202235144 |  | 8202223246#MAT.PERB.LINE 21-P412-30" DI | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 1523901334 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102363110 | 8202233006 |  | 8202223244#Perbaikan Pneumatic Transmitt | RU6-HSC | 23-FT-005/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366017 | 8202240490 |  | 8202223243#25_Pengadaan 530P301BM | RU4-UTL | 530P301BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366008 | 8202240486 |  | 8202223242#25_Pengadaan 053P101CM | RU4-UTL | 053P101CM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366016 | 8202240482 |  | 8202223241#25_Pengadaan 051P102BM | RU4-UTL | 051P102BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366015 | 8202240478 |  | 8202223240#25_Pengadaan 051P101BM | RU4-UTL | 051P101BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-11-02 | 2102361009 | 8202235214 |  | 8202223239#Pekerjaan Rejuvenate Isolasi | RU4-UTL | 051E103/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102362778 | 8202233012 |  | 8202223238#Perbaikan part sample gas coo | RU6-RCC | 15-AT-004/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102362405 | 8202233493 |  | 8202223235#Penggantian Solenoid pada 33- | RU6-HSC | 33-XV-021/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-12 | 2026-01-14 | 2102358963 | 8202235101 |  | 8202223233#Perbaikan Scrapper DAF D-34-0 | RU5-D&W | D-34-04B/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 3200269 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-29 | 2025-12-15 | 2025-12-17 | 2102360592 | 8202235123 |  | 8202223232#Perbaikan Motor GM-1-12C | RU5-E15111 | GM-1-12C/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1384427 | 0 | MA2-LIS |  | SAPBATCH | 2026-05-29 | 2026-02-11 | PT02 |  | 3 | 2026-05-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102365686 | 8202240475 |  | 8202223230#25_[CR] Perbaikan Pompa 13P3 | RU4-FOC1 | 13P3/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1465 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-31 | 2102365706 | 8202240471 |  | 8202223227#25_[CR] 011E111K3 Bearing Def | RU4-FOC2 | 011E111K03/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 6650551 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-20 | 2026-02-03 | 2026-07-28 | 2102361215 | 8202237359 |  | 8202223226#84K202P4B Mech Seal Bocor | RU4-KPC | 84K202P4B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2025-10-01 | 2025-12-30 | 2102360074 | 8202235142 |  | 8202223213#Penambahan UPS untuk Metering | RU5-TBL |  | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 53001152 | 0 | MA4-LIS |  | GHAGASP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359806 | 8202235132 |  | 8202223212#Pengadaan material dan Perb M | RU5-TBL | PLANT-24-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 50 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102359309 | 8202235124 |  | 8202223210#Perb. Motor GM20-07B Gasoline | RU5-TBL | GM-20-07B/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 4753975 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-09 | 2026-03-05 | 2026-03-05 | 2102359679 | 8202235122 |  | 8202223208#Perbaikan Motor GM-3-35D | RU5-E15112 |  | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 727491 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-11-27 | 2102361260 | 8202237531 |  | 8202223206#TGH3_22 UP Penyehatan HE MA 1 | RU4-FOC1 | 12E1A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-17 | 2102362853 | 8202233096 |  | 8202223202#Perbaikan mech seal pompa | RU6-ITP | 42-P-304B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 25080 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360972 | 8202234438 |  | 8202223201#Pengadaan ring burner 12F-1 | RU4-FOC1 | 12F1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361128 | 8202236632 |  | 8202223198#Penggantian Microfilter 16MF1 | RU4-FOC1 | 16WS101/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361090 | 8202236477 |  | 8202223197#Penggantian strainer 14PV-018 | RU4-FOC1 | 14PV018A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361138 | 8202236862 |  | 8202223195#penggantian filter lobe oil 1 | RU4-FOC1 | 14K602BM-S1A/B/00 | 50 WAMA WENG | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 001
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360974 | 8202234500 |  | 8202223194#Pengadaan oring burner FO 11F | RU4-FOC1 | 11F1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361021 | 8202235166 |  | 8202223193#Pemasangan steam trece | RU4-FOC1 | 11C1/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-08-13 | 2102362113 | 8202233819 |  | 8202223177#Pengadaan entrance bushing 11 | RU6-HSC | 11-V-101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2027-02-15 | 2102359302 | 8202235098 |  | 8202223175#Perb. Sol.Control Val. 35-XCV | HCC-UP5 | 35-INTAIR-INT/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1000000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2027-01-25 | 2102359429 | 8202235097 |  | 8202223174#Perbaikan Control Valve 8A-LC | RU5-E15112 | 08A-LCV-297/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 300000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365806 | 8202240467 |  | 8202223171#25_Mtl. Perbaikan Strainer Di | RU4-FOC1 | 11C2/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 155755 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353248 | 8202234829 |  | 8202223169#Pengambilan Gasket Pompa | RU3-CDGP | CD3-P-001/00 | 60 | REL CSER MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-08 | 2026-02-02 | 2026-11-18 |  | 8202236590 | 8202232732 | 8202223167#Tahap TKDN PM Rutin MA 1 | RU6-RCC | 15-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-11-18 |  | 8202236596 | 8202232732 | 8202223162#Tahap 11 PM Rutin MA 1 | RU6-RCC | 15-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-11-18 |  | 8202236598 | 8202232732 | 8202223161#Tahap 10 PM Rutin MA 1 | RU6-RCC | 15-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-08 | 2026-02-02 | 2026-11-18 |  | 8202236592 | 8202232732 | 8202223159#Tahap 9 PM Rutin MA 1 | RU6-RCC | 15-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2025-12-31 | 2025-12-31 | 2102360078 | 8202235094 |  | 8202223157#Perbaikan G-5-26 | RU5-E15111 | G-5-26/00 | 60 | TECO CNF NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K201 | 2026-02-04 | 2026-03-31 | 2026-05-04 | 2026-05-04 |  | 8202238243 |  | 8202223156#LTSA Piping Bordesk HSC | RU2-HSC | 6-SL-084-BP/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 800000000 | 300000000 | MA2-STA |  | NURFADHILLA |  | 2026-02-07 | PT02 |  | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-12 | 2102362950 | 8202233027 |  | 8202223155#Perbaikan motor 64-M-101 | RU6-HSC | 64-M-101/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366048 | 8202240463 |  | 8202223149#25_88PC257 Rusak |  |  | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 98388910 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365936 | 8202240427 |  | 8202223148#25_Kebocoran body control 85F | RU4-KPC | 85FV225/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238242 | 8202238040 | 8202223145#Kontr.Vol.Mekanik area Utara |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366047 | 8202240424 |  | 8202223144#25_88FC236 Rusak |  |  | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 73064710 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365857 | 8202240400 |  | 8202223142#25_Penggantian PG yang rusak | RU4-RFCC | 101R502/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 6800000 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102362889 | 8202233618 |  | 8202223138#Penggantian Katodik Magnesium | RU6-UTL | 51-G-101D-E1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 7920 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2025-11-10 | 2025-12-19 | 2102358170 | 8202234393 |  | 8202223127#Service air kompressor 4 K 02 | RU7-UTL | 4-K-02B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-4-D1H | 768 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365564 | 8202240397 |  | 8202223125#25_[CR] Penggantian Hanger 02 | RU4-LOC2 | 024S101A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 15916667 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-22 |  | 8202233931 | 8202233902 | 8202223124#Material Mitigasi Panel ELOP | RU6-UTL | 51-G-101CD-BCP/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1800 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102364383 | 8202236122 |  | 8202223122#Gate Valve 4"-150# (Block mod |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237080 |  | 8202223121#Pengambilan Steam Trap Size 1 |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102358914 | 8202235095 |  | 8202223119#Penggantian Gland Packing Pom | RU5-E15112 | GM-3-02D/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365538 | 8202240394 |  | 8202223118#25_[CR] 014K101 delta press f | RU4-FOC2 | 014K101/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 31144216 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366083 | 8202240391 |  | 8202223116#25_[CR] 011P103BT Journal Bea | RU4-FOC2 | 011P103B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-31 | 2025-12-31 | 2102358964 | 8202235089 |  | 8202223115#Perbaikan K-3-02C | RU5-E15112 | K-3-02C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 350293768 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-02 | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362804 | 8202232934 |  | 8202223112#Perbaikan Pompa Chiller B di | RU6-LAB | LABORATORIUM/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 739435 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-07-31 | 2102363323 | 8202234032 |  | 8202223106#Cons Penggantian LCS motor Ar | RU6-UTL | 54-P-101A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 405628 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-24 | 2102362881 | 8202233612 |  | 8202223105#Penggantian lampu emergency a | RU6-UTL | SS-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2064 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-04-30 | 2102362859 | 8202233706 |  | 8202223104#Penggantian Battery 42-P-503C | RU6-ITP | 42-P-503CD/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1416 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365859 | 8202240388 |  | 8202223103#25_Bladder acc Lube oil Kompr | RU4-KPC | 84K201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363609 | 8202232323 |  | 8202223102#Perbaikan Gearbox Drill Stem | RU2-HOC | 140-PX-51A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 65619092 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-11-25 | 2102366026 | 8202241373 |  | 8202223100#25_[CR] Penggantian M.Seal & | RU4-LOC1 | 24P3C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 70643470 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K201 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2102366515 | 8202241572 |  | 8202223098#Perbaikan thermal insulation | RU2-HSC | 200-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 316822000 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-03-11 | PT02 |  | 3 | 2026-03-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365496 | 8202240384 |  | 8202223097#25_[BK] Perbaikan Pompa 101P5 | RU4-RFCC | 101P523B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 182553167 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-11-18 | 2102362802 | 8202233968 |  | 8202223094#LTSA Service Perawatan/Perbai | RU6-RCC | SHELTER-PEM1/00 | 60 | CLSD CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-02-04 | 2102363795 | 8202238025 |  | 8202223092#CLEANING SETT. BASIN DCU 140 | HOC-UP2 | 140-T-52/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 849758000 | 849758000 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-08 | 2026-02-02 | 2026-11-19 |  | 8202236594 | 8202232732 | 8202223091#Tahap 8 PM Rutin MA 1 | RU6-RCC | 15-R-101/00 | 60 | CLSD NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-22 | 2102362766 | 8202233921 |  | 8202223090#Material RAFI Electrical Area | RU6-UTL | 059-A-101A-V4/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1800 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-09 | 2026-02-02 | 2026-09-22 | 1102329623 | 8202232732 |  | 8202223088#Superior Order PM Stationary | RU6-RCC | 15-R-101/00 | 01 | CLSD CSER NCMP NMAT PRC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-09 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-06 | 2102358670 | 8202234392 |  | 8202223086#PENGGANTIAN HANDVALVE FURNACE |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/25/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 | 2026-04-28 | 2026-05-04 | 2026-05-04 | 2102363755 | 8202232580 |  | 8202223085#Penggantian Catridge Filter 5 | RU2-UTL | 560-GT-3/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 469452 | 0 | MA3-STA |  | ERLANGGA |  | 2026-04-28 | PT02 |  | 3 | 2026-05-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-23 |  | 8202233118 |  | 8202223082#Perbaikan Limit Switch 58-K-1 | RU6-UTL | 58-FT-003B/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 19883 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202232916 |  | 8202223081#Perbaikan Press Gauge 56-P-10 | RU6-UTL | 56-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1235 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202232846 |  | 8202223080#Perbaikan Transmitter 55-FT-0 | RU6-UTL | 55-FT-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1235 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-23 |  | 8202232912 |  | 8202223079#Perbaikan Press Switch 52-B-1 | RU6-UTL | 52-FT-204A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 19883 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365390 | 8202240381 |  | 8202223076#25_Perbaikan Pompa 100P632A | RU4-GTO | 100P632A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 1261800 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365537 | 8202240378 |  | 8202223075#25_[CR] Penggantian Mech Seal | RU4-LOC2 | 023P110B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 6928350 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102363823 | 8202238179 |  | 8202223072#Pemeliharaan AC Central (HVAC | RU2-UTL | UTL-AC-ES/00 | 50 | REL NMAT PRC SETC | 2IR | D12/22/B6/RT-D2H | 0 | 0 | WS-IN2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-09 | 2026-03-09 | 2102366032 | 8202241371 |  | 8202223071#25_[CR] Penggantian Bearing 0 | RU4-LOC2 | 021P108/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 90501100 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 |  | 8202233475 |  | 8202223065#Penggantian Tooth belt 36-E-1 | RU6-POC | 36-E-101/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C3H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2102359360 | 8202235074 |  | 8202223063#Perbaikan Ampere Indikator GM | RU5-D&W | GM-202-02A/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-04 | 2025-12-08 | 2102359105 | 8202235072 |  | 8202223062#Perbaikan power motor P-2 A/B | RU5-D&W | PM-2A-CPI/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 12469400 | 0 | MA2-LIS |  | SAPBATCH | 2026-06-02 | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102359422 | 8202235083 |  | 8202223058#Penggantian Junction Box Mete | RU5-TBL | METER-4511/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 107376082 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363758 | 8202232588 |  | 8202223057#Penggantian Bearing Motor 140 | RU2-HOC | 140-PM-4B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102361259 | 8202237530 |  | 8202223056#TGH5_24 Monitoring Peralatan | RU4-UTL | 50FT202/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102361258 | 8202237529 |  | 8202223052#TGH2_24 Monitoring Peralatan |  | 011FT701/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361085 | 8202236407 |  | 8202223050#D25_Control valve module FTA | RU4-LOC2 | 021F102/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361083 | 8202236404 |  | 8202223049#D25_Control valve module FTA | RU4-LOC2 | 021F102/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102359022 | 8202235080 |  | 8202223047#Penggantian V belt fin-fan Ea | RU5-E15112 | EA-32-01L/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-11-03 | 2025-11-03 | 2102359023 | 8202235077 |  | 8202223046#Penggantian Vbelt fin-fan EA- | RU5-E15112 | EF-32-01G/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1455380 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-03-04 | 2026-03-04 | 2102359754 | 8202235073 |  | 8202223042#Perbaikan Fin-fan EA-32-01P | RU5-E15112 | EA-32-01P/00 | 60 | TECO CNF CSER MSPT PRC SETC | 5MR | D15/26/B6/RT-C2H | 1455380 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359025 | 8202235087 |  | 8202223040#MAT.GANTI VALVE REF. MOC NO. | RU5-E15500 | T900-FWL-001/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 458754228 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-09 | 2026-02-02 | 2026-02-02 | 2102352189 | 8202234182 |  | 8202223038#Vibrasi Alarm 900-02P-3A | RU2S-KIL | 900-02P-3A/00 | 60 | REL CSER GMPS MANC PRC SETC | 2RS | D12/26/B6/NRZ-C3H | 668335 | 667710 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365872 | 8202240374 |  | 8202223037#25_PENGGANTIAN 151TT841 | RU4-RFCUTL | 151TT-U151/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365871 | 8202240371 |  | 8202223036#25_PENGGANTIAN 151TT741 | RU4-RFCUTL | 151TT-U151/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365870 | 8202240368 |  | 8202223033#25_PENGGANTIAN 151TT641 | RU4-RFCUTL | 151TT-U151/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365725 | 8202240365 |  | 8202223032#25_[NP] Perbaikan 14K1P1AT | RU4-FOC1 | 14K1P1A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 63624645 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361116 | 8202236563 |  | 8202223030#D_25 Perbaikan UPS 05EE0043 d | RU4-UTL | 05EE0043/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237528 | 8202238636 | 8202223029#TGH10_SIP_UP Rumput All Area | RU4-TRML | 72FMMOV101AM/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 666886000 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362800 | 8202232189 |  | 8202223025#toothbelt 4326 | RU6-HSC | 32-E-103/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 177042857 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361119 | 8202236576 |  | 8202223022#D_25 Perbaikan Push Button St | RU4-RFCC | 101P502C/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361117 | 8202236569 |  | 8202223021#D_25 Perbaikan seal air fan S | RU4-RFCC | 101F503A17/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361118 | 8202236571 |  | 8202223020#D_25 Perbaikan SB no.8 dan 15 | RU4-RFCC | 101F503/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360958 | 8202237037 |  | 8202223019#D_24 Perbaikan sealant body 1 | RU4-RFCC | 101A510B-P2M/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-05 | 2026-04-23 | 2026-02-26 | 2026-02-26 |  | 8202238674 |  | 8202223014#Perbaikan Kabel Motor Pompa | RU2-HSC | 100-PM-1A/00 | 60 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1270000000 | 1200135000 | MA2-LIS |  | ADEMULYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-26 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-23 | 2026-04-22 | 2102358966 | 8202235069 |  | 8202223004#Penggantian PSU DCS STG 2.1 |  |  | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-23 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-17 | 2026-07-30 | 2026-07-30 | 2102359020 | 8202235059 |  | 8202222998#Perbaikan lampu penerangan SS |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 65736600 | 0 | MA3-LIS |  | FAUZANR |  | 2026-02-11 | PT02 |  | 3 | 2026-07-30 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363689 | 8202232437 |  | 8202222996#Perbaikan 910-CT-1B | RU2-UTL | 910-CT-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363666 | 8202232413 |  | 8202222994#Perbaikan 940-PM-1C | RU2-UTL | 940-PM-1C/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-03 | 2102362735 | 8202237778 |  | 8202222988#Penyelesaian Repair & Rewindi | RU6-HSC | 31-P-107B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | WS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102366107 | 8202240362 |  | 8202222986#25_Mtl. Perbaikan Boardesk Un | RU4-SRU | 90V403/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-22 | 2025-10-31 | 2025-10-31 | 2102359759 | 8202235045 |  | 8202222984#Perbaikan Pompa G-3-10C | RU5-E15112 | G-3-10C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 11977003 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-04-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-31 | 2025-12-31 | 2102359755 | 8202235060 |  | 8202222982#Perbaikan Fin-fan EA-31-21I | RU5-E15112 | EF-31-21I/00 | 60 | CLSD CNF NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-08 | 2026-04-27 | 2026-01-02 | 2027-01-21 | 2102363719 | 8202238754 |  | 8202222977#25_Penggantian Trafo 30BD12-E | RU4-FOC2 | 30BD12EE0012B/00 | 50 | CRTD NMAT PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 100000 | 0 | MA3-LIS |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359107 | 8202235071 |  | 8202222973#Penggantian hub coupling HM-4 | RU5-E15112 | 41-AC-CENTRPPK/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 6690000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2027-01-15 |  | 8202236843 | 8202233979 | 8202222972#PM 5 - LTSA FGDS General Moni | RU6-ITP | 42-T-301A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-08 | 2026-10-12 | 2102362891 | 8202233979 |  | 8202222971#LTSA FGDS Merk General Monito | RU6-ITP | 42-T-301A/00 | 50 | CRTD NMAT PRC | 6IR | D16/25/B6/RT-C2H | 2560 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238239 | 8202234623 | 8202222969#Tag 1 KV Perbaikan Isolasi Ar |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-06-10 | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102353320 | 8202234623 |  | 8202222968#Perbaikan Isolasi Area PP dan |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-12-10 |  | 8202236768 | 8202232770 | 8202222966#SPK 15 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-13 | 2102362281 | 8202233435 |  | 8202222965#Penyehatan EWTP Perbaikan 63- | RU6-ITP | 63-M-401/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 16368 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202235039 | 8202234959 | 8202222960#MAT.PERB.JOHNSON COUPLING 20" | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 19204169 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2025-12-01 | 2025-12-01 | 2102359804 | 8202235028 |  | 8202222953#Perbaikan Motor Gm-17-03B | RU5-E15112 | GM-17-03A/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 348672 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-19 | 2025-12-01 | 2025-12-01 | 2102359758 | 8202235031 |  | 8202222952#Perbaikan Motor Em-8-10A | RU5-E15112 | EM-8-10A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 614846 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 005
| K601 | 2026-02-02 | 2026-06-15 | 2025-12-05 | 2026-09-11 | 2102362597 | 8202233846 |  | 8202222949#Penagihan PM Rotating Equipme | RU6-RCC | 16-P-101A/00 | 01 | CLSD NCMP NMAT PRC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-01-12 |  | 8202237776 |  | 8202222944#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-01-12 |  | 8202237774 |  | 8202222942#LTSA PMPdM Electr-Instr MA3 T | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353228 | 8202234595 |  | 8202222936#MUNICATION INTERFACE,MDL.3211 | RU3-CDGP | CDU234-ESD-SYS/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365493 | 8202240359 |  | 8202222935#25_UP Activity Pekerjaan Pipi |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 107301780 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102366031 | 8202241370 |  | 8202222932#25_[CR] Perbaikan Pompa 021P- | RU4-LOC2 | 021P107B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 174887000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365960 | 8202240326 |  | 8202222926#25_PENGGANTIAN TRANSMITTER 15 | RU4-RFCC | 154LT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365953 | 8202240323 |  | 8202222925#25_PENGGANTIAN TRANSMITTER 15 | RU4-RFCUTL | 153TT002/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363785 | 8202232687 |  | 8202222922#Unloader Cyl 1 Abnormal 300-C | RU2-HSC | 300-C-2B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363784 | 8202232686 |  | 8202222921#Unloader Cyl 1 dan 2 Abnorma | RU2-HSC | 300-C-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-12 | 2026-01-06 | 2102359104 | 8202235042 |  | 8202222919#Ganti BF Valve 20" DAF Utara/ | RU5-D&W | D-34-04A/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 254614007 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238234 | 8202235233 | 8202222917#Tag 6 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360072 | 8202235035 |  | 8202222907#Perbaikan Bocoran E-8-19B | RU5-E15112 | E-8-19B/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-08NH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102359253 | 8202235037 |  | 8202222905#Perbaikan Backwash Tank Polis | RU5-UTL | D5-BV-4-2/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 57164005 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-11-30 | 2102361257 | 8202237527 |  | 8202222901#TGH4_24 UP Clean HE utl | RU4-UTL | 51E3/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-12-17 | 2102365826 | 8202240320 |  | 8202222897#25_Mtl. Check Valve 011P501B | LOC1-UP4 | 011P501B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363752 | 8202232568 |  | 8202222895#Penggantian Coupling Mengguna | RU2-HSC | 100-P-1A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362644 | 8202233564 |  | 8202222894#Penggantian peephole All Boil | RU6-UTL | 052-B-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 11880 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-04-27 | 2102362646 | 8202233565 |  | 8202222893#Penggantian peephole All Boil | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 1152 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-31 | 2025-12-31 | 2102359259 | 8202234965 |  | 8202222890#Perbaikan K-3-02C | RU5-E15112 | K-3-02C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 758482356 | 0 | MA3-ROT |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2025-12-31 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352145 | 8202234180 |  | 8202222888#Pemeriksaan Heater FO Pump 10 | RU2S-KIL | 101-P-9A-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C1H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-02-03 | 2026-04-30 | 2102359106 | 8202234991 |  | 8202222884#Pengadaan Lampu structure bar |  |  | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 57375000 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-09-14 | 2026-10-13 | 2102359672 | 8202234993 |  | 8202222882#Modifikasi line FT Spraywater | RU5-UTL | HHP-6/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 752996 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-09-14 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-12 | 2026-02-02 | 2026-11-25 | 2102362544 | 8202233111 |  | 8202222881#Perbaikan Mech Seal 11-P-102 | RU6-HSC | 11-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 355351216 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-01 | 2025-12-01 | 2102359757 | 8202234969 |  | 8202222880#Perbaikan Em-17-03B | RU5-E15112 | EM-17-03B/00 | 60 | TECO CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2102359252 | 8202234971 |  | 8202222879#Penggantian sight glass pompa | RU5-E15112 | G-3-11B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102359366 | 8202234974 |  | 8202222878#Penggantian Journal Bearing D | RU5-E15112 | G-3-01C/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 | 2102359171 | 8202234959 |  | 8202222877#MAT. JOHNSON COUPLING 20" TAN | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 124766000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102362514 | 8202233737 |  | 8202222873#pengantian relay MBX 22-K-101 | RU6-DHC | 22-K-101B-LP/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102362640 | 8202232898 |  | 8202222872#Perbaikan relay MBX 22-K-101A | RU6-DHC | 22-K-101A-LP/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-05-07 | 2026-02-02 | 2026-02-03 | 2102358673 | 8202234375 |  | 8202222871#Pekerjaan Perbaikan Pompa Mix | RU7-OFF | 5-AM-25/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-5-D1H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-03-08 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362264 | 8202233964 |  | 8202222864#Make Up Rock Salt 14-V-108 | RU6-DHC | 14-V-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 369717 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-01-05 |  | 8202237771 |  | 8202222862#Per.Gen. Steam Turbin 11-P-10 | RU6-HSC | 11-P-109A-T/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353322 | 8202234495 |  | 8202222861#N_Perbaikan Pompa P-7 CDU II | RU3-CDGP | CD2-P-007/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-12-11 |  | 8202236770 | 8202232770 | 8202222857#SPK 14 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-12-11 |  | 8202236772 | 8202232770 | 8202222856#SPK 13 LTSA Transformator RU | RU6-UTL | SS-01/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365450 | 8202240317 |  | 8202222854#25_PENGGANTIAN LIMIT SWITCH 1 | RU4-RFCUTL | 152UZV632/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 5000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-04 | 2102359176 | 8202234937 |  | 8202222852#Perbaikan Back Wash Filter V- | RU5-E15112 | 03-FT-1385/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 63000000 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365395 | 8202240314 |  | 8202222850#25_PENGGANTIAN LIMIT SWITCH 1 | RU4-RFCUTL | 151UV669/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 8000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365429 | 8202240311 |  | 8202222849#25_PENGGANTIAN SOLENOID 151UV | RU4-RFCUTL | 151UV668A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 24500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-04 | 2102359175 | 8202234938 |  | 8202222848#Perbaikan Back wash Filter V- | RU5-E15112 | V-3-02A/01 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 57000000 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365394 | 8202240308 |  | 8202222847#25_PENGGANTIAN LIMIT SWITCH 1 | RU4-RFCUTL | 151UV667/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 8000000 | 8000000 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361017 | 8202235391 |  | 8202222841#Perbaikan thermocouple 101TI0 | RU4-RFCC | 101TT-U101/00 | 50 WENG | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361018 | 8202235402 |  | 8202222839#Perbaikan TG casing 101P523A | RU4-RFCC | 101P523A/00 | 50 WENG | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366078 | 8202240304 |  | 8202222838#25_Pompa 21P-7A vibrasi | RU4-LOC1 | 21P7A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 65880000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-10-13 | 2102362086 | 8202232745 |  | 8202222828#Repair servo 34-P-101 B | RU6-POC | 34-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365428 | 8202240300 |  | 8202222826#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365427 | 8202240296 |  | 8202222825#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365426 | 8202240292 |  | 8202222823#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365425 | 8202240289 |  | 8202222822#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365424 | 8202240286 |  | 8202222821#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365963 | 8202240283 |  | 8202222820#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365423 | 8202240279 |  | 8202222819#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365422 | 8202240275 |  | 8202222818#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365421 | 8202240271 |  | 8202222817#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365420 | 8202240267 |  | 8202222816#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365399 | 8202240263 |  | 8202222815#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365398 | 8202240259 |  | 8202222814#25_Penggantian PROXIMITY SWIT | RU4-RFCUTL | 152ZE-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365397 | 8202240256 |  | 8202222813#25_PENGGANTIAN LIMIT SWITCH 1 | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 5000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-09 | 2026-11-02 | 2026-12-30 | 2102359465 | 8202234955 |  | 8202222812#Penggatian lampu indikator MO |  |  | 60 | REL CSER GMPS MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 22897500 | 22897500 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 | 8 | 3 | 2026-11-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365396 | 8202240252 |  | 8202222811#25_PENGGANTIAN LIMIT SWITCH 1 | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 5000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365869 | 8202240249 |  | 8202222810#25_PENGGANTIAN TRANSMITTER 15 | RU4-RFCUTL | 151TT-U151/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365728 | 8202240246 |  | 8202222809#25_[PV] Perbaikan 14P607A | RU4-FOC1 | 14P607A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 30875000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-08-28 |  | 8202238641 |  | 8202222808#TGH6_22 TSA FGDS Gastron RFCC | RU4-RFCC | 102TG005/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-02-05 |  | 8202238643 |  | 8202222807#TGH3_24 TSA AC Central PLC | RU4-KPC | 80BD21AHU1CRA/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-12-29 | 2026-12-31 | 2102359462 | 8202234934 |  | 8202222806#Perbaikan/Penggantian Limit S | RU5-D&W | SBM-201-01A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 4 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-12-29 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102361256 | 8202237526 |  | 8202222805#TGH1_SIP_UP Pagar 2024 | RU4-TRML | 70SS1/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102361255 | 8202237525 |  | 8202222803#TGH8_Building Management Serv | RU4-K3LL | FT34/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-15-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-22 | 2025-12-29 | 2025-12-29 | 2102359170 | 8202234936 |  | 8202222801#Perbaikan Elmot P-6 WTP-I | RU5-UTL | P-6PAMPANCUR/00 | 60 | CLSD CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | WS-LIS |  | SAPBATCH | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-04-23 | PM |  | 005
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-18 | 2026-06-30 | 2102359174 | 8202234940 |  | 8202222800#Perbaikan Back Wash Filter V- | RU5-E15112 | 03-FCV-020/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 3906081554 | 0 | MA3-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-10-29 | 2026-11-27 | 2102359173 | 8202234962 |  | 8202222795#Ganti Valve Suction Pompa Deg | RU5-UTL | 1UA-03-D002/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 82244022 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-29 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102362593 | 8202233175 |  | 8202222793#Perbaikan filter DGS 32-K-101 | RU6-HSC | 32-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-14 | 2025-12-09 | 2025-12-09 |  | 8202238230 |  | 8202222792#Permintaan Kelanjutan Kontrak | RU2-HCC | 0-75P21350A2A2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 602000000 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-01-23 | 2026-07-31 | 2102362259 | 8202233471 |  | 8202222790#Penggantian transmitter 052-F | RU6-UTL | 052-FT-901C/00 | 60 | REL NMAT PRC SETC | 6IR | D16/26/B6/RT-C2H | 15939 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-23 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102361616 | 8202233504 |  | 8202222789#Penggantian Servo 34-P-101A | RU6-POC | 34-P-101A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102361678 | 8202233794 |  | 8202222788#Pengadaan material baru 19-KV | RU6-RCC | 19-KV-018/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360538 | 8202235771 |  | 8202222787#Perbaikan motor 92E-409A | RU4-SRU | 92E409AM/00 | 50 WAMA | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365902 | 8202240242 |  | 8202222785#25_penggantan o-iring 14K602B | RU4-FOC1 | 14K602B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102365682 | 8202240239 |  | 8202222783#25_penggantian gasket 13K1B | RU4-FOC1 | 13K1B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 689594 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-01 | 2025-12-01 | 2102359676 | 8202234932 |  | 8202222780#Perbaikan Gm-3-11A | RU5-E15112 |  | 60 | TECO CNF NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362309 | 8202233285 |  | 8202222776#Perbaikan 33-FV-012 | RU6-HSC | 33-FV-012/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-20 | 2025-12-24 | 2025-12-24 | 2102359172 | 8202234906 |  | 8202222772#rewinding motor P-18 WTP Panc |  |  | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2015176 | 0 | WS-LIS |  | SAPBATCH | 2026-04-21 | 2026-02-11 | PT02 |  | 3 | 2026-04-21 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 | 2102362518 | 8202233762 |  | 8202222768#Pengadaan Pompa Assy 12-P-512 | RU6-DHC | 12-P-512/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2027-01-05 | 2102365933 | 8202240236 |  | 8202222767#25_[CR] Penggantian Filter WG | RU4-RFCC | 102K501/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 56020000 | 0 | MA6-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-12 | 2102362605 | 8202233043 |  | 8202222765#Perbaikan Motor 20E104A | RU6-RCC | 20-E-104A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 |  | 8202232770 |  | 8202222760#PM Trafo RU VI Tahun 2025 | RU6-UTL | SS-01/00 | 01 | CRTD NMAT PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-01 | 2025-12-01 | 2102359805 | 8202234882 |  | 8202222755#Perbaikan Motor Gm-8-03A | RU5-E15112 | GM-8-03A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 337634 | 0 | MA3-LIS |  | SAPBATCH | 2026-06-09 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360963 | 8202236251 |  | 8202222753#Fan Motor 140P610A Rontok | RU4-GTO | 140P610A/00 | 50 WAMA | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA7-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360962 | 8202236243 |  | 8202222750#Perbaikan alarm status breake | RU4-UTL | 051G103/00 | 50 WAMA | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA5-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-01 | 2102362400 | 8202237769 |  | 8202222749#LTSA change out adsorbent Dry | RU6-UTL | 58-D-101C/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352654 | 8202234687 |  | 8202222748#Material Plug Brass | RU3-CDGP | 24-T-1251/00 | 60 | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-12-07 | 2102362469 | 8202238238 |  | 8202222747#Perbaikan Panel Box Vibrasi 0 | RU6-UTL | 056-K-101-A1-M/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-08-07 | 2102362511 | 8202233342 |  | 8202222746#Perbaikan 15-V-101B | RU6-RCC | 15-V-101B/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361042 | 8202235920 |  | 8202222737#Perbaikan lampu substandar di |  | 11P4AM-108P/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361044 | 8202235963 |  | 8202222736#Perbaikan kabel intertriping | UTL-UP4 | 10EE0310AB/00 | 01 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361123 | 8202236595 |  | 8202222735#D_25 Penggantian modul Rectif | RU4-UTL | 05EE0043/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361130 | 8202236716 |  | 8202222734#D_25 048K101CM power supply r | RU4-TRML | 048K101CM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-03 | 2026-05-11 | 2026-01-02 | 2026-01-02 | 2102361254 | 8202237524 |  | 8202222731#RKAP25_Ganti VCB 63EE1111A/B | RU4-UTL | 63EE1111A/00 | 50 | REL GMPS NMAT PRC SETC | 4ER | D14/26/B6/NR-5-C2H | 3565000000 | 3030250000 | MA5-LIS |  | FARIZSETYANA |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365724 | 8202240233 |  | 8202222730#25_Kebocoran Cover Flange Dry | RU4-GTO | 140D601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 42555000 | 0 | MA7-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365720 | 8202240230 |  | 8202222728#25_[CR] Perbaikan M/S Pompa 1 | RU4-RFCC | 101P502C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 134463000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-18 | 2026-01-02 | 2026-01-02 | 2102366066 | 8202240227 |  | 8202222725#25_[RP] Pompa 101A519P2 | RU4-RFCC | 101A519P2/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 220400000 | 220400000 | MA6-ROT |  | LUQMANULH | 2026-01-02 | 2026-03-10 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-01-02 | 2102366070 | 8202240224 |  | 8202222724#25_[RP] Pompa 101A519P1 | RU4-RFCC | 101A519P1/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 220400000 | 220400000 | MA6-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-29 | 2102362402 | 8202237767 |  | 8202222721#LTSA Scaffolding 2024-2026 Ta | RU6-UTL | 52-B-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-06-29 | 2102362513 | 8202234072 |  | 8202222720#22-E-102 | RU6-DHC | 22-E-102/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366014 | 8202240222 |  | 8202222712#25_Penggantian assy 510LV002 | RU4-UTL | 510G301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365638 | 8202240220 |  | 8202222711#25_PENGGANTIAN TRANSMITTER 15 | RU4-RFCUTL | 154AT002/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365637 | 8202240217 |  | 8202222710#25_PENGGANTIAN TRANSMITTER 1 | RU4-RFCUTL | 154AT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365636 | 8202240214 |  | 8202222709#25_PENGGANTIAN 152AT005 | RU4-RFCUTL | 152AT005/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365635 | 8202240212 |  | 8202222708#25_PENGGANTIAN 152AT001 | RU4-RFCUTL | 152AT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365942 | 8202240209 |  | 8202222706#25_PENGGANTIAN TRANSMITTER 63 | RU4-RFCC | 63-PA0001-2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 3 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365645 | 8202240205 |  | 8202222703#25_PENGGANTIAN TRANSMITTER 15 | RU4-RFCUTL | 154T502B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365634 | 8202240203 |  | 8202222701#25_PENGGANTIAN TRANSMITTER 15 | RU4-RFCUTL | 152TT-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-04-20 | 2026-01-14 | 2026-11-13 | 2102362651 | 8202232762 |  | 8202222700#Pngadan Mterial Fire Water Li | RU6-UTL | 66-FW-8102-MS20/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 724377264 | 666611000 | MA4-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 004
| K501 | 2026-02-02 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2102359308 | 8202234867 |  | 8202222696#Perbaikan pompa G-34-111A (Be | RU5-D&W | G-34-111A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 2028241 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365904 | 8202240200 |  | 8202222695#25_perbaikan 12FT-801 | RU4-FOC1 | 12FT702/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-10-30 | 2102365707 | 8202240197 |  | 8202222694#25_Fabrikasi Test Ring 590A30 | RU4-UTL | 560K301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365903 | 8202240193 |  | 8202222693#25_perbaikan 12FT-802 | RU4-FOC1 | 12FV702/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102361253 | 8202237522 |  | 8202222683#Pemindahan Kontainer Ex Proje | RU4-RFCC | 101A540/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 4500000000 | 0 | MA6-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-23 | 2102359420 | 8202234869 |  | 8202222680#Perbaikan Control Valve 08B-F | RU5-E15112 | 08B-FCV-284/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 336797000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102359427 | 8202234871 |  | 8202222679#Perbaikan Control Valve 05-FC | RU5-E15111 | 05-FCV-379/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 232794000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102359425 | 8202234874 |  | 8202222678#Perbaikan Control Valve 04-PC | RU5-E15111 | 04-PCV-058A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 232794000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-26 | 2026-06-05 | 2102359752 | 8202234879 |  | 8202222677#Peng. Probe Housing Vibration |  | 05-TSHH-682A/00 | 50 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 15001536 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-09-24 |  | 8202237765 | 8202233881 | 8202222675#LTSA PMPdM Electr-Instr MA4 T | RU6-UTL | 56-K-101A-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-09-24 |  | 8202236601 | 8202233881 | 8202222672#Tagihan TKDN Tahap 10PMPdM El | RU6-UTL | 56-K-101A-M/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | ZAMZAMKHALID |  | 2026-02-07 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-24 |  | 8202236603 | 8202233881 | 8202222668#Tagihan TKDN Tahap 1 PMPdM El | RU6-UTL | 56-K-101A-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-21 | 2026-02-02 | 2026-08-10 | 2102362119 | 8202233631 |  | 8202222666#Penggantian gate valve 34-A-1 | RU6-POC | 34-A-101-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | ARYATHONI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2025-11-03 | 2025-11-03 | 2102359905 | 8202234865 |  | 8202222662#G-3-02C O-Ring rusak | RU5-E15112 | GM-3-02C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 51597963 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-04-23 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102361860 | 8202233263 |  | 8202222661#Perbaikan 51-G-101D | RU6-UTL | 51-G-101D-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-11 | 2026-06-15 | 2102360335 | 8202234860 |  | 8202222659#material tamb perbaikan MOV c | RU5-UTL | PP-2-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 84217500 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365709 | 8202240189 |  | 8202222655#25_[CR] Perbaikan M/S Pompa 1 | RU4-RFCC | 101P501C/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 136665000 | 74202000 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365965 | 8202240185 |  | 8202222650#25_Kerusakan Level & Oiler Gl | RU4-GTO | 48P601B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 72500000 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 | 2102359256 | 8202234827 |  | 8202222643#Vibrasi Pada Pompa G-4-02 | RU5-E15111 | G-4-02/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2102359303 | 8202234858 |  | 8202222642#Penggantian Coolant Radiator | RU5-UTL | D-EMERG-2-PPII/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 6350000 | 0 | MA1-ROT |  | ABASMAHROJI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238237 | 8202235068 | 8202222637#Tagihan Ke- 3 Pekerjaan Isola |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-25 | 2102362404 | 8202233517 |  | 8202222631#penggantian relay MBX 22-K-10 | RU6-DHC | 22-K-101C/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-31 | 2025-12-31 | 2102359423 | 8202234813 |  | 8202222630#Pompa P6 WTP 1 cekat | RU5-UTL | P-6PAMPANCUR/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 2032264 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-02 | 2026-02-02 | 2026-12-31 |  | 8202232720 | 8202236854 | 8202222629#SWO Tube Bundle 50-E-101 (DC) | RU6-UTL | 50-E-101/00 | 50 | REL MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 29040 | 0 | MA4-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-01 | 2026-02-01 | 2102362351 | 8202232911 |  | 8202222628#Perbaikan Press Switch area 2 | RU6-DHC | 22-K-101C/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-20 |  | 8202233970 | 8202233881 | 8202222625#LTSA PMPdM Electr-Instr MA4 T | RU6-UTL | 56-K-101A-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 16764 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-20 | 2026-02-02 | 2026-02-02 | 2102352191 | 8202234179 |  | 8202222624#Verifikasi Ulang Meter Prover | RU2S-KIL | 946-MOV-1900H/00 | 60 | REL NMAT PRC SETC | 2ES | D12/25/B6/NRZ-C3H | 125000000 | 0 | MAS-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-04 | 2026-06-10 | 2026-06-10 | 2027-03-09 |  | 8202238539 | 8202236720 | 8202222620#NRK_Penggantian sistem HVAC R | RU5-E15112 | 41-AC-CENTRPPK/00 | 50 | CRTD NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 20000000 | 0 | WS-LIS |  | HIMMATUSS |  |  | PT02 |  | 2 | 2026-06-10 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102362201 | 8202233777 |  | 8202222619#Pengadaan microfilter Avtur | RU6-ITP | 42-T-106/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-19 | 2102359257 | 8202234819 |  | 8202222617#Perbaikan GM-34-121 | RU5-D&W | GM-34-121A/00 | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 44550 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102363960 | 8202238538 |  | 8202222616#Sertifikasi Peralatan Migas H | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-06-30 | 2102359363 | 8202234822 |  | 8202222614#Perbaikan CEMS Area HSC | RU5-E15500 | CEMS-SYSTEM-INT/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 161101539 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-26 | 2026-06-05 | 2102359623 | 8202234815 |  | 8202222611#PERBAIKAN SOLENOID VALVE 05-X | RU5-E15111 | 05-XCV-254C/00 | 50 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 81001536 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-26 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238128 | 8202234832 | 8202222608#Tag 15 KV Tambat Kapal Area S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-17 | 2102362313 | 8202233280 |  | 8202222602#Perbaikan 34-PCV-400 | RU6-POC | 34-A-102-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 | 2102362167 | 8202233447 |  | 8202222601#Penggantian valve 34-A-101-P- | RU6-POC | 34-A-101-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2102366025 | 8202241369 |  | 8202222598#25_[CR] Mech seal pompa 21P-1 | RU4-LOC1 | 21P17/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 129402305 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 |  | 8202233949 |  | 8202222597#Material 2 Perbaikan Pompa 51 | RU6-UTL | 51-P-102D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 |  | 8202233950 |  | 8202222595#Material 2 Perbaikan Pompa 51 | RU6-UTL | 51-P-101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362336 | 8202233924 |  | 8202222592#Material Prbaikan Turbin 51-G | RU6-UTL | 51-G-101D-P2A-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102362380 | 8202233925 |  | 8202222591#Material Prbaikan Turbin 51-G | RU6-UTL | 51-G-101D-P1A-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 19800 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362051 | 8202233953 |  | 8202222589#Mat Perbaikan Turbin 51-P-101 | RU6-UTL | 51-P-101D-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-11-04 | 2102359469 | 8202234777 |  | 8202222588#Perbaikan Control Valve 3A-TC | RU5-E15112 | 03A-TCV-186/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 116397000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-11-04 | 2102359620 | 8202234773 |  | 8202222587#Perbaikan Control Valve 3B-FC | RU5-E15112 | 03B-FCV-386/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 116456000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-11-04 | 2102359621 | 8202234769 |  | 8202222586#Perbaikan Control Valve 3B-LC | RU5-E15112 | 03B-LCV-438/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 121456000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-12 | 2026-06-09 | 2102359362 | 8202234809 |  | 8202222584#Penggantian FIlter Oil STG 2. | RU5-UTL | TG-3-PP2/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 28350000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-15 | 2026-03-09 | 2026-03-09 | 2102365985 | 8202241365 |  | 8202222578#25_[CR] Perbaikan 11P14A | RU4-FOC1 | 11P14A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 1170773 | 0 | MA1-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365915 | 8202240178 |  | 8202222576#25_Perbaikan Drawer HVAC 90SS | RU4-LOC1 | 90EE0138A1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361120 | 8202236585 |  | 8202222575#D_25 Perbaikan MOV 93HV-183 ( | RU4-SRU | 93HV183/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361126 | 8202236623 |  | 8202222574#D_25 pemasangan lampu peneran | RU4-TRML | 46P2AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-02-03 | 2026-04-30 | 2102359626 | 8202234807 |  | 8202222573#Penggantian Lampu RPPK dan Pl | RU5-E15112 | 41-R-RPPK-LIS/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 386811000 | 0 | MA3-LIS |  | SAPBATCH | 2026-06-09 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363727 | 8202232524 |  | 8202222572#Penyehatan Gearbox Conveyor 1 | RU2-HOC | 170-ME-103-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 21556877 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363725 | 8202232521 |  | 8202222571#Penyehatan Gearbox Conveyor 1 | RU2-HOC | 170-ME-103-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 21556877 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365917 | 8202240174 |  | 8202222568#25_Bearing motor 23P10A noise | RU4-LOC1 | 23P10AM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 661850 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-23 | 2026-03-05 | 2026-03-05 | 2102365457 | 8202240170 |  | 8202222565#25_Perbaikan Flowmeter Claus | RU4-SRU | 93FE003/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-6-C2H | 256780000 | 256780000 | MA1-INT |  | SAPBATCH | 2026-04-24 | 2026-03-10 | PT02 |  | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365341 | 8202240166 |  | 8202222563#25_Perbaikan Flow Transmitter | RU4-SRU | 93E403/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365316 | 8202240162 |  | 8202222561#25_Penggantian Selenoid 32UV0 | RU4-TRML | 32UV013B/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 23880000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365315 | 8202240158 |  | 8202222560#25_Penggantian Selenoid 32UV0 | RU4-TRML | 32UV013A/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 47760000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366024 | 8202240154 |  | 8202222559#25_90P-401B, Perbaikan motor | RU4-SRU | 90P401BM/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-6-C2H | 266365 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365317 | 8202240150 |  | 8202222558#25_Perbaikan 14FT-218 | RU4-FOC1 | 14FT218/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2025-12-29 | 2025-12-29 | 2102359464 | 8202234806 |  | 8202222557#Penggantian socket 1 phasa La |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 156545000 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365319 | 8202240146 |  | 8202222556#25_Replacement 65PT201 | RU4-UTL | 50FE201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 13771686 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-01 | 2025-12-01 | 2102359368 | 8202234810 |  | 8202222555#Motor pompa listrik no.7 WTP | RU5-UTL | P-7-WTP/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2514917 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-01 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365456 | 8202240142 |  | 8202222554#25_Replacement 65LT201 | RU4-UTL | 50FE201/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 24148273 | 19250000 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102366028 | 8202240139 |  | 8202222553#25_Motor 23P9 noise | RU4-LOC1 | 23P9M/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 676550 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365318 | 8202240137 |  | 8202222552#25_Replacement 65PT202 | RU4-UTL | 50FE201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 13771686 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-01 | 2025-12-01 | 2102359369 | 8202234744 |  | 8202222550#Perbaikan Motor P8 WTP 1 | RU5-UTL | P-8-WTP/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 842609 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-01 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-22 | 2025-12-31 | 2025-12-31 |  | 8202234811 |  | 8202222549#Fabrikasi Liner Cyl.6 K-3-02A | RU5-E15112 | K-3-02C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-04-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359904 | 8202234741 |  | 8202222546#Perbaikan Pompa G-3-02D | RU5-E15112 | G-3-02D/01 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 54130642 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-12-10 | 2102361252 | 8202237521 |  | 8202222545#TGH2_24 UP Scaffold Rejuve Is | RU4-RFCGTO | 105K501P1/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K701 | 2026-02-02 | 2026-05-07 | 2026-02-02 | 2026-02-03 | 2102358172 | 8202234361 |  | 8202222541#PERBAIKAN 5-PM-25B/00 | RU7-OFF | 5-PM-25B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-5-D4H | 0 | 0 | MA-LINT |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-03-08 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2025-11-10 | 2025-12-19 | 2102358161 | 8202234360 |  | 8202222540#Perbaikan 2-K-01/02 | RU7-NHT | 2-K-01-02/00 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D4H | 1152 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238233 | 8202235215 | 8202222537#Tag 6 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365738 | 8202240134 |  | 8202222536#25_Penggantian oil gun 52B-20 | RU4-UTL | 52B201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-06-30 | 2102359365 | 8202234738 |  | 8202222535#Perbaikan/Penggantian PI Disc | RU5-D&W | G-202-02B/00 | 50 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 23550595 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-31 | 2025-12-31 | 2102363629 | 8202232320 |  | 8202222531#Recovery Temporary & Permanen | RU2-ITP | 1-5P99001A1A2/00 | 50 | REL MACM PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361121 | 8202236587 |  | 8202222530#D_25 Perbaikan Motor 47M408A | LOC1-UP4 | 47M508A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361124 | 8202236597 |  | 8202222527#D_25 Penggantian fuse 14E652 | RU4-FOC1 | 14E652/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361122 | 8202236591 |  | 8202222526#D_25 perbaikan bearing 11E52D | RU4-FOC1 | 11E52DM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361145 | 8202236932 |  | 8202222524#D_25 011K-101B, Motor rusak | RU4-FOC2 | 011K101BM/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-10 | 2026-02-04 | 2026-02-04 | 2102352651 | 8202238145 |  | 8202222523#R_Transformer Separation Wall |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-LIS |  | HARISASEPWIJ |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102363799 | 8202238050 |  | 8202222521#Perbaikan electrical system J | RU2-ITP | 990-FQI-1107/00 | 50 | CRTD NMAT PRC | 2MR | D12/22/B6/RT-D2H | 1 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-12-02 | 2102362267 | 8202233853 |  | 8202222519#Pemb. LTSA Slide Valve Unit R | RU6-RCC | 15-SLV-105/00 | 01 | CLSD CSER NCMP NMAT PRC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2025-11-24 | 2025-11-24 | 2102363794 | 8202238014 |  | 8202222518#Perbaikan motor compressor | RU2-HCC | 410-CM-1B/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 005
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-08-10 | 2102362161 | 8202233881 |  | 8202222517#Pekerjaan LTSA PM PDM UTL 202 | RU6-UTL | 56-K-101A-M/00 | 01 | CRTD NMAT PRC | 6ER | D16/25/B6/RT-C2H | 15840 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-03-04 | 2026-03-11 | 2102359854 | 8202234736 |  | 8202222515#MAT. PERB. PIPE DEEP WELL 101 | RU5-TBL | PIPE-ON-SHORE/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 60594090 | 0 | MA4-STA |  | SAPBATCH | 2026-03-13 | 2026-02-11 | PT02 |  | 3 | 2026-03-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-19 | 2102360483 | 8202234733 |  | 8202222512#Perbaikan GM-34-121A | RU5-D&W | GM-34-121A/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352656 | 8202234546 |  | 8202222506#N_Penggantian peripheral spar | RU3-UTL | UTL-DCS/00 | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-13 | 2102362262 | 8202233825 |  | 8202222505#Pengadaan consumable matrial | RU6-UTL | 55-XV-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 13200 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-10-22 | 2102365664 | 8202240132 |  | 8202222501#25_Kerusakan finfan 240E125 A | RU4-LOC3 | 240E125K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-10-22 | 2102365665 | 8202240129 |  | 8202222499#25_Kerusakan finfan 260E172 M | RU4-LOC3 | 260E172B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359969 | 8202234734 |  | 8202222498#Pengadaan Control Valve 01-PC | RU5-E15111 | 01-PCV-211A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 116397000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352800 | 8202235000 |  | 8202222497#Pemasangan Fluq Drain Dermaga |  |  | 60 | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363741 | 8202232550 |  | 8202222493#Penggantian line naptha 6" ja | RU2-ITP | DPN-PIPING/00 | 01 | CRTD CSER MACM PRC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358164 | 8202234359 |  | 8202222490#PERBAIKAN 1-EA-01A | RU7-CDU | 1-EAM-01A/00 | 60 WASR | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/NR-1-D2H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-01 | 2026-01-02 | 2102359809 | 8202234730 |  | 8202222488#Perbaikan Motor Em-31-21F | RU5-E15112 | EM-31-21G/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 384 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102361900 | 8202232877 |  | 8202222487#Perbaikan Solenoid Valve 22-A | RU6-DHC | 22-A-105/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102362020 | 8202232876 |  | 8202222485#Perbaikan Solenoid Valve 22-V | RU6-DHC | 22-V-109B/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2025-11-19 | 2025-11-19 | 2102363546 | 8202232199 |  | 8202222481#Pengadaan Material Instrument | RU2-HOC | 140-FV-463/00 | 50 | CRTD NMAT PRC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2025-11-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-21 | 2025-12-15 | 2025-12-17 | 2102359756 | 8202234732 |  | 8202222480#Perbaikan Motor EM-1-25D | RU5-E15111 | EM-1-25D/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 567333 | 0 | MA2-LIS |  | SAPBATCH | 2026-05-21 | 2026-02-11 | PT02 |  | 3 | 2026-05-21 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-11 |  | 8202237763 |  | 8202222475#Per.Gen.Steam.Turbin 13-K-101 | RU6-DHC | 13-K-101-P2A-T/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365723 | 8202240126 |  | 8202222471#25_Bearing Finfan 120E602B-B | RU4-GTO | 120E602B-B/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 10935798 | 0 | MA7-ROT |  | FARIZSETYANA | 2026-05-21 | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365722 | 8202240123 |  | 8202222470#25_Bearing Finfan 120E605B Ru | RU4-GTO | 120E605B/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 10935798 | 0 | MA7-ROT |  | FARIZSETYANA | 2026-05-21 | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365729 | 8202240120 |  | 8202222469#25_[CR] Penggantian LO Filter | RU4-FOC1 | 11K401A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 18400500 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352711 | 8202234512 |  | 8202222468#N_Penggantian Valve XV004/05 | RU3-CDGP | CD2-82-XV-004/00 | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-14 | 2026-01-14 | 2102362755 | 8202233205 |  | 8202222453#Perbaikan check valve 14-P-10 | RU6-DHC | 14-P-101B/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-14 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-05-03 | 2102360394 | 8202234714 |  | 8202222452#Pengadaan Bola Prover Meterin | RU5-TBL | PROVER-1201/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 541563564 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363625 | 8202232245 |  | 8202222448#Perbaikan Motor 100-P-7 | RU2-HSC | 100-PM-7/00 | 60 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 4970000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361251 | 8202237519 |  | 8202222447#TGH2_24 Cleaning Bagian Dalam | RU4-TRML | 71T6/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-09 | 2026-05-21 | 2026-03-09 | 2027-01-05 | 2102363975 | 8202241368 |  | 8202222436#25_[PdM] 011P106B High Vibrat | RU4-FOC2 | 011P106B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 206359000 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-11-10 | 2025-12-30 | 2102360609 | 8202234697 |  | 8202222432#Perb. Shell Tank O-23 NBF ST | RU5-TBL | O-23/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-FINH | 448 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-10 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-11-28 | 2025-12-30 | 2102360396 | 8202234698 |  | 8202222431#Perb. Seal Filter Avtur di OM | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 269 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359964 | 8202234721 |  | 8202222430#MAT.PERB.LINE 21P-868-6"RFO P | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 102188902 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360480 | 8202234692 |  | 8202222429#PERB.LINE 21-P34-16" NAPTHA T | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 140011115 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360399 | 8202234705 |  | 8202222427#Perb. BV 12" Disch GM20-17B H | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-FJNH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360107 | 8202234696 |  | 8202222426#PERB.LINE 21-951-24"-B20 ISAP | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 573448227 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360106 | 8202234693 |  | 8202222425#PERB.LINE 21-P33-12" DEPAN TA | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 25943369 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-05 | 2025-12-03 | 2102360715 | 8202234686 |  | 8202222424#Perbaikan Baseplate Pompa G-3 | RU5-E15111 | G-34-63/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 17455679 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-19 | 2102360714 | 8202234688 |  | 8202222423#Perbaikan Baseplate Pompa G-3 | RU5-D&W | G-34-53/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 12244694 | 0 | MA2-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-05 | 2025-12-03 | 2102360713 | 8202234689 |  | 8202222422#Perbaikan Baseplate Pompa G-3 | RU5-D&W | G-34-52/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 5210985 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360336 | 8202234685 |  | 8202222421#Perbaikan Bocoran Line to 01- | RU5-E15111 | 01-PSV-562D/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-01NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-08 | 2025-12-30 | 2102359670 | 8202234715 |  | 8202222420#Material perbaikan line 6" is | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-FJNH | 192 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-27 | 2026-08-03 | 2102359625 | 8202234659 |  | 8202222418#Perbaikan Meter 1211 Area OM | RU5-TBL | 22-DPIT-505A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 580670150 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-27 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102359965 | 8202234691 |  | 8202222417#PERB.LINE 21-P754-10" CRUDE J | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 186115135 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360607 | 8202234675 |  | 8202222416#Perbaikan Dinding Hot Spot F- | RU5-E15112 | F-8-01B/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-08NH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-01-21 | 2026-02-05 | 2102360527 | 8202234690 |  | 8202222414#PERB.LINE CLOSE DRAIN SYSTM D | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 32987427 | 0 | MA4-STA |  | SAPBATCH | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-11-28 | 2025-12-30 | 2102360526 | 8202234701 |  | 8202222413#Perb. L866 pd hairpin dp RPPK | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 269 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 | 2102360606 | 8202234676 |  | 8202222412#Perbaikan Dinding Hot Spot F- | RU5-E15112 | F-8-01A/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 | 2102360672 | 8202234718 |  | 8202222411#Material Gasket Burner F-8-01 | RU5-E15112 | F-8-01A/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360522 | 8202234678 |  | 8202222409#Perbaikan dan Cleaning E-2-16 | RU5-E15112 | E-2-16B/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-02NH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360521 | 8202234680 |  | 8202222408#Perbaikan dan Cleaning E-2-16 | RU5-E15112 | E-2-16A/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-01NH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-11 | 2026-12-10 | 2102360710 | 8202234655 |  | 8202222407#Perbaikan Valve THOP STG 2.1 | RU5-UTL | TG-1-PP2/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-11 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360032 | 8202234663 |  | 8202222406#Perbaikan lantai area FDF & I | RU5-D&W | K-201-03/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-D5NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-11-28 | 2025-12-30 | 2102360643 | 8202234660 |  | 8202222402#Perbaikan line drain jalur pa | RU5-TBL | PIPE-ON-SHORE/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-FLNH | 269 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102359966 | 8202234711 |  | 8202222400#Penggantian line tanki HCL ba | RU5-UTL | 0UA-41-D002/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 | 2102360640 | 8202234673 |  | 8202222399#Perbaikan Hydrant Area Gn. Du | RU5-E15500 | KUP-FWL-601/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | GM-SIP |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-25 | 2102360486 | 8202234722 |  | 8202222397#Mat. Perbaikan Saluran Blowdo | RU5-UTL | HHP-6/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-S3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-05-25 | 2102360644 | 8202234726 |  | 8202222396#Ganti Valve Outlet Tangki W 2 | RU5-UTL | OFC03203/00 | 50 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-26 | 2026-02-03 | 2026-08-10 | 2102360649 | 8202234682 |  | 8202222395#Perbaikan Cover Air Cooler ST | RU5-UTL | TG-1-PP2/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 42541061 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-14 | 2026-02-10 | 2026-02-10 | 2102359900 | 8202234708 |  | 8202222394#Penggantian Pompa Dosing HCL | RU5-UTL | 0UA-41-D004/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360156 | 8202234724 |  | 8202222393#LT-408 (plant 3A) : B/V impul | RU5-E15112 | 03A-FT-406/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-03NH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-15 | 2025-12-30 | 2102359807 | 8202234684 |  | 8202222390#Perbaikan breather valve tang | RU5-TBL | A-1/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-FCNH | 128 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-12-15 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363633 | 8202232349 |  | 8202222389#Perbaikan Fan 905-DEG | RU2-UTL | 905-DEG-E01/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-01 | 2026-12-31 | 2026-12-31 | 2102360395 | 8202234666 |  | 8202222388#Perbaikan kompresor K-1-01A | RU5-E15111 | K-1-01A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-04-02 | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102359627 | 8202234643 |  | 8202222385#penggantian sight glass G-8-0 | RU5-E15112 | G-8-03C/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 19101670 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234178 |  | 8202222384#PERBAIKAN/CEK FILTER AIR DRAY | RU2S-KIL | 900-09AD-1A/00 | 50 | REL NMAT PRC SETC | 2RS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-10 | 2102362115 | 8202233242 |  | 8202222383#Perbaikan aux oil pump 11-P-1 | RU6-HSC | 11-P-102B-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-21 | 2026-01-21 | 2102359671 | 8202234642 |  | 8202222380#Perbaikan Conveyor Belt Centr | RU5-D&W | TM-34-09/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-21 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102363118 | 8202233897 |  | 8202222379#Notifikasi Hand Valve SPM 165 | RU6-ITP | 43-SPM-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 15972 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363594 | 8202232270 |  | 8202222377#COA 211 V-103 | RU2-HCC | 211-V-103/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 5614096 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363638 | 8202232223 |  | 8202222374#Breaker Coupler mcc 2-4 | RU2-UTL | 905-MCC24-INC/00 | 50 | REL NMAT PRC SETC | 2ER | D12/22/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-07 | 2025-12-16 | 2025-12-16 | 2102352759 | 8202234728 |  | 8202222373#Penggantian Valve 14 IN ANSI |  |  | 60 | TECO CNF PRT CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH | 2026-05-07 | 2026-02-07 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365391 | 8202240116 |  | 8202222364#25_Kebocoran body control val | RU4-KPC | 87FV217/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102363250 | 8202233868 |  | 8202222361#pekerjaan resertifikasi Boile | RU6-UTL | 052-B-101A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 4015840 | 1500000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359962 | 8202234653 |  | 8202222360#Leaking seal hydraulic LA No. | RU5-TBL | L-ARM-2-JT-1/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 9725090 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-03-13 | 2026-10-29 | 2102360033 | 8202234646 |  | 8202222355#NRK_Pemasangan PT dan TT pada | RU5-E15112 | 03-PG-5211/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA3-INT |  |  |  |  | PT02 |  | 2 | 2026-03-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-17 | 2026-02-10 | 2026-02-10 | 2102359901 | 8202234644 |  | 8202222354#Penggantian Pompa Dosing NaOH | RU5-UTL | 0UA-42-D002/00 | 01 | CLSD CSER NCMP NMAT PRC | 5RR | D15/10/B6/RT1-PDNH | 0 | 0 | MA1-ROT |  | ANDREAYR |  |  | PT02 |  | 2 | 2026-06-17 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102361250 | 8202237517 |  | 8202222353#Perbaikan Contl Panel Heater | RU4-KPC | 86K201/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 1000000000 | 824500000 | MA4-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360994 | 8202234897 |  | 8202222352#Penambahan Valve 18" & 20" Ta | RU4-TRML | 46T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-19 | 2102360039 | 8202234641 |  | 8202222348#Perbaikan Kabel Power Motor G | RU5-E15111 | GM-1-38/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 35000000 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361205 | 8202237316 |  | 8202222341#Belt Fin Fan 88E215A & B Rusa | RU4-KPC | 88E215A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361204 | 8202237315 |  | 8202222340#Belt Fin Fan 88E215B Rusak | RU4-KPC | 88E215B/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363783 | 8202232669 |  | 8202222339#Pengadaan Material PM 220 C-1 | RU2-HOC | 220-C-1A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 |  | 8202233516 |  | 8202222335#Penggantian relay rake clarif | RU6-UTL | 53-CL-201A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 12012 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365705 | 8202240113 |  | 8202222333#25_Perbaikan ProxySwitch ESV | RU4-RFCUTL | 152ZS-U152/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 6 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-24 | 2102361644 | 8202233609 |  | 8202222329#Penggantian lampu stack 052- | RU6-UTL | 52-SK-101A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2064 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-27 | 2025-11-27 | 2102361086 | 8202236445 |  | 8202222325#D25_041T121 | RU4-TRML | 041T121/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365452 | 8202240110 |  | 8202222324#25_018PV013 pasing | RU4-FOC2 | 018PV013A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-10-27 | 2026-11-25 | 2102360157 | 8202234650 |  | 8202222321#Material Pek.Resertifikasi Bo | RU5-UTL | HHP-2/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 51221439 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-27 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-27 | 2102362028 | 8202232854 |  | 8202222319#Perbaikan Trafo Desalter A | RU6-HSC | 11-V-101A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 42726000 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361033 | 8202235619 |  | 8202222310#perbaikan plenum fin fan | RU4-FOC2 | 013E107-1/00 | 50 WAMA | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364352 | 8202236618 |  | 8202222307#D_25 Pengadaan JB & Modif Cab |  |  | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359803 | 8202234638 |  | 8202222306#perbaikan Pompa G-37-05B | RU5-UTL | G-37-05B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 4850020 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361098 | 8202236493 |  | 8202222303#Penggantian PV Vent 41T-11 (r | RU4-TRML | 41T11/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365990 | 8202240107 |  | 8202222301#25_Penggantian filter lLO 14K | RU4-FOC1 | 14K602BM-S1A/B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 6668182 | 3334091 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238241 | 8202234832 | 8202222297#Tag 14 KV Tambat Kapal Area S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365989 | 8202240104 |  | 8202222296#25_Penggantian filter 14K602B | RU4-FOC1 | 14K602BM-S1A/B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 6668182 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365988 | 8202240101 |  | 8202222295#25_Penggantian filter lube oi | RU4-FOC1 | 14K602BM-S1A/B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 6668182 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365987 | 8202240099 |  | 8202222289#25_[CR] Penggantian Filter Pe | RU4-FOC1 | 14K602BM-S1S2/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3334091 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359850 | 8202234636 |  | 8202222286#Perbaikan Speed Indicator K-5 | RU5-E15111 | K-5-02C/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 36300891 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365731 | 8202240095 |  | 8202222285#25_[CR] 014E108K01 Bearing & | RU4-FOC2 | 014E108K01/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365727 | 8202240092 |  | 8202222284#25_penggantian filter lube oi | RU4-FOC1 | 14K602BM-S1A/B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 3334091 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-11-04 |  | 8202236652 | 8202233851 | 8202222281#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-11-04 |  | 8202236655 | 8202233851 | 8202222280#SWO Pemb. LTSA Metering Termi | RU6-ITP | 42-A-100/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352188 | 8202234177 |  | 8202222279#LINE WATER SPRAYER TK 10 & TK | RU2S-LKKK | 946-LK3-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 189705 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102363188 | 8202233316 |  | 8202222278#Perbaikan 19-PDT-722 | RU6-RCC | 19-PDT-722B/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352718 | 8202234499 |  | 8202222273#N_Perbaikan P-8 CDU IV | RU3-CDGP | CD4-P-008/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352717 | 8202234501 |  | 8202222272#N_Perbaikan P-7 Stab C | RU3-CDGP | STA-P-007/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-02-27 | 2102362024 | 8202233017 |  | 8202222271#Perbaikan MotorOverhead Crane | RU6-HSC | 31-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 576 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365986 | 8202240088 |  | 8202222270#25_Pengadaan control valve ba | RU4-FOC1 | 14PV030/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-28 | 2102361907 | 8202233019 |  | 8202222269#Perbaikan Motor OverheadCrane | RU6-HSC | 31-K-101A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2025-12-01 | 2025-12-01 | 2102359856 | 8202234634 |  | 8202222264#Perbaikan Motor GM-3-49A | RU5-E15112 | GM-3-49A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 77617 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361059 | 8202236091 |  | 8202222261#Perbaikan Coupling 47S506A | LOC1-UP4 | 47S506A-M/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-15 | 2026-03-09 | 2026-03-09 | 2102363976 | 8202241367 |  | 8202222256#[CR] 011P110C Mech Seal IB bo | RU4-FOC2 | 011P110C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 25903700 | 0 | MA2-ROT |  | YUNITAMR |  | 2026-03-10 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363672 | 8202232303 |  | 8202222254#300-C-2A cylinder 1 high temp | RU2-HSC | 300-C-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 56045413 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365644 | 8202240083 |  | 8202222248#25_011P-113C, Mech seal bocor | RU4-FOC2 | 011P113C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 12014850 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363773 | 8202232646 |  | 8202222246#Pengadaan Transmitter 310-FT- | RU2-HSC | 310-FT-363/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-04 | 2026-04-06 | 2026-02-04 | 2026-02-04 | 2102364379 | 8202238049 |  | 8202222242# CLEANING BURNER RUTIN AREA H | RU2-HOC | 140-V-1A/00 | 50 | CRTD NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1 | 0 | MA1-STA |  | ERLANGGA |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-15 | 2025-12-15 | 2025-12-15 | 2102359852 | 8202234632 |  | 8202222241#MAT. PERB valve discharge G-2 | RU5-E15112 | G-2-03B/00 | 60 | TECO CNF MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 52425000 | 0 | MA3-STA |  | SAPBATCH | 2026-06-15 | 2026-02-11 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K201 | 2026-02-04 | 2026-05-25 | 2026-02-04 | 2026-02-04 |  | 8202238048 |  | 8202222240#RK0102 LTSA WATER SPRINKLER | RU2-HOC |  | 50 | CRTD NMAT PRC RELR SETC | 2MR | D12/25/B6/RT-D2H | 1 | 0 | MA1-STA |  | DEDISUKMANA |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-25 | 2026-02-04 | 2026-02-04 |  | 8202238047 |  | 8202222237#RK0367 LTSA CLEANING TRANSFER | RU2-HOC |  | 50 | CRTD NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1 | 0 | MA1-STA |  | DEDISUKMANA |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-04 | 2102361249 | 8202237515 |  | 8202222234#TGH1_24 UP Boardesk MA 2 | RU4-TRML | 048V101/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-25 | 2026-02-05 | 2026-02-05 |  | 8202238235 |  | 8202222232#RK0119 PIPING STEAM NON TRAP | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 400000000 | 0 | MA2-STA |  | DEDISUKMANA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-26 | 2026-02-05 | 2026-02-05 |  | 8202238232 |  | 8202222231#RK0376 KONTRAK SCAFFOLDING AL | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | DEDISUKMANA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-12-16 | 2102361902 | 8202233981 |  | 8202222230#LTSA Conmon PLC dan MMS all A | RU6-RCC | ES-B14-01/00 | 01 | CRTD CSER NMAT PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-30 | 2025-12-30 | 2102359859 | 8202234631 |  | 8202222228#Perbaikan Motor P17 WTP 1 | RU5-UTL | P-17-WTP/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1417450 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-30 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102361905 | 8202232837 |  | 8202222226#Perbaikan Turbine 052-B-101A- | RU6-UTL | 052-B-101A-K-101/0 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363626 | 8202232247 |  | 8202222225#perbaikan motor 905-CM-52 | RU2-UTL | 905-CM-52/00 | 50 | REL MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361089 | 8202236474 |  | 8202222224#Penggantian strainer pilot 14 | RU4-FOC1 | 14PV002A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-05-06 | 2025-12-05 | 2026-12-04 | 2102361709 | 8202233089 |  | 8202222223#Perbaikan Mechseal 14-P-107B | RU6-DHC | 14-P-107B/00 | 50 WAMA | REL CSER MANC PRC SETC | 6RR | D16/25/B6/RT-C2H | 183895858 | 0 | MA2-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-13 | 2026-01-13 | 2102352195 | 8202234176 |  | 8202222222#Pemeriksaan Foot Valve Raw Pu | RU2S-KIL | 900-01P-1A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C3H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363544 | 8202232197 |  | 8202222221#Perbaikan Packing Level Glass | RU2-UTL | 940-B-3/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352833 | 8202234589 |  | 8202222216#N_ Perbaikan Weight Scale Mus | RU3-ITP | V-801-D/00 | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-08-10 | 2102359961 | 8202234629 |  | 8202222215#penggantian filter LO | RU5-E15112 | GM-3-01A/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-02-04 | 2102361824 | 8202233293 |  | 8202222212#Perbaikan 32-FI-006 | RU6-HSC | 32-FT-006A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-29 | 2026-02-02 | 2027-01-04 | 2102363112 | 8202233813 |  | 8202222211#Pengadaan Gearbox Pompa 12-P- | RU6-DHC | 12-P-501A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 1137428055 | 1137428055 | MA2-ROT |  | SAPBATCH | 2026-05-29 | 2026-02-07 | PT02 |  | 3 | 2026-05-29 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363726 | 8202232523 |  | 8202222210#Mixer Rusak | RU2-HCC | 701-M-51/00 | 50 | REL MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 0 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363728 | 8202232525 |  | 8202222205#mixer jammed | RU2-HCC | 702-MM-51/00 | 50 | REL MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-12-04 |  | 8202233768 | 8202233764 | 8202222203#Pengadaan Part Pompa 34-A-103 | RU6-POC | 34-A-103-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 3072 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365641 | 8202240078 |  | 8202222202#25_[CR] Penggantian Valve 13K | RU4-FOC1 | 13K1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2027-01-20 | 2102365901 | 8202240074 |  | 8202222199#25_Mtl. Perbaikan line drain | RU4-FOC1 | 11V10/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-1-C2H | 3252034 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363768 | 8202232627 |  | 8202222196#Pengambilan V-belt 140 E-8A | RU2-HOC | 140-EF-8A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 12146000 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363769 | 8202232628 |  | 8202222194#Pengambilan V-belt 140 E-12B | RU2-HOC | 140-EF-12B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 1888000 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-18 | 2026-02-02 | 2026-06-29 | 2102361618 | 8202233793 |  | 8202222183#Pengadaan material baru 20-FV | RU6-RCC | 20-FV-008/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 48236464 | MA1-INT |  | AHMADAKHYAR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365959 | 8202240070 |  | 8202222167#25_Penggantian 154-LI-877 | RU4-RFCUTL | 154LI-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 4 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-02-05 | 2102361743 | 8202232823 |  | 8202222164#Perbaikan Valve PSA 22-V-109G | RU6-DHC | 22-V-109G/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2025-11-24 | 2026-04-07 | 2102361741 | 8202232824 |  | 8202222163#Perbaikan Valve PSA 22-V-109E | RU6-DHC | 22-V-109E/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 1024 | 0 | MA2-INT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365633 | 8202240066 |  | 8202222161#25_Penggantian Pre-After Filt | RU4-RFCUTL | 156A501A/00 | 60 | REL CSER GMPS MSPT PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 83170000 | 83170000 | MA5-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366027 | 8202240062 |  | 8202222156#25_47S-506A-P4 | LOC1-UP4 | 47S506A-P4/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 750500 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365916 | 8202240057 |  | 8202222155#25_Penggantian bearing motor | LOC1-UP4 | 47S506A-P5/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 750500 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-11-26 | 1102328283 | 8202234619 |  | 8202222151#Perbaikan Cell O2 Analyzer 3B | RU5-E15112 | F-3-03B-INST/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 18651000 | 0 | MA3-INT |  | HASRUDDINA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-10 | 2026-02-10 | 2102352251 | 8202234175 |  | 8202222148#Emergency Isolation Valve 101 | RU2S-KIL | 101-T-3/01 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C4H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-10 | PM |  | 004
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352250 | 8202234174 |  | 8202222147#Pemsgn Emergency Isolation Va | RU2S-KIL | 101-T-1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-D1H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-19 | 2102363181 | 8202233018 |  | 8202222145#Perbaikan Motor pompa 20R101C | RU6-RCC | 20-R-101C/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-12-28 | 2102361247 | 8202237513 |  | 8202222135#TGH25-26_22 Sewa CCTV Tanki 4 | RU4-RFCGTO | 47T511A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 114296000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361246 | 8202237512 |  | 8202222134#TGH10_23 TSA ConMon Instrumen | RU4-RFCC | 101FJB001/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 287652000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352757 | 8202234505 |  | 8202222124#N_Perbaikan Indikasi FLPC1001 | RU3-CDL | FLRS-FT-1022/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-04 | 2026-05-26 | 2026-12-04 | 2026-12-04 |  | 8202238108 |  | 8202222123#RK0042 LTSA Casting Rotating | RU2-HCC |  | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA2-ROT |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-12-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-19 |  | 8202234612 |  | 8202222120#Penggantian Battery UPS PLC F |  | 341-FGDS-F18-3/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 22 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358205 | 8202234358 |  | 8202222119#Penggantian kerangan 1-FV-114 | RU7-CDU | 1-FV-114/00 | 60 WASR | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/NR-1-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-04 | 2026-02-21 | 2025-12-22 | 2025-12-22 |  | 8202238180 |  | 8202222115#Pengadaan Kontrak Sertifikasi | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1000000000 | 0 | MA4-INT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2025-12-22 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353030 | 8202234586 |  | 8202222114#N_Antisipate Mech.Seal CDL | RU3-CDL | SWS-P-63-003B/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352716 | 8202234503 |  | 8202222113#N_Perbaikan P-10 CDU IV | RU3-CDGP | CD4-P-010/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352908 | 8202234497 |  | 8202222112#N_Perbaikan Pompa P-45 CDU II | RU3-CDGP | CD2-P-045/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352715 | 8202234502 |  | 8202222110#N_Perbaikan P-48 CDU II | RU3-CDGP | CD2-P-048/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-24 | 2102362698 | 8202233169 |  | 8202222109#Perbaikan Fin-fan 12-E-105A | RU6-DHC | 12-E-105A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-12-02 | 2102361703 | 8202233862 |  | 8202222097#Pemb LTSA DCS Centum VP dan E | RU6-ITP | DCSOFFSITE/00 | 50 | CLSD CSER NCMP NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-01-21 | 2026-02-20 | 2102360071 | 8202234568 |  | 8202222094#PERB.LINE 21-P909-20"-B20 DPN | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 387614857 | 0 | MA4-STA |  | SAPBATCH | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365643 | 8202240053 |  | 8202222091#25_[CR] Penggantian membran 1 | RU4-FOC1 | 11P15A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365642 | 8202240050 |  | 8202222090#25_[CR] Perbaikan 11P15B tida | RU4-FOC1 | 11P15B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363255 | 8202232258 |  | 8202222088#Pengadaan Level Glass Steam D | RU2-HOC |  | 50 | REL CSER MACM PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-30 | 2102360103 | 8202234602 |  | 8202222080#Lampu penerangan Kepala Jetty |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 47300360 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-30 | 2102360154 | 8202234566 |  | 8202222078#Perbaikan Lampu Penerangan je |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 97590790 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-01-13 | 2026-01-13 | 2102362816 | 8202233164 |  | 8202222074#Perbaikan Foot Valve Ejector | RU6-HSC | 30-J-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-13 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361700 | 8202234061 |  | 8202222071#31-LT-008 | RU6-HSC | 31-LT-008/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359967 | 8202234486 |  | 8202222063#Material Perb. Pipa Pemadam 2 | RU5-E15500 | KUP-FWL-601/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/NR-C2H | 1291347785 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-29 | 2102360036 | 8202234457 |  | 8202222061#Perbaikan PI pompa G-201-09A | RU5-D&W | G-201-09A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 6807222 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-29 | 2102360037 | 8202234431 |  | 8202222060#Perbaikan PI pompa G-201-09B | RU5-D&W | G-201-09B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 6807222 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2027-01-06 |  | 8202238636 | 8202237510 | 8202222056#TGH9_SIP_UP Rumput All Area K | RU4-TRML | 72FMMOV101AM/00 | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-04 | 2102361245 | 8202237510 |  | 8202222055#TGH8_SIP_UP Rumput All Area K | RU4-TRML | 72FMMOV101AM/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-13 | 2026-06-23 | 2026-06-23 | 2102360332 | 8202234487 |  | 8202222054#Consumable Material Engine GD | RU5-E15500 | 33-DE-1055-01C/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 1585200 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-02-07 | PT02 |  | 3 | 2026-06-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-25 | 2026-03-25 | 2026-03-27 | 2102360159 | 8202234462 |  | 8202222053#Perbaikan Motor G-31-49B Demi | RU5-UTL | DEMIN-123-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 7741965 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-16 | 2102365668 | 8202240046 |  | 8202222045#25_[CR] 018P702A Membran Coup | RU4-FOC2 | 018P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-08 | 2026-01-27 | 2026-02-18 | 2102360393 | 8202234470 |  | 8202222043#Perb. P13 A Hitam ADO Loading | RU5-TBL | P-13RP-A-HITAM/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C1H | 0 | 0 | MA4-ROT |  | SAPBATCH | 2026-06-08 | 2026-02-11 | PT02 |  | 3 | 2026-06-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-02 | 2026-02-02 | 2102360070 | 8202234468 |  | 8202222035#Perbaikan Mech seal Pompa 11 | RU5-TBL | P-11-RP-R/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 27941834 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-15 | 2026-02-02 | 2026-12-02 | 2102361684 | 8202233852 |  | 8202222034#Pemb.LTSA PLC Honeywell | RU6-POC | 38-E-101/00 | 01 | CLSD CSER NCMP NMAT PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-06 | 2102365663 | 8202240042 |  | 8202222033#25_017E-105 M22, blade nyengg | RU4-FOC2 | 017E105K22/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 14007883 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-23 | 2026-01-26 | 2102360674 | 8202234474 |  | 8202222031#Material Perbaikan Pompa G-3- | RU5-E15112 | G-3-06D/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 15838710 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-03 | 2026-11-24 | 2102360073 | 8202234488 |  | 8202222030#Bearing housing BFW 7 crack | RU5-UTL | T-BFW-P-7/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-11-03 | PM |  | 003
| K601 | 2026-02-04 |  | 2026-02-04 | 2027-04-02 |  | 8202238226 |  | 8202222022#Penggantian unit Trafo | RU6-UTL | 51-PTR-101D/00 | 50 | CRTD CSER NMAT PRC | 6ER | D16/25/B6/RT-C2H | 1 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363583 | 8202232227 |  | 8202222018#Pengadaan material | RU2-HCC | 212-PT-14B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 377582 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 | 2102352181 | 8202234173 |  | 8202222016#Lanjutan Pek. Sewa Crane Thn | RU2S-MA | 972-CCEH-04/00 | 60 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353367 | 8202234489 |  | 8202222015#N_PLC N2 Plant Utilties Plaju |  |  | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360079 | 8202234419 |  | 8202222012#Mat. Tam. Perbaikan Tank Foam | RU5-E15500 | JT5-MFT-002/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 16017634 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K201 | 2026-02-04 | 2026-04-15 | 2026-02-05 | 2026-02-05 |  | 8202238225 |  | 8202222002#TSA 7 Alat Peralatan Lab RU I | RU2-LAB | LAB-GAS-21/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 1000000000 | 0 | WS-IN1 |  | DONITGN |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-09 | 2026-03-09 | 2026-12-07 | 2102362507 | 8202233093 |  | 8202221998#Perbaikan Mech Seal Pompa 42- | RU6-ITP | 42-P-207B/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/NR-C2H | 791517062 | 431949052 | MA4-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-04-30 | 2026-07-29 | 2102360075 | 8202234401 |  | 8202221983#Pengadaan Gas Kalibrasi O2 An | RU5-E15112 | 02-AT-1002/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 10 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-04-30 | PM |  | 003
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-07-13 | 2102358256 | 8202234357 |  | 8202221981#Penggantian Selenoid Valve 2- | RU7-NHT | 2-XY-411/00 | 50 WAMA | CRTD CSER MACM PRC | 7RT | D17/25/B6/RT-2-D4H | 0 | 0 | MA-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358255 | 8202234356 |  | 8202221980#Penggantian Selenoid Valve 2- | RU7-NHT | 2-XY-403A/00 | 60 | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D4H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238224 | 8202234902 | 8202221973#Tag 2 KV Sipil Area SG 2024-2 |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-04-30 | 2102360104 | 8202234397 |  | 8202221964#perbaikan cover motor Gm-2-16 | RU5-E15112 |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 7318252 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-08 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102363717 | 8202238743 |  | 8202221962#25L_Pengadaan Hydrogen Kilang | RU4-FOC2 | 012PT007/00 | 50 | CRTD NMAT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 100000 | 0 | MA1-STA |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352803 | 8202234531 |  | 8202221961#Perbaikan P-8 CDU V | RU3-CDGP | CD5-P-008/00 | 60 | REL CSER GMPS MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 2780099 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2025-12-31 | 2025-12-31 | 2102353137 | 8202234529 |  | 8202221960#Perbaikan Panel FGDS Unit Pol | RU3-PP | FIELD-PP-FGDS/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 2 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365632 | 8202240038 |  | 8202221959#25_[CR] Perbaikan Fan Radiato | RU4-RFCUTL | 152G502D-D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361136 | 8202236837 |  | 8202221954#D_25 014E-104 M2, belt rusak | RU4-FOC2 | 014E104M02/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361137 | 8202236840 |  | 8202221953#D_25 014E-104 M1, belt rusak | RU4-FOC2 | 014E104M01/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233934 |  | 8202221952#Material Make Up Rocksalt 21 | RU6-DHC | 21-V-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362657 | 8202232942 |  | 8202221949#Perbaikan Pompa 62-P-201D | RU6-UTL | 62-P-201D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-12 | 2102363403 | 8202233629 |  | 8202221947#Penggantian gland cable | RU6-UTL | 56-K-101A-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 8316 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-10-06 |  | 8202233279 |  | 8202221946#Perbaikan 34-TI-040 | RU6-POC | 34-C-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-10-06 |  | 8202233267 |  | 8202221945#Perbaikan 39-TI-032 | RU6-POC | 34-E-111/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-07 | 2026-02-03 | 2026-02-03 | 2102361032 | 8202235608 |  | 8202221939#Perbaikan pompa 42P-4A | RU4-TRML | 42P4A/00 | 01 | CLSD NCMP NMAT PRC | 4RR |  | 0 | 0 | MA1-ROT |  | BADIPUTRO |  |  | PT02 |  | 2 | 2026-03-07 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363186 | 8202233421 |  | 8202221933#Perbaikan 059-A-101B-K1 | RU6-UTL | 059-A-101B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 6912 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2102360108 | 8202234365 |  | 8202221932#Perb Mixer Tangki D20-07B TM2 | RU5-TBL | TM-20-07C/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2269228 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-07-31 | 2102360330 | 8202234386 |  | 8202221931#Panel Power Electrical All Ar | RU5-E15112 |  | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-06-09 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K601 | 2026-02-01 | 2026-06-02 | 2026-02-02 | 2026-12-15 |  | 8202233271 |  | 8202221929#Perbaikan 38-GDF-015 | RU6-POC | 35-GDF-001/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 952635000 | 952635000 | MA3-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-01-28 | 2026-07-27 | 2102360338 | 8202234367 |  | 8202221928#Penggantian EHT C-3-01B | RU5-E15112 | EHT-108-3/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-17 | 2026-03-02 | 2026-09-01 | 2102360337 | 8202234369 |  | 8202221926#Penggantian EHT C-3-01A | RU5-E15112 | EHT-100-3/00 | 60 | REL CNF CSER MACM PRC SETC | 5ER | D15/26/B6/NR-C3H | 0 | 0 | MA3-LIS |  | FAUZANR | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-03-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-04-01 | 2102361961 | 8202233080 |  | 8202221925#Perbaikan Modul 19-K-101 | RU6-RCC | 19-K-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1280 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-06 | 2102361244 | 8202237508 |  | 8202221919#TGH2_24 UP Perpipaan & Akseso | RU4-UTL | LN52-104VA/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102363977 | 8202240035 |  | 8202221912#014K102A bearing rusak, valve | RU4-FOC2 | 014K102A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 191262999 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-05-11 | 2102360487 | 8202234387 |  | 8202221910#Material Perbaikan/Cleaning E | RU5-D&W | E-201-05A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 29853750 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352838 | 8202234731 |  | 8202221908#Penggantian Printer Bagging 2 | RU3-PP | 23-2601-IJP-A/00 | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358290 | 8202234355 |  | 8202221907#Permintaan Gasket 6" 150 5 Pc |  |  | 60 WASR | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-4-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358382 | 8202234348 |  | 8202221906#Perbaikan Pompa 1-P-05 B | RU7-CDU | 1-P-05B/00 | 60 WASR | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-04-10 | 2026-04-10 | 2026-05-12 | 2102360158 | 8202234362 |  | 8202221901#Perbaikan G-202-07B (casing b | RU5-D&W | G-202-07B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 163557115 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358296 | 8202234347 |  | 8202221898#Ganti bearing motor 1-P-12 A | RU7-CDU | 1-P-12A/00 | 60 WASR | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-28 | 2025-11-28 | 2102361080 | 8202236387 |  | 8202221897#D25_level transmiter 019LT030 | RU4-FOC2 | 019LT030/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365667 | 8202240031 |  | 8202221896#25_Penggantian 260TI_106 | RU4-LOC3 | TEMP-U260/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102363114 | 8202233938 |  | 8202221895#Material Filter Oil 32-A-101 | RU6-HSC | 32-A-101-S2B/00 | 50 | CRTD CSER MACM PRC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365939 | 8202240027 |  | 8202221893#25_[CR] Perbaikan Mechseal 10 | RU4-RFCC | 101P502A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 1101000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352641 | 8202234504 |  | 8202221892#Perbaikan Vessel SWS | RU3-CDGP |  | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365938 | 8202240024 |  | 8202221889#25_[CR] Perbaikan Mechseal 10 | RU4-RFCC | 101P502C/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 36382195 | 26463000 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102360712 | 8202237434 |  | 8202221888#Material Perbaikan Fin-fan EA | RU5-E15112 | EA-31-21D/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 6826085 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361125 | 8202236599 |  | 8202221887#D_25 penggantian belt 14E5A | RU4-FOC1 | 14E5AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2025-12-16 | 2025-12-16 | 2102360673 | 8202237435 |  | 8202221885#G-17-01A High Vibration | RU5-E15112 | G-17-01A/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/24/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-18 | 2102362561 | 8202233888 |  | 8202221879#Overhaul dan rewinding Motor | RU6-RCC | 16-P-109B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-24 | 2025-12-30 | 2102360155 | 8202237430 |  | 8202221878#Perbaikan Exciter STG 2.1 | RU5-UTL | 1SP10/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 26 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2025-12-24 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363749 | 8202232562 |  | 8202221877#Perbaikan Valve 220 C-1 | RU2-HOC | 220-C-1B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363690 | 8202232439 |  | 8202221876#Perbaikan 905-TRF-2-2 | RU2-UTL | 905-TRF-2-2/00 | 50 | REL MACM PRC SETC | 2ER | D12/24/B6/NR-D2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102361243 | 8202237506 |  | 8202221875#Jasa Pemasangan 80EE2112D | RU4-KPC | 80EE2112D/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/24/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363545 | 8202232198 |  | 8202221874#Perbaikan Online Analizer | RU2-UTL | 940-B-1/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | WS-IN1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363619 | 8202232264 |  | 8202221873#Perbaikan Lampu Penerangan Ar | RU2-UTL | 510-M-C-OH/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-06-05 | 2102360390 | 8202237433 |  | 8202221870#Penambahan License DCS HMI HI | RU5-E15112 | 50R-EC-01/00 | 50 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 370000000 | 0 | MA3-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360484 | 8202237432 |  | 8202221869#Penggantian Lamp Test K-5-02 | RU5-E15111 | K-5-02A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102362151 | 8202232874 |  | 8202221868#Perbaikan Speed Indikator 15- | RU6-RCC | 15-P-111F-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K401 | 2026-02-03 | 2026-05-07 | 2026-04-01 | 2026-12-30 | 2102361242 | 8202237505 |  | 8202221867#perpanjangngan lift elevato c | RU4-FOC1 | 14K650M/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-04-01 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358310 | 8202234346 |  | 8202221866#Ganti PI di Outlet 3-R-01 | RU7-CRU | 3-R-01/00 | 60 WASR | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D4H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358313 | 8202234345 |  | 8202221865#Penggantian bearing motor 2-E | RU7-NHT | 2-EAM-01A/00 | 60 | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-2-D4H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-08 | 2026-10-23 | 2026-12-04 | 2102360604 | 8202237413 |  | 8202221860#Perbaikan Journal Bearing BFW | RU5-UTL | 3RL-20-D001/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/24/B6/RT-C2H | 2353475 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102360392 | 8202237427 |  | 8202221859#GT-20-23B PM Equipment | RU5-TBL | GT-20-23B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/24/B6/RT-C2H | 131728975 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361241 | 8202237503 |  | 8202221858#TGH7_23 Tagihan TSA Fire Supp | RU4-FOC1 | 11FT001/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360334 | 8202237412 |  | 8202221857#Perb Press Transmitter Boiler | RU5-UTL | HHP-6-INST/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-13 | 2026-02-03 | 2026-04-30 | 2102360645 | 8202237410 |  | 8202221853#perbaikan IHLA Tangki A-27 | RU5-TBL | A-27/00 | 60 | REL CSER MANC PRC SETC | 5IR | D15/25/B6/RT-C2H | 30807000 | 0 | MA4-INT |  | ANTONIUSAD |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363111 | 8202233290 |  | 8202221850#Perbaikan 32-P-108B | RU6-HSC | 32-P-108B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102362341 | 8202233988 |  | 8202221847#Lampu Penerangan Area TPS Cat | RU6-LK/KK | JALANKILANG/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 16236 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102361796 | 8202233284 |  | 8202221845#Perbaikan 33-PV-003 | RU6-HSC | 33-PV-003/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365662 | 8202240020 |  | 8202221843#25_Penggantian 260TI_101 | RU4-LOC3 | TEMP-U260/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363621 | 8202232315 |  | 8202221836#Perbaikan HE | RU2-HCC | 410-E-2/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-06 | 2026-02-13 | 2026-02-06 | 2026-02-06 | 2102352832 | 8202238693 |  | 8202221835#Perbaikan HMI Catalyst Feeder | RU3-CDL | FC-HS-2001/00 | 50 WAMA | CRTD CSER MACM PRC | 3IR |  | 42519000 | 0 | MA3-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363030 | 8202233778 |  | 8202221833#Pengadaan Membran Coupling 16 | RU6-RCC | 16-K-102-P1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2027-01-04 | 2102363035 | 8202233857 |  | 8202221829#Pemb. LTSA O2 Ametek | RU6-RCC | 15-AT-002/00 | 60 | CLSD CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102361505 | 8202233302 |  | 8202221828#Perbaikan 22-V-109J | RU6-DHC | 22-V-109J/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102361650 | 8202233304 |  | 8202221827#Perbaikan 22-V-109D | RU6-DHC | 22-V-109D/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-05-22 | 2025-11-10 | 2026-07-06 |  | 8202238532 |  | 8202221826#penggantian analyzer conduct | RU6-UTL | 055-A-101-V2/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 20000132 | 0 | MA4-INT |  | ARYATHONI |  | 2026-02-07 | PT02 |  | 3 | 2025-11-10 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-07-20 | 2026-07-20 | 2102363737 | 8202232542 |  | 8202221823#Pompa penanggulangan banjir C | RU2-HSC | 301-P-1A/00 | 50 | REL MACM PRC SETC | 2MR | D12/26/B6/NR-D2H | 0 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-07-20 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-08-03 | 2026-08-03 | 2102360523 | 8202237408 |  | 8202221822#G-32-06B meach seal bocor | RU5-E15112 | G-32-06B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 14173347 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-08-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-12-01 | 2026-12-22 | 2102360601 | 8202237406 |  | 8202221821#Perbaikan K-201-03 | RU5-D&W | K-201-03/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 26000000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-01 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-02 | 2025-12-02 | 2102360999 | 8202234981 |  | 8202221820#Tagihan pemasangan kabel inst | RU4-FOC1 | 11LT701/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-11 |  | 8202236798 |  | 8202221819#PMPdM Electr-Instr MA3 Tahap | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-11 |  | 8202236799 |  | 8202221818#PMPdM Electr-Instr MA3 Tahap | RU6-HSC | 17-PBD3-01A/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 | 2102353352 | 8202238219 |  | 8202221799#Perbaikan Tangga Cooling Towe |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102363034 | 8202234011 |  | 8202221795#Indikasi kerusakan Bearing 34 | RU6-POC | 34-P-106B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102364226 | 8202238046 |  | 8202221785#PERFORMANCE SERVICE AGREEMENT | RU2-UTL |  | 50 | CRTD NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 230000001 | 0 | MA3-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102364381 | 8202238531 |  | 8202221782#ruTSA STEAM LEAKS NON TRAP AR | RU2-ITP |  | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 690446 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238018 |  | 8202221781#SERTIFIKASI T.U.METERING | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 681151000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238214 |  | 8202221780# LTSA PERBAIKAN ROOF TANK | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2102366516 | 8202241571 |  | 8202221779# LTSA CLEANING SEPARATOR 1,2, | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 2138185000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-03-11 | PT02 |  | 3 | 2026-03-11 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-25 | 2026-02-04 | 2026-02-04 |  | 8202238045 |  | 8202221778#RK0025 TSA ATG | RU2-ITP |  | 50 | CRTD NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1 | 0 | MA4-INT |  | DEDISUKMANA |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-25 | 2026-02-05 | 2026-02-05 | 2102364380 | 8202238227 |  | 8202221776#RK0128 PIPING SYSTEM AREA OM | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 300000000 | 0 | MA4-STA |  | DEDISUKMANA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102363972 | 8202238220 |  | 8202221762#PEMBERSIHAN BERKALA LUMPUR DI | RU2-UTL |  | 60 | REL NMAT PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-09 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K201 | 2026-02-04 | 2026-05-26 | 2026-02-05 | 2026-02-05 | 2102363828 | 8202238217 |  | 8202221759#RK0372 LTSA CEMS AREA HOC_202 | RU2-HOC | 110-H-1A/00 | 50 | CRTD NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 1 | 0 | MA1-INT |  | DEDISUKMANA |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-11-16 | 2102365666 | 8202240016 |  | 8202221751#25_[CR]Perbaikan Pompa 10P4 | RU4-FOC1 | 10P2/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 2204 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-25 |  | 8202233932 |  | 8202221748#Material Make Up Rocksalt 14- | RU6-DHC | 14-V-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237020 |  | 8202221741#Penggantian protection relay | RU4-TRML | 38P103A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-17 | 2025-12-17 | 2102363688 | 8202232435 |  | 8202221739#Penambahan AC MCR | RU2-HCC | HCC-AC-MCR/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-17 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352901 | 8202234802 |  | 8202221731#Penggantian Controller DCS Ut | RU3-UTL | UTL-DCS/00 | 50 WAMA | REL CSER MACM PRC SETC | 3IR | D13/25/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2027-01-04 | 2102362349 | 8202236854 |  | 8202221729#Perbaikan tube 50-E-101 | RU6-UTL | 50-E-101/00 | 50 WAMA | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 1 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102361697 | 8202233303 |  | 8202221727#Perbaikan 22-V-109F | RU6-DHC | 22-V-109F/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102363071 | 8202233371 |  | 8202221726#Perbaikan 13-LT-261 di 13-V-1 | RU6-DHC | 13-LT-261/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102363077 | 8202233390 |  | 8202221725#Perbaikan 12-PSLL-366 di 12-P | RU6-DHC | 12-P-501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-16 | 2026-04-16 | 2026-11-25 | 2102362343 | 8202232927 |  | 8202221724#Perbaikan Positioner 16-FV-01 | RU6-RCC | 16-FV-017/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6IR | D16/26/B6/RT-C2H | 53136464 | 48236464 | MA1-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102362949 | 8202232928 |  | 8202221723#Perbaikan Positioner 15-UV-04 | RU6-RCC | 15-FV-047/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102363444 | 8202233398 |  | 8202221722#Perbaikan 12-LT-277 | RU6-DHC | 12-LT-277/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102352837 | 8202234521 |  | 8202221721#Perbaikan Pompa P-5 Fuel Oil | RU3-CDGP | CD5-P-005HVU/00 | 60 | REL NMAT PRC SETC | 3RR |  | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363739 | 8202232544 |  | 8202221716#Mechanical Seal Cooler Low Pe | RU2-HCC | 211-P-9C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-09 | 2026-02-02 | 2026-02-02 | 2102363748 | 8202232561 |  | 8202221715#Penggantian Filter | RU2-HCC | 212-C-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 341136000 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-09 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238216 | 8202235215 | 8202221714#Tag 5 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352902 | 8202234756 |  | 8202221711#Penggantian Photo Electric Ce |  |  | 50 WAMA | REL CSER MACM PRC SETC | 3MR |  | 0 | 0 | GEN-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-04 | 2026-06-11 | 2026-02-05 | 2026-02-05 |  | 8202238212 | 8202235233 | 8202221710#Tag 5 Kontrak Volume Mekanik |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-12-02 | 2102362895 | 8202233859 |  | 8202221708#Pemb. LTSA ATG | RU6-ITP | 42-T-403A/00 | 01 | CRTD NMAT PRC | 6IR | D16/25/B6/RT-C2H | 26400 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361240 | 8202237501 |  | 8202221707#Perbaikan kabel control heate | RU4-TRML | 041E314BDF-PNL/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 |  | 2025-12-08 | 2026-10-26 | 2102362973 | 8202233851 |  | 8202221706#Pembayaran LTSA Metering Syst | RU6-ITP | 42-A-100/00 | 50 | CRTD NMAT PRC | 6IR | D16/25/B6/RT-C2H | 2688 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-07 | 2025-12-30 | 2025-12-30 | 2102358323 | 8202238004 |  | 8202221700#LTSA mettering PKS dan Residu |  |  | 50 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-5-D3H | 1 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102366013 | 8202240014 |  | 8202221697#25_Perbaikan bocoran line ste | RU4-UTL | 50AUX1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 10451417 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-07 | 2026-10-30 | 2102358932 | 8202237399 |  | 8202221695#MAT.PERB.PIPING TANGKI TU-10, | RU5-UTL | HHP-PT-101/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360529 | 8202237374 |  | 8202221694#Relay Undervoltage Motor Sei | RU5-UTL | S-WAIN-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 6099000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2025-12-01 | 2025-12-08 | 2102360676 | 8202237376 |  | 8202221693#Perbaikan Motor Gm-17-01B | RU5-E15112 | GM-17-01B/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 348748 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-01 | 2025-12-08 | 2102360524 | 8202237375 |  | 8202221692#Perbaikan Motor GM-2-14B | RU5-E15112 | GM-2-14B/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 245304 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-04 | 2026-02-02 | 2027-01-12 | 2102362890 | 8202233974 |  | 8202221684#LTSA Pemeliharaan Elevator RU | RU6-HSC | 32-R-103/00 | 01 | CLSD CSER NCMP NMAT PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-13 | 2102362893 | 8202233134 |  | 8202221677#Perbaikan Kompresor 059-A-101 | RU6-UTL | 059-A-101B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 460005 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360603 | 8202237394 |  | 8202221671#Penggantian Lampu Sub Station |  |  | 50 | REL CSER NMAT PRC SETC | 5ER | D15/24/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-01 | 2025-12-10 | 2102360648 | 8202237382 |  | 8202221669#Perbaikan Motor Ea-3-03C | RU5-E15112 |  | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 6900102 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360605 | 8202237396 |  | 8202221668#Penggantian Lampu Sub Station | RU5-UTL | 41-R-SS-67-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 44028240 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353078 | 8202235603 |  | 8202221664#Field Local Panel Instrument | RU3-CDGP |  | 60 | REL CSER NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365393 | 8202240010 |  | 8202221662#25_Penggantian 156_TI_751A | RU4-RFCUTL | 156TT-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365392 | 8202240009 |  | 8202221661#25_Penggantian 156_TI_752A | RU4-RFCUTL | 156TT-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365868 | 8202240007 |  | 8202221660#25_Penggantian 154_TI606A | RU4-RFCUTL | 154TT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365867 | 8202240006 |  | 8202221659#25_Penggantian 154_TI606C | RU4-RFCUTL | 154TT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365866 | 8202240005 |  | 8202221658#25_Penggantian 154_TI602B | RU4-RFCUTL | 154TT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102363808 | 8202238114 |  | 8202221657#Perbaikan Box Cooler 100-E14B | RU2-HSC | 100-E-14B/00 | 50 | CRTD NMAT PRC | 2MR | D12/25/B6/RT-D2H | 6000000 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365865 | 8202240004 |  | 8202221656#25_Penggantian 154_TI606B | RU4-RFCUTL | 154TT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365864 | 8202240003 |  | 8202221655#25_Penggantian 154_TI602C | RU4-RFCUTL | 154TT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-12 | 2102362897 | 8202233741 |  | 8202221654#Pengambilan Material Con. tub | RU6-HSC | 31-A-102/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365863 | 8202240001 |  | 8202221653#25_Penggantian 154_TI602A | RU4-RFCUTL | 154TT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-23 | 2026-05-22 | 2102360600 | 8202237336 |  | 8202221649#Perbaikan Level Distillate LI | RU5-UTL | 37-3J-JB-01/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 23573920 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-23 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365647 | 8202240000 |  | 8202221648#25_[CR] Perbaikan lipseal LP | RU4-UTL | 051G103T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA3-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-02 | 2102362157 | 8202234027 |  | 8202221646#Emergency Vent 34-PSV-404 | RU6-POC | 34-A-102-T-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-02-05 | 2102364382 | 8202238635 |  | 8202221645#TGH15_23 TSA AC Central Non P | RU4-UTL | TEMP-U50/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 195746000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362894 | 8202233942 |  | 8202221644#Material COA 32-V-106 A pada | RU6-HSC | 32-V-106A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-30 | 2102361572 | 8202234014 |  | 8202221642#indikasi kerusakan 38-PSH-102 | RU6-POC | 38-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-18 | 2025-12-05 | 2026-09-11 | 2102362892 | 8202233215 |  | 8202221639#Perbaikan Bocoran Pompa 23-P- | RU6-HSC | 23-P-101A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 150191 | 0 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362813 | 8202233277 |  | 8202221634#Perbaikan 35-P-102B | RU6-POC | 35-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 2304 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-19 | 2026-02-02 | 2026-02-02 | 2102352200 | 8202234172 |  | 8202221623#101-P12A SUMP PUMP TIDAK DAPA | RU2S-KIL | 101-P-12A/00 | 60 | REL CSER MANC PRC SETC | 2RS | D12/26/B6/RTZ-C3H | 3667501 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358325 | 8202234344 |  | 8202221622#Perbaikan 2-PM-02 B | RU7-NHT | 2-PM-02B/00 | 60 | REL CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365661 | 8202239998 |  | 8202221617#25_[CR] Coupling Speed Variat | RU4-LOC1 | 24S1B-G/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365660 | 8202239997 |  | 8202221616#25_[CR] Shaft & Bearing 24E23 | RU4-LOC1 | 24E23K-B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 15715304 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352966 | 8202234797 |  | 8202221606#Penggantian Hydraulic Swing A | RU3-UTL | UTL-DCS/00 | 60 | REL NMAT PRC SETC | 3MR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366005 | 8202239996 |  | 8202221605#25_Penggantian 6 Assy SOV & S | RU4-UTL | 56DR201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 13 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366004 | 8202239995 |  | 8202221604#25_Replacement 520TE201A & 52 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366003 | 8202239993 |  | 8202221603#25_Replacement 520TE402 Inlet |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366002 | 8202239989 |  | 8202221602#25_Replacement 520TE203A/B Te |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366105 | 8202239987 |  | 8202221601#25_Perbaikan Air Register 520 | RU4-UTL | 520HY701A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 71990000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366104 | 8202239986 |  | 8202221600#25_Perbaikan Air Register 520 | RU4-UTL | 520P601CM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 71990000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352210 | 8202234170 |  | 8202221578#Mechanical Seal Leak 101-P-6C | RU2S-KIL | 101-P-6C/00 | 50 | REL NMAT PRC SETC | 2RS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-06-05 | 1102328596 | 8202237320 |  | 8202221577#Perbaikan Peralatan OPGD FGDS |  |  | 60 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 110616301 | 0 | HSSE |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-14 | 2102362659 | 8202237761 |  | 8202221573#LTSA Scaffolding 2024-2026 Ta | RU6-UTL | 052-B-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-07 | 2026-02-05 | 2026-02-05 |  | 8202238523 |  | 8202221572#Total Replacement Box Cooler | RU2-HSC | 100-E-14E/00 | 60 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-08-04 | 2102362817 | 8202233229 |  | 8202221567#Perbaikan Bearing Motor 58-K- | RU6-UTL | 58-K-101A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2250 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365536 | 8202239985 |  | 8202221565#25_Pengadaan steam hose 3/4'' |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 54275000 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2027-01-18 | 2102362812 | 8202233969 |  | 8202221561#LTSA Service Engine FireTruck | RU6-LK/KK | 66-FT-01/00 | 50 | CLSD CSER NCMP NMAT PRC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA4-ROT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-09-23 | 2102361967 | 8202233399 |  | 8202221554#Perbaikan 12-LT-222 | RU6-DHC | 12-LT-222/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/XX/B6/RT-C2NH | 0 | 0 | MA2-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-03-17 | 1102329033 | 8202237302 |  | 8202221551#Perbaikan Level Transmitter 2 | RU5-D&W | 201-LT-014/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 28001152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360646 | 8202237301 |  | 8202221550#Perbaikan UPS Fire Station La |  | HMIFGDS/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | HSSE |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-15 | 2102362186 | 8202232756 |  | 8202221547#Program penyehatan EWTP perba | RU6-ITP | 63-P-402B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 27720 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352907 | 8202234848 |  | 8202221545#Pengadaan Material Level glas | RU3-CDL | E-14-015/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363582 | 8202232226 |  | 8202221544#Pengadaan material | RU2-HCC | 212-PT-14B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363603 | 8202232300 |  | 8202221543#Perbaikan jangka pendek | RU2-HCC | 212-PT-14B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/XX/B6/RT-D2NH | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 |  | 8202232566 |  | 8202221542#Measurement Tools REIE | RU2-UTL |  | 50 | CRTD NMAT PRC | 2MR | D12/10/B6/RT1-STMNH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-14 |  | 8202232721 | 8202233626 | 8202221540#SWO Solenoid STG-D | RU6-UTL | 51-G-101D-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 16500 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102361690 | 8202233626 |  | 8202221539#Penggantian Instrumentasi STG | RU6-UTL | 51-G-101D-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 7920 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-10 | 2026-06-10 | 2102360647 | 8202237300 |  | 8202221537#Perbaikan line flushing Pompa | RU5-UTL | P-4-WTP-I/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-02-03 | 2026-05-07 | 2025-12-08 | 2026-12-29 | 2102360948 | 8202237499 |  | 8202221535#RKA25L_Coating 32T-1 dan 32T- | RU4-TRML | 32T1/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102360946 | 8202237497 |  | 8202221534#RKA25L_Coating 32T-104 | RU4-TRML | 32T104/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 1279000000 | 1023200000 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102362758 | 8202233987 |  | 8202221533#lATERIAL CLEANING 11-V-101 AB | RU6-HSC | 11-V-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 739435 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362702 | 8202233810 |  | 8202221531#Pengadaan gun burner FO 52-B- | RU6-UTL | 52-B-101F/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-05-05 | 2102362695 | 8202233902 |  | 8202221508#Mtl Panel Control Emg LO STG | RU6-UTL | 51-G-101CD-BCP/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1680 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K301 | 2026-02-05 | 2026-02-13 | 2026-02-06 | 2026-02-06 | 2102352968 | 8202238664 |  | 8202221507#Bocoran windows M-2301 | RU3-PP | 23-M-2301/00 | 50 | CRTD NMAT PRC | 3MR |  | 600000000 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102358381 | 8202234343 |  | 8202221502#Perbaikan Mechseal Pompa 1-P- | RU7-CDU | 1-P-12A/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/25/B6/RT-1-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362754 | 8202232836 |  | 8202221501#Perbaikan Turbine 052-B-101B- | RU6-UTL | 052-B-101B-K-101/0 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 | 2102362451 | 8202232851 |  | 8202221500#Perbaikan Transmitter 11-LT-4 | RU6-HSC | 11-P-101A/01 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-14 | 2102362453 | 8202237759 |  | 8202221498#LTSA Piping Work Tahap 9 Area | RU6-UTL | 53-Z-202/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-07-14 | 2102362691 | 8202237757 |  | 8202221497#LTSA Piping Work Tahap 4 Area | RU6-DHC | 14-V-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-03-10 | 2026-02-02 | 2026-06-12 | 2102362345 | 8202233444 |  | 8202221494#Penggantian valve bypass 052- | RU6-UTL | 052-B-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 71470680 | 0 | MA4-STA |  | HARSARIZANO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-27 | 2102362655 | 8202233029 |  | 8202221492#Perbaikan Motor 57-E-401L | RU6-DHC | 57-E-401L-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360970 | 8202234372 |  | 8202221487#Pengadaan Trafo Ignitor 101F5 | RU4-RFCC | 101F502/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360971 | 8202234373 |  | 8202221486#Pengadaan Trafo Ignitor 101F5 | RU4-RFCC | 101F501/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA6-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 | 2102361127 | 8202236627 |  | 8202221485#Penggantian Motor 052E101-M2M | RU4-UTL | 052E101M2/00 | 50 WENG | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-05-13 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360717 | 8202237299 |  | 8202221484#MAT.PERB.LINE 21-P33-6" L.NAP | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 17180286 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202236286 |  | 8202221483#DAM_Pengadaan JB & Modif Cabl |  |  | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K701 | 2026-02-02 | 2026-04-16 | 2026-02-02 | 2026-08-10 |  | 8202234342 | 8202234335 | 8202221475#PERBAIKAN 1-P-05 B | RU7-CDU | 1-P-05B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-03 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352909 | 8202234782 |  | 8202221474#Penggantian LV20273A Valve BW | RU3-UTL | LV-20273A/00 | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363730 | 8202232528 |  | 8202221471#Membrane Coupling 211-P-17A/0 | RU2-HCC | 211-P-17A/01 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-06-17 | 2026-02-03 | 2026-10-22 |  | 8202237755 |  | 8202221464#Penggantian Fire Water Line 6 | RU6-UTL | 66-FW-8102-MS20/00 | 60 | TECO GMCO GMPS NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 749500000 | 749500000 | MA4-STA |  | ZAMZAMKHALID |  | 2026-02-11 | PT02 |  | 3 | 2026-06-17 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-14 | 2026-01-02 | 2026-01-02 |  | 8202232241 | 8202238699 | 8202221461#LAMPU EMERGENCY AREA PROSES | RU2-HSC | 100-H-1/00 | 50 | REL MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA2-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-08 | 2026-02-02 | 2026-02-02 | 2102362607 | 8202232731 |  | 8202221455#Superior Order PM Stationary | RU6-DHC | 12-R-101/00 | 01 | CLSD CSER NCMP NMAT PRC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | ZAMZAMKHALID |  |  | PT02 |  | 2 | 2026-06-08 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 | 2102358944 | 8202237174 |  | 8202221452#Perbaikan Pondasi Evaporator |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360745 | 8202237293 |  | 8202221451#Ganti Saluran pompa chemical |  |  | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 2647996 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-07-22 | 2102360295 | 8202237285 |  | 8202221450#Ganti Saluran soda ke tangki |  |  | 50 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 1618138 | 0 | MA1-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2027-01-28 | 2102363339 | 8202238211 |  | 8202221448#Notifikasi Pembuatan Catwalk | RU6-ITP | 42-T-301A/00 | 50 | CLSD CSER NCMP NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 1 | 0 | MA4-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360841 | 8202237205 |  | 8202221447#Perb. Sal disch pompa degasse |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-05 | 2102359912 | 8202237217 |  | 8202221446#Perb. Bypass Block valve 60 b |  |  | 50 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-P1NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360842 | 8202237242 |  | 8202221445#Perb line Buangan tengah poli |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102358808 | 8202237269 |  | 8202221444#Ganti Sealing ejektor no.1 ST |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-P2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360911 | 8202237221 |  | 8202221442#Perb Line SCW from CWI to PP- |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SCNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-02 | 2026-01-02 | 2026-12-31 | 2102360899 | 8202237228 |  | 8202221441#Perb Line Bypass CWI to PP-1 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-P2NH | 0 | 0 | MA1-STA |  | RESTUANDRI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102359577 | 8202237250 |  | 8202221440#Ganti Valve Ejektor STG 2.4 | RU5-UTL | TG2-PP2-2RF04-S/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-P2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102359923 | 8202237249 |  | 8202221439#GantiTalang Air Clarifier 1,2 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-W2NH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 | 2102359579 | 8202237295 |  | 8202221438#Ganti Level Glass Deaerator 5 | RU5-UTL | HHP-5-V-1/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-03-25 | 2102360122 | 8202237297 |  | 8202221437#Flange Pendingin Pompa Blowdo |  | E-37-02/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 172936 | 0 | MA1-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102359871 | 8202237187 |  | 8202221436#Perbaikan Final Condensor & E |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SWNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102362509 | 8202232867 |  | 8202221434#Perbaikan Tandem Seal Outboar | RU6-ITP | 42-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31416 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238210 | 8202235367 | 8202221430#Tag 4 Kontr.Vol Steam Leak No |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358383 | 8202234341 |  | 8202221428#Pemasangan pompa Chemical di | RU7-OFF | 5-P-19A/00 | 01 | CRTD CSER MACM PRC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-29 | 2102362455 | 8202233092 |  | 8202221427#Perbaikan Mech Seal Pompa 42- | RU6-ITP | 42-P-501C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31680 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-07-13 | 2102358931 | 8202237155 |  | 8202221423#Baterai relay proteksi FDFMot | RU5-UTL | 2HT-28/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K301 | 2026-02-02 | 2026-04-22 | 2026-04-22 | 2026-12-31 | 2102352967 | 8202234710 |  | 8202221420#Lvl switch MA-2302&speed sens | RU3-PP | 23-LT-2320-1/00 | 60 | REL CSER GMPS MSPT PRC SETC | 3IR | D13/26/B6/RT-2-D2H | 603288000 | 603288000 | MA2-INT |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-22 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358384 | 8202234340 |  | 8202221419#Penggantian Flexibel Joint 5- |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-11 | 2102362501 | 8202234009 |  | 8202221418#Indikasi kerusakan valve inle | RU6-POC | 34-R-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2025-12-18 | 2102362253 | 8202234033 |  | 8202221413#Cons Material Electrical NATA | RU6-UTL | 01-PSW2-01A-006/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 116 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102361642 | 8202233090 |  | 8202221404#Perbaikan Mechseak Outboard 4 | RU6-ITP | 42-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358385 | 8202234339 |  | 8202221383#Penggantian bearing motor HVA |  |  | 60 | REL MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 2156000 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-09 |  | 8202234001 |  | 8202221379#Kebutuhan Material Butterfly | RU6-ITP | 63-P-202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 55440 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358386 | 8202234338 |  | 8202221378#Pemasangan Tubing dii 5-P-03 |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358476 | 8202234337 |  | 8202221377#Instal tubing suction/dischar |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-06 | 2102363132 | 8202233885 |  | 8202221372#Overhoul Ex Motor 12-K-501-P2 | RU6-DHC | 12-K-501A-P2-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 20000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363620 | 8202232286 |  | 8202221367#Perbaikan Kerangan 510-P-1D | RU2-UTL | 510-P-01D/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102359240 | 8202237127 |  | 8202221364#Perbaikan Sol in out serv. Bo | RU5-UTL | B1-1SV-605/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102360884 | 8202237126 |  | 8202221363#Req Perbaikan Valve Venting P | RU5-TBL | 22-716B/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 14492700 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-06-29 | 2102360860 | 8202237125 |  | 8202221362#Sensor RPM BFW 12 rusak | RU5-UTL | HHP-6-INST/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 |  | 8202237128 |  | 8202221360#Penggantian Flow Indikator 20 | RU5-D&W | INT-CDU-V/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 23572000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 |  | 8202237129 |  | 8202221359#Penggantian 231-FI-002 | RU5-D&W | INT-CDU-V/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 23572000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-27 | 2102362315 | 8202233697 |  | 8202221358#Penggantian Bearing Motor 16K | RU6-RCC | 16-K-102-P1C-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-22 | 2026-01-01 | 2026-12-31 | 2102352982 | 8202234482 |  | 8202221356#Pergerakan XCV 2234 A Lambat | RU3-PP | 23-XCV-2234A/00 | 60 | REL NTUP PRC SETC | 3IR | D13/26/B6/NR-2-D2H | 0 | 0 | MA2-INT |  | ALEPDALITAN |  | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 004
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365958 | 8202239982 |  | 8202221355#25_Penggantian Sensor Speed 1 | RU4-RFCUTL | 156K502B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-03 | 2026-01-01 | 2026-01-01 |  | 8202235423 | 8202235464 | 8202221353#Kontr.Vol Cleaning Tangki Min |  |  | 60 | REL CNF PRT NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RAMADENY | 2026-06-08 | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202235438 | 8202235464 | 8202221351#Kontr.Vol Cleaning Tangki Min |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-06-05 | 1102327684 | 8202237122 |  | 8202221350#Perbaikan Cable Gland Convert | RU5-UTL | B5-PK-203/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 4800000 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102353072 | 8202234484 |  | 8202221347#perbaikan ZV2522 C, ZV2522 D, | RU3-PP | 23-SOV-2552/00 | 60 | REL CSER MACM PRC SETC | 3IR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-06-10 | 2026-02-02 | 2026-02-02 | 2102353225 | 8202234421 |  | 8202221346#Potensio Controller Error | RU3-PP | 23-ZB-2601Z1/00 | 60 | TECO CNF CSER MACM PRC SETC | 3RR |  | 0 | 0 | MA2-INT |  | SAPBATCH | 2026-06-10 | 2026-02-07 | PT02 |  | 3 | 2026-06-10 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102362317 | 8202232804 |  | 8202221345#Permanent Repair Pompa 42-P-3 | RU6-ITP | 42-P-304B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366012 | 8202239980 |  | 8202221342#24_Penggantian Transmitter 51 | RU4-UTL | 510PIT815/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366022 | 8202239979 |  | 8202221341#24_Penggantian Transmitter 52 | RU4-UTL | 52FT002/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 21500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366011 | 8202239978 |  | 8202221340#24_Penggantian Transmitter 52 | RU4-UTL | 52FT304/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 22000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102363807 | 8202238113 |  | 8202221339#Perbaikan Box Cooler 100-E-14 | RU2-HSC | 100-E-14E/00 | 50 | CRTD NMAT PRC | 2MR | D12/10/B6/RT1-100NH | 6000000 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365962 | 8202239977 |  | 8202221338#24_Penggantian Positioner 154 | RU4-RFCUTL | 154LV605C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 20000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365961 | 8202239976 |  | 8202221337#24_Penggantian Reg Positioner | RU4-RFCUTL | 154LV601A/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 7500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102359636 | 8202237116 |  | 8202221336#Perbaikan 201-FI-025 | RU5-D&W | 201-FCV-034/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 11786000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360894 | 8202237121 |  | 8202221333#Penggantian Lampu Rp "R" OM | RU5-TBL | PLANT-21-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 37236628 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-10 | 2102361722 | 8202233137 |  | 8202221331#Perbaikan kerangan line venti | RU6-DHC | 12-P-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363615 | 8202232345 |  | 8202221330#Cleaning Filter 211/212 F-1A/ | RU2-HCC | 211-F-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102362787 | 8202232968 |  | 8202221324#Perbaikan Pompa 32-P-111A | RU6-HSC | 32-P-111A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-31 | 2025-12-31 | 2102360658 | 8202237093 |  | 8202221322#KT-3-02A Refurbish Diaphragm | RU5-E15112 | KT-3-02A/00 | 01 | CRTD NMAT PRC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-31 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364225 | 8202235330 |  | 8202221317#Perbaikan Valve Cooling Water |  |  | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202235093 |  | 8202221316#RKAP25_Perbaikan Isolasi Pipa | RU4-RFCUTL |  | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-01 | 2102360859 | 8202237095 |  | 8202221315#Ganti Valve pendingin Oilcool | RU5-UTL | TG-5A-PP1/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 7310456 | 0 | MA1-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-10-15 | 2102365701 | 8202239975 |  | 8202221305#25_Perbaikan CV BFW 520B601 | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-09 | 2102362107 | 8202233806 |  | 8202221302#Pengadaan kopling assy 42-P10 | RU6-ITP | 42-P-107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 32472 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-29 | 2025-12-29 | 2102358942 | 8202237086 |  | 8202221300#Perb. Kabel lampu Tangki O-1 | RU5-TBL | PLANT-20-LIS/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 23232600 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363705 | 8202232470 |  | 8202221299#Perbaikan 220 PM-4A | RU2-HOC | 220-PM-4A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 453119 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102353075 | 8202238533 |  | 8202221298#Perbaikan Kantor CD&L dalam K |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-08-27 | 2102361636 | 8202236620 |  | 8202221292#SWO Pemb. LTSA UV Spectro. Te | RU6-LAB | LABORATORIUM/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-02-02 |  | 8202233943 | 8202232734 | 8202221291#Material Cleaning 51-G-101 | RU6-UTL | 51-G-101D-E1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 2723951 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-02-02 | 2026-02-02 | 2102361762 | 8202232734 |  | 8202221290#Superior Order 51-G-101 | RU6-UTL | 51-G-101D-E1/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-15 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-05-04 | 2102359408 | 8202237084 |  | 8202221289#UPS Overhead Crane WS Manufac |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/24/B6/RT-C2H | 7000000 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102360888 | 8202237085 |  | 8202221288#MV CB Feeder to SS-40 | RU5-UTL | 41-R-SS-38-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 1197000000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102362994 | 8202233350 |  | 8202221287#Perbaikan 15-K-104 | RU6-RCC | 15-K-104/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-10 | 2102362003 | 8202233700 |  | 8202221286#Penggantian bearing motor 059 | RU6-UTL | 059-A-101B-K3/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 836296 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2025-12-05 | 2026-01-21 |  | 8202238206 |  | 8202221284#LTSA O2 Analyzer Termin 6 (WO | RU6-UTL | 52-AT-201A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-26 | 2102361875 | 8202236549 |  | 8202221283#Unit Price Repair Built Up Ta | RU6-RCC | 20-R-101B/00 | 60 | REL NMAT PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-11-04 |  | 8202236845 | 8202233978 | 8202221282#PM 4 - LTSA FGDS General Moni | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-02-10 | 2102362879 | 8202232953 |  | 8202221280#Perbaikan Pompa 42-P-503E | RU6-ITP | 42-P-503E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 32736 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102353071 | 8202235536 |  | 8202221279#kerangan drain 4"300 26-T-002 |  |  | 60 | REL CSER GMPS MACM PRC SETC | 3MR |  | 0 | 9088000 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-04 | 2102363966 | 8202238019 |  | 8202221278#Perbaikan Pagar Fire Ground | RU2-PK |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 638050000 | 0 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-06-19 | 2026-02-02 | 2027-01-22 | 2102362001 | 8202233283 |  | 8202221276#Perbaikan 34-A-101-P-101B | RU6-POC | 34-A-101-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | PANDUA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352205 | 8202234169 |  | 8202221275#Review Kondisi Short Bolting | RU2S-KIL | 101-T-1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102363806 | 8202238112 |  | 8202221274#Perbaikan 100-E-14-E | RU2-HSC | 100-E-14E/00 | 50 | CRTD NMAT PRC | 2MR | D12/24/B6/NR-D2H | 6000000 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352286 | 8202234168 |  | 8202221272#Pengadaan Lube Oil ServoMotor | RU2S-KIL | 900-06GE-5-GT/00 | 50 | REL MACM PRC SETC | 2MS | D12/25/B6/NRZ-C3H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362215 | 8202234088 |  | 8202221270#15P102A Pompa vibrasi tinggi | RU6-RCC | 15-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 6912 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363596 | 8202232276 |  | 8202221269#Pengadaan HCGB 170 CT-52 | RU2-HOC | 170-CT-52/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-04-27 | 2102362938 | 8202233811 |  | 8202221268#Pengadaan Governor Spare 16-K | RU6-RCC | 16-K-101-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-04-27 | 2102362869 | 8202233812 |  | 8202221267#Pengadaan Governoor Spare 15- | RU6-RCC | 15-K-101-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-03-12 | 2026-02-02 | 2026-02-02 | 2102363662 | 8202232401 |  | 8202221263#Perbaikan 940-PT-1B | RU2-UTL | 940-PT-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 188791 | 0 | MA3-ROT |  | AZIZFATONI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102361565 | 8202233765 |  | 8202221255#Pengadaan Pompa 12-P-512 | RU6-DHC | 12-P-512/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-09 | 2025-12-09 | 2102363656 | 8202232388 |  | 8202221250# Pengadaan lampu penerangan j | RU2-ITP | LI-TK-101/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102361688 | 8202232959 |  | 8202221246#Perbaikan Pompa 42-P-107B | RU6-ITP | 42-P-107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102358807 | 8202237074 |  | 8202221244#Penggantian LCS (swict On/Off | RU5-TBL | P-16RP-A-HITAM/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 10908579 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102360582 | 8202237072 |  | 8202221243#Perbaikan Tombol Stop Gangway | RU5-TBL | 22-GANGWAY-5BC/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/24/B6/RT-C2H | 1 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360744 | 8202237069 |  | 8202221234#Perbaikan sub standard electr | RU5-E15112 | C-3-01A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 950430280 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235314 | 8202235331 | 8202221229#Kontr.Vol Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358388 | 8202234336 |  | 8202221223#Perbaikan 6-PM-106A |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361104 | 8202236502 |  | 8202221222#D24_Control valve area HVU II |  | 021FV012/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2025-12-11 | 2102361962 | 8202233422 |  | 8202221214#Perbaikan 052-ZSL-913C | RU6-UTL | 052-B-101C/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 46 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365947 | 8202239974 |  | 8202221211#24_Perbaikan Transmiter 104 P | RU4-RFCC | 104C501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-09-23 | 2102363133 | 8202233730 |  | 8202221210#Penggantian 052-PSHH-909C | RU6-UTL | 052-B-101C/00 | 01 | CLSD NCMP NMAT PRC | 6IR | D16/24/B6/RT-C2H | 19883 | 0 | MA4-INT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-24 | 2026-03-30 |  | 8202233428 |  | 8202221209#Perb. valve 22-XV-6484 + MIV | RU6-DHC | 22-XV-6484/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102358935 | 8202237051 |  | 8202221202#Perbaikan Level LIC 203 SWD 2 | RU5-UTL | 37A-LICSA-203/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 21948149 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102360816 | 8202237064 |  | 8202221201#Perb. lampu bundwall T901&T90 | RU5-TBL | PLANT-20-LIS/00 | 50 | REL CSER MANC PRC SETC | 5ER | D15/24/B6/RT-C2H | 145648400 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102360168 | 8202237057 |  | 8202221200#Perb.Pergantin lampu jalan A3 | RU5-TBL | PLANT-20-LIS/00 | 60 | REL MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 39444750 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-04 | 2102363811 | 8202238133 |  | 8202221198#Perbaikan Rumah Pompa Area WP | RU2-UTL | 510-P-01D/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 950000000 | 950000000 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2102358939 | 8202237053 |  | 8202221197#Perbaikan Lampu Penerangan Ar | RU5-D&W | CDU-V-LIS/00 | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 125962810 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102358603 | 8202238003 |  | 8202221194#Konsultan Renov Gedung Main C |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/NR-1-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-24 |  | 8202232725 | 8202232818 | 8202221192#SWO Penggantian pipa outlet 4 | RU6-ITP | 42-T-101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 17160 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 |  | 8202238208 |  | 8202221191#Resertifikasi PSV Area HSC | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1000000 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-06-22 | 2102362367 | 8202232929 |  | 8202221189#Perbaikan Positioner 10-PV-00 | RU6-DHC | 10-PV-001A/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1920 | 21473227 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-28 | 2026-03-11 | 2102362926 | 8202233537 |  | 8202221188#Penggantian Power Supply OS14 | RU6-RCC | OS-14/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-05-08 |  | 8202233307 |  | 8202221186#Perbaikan 22-HS-803 | RU6-DHC | 22-F-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-28 |  | 8202237028 |  | 8202221183#Pemasangan Pipa Deep Well |  |  | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-05-25 | 2102360749 | 8202237011 |  | 8202221181#Perb. Line Outlet Final Cond. | RU5-UTL | EA20-218-CW4KIL/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-22 |  | 8202233807 |  | 8202221179#Pengadaan Hub Coupling 53-P-1 | RU6-UTL | 53-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 33660 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-03-17 | 2102360277 | 8202237012 |  | 8202221178#Penggantian Thermocouple 201- | RU5-D&W | F-201-01-INST/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 5022690 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-03-17 | 1102328004 | 8202237010 |  | 8202221177#Perbaikan CCR Valve 05-KV-553 | RU5-E15111 | 05-KV-553/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 205771152 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-06 | 2025-11-06 | 2102363651 | 8202232382 |  | 8202221174#Perbaikan Bleed Valve pada Me | RU2-ITP | 610-MOV-1104-A1/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-12 | 2025-12-29 | 2102358949 | 8202236998 |  | 8202221171#Pemindahan Switch Start/Stop | RU5-TBL | P-20-OC-RP-A/00 | 60 | REL MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 15040128 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-13 | 2025-12-29 | 2025-12-29 | 2102359060 | 8202237008 |  | 8202221169#Pemasangan power gudang OM | RU5-TBL | PLANT-22-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 420025 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-12 | 2025-12-12 | 2026-01-02 | 2102359347 | 8202237009 |  | 8202221168# Perb Motor Mixer 101-MI-01B2 | RU5-TBL | 101-MI-1B2/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 1987366 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 005
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-03-26 |  | 8202237753 |  | 8202221167#LTSA - PM 2 PT ISSI | RU6-LAB | LABORATORIUM/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365567 | 8202239972 |  | 8202221165#25_RKAP 2025_Penyehatan Aerat | LOC1-UP4 | 47S505-M1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-11-04 |  | 8202236664 |  | 8202221158#SWO Pemb. LTSA AC Termin 9 | RU6-RCC | SHELTER-PEM1/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2102358802 | 8202236995 |  | 8202221157#Perbaikan Motor sootblower no | RU5-UTL | 1NV00DOO1-S1/00 | 60 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 273091 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-06-03 | 2026-06-05 | 2102360554 | 8202236996 |  | 8202221155#Perbaikan Motor pompa 1 regen | RU5-UTL | DM-5-P02A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 259749 | 0 | MA1-LIS |  | SAPBATCH | 2025-12-28 | 2026-02-11 | PT02 |  | 3 | 2025-12-27 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-08-10 | 2102363073 | 8202233641 |  | 8202221154#Penggantian flange 14" HPS he | RU6-UTL | 51-G-101C-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 15840 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102359570 | 8202237007 |  | 8202221153#Pembelian Motor Pompa Chemica |  |  | 50 | REL CSER NMAT PRC SETC | 5ER | D15/24/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K202 | 2026-02-02 | 2026-03-03 | 2026-01-02 | 2026-12-30 | 2102352218 | 8202234167 |  | 8202221145#LTSA PIPING SYSTEM KILANG SPK | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/RTZ-D3H | 1000000000 | 0 | MAS-ME2 |  | JUNAIDIT |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-03-04 | 2102361583 | 8202233358 |  | 8202221142#Perbaikan 15-A-107 | RU6-RCC | 15-A-107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 640 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363782 | 8202232665 |  | 8202221141#Pengadaan mixer green dyes ar | RU2-ITP | 945-P-1A/00 | 50 | REL GMPS MACM PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 525000000 | MA4-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-11 | 2026-06-09 | 2026-11-27 | 2102361682 | 8202233161 |  | 8202221138#Perbaikan Gearbox Ex-Run 56-K | RU6-UTL | 56-K-101F/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 430773614 | 430594336 | MA4-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-22 | 2025-12-05 | 2026-06-02 | 2102361587 | 8202238522 |  | 8202221133#Penambahan Rotork Master Stat | RU6-ITP | 42-T-301A/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 24137000 | 0 | MA4-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202234902 | 8202235173 | 8202221131#KV Sipil Area SG 2024-2025 |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | 8202235102 | 8202235125 | 8202221129#KV Isolasi Area CDGP OM Plaju | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2027-01-25 | 2102362135 | 8202236847 |  | 8202221127#PM 4 - LTSA Asphaltene Analyz | RU6-LAB | LABORATORIUM/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-04 | 2026-08-19 |  | 8202236980 |  | 8202221126#PERBAIKAN XCV 031 & 041 PLANT | RU5-E15112 | 25-XCV-033/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 30000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233189 |  | 8202221125#perbaikan control valve PSA 2 | RU6-DHC | 22-XV-6473/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-08 | 2026-04-30 | 2102361844 | 8202233473 |  | 8202221123#Penggantian trafo Sootblower | RU6-UTL | 52-B-101A/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/25/B6/RT-C2H | 1350 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363631 | 8202232291 |  | 8202221121#Perbaikan kebocoran 925-V-60 | RU2-UTL | 925-V-60/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-11 | 2102362704 | 8202232878 |  | 8202221119#Perbaikan solenoid valve 12-J | RU6-DHC | 12-J-501A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-04-30 | 2102362099 | 8202233672 |  | 8202221116#Penggantian control ignitor 5 | RU6-UTL | 52-B-101E/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1350 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102361501 | 8202233443 |  | 8202221115#Penggantian valve bypass 052- | RU6-UTL | 052-B-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C1H | 31020 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-04-30 | 2102362093 | 8202233673 |  | 8202221114#Penggantian control ignitor 5 | RU6-UTL | 52-B-101D/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1350 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2025-12-08 | 2026-04-30 | 2102362043 | 8202233675 |  | 8202221113#Penggantian control ignitor 5 | RU6-UTL | 52-B-101B/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1350 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-04-30 | 2102362046 | 8202233674 |  | 8202221112#Penggantian control ignitor 5 | RU6-UTL | 52-B-101C/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1350 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-04-30 | 2102362090 | 8202233676 |  | 8202221111#Penggantian control ignitor 5 | RU6-UTL | 52-B-101A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1350 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-24 |  | 8202233308 |  | 8202221110#Perbaikan 22-FT-554 | RU6-DHC | 22-A-105/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-24 | 2102364222 | 8202233309 |  | 8202221109#Perbaikan 22- FT-551 | RU6-DHC | 22-A-105/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-01-22 |  | 8202233188 |  | 8202221106#perbaikan control valve PSA 2 | RU6-DHC | 22-XV-6477/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 384 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-05-11 |  | 8202233249 |  | 8202221105#Perbaikan 62-PV-104B | RU6-UTL | 62-PV-104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 75095 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-24 | 2102363131 | 8202233714 |  | 8202221102#Penggantian Air Filter 059-A- | RU6-UTL | 059-A-101A-K1/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 33924 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-25 | 2102362707 | 8202233648 |  | 8202221100#Penggantian filter LO 059-A-1 | RU6-UTL | 059-A-101A-K3/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 34056 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-03-12 |  | 8202236588 | 8202232191 | 8202221083#Tenaga Ast Supporting EIIE Pe | RU6-RCC | 14B-PMC2-01A-00/00 | 50 | CLSD CSER NCMP NMAT PRC | 6ER | D16/24/B6/RT-C2H | 1 | 0 | MA1-LIS |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202234997 | 8202234973 | 8202221076#KV Pemasangan Hose Handling 2 |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234016 | 8202234015 | 8202221075#Indikasi bocoran pada flange | RU6-POC | 37-XV-073A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-20 | 2102361621 | 8202233518 |  | 8202221071#Penggantian Push Button Area | RU6-ITP | 63-P-301A/00 | 60 | REL MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 3031716 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-02-02 | 2102358389 | 8202234335 |  | 8202221069#Cek dan perbaikan 1-P-05 B |  |  | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D1H | 0 | 0 | MA-STA |  | SYAIPULANUAR | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102362493 | 8202232902 |  | 8202221068#Perbaikan Purifier 51-G-101D- | RU6-UTL | 51-G-101D-S1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358410 | 8202234334 |  | 8202221067#Penggantian PI di 2-K-01/02 |  |  | 50 | CRTD CSER MACM PRC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358411 | 8202234333 |  | 8202221066#Penggantian PI di 3-P-01 A/B |  |  | 50 | CRTD CSER MACM PRC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-08-07 | 2102359658 | 8202236972 |  | 8202221064#Perbaikan selenoid 05-XV-755 |  |  | 50 | REL CSER MSPT PRC SETC | 5IR | D15/26/B6/RT-C2H | 319074999 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102360723 | 8202236957 |  | 8202221063#Perbaikan TI & PI Area HCC | RU5-E15112 |  | 60 | REL CSER MSPT PRC SETC | 5IR | D15/24/B6/RT-C2H | 43232000 | 0 | MA3-INT |  | HASRUDDINA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359825 | 8202236974 |  | 8202221062#Perb Transmitter 3B-FT-378 2- | RU5-E15112 | 03B-FR-378-411/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 32922224 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358412 | 8202234332 |  | 8202221061#Penggantian bearing motor 2-P |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358413 | 8202234331 |  | 8202221060#Pasang PI dan temperatur indi |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363628 | 8202232248 |  | 8202221044#Belt Putus 110-EF-13E, 110-EF | RU2-HOC | 110-EF-13E/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363746 | 8202232558 |  | 8202221043#penggantian filter catridge | RU2-HSC | 301-C-1/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363708 | 8202232483 |  | 8202221042#Perbaikan 170 CT-52 | RU2-HOC | 170-CT-52/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363722 | 8202232504 |  | 8202221039#Perbaikan 110 P-15A | RU2-HOC | 110-P-15A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 113640413 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-08-26 | 2102359743 | 8202236945 |  | 8202221038#Penggantian Temp Sensor 3B-TI | RU5-E15112 | F-3-01B-INST/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/24/B6/RT-C2H | 9944000 | 0 | MA3-INT |  | HASRUDDINA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 1102328803 | 8202236946 |  | 8202221037#Penggantian Level Transmitter | RU5-E15112 | 03-LT-031/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 10974075 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 1102328384 | 8202236943 |  | 8202221036#Perbaikan Sensor Temp Bearing | RU5-TBL | 101-GT-1A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 117000000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363743 | 8202232554 |  | 8202221034#Penggantian gasket 12 inch 15 | RU2-ITP | 509-PSV-1000/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361007 | 8202235130 |  | 8202221033#RKAP2025_Pek. Kontrak PSA MCC | RU4-RFCUTL | 30BD12EE0102A/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA5-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-09 | 2102363076 | 8202233903 |  | 8202221032#Motor noise dan vibrasi 19-P- | RU6-RCC | 19-P-109A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363721 | 8202232498 |  | 8202221023#Perbaikan 140 E-20 | RU2-HOC | 140-E-20/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-03-12 | 2102362995 | 8202237750 |  | 8202221021#LTSA Cleaning 15E104/106 Taha | RU6-RCC | 15-E-104A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/24/B6/RT-C3H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 | 2102362998 | 8202232910 |  | 8202221020#Perbaikan pressure gauge area | RU6-DHC | 12-A-501/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102358414 | 8202234330 |  | 8202221018#Perbaikan mechseal 3-P-01 A | RU7-CRU | 3-P-01A/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-03 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-11-04 | 2102361595 | 8202233983 |  | 8202221017#LTSA 5 Unit Analyzer | RU6-LAB | LABORATORIUM/00 | 50 | CLSD CSER NCMP NMAT PRC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-11-04 |  | 8202236628 | 8202233976 | 8202221015#SWO Pemb. LTSA O2 Ametek Term | RU6-RCC | 15-AT-002/00 | 60 | CLSD NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-11-04 | 2102363075 | 8202233976 |  | 8202221014#LTSA O2 Analyzer Ametek | RU6-RCC | 15-AT-002/00 | 60 | CLSD CSER NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-02-02 | 2026-02-02 | 2102363134 | 8202232191 |  | 8202221013#Tenaga Assistant Engineer Sup | RU6-RCC | 14B-PMC2-01A-00/00 | 50 | CLSD CSER NCMP NMAT PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360802 | 8202236939 |  | 8202220966#MAT.PERB.LINE FIRE MONITOR JE | RU5-E15500 | JT3-WFM-1200-05/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 64362766 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360792 | 8202236941 |  | 8202220965#MAT.PERB.HYDRANT NO. 75 JETTY | RU5-E15500 | JT5-SPH-001/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 115514305 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-18 | 2026-02-05 | 2026-02-05 | 2102363259 | 8202238521 |  | 8202220957#Sewa alat berat crane dan pon | RU2-ITP | 990-HVM-1044/00 | 50 | CRTD NMAT PRC RELR SETC | 2MR | D12/26/B6/NR-D2 | 5500000000 | 0 | MA4-STA |  | HENDRAPARLI |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102363827 | 8202238205 |  | 8202220956#970-PD-1D Problem Rubber Coup | RU2-PK | 970-PD-1D/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102363258 | 8202238520 |  | 8202220955#Penggantian Cathodic Protecti | RU2-ITP | 12-P-99003-A1A2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363130 | 8202233785 |  | 8202220952#Pengadaan material perbaikan | RU6-RCC | 15-C-101/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-31 | 2102362990 | 8202232818 |  | 8202220948#Perbaikan/penggantian pipa ou | RU6-ITP | 42-T-101D/00 | 50 WAMA | REL CSER GMCO GMPS MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 29040 | 1500000 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-12-02 | 2102363072 | 8202233982 |  | 8202220943#LTSA Automatic Tank Gauging S | RU6-ITP | 42-ESV-003/00 | 01 | CLSD NCMP NMAT PRC | 6IR | D16/24/B6/RT-C2H | 26400 | 0 | MA4-INT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360954 | 8202237019 |  | 8202220941#D_24 Soot Blowing 87F201 sequ | RU4-KPC | 87F201/00 | 50 WASR | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358415 | 8202234329 |  | 8202220938#Penggantian bearing 1-EA-01 C | RU7-CDU | 1-EA-01C/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360627 | 8202236936 |  | 8202220937#Penggantian Modul DC Charger |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 94900000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-06-25 | 2026-07-16 | 2102359484 | 8202236926 |  | 8202220931#CLEANING & PERBAIKAN E-201-22 | RU5-D&W | 201-TT-020/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 34429884 | 0 | MA1-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 |  | 3 | 2026-06-25 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-28 | 2102362867 | 8202233563 |  | 8202220928#Penggantian peralatan inst 38 | RU6-POC | 38-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358416 | 8202234328 |  | 8202220927#Penggantian Bearing 2-EAM-01A | RU7-NHT | 2-EAM-01A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102353079 | 8202234491 |  | 8202220925#Tagihan LTSA Fire Extinguishe | RU3-LKKK |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-1-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 | 2102363826 | 8202238204 |  | 8202220924#Perbaikan Steam Leak Area Uti | RU2-UTL | 1-5IA92001MS2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 3000000 | 0 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-05-06 | 2026-05-05 | 2026-12-11 | 2102363079 | 8202233764 |  | 8202220922#Pengadaan Pompa 34-A-103-P-10 | RU6-POC | 34-A-103-P-101A/00 | 50 WAMA | REL CSER GMCO GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 719865000 | 719865000 | MA3-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-05-05 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363590 | 8202232260 |  | 8202220920#Abnormal Noise dan High Temp | RU2-HSC | 200-C-1A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-21 | 2026-01-20 | 2102360796 | 8202236916 |  | 8202220918#Penggantian 201-PDI-035 / 036 | RU5-D&W | INT-CDU-V/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 772 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-21 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358417 | 8202234327 |  | 8202220917#Perbaikan 3-K-01B | RU7-CRU | 3-KM-01B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360939 | 8202236879 |  | 8202220913#MAT.PERB.LINE 8" RECYCLE GM-2 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 23425089 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362866 | 8202233141 |  | 8202220911#Perbaikan kebocoran line drai | RU6-ITP | 42-T-301B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-01 | 2102362991 | 8202233049 |  | 8202220905#Perbaikan Motor 16-K-102-P1C- | RU6-RCC | 16-K-102-P1C-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 369717 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-12 | 2102359581 | 8202236875 |  | 8202220892#K-3-01B:MOV 072 Battery | RU5-E15112 | 03B-MOV-072/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/24/B6/RT-C2H | 6 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2026-04-01 |  | 8202238042 | 8202234096 | 8202220890#Pengganti PO SPK 4 LTSA Trafo | RU6-RCC | 14A-PTR1-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/24/B6/RT-C2H | 1 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-16 | 2026-03-13 | 1102328196 | 8202236871 |  | 8202220889#Perb Level Control Valve 02-L | RU5-E15112 | E-2-16B/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 531376152 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-14 |  | 8202232906 |  | 8202220888#Perbaikan Probe temp 33-P-101 | RU6-HSC | 33-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-08 | 2102362863 | 8202233062 |  | 8202220887#Perbaikan Motor 14-P-104A | RU6-DHC | 14-P-104A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-17 | 2102362936 | 8202233409 |  | 8202220886#Perbaikan 12-E-505A | RU6-DHC | 12-E-505A-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358418 | 8202234326 |  | 8202220884#Perbaikan pompa 1-PM-05A | RU7-CDU | 1-PM-05A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360163 | 8202236873 |  | 8202220882#MAT.PERB.LINE 21-P508-6" HVGO | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 55110405 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358697 | 8202234325 |  | 8202220877#MATERIAL RU7 KASIM | RU7-CDU | 1-C-01/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-05-11 | 2026-02-02 | 2026-12-02 | 2102361561 | 8202233320 |  | 8202220874#Perbaikan 17LC010 | RU6-RCC | 17-LT-010/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365704 | 8202239971 |  | 8202220873#25_Perbaikan Limit Switch 101 | RU4-RFCC | 101UV771/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102358441 | 8202238002 |  | 8202220867#Inspeksi katodik protection d |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358506 | 8202234324 |  | 8202220865#Ganti T-Belt 2-EA-01B | RU7-NHT | 2-EAF-01B/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358444 | 8202234323 |  | 8202220864#Perbaikan 2-EA-02B | RU7-NHT | 2-EAM-02B/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-04 | 2026-02-22 | 2026-02-04 | 2026-12-04 | 2102361714 | 8202238519 |  | 8202220858#Penggantian support line area | RU6-UTL | 56-CT-101A/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 31000000 | 3100000000 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362332 | 8202233662 |  | 8202220855#Penggantian Distributor 56-CT | RU6-UTL | 56-CT-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 15840 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-16 | 2026-03-16 | 2026-03-25 | 2102364139 | 8202236865 |  | 8202220854#Perbaikan dioda trisistor D.E | RU5-UTL | D-EMERG-1-PPII/00 | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 78575000 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-16 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-07 | 2026-02-05 | 2026-02-05 | 2102363257 | 8202238518 |  | 8202220851#Perbaikan 580-PM-301A/B/C/D | RU2-UTL | 580-PM-301A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/22/B6/RT-D2H | 19300000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-28 |  | 8202238203 | 8202232835 | 8202220849#Fabrikasi Pedestal 19-P-114B- | RU6-RCC | 19-P-114B-T/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102360795 | 8202236860 |  | 8202220848#Penggantian solenoid fuel gas | RU5-UTL | HHP-6-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 29984286 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102359876 | 8202236853 |  | 8202220846#Perbaikan Flow Transmitter 3B | RU5-E15112 | 03B-FI-496E/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 47144000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102359872 | 8202236857 |  | 8202220845#Perbaikan Flow Transmitter 02 | RU5-E15112 | 02-FT-052/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 35358000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-09 | 2102359790 | 8202236850 |  | 8202220844#Perbaikan transmitter 01-FT-0 | RU5-E15111 | 01-FT-031/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 117860000 | 0 | MA2-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102359823 | 8202236855 |  | 8202220843#Perbaikan Flow Transmitter 3A | RU5-E15112 | 03A-FT-488/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 35358000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2025-10-29 | 2025-12-24 | 2102360872 | 8202236859 |  | 8202220842#Perbaikan Flow Indikator 003A | RU5-E15112 | 03A-FT-386/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 153218768 | 0 | MA3-INT |  | SAPBATCH | 2026-05-26 | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-10-27 | 2025-10-27 | 2102363735 | 8202232535 |  | 8202220840#Penggantian Push Botton | RU2-ITP | 945-PM-7A/00 | 50 | REL MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-27 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363696 | 8202232449 |  | 8202220833#Perbaikan 580-P-304C | RU2-UTL | 580-P-304C/00 | 50 | REL MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-16 | 2026-02-02 | 2026-08-07 | 2102363335 | 8202233345 |  | 8202220831#Perbaikan 15-PSV-001 | RU6-RCC | 15-PSV-001A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C1H | 627010000 | 0 | MA1-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363775 | 8202232649 |  | 8202220822#Pengadaan Sinker/Anchor & Acc | RU2-ITP | 970-PM-1C/00 | 50 | REL MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363713 | 8202232493 |  | 8202220821#Perbaikan 140 P-13A | RU2-HOC | 140-P-13A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 4830136 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-10 | 2102362784 | 8202237747 |  | 8202220817#LTSA Piping Work Tahap 3 (Are | RU6-HSC | 24-T-101/00 | 60 | REL NMAT PRC SETC | 6MR | D16/24/B6/RT-C1H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-14 | 2025-12-02 | 2102362220 | 8202233074 |  | 8202220806#Perbaikan Modul Ethernet Digi | RU6-RCC | 15-SLV-101/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 166 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358443 | 8202234322 |  | 8202220804#Perbaikan 2-P-02B | RU7-NHT | 2-PM-02B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358445 | 8202234321 |  | 8202220803#PERBAIKAN 2-EAM-01B | RU7-NHT | 2-EAM-01B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-24 |  | 8202237744 |  | 8202220801#LTSA Oksigen Analyzer Termin | RU6-UTL | 52-AT-201A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-24 |  | 8202237743 |  | 8202220800#LTSA Oksigen Analyzer Termin | RU6-UTL | 52-AT-201A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363709 | 8202232484 |  | 8202220799#Perbaikan 140-DCU Train AB | RU2-HOC | 140-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-23 | 2025-12-30 | 2102359521 | 8202236842 |  | 8202220798#Perbaikan Motor P17 A Hitam | RU5-D&W | P-17-DW/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1684364 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-23 | PM |  | 003
| K701 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102358705 | 8202238044 |  | 8202220795#PERBAIKAN POWER PS |  |  | 50 | CRTD NMAT PRC | 7RT | D17/24/B6/RT-4-D2H | 1 | 0 | MA-STA |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 |  | 8202238527 |  | 8202220794#RKA25L_Pemasangan LA CIB II | RU4-TRML | 72X204/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 70000000 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-19 | 2025-12-29 | 2102360276 | 8202236838 |  | 8202220791#Perbaikan Motor P20 Bak Sapar | RU5-TBL | P-20RP-A-HITAM/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1104831 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-03 | 2025-12-30 | 1102329290 | 8202233378 |  | 8202220790#Perbaikan 13-E-111 | RU6-DHC | 12-E-111/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 512 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-08-11 | 2102358586 | 8202237969 |  | 8202220787#Blank | RU7-HSE | 4-B-01/01 | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-4-D2H | 1 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363765 | 8202232611 |  | 8202220785#Perbaikan pompa 520-PM-609A | RU2-UTL | 520-PM-609A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 1034000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363817 | 8202238150 |  | 8202220776#LTSA Scada Trafo RU II Tahun | RU2-UTL | 905-TRF-1-1/01 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362865 | 8202233941 |  | 8202220775#Material consumable 10-OS-901 | RU6-DHC | 10-OS-901/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C1H | 1350000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353188 | 8202234645 |  | 8202220771#Membrane Valve XV 20647 Bocor | RU3-UTL | XV-20647/00 | 60 | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-05 |  | 8202232723 | 8202232817 | 8202220770#SWO Perbaikan/penggantian PSL | RU6-UTL | 51-G-102-K1C/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 23925 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-03 | 2102362783 | 8202233286 |  | 8202220769#Perbaikan 33-E-118 G1 | RU6-HSC | 33-E-118G1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C3H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-04-22 | 2026-12-31 | 2102360684 | 8202236814 |  | 8202220761#Perbaikan Filter D WTP |  |  | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/NR-C2H | 19602197 | 0 | MA4-STA |  | RESTUANDRI |  | 2026-02-11 | PT02 | 2 | 3 | 2026-04-22 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360807 | 8202236818 |  | 8202220760#MAT.PERB.LINE FIRE MONITOR NO | RU5-E15500 | JT5-WFM-1200-09/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 60351568 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360806 | 8202236822 |  | 8202220759#MAT.PERB.LINE FIRE MONITOR NO | RU5-E15500 | JT5-WFM-1200-09/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 60351568 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-03 | 2102360803 | 8202236826 |  | 8202220758#MAT.GANTI VLV FERALIUM HYDRAN | RU5-E15500 | JT3-WFM-1200-05/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 26235000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-18 | 2102361712 | 8202234015 |  | 8202220755#Indikasi bocoran pada flange | RU6-POC | 37-XV-073A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-02 | 2025-12-02 | 2102363677 | 8202232390 |  | 8202220746#Pengadaan card module multisc | RU2-ITP | RTU01A/00 | 60 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-05-07 | 2026-04-23 | 2026-12-30 | 2102360945 | 8202237495 |  | 8202220743#RKA25L_Kaca Jendela Gedung OM | RU4-TRML | 70BD101CU1-BF/00 | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 1 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2026-04-23 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  | 8202235068 | 8202235085 | 8202220741#KV Isolasi Area CDL UTL OM SG |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-20 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-13 | 2102362226 | 8202233294 |  | 8202220740#Perbaikan 31-P-107B | RU6-HSC | 31-P-107B/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-07 | 2025-12-05 | 2026-10-12 | 2102362781 | 8202238202 |  | 8202220739#Perbaikan Valve di Unit 55-A- | RU6-UTL | 55-XV-101A/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 84 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363771 | 8202232640 |  | 8202220738#pengambilan gasket 10 inch 15 | RU2-ITP | 690-PX-3/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202232722 | 8202233072 | 8202220736#SWO Prbikan MOP 059-A-101B-K1 | RU6-UTL | 059-A-101B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102364376 | 8202238526 |  | 8202220727#Switchgear SWS#3 dan SWS#4 | RU2-UTL | 560-SWG-1RSI/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-29 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-01 | 2026-02-01 |  | 8202232817 |  | 8202220726#Perbaikan/penggantian PSL PSH | RU6-UTL | 51-G-102-K1C/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-01 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352219 | 8202234166 |  | 8202220725#KOROSI PADA PIPA 101 CDU SPK | RU2S-KIL | 101-PI-017B/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352221 | 8202234165 |  | 8202220723#Korosi Pada Pipa Daerator Boi | RU2S-KIL | 900-08F-01/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-11 | 2102362780 | 8202233896 |  | 8202220721#Notifikasi Pengecatan Pipa di | RU6-ITP | 42-PIPE/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 924 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-03 | 2102362709 | 8202233095 |  | 8202220720#Perbaikan Mech Seal Pompa 16- | RU6-RCC | 16-K-102-P1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358446 | 8202234320 |  | 8202220716#Penggantian Gasket 2" | RU7-CDU | 1-LT-413/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363720 | 8202232495 |  | 8202220706#Perbaikan 140 EM-5C | RU2-HOC | 140-EM-5C/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 5157736 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 1102328982 | 8202236779 |  | 8202220703#Pengadaan Part FGDS Gedung La | RU5-LAB | BWB-316020/00 | 60 | REL NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | LAB |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102359249 | 8202236778 |  | 8202220702#Perbaikan Pressure Transmitte | RU5-E15112 | 02-PR-071-082/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 225132670 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363543 | 8202232196 |  | 8202220701#Pengadaan Material Kabel siny | RU2-HOC | 110-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/24/B6/NR-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 001
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 |  | 8202238525 |  | 8202220685#Penyediaan Sewa Truck Cargo | RU2-WS |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1640167000 | 0 | WS-TL |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237968 | 8202237967 | 8202220684#PM 2000H 4-KDE-03E |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358526 | 8202237967 |  | 8202220683#PM 2000H 4-KDE-03D |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102362700 | 8202232835 |  | 8202220677#Perbaikan Turbine 19-P-114B-T | RU6-RCC | 19-P-114B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-15 | 2026-02-05 | 2026-02-05 | 2102352173 | 8202238178 |  | 8202220672#Pemb Kontrak Portal Batas Ket | RU3-LKKK |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/NR-5-D2H | 0 | 0 | GEN-STA |  | HERDIYAND | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202236776 | 8202237437 | 8202220667#MAT.REROUTE EMOC-00061/F1/E15 | RU5-UTL | OFC03203/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-W2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 001
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363792 | 8202232709 |  | 8202220665#Shaft Rusak | RU2-HCC | 211-P-13AR/01 | 01 | CRTD NMAT PRC | 2RR | D12/10/B6/RT1-211NH | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363679 | 8202232423 |  | 8202220661#Perbaikan 940-EF-55AW | RU2-UTL | 940-EF-55AW/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363604 | 8202232302 |  | 8202220660#Perbaikan Jangka Panjang 110- | RU2-HOC | 110-P-5BR/01 | 50 | CRTD CSER MACM PRC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 |  | 2026-02-04 | 2026-02-04 | 2102363838 | 8202238109 |  | 8202220657#Monitoring Peralatan Rot&Rota | RU2-HCC |  | 50 | CRTD NMAT PRC | 2RR | D12/09/B6/RT1-212NH | 1000000 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102362668 | 8202233223 |  | 8202220654#Perbaikan Bocoran 22-E-102A | RU6-DHC | 22-E-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-04 | 2102362701 | 8202233072 |  | 8202220652#Perbaikan MOP 059-A-101B-K1 | RU6-UTL | 059-A-101B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363681 | 8202232426 |  | 8202220648#Perbaikan 940-CT-53 | RU2-UTL | 940-C-53/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 145880225 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363597 | 8202232278 |  | 8202220645#940-PT-2A Rekomendasi Pasca O | RU2-UTL | 940-PT-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363703 | 8202232467 |  | 8202220640#Perbaikan 220-H-2 | RU2-HOC | 220-H-2/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358448 | 8202234319 |  | 8202220638#Penggantian Bearing 1-P-05B | RU7-CDU | 1-PM-05B/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 10421000 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-19 | 2026-02-18 | 2102360747 | 8202236775 |  | 8202220637#Penggantian Limit Switch 05-K | RU5-E15111 | 05-KV-514/00 | 50 | REL MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 88260768 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-06 | 2102361881 | 8202233432 |  | 8202220630#Penyehatan Motor 64-A-103 | RU6-HSC | 64-A-103-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-15 | 2102361850 | 8202233433 |  | 8202220629#Penyehatan motor 64-A-101K1 | RU6-HSC | 64-A-101/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-18 | 2102361818 | 8202233434 |  | 8202220627#Penyehatan motor 64-A-101A1 | RU6-HSC | 64-A-101-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 73943 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362616 | 8202233069 |  | 8202220626#Perbaikan motor 11-E-117 B | RU6-HSC | 11-E-117B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102353304 | 8202238164 |  | 8202220622#Pengecatan Area Utilties | RU3-UTL | FT-22009/00 | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/NR-4-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363685 | 8202232431 |  | 8202220620#Penambahan Fasilitas Injeksi | RU2-ITP | 509-MOV-900F/00 | 50 | REL MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-05-11 |  | 8202233395 |  | 8202220619#Perbaikan 12-LV-615 | RU6-DHC | 12-LV-615/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238516 | 8202238781 | 8202220616#Amandemen Waktu Pelaksanaan d | RU2-HCC | 211-E-10/00 | 50 | CRTD NMAT PRC SETC | 2MR | D12/24/B6/RT-D2H | 12000000 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-10 | 2026-02-02 | 2026-02-02 | 2102363647 | 8202232376 |  | 8202220614#Jasa kontrak perbaikan belt c | RU2-ITP | 170-ME-313/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 829235880 | 0 | MA4-ROT |  | T_YUDIPRAS |  | 2026-02-10 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358449 | 8202234318 |  | 8202220613#Penggantian PI Pompa injeksi |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234317 | 8202234316 | 8202220612#PM Engine 4-KDE-03E | RU7-UTL | 4-KDE-03D/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-14 | 2026-02-13 | 1102328949 | 8202236763 |  | 8202220611#Perbaikan Thermocouple 01-TE- | RU5-E15111 | 01-TE-1112/00 | 60 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 3944252 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2025-12-10 | 2025-12-12 | 2102360110 | 8202236765 |  | 8202220607#Perbaikan motor TM-34-05D | RU5-D&W | TM-34-05D/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 645998 | 0 | MA2-LIS |  | SAPBATCH | 2026-04-04 | 2026-02-11 | PT02 |  | 3 | 2026-04-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-09-02 | 2102360555 | 8202236761 |  | 8202220605#Pmblian MotorPompa-2 Regenera | RU5-UTL | DM-5-P02B/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358450 | 8202234316 |  | 8202220603#Material PM Engine 4-KDE-03D& | RU7-UTL | 4-KDE-03D/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 262198442 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 001
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358711 | 8202237966 |  | 8202220601#Jasa Pembuatan Aplikasi IDMS |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/NR-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102360902 | 8202236759 |  | 8202220599#Perb.H-Beam Pondasi & Enclosu | RU5-E15500 | 33-DE-1055-01D/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 15775066 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-04-30 | 2102362563 | 8202233720 |  | 8202220592#Penggantian 52-XV-209C | RU6-UTL | 52-XV-209C/00 | 50 | REL CSER GMPS MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1317 | 4477000 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235367 | 8202235351 | 8202220589#Kontr.Vol Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 |  | 8202233996 |  | 8202220588#Kerusakan 34-AI-500 | RU6-POC | 34-A-103-E-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-07 | 2102362384 | 8202233651 |  | 8202220584#Penggantian Filter 51-G-101D- | RU6-UTL | 51-G-101D-SRB2B/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-07 | 2102362491 | 8202233652 |  | 8202220583#Penggantian Filter 51-G-101D- | RU6-UTL | 51-G-101D-SRB2A/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-03 | 2102362434 | 8202233653 |  | 8202220582#Penggantian Filter 51-G-101D- | RU6-UTL | 51-G-101D-SRB1B/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 26532 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-04 | 2102362331 | 8202233654 |  | 8202220581#Penggantian Filter 51-G-101D- | RU6-UTL | 51-G-101D-SRB1A/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 26664 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-07 | 2102362490 | 8202233550 |  | 8202220579#Penggantian Pompa 51-G-101D-P | RU6-UTL | 51-G-101D-P2A/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102362382 | 8202233551 |  | 8202220578#Penggantian Pompa 51-G-101D-P | RU6-UTL | 51-G-101D-P1A/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235215 | 8202235224 | 8202220574#Kontrak Volume Mekanik Utilit |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235502 | 8202235598 | 8202220570#Kont. Vol Sipil ARea Utara 20 | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-12 | 2025-12-16 | 2102360408 | 8202236755 |  | 8202220568#Perbaikan hub motor HM-41-10B | RU5-E15112 | 41-AC-RPPK-BPP2/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 996826 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358473 | 8202234315 |  | 8202220564#Pemasangan pompa versametic |  |  | 50 | CRTD CSER MACM PRC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358456 | 8202234314 |  | 8202220563#Perbaikan new footvalve 6-P-0 |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 | 2026-05-18 | 2025-11-17 | 2025-11-17 | 2102363774 | 8202232647 |  | 8202220562#Pengadaan Trafo 4-C4 | RU2-UTL | 905-DEG-E01/00 | 50 | REL MACM PRC SETC | 2ER | D12/25/B6/NR-D2H | 475000000 | 0 | MA3-LIS |  | DEDISUKMANA |  | 2026-02-07 | PT02 |  | 3 | 2025-11-17 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358470 | 8202234313 |  | 8202220560#Penggantian Bearing 6-P-06C/D | RU7-UTL | 6-P-06C/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358459 | 8202234312 |  | 8202220559#Penggantian Bearing 5-P-25A | RU7-OFF | 5-P-25A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-04-03 | 2026-02-02 | 2026-02-02 | 2102358471 | 8202234311 |  | 8202220558#Ganti mech seal 1 - P - 06 B | RU7-CDU | 1-P-06B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-28 | 2025-11-26 | 2102362567 | 8202234083 |  | 8202220557#17-LT-015 ( 17-V-106 ) Rusak | RU6-RCC | 17-LT-015/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 282 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202233193 |  | 8202220556#Perbaikan Control Valve 32-LV | RU6-HSC | 32-LV-017/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363693 | 8202232442 |  | 8202220553#Pembuatan Closed Loop Samplin | RU2-LAB | LAB-GAS-21/00 | 60 | REL MACM PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-08 | 2026-06-19 | 2102362031 | 8202233717 |  | 8202220549#Penggantian 53-LT-001AB | RU6-UTL | 53-LT-001/00 | 50 | CRTD CSER MACM PRC | 6IR | D16/24/B6/RT-C2H | 1619 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363605 | 8202232304 |  | 8202220539#Coupling putus | RU2-HCC | 212-EG-15A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363747 | 8202232560 |  | 8202220538#Persiapan material coupling | RU2-HCC | 212-EG-15A/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363671 | 8202232288 |  | 8202220537#Filter lube oil rusak | RU2-HSC | 300-C-2A/00 | 60 | REL NMAT PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363645 | 8202232370 |  | 8202220535#211-EF-8B high vibration | RU2-HCC | 211-EF-8B/00 | 01 | CRTD CSER MACM PRC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-06 |  | 2026-02-06 | 2026-02-06 |  | 8202238699 |  | 8202220534#Lampu Emergency Area HSC | RU2-HSC | 100-H-1/00 | 01 | CRTD NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363632 | 8202232333 |  | 8202220531#Perbaikan FSS di DCS UTL HDC | RU2-PK | 970-SD-CR905-01/00 | 50 | REL GMPS MACM PRC SETC | 2IR | D12/24/B6/NR-D2H | 0 | 58500000 | WS-IN1 |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363781 | 8202232661 |  | 8202220530#Pengadaan NMT ATG 945 T-01 da | RU2-ITP | TT-TK-01/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2025-12-23 | 2102362082 | 8202233515 |  | 8202220529#Penggantian Relay Undervolt 0 | RU6-UTL | 01-PSW3-02/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-07 | 2102362148 | 8202234051 |  | 8202220525#37-P-101B Perbaikan Pompa | RU6-POC | 37-P-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2026-05-08 | 2102362035 | 8202233545 |  | 8202220521#Penggantian Positioner 052-FI | RU6-UTL | 052-FT-903A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1235 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-08-12 | 2102362080 | 8202238103 |  | 8202220519#Instalasi Relay Proteksi ABB | RU6-UTL | 01-PSW1-01A-18A/00 | 60 | REL NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-04 | 2102362037 | 8202232950 |  | 8202220505#Perbaikan Pompa 51-P-102E | RU6-UTL | 51-P-102E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102352921 | 8202235612 |  | 8202220504#Display monitor GT 2015 UA/UB | RU3-UTL | 2015-UA/00 | 60 | REL NMAT PRC SETC | 3IR |  | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352843 | 8202234584 |  | 8202220503#N_Pengadaan Consumable Gas PG | RU3-PP | 23-AT-2201/00 | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-02 | 2026-02-02 | 2026-12-03 | 2102361857 | 8202232964 |  | 8202220484#Perbaikan Pompa 39-K-101-P1A | RU6-POC | 39-K-101-P1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 74051181 | 73435081 | MA3-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102363373 | 8202232952 |  | 8202220482#Perbaikan Pompa 51-P-101E | RU6-UTL | 51-P-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-04 | 2102362140 | 8202232961 |  | 8202220477#Perbaikan pompa 42-P-104B | RU6-ITP | 42-P-104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C1H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-02-02 | 2102358489 | 8202234310 |  | 8202220475#Perbaikan 3-K-01 | RU7-CRU | 3-K-01B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SYAIPULANUAR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358488 | 8202234309 |  | 8202220474#Perbaikan 3 K 02 |  |  | 50 | CRTD CSER MACM PRC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102360577 | 8202236745 |  | 8202220471#Perbaikan Seal DBB Valve Mete | RU5-TBL | 22-716B/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1336260020 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2102360552 | 8202236741 |  | 8202220459#Perbaikan pully motor EM-2-12 | RU5-E15112 | EM-2-12E/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 18074000 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102358501 | 8202234308 |  | 8202220457#Perbaikan 1-P-07 B |  |  | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH | 2026-02-03 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358500 | 8202234307 |  | 8202220456#Pemasangan temperature indica |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-5-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238043 |  | 8202220454#PEMELIHARAAN/ PEMBERSIHAN BER | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 1 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358504 | 8202234306 |  | 8202220453#Perbaikan level transmiter 1- |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358503 | 8202234305 |  | 8202220452#Perbaikan level transmiter 1- |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358502 | 8202234304 |  | 8202220451#Perbaikan level transmiter 1- |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358505 | 8202234303 |  | 8202220449#Perbaikan level transmiter 1- |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358508 | 8202234302 |  | 8202220448#Ganti kerangan 4" 150 inlet s |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358520 | 8202234301 |  | 8202220447#Perbaikan Penggantian Bearing |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363646 | 8202232375 |  | 8202220446#211 P-18B Mech seal bocor | RU2-HCC | 211-P-18B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363673 | 8202232307 |  | 8202220445#3 way valve to T&T rusak | RU2-HSC | 300-CT-2A/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2102360915 | 8202236723 |  | 8202220444#Perbaikan Auxiliary Contact | RU5-E15112 | KM-35-02C/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 104534977 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-23 | 2026-12-23 | 2026-12-29 | 2102364260 | 8202236720 |  | 8202220443#Perbaikan Fan Outdoor H-41-01 | RU5-E15112 | 41-AC-CENTRPPK/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/26/B6/RT-C2H | 1 | 0 | MA3-LIS |  | ANTONIUSAD |  | 2026-02-11 | PT02 |  | 3 | 2026-12-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-24 | 2025-12-30 | 2102360727 | 8202236717 |  | 8202220442#perbaikan Motor EM-3-11B dan | RU5-E15112 | EAM-3-11B/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 5520419 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-23 | 2025-12-29 | 2102360933 | 8202236714 |  | 8202220440#Perbaikan motor EM-32-01K | RU5-E15112 | EM-32-01K/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1775711 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-07 |  | 8202238197 | 8202232805 | 8202220439#Fabrikasi Impeller 16-P-111B | RU6-RCC | 16-P-111B/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-12-30 | 2026-12-31 | 2102359709 | 8202236730 |  | 8202220438#OCB to VCB Incoming dan Coupl | RU5-UTL | 41-R-SS-64-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/NR-C3H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-03 | 2102359741 | 8202236726 |  | 8202220437#OCB to VCB Incoming dan Coupl | RU5-UTL | 41-R-SS-65-LIS/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 | 2102362084 | 8202232814 |  | 8202220434#Perbiak Bearing & Meach pomp | RU6-RCC | 15-P-102C/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 6912 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102352325 | 8202234164 |  | 8202220433#LTSA Sparing | RU2S-LKKK |  | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/26/B6/NRZ-D2H | 600000000 | 134563000 | MAS-ME2 |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 | 2102352256 | 8202234162 |  | 8202220432#Penambahan Atap TPS Limbah B3 | RU2S-LKKK |  | 60 | REL NMAT PRC SETC | 2MS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-20 | 2102361971 | 8202233108 |  | 8202220428#Perbaikan Mech Seal 31-P-103 | RU6-HSC | 31-P-103B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-03 | 2102361855 | 8202234038 |  | 8202220420#Check valve discharge 15-P-10 | RU6-RCC | 15-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-10-31 | 2026-01-30 | 2102360922 | 8202236696 |  | 8202220419#Perb Sensor Temperatur Meteri | RU5-TBL | 22-716B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 1202 | 0 | MA4-INT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-10-31 | 2026-01-30 | 2102360576 | 8202236690 |  | 8202220417#Perbaikan Transmitter Meterin | RU5-TBL | 22-716B/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 482873152 | 0 | MA4-INT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-02-04 | 2102363819 | 8202238163 |  | 8202220414#Perbaikan Pipa Raw Water Km 4 | RU2-UTL | 510-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 500000000 | 0 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-18 | 2102362875 | 8202233771 |  | 8202220412#Pengadaan Motor Assy CFR F1 N | RU6-LAB | P-9042004000/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-08-11 | 2102361947 | 8202233143 |  | 8202220411#Perbaikan kabel di area tangk | RU6-ITP | 42-T-206/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 3976 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102361597 | 8202233678 |  | 8202220410#Penggantian Check Valve HPS 5 | RU6-UTL | 52-B-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 93060 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 006
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-31 | 2026-09-04 | 2102361591 | 8202232994 |  | 8202220409#Perbaikan pompa 14-P-101A P1B | RU6-DHC | 14-P-101A-P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 7680 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 005
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352236 | 8202234160 |  | 8202220405#Faslitas Listrik & Instrument | RU2S-KIL | 946-MIX-13-1/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/NRZ-C2H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352232 | 8202234159 |  | 8202220403#Pompa F-132 indikasi vibrasi | RU2S-KIL | 946-LOG-G153A-M/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/RTZ-C2H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-02 | 2026-04-01 | 2026-12-30 | 2102352233 | 8202234157 |  | 8202220394#Sewa Vacuum Truck | RU2S-LKKK | 946-F-132-D/00 | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 900000000 | 103000000 | MAS-ME2 |  | JUNIANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-04-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102362410 | 8202233927 |  | 8202220389#Material Perbaikan Turbine 51 | RU6-UTL | 51-G-101D-T/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363694 | 8202232443 |  | 8202220388#Gearbox 940-EF-55AL berasap | RU2-UTL | 940-EF-55AL/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 31239911 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361113 | 8202236515 |  | 8202220387#D24_011E110 switch monitoring | RU4-FOC2 | 011E110-01/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-04 | 2102361695 | 8202233259 |  | 8202220385#Perbaikan 52-A-101-P1 ABCD | RU6-UTL | 52-A-101-P1A/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-16 | 2026-05-20 | 2102361631 | 8202234030 |  | 8202220384#Control valve passing | RU6-RCC | 15-UV-044/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1216 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-01 | 2102359638 | 8202236671 |  | 8202220383#Ganti Valve suction cond pump |  |  | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-03 | 2102361776 | 8202233258 |  | 8202220382#Perbaikan 52-A-102-P1 ABCD | RU6-UTL | 52-A-102-P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 26664 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-04 | 2102363309 | 8202232812 |  | 8202220380#Peremajaan Control & OST Devi | RU6-UTL | 56-P-101A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 26796 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363611 | 8202232331 |  | 8202220376#Perbaikan Fuse Trafo Area Lua | RU2-UTL | 560-SWGTR-3A1/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-25 | 2102360702 | 8202236653 |  | 8202220370#Ganti Rupture Disc New Air dr | RU5-E15112 | E-35-07B/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-35NH | 0 | 0 | MA3-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-07 |  | 8202234067 | 8202234068 | 8202220369#24-M-302 Pengadaan Multi Top | RU6-HSC | 24-M-302/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-30 |  | 8202233616 |  | 8202220366#Penggantian kontrol 059-PIC-7 | RU6-UTL | 059-PIC-725B/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 12045 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-03-09 | 2102361814 | 8202234077 |  | 8202220364#20-P-107A Motor vibrasi tingi | RU6-RCC | 20-P-107A-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-11 | 2026-02-02 | 2026-08-10 |  | 8202233209 |  | 8202220359#Perbaikan cathodic struktur j | RU6-ITP | 41-LA-101/00 | 50 WAMA | REL MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 441380972 | 0 | MA4-STA |  | T_FATAHY |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-25 | 2102361778 | 8202233322 |  | 8202220355#Perbaikan 17-PTR2-01B | RU6-HSC | 17-PTR2-01B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 28484000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-08 |  | 8202233841 |  | 8202220354#Penarikan dan pemindahan powe | RU6-UTL | 51-G-101D-LP/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 12870 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-23 | 2026-12-30 | 2026-12-31 | 2102360709 | 8202236642 |  | 8202220352#Perbaikan MCC/Fuse SS 64-65 | RU5-E15111 | EM-1-21A/00 | 60 | REL CSER MANC PRC SETC | 5ER | D15/26/B6/RT-C2H | 1529542448 | 0 | MA2-LIS |  | GHAGASP |  | 2026-02-11 | PT02 | 8 | 3 | 2026-12-30 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-23 | 2102361666 | 8202234106 |  | 8202220350#11-P-112 B | RU6-HSC | 11-P-112B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2102364257 | 8202236645 |  | 8202220349#Perbaikan GM-19-04A | RU5-E15112 | GM-19-04A/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 1 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-07 | 2102361691 | 8202233585 |  | 8202220346#Penggantian Mech Seal 24-P-30 | RU6-HSC | 24-P-302A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-30 |  | 8202233492 |  | 8202220343#Penggantian solenoid valve 05 | RU6-UTL | 059-ZV-271A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 12045 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102361771 | 8202233523 |  | 8202220342#Penggantian Pressure Indicato | RU6-ITP | 42-A-314/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 15923 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-08 | 2102361773 | 8202233041 |  | 8202220341#Perbaikan motor 21-P-106B | RU6-DHC | 21-P-106B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147887 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-05-07 | 2026-02-02 | 2026-02-02 | 2102358545 | 8202234300 |  | 8202220337#Perbaikan 1-P-03B |  |  | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  | SAPBATCH | 2026-02-03 | 2026-02-07 | PT02 |  | 3 | 2026-03-08 | PM |  | 005
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358521 | 8202234294 |  | 8202220336#Pengambilan Material Tahap II |  |  | 50 | CRTD CSER MACM PRC | 7RT | D17/24/B6/RT-2-D1H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361733 | 8202233588 |  | 8202220335#Penggantian LO filter 56-P-10 | RU6-UTL | 56-P-101E-S2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C1H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353167 | 8202234977 |  | 8202220329#Pembacaan RPM P-4 Poly tidak | RU3-CDGP | C4P-P-04/00 | 60 | REL CSER MACM PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-26 | 2102358522 | 8202234273 |  | 8202220324#Perbaikan Roof Drain 5-T-11 | RU7-OFF | 5-T-11/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363581 | 8202232220 |  | 8202220321#perbaikan motor 212-pm-21A | RU2-HCC | 212-PM-21A/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/24/B6/RT-D2H | 7119200 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352238 | 8202234156 |  | 8202220306#101-E-7B-FF | RU2S-KIL | 101-E-7B-FF/00 | 60 | REL CSER MACM PRC SETC | 2RS | D12/25/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-10-02 | 2102362364 | 8202234045 |  | 8202220305#61-V-101 | RU6-HSC | 61-V-101/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352335 | 8202234154 |  | 8202220303#101-E-6-A indikasi bocor | RU2S-KIL | 101-E-6A-MCC-A/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/26/B6/RTZ-D2H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-05-06 | 2026-08-05 | 2102360556 | 8202236604 |  | 8202220301#Perbaikan Sensor DE K-3-01A | RU5-E15112 | K-3-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 40591230 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-02-03 | 2026-05-08 | 2102360553 | 8202236607 |  | 8202220300#Perbaikan Positioner Damper F | RU5-E15112 | F-3-03A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 602000000 | 0 | MA3-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102359524 | 8202236602 |  | 8202220293#Perbaikan Motor P19 A Hitam S | RU5-TBL | P-20-OC-RP-A/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 853574 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363778 | 8202232658 |  | 8202220287#Pengadaan PD Trans Sarfas Inj | RU2-ITP | 945-T-08/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/24/B6/NR-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-12-03 | 2102363379 | 8202237741 |  | 8202220284#LTSA Perbaikan 15-P-102C Body | RU6-RCC | 15-P-102C/01 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-05-11 | 2102363377 | 8202237739 |  | 8202220283#LTSA Perbaikan 15-P-102C Body | RU6-RCC | 15-P-102C/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 |  | 8202233666 |  | 8202220278#Penggantian control valve mak | RU6-UTL | 56-LV-001/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 19932 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233591 |  | 8202220274#Penggantian Limit Switch 052- | RU6-UTL | 052-B-101A-K-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 15923 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-27 | 2102363179 | 8202233256 |  | 8202220272#Perbaikan 53-AIT-517 | RU6-UTL | 53-Z-201/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 14652 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-02-13 | 2102361600 | 8202233146 |  | 8202220270#Perbaikan junction box all ar | RU6-ITP | 43-PMOV-01-JBA/00 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1700439 | 177297 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-08 | 2026-02-02 | 2026-04-16 | 2102361604 | 8202233144 |  | 8202220269#Perbaikan Jungtion Box di NPU | RU6-HSC | 30-LPB-01/00 | 60 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 65817717 | 38075369 | MA3-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-16 |  | 8202232774 |  | 8202220268#PM Junction Box Elec & Inst M | RU6-DHC | 12-J-501/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1699135 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-04-01 |  | 8202233147 |  | 8202220267#Perbaikan JB list Inst area M | RU6-HSC | 25-LPB-01/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1699135 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366021 | 8202239970 |  | 8202220265#24_Perbaikan transmitter 52LT | RU4-UTL | 52B201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 9800000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-29 | 2025-12-29 | 2102360557 | 8202236593 |  | 8202220260#Perbaikan control P1 sei wain | RU5-UTL | P-1-W-WAIN-EM/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 11000000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-18 | 2026-03-25 | 2102360843 | 8202236583 |  | 8202220259#Material Perbaikan & Cleaning | RU5-E15111 | E-1-31A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 564178803 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-18 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363724 | 8202232520 |  | 8202220244#motor high vibrasi | RU2-HCC | 211-EM-22A/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/24/B6/RT-D2H | 0 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-05 |  | 8202232726 | 8202233733 | 8202220241#SWO Penggantian 059-PI-781/78 | RU6-UTL | 059-A-101A-K3/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 23925 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-11 | 2026-02-03 | 2026-02-03 | 2102353165 | 8202235557 |  | 8202220240#Kaca intai TK-2503 | RU3-PP | 23-TK-2503/00 | 60 | CLSD CNF CSER MACM PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 003
| K701 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2102358544 | 8202234271 |  | 8202220235#Penggantian Bearing Floot 1-E |  |  | 50 | CRTD CSER MACM PRC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202233155 |  | 8202220234#Perbaikan Instrumentasi 12-K- | RU6-DHC | 12-PT-673/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102358563 | 8202234262 |  | 8202220229#Wo Rutine Bulan September 202 |  |  | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 9163029 | 0 | MA-ROT |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-05-08 |  | 8202236619 |  | 8202220226#SWO Pemb. PM/PDM Control Valv | RU6-DHC | 22-A-101/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202232644 | 8202238700 | 8202220218#Pengadaan volume booster 140- | RU2-HOC | 140-C-1/00 | 50 | REL NMAT PRC SETC | 2IR | D12/24/B6/NR-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-06 | 2026-02-09 | 2026-02-06 | 2026-02-06 | 2102363961 | 8202238700 |  | 8202220217#Pengadaan Potitioner 140 H-1 | RU2-HOC | 140-C-1/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-09 | PT02 |  | 3 | 2026-02-06 | PM |  | 005
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-05 | 2026-02-05 | 2102363825 | 8202238200 |  | 8202220216#CONMON Gearbox High Vibrasi | RU2-HCC | 212-EG-15A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/24/B6/NR-D2H | 300000000 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-09-24 | 2102361527 | 8202233065 |  | 8202220208#Perbaikan Motor 12-P-111A | RU6-DHC | 12-P-111A-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236550 | 8202238852 | 8202220206#MAT.TAMBAH FABRIKASI LN JUMPE | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 30158502 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-02-07 | 2026-02-10 | 2025-10-31 | 2026-08-05 |  | 8202238733 |  | 8202220205#Perbaikan PSV 12-PSV-856B | RU6-DHC | 12-PSV-856B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C1H | 2304 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363729 | 8202232527 |  | 8202220202#Penggantian valve supply & re | RU2-HCC | 211-E-12A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358732 | 8202237965 |  | 8202220198#Perbaikan 6-P-06A | RU7-UTL | 6-P-06A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-12-02 |  | 8202233984 |  | 8202220196#LTSA - PT Petrolabindo | RU6-LAB | LABORATORIUM/00 | 01 | CLSD CSER NCMP NMAT PRC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102359744 | 8202236548 |  | 8202220195#Material Modifikasi Line Gas | RU5-UTL | B2-PT-813/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/NR-C2H | 22222962 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 001
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352239 | 8202234153 |  | 8202220184#Material Coupling Pompa Area | RU2S-KIL | 101-P-2A/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C3H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-04 | 2026-01-28 | 2026-02-26 | 2102361525 | 8202232151 |  | 8202220178#Penggantian V-Belt Fin Fan 11 | RU6-HSC | 11-E-112D/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 3344000 | MA1-ROT |  | ACHMADY | 2026-06-04 | 2026-02-07 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 | 2102363441 | 8202232887 |  | 8202220175#Perbaikan Shaft Sleeve 19-P-1 | RU6-RCC | 19-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-23 | 2026-02-03 | 2026-02-03 |  | 8202235233 | 8202235240 | 8202220169#Kontrak Volume Mekanik PP 202 |  |  | 60 | REL CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | RRAMADHANI | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102362744 | 8202233200 |  | 8202220165#Perbaikan Compressor 22-K-101 | RU6-DHC | 22-K-101B/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202232170 |  | 8202220160#Total Solution Vibrasi Fin-Fa | RU6-RCC | 20-E-107E-K/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202232171 |  | 8202220159#Total Solution Vibrasi Fin-Fa | RU6-RCC | 20-E-107B-K/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202232993 |  | 8202220157#Perbaikan Pompa 14-P-105A | RU6-DHC | 14-P-105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202232172 |  | 8202220155#Total Solution Vibrasi Fin-Fa | RU6-RCC | 16-E-119P-K/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102362449 | 8202233601 |  | 8202220153#Penggantian Level Glass 55-A- | RU6-UTL | 55-A-101C-V4/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 19883 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 |  | 8202232173 |  | 8202220150#Total Solution Vibrasi Fin-Fa | RU6-RCC | 16-E-117A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 |  | 8202232174 |  | 8202220149#Total Solution Vibrasi Fin-Fa | RU6-RCC | 15-E-110S/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 |  | 8202232175 |  | 8202220147#Total Solution Vibrasi Fin-Fa | RU6-RCC | 15-E-110J/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 |  | 8202232176 |  | 8202220146#Total Solution Vibrasi Fin-fa | RU6-RCC | 15-E-108D-K/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-18 | 2026-02-03 | 2026-02-03 |  | 8202234916 | 8202235505 | 8202220137#KV Sarana Tambat Kapal Area P |  |  | 60 | TECO NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-18 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102353169 | 8202235549 |  | 8202220134#Kebutuhan Material PM HE Area | RU3-CDGP |  | 50 WAMA | REL CSER MACM PRC SETC | 3MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-27 |  | 8202232779 |  | 8202220132#Perubahan pada 16-PIC-741 | RU6-RCC | 16-PIC-741/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-11 |  | 8202233328 |  | 8202220130#Perbaikan 16-PV-011 | RU6-RCC | 16-PV-011/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358714 | 8202234260 |  | 8202220129#PENGADAAN BATTERY CHARGER PT |  |  | 60 | REL MACM PRC SETC | 7RT | D17/24/B6/RT-1-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-31 | 2026-08-05 | 2102363371 | 8202233920 |  | 8202220128#Material spring coil heater 1 | RU6-DHC | 14-V-108/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 2304 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-26 | 2102361951 | 8202232925 |  | 8202220124#Perbaikan Positioner CV dampe | RU6-UTL | 059-A-101A-C1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 17259 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102362570 | 8202233966 |  | 8202220122#Maintenance instrument meteri | RU6-ITP | 42-A-100/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 15874 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-11 |  | 8202233411 |  | 8202220121#perbaikan 11TI183 | RU6-HSC | 11-E-112/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 |  | 8202232178 |  | 8202220111#Total Solution Fin-Fan 20-E-1 | RU6-RCC | 20-E-107C/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 |  | 8202232180 |  | 8202220110#Total Solution Fin-Fan 16-E-1 | RU6-RCC | 16-E-117AE/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-18 | 2026-02-02 | 2026-11-27 |  | 8202232183 |  | 8202220109#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-110AP/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/24/B6/RT-C2H | 19385772 | 19337808 | MA1-ROT |  | ACHMADY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-27 | 2026-02-02 | 2026-11-27 |  | 8202232187 |  | 8202220108#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-109A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 13408912 | 13408912 | MA1-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 |  | 8202232188 |  | 8202220104#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-108C-K/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363614 | 8202232342 |  | 8202220103#Pengadaan CV Area 211/212, 84 | RU2-HCC | 211-FV-180/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-11 | 2102363425 | 8202233721 |  | 8202220102#Penggantian 52-PT-223 C | RU6-UTL | 52-B-101C/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 16005 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-05-09 | 2026-12-30 | 2026-12-30 | 2102358583 | 8202237964 |  | 8202220101#PERBAIKAN PANEL COMUNITTY |  |  | 60 | REL GMCO NMAT PRC SETC | 7RT | D17/26/B6/RT-2-D2H | 1 | 0 | MA-STA |  | RYANMANGGASA |  | 2026-02-11 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-06 | 2026-01-02 | 2026-01-02 | 2102353218 | 8202234648 |  | 8202220095#MCC 209 B Pemasangan Relay Gr | RU3-PP | MCC-PM-209-B/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 3ER | D13/26/B6/RT-2-D2H | 128200000 | 128200000 | MA2-LIS |  | ALEPDALITAN | 2026-06-15 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102363409 | 8202233139 |  | 8202220092#Perbaikan Kebocoran Mech Seal | RU6-RCC | 15-P-113B/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102360870 | 8202236491 |  | 8202220087#Penggantian Lampu ACWL Flare |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 94792400 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-30 |  | 8202233746 |  | 8202220082#Pengadaan Transmission Unit 4 | RU6-ITP | 42-P-205C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C1H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363723 | 8202232517 |  | 8202220079#Motor vibrasi | RU2-HCC | 211-PM-13A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 948000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-12 | 2025-11-12 | 2102361189 | 8202237220 |  | 8202220072#CM_Perbaikan line 3" N2 107T5 | RU4-GTO | 107T501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102360944 | 8202237494 |  | 8202220071#RKA25_L Cleaning Burner Tande | RU4-KPC | 82P202A/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 100000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-03 | 2102363401 | 8202232872 |  | 8202220069#Perbaikan Steam Turbin 15-P-1 | RU6-RCC | 15-P-101B-T/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C1H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102360773 | 8202236464 |  | 8202220068#Penggantian Solid State Relay |  | E-3-60B/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 32 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-06 | 2026-02-02 | 2026-02-02 | 2102352249 | 8202234152 |  | 8202220067#900-02-P-3B | RU2S-KIL | 900-02P-3B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/NRZ-C2H | 0 | 45900000 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361107 | 8202236506 |  | 8202220056#D24_018F-102 panel soot blowe | RU4-FOC2 | 018F102/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361108 | 8202236507 |  | 8202220055#D24_014K102B Power panel arm | RU4-FOC2 | 014K102B/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361109 | 8202236508 |  | 8202220054#D24_013F-102D24_ Panel sootbl | RU4-FOC2 | 013F102/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361110 | 8202236510 |  | 8202220053#D24_013F-101 Soot blower moto | RU4-FOC2 | 013F101/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-15 | 2025-12-15 | 2102360889 | 8202236461 |  | 8202220048#Perbaikan Pompa G-2-13B | RU5-E15112 | G-2-13B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1030877 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-17 | 2102360847 | 8202236458 |  | 8202220044#Pompa boster no.1 STG 2.4 vib | RU5-UTL | 4VF-02-D001/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 7020000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361157 | 8202237089 |  | 8202220040#D_24 Logic soor blower 025F10 | RU4-LOC2 | 025F101/00 | 50 WASR | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-04 | 2026-03-02 | 2026-12-04 | 2026-12-04 | 2102363813 | 8202238141 |  | 8202220037#LTSA PEMELIHARAAN/PERBAIKAN T | RU2-HCC | 211-PIPING/00 | 50 | REL GMCO NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 9000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-12-04 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-02-04 | 2102363816 | 8202238149 |  | 8202220036#LTSA Pemeliharaan/ Perbaikan | RU2-HSC | 200-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 600000001 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-14 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-06-05 | 2102358806 | 8202236456 |  | 8202220033#Ganti Seal casing turbine FDF | RU5-UTL | 2NG00D001/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-29 | 2026-11-27 | 2102360907 | 8202236453 |  | 8202220032#Membran pompa injeksi NaOH ru | RU5-UTL | 0UA-42-D004/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/24/B6/RT-C2H | 36860000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-30 | 2025-12-30 | 2102360882 | 8202236416 |  | 8202220018#Perbaikan EM-32-01M | RU5-E15112 | EM-32-01M/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 591895 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-03-06 | 2102360883 | 8202236412 |  | 8202220016#Perbaikan GM-19-03A | RU5-E15112 | GM-19-03A/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 388871 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-05 | 2102360791 | 8202236451 |  | 8202220015#Ganti Valve 16" Pengisian W14 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-W1NH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102363355 | 8202232949 |  | 8202220014#Perbaikan pompa 53-P-102 ABC | RU6-UTL | 53-P-102A-EN/01 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C1H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-05-18 | 2102360372 | 8202236422 |  | 8202220013#Penggantian Wire Sling OH Cra |  |  | 60 | REL CSER NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-05 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358226 | 8202234249 |  | 8202220009#KERUSAKAN 1-P-04A | RU7-CDU | 1-P-04A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363586 | 8202232242 |  | 8202220008#Perbaikan Motor 110 PM-5B | RU2-HOC | 110-PM-5BR/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-10 | 2102360731 | 8202236386 |  | 8202220000#Penggantian Check Valve RWP 1 |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 460330031 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-05 | 2102360790 | 8202236349 |  | 8202219998#Perbaikan Cation 3 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-15 | 2026-04-15 | 2026-06-04 | 2102359842 | 8202236409 |  | 8202219997#Ganti Valve suction BFWP 5 |  |  | 60 | CLSD CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-04-15 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102359528 | 8202236333 |  | 8202219988#Perbaikan Ignition Transforme |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 21400000 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360923 | 8202236371 |  | 8202219983#Penggantian Lampu Penerangan | RU5-D&W |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 5012200 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360274 | 8202236329 |  | 8202219972#Lampu penerangan All area HCC |  |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1643554038 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102361991 | 8202233799 |  | 8202219969#Pengadaan man hole bottom 20- | RU6-RCC | 20-R-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-30 | 2025-12-30 | 2102359919 | 8202236285 |  | 8202219968#Perbaikan motor GM-2-09A | RU5-E15112 | GM-2-09A/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1693901 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-19 | 2025-12-29 | 2102359703 | 8202236284 |  | 8202219965#Perbaikan motor Gm-34-66 | RU5-D&W | GM-34-66/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 16548132 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-04-02 | 2102360901 | 8202236308 |  | 8202219964#Perb.Flow Transmitter 3A-FT-4 | RU5-E15112 |  | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 32922224 | 0 | MA3-INT |  | SAPBATCH | 2026-05-26 | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2102359404 | 8202236309 |  | 8202219962#Penggantian Socket Outlet HCC | RU5-E15112 | EA-3-03B/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 683300000 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 1102329106 | 8202236310 |  | 8202219961#Pengadaan Part FGDS Gedung La |  | 341-BWHM-1/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 270000000 | 0 | LAB |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-11-30 | 2026-11-30 | 2102358809 | 8202236283 |  | 8202219959#Perbaikan Ea-202-04A | RU5-D&W | EA-202-04A/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-30 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358621 | 8202234248 |  | 8202219958#PERBAIKAN 3-K-02 BOCOR PADA S | RU7-CRU | 3-K-02/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-5-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102360730 | 8202236281 |  | 8202219956#Perb. Shutoff Valve Fuel oil | RU5-UTL | HHP-1-INST/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 441101811 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102359843 | 8202236282 |  | 8202219953#PENG SOL Valve 101-PT-1B-LW | RU5-TBL | 101-PT-01A-INST/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 301391000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2025-12-05 | 2026-09-14 |  | 8202238162 |  | 8202219950#Fabrikasi & Perbaikan Rotor 0 | RU6-UTL | 055-P-101AT/00 | 50 | CRTD NMAT PRC RELR SETC | 6RR | D16/25/B6/RT-C1H | 519500000 | 0 | MA4-ROT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-12 | 2025-12-29 | 2102359479 | 8202236280 |  | 8202219944#Perbaikan Motor P15 A Hitam | RU5-TBL | P-15RP-A-HITAM/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2600046 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352261 | 8202234151 |  | 8202219942#900-03-P-4A indikasi bocor pa | RU2S-KIL | 900-03P-4A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C3H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-03 | 2026-02-02 | 2026-02-02 | 3102742902 | 8202234247 | 8202234130 | 8202219941#PENGGANTIAN FILTER 3-K-01/02 | RU7-CRU | 3-K-01B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358626 | 8202234241 |  | 8202219940#Penggantian /Perbaikan Mechse | RU7-CDU | 1-P-04B/00 | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-5-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352244 | 8202234150 |  | 8202219939#Perbaikan Line 8 Inch Prod LS | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352267 | 8202237474 |  | 8202219934#Rorating - support Startup | RU2S-KIL | 101-P-3A/00 | 60 | REL CSER MACM PRC SETC | 2RS | D12/24/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352242 | 8202234149 |  | 8202219933#Sight Glass Rotating Equipmen | RU2S-KIL | 101-P-2A/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-02 | 2025-12-02 | 2102361026 | 8202235379 |  | 8202219932#Perbaikan TS7000 Brand TSHR | RU4-FOC2 | 010AOC1/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-22 | 2102363175 | 8202233722 |  | 8202219923#Penggantian 51-VT-251,252,253 | RU6-UTL | 53-CL-201C/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1701 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102363159 | 8202234108 |  | 8202219921#11-P-103B | RU6-HSC | 11-P-103B-V1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102363325 | 8202233733 |  | 8202219915#Penggantian 059-PI-781/784/7 | RU6-UTL | 059-A-101A-K3/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 23760 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-06 | 2026-02-19 | 2102360453 | 8202236277 |  | 8202219912#Perbaikan Scrapper & Roller T | RU5-D&W | VIKOMA/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 7193283 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-06 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-07 | 2102362482 | 8202232894 |  | 8202219907#Perbaikan scratch pada hose a | RU6-ITP | 41-LA-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 7920 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-23 | 2102362576 | 8202232901 |  | 8202219897#Perbaikan Push Button motor a | RU6-ITP | 42-M-206-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 19932 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-30 | 2102362740 | 8202233703 |  | 8202219892#Penggantian Bearing 38-K-101 | RU6-POC | 38-K-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102362442 | 8202233571 |  | 8202219883#Penggantian Needle Valve 52-B | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102362416 | 8202233572 |  | 8202219882#Penggantian Needle Valve 52-B | RU6-UTL | 52-B-101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102362325 | 8202233573 |  | 8202219881#Penggantian Needle Valve 52-B | RU6-UTL | 52-B-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102362413 | 8202233574 |  | 8202219880#Penggantian Needle Valve 52-B | RU6-UTL | 52-B-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 | 2102362419 | 8202233575 |  | 8202219879#Penggantian Needle Valve 52-B | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2025-10-29 | 2025-12-24 | 2102359013 | 8202236276 |  | 8202219878#Perbaikan O2 Analyzer 01-AIT- | RU5-E15111 | 01-AIT-313B/00 | 60 | TECO CNF NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 768 | 0 | MA2-INT |  | SAPBATCH | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102358491 | 8202237963 |  | 8202219872#Perbaikan Gedung Control Room |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D1H | 287671000 | 0 | MA-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K601 | 2026-02-01 | 2026-04-09 | 2026-02-02 | 2026-11-27 | 2102362573 | 8202232967 |  | 8202219865#Perbaikan Pompa 33-P-110A | RU6-HSC | 33-P-110A/00 | 50 | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 307308183 | 307308182 | MA3-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-07 |  | 8202238515 |  | 8202219861#Perbaikan Overhead Crane 15-A | RU6-RCC | 15-A-204-M1/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102363824 | 8202238199 |  | 8202219857#Paket Kontrak Manpower Emerge | RU2-HSC | 100-H-1/00 | 50 | CRTD NMAT PRC SETC | 2MR | D12/24/B6/NR-D2H | 240000000 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102359700 | 8202236268 |  | 8202219856#Req Penggantian Hose Hydrauli | RU5-TBL | L-ARM-4-JT-5/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/24/B6/RT-C2H | 0 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-02 | 2026-06-02 | 2102359630 | 8202236270 |  | 8202219842#Perbaikan G-34-117A | RU5-D&W | G-34-117A/00 | 60 | CLSD CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-20 |  | 8202238148 |  | 8202219832#Repair & Penggantian Blower G | RU6-LOG | OO-S-102/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363701 | 8202232462 |  | 8202219829#Pemasangan Kamera Monitoring | RU2-HOC | 1-5FG11004-A1A1/00 | 50 | CRTD MACM PRC | 2IR | D12/24/B6/NR-D2H | 2131200000 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365304 | 8202239969 |  | 8202219827#24_Penggantian valve under gr | RU4-TRML | 72FMMOV101AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-06-15 | 2102359650 | 8202236265 |  | 8202219826#Perbaikan EA-3-08D | RU5-E15112 | EA-3-08D/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 4793103 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 | 2102362322 | 8202232805 |  | 8202219822#Permanent Repair Pompa 16-P-1 | RU6-RCC | 16-P-111B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-10 | 2025-12-08 | 2025-12-08 | 2102363654 | 8202232386 |  | 8202219820#Pengadaan cartridge Filter 14 | RU2-HOC | 140-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 498000000 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363698 | 8202232455 |  | 8202219806#Perbaikan 520-P-607D | RU2-UTL | 520-P-607D/00 | 50 | REL MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365935 | 8202239968 |  | 8202219803#24_Perbaikan PG 102P507B | RU4-RFCC | 102P507B/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 33888351 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365351 | 8202239967 |  | 8202219791#[CR] Perbaikan mechseal leak | RU4-RFCGTO | 148P502A/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 10967700 | 0 | MA7-ROT |  | FARIZSETYANA | 2026-05-21 | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-04 | 2026-01-05 |  | 8202236214 | 8202235139 | 8202219782#MAT. PENGGANTIAN PIPA 16" INO | RU5-D&W | E-34-08/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1080092583 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-13 | 2102360239 | 8202236237 |  | 8202219770#Ganti Material Piping Filter |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 83270507 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-13 | 2102360898 | 8202236212 |  | 8202219766#RK_Mat Retub Evaporator Tube | RU5-UTL | EA20-214-UW-2A1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 17181279563 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 | 2102362361 | 8202233997 |  | 8202219763#Kerangan Upstream dan Downstr | RU6-HSC | 11-PSV-013C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-03-17 | 2102359914 | 8202236184 |  | 8202219758#Perbaikan Level Transmitter 0 | RU5-E15111 | C-7-02/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 334361100 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-15 | 2026-03-04 | 2026-04-09 | 2102360318 | 8202236181 |  | 8202219757#Perbaikan Valve 31-PCV-040B | RU5-E15112 | 31-PCV-040B/00 | 60 | CLSD CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 195000000 | 0 | MA3-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K301 | 2026-02-04 | 2026-06-10 | 2026-02-05 | 2026-02-05 | 2102353305 | 8202238198 |  | 8202219755#Pekerjaan Coating Lantai SS#1 |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | GEN-STA |  | HARISASEPWIJ |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-31 | 2026-08-05 | 2102361915 | 8202233838 |  | 8202219754#Pengadaan 14-PSV-403 | RU6-DHC | 14-PSV-403/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C1H | 2304 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-31 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102362272 | 8202233140 |  | 8202219753#Perbaikan Kebocoran Mech Seal | RU6-HSC | 11-P-103C/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 | 2102359971 | 8202236185 |  | 8202219752#Perb.Press Reducer Valve 05-P | RU5-E15111 | KT-5-02B/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 420000000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-09 | 2102360041 | 8202236207 |  | 8202219750#Bearing motor Pompa produksi |  |  | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 1463800 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365522 | 8202239966 |  | 8202219740#24_93F-401 Perbaikan power su | RU4-SRU | 93F401/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-6-C2H | 2 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233195 |  | 8202219739#Perbaikan Control Valve 15-UV | RU6-RCC | 15-UV-028/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363697 | 8202232451 |  | 8202219728#Perbaikan 550-P-104 | RU2-UTL | 550-P-104/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 1233838 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235145 | 8202235632 | 8202219726#KV Cleaning Cooler&Cond. CD I | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102362223 | 8202232960 |  | 8202219724#Perbaikan Pompa 42-P-104B | RU6-ITP | 42-P-104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-19 | 2025-12-29 | 2102359632 | 8202236179 |  | 8202219723#Perb. Motor GM34-71A sparator | RU5-TBL | GM-34-71A/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 893100 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-19 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366096 | 8202239964 |  | 8202219718#24_[CR] 018P103B MS bocor | RU4-FOC2 | 018P103B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 89508800 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102366030 | 8202239963 |  | 8202219716#24_[CR] Bearing FDF 21F1 Suar | RU4-LOC1 | 21F1K/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-13 | 2102361958 | 8202233990 |  | 8202219712#Lampu Aksesoris untuk area RP | RU6-HSC | GROUNDSYS-RPPK/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363599 | 8202232240 |  | 8202219710#Blade putus 940-EF-55AB | RU2-UTL | 940-EF-55AB/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-30 | 2102362177 | 8202234109 |  | 8202219708#11-P-102 B | RU6-HSC | 11-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-24 | 2102363242 | 8202233040 |  | 8202219705#Perbaikan Motor 23-P-201B-M | RU6-HSC | 23-P-201B-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102362174 | 8202232834 |  | 8202219698#Perbaikan Turbine 39-K-101-P1 | RU6-POC | 39-K-101-P1-T/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365508 | 8202239962 |  | 8202219697#24_[CR]Perbaikan coupling gea | RU4-LOC2 | 024S101D/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-8-C2H | 7250000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-09 |  | 2026-02-09 | 2026-02-09 |  | 8202238781 |  | 8202219693#PERBAIKAN 211-E-10, 702-E-7, | RU2-HCC | 211-E-10/00 | 01 | CRTD CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 722700000 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-01 | 2025-12-03 | 2102358898 | 8202236178 |  | 8202219690#perbaikan Lampu Sorot Rumah K | RU5-E15112 | K-3-02A/00 | 60 | REL CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 709460564 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365308 | 8202239961 |  | 8202219686#24_Kerusakan 153VSH001ABCDEFG | RU4-RFCUTL | 153A501B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-08 | 2025-12-01 | 2025-12-01 | 2102353343 | 8202234524 |  | 8202219682#Perbaikan Pompa P-1 CDU II | RU3-CDGP | CD2-P-001A/00 | 60 | CLSD CNF NMAT PRC SETC | 3RR |  | 0 | 0 | MA1-ROT |  | MULYONO701 | 2026-04-27 | 2026-02-07 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-14 | 2102361953 | 8202233292 |  | 8202219675#Perbaikan 32-FT-039 | RU6-HSC | 32-FT-039/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-27 | 2102362138 | 8202233291 |  | 8202219674#Perbaikan 32-FV-039 | RU6-HSC | 32-FV-039/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-13 |  | 8202233076 |  | 8202219672#Perbaikan Modul Annunciator 1 | RU6-DHC | 14-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102360626 | 8202236177 |  | 8202219670#Perb.Flow Meter WM Deepwell 9 | RU5-UTL | P-8-DWELL-INST/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 60000000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-03-13 | 2102360571 | 8202236155 |  | 8202219664#perbaikan GT-8-12B | RU5-E15112 | GT-8-12B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 5529256 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-01 | 2026-10-21 | 2102360654 | 8202236151 |  | 8202219656#Perbaikan Pompa BFW 5 | RU5-UTL | 3RL-20-D001/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/24/B6/RT-C2H | 10474725 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-01 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-21 | 2025-11-21 | 2102359749 | 8202236175 |  | 8202219652#Mixer Soda Demin Rusak |  |  | 50 | REL MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-21 | PM |  | 045
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-02 | 2025-12-19 | 2102359745 | 8202236148 |  | 8202219651#Pkrjn. G-15-01B RFO pump St8 | RU5-TBL | G-15-01B/01 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 649357818 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2025-10-27 | 2025-12-05 | 2102360732 | 8202236157 |  | 8202219650#Perb. Mech Seal&pompa P13A Hi | RU5-TBL | P-13RP-A-HITAM/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 11400753 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-23 | 2026-02-11 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-12-02 | 2026-12-10 | 2102359746 | 8202236159 |  | 8202219648#Perb. G-20-09B LSWR loading S | RU5-TBL | G-20-09B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 230000 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-12-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-24 | 2025-12-02 | 2025-12-10 | 2102359748 | 8202236146 |  | 8202219647#Pkrjn. P 6 A Hitam LSWR Rp A | RU5-TBL | P-6RP-A-HITAM/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 41445490 | 0 | MA4-ROT |  | SAPBATCH | 2026-02-12 | 2026-02-11 | PT02 |  | 3 | 2026-02-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-12-30 | 2026-12-30 | 2102359844 | 8202236153 |  | 8202219646#PERBAIKAN MAIN LUBE OIL PUMP | RU5-TBL | 101-PT-1B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 11185309 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-29 | 2026-06-29 | 2026-07-08 | 2102359847 | 8202236161 |  | 8202219642#Perb. G-20-08A ADO loading ST | RU5-TBL | G-20-08A/00 | 60 | REL CSER GMCO MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 3308941 | 0 | MA4-ROT |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-29 | 2026-06-29 | 2026-07-08 | 2102359910 | 8202236147 |  | 8202219640#Pkrjn. P 5 A Putih Kero Rp A | RU5-TBL | P-A5-PUTIH/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 27485076 | 0 | MA4-ROT |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-03-04 | 2026-03-13 | 2102359913 | 8202236163 |  | 8202219639#PENGGANTIAN BEARING POMPA 101 | RU5-TBL | 101-P-1D/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-09-29 | 2026-10-19 | 2102359702 | 8202236150 |  | 8202219638#Perbaikan Pompa degasser 2 | RU5-UTL | 2UA-03-D002/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 18759484 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-09-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365276 | 8202239960 |  | 8202219631#24_Perbaikan PG range 25 Kg ( | RU4-RFCC | 104K501/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 33888351 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365934 | 8202239959 |  | 8202219629#24_Perbaikan PG range 14 Kg ( | RU4-RFCC | 102K501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 34272385 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365307 | 8202239958 |  | 8202219624#24_Penggantian DPT DPA B | RU4-RFCUTL | 156PDT-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-13 |  | 8202232909 |  | 8202219619#Perbaikan pressure gauge area | RU6-HSC | 11-C-101/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 2873466 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-15 | 2102361911 | 8202234046 |  | 8202219616#61-LSHL-902 | RU6-HSC | 11-DTU-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102363019 | 8202233380 |  | 8202219613#Perbaikan 12-PTR2-02A | RU6-DHC | 12-PTR2-02A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 71238791 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-11 | 2102363057 | 8202233370 |  | 8202219612#Perbaikan 13-PTR1-01A | RU6-DHC | 13-PTR1-01A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 71238791 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-26 | 2102363053 | 8202233369 |  | 8202219610#Perbaikan 13-PTR1-01B | RU6-DHC | 13-PTR1-01B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 71238791 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-01 | 2102363059 | 8202233368 |  | 8202219608#Perbaikan 13-PTR2-01A | RU6-DHC | 13-PTR2-01A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 28791 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-27 | 2102363148 | 8202233692 |  | 8202219603#Penggantian bearing motor spa | RU6-HSC | 11-E-112B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102360985 | 8202234472 |  | 8202219597#RKA24_Penggantian Junction Bo | RU4-FOC2 | 012E102M01/00 | 60 WASR | REL CSER NMAT PRC SETC | 4ER | D14/24/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352247 | 8202234148 |  | 8202219585#946-P-8B IPAL indikasi High V | RU2S-KIL |  | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-08 | 2102361919 | 8202233567 |  | 8202219581#Penggantian part LG 15-V-101 | RU6-RCC | 15-V-101B/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-14 | 2026-02-02 | 2026-05-08 | 2102361917 | 8202233602 |  | 8202219580#Penggantian Level Glass 15-V- | RU6-RCC | 15-V-117/00 | 60 | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 447500000 | 447500000 | MA1-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365350 | 8202239957 |  | 8202219575#24_Preventive Maintenance Com | RU4-GTO | 180A601K1B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 96858180 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366087 | 8202239956 |  | 8202219574#24_[TGH] Penggantian membran | RU4-TRML | 43P5A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 57224622 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102363305 | 8202233224 |  | 8202219550#Perbaikan blowback 15-V-104 | RU6-RCC | 15-V-104/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-30 | 2102361913 | 8202233993 |  | 8202219549#Kerusakan Sensor COD SPARING | RU6-LK/KK | JALANKILANG/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 12045 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365327 | 8202239955 |  | 8202219544#24_011P123B coupling rontok | RU4-FOC2 | 011P123BM/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-2-C2H | 21500000 | 0 | MA2-LIS |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102360992 | 8202234786 |  | 8202219542#Pengadaan check valve OEM 156 | RU4-RFCUTL | 156K502B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360993 | 8202234789 |  | 8202219541#Pengadaan check valve OEM 156 | RU4-RFCUTL | 156K502A/00 | 50 | CRTD CSER MACM PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-21 | 2102360457 | 8202236140 |  | 8202219540#perbaikan switch local finfan | RU5-E15112 | PLANT-8B-LIS/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 355606398 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360403 | 8202236145 |  | 8202219539#Ganti Tube EA-201-03C | RU5-D&W | EA-201-03C/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-D5NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2102360313 | 8202236142 |  | 8202219536#Perbaikan fan motor GM-2-14B | RU5-E15112 | GM-2-14B/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 10 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102361804 | 8202233100 |  | 8202219531#Perbaikan Mech Seal 42-M-101G | RU6-ITP | 42-M-101G2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102361753 | 8202233101 |  | 8202219530#Perbaikan Mech Seal 42-M-101G | RU6-ITP | 42-M-101G1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102361759 | 8202233102 |  | 8202219529#Perbaikan Mech Seal 42-M-101F | RU6-ITP | 42-M-101F3/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 | 2102361840 | 8202233104 |  | 8202219528#Perbaikan Mech Seal 42-M-101F | RU6-ITP | 42-M-101F1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102361755 | 8202233103 |  | 8202219527#Perbaikan Mech Seal 42-M-101F | RU6-ITP | 42-M-101F2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360736 | 8202236138 |  | 8202219524#MAT.GANTI B/V LINE PMANAS 532 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 882751 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 |  | 8202236084 | 8202235121 | 8202219523#Perbaikan Spoel Contactor Gm- | RU5-E15112 | GM-8-05C/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 198 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-09 | 2026-01-02 | 2026-01-02 | 2102352248 | 8202234146 |  | 8202219520#101-P-2B Indikasi Vibrasi pad | RU2S-KIL | 101-P-2B-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-D2H | 7467640 | 7467640 | MAS-LIS |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-22 | 2025-12-30 | 2102360935 | 8202236113 |  | 8202219518#Perbaikan motor EM MA3 | RU5-E15112 | EM-32-01M/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1001004 | 0 | MA3-LIS |  | MKASPUDDIN | 2025-12-22 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102358980 | 8202236116 |  | 8202219517#MAT.PERB.LINE OUTLET TANK A26 | RU5-TBL | 022-R-RP-PSA/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 521000983 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-19 | 2025-12-29 | 2102360262 | 8202236110 |  | 8202219516#Perbaikan Motor GM/EM MA3 | RU5-E15112 |  | 60 | TECO CNF MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 26083045 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102361806 | 8202234048 |  | 8202219506#42-M-301C | ITP-UP6 | 42-M-301C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 | 2102361808 | 8202233266 |  | 8202219505#Perbaikan 42-M-301A | ITP-UP6 | 42-M-301A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365520 | 8202239954 |  | 8202219503#24_Penggantian Transmitter 52 | RU4-UTL | 520PDT634/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365489 | 8202239953 |  | 8202219502#24_Penggantian Transmitter 52 | RU4-UTL | 520PDT633/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-27 | 2025-11-27 | 2102361092 | 8202236481 |  | 8202219500#D24_sensor vibrasi finfan rus | RU4-FOC2 | 011E110-01/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-20 | 2102361656 | 8202238514 |  | 8202219497#Perbaikan 20-R-101 | RU6-RCC | 20-R-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2102360360 | 8202236082 |  | 8202219487#Perbaikan Motor EM-1-27A | RU5-E15111 | EM-1-27A/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 5242321 | 0 | MA2-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102353348 | 8202235700 |  | 8202219485# Penggantian Transmitter FT85 | RU3-CDGP | CD5-FT-8511/00 | 60 | REL CSER MACM PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 004
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360866 | 8202236083 |  | 8202219480#MAT.MODIF PIPING STEAM KE NEW | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 78657850 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365373 | 8202239952 |  | 8202219477#24_[CR] Penggantian Bearing 1 | RU4-FOC1 | 11E52K-D/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 10798760 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-01-28 |  | 8202237737 | 8202233956 | 8202219475#Per. Gen. Steam Turbin 19-P-1 | RU6-RCC | 19-P-114B-T/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365545 | 8202239951 |  | 8202219454#24_Penggantian FTA Fuse (50mA | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 20 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365278 | 8202239950 |  | 8202219451#24_Pengadaan checkvalve dual | RU4-RFCUTL | 156K502B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365402 | 8202239949 |  | 8202219450#24_Penggantian Trnsmtrr 054PI | RU4-UTL | 054WS105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 15000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365401 | 8202239948 |  | 8202219448#24_Penggantian Trsmitr 054FT3 | RU4-UTL | 052B103/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 18500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366097 | 8202239947 |  | 8202219447#24_Penggantian solenoid Tripp | RU4-RFCUTL | 156UY-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 46550000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-11 | 2102365451 | 8202239946 |  | 8202219446#24_Mtl. Cleaning Preheater 01 | RU4-FOC2 | 011E103C1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 13117525 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 | 2102361751 | 8202233270 |  | 8202219436#Perbaikan 38-K-101 A | RU6-POC | 38-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-13 | 2102360193 | 8202236078 |  | 8202219434#Material Perbaikan Mud Drum H | RU5-UTL | HHP-4/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 48765020 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102363244 | 8202233726 |  | 8202219433#Penggantian 32-FI-324 (32-K-1 | RU6-HSC | 32-K-101/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 90000000 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-03-05 | 2102360912 | 8202236076 |  | 8202219432#Penggantian Channel Oil Coole | RU5-UTL | TG-5A-OIL-COOLR/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 18273570 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-28 | 2102363321 | 8202233446 |  | 8202219430#Penggantian valve 52-XV-228E | RU6-UTL | 52-XV-228E/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 14685 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-17 | 2102361842 | 8202232744 |  | 8202219428#Reposisi Blind 37-R-101 B | RU6-POC | 37-R-101B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 14651850 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352336 | 8202234145 |  | 8202219417#Perbaikan Tiang pancang BD-3& | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-C2H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-16 | 2026-02-02 | 2026-08-31 | 2102352255 | 8202234144 |  | 8202219410#CV Gas to Flare 101-PC-076 | RU2S-KIL | 101-PCV-076/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2ES | D12/26/B6/RTZ-D2H | 591002 | 591003 | MAS-INT |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102366106 | 8202239945 |  | 8202219409#24_91P402A, Perbaikan Couplin | RU4-SRU | 91P402A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 49000000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102361658 | 8202234102 |  | 8202219390#11-P-121A | RU6-HSC | 11-P-121A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102361757 | 8202233583 |  | 8202219389#Penggantian Membran Kopling 0 | RU6-UTL | 055-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238513 |  | 8202219387#Perbaikan Online Corrosion Mo | RU2-HSC | 8-P-039-B/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363686 | 8202232433 |  | 8202219385#Gearbox kasar 520-AG-1 | RU2-UTL | 520-AG-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363779 | 8202232663 |  | 8202219384#Major Repair 110-PT-3B | RU2-HOC | 110-PT-3B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/RT-D2H | 284000 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363964 | 8202232383 |  | 8202219381#Pengadaan Cat Untuk GHK Area | RU2-ITP |  | 50 | REL MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K202 | 2026-02-02 | 2026-06-11 | 2026-02-02 | 2026-11-30 | 2102352254 | 8202234143 |  | 8202219380#101-P-8C indikasi Vibrasi pad | RU2S-KIL | 101-P-8C-M/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2ES | D12/26/B6/RTZ-C2H | 0 | 31180000 | MAS-LIS |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-24 | 2102361710 | 8202233356 |  | 8202219375#Perbaikan 15-E-106A/B | RU6-RCC | 15-E-106A/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-13 | 2102360651 | 8202236051 |  | 8202219370#Perbaikan Pompa NaOH No. 2 De | RU5-UTL | 0UA-42-D004/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365480 | 8202239944 |  | 8202219369#24_Penggantian transmiter 143 | RU4-FOC1 | 14PT314B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2025-11-13 | 2025-11-13 | 2102361093 | 8202236483 |  | 8202219367#D24_Reaming Transmitter 101XI | RU4-RFCC | 101R501/00 | 60 | CLSD NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-08-10 | 2026-09-10 | 2102360479 | 8202236072 |  | 8202219366#Oil Purifier Alfa Laval U/ ST |  |  | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 2804938 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-08-10 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365856 | 8202239943 |  | 8202219365#24_Penggantian PG discharge 1 | RU4-RFCC | 101P528A/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 3677013 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361099 | 8202236494 |  | 8202219362#D24_Perbaikan 014FT-362 | RU4-FOC2 | 014FT362/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 045
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-08-10 | 2102361717 | 8202233510 |  | 8202219357#Penggantian Safety Relay 16P1 | RU6-RCC | 16-P-110A-M/01 | 50 WAMA | CRTD CSER MACM PRC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-04-27 |  | 8202233907 | 8202233718 | 8202219349#Memo 323 Actuator 53-XV-508/5 | RU6-UTL | 53-FT-002/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 39600 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-05 | 2026-02-05 | 2102363820 | 8202238195 |  | 8202219341#Pekerjaan TSA Grounding Bound | RU2-ITP | 509-MOV-900F/00 | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 2369196000 | 1 | MA4-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 | 2102361574 | 8202232760 |  | 8202219333#Pngdaan Pump Injection 52-B-1 | RU6-UTL | 52-B-101F-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-13 |  | 8202233156 |  | 8202219321#Perbaikan Heater 19-K-101 TH1 | RU6-RCC | 19-K-101-TH1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-11 |  | 8202233281 |  | 8202219311#Perbaikan 34-LV-400 | RU6-POC | 34-A-102-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-11 | 2026-06-11 | 2026-11-03 | 2102361654 | 8202232943 |  | 8202219305#Perbaikan Pompa 62-P-201B | RU6-UTL | 62-P-201B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 84653554 | 84640354 | MA4-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358647 | 8202234239 |  | 8202219299#Penggantian PSV di Om |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 3 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102360834 | 8202236040 |  | 8202219298#Perbaikan ATG Tangki V-16 | D&W-E5110 | V-16/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-10 | 2102363280 | 8202232822 |  | 8202219288#Perbaikan Valve Suction 36-P- | RU6-POC | 36-P-101B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1571401 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-04-02 | 2102360868 | 8202236035 |  | 8202219286#Penggantian Detector Fire Ala |  |  | 60 | REL CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | HSSE |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236037 |  | 8202219285#MAT.MODIF/TAMBAH LINE JUMPER | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 85569250 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237092 |  | 8202219265#D_24 Gasket Steam Drum Mud Ru | RU4-REL |  | 50 | CRTD CSER MACM PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-11-28 | 2025-11-28 |  | 8202237071 |  | 8202219262#D_24 Penggantian Filter 156A5 | RU4-RFCUTL |  | 01 | CRTD CSER MACM PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-STA |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-11-28 | 2025-11-28 | 2102361150 | 8202237039 |  | 8202219259#D_24 Perbaikan Butterfly Valv | RU4-UTL | 590A301K2/00 | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-STA |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 |  | 2025-11-28 | 2025-11-28 |  | 8202237049 |  | 8202219256#D_24 Perbaikan 63-A501AP2 str | RU4-RFCUTL |  | 01 | CRTD NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-STA |  |  |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365371 | 8202239942 |  | 8202219251#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E57K-G/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 97581201 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365370 | 8202239941 |  | 8202219250#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E57K-B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 97581201 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365359 | 8202239940 |  | 8202219249#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E56AK-B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 34250000 | 20000000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365358 | 8202239939 |  | 8202219248#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E56AK-A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 34250000 | 20000000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365357 | 8202239938 |  | 8202219246#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E53K-C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 74631068 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365356 | 8202239937 |  | 8202219245#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E52K-E/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 131100667 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365858 | 8202239936 |  | 8202219244#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E52K-B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 105600667 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365355 | 8202239935 |  | 8202219243#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E50K-R/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 152195235 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365566 | 8202239934 |  | 8202219242#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E50K-Q/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 152195235 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365354 | 8202239933 |  | 8202219241#24_[CR] Penyehatan Fin Fan 11 | RU4-FOC1 | 11E50K-N/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 152195235 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365322 | 8202239932 |  | 8202219239#24_relay proteksi ZCT untuk 0 | RU4-FOC2 | 019K102AM/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-2-C2H | 46690000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 |  | 8202234047 | 8202233087 | 8202219234#42-P-205 Pengadaan Coupling A | RU6-ITP | 42-P-205C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236024 | 8202235640 | 8202219228#MAT.PERB.PIPING PEMADAM JT 1& | RU5-E15500 | JT1-WFM-1200-01/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 173473220 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2102360761 | 8202236022 |  | 8202219227#pengadaan MCC & kelengkapan D |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 270382800 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-26 | 2102361652 | 8202233900 |  | 8202219225#Noise Motor 32-P-101B | RU6-HSC | 32-P-101B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363657 | 8202232391 |  | 8202219215#Conmon PTO 510-DE-11 | RU2-UTL | 510-DE-11/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365526 | 8202239931 |  | 8202219200#24_Pengadaan gasket strainer | RU4-LOC3 | LN260-1063JK/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-9-C2H | 0 | 0 | MA4-STA |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102362964 | 8202233738 |  | 8202219193#Pengantian mech seal 34-A-103 | RU6-POC | 34-A-103-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-31 | 2026-12-31 | 2102360864 | 8202235999 |  | 8202219192#Perbaikan K-235-01C | RU5-D&W | K-235-01C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-31 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-07-13 | 2102361190 | 8202237254 |  | 8202219190#CM_Bocoran Tube side 105E503 | RU4-GTO | 105E503/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365922 | 8202239930 |  | 8202219189#24_[CR] Mech Seal 024P117A Bo | RU4-LOC2 | 024P117A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 87508800 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-11 | 2026-01-02 | 2026-01-02 | 2102353366 | 8202235565 |  | 8202219180#Jasa Operator& Pem. Ringan Al | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF GMCO NMAT PRC SETC | 3RR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | MHAMDIBRD | 2026-05-07 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363630 | 8202232268 |  | 8202219175#Perbaikan lampu penerangan 94 | RU2-ITP | BL-B-1/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365374 | 8202239929 |  | 8202219170#24_[CR] Perbaikan Unloader 14 | RU4-FOC1 | 14K602A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 121600 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-01-02 | 2026-01-02 | 2102353369 | 8202234884 |  | 8202219161#Pengadaan Gearbox Mixer PET S | RU3-CDGP | PET-MAM-62-905/00 | 50 WAMA | REL MACM PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-24 |  | 8202232825 |  | 8202219160#Perbaikan valve outlet tanki | RU6-ITP | 42-T-403A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 14520 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365361 | 8202239928 |  | 8202219145#24_[CR] Penggantian pompa lub | RU4-FOC1 | 12K1C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-1-C2H | 894512000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-10-22 | 2026-10-28 | 2102359063 | 8202235995 |  | 8202219121#Material Perbaikan K-235-01A | RU5-D&W | K-235-01A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 24979712 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-22 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-01 | 2026-02-02 | 2026-05-08 | 2102361540 | 8202233805 |  | 8202219120#Pengadaan Lampu All Area RU V | RU6-DHC | 13-LPB-01/00 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 433827500 | 150420000 | MA2-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-27 | 2102363227 | 8202232938 |  | 8202219115#Perbaikan Pompa 63-P-301A | RU6-ITP | 63-P-301A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C1H | 26136 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360800 | 8202235997 |  | 8202219113#MAT.PERB.STANDPIPE/HYDRANT NO | RU5-E15500 | JT3-WFM-1200-05/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 26727039 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-02 |  | 8202235994 |  | 8202219112#Material Support TSA Lab AFID | RU5-LAB | BWB-316020/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/NR-C2H | 226153080 | 0 | LAB |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 | 2102361542 | 8202232190 |  | 8202219100#Tindaklanjut WO 8202207155 11 | RU6-HSC | 11-P-109A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-30 | 2025-12-30 | 2102360617 | 8202235968 |  | 8202219095#Perbaikan Motor Gm-3-15A | RU5-E15112 | GM-3-15A/00 | 60 | CLSD MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 459864 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-12-21 | 2026-12-21 | 2102360698 | 8202235966 |  | 8202219092#Perbaikan pompa G-2-09B | RU5-E15112 | G-2-09B/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 248061250 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-21 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361005 | 8202235114 |  | 8202219088#RKAP24_Mtl. Coalescer Element | RU4-FOC2 | 011V111/00 | 50 WAMA WASR | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365403 | 8202239927 |  | 8202219087#24_Penggantian 240LT_040 | RU4-LOC3 | 240LT040/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365309 | 8202239926 |  | 8202219086#24_Penggantian 16LI-014 | RU4-FOC1 | 16LT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-1-C2H | 3 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365372 | 8202239925 |  | 8202219085#24_Penggantian 13FT013 | RU4-FOC1 | 13FT013/00 | 60 | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 19250000 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366101 | 8202239924 |  | 8202219084#24_Pengadaan material TDR FOC | RU4-FOC1 | 11FT701/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 90052692 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2102360573 | 8202235969 |  | 8202219080#Perb. lampu 2Ea pada OC "O" j | RU5-TBL | PLANT-21-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 38681100 | 0 | MA4-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2102360165 | 8202235992 |  | 8202219079#Motor mixer NaOH Demin |  |  | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 255217 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102359068 | 8202235993 |  | 8202219077#MAT.PERB.LINE 21-P26-6" SLOP | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 28821737 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365311 | 8202239922 |  | 8202219070#24_Overhoul motor 240S_120 P1 | RU4-LOC3 | 240S120P1M/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 424800 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102359065 | 8202235938 |  | 8202219068#MAT.PERB.LINE 21-P812-6" SLOP | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 224022692 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360938 | 8202235932 |  | 8202219065#MAT.PERB.LINE DISCH GM-34-91B | RU5-TBL | OFC03401/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 23965374 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102359989 | 8202235928 |  | 8202219062#MAT.PERB.LINE SUCT POMPA TORA | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 8171276 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-26 | 2102359480 | 8202235926 |  | 8202219061#Mat'l Piping Condensate Coole |  | E-37-02/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 33564789 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102359409 | 8202235962 |  | 8202219060#Mat. Drain Water Box Evaporat |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 56437858 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360767 | 8202235930 |  | 8202219056#MAT.PERB.LINE MP STEAM POMPA | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 24207725 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K201 | 2026-02-06 | 2026-03-11 | 2026-02-06 | 2026-02-06 | 2102363962 | 8202238702 |  | 8202219049#Perbaikan Pompa 110 PM-5A | RU2-HOC | 110-PM-5A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/NR-D2H | 883452 | 0 | MA1-LIS |  | SUJATMIKO1 |  | 2026-02-09 | PT02 |  | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 | 2102359878 | 8202235941 |  | 8202219045#MAT.PERB.LINE 21-P73-6" SERVI | RU5-TBL | D-20-04B/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 139498949 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360620 | 8202235933 |  | 8202219044#MAT.PERB.LINE 21P-756-10 CRUD | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 51257715 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 | 2102360865 | 8202235939 |  | 8202219043#MAT.PERB.LINE 21-P753-10" & 2 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 11894405 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 | 2102359247 | 8202235936 |  | 8202219042#MAT.PERB.LINE 21-P913-20" KER | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 110543427 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360793 | 8202235894 |  | 8202219026#MAT.PERB.STANDPIPE NO. 38 DI | RU5-E15500 | JT4-SPH-002/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 30944798 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 | 2102363011 | 8202232735 |  | 8202219022#Stem control valve lepas | RU6-RCC | 15-FV-018/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237962 | 8202237868 | 8202219021#Amandemen Perbaikan Crane Lin |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360805 | 8202235903 |  | 8202219016#MAT.PERB.LINE FIRE MONITOR 7 | RU5-E15500 | JT4-WFM-1200-07/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 192641703 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360801 | 8202235896 |  | 8202219015#MAT.PERB.STANDPIPE NO. 35 DI | RU5-E15500 | JT4-WFM-1200-07/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 47664138 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 | 2102360798 | 8202235899 |  | 8202219011#MAT.PERB.LINE FOAM MNTR 4 & S | RU5-E15500 | JT2-WFM-1200-03/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 230295829 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360799 | 8202235910 |  | 8202219010#MAT.GANTI VALVE LINE HEADER F | RU5-E15500 | JT1-WFM-1200-01/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 9898109 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366108 | 8202239921 |  | 8202219007#24_[CR] 24E1A Bearing Rusak | RU4-LOC1 | 24E1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 98881200 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365968 | 8202239920 |  | 8202219006#24_Service Motor 166P565B (MA | RU4-RFCGTO | 166P565B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365967 | 8202239919 |  | 8202219005#24_Service Motor 166P565A (MA | RU4-RFCGTO | 166P565A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365587 | 8202239918 |  | 8202219004#24_166K5511AM Service (MA7 El | RU4-RFCGTO | 166P553A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-14-C2H | 463400 | 0 | MA7-LIS |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365966 | 8202239917 |  | 8202219003#24_Service Motor 166P512BM (M | RU4-RFCUTL | 166P512B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 2750000 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102360797 | 8202235907 |  | 8202219001#MAT.PERB.LINE FIRE MONITOR 1& | RU5-E15500 | JT1-WFM-1200-01/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 197389848 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365615 | 8202239916 |  | 8202218995#24_Service motor 166K5511CM | RU4-RFCUTL | 166P510M/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-14-C2H | 463400 | 0 | MA7-LIS |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353373 | 8202235518 |  | 8202218992#Kerusakan Flowmeter Dermaga |  |  | 60 | REL NMAT PRC SETC | 3IR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365529 | 8202239915 |  | 8202218978#24_Penambahan FI N2 Supp ke A | RU4-KPC | 84FE232/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-10-C2H | 54690550 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366074 | 8202239914 |  | 8202218977#24_Penambahan FT,PT N2 KPC ke | RU4-TRML | 36T105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 86592157 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363598 | 8202232246 |  | 8202218976#Belting Fin Fan Desalter | RU2-HSC | 100-A-301-E01B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-12 | 2102363223 | 8202233718 |  | 8202218972#Penggantian 53-FT-002 | RU6-UTL | 53-FT-002/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 10643 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-12 | 2102363171 | 8202233719 |  | 8202218970#Penggantian 53-FT-001 | RU6-UTL | 53-FT-001/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 10643 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363669 | 8202232418 |  | 8202218968#Conmon Filter 905-TG-3 | RU2-UTL | 905-GT-3/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 223353600 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363668 | 8202232415 |  | 8202218967#Conmon Filter 905-TG-5 | RU2-UTL | 905-GT-5/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-15 | 2102362871 | 8202234026 |  | 8202218964#Equipment 15-A-107 Part 2 Reg | RU6-RCC | 15-A-107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 | 2102360785 | 8202235891 |  | 8202218955#MAT.PERB.LINE 21-P220-3" RFO | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 18356372 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358698 | 8202237961 |  | 8202218954#LTSA AC CONTROL & AC Split Ar |  |  | 60 | CRTD NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 3463500000 | 0 | MA-LINT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358707 | 8202237960 |  | 8202218952#LSTA ATG dan IHLA Tokyo Keiso |  |  | 60 | CRTD NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 2100000000 | 0 | MA-LINT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-12-18 | 2102360998 | 8202234967 |  | 8202218946#SIP_Matl Rejuvenate Isolasi M | RU4-RFCC | 104-WT0822-3-4/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102364373 | 8202233767 |  | 8202218943#Pengadaan parts pompa | RU6-ITP | 42-P-305/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102364371 | 8202233766 |  | 8202218941#Pengadaan parts pompa | RU6-ITP | 42-P-301B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360956 | 8202237033 |  | 8202218934#D_24 Perbaiki push bottom 041 | RU4-TRML | 041P108B/00 | 60 WASR | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233077 |  | 8202218933#Perbaikan modul 61-LT-601 | RU6-HSC | 61-LV-601/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361159 | 8202237091 |  | 8202218931#D_24 Kabel motor 021P113B sho | RU4-LOC2 | 021P113B/00 | 60 WASR | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361162 | 8202237098 |  | 8202218930#D_24 019P-124B Motor Trip2an, | RU4-FOC2 | 019P124BM/00 | 60 WASR | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361168 | 8202237140 |  | 8202218929#D_24 011P128B motor terlepas | RU4-FOC2 | 011P128BM/00 | 60 WASR | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 |  | 8202238512 |  | 8202218922#AUDIT KINERJA/ KALIBRASI CEMS | RU2-HOC | 110-V-1/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | WS-IN1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-29 |  | 8202238017 | 8202233162 | 8202218921#Refurbishment Gearbox Assy 14 | RU6-DHC | 14-P-102A/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-16 | 2026-01-02 | 2026-01-02 | 2102352259 | 8202234142 |  | 8202218920#101-P-7B indikasi damage pada | RU2S-KIL | 101-P-7B/00 | 50 | REL CSER GMPS MSPT PRC SETC | 2RS | D12/26/B6/RTZ-D3H | 6423874 | 165000 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352258 | 8202234141 |  | 8202218914#900-02-P-3A Indikasi Vibrasi | RU2S-KIL | 900-02P-3A/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-D3H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233078 |  | 8202218913#Perbaikan modul 61-FT-501 | RU6-HSC | 61-FV-501/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233592 |  | 8202218912#Penggantian Limit Switch 052- | RU6-UTL | 052-XV-909A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 26483 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-15 | 2102364223 | 8202233540 |  | 8202218911#Penggantian positioner FDF Bo | RU6-UTL | 52-FV-206E/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 33000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202233079 |  | 8202218909#Perbaikan modul 61-FT-401 | RU6-HSC | 61-FV-401/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365312 | 8202239913 |  | 8202218899#24_Perbaikan 54LT301 Level Tr | RU4-UTL | 54LT301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 25200000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-12-31 | 2025-12-31 | 2102360126 | 8202235863 |  | 8202218885#Penggantian MechSeal G-34-115 | RU5-D&W | G-34-115B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 16119888 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-08-26 | 2102360943 | 8202237492 |  | 8202218871#DEG 80G201 Rusak | RU4-KPC | 80G201/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352268 | 8202234140 |  | 8202218868#Instalasi Air Compressor Alta | RU2S-KIL | 900-09AC-4/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C3H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363757 | 8202232586 |  | 8202218865#Perbaikan soot blower 550-B-M | RU2-UTL | 550-SOBL-2-B2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102363094 | 8202233723 |  | 8202218864#Penggantian 51-VT-239C | RU6-UTL | 51-G-101C-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 15923 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-30 | 2026-08-04 | 2102362969 | 8202233166 |  | 8202218860#Perbaikan Flexible Joint 21-F | RU6-DHC | 21-F-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 2304 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365306 | 8202239912 |  | 8202218854#24_Penggantian 63_FI609D Flow | RU4-RFCUTL | 63FT609D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2027-01-26 | 2102362960 | 8202237736 |  | 8202218851#Penyediaan Tenaga Kerja Welde | RU6-RCC | 20-R-101A/00 | 60 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 1717240000 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-23 | 2025-12-23 | 2102363753 | 8202232573 |  | 8202218849#Perbaikan Trafo 140-PM-17B | RU2-UTL | 905-TRF-17B/00 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366091 | 8202239911 |  | 8202218847#[CR] Sproket dan bearing 24E- | RU4-LOC1 | 24E2B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 94500000 | 27000000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202233439 |  | 8202218846#Penggantian valve drain pompa | RU6-UTL | 56-P-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 23760 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366090 | 8202239910 |  | 8202218843#24_[CR] Sproket dan bearing 2 | RU4-LOC1 | 24E2A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 94500000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-12 | 2102363015 | 8202233491 |  | 8202218827#Penggantian Speed indicator | RU6-UTL | 51-G-101E-P1A-T/00 | 60 | REL MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 63522803 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-11 | 2026-01-30 | 2026-09-29 | 2102360537 | 8202235769 |  | 8202218815#24_Loader Valve Kompressor | RU4-KPC | 82K201A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH | 2026-03-12 | 2026-02-07 | PT02 |  | 3 | 2026-03-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102359241 | 8202235830 |  | 8202218814#Perbaikan Pompa G-2-16A | RU5-E15112 | G-2-16A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 51286221 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-31 | 2025-12-31 | 2102360937 | 8202235832 |  | 8202218813#Perbaikan pompa G-2-07A | RU5-E15112 | G-2-07A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 29027500 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-02 | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102360120 | 8202235855 |  | 8202218812#Perbaikan G-3-44B | RU5-E15112 | G-3-44B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 5756744 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-24 | 2026-06-02 | 2026-06-02 | 2102360861 | 8202235858 |  | 8202218809#Leak swivel joint line vapor | RU5-TBL | L-ARM-1-JT-3/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 7012725 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365911 | 8202239909 |  | 8202218806#24_Perbaikan thermocouple 052 | RU4-UTL | 052B104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 1205667 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2025-12-18 | 2025-12-18 | 2102360897 | 8202235859 |  | 8202218804#KT-5-02B (pengadaan spare cou | RU5-E15111 | KT-5-02B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | BAMBANGSS | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352284 | 8202234139 |  | 8202218803#Flow Meter F-132 | RU2S-KIL | 946-ITP-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C3H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-10-20 |  | 8202232845 |  | 8202218801#Perbaikan transmitter pada 15 | RU6-RCC | 15-B-101/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-09-22 |  | 8202233329 |  | 8202218800#Perbaikan 16-PSHH-512 & 16-PS | RU6-RCC | 16-A-101/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2027-01-04 |  | 8202234086 |  | 8202218799#15UV038 anomali | RU6-RCC | 15-UV-038/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-07-27 |  | 8202234091 |  | 8202218798#15FT501 anomali | RU6-RCC | 15-FT-501/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-09-09 | 2102364261 | 8202233562 |  | 8202218797#penggantian PG Diafragma 11-P | RU6-HSC | 11-P-101A-P1-M/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-09-23 | 2102364262 | 8202233561 |  | 8202218796#penggantian PG Diafragma 11-P | RU6-HSC | 11-P-101A-P1-M/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 |  | 8202235852 |  | 8202218788#Perbaikan panel Fire Suppress |  |  | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | HSSE |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-12-21 | 2026-12-31 | 2102360857 | 8202235856 |  | 8202218787#Perbaikan bearing turbine BFW | RU5-UTL | T-BFW-P-0101B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 97878320 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-21 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-03 |  | 8202233366 |  | 8202218783#Perbaikan 13-PV-293 | RU6-DHC | 13-PV-293/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 |  | 2025-12-05 | 2026-01-28 |  | 8202233361 |  | 8202218774#Perbaikan 14-P-903A-M | RU6-DHC | 14-P-903A-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/24/B6/RT-C2H | 384 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2027-01-25 |  | 8202236852 | 8202233867 | 8202218768#PM 1 - LTSA FGDS Merk Sieger | RU6-LK/KK | 66-CGD-01/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352313 | 8202234138 |  | 8202218758#Flow Meter Own Use ADO F-124 | RU2S-KIL | 900-08PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-D3H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365606 | 8202239908 |  | 8202218751#24_Pembelian PU foam untuk 20 | RU4-LOC3 | 200SS1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-9-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-31 | 2102360832 | 8202235812 |  | 8202218745#Perbaikan Thermowell F-2-01A | RU5-E15112 | F-2-01A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 114000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363580 | 8202232219 |  | 8202218739#Pengadaan Material Control Fl | RU2-HOC | 110-FV-119A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/24/B6/NR-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-09 | 2102360624 | 8202235820 |  | 8202218736#Oil Vapour fan STG 2.1 | RU5-UTL | 1SC00D005/00 | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 48626 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365507 | 8202239907 |  | 8202218730#24_[CR] Perbaikan diesel engi | RU4-TRML | 38P111D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-3-C2H | 37549000 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-16 | 2025-12-31 | 2102360833 | 8202235816 |  | 8202218727#Perb. Sal RFO Line Oil Heater | RU5-UTL | HHP-1/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 128 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-12-16 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365862 | 8202239906 |  | 8202218725#24_[CR] Perbaikan HE Fire Pum | RU4-RFCUTL | 155P501C-EN/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-13-C2H | 1891500 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 | 2102351004 | 8202232195 |  | 8202218722#Indikasi driver motor stator | RU6-RCC | 15-K-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-07 | 2102362924 | 8202232884 |  | 8202218720#Perbaikan silincer 25-K-103 | RU6-HSC | 25-K-103-A1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-11-25 | 2026-12-22 |  | 8202235807 |  | 8202218717#GANTI UNIT COMPLETE E-35-104B | RU5-E15112 | K-35-102C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D16/26/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-11-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365347 | 8202239905 |  | 8202218712#24_Perbaikan 82FT226 | RU4-KPC | 82FT226/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365984 | 8202239904 |  | 8202218711#24_Pressure Gauge 106T501 Loc | RU4-RFCGTO | 106PG-U106/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 739500 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-08 | 2026-01-26 |  | 8202233844 |  | 8202218708#Penambahan N2 (tabung) untuk | RU6-RCC | 19-PTR1-01A/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/24/B6/RT-C2H | 533 | 0 | MA4-LIS |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365900 | 8202239903 |  | 8202218707#24_Power Supply 106FV001 Rusa | RU4-RFCGTO | 106FV001/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 10000000 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361095 | 8202236486 |  | 8202218705#D24_Perbaikan Connector Hyd 1 | RU4-RFCC | 101A514/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-15 | 2026-02-05 | 2026-02-05 | 2102363971 | 8202238511 |  | 8202218702#Perbaikan Unit Ex-used (140 P | RU2-HOC | 140-PX-52/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA1-ROT |  | MSADLI |  | 2026-02-10 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-17 | 2102360858 | 8202235798 |  | 8202218701#Perbaikan Bearing Motor P-04 |  |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1022731 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K601 | 2026-02-01 |  | 2025-12-05 | 2026-01-28 |  | 8202233408 |  | 8202218692#Perbaikan 12-E-505B-M | RU6-DHC | 12-E-505B-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/24/B6/RT-C2H | 384 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363691 | 8202232440 |  | 8202218690#gearbox alarm vibration |  | 211-P-6AR/01 | 60 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 23020610 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363653 | 8202232385 |  | 8202218687#Conmon PTO 510-DE-12 | RU2-UTL | 510-DE-12/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363742 | 8202232551 |  | 8202218686#Mech Seal Bocor | RU2-HCC | 702-P-3A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363738 | 8202232543 |  | 8202218685#mechanical seal pompa bocor | RU2-HCC | 702-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 59529958 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-12 | 2026-02-02 | 2026-02-02 | 2102363736 | 8202232541 |  | 8202218684#mechseal bocor | RU2-HCC | 212-P-25B/00 | 60 | REL PRT NMAT PRC SETC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA2-ROT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363740 | 8202232549 |  | 8202218683#Mech.seal bocor NDE Side | RU2-HCC | 212-P-1/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363592 | 8202232263 |  | 8202218682#Abnormal Noise | RU2-HCC | 211-P-53B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 87042282 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363641 | 8202232309 |  | 8202218676#Perbaikan Header Strainer Suc | RU2-UTL | 520-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-08-26 | 2102360955 | 8202237022 |  | 8202218661#D_24 Ring Burner & Karet Burn | RU4-UTL | 52B2-BF/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365823 | 8202239902 |  | 8202218657#24_[MOC] Pengadaan Booster Pu | RU4-UTL | 051P103B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 47500000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-05 | 2026-07-27 | 2102362837 | 8202233867 |  | 8202218655#Pelaksanaan LTSA FGDS Merk Si | RU6-LK/KK | 66-CGD-01/00 | 50 | CRTD NMAT PRC | 6IR | D16/25/B6/RT-C2H | 9024 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-12-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-18 | 2026-06-18 | 2026-08-18 | 2102360850 | 8202235747 |  | 8202218649#Pengadaan Bejana Ukur 60L Met | RU5-TBL | METER-4571/00 | 60 | REL CSER MANC PRC SETC | 5IR | D15/26/B6/RT-C2H | 110000000 | 0 | MA4-INT |  | RIANDAADI |  | 2026-02-11 | PT02 |  | 3 | 2026-06-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234017 |  | 8202218643#Indikasi bocoran line LS deka | RU6-POC | 35-P-102A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C3H | 1504147 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-05 | 2026-06-02 | 2102362776 | 8202233978 |  | 8202218626#LTSA FGDS Merk General Monito | RU6-LK/KK | 66-CGD-01/00 | 50 | CRTD NMAT PRC | 6IR | D16/24/B6/RT-C2H | 6912 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365575 | 8202239901 |  | 8202218619#24_Relay Pilot 105F501 Rusak | RU4-RFCGTO | 105F501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-07-10 |  | 8202232840 |  | 8202218610#Perbaikan Tubing Re-grease Al | RU6-UTL | 052-K-102D1-M/00 | 50 | CRTD CSER MACM PRC | 6ER | D16/24/B6/RT-C2H | 13200 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365488 | 8202239900 |  | 8202218599#24_56K3A : Perbaikan Alarm ND | RU4-UTL | 56K3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365525 | 8202239899 |  | 8202218597#24_Penggantian Ampermeter 240 | RU4-LOC3 | 240K101M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-9-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-05 | 2026-02-05 | 2102363256 | 8202238517 |  | 8202218592#Perbaikan Pipa Distribusi WTP | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/NR-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365726 | 8202239898 |  | 8202218588#24_Pengadaan materia transmit | RU4-FOC1 | 11LT701/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 25267865 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365497 | 8202239897 |  | 8202218586#24_Penggantian Pressure Gauge | RU4-RFCC | 104P501A/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1219906 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366036 | 8202239896 |  | 8202218584#24_Pengadaan solenoid KV Drai | RU4-LOC2 | 024S101C/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 168162000 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237473 |  | 8202218578#Pengadaan Actuator-Servo Elec | RU2S-KIL | 900-06GE-7/00 | 50 | REL MACM PRC SETC | 2MS | D12/24/B6/RTZ-D2H | 0 | 0 | MAS-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358690 | 8202237959 |  | 8202218576#Routine Maintenance Semester |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358691 | 8202237958 |  | 8202218575#Routine Inspection Semester I |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-03 |  | 2026-02-03 | 2026-02-03 |  | 8202237472 |  | 8202218573#Material Tambahan utk line By | RU2S-KIL | 101-E-7A/00 | 01 | CRTD NMAT PRC | 2MS | D12/24/B6/RTZ-D3H | 0 | 0 | MAS-ME1 |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 |  | 8202236849 |  | 8202218569#PM 3 - LTSA Asphaltene Analyz | RU6-LAB | LABORATORIUM/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-07 | 2026-02-05 | 2026-02-05 | 2102352356 | 8202238194 |  | 8202218564#Perbaikan kompresor CAB | RU3-CDL | FC-B-2/00 | 60 | REL NMAT PRC SETC | 3RR | D13/25/B6/RT-2-D2H | 1 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358696 | 8202234233 |  | 8202218555#Perbaikan pompa 2-P-02B Mech |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365732 | 8202239895 |  | 8202218550#24_[BD] Perbaikan Pompa 42P10 | RU4-TRML | 42P101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 6928350 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102362830 | 8202233956 |  | 8202218541#Mat Per Turbine SPK 7 19-P-11 | RU6-RCC | 19-P-114B-T/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202233087 |  | 8202218540#Perbaikan membran coupling | RU6-ITP | 42-P-205C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365556 | 8202239894 |  | 8202218538#24_[CR] Penggantian Bearing F | RU4-SRU | 91E409B2M/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 10798760 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102366092 | 8202239893 |  | 8202218532#24_Perbaikan Mec.seal 240P102 | RU4-LOC3 | 240P102A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 50600000 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-05 | 2025-12-03 | 2102360863 | 8202235727 |  | 8202218529#Penggantian Valve drain Suct | RU5-D&W | T-34-12A/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 236318385 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365521 | 8202239892 |  | 8202218521#24_91PDIT-576 rusak | RU4-SRU | 91PDIT576/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365336 | 8202239891 |  | 8202218520#24_Perbaikan 260LAL_092 A | RU4-LOC3 | 260LSL092/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365335 | 8202239890 |  | 8202218519#24_Perbaikan 260LAL_091 A | RU4-LOC3 | 260LSL091/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-9-C2H | 0 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365530 | 8202239889 |  | 8202218518#24_Penggantian PG Outlet 101E | RU4-RFCC | 101E527A/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1203448 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365487 | 8202239888 |  | 8202218515#24_Perbaikan 52PV004AB | RU4-UTL | 52PV005B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365486 | 8202239887 |  | 8202218514#24_Perbaikan 52PV005B | RU4-UTL | 52PV005B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232939 |  | 8202218507#Perbaikan Pompa 63-P-201A | RU6-ITP | 63-P-201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-09-02 | 2102360987 | 8202234658 |  | 8202218505#RKA_24 Penggantian Int Tube 5 | RU4-UTL | 56D101/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-29 | 2026-08-03 |  | 8202233951 |  | 8202218500#Mat'l Soft Good Kit 14-PSV-40 | RU6-DHC | 14-PSV-403/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C1H | 2304 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-29 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-11-19 | 2026-11-26 | 2102358985 | 8202235724 |  | 8202218497#Ganti Rubber coupling FDF T B |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 2376000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-19 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-09-23 |  | 8202236668 |  | 8202218485#SWO Pemb thp 1 LTSA PT Spektr | RU6-LAB | LABORATORIUM/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102352281 | 8202234137 |  | 8202218480#900-01P-1D/00 Vibrasi pompa h | RU2S-KIL | 900-01P-1D/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RS | D12/26/B6/RTZ-D2H | 950000 | 950000 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-19 | 2026-02-02 | 2026-02-02 | 2102352302 | 8202234136 |  | 8202218479#101-P-3B-M | RU2S-KIL | 101-P-3B-M/00 | 50 | REL CSER GMPS MANC PRC SETC | 2ES | D12/26/B6/RTZ-D2H | 7900410 | 5442410 | MAS-LIS |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202233081 |  | 8202218474#Perbaikan Mixer Tanki 42-M-10 | RU6-ITP | 42-M-107C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102366089 | 8202239886 |  | 8202218472#24_Penggantian (PI) Discharge | RU4-UTL | 57P201C/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 75875564 | 0 | MA5-INT |  | REHANR |  | 2026-03-10 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102366088 | 8202239885 |  | 8202218471#24_Penggantian (PI) Discharge | RU4-UTL | 54P201AM/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 75875564 | 0 | MA5-INT |  | REHANR |  | 2026-03-10 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102366076 | 8202239884 |  | 8202218470#24_Penggantian PI flue gas 52 | RU4-UTL | 52B201/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 75875564 | 0 | MA5-INT |  | REHANR |  | 2026-03-10 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 |  | 8202233919 |  | 8202218468#Material Tambahan 11-P-113A | RU6-HSC | 11-P-113A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365541 | 8202239883 |  | 8202218467#24_Penggantian Dial TI 13K-1A | RU4-FOC1 | 13K1AP2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-1-C2H | 10 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365494 | 8202239882 |  | 8202218465#24_Penggantian PG suction 101 | RU4-RFCC | 101P523B/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 1203448 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232975 |  | 8202218461#Perbaikan Pompa 24-P-103A | RU6-HSC | 24-P-103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365921 | 8202239881 |  | 8202218455#24_[CR] Scroll 024S101A Macet | RU4-LOC2 | 024S101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 8666667 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365630 | 8202239880 |  | 8202218454#24_Motor 021E130M4 noise | RU4-LOC2 | 021E130M04/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-8-C2H | 1429050 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365499 | 8202239879 |  | 8202218443#24_Penggantian PG outlet tube | RU4-RFCC | 101E523A/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2741791 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365563 | 8202239878 |  | 8202218442#24_021LT009 penunjukkan error | RU4-LOC2 | 021LT009/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 | 2102360890 | 8202235672 |  | 8202218440#Penggantian butterfly valve G | RU5-D&W | G-34-109A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 24073401 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365581 | 8202239877 |  | 8202218436#24_Penggantian Level Transmit | RU4-RFCUTL | 151B501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-08-10 |  | 8202232800 |  | 8202218435#Permintaan gas carrier 19-AT- | RU6-RCC | 19-AT-003/00 | 50 | CRTD CSER MACM PRC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365580 | 8202239876 |  | 8202218432#24_Penggantian Level Transmit | RU4-RFCUTL | 151B501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102366041 | 8202239875 |  | 8202218421#24_[CR] Perbaikan 14E605A | RU4-FOC1 | 14E605/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 10798760 | 60698760 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-05 | 2102360913 | 8202235664 |  | 8202218411#Perbaikan Motor Eam-201-03A | RU5-D&W | EAM-201-03A/00 | 60 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 401000 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365855 | 8202239874 |  | 8202218407#24_[CR] Ganti Mechanical seal | RU4-TRML | 71P1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 62487250 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-08-14 | 2102360997 | 8202234886 |  | 8202218396#Refurbish ex-63-P502A | RU4-RFCUTL | 63P502A/00 | 60 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-11-26 | 2026-12-29 | 2102358895 | 8202235667 |  | 8202218393#Perb.Saluran cond sebelum PSV | RU5-UTL | 031-PSV-01A/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 1089186 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-26 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360892 | 8202235662 |  | 8202218392#Perb. Line Outfall utara PP1 | RU5-UTL | PP1-/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-09-09 | 2102361031 | 8202235606 |  | 8202218389#Perbaikan Pompa 63-P-502B (Pe | RU4-RFCUTL | 63P502B/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/25/B6/NR-13-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-06-30 |  | 8202236742 | 8202234096 | 8202218376#SPK 9 LTSA Transformator RU V | RU6-RCC | 14A-PTR1-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 | 2102359182 | 8202235659 |  | 8202218373#MAT.PERB.PIPING PEMADAM JETTY | RU5-E15500 | JT5C-WF-1000-05/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 629374177 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202233269 |  | 8202218371#Perbaikan 38-K-101 B #2 | RU6-POC | 38-K-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-03 | 2025-12-23 | 2102360919 | 8202235649 |  | 8202218369#Ganti valve 8 inch drain Grav | RU5-UTL | DM-4-P111/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-PDNH | 192 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-12-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365333 | 8202239873 |  | 8202218360#24_Perbaikan 14FT-053 | RU4-FOC1 | 14FT553/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/24/B6/RT-1-C2H | 1 | 21500000 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365332 | 8202239872 |  | 8202218359#24_Perbaikan 14FT-524 | RU4-FOC1 | 14FT524/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/24/B6/RT-1-C2H | 1 | 21500000 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365331 | 8202239871 |  | 8202218358#24_Perbaikan 14FT503 | RU4-FOC1 | 14FT503/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/24/B6/RT-1-C2H | 1 | 21500000 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365349 | 8202239870 |  | 8202218352#24_Penggantian PG Outlet 101E | RU4-RFCC | 101E526B/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1203448 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365490 | 8202239869 |  | 8202218351#24_Penggantian Level Transmit | RU4-UTL | 052LT402/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 18500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365551 | 8202239868 |  | 8202218349#24_Penggantian Flow Transmitt | RU4-UTL | 052LT401/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 18500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365459 | 8202239867 |  | 8202218346#24_Penggantian Level Transmit | RU4-UTL | 052LT401/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 18500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-02 | 2102359123 | 8202235642 |  | 8202218338#Perbaikan MOV K-3-02 | RU5-E15112 | K-3-02B/00 | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-10-21 |  | 8202234020 |  | 8202218336#Gas kalibrasi CEM habis | RU6-RCC | 15-B-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363751 | 8202232565 |  | 8202218333#penggantian dengan globe valv | RU2-HCC | 212-P-6/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 3423966 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234003 |  | 8202218331#Kebocoran Flange Channel Cove | RU6-POC | 37-E-105/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C3H | 6835460 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365560 | 8202239866 |  | 8202218330#24_[CR] Perbaikan Mech Seal 2 | RU4-LOC1 | 21P5/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 11664200 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102360751 | 8202235644 |  | 8202218327#Perbaikan Ea-32-01T | RU5-E15112 | EA-32-01T/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 9999444 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365906 | 8202239865 |  | 8202218320#24_[CR] 011P128B: Coupling de | RU4-FOC2 | 011P128B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 901200 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365602 | 8202239864 |  | 8202218318#24_Perbaikan Positioner 052FV | RU4-UTL | 560PSV602/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232177 |  | 8202218313#Total Solution Fin-Fan 20-E-1 | RU6-RCC | 20-E-107G/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232179 |  | 8202218310#Total Solution Fin-Fan 16-E-1 | RU6-RCC | 16-E-120J/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232181 |  | 8202218305#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-110W/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232182 |  | 8202218304#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-110U/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-19 | 2102359184 | 8202235640 |  | 8202218302#MAT.PERB.PIPING PEMADAM JETTY | RU5-E15500 | JT1-WFM-1200-01/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 162801174 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2025-11-14 | 2025-12-12 | 2102360234 | 8202235597 |  | 8202218298#Perbaikan VCB Outgoing Feeder | RU5-UTL | 41-R-SS-63-LIS/00 | 60 | CLSD CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 258 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-13 | 2102360233 | 8202235601 |  | 8202218297#Perbaikan VCB Outgoing Feeder | RU5-UTL | 41-R-SS-62-LIS/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2025-11-18 | 2025-12-24 | 2102360231 | 8202235602 |  | 8202218295#Perbaikan VCB Outgoing Feeder | RU5-UTL | 41-R-SS-61-LIS/00 | 60 | CLSD CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 346 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-05 | 2102358981 | 8202235605 |  | 8202218291#Perbaikan LCS GM-319-05B |  | GM-319-05B/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 2 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359243 | 8202235607 |  | 8202218284#Perb Modul Temperature HHP Bo | RU5-UTL | HHP-5/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 111000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363750 | 8202232564 |  | 8202218278#Perbaikan V Belt 701 EF-9C | RU2-HCC | 701-EF-9C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232184 |  | 8202218269#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-110AM/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-08 | 2026-02-02 | 2027-01-26 |  | 8202232185 |  | 8202218268#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-110AL/00 | 60 | REL CSER GMPS MANC PRC SETC | 6RR | D16/25/B6/RT-C2H | 16329891 | 16329890 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232186 |  | 8202218264#Total Solution Fin-Fan 15-E-1 | RU6-RCC | 15-E-110AB/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365586 | 8202239863 |  | 8202218262#24_Pressure Gauge Outlet 105F | RU4-RFCGTO | 105PG-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366112 | 8202239862 |  | 8202218261#24_Perbaikan actuator SOV FO | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102366072 | 8202239861 |  | 8202218249#24_[CR] Perbaikan 14K1P2A-T | RU4-FOC1 | 14K1P2A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-29 | 2025-12-09 | 2025-12-11 | 2102359245 | 8202235594 |  | 8202218245#Perbaikan EM-1-28 A | RU5-E15111 | EM-1-28A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 446413 | 0 | MA2-LIS |  | SAPBATCH | 2026-05-29 | 2026-02-11 | PT02 |  | 3 | 2026-05-29 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365561 | 8202239860 |  | 8202218232#24_[CR] Penggantian bearing 0 | RU4-LOC2 | 024E101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 494016 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-06-29 |  | 8202233142 |  | 8202218222#Perbaikan Kabel Motor Aux Pum | RU6-UTL | 56-P-101D-P1B-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 2460 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-27 |  | 8202233698 |  | 8202218218#Penggantian bearing motor 16- | RU6-RCC | 16-E-117AB/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 73943 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-27 |  | 8202233068 |  | 8202218216#Perbaikan Motor 11-E-117B | RU6-HSC | 11-E-117B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 73943 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102359983 | 8202235587 |  | 8202218208#Perb. Inlet pendingin kondens | RU5-UTL | TG-6-PP1/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 4501447 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-06-04 | 2026-07-03 | 2102360689 | 8202235589 |  | 8202218205#Penggantian Tangki NaOH Demin | RU5-UTL | D5-BV-2-1/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 |  | 8202233827 |  | 8202218204#Pengadaan consumable material | RU6-UTL | 52-B-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 19800 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-27 |  | 8202234043 |  | 8202218203#Abnormal noise motor 16-E-117 | RU6-RCC | 16-E-117AC/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 73943 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-04 | 2102363815 | 8202238147 |  | 8202218196#Perbaikan Autotrafo 140-PM-17 | RU2-UTL | 905-TRF-17B/00 | 50 | REL NMAT PRC SETC | 2ER | D12/24/B6/RT-D2H | 597512000 | 0 | MA1-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 004
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363812 | 8202238140 |  | 8202218195#Perbaikan 925 PM-7C | RU2-UTL | 925-PM-7C/01 | 50 | REL NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 004
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-23 |  | 8202233367 |  | 8202218191#Perbaikan 13-PV-065 | RU6-DHC | 13-PV-065/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233211 |  | 8202218188#Perbaikan bocoran weld di 38- | RU6-POC | 38-V-105/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 6112057 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233872 |  | 8202218187#Pekerjaan MOC No 1963/POC/IV/ | RU6-POC | 36-PSV-001A/00 | 50 | REL CSER GMPS MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 4666563 | 7627500 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365344 | 8202239859 |  | 8202218186#24_84TSHH551B Rusak | RU4-FOC2 | 84TSHH551B/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 37000000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365346 | 8202239858 |  | 8202218185#24_84TSHH551A Rusak | RU4-FOC2 | 84TSHH551A/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 37000000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365559 | 8202239857 |  | 8202218184#24_24K-1 TT-027 Penunjukan Te | RU4-LOC1 | 24TT027/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 28000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232801 |  | 8202218175#Permanent Repair Root Blower | RU6-POC | 38-K-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365532 | 8202239856 |  | 8202218172#24_penggantian power supply p | RU4-RFCUTL | 157TT-U157/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 10000000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365303 | 8202239855 |  | 8202218169#24_84TE551A Rusak | RU4-KPC | 85PDE284/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365302 | 8202239854 |  | 8202218168#24_84TE551B Rusak | RU4-KPC | 84PDAH506/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363636 | 8202232202 |  | 8202218167#Pengadaan material gate valve | RU2-ITP | P-208A-DMI/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365484 | 8202239853 |  | 8202218166#24_Perbaikan PT pompa 38P-111 | RU4-TRML | 30P104BM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-4-C2H | 0 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102359036 | 8202235569 |  | 8202218161#Perb Hose reel & gate Valve H | RU5-E15500 | FAS-PEMADAM-JB/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 3804977 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102359037 | 8202235572 |  | 8202218160#Perb air line Deluge seri C & | RU5-E15500 | B-8-205/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1053039 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102358989 | 8202235566 |  | 8202218159#Perb. Handwheel,flange 6",lin | RU5-E15500 | B-8-205/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 13493637 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2027-01-20 | 2102359035 | 8202235550 |  | 8202218158#Perbaikan Valve No 88, 12" 15 | RU5-E15500 | FAS-PEMADAM-JB/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/NR-C2H | 55426568 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-30 | 2102359031 | 8202235584 |  | 8202218157#Ganti valve No 86,86A,87 12" | RU5-E15500 | B-8-205/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 164242645 | 0 | MA1-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-06 | 2026-01-07 | 2102359034 | 8202235553 |  | 8202218154#Perbaikan Line pipa 16" Jln 1 | RU5-E15500 | B-8-205/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 109206467 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-06 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-13 | 2102359032 | 8202235559 |  | 8202218153#Perbaikan line pendingin 3" T | RU5-E15500 | B-8-205/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-K3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102358987 | 8202235580 |  | 8202218152#Penggantian Line Chamber 2" k | RU5-E15500 | B-8-205/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-K3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 | 2102359030 | 8202235575 |  | 8202218151#Penggantian valve dan line ta | RU5-E15500 | B-8-205/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 45421065 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2025-12-29 | 2025-12-29 | 2102360374 | 8202235582 |  | 8202218150#Part Untuk Refurbish Rotor K- | RU5-E15111 | K-5-01/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-07 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102359038 | 8202235585 |  | 8202218149#Ganti Valve 16 (no 76B) area | RU5-E15500 | B-8-205/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-K3NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-13 | 2102358988 | 8202235555 |  | 8202218148#Perbaikan Line Pipa 16" Jl. 1 | RU5-E15500 | FAS-PEMADAM-JB/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-K3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-15 | 2025-12-30 | 2102359922 | 8202235561 |  | 8202218143#Perb. Saluran Outlet vessel 1 | RU5-E15112 | C-32-04B/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-32NH | 128 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2025-12-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361154 | 8202237079 |  | 8202218130#D_24 Penggantian Catridge Fil | RU4-GTO | 106S501/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361153 | 8202237078 |  | 8202218129#D_24 Penggantian Catridge Fil | RU4-GTO | 106S503/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363588 | 8202232251 |  | 8202218128#Baut manifold 211 P-6AR patah | RU2-HCC | 211-P-6AR/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-04-12 |  | 8202233300 |  | 8202218127#Perbaikan 23-LV-011 | RU6-HSC | 23-LV-011/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-17 | 2102358896 | 8202235551 |  | 8202218124#Perbaikan Motor Ea-202-06A | RU5-D&W | EAM-202-06A/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 513764 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-09 | 2026-02-02 | 2026-02-02 | 2102363644 | 8202232368 |  | 8202218117#pompa jammed | RU2-HCC | 212-P-11A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 925738575 | 0 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-09 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-02-02 | 2026-12-01 |  | 8202232765 |  | 8202218110#PM/Pdm Listrik & Instrument M | RU6-RCC | 15-R-REGEN/00 | 50 | CLSD CSER NCMP NMAT PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-26 |  | 8202233416 |  | 8202218107#Perbaikan 11-PTR2-01A | RU6-HSC | 11-PTR2-01A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 7121000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363667 | 8202232414 |  | 8202218088#HIGH VIBRATION 110 PM-3A | RU2-HOC | 110-PM-3A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 5756813 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363658 | 8202232394 |  | 8202218080#Pengadaan Bejana Ukur Tera Ul | RU2-ITP | METER-SKID031/00 | 50 | REL GMPS MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 0 | 264500000 | MA4-INT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233752 |  | 8202218079#Pengadaan solenoid valve | RU6-RCC | 16-V-107/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-22 | 2025-12-30 | 2102359067 | 8202235525 |  | 8202218075#perbaikan motor Gm-17-01A vib | RU5-E15112 | GM-17-01A/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 534409 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365550 | 8202239852 |  | 8202218074#24_Perbaikan Positioner 052FV | RU4-UTL | 052FV406/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 18000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365601 | 8202239851 |  | 8202218072#24_Perbaikan Modul Vibrasi 51 | RU4-UTL | 51G201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365277 | 8202239850 |  | 8202218065#25_Ganti Analyzer&sensor cond | RU4-RFCUTL | 154A503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 4 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365329 | 8202239849 |  | 8202218058#24_[CR] Perbaikan 11K401B Noi | RU4-FOC1 | 11K401B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-1-C2H | 229457741 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-10 | 2102359061 | 8202235545 |  | 8202218049#Perbaikan motor degaser venti |  |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 283297 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102366110 | 8202239848 |  | 8202218045#24_[PdM] Pompa 260P104B Vibra | RU4-LOC3 | 260P104B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-9-C2H | 86162640 | 43081320 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365739 | 8202239847 |  | 8202218037#24_[CR] Perbaikan 23E8K-A | RU4-LOC1 | 23E8K-A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 10798760 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365619 | 8202239846 |  | 8202218036#24_[CR] Perbaikan 23E4K-B | RU4-LOC1 | 23E4K-B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 10798760 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366077 | 8202239845 |  | 8202218034#24_[CR] Perbaikan Mechseal OB | RU4-LOC1 | 24P7A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 55871450 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363760 | 8202232595 |  | 8202218031#Perbaikan Rubber Hose Jetty | RU2-ITP | DPN-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352300 | 8202234134 |  | 8202218023#Kerangan water sprayer TK-18 | RU2S-LKKK | 946-F-132-D/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-D1H | 0 | 0 | MAS-ME2 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-06 | 2026-02-06 | 2102352296 | 8202234133 |  | 8202218022#900-03-PM-4B | RU2S-KIL | 900-03P-4B/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-06 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-25 | 2026-02-02 | 2026-02-02 | 2102352274 | 8202234132 |  | 8202218012#Selenoid Auto Drain - WTP | RU2S-KIL | 900-02AC-1B/00 | 60 | REL CSER MACM PRC SETC | 2ES | D12/26/B6/RTZ-D4H | 0 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-02-15 |  | 8202233372 |  | 8202218010#Perbaikan 13-LT-212 | RU6-DHC | 13-LT-212/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363702 | 8202232465 |  | 8202217996#Perbaikan 310-C-2 | RU2-HSC | 310-C-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 56874000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-06-23 | 2026-07-13 | 2102359124 | 8202235523 |  | 8202217990#Ganti Mech seal sisi NDE BFW | RU5-UTL | P-0101A/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-06-23 | PM |  | 003
| K701 | 2026-02-03 | 2026-03-10 | 2026-02-03 | 2026-02-03 | 2102358703 | 8202237957 |  | 8202217988#Sewa Genset 2MW Selama 1 Tahu |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D1H | 1 | 0 | MA-LINT |  | RYANMANGGASA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363818 | 8202238161 |  | 8202217987#Perbaikan Motor 140-PM-17B | RU2-HOC | 140-PM-17B/00 | 50 | CRTD NMAT PRC RELR SETC | 2ER | D12/24/B6/RT-D2H | 500000000 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234018 |  | 8202217984#Indikasi bocoran line LC deka | RU6-UTL | 61-V-303/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 1475500 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-13 |  | 8202233699 |  | 8202217983#Penggantian bearing motor 11- | RU6-HSC | 11-E-112B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 73943 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 | 2102359616 | 8202235516 |  | 8202217982#MAT.PERB.LINE SLOP 3"DI KEPAL | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 16795783 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-10-08 | 2026-11-06 | 2102359574 | 8202235521 |  | 8202217978#Ganti Material Valve MCW no.3 | RU5-UTL | 3VC-00-D001/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 16021201 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-02-03 | 2026-05-08 | 2102359066 | 8202235519 |  | 8202217976#Ganti Mechanical Seal G-3-34C | HCC-RU5 | G-3-34C/01 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 45868970 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-02 | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-27 |  | 8202233705 |  | 8202217973#Penggantian bearing 15-E-110H | RU6-RCC | 15-E-110H-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-23 |  | 8202234044 |  | 8202217972#Abnormail noise motor 15-E-11 | RU6-RCC | 15-E-110D-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-06-09 | 2026-02-02 | 2026-02-02 | 2102352298 | 8202234131 |  | 8202217965#Perbaikan Ganti Bearing 900-0 | RU2S-KIL | 900-03P-6D/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/NRZ-C2H | 3020519 | 3020519 | MAS-ME1 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-27 | 2026-10-27 | 2102359246 | 8202235511 |  | 8202217959#Perbaikan Pompa Pengendali Ba |  |  | 60 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 29888300 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-27 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365558 | 8202239844 |  | 8202217957#24_24FT023 Transmiter Rusak | RU4-LOC1 | 24FT023/00 | 60 | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 18500000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365981 | 8202239843 |  | 8202217956#24_Kerusakan Control Valve 14 | RU4-GTO | 140KV028B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-22 | 2102359127 | 8202235461 |  | 8202217947#Perbaikan QCV Jetty 5ABC | RU5-TBL | 22-QCV-519A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 55047547 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-06-17 |  | 8202238160 |  | 8202217942#Jasa Perbaikan & Fabrikasi 38 | RU6-POC | 38-K-101B/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358704 | 8202234230 |  | 8202217933#Pengadaan Spare part Oxygen A |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-24 | 2025-12-30 | 2102359295 | 8202235515 |  | 8202217932#perbaikan EM-32-01R | RU5-E15112 | EM-32-01R/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 5895424 | 0 | MA3-LIS |  | MKASPUDDIN | 2025-12-24 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-02-03 | 2026-05-08 | 2102359181 | 8202235514 |  | 8202217928#perbaikan Gm-17-02B | RU5-E15112 | G-17-02B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 203000000 | 0 | MA3-ROT |  | SAPBATCH | 2026-06-02 | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K201 | 2026-02-04 |  | 2026-02-05 | 2026-02-05 | 2102363970 | 8202238509 |  | 8202217926#Penyelesaian Pemasangan MOV T | RU2-ITP | 610-BV-107A/00 | 50 | CRTD NMAT PRC | 2MR | D12/22/B6/RT-D2H | 13000000 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-03-09 | 2026-01-02 | 2026-11-30 | 2102352272 | 8202234127 |  | 8202217921#Penggantian blind flange area | RU2S-KIL | 101-D-1/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/25/B6/RTZ-D1H | 17506906 | 15952324 | MAS-ME1 |  | JUNIANTO |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-16 | 2026-03-16 | 2026-03-30 | 2102359129 | 8202235453 |  | 8202217920#Perbaikan Motor Eam-202-05A | RU5-D&W | EAM-202-05A/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 6900000 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-16 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-03-17 | 2102359125 | 8202235452 |  | 8202217917#Perbaikan Transmitter Meterin | RU5-TBL | METER-4511/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 539725979 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-25 | 2026-03-25 | 2026-04-01 | 2102359126 | 8202235455 |  | 8202217916#Perb. motor sootblower Boiler | RU5-UTL | 1NV00D001-S2/00 | 60 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 48626 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-03-29 |  | 8202233348 |  | 8202217904#Perbaikan 15-LT-507 indikasi | RU6-RCC | 15-E-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102360586 | 8202235459 |  | 8202217900#G-34-54 | RU5-D&W | G-34-54/00 | 50 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-05-26 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102360583 | 8202235457 |  | 8202217898#Penggantian Unit Pompa G-34-5 | RU5-D&W | G-34-58B/00 | 50 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-05-26 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-05 |  | 8202233842 |  | 8202217886#Penambahan TI & PI Prover | RU6-ITP | 42-A-314/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 2765 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365498 | 8202239842 |  | 8202217881#24_[PV] Penggantian filter se | RU4-RFCC | 101F503A3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-01-02 | 2026-01-02 | 2102366103 | 8202239841 |  | 8202217875#24_[CR] Penggantian Governor | RU4-UTL | 053P201C-T/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | YMOHAMMAD | 2026-06-11 | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363655 | 8202232387 |  | 8202217869#Perbaikan bearing motor 925-P | RU2-UTL | 925-P-6B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/25/B6/RT-D2H | 73650750 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-04-21 | 2026-04-17 | 2026-12-31 | 2102363969 | 8202238508 |  | 8202217865#Switchgear & MCC Substation E | RU2-UTL | 905-SWG-52D11/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 300000000 | 0 | MA3-LIS |  | ADEMULYADI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365874 | 8202239840 |  | 8202217864#24_156XS626 Solenoid drain Va | RU4-RFCUTL | 156K501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 699462 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361102 | 8202236499 |  | 8202217860#D24_Material temporary untuk | RU4-FOC2 | 012K101A/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 |  | 8202233816 |  | 8202217841#Pengadaan filter Oil Purifier | RU6-UTL | 51-G-101E-S1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365980 | 8202239839 |  | 8202217830#24_Bearing Motor 100P611AM Ov | RU4-GTO | 100P611AM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-14-C2H | 3417800 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363650 | 8202232380 |  | 8202217818#Perbaikan Bowl 925-P-6A | RU2-UTL | 925-P-6A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233568 |  | 8202217809#Penggantian Part Alarm Setter | RU6-UTL | 52-B-101A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 26483 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102352922 | 8202238101 |  | 8202217800#Tag Pek Perawatan dan Pembers | RU3-CDGP |  | 50 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363643 | 8202232362 |  | 8202217796#Perbaikan Dischage Valve 945 | RU2-ITP | 945-P-1A/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365345 | 8202239838 |  | 8202217795#24_Flow Transmitter Rusak | RU4-KPC | 84FT204/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 19250000 | 19000000 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-04 |  | 8202238100 | 8202238701 | 8202217784#LTSA PERIODIC MAINTENANCE TRA | RU2-HOC | 140-PIPING/00 | 60 | REL NMAT PRC SETC | 2MR | D12/24/B6/RT-D2H | 200000000 | 0 | MA1-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232808 |  | 8202217783#Permanent Repair 38-K-101B | RU6-POC | 38-K-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365576 | 8202239837 |  | 8202217749#24_[COR] Penggantian Membran | RU4-UTL | 54WS2P3/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-5-C2H | 33875000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102360665 | 8202235449 |  | 8202217745#MAT.PERB.LINE 3/4IN TSV 496 D | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/25/B6/RT-C2H | 5674970 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-07 | 2026-02-04 | 2026-02-04 | 2102363800 | 8202238086 |  | 8202217742#Isolir perbaikan bocoran pipa | RU2-HSC | 100-E-14E/00 | 50 | REL NMAT PRC SETC | 2MR | D12/24/B6/RT-D2H | 6000000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365519 | 8202239836 |  | 8202217717#24_[PV] Penggantian filter au | RU4-RFCUTL | 154P505A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-13-C2H | 9962000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363805 | 8202238099 |  | 8202217712#LTSA PREVENTIVE MAINTENANCE M | RU2-HOC | 110-CM-1A/00 | 50 | REL NMAT PRC SETC | 2ER | D12/24/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102363770 | 8202232633 |  | 8202217711#Pengambilan material isolasi | RU2-ITP | 6-FW-97010-MS1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/XX/B6/RT-D2NH | 0 | 0 | MA4-STA |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-12 | 2102359406 | 8202235447 |  | 8202217710#Penggantian Hydraulic Seal LA | RU5-TBL | L-ARM-2-JT-4/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 1957489 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-05 | 2102359290 | 8202235444 |  | 8202217703#perbaikan cover fan motor P05 |  |  | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 5675809 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2025-12-31 | 2025-12-31 | 2102358351 | 8202234224 |  | 8202217701#Perbaikan/Penggantian Kabel P |  |  | 50 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-4-D1H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365523 | 8202239835 |  | 8202217695#24_47LI415B, Penggantiam tran | LOC1-UP4 | 47S507B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-7-C2H | 3 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-06-22 | 2026-02-02 | 2026-03-27 |  | 8202233355 |  | 8202217690#Perbaikan 15-E-109E | RU6-RCC | 15-E-109E-K/00 | 60 | CLSD CNF CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH | 2026-04-23 | 2026-02-07 | PT02 |  | 3 | 2026-04-23 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-12-08 | 2027-03-18 | 2102364049 | 8202233774 |  | 8202217682#Pengadaan Motor 32-A-101-K1M | RU6-HSC | 32-A-101-K1/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/NR-C2H | 1456003840 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-12 | 2025-12-22 | 2102359576 | 8202235426 |  | 8202217681#Kabel power ke deep well 9A r |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 370704090 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-12 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361097 | 8202236492 |  | 8202217679#D24_Perbaikan 018PCV145 | RU4-FOC2 | 018PCV145/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361096 | 8202236490 |  | 8202217678#D24_Perbaikan 018PCV145 | RU4-FOC2 | 018PCV145/00 | 50 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361112 | 8202236514 |  | 8202217677#D24_011PT-024 & 026 (FG Cell | RU4-FOC2 | 011F101A/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202233098 |  | 8202217676#Perbaikan Mech Seal 42-P-304B | RU6-ITP | 42-P-304B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-27 |  | 8202233099 |  | 8202217675#Perbaikan Mech Seal 42-P-304A | RU6-ITP | 42-P-304A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366085 | 8202239834 |  | 8202217673#24_88P206A Mechseal IB Bocor | RU4-KPC | 88P206A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 58779300 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366086 | 8202239833 |  | 8202217672#24_Perbaikan TBP Potstill AST | RU4-FOC2 | 010AOC1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 665370000 | 665370000 | WS-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 |  | 8202233149 |  | 8202217670#Perbaikan Jangka Pendek 11-E- | RU6-HSC | 11-E-117A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C3H | 2304 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233116 |  | 8202217662#perbaikan line 38-RG-8020 | RU6-POC | 37-R-101A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 12353800 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-05 | 2025-12-19 | 2025-12-29 | 2102359294 | 8202235384 |  | 8202217653#Perbaikan EM-2-12E | RU5-E15112 | EM-2-12E/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1517066 | 0 | MA3-LIS |  | SAPBATCH | 2025-12-20 | 2026-02-11 | PT02 |  | 3 | 2025-12-20 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-05-13 |  | 8202233232 |  | 8202217651#Perbaikan bearing motor 19-P- | RU6-RCC | 19-P-112A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-03 | 2102359739 | 8202235383 |  | 8202217649#MAT.PERB.LINE SUCTION GM-32-0 | RU5-UTL | G-32-03A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 98808355 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-27 | 2025-12-29 | 2102360166 | 8202235381 |  | 8202217640#Material Kabel NGR Transforme |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 370836269 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-27 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202234668 |  | 8202217631#Perbaikan Bocoran Online leak | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359925 | 8202235360 |  | 8202217628#Perbaikan elektrikal sootblow | RU5-UTL | 3NV00S100/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 463808102 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-30 | 2102359298 | 8202235358 |  | 8202217627#Perbaikan Sootblower HHP 4,5, |  |  | 50 | REL CSER MACM PRC SETC | 5ER | D15/24/B6/RT-C2H | 1216116834 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-26 |  | 8202234041 |  | 8202217625#Blower inlet MAB 15K101K1A tr | RU6-RCC | 15-K-101-K1A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 147887 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-09-11 |  | 8202238098 |  | 8202217618#kalibrasi CGA/RCA untuk CEMS | RU6-RCC | 15-B-101/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-03-15 |  | 8202234092 |  | 8202217617#15-SLV-104 Servo | RU6-RCC | 15-SLV-104/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365518 | 8202239832 |  | 8202217615#24_[PV] Penggantian filter lu | RU4-RFCUTL | 154P503A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-13-C2H | 4981000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233619 |  | 8202217613#Penggantian kabel motor 56-K- | RU6-UTL | 56-K-101F-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/24/B6/RT-C2H | 66 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102360957 | 8202237034 |  | 8202217612#D_24 Perbaikan Tube 105E507 | RU4-RFCGTO | 105E507A1/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-01-29 |  | 8202232776 |  | 8202217610#PM instrument dan Electrical | RU6-ITP | 42-T-102A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1700146 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363762 | 8202232602 |  | 8202217598#Penggantian 1 unit mixer | RU2-HCC | 211-ME-3/00 | 50 | REL NMAT PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363767 | 8202232622 |  | 8202217597#Perbaikan pompa 140 P-12AB | RU2-HOC | 140-P-12A/00 | 50 | REL GMPS MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 499800000 | MA1-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-02 | 2026-12-14 | 2102359299 | 8202235333 |  | 8202217586#Perbaikan Blok Valve Conv 60/ | RU5-UTL | 0RF03P001/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 360166922 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361164 | 8202237100 |  | 8202217569#D_24 018K101 A amper meter lo | RU4-FOC2 | 018K101AM/00 | 60 | REL CSER NMAT PRC SETC | 4ER | D14/24/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 | 2102364221 | 8202233490 |  | 8202217566#Penggantian spring 51-PSV-637 | RU6-UTL | 51-P-101D-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365573 | 8202239831 |  | 8202217562#24_ABO 2024 EIIE Tools Flowme | RU4-RFCUTL | 154FT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 |  | 8202233756 |  | 8202217561#Pengadaan Pulley Driver 33-E- | RU6-HSC | 33-E-118I2/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C3H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-02-04 | 2102363803 | 8202238095 |  | 8202217555#PSA UPS dan DC Charger Brand | RU2-UTL | 560-DC-SS2/00 | 50 | REL NMAT PRC SETC | 2ER | D12/24/B6/RT-D2H | 2000000 | 0 | MA3-LIS |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365330 | 8202239830 |  | 8202217553#24_Perbaikan 154TT604 SWD B | RU4-RFCUTL | 154TT-U154/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366082 | 8202239829 |  | 8202217550#24_011P103A MS rembes OB | RU4-FOC2 | 011P103A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 119111613 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233660 |  | 8202217549#Penggantian FFC 18-A-201 & 18 | RU6-RCC | 18-A-201/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361111 | 8202236513 |  | 8202217542#D24_012LV-010 GP bocor | RU4-FOC2 | 012LV010/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365485 | 8202239828 |  | 8202217541#24_Perbaikan Flow Strainer 54 | RU4-UTL | 54DA201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233449 |  | 8202217534#Penggantian valve 2" 34-A-10 | RU6-POC | 34-A-102-V-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C1H | 1420494 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233450 |  | 8202217533#Penggantian valve 1" 34-A-103 | RU6-POC | 34-A-103-S-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 264862 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-06-11 | 2102359405 | 8202235327 |  | 8202217528#perbaikan vibrasi GT-8-05B | RU5-E15112 | GT-8-05B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 167366469 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102366040 | 8202239827 |  | 8202217525#24_[CR] 019K102C Coupling def | RU4-FOC2 | 019K102C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-2-C2H | 31750000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-16 | 2025-12-22 | 2102360164 | 8202235328 |  | 8202217519#Perb. Motor GM20-28 lube oil | RU5-TBL | PLANT-21-LIS/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 116787 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-04-10 | 2102359879 | 8202235329 |  | 8202217518#motor condensate no.1 STG 2.4 | RU5-UTL | 4RM-01-D001/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 550100 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363602 | 8202232287 |  | 8202217515#Kebutuhan Kaca Level Glass 11 | RU2-HOC | 110-V-10/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102366071 | 8202239825 |  | 8202217514#24_[CR] Perbaikan Pompa 63-A- | RU4-RFCUTL | 63A502P1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-07 | 2026-02-04 | 2026-02-04 | 2102363804 | 8202238097 |  | 8202217509# Switchgear & MCC Substation | RU2-UTL | 905-SWG-52D11/00 | 50 | REL NMAT PRC SETC | 2ER | D12/24/B6/RT-D2H | 300000000 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365744 | 8202239824 |  | 8202217490#24_Perbaikan Coupling 21P3A | RU4-LOC1 | 21P3A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 13800000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102352279 | 8202234126 |  | 8202217485#Rubber Fender Jetty-2 MD-3 ou | RU2S-KIL |  | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-D3H | 235000000 | 235000000 | MAS-ME2 |  | JUNAIDIT |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-15 | 2025-12-15 | 2102359407 | 8202235326 |  | 8202217478#G-3-29 mech seal bocor | RU5-E15112 | G-3-29/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 40588129 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-22 |  | 8202233637 |  | 8202217476#Penggantian Fuse control & po | RU6-UTL | 56-P-101C-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1734 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233775 |  | 8202217472#Pengadaan Modul Tyristor 059- | RU6-UTL | 059-A-101A-D1/00 | 60 | REL MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1408472 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-06-19 |  | 8202233509 |  | 8202217471#Penggantian Selector & push b | RU6-UTL | 052-P-103A-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 1619 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 |  | 8202238505 |  | 8202217460#NRKA24_Perbaikan Jalan New Pl | RU4-TRML | 72FP201M/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 90000000 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-02 |  | 8202235325 |  | 8202217453#Battery ACCU Genset RPPK drop | RU5-E15112 | 41-R-RPPK-LIS/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 12437143 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365491 | 8202239823 |  | 8202217449#24_[PV] Perbaikan Tandem Seal | RU4-RFCC | 101P523C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365639 | 8202239822 |  | 8202217446#24_Penggantian Pressure Gauge | RU4-RFCUTL | 156PG-U156/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 9327766 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365616 | 8202239821 |  | 8202217445#24_Penggantian Pressure Gauge | RU4-RFCUTL | 154PG-U154/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 5047868 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366067 | 8202239820 |  | 8202217444#24_Penggantian sensor conduct | RU4-RFCUTL | 154A501B-S3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 88350000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-05 | 2102365730 | 8202239819 |  | 8202217441#24_013E111K03 Blade nyenggol | RU4-FOC2 | 013E111K03/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 13786500 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-04-30 | 2026-07-09 | 2102359489 | 8202235323 |  | 8202217440#Penggantian Vessel C-34-01AB |  |  | 50 | REL CSER MACM PRC SETC | 5MR | D15/24/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-04-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365737 | 8202239818 |  | 8202217439#24_Penggantian Flow Transmitt | RU4-RFCC | 102FT041/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 21060000 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-05 | 2026-07-13 | 2102359572 | 8202235324 |  | 8202217434#Ganti Unit Bejana D-34-15 A E | RU5-D&W | D-34-15A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K401 | 2026-02-03 | 2026-05-07 | 2025-12-08 | 2026-12-29 | 2102360942 | 8202237490 |  | 8202217417#Penggantian UPS 30EE42 Substa | RU4-TRML | 30EE1202/00 | 60 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-LIS |  | WAHYUCATUR |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365362 | 8202239817 |  | 8202217415#24_[CR] Perbaikan pompa 47P10 | RU4-TRML | 47P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102352884 | 8202238096 |  | 8202217413#Pemasangan Swivel Joint L.Arm |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/NR-4-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-15 | 2026-11-26 | 2102359483 | 8202235290 |  | 8202217410#Condensate pump A STG 1.6 | UTL-RU5 | P-31-02A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 315233 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-05 | 2025-12-03 | 2102359482 | 8202235286 |  | 8202217401#Ganti Check Valve& Disch Valv | RU5-D&W | G-34-109A/00 | 60 | REL MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 243737099 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 |  | 8202233952 |  | 8202217397#Mat Prbaikan Jngka Panjang 53 | RU6-UTL | 53-K-301B-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 401001 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-10 | 2026-02-02 | 2027-01-27 |  | 8202233954 |  | 8202217395#Mat Perba Jngka Panjang 53-K- | RU6-UTL | 53-K-301A/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 69359241 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-10 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 |  | 8202233649 |  | 8202217385#Penggantian Filter Control Oi | RU6-RCC | 15-K-101-S1A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102366073 | 8202239816 |  | 8202217383#24_[CR] 019K102A Coupling def | RU4-FOC2 | 019K102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202233276 |  | 8202217382#Perbaikan 36-E-101 F2 | RU6-POC | 36-E-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202232881 |  | 8202217379#Perbaikan Solenoid 22-KV-578 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202232880 |  | 8202217378#Perbaikan Solenoid 22-KV-579 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202232882 |  | 8202217377#Perbaikan Solenoid 22-KV-574 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202232883 |  | 8202217375#Perbaikan Solenoid 22-KV-568 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202233397 |  | 8202217374#Perbaikan 12-LT-801 | RU6-DHC | 12-LT-801/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363695 | 8202232446 |  | 8202217370#Gasket Cleaning Transfer Line | RU2-HOC | 140-H-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202233483 |  | 8202217368#Penggantian Temp.Gauge STG 51 | RU6-UTL | 52-B-101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1202 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202233732 |  | 8202217367#Penggantian 052-LT-541 (KO Dr | RU6-UTL | 052-LT-541/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1202 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-05 | 2026-03-05 | 2026-05-11 | 2102359481 | 8202235280 |  | 8202217366#Mat.Retubing final condensor |  | FA-201/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 2608480000 | 0 | MA1-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2025-12-30 |  | 8202232828 |  | 8202217365#Perbaikan valve 22-XV-6475 | RU6-DHC | 22-XV-6475/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 320 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202233587 |  | 8202217363#Penggantian local RPM 056-P-1 | RU6-UTL | 056-P-101B-T/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1202 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363772 | 8202232643 |  | 8202217357#Pengadaan Wire Rope Air Wing | RU2-HOC | 140-V-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-30 | 2026-03-30 | 2026-06-29 | 2102359924 | 8202235276 |  | 8202217352#MAT.GANTI VALVE INLET TANK D2 | RU5-TBL | 21-MOV-112/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 96606076 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-03-30 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102352278 | 8202234123 |  | 8202217351#Pompa c/w 900-07-P-1A & C | RU2S-KIL | 900-07P1C-MCC-E/00 | 60 | REL MACM PRC SETC | 2RS | D12/25/B6/NRZ-D2H | 0 | 0 | MAS-ME1 |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365483 | 8202239815 |  | 8202217346#24 pengadaan Grease motor utk | RU4-FOC2 | 012P101AM/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/24/B6/RT-2-C2H | 0 | 24940400 | MA2-LIS |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363665 | 8202232411 |  | 8202217339#Conmon High Delta Press Filte | RU2-UTL | 910-C-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 40716551 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363613 | 8202232338 |  | 8202217338#Conmon Speed Hunting 940-PT-3 | RU2-UTL | 940-PT-3B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 | 2102360230 | 8202235273 |  | 8202217335#G-3-07A Putaran Berat | RU5-E15112 | G-3-07A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 127612243 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-23 | 2026-02-04 | 2026-02-04 | 2102363802 | 8202238093 |  | 8202217329#Perbaikan Pondasi Pompa Area | RU2-HCC | 212-P-25B/00 | 50 | CRTD NMAT PRC SETC | 2RR | D12/24/B6/NR-D2H | 290000000 | 0 | MA2-ROT |  | AHILMANSYAH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-15 | 2025-12-15 | 2102359618 | 8202235270 |  | 8202217328#G-3-37C Low Performance | RU5-E15112 | G-3-37C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 253695181 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202232799 |  | 8202217320#Permintaan Press Gauge 0 - 60 | RU6-HSC | 32-A-101-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202233204 |  | 8202217318#Perbaikan Coalescer Assembly | RU6-HSC | 32-K-101/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 |  | 8202233755 |  | 8202217308#Pengadaan Relay Proteksi 56-P | RU6-UTL | 56-P-101C-M/00 | 60 | REL NMAT PRC SETC | 6ER | D16/24/B6/RT-C2H | 11946 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-11 |  | 8202233923 |  | 8202217307#Material radiness lebaran 202 | RU6-HSC | 16-PBC3-01C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 969763 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-11 |  | 8202233783 |  | 8202217306#Pengadaan material relay 400V | RU6-UTL | SS-01/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 16104 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102359610 | 8202235267 |  | 8202217298#Perbaikan Speed RPM no.2 STG | RU5-UTL | TG-2-PP2-INST/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102360279 | 8202235261 |  | 8202217288#Perbaikkan I/P FCV 102 HHP Bo | RU5-UTL | HHP-2-INST/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 78721138 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-04-10 | 2026-02-02 | 2026-02-02 | 2102363585 | 8202232237 |  | 8202217279#Blade rusak | RU2-HCC | 211-EF-5G/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-04-10 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-07-09 | 2102359988 | 8202235265 |  | 8202217252#Mat'l Perb. Line Drain Evap. | RU5-UTL | G-37-04/00 | 01 | CRTD CSER MACM PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360238 | 8202235266 |  | 8202217251#Ganti Valve Regen HCL Cation | RU5-UTL | 0UA-41-D002/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365680 | 8202239814 |  | 8202217250#24_Transmitter 21FV-039 Rusak | RU4-LOC1 | 21FV039/00 | 60 | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 18500000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365743 | 8202239813 |  | 8202217249#24_Transmitter 21FV-037 Rusak | RU4-LOC1 | 21FV037/00 | 60 | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 18500000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365610 | 8202239812 |  | 8202217248#24_Positioner 21FV037 Rusak | RU4-LOC1 | 21FV037/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/24/B6/RT-7-C2H | 20000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365742 | 8202239811 |  | 8202217244#24_Transmitter 21FV-035 Rusak | RU4-LOC1 | 21FV035/00 | 60 | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 18500000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365579 | 8202239810 |  | 8202217243#24_Positioner 21FV035 Rusak | RU4-LOC1 | 21FV035/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/24/B6/RT-7-C2H | 20000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365578 | 8202239809 |  | 8202217242#24_Positioner 21FV033 Rusak | RU4-LOC1 | 21FV033/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/24/B6/RT-7-C2H | 20000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365741 | 8202239808 |  | 8202217241#24_Transmitter 21FV033 Rusak | RU4-LOC1 | 21FV033/00 | 60 | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-7-C2H | 18500000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102360161 | 8202235264 |  | 8202217232#Penggantian Limit Switch 202- | RU5-D&W | 202-XCV-007/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102360589 | 8202235260 |  | 8202217225#MAT.PERB.LINE 21-P22-4" POD J | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 69138100 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102358181 | 8202237956 |  | 8202217223#LTSA Fire Truck |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/25/B6/RT-1-D2H | 1 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2026-10-05 | 2026-11-02 | 2102359920 | 8202235259 |  | 8202217220#Perbaikan pompa G-201-06A | RU5-D&W | G-201-06A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 214330000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-05 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363627 | 8202232285 |  | 8202217217#905-PT-58 High Vibrasi | RU2-UTL | 905-PT-58/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202232924 |  | 8202217211#Perbaikan power supply ESD | RU6-DHC | OS-11/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102359926 | 8202235252 |  | 8202217209#MAT.PERB.DRAIN HEADER LOADING | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 2053781 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-15 | 2025-12-15 | 2102360322 | 8202235258 |  | 8202217206#G-31-39B Perbaikan | RU5-E15112 | G-31-39B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 163227688 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363640 | 8202232295 |  | 8202217196#520-CL-02 Perbaikan gearbox | RU2-UTL | 520-AG-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363707 | 8202232477 |  | 8202217191#Perbaikan 212-E-26 | RU2-HCC | 212-E-26/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-10-14 | 2026-11-12 | 2102360063 | 8202235256 |  | 8202217190#Ganti Valve Raw water Demin | RU5-UTL | 1UA04F001/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 61477024 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-14 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363606 | 8202232313 |  | 8202217188#Pengadaan Gasket Antifoam | RU2-HOC | 140-V-1A/00 | 60 | REL CSER MACM PRC SETC | 2MR | D12/25/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-12 | 2025-11-12 | 2102361167 | 8202237120 |  | 8202217181#D_24 014FSL384 tidak berfungs | RU4-FOC2 | 014R104/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-12-30 | 2025-12-30 | 2102360959 | 8202237038 |  | 8202217180#D_24 Perbaikan HMI PSA N2 Pla | RU4-KPC | 81A201K1A/00 | 50 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-12-30 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202232802 |  | 8202217167#Permanent Repair Pompa HBW 52 | RU6-UTL | 52-P-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 31284 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365746 | 8202239807 |  | 8202217165#24_Peremajaan pulley fin fan | RU4-LOC3 | 240E112AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-9-C2H | 223299113 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-08-14 |  | 8202232750 |  | 8202217158#Regulator 58-K-101C antisipas | RU6-UTL | 58-FT-003A/00 | 50 WAMA | CRTD CSER MACM PRC | 6IR | D16/24/B6/RT-C2H | 16500 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365735 | 8202239806 |  | 8202217155#24_[CR] Perbaikan 67FP2 Utili | RU4-TRML | 67FQI6761/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | GEN-MEK |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-03-17 | 2026-02-02 | 2026-02-02 |  | 8202233947 |  | 8202217151#Material Antisipasi Lebaran M | RU6-HSC | 32-A-101-S1/00 | 60 | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 654845896 | 64552490 | MA3-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365562 | 8202239805 |  | 8202217147#24_[CR] Penggantian Shearpin | RU4-LOC2 | 024E102C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 106090 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365861 | 8202239804 |  | 8202217141#24_ Transmitter 84FT363 Rusa | RU4-KPC | 84FT363/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365570 | 8202239803 |  | 8202217140#24_Perbaikan 152-PI-801 | RU4-RFCUTL | 152G501C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-04-20 |  | 8202233731 |  | 8202217139#Penggantian 052-PSH-963A/B/C | RU6-UTL | 052-B-101A-K-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365517 | 8202239802 |  | 8202217138#24_perbaikan press indikator | RU4-RFCUTL | 152G501B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365533 | 8202239801 |  | 8202217137#24_Pompa Injeksi 140P602B Low | RU4-GTO | 140P602B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 200000000 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365516 | 8202239800 |  | 8202217136#24_perbaikan press indikator | RU4-RFCUTL | 152G501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 2 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365949 | 8202239799 |  | 8202217134#24_Penggantian TG casing pomp | RU4-RFCC | 101P523B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 2387143 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237955 | 8202237868 | 8202217124#Perbaikan Motor Winch dan She |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/NR-1-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-01-05 |  | 8202233234 |  | 8202217115#Perbaikan bearing motor | RU6-ITP | 63-M-302-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 251 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-18 |  | 8202233454 |  | 8202217111#Penggantian Tube Bundle Assy | RU6-HSC | 11-E-128A/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C3H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-03-04 | 2026-02-02 | 2026-11-04 |  | 8202233680 |  | 8202217109#Penggantian check valve 58-D- | RU6-UTL | 58-D-101C/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 96599760 | 24144000 | MA4-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-13 |  | 8202233757 |  | 8202217108#Pengadaan PSV 11-P-117 C&D | RU6-HSC | 11-P-117A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363761 | 8202232597 |  | 8202217104#Perbaikan rembesan lube oil 1 | RU2-HOC | 140-P-17B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 86007000 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2102359927 | 8202235243 |  | 8202217103#Governor STG 1.5A bocor | RU5-UTL | TG-5A-PP1/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K301 | 2026-02-02 | 2026-05-07 | 2025-12-31 | 2025-12-31 | 2102353082 | 8202235669 |  | 8202217098#Anticipate Material Mech. Sea |  |  | 60 | REL CNF PRT NMAT PRC SETC | 3MR | D13/25/B6/NR-2-D2H | 0 | 0 | MA3-ROT |  | HANGGAO | 2026-03-06 | 2026-02-07 | PT02 |  | 3 | 2025-12-31 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365339 | 8202239798 |  | 8202217092#24_93FT-140, penggantian flow | RU4-SRU | 93FT255/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365574 | 8202239797 |  | 8202217091#24_Penggantian transmiter 48F | RU4-GTO | 48FT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365549 | 8202239796 |  | 8202217086#24_Perbaikan control valve 22 | RU4-LOC3 | 220TV130/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202234082 |  | 8202217085#19-AT-001 & 19-AT-002 Spare G | RU6-RCC | 19-AT-001/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363601 | 8202232284 |  | 8202217076#Filter Lube Oil Tank C2 tidak | RU2-HCC | 212-C-2/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363791 | 8202232706 |  | 8202217075#Suara gear pump kasar | RU2-HCC | 212-C-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 1410000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-01-02 | 2026-01-02 | 2102360125 | 8202235241 |  | 8202217055#G-3-37A Low Performance | RU5-E15112 | G-3-37A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 158877 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202232969 |  | 8202217046#Perbaikan Pompa 32-P-108B | RU6-HSC | 32-P-108B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202235239 | 8202238852 | 8202217041#MAT.FABRIKASI LINE JUMPER SF0 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/25/B6/RT-C2H | 249607289 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233206 |  | 8202217013#Perbaikan Check dan gate Valv | RU6-HSC | 31-C-103/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202232728 | 8202233375 | 8202217004#SWO Fabrikasi Inner Parts 12- | RU6-DHC | 13-FV-030/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366059 | 8202239794 |  | 8202216996#24_Perbaikan 240LV058 | RU4-LOC3 | 240LV058/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 83151822 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102352305 | 8202234121 |  | 8202216990#Penggantian Line 8 Inch Resid | RU2S-KIL | 101-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-11-16 | 2102365649 | 8202239793 |  | 8202216989#24_Mtl. Perbaikan Pipa Unit 9 | RU4-SRU | 93A404/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 61805324 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202232789 |  | 8202216988#Permintaan Press Gauge 24-P-1 | RU6-HSC | 24-P-105A-M/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 892810 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-11-16 | 2102365648 | 8202239792 |  | 8202216987#24_Mtl. Perbaikan line disch | RU4-SRU | 93P402B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 37360286 | 0 | MA1-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-18 | 2026-02-02 | 2026-11-04 |  | 8202232783 |  | 8202216986#Permintaan Press Gauge 64-P-1 | RU6-HSC | 64-P-104A-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-18 | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232784 |  | 8202216985#Permintaan Press Gauge 64-P-1 | RU6-HSC | 64-P-103A-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232785 |  | 8202216984#Permintaan Press Gauge 64-P-1 | RU6-HSC | 64-P-102A-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232792 |  | 8202216983#Permintaan Press Gauge 23-P-6 | RU6-HSC | 23-P-601A-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232788 |  | 8202216982#Permintaan Press Gauge 24-P-2 | RU6-HSC | 24-P-204-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232790 |  | 8202216981#Permintaan Press Gauge 24-P-1 | RU6-HSC | 24-P-104-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232786 |  | 8202216979#Permintaan Press Gauge 24-P-3 | RU6-HSC | 24-P-302B-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-16 | 2026-04-23 |  | 8202232791 |  | 8202216978#Permintaan Press Gauge 24-P-1 | RU6-HSC | 24-P-103A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-16 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232787 |  | 8202216977#Permintaan Press Gauge 24-P-3 | RU6-HSC | 24-P-302A-M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-18 | 2026-02-02 | 2026-11-04 |  | 8202232795 |  | 8202216974#Permintaan Press Gauge 11-P-1 | RU6-HSC | 11-P-114B-M/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 1131805 | MA1-INT |  | AHMADAKHYAR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232794 |  | 8202216973#Permintaan Press Gauge 11-P-1 | RU6-HSC | 11-P-123/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 1131805 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202232796 |  | 8202216972#Permintaan Press Gauge 11-P-1 | RU6-HSC | 11-P-114A-M/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202232781 |  | 8202216971#Permintaan Press Guge 11P111A | RU6-HSC | 11-P-111A-E1/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202232782 |  | 8202216970#Permintaan Press Gauge11-P-10 | RU6-HSC | 11-P-103B-E1/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366111 | 8202239791 |  | 8202216968#24_Perbaikan actuator SOV FG | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202232798 |  | 8202216966#Permintaan Press Gauge 11-P-1 | RU6-HSC | 11-P-103A-M/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363674 | 8202232308 |  | 8202216965#control valve passing | RU2-HSC | 310-BV-45/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/24/B6/NR-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-05-26 | 2026-02-02 | 2026-11-04 |  | 8202232793 |  | 8202216964#Permintaan Press Gauge 11P115 | RU6-HSC | 11-P-115B/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 957822 | MA1-INT |  | SAPBATCH | 2026-05-26 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-04 |  | 8202232797 |  | 8202216957#Permintaan Press Gauge 11-P-1 | RU6-HSC | 11-P-117A-M/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-05 | 2026-02-05 |  | 8202238510 |  | 8202216949#RKA23L_Extend MCB RFCC + Aman | RU4-RFCUTL | 150BD1MMP010/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 48750000 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-01-05 |  | 8202233112 |  | 8202216930#Perbaikan marine lantern | RU6-ITP | 41-A-102/00 | 50 WAMA | REL MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 42044856 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366056 | 8202239790 |  | 8202216915#24_[CR] 47P-503C, Penggantian | LOC1-UP4 | 47T501/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 66566107 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365554 | 8202239789 |  | 8202216908#24_[CR] 47P-503A, Penggantian | LOC1-UP4 | 47P503A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 3152479 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363623 | 8202232243 |  | 8202216907#Belting putus | RU2-HCC | 410-E-14/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102360160 | 8202235234 |  | 8202216902#cover bearing & reversing bla | RU5-E15112 | KT-8-02A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 201978 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 | 2102352289 | 8202234120 |  | 8202216899#Pekerjaan Urgent Kilang | RU2S-KIL |  | 50 | REL NMAT PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233319 |  | 8202216896#Perbaikan 18-LSLL-004 | RU6-RCC | 18-V-102/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233387 |  | 8202216895#Perbaikan 12-PT-293 | RU6-DHC | 12-PT-293/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233388 |  | 8202216893#Perbaikan 12-PT-214 | RU6-DHC | 12-PT-214/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-11 |  | 2026-02-11 | 2026-05-05 |  | 8202238852 |  | 8202216871#MODIFIKASI LINE JUMPER SF O5 | RU5-TBL | PIPE-TANK-PUMP/00 | 01 | CRTD NMAT PRC SETC | 5MR | D15/25/B6/RT-C2H | 82000000 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-11 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-18 | 2026-01-02 | 2026-01-02 |  | 8202235151 | 8202235285 | 8202216869#KV Cleaning & Ganti Catalyst | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-01-09 | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366010 | 8202239788 |  | 8202216867#24_Penggantian PT Vacum | RU4-UTL | 054WS103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 15000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238094 | 8202238780 | 8202216865#PEMBAYARAN PEKERJAAN KONTRAK | RU2-ITP |  | 50 | CRTD NMAT PRC SETC | 2IR | D12/24/B6/RT-D2H | 1101600 | 0 | MA4-INT |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K201 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2102366514 | 8202241569 |  | 8202216847#Perbaikan dan Penggantian spr | RU2-ITP | 1-5LS91501MS11/00 | 50 | REL NMAT PRC SETC | 2MR | D12/25/B6/RT-D2H | 260000000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-03-11 | PT02 |  | 3 | 2026-03-11 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-26 |  | 8202233162 |  | 8202216840#Perbaikan Gearbox 14-P-102B | RU6-DHC | 14-P-102A/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2102360127 | 8202235231 |  | 8202216837#Perbaikan GS-202-01B (Speed H | RU5-D&W | GS-202-01B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2027-01-25 |  | 8202233808 |  | 8202216832#Pengadaan HE ASSY 56-P-101E A | RU6-UTL | 56-P-101A-E1/00 | 50 WAMA | CRTD MACM PRC | 6MR | D16/25/B6/RT-C2H | 1086031020 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363766 | 8202232613 |  | 8202216831#Perbaikan Pompa 211 P-26 A | RU2-HCC | 211-P-26A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363612 | 8202232337 |  | 8202216827#Perbaikan Flange 5" outlet 11 | RU2-HOC | 110-H-1A/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-01-02 | 2102366058 | 8202239787 |  | 8202216824#24_Perbaikan mechseal pompa 2 | RU4-LOC3 | 240P111B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 96198000 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363587 | 8202232234 |  | 8202216822#bocoran lube oil Gearbox | RU2-HCC | 702-PT-3B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-11 |  | 8202233948 |  | 8202216811#Material Antisipasi Lebaran 2 | RU6-HSC | 32-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1482566 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233157 |  | 8202216808#Perbaikan Heat Detector di OC | RU6-UTL | 66-A-224/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 26450 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233257 |  | 8202216804#Perbaikan 52-FV-206F | RU6-UTL | 52-FV-206F/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 26450 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233262 |  | 8202216802#Perbaikan 51-LV-120D | RU6-UTL | 51-LV-120D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 26450 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233437 |  | 8202216801#Penggantian vibrasi switch 05 | RU6-UTL | 052-K-102A1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 26450 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 1102328951 | 8202235216 |  | 8202216795#Perbaikan Alat Lab TBP&POTS | RU5-LAB | 90P0036/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | LAB |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365548 | 8202239786 |  | 8202216794#24_94PIT-107 Transmiter rusak | RU4-SRU | 94PIT107/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365547 | 8202239785 |  | 8202216793#24_94PCV061 | RU4-SRU | 94PCV061/00 | 60 | REL MACM PRC SETC | 4IR | D14/24/B6/RT-6-C2H | 78200000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365546 | 8202239784 |  | 8202216791#24_93PCV101, perbaikan PCV ru | RU4-SRU | 93PCV101/00 | 60 | REL MACM PRC SETC | 4IR | D14/24/B6/RT-6-C2H | 75000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365605 | 8202239783 |  | 8202216790#24_91PCV618, perbaikan PCV | RU4-SRU | 91PCV618/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365604 | 8202239782 |  | 8202216789#24_91PCV607, perbaikan PCV (I | RU4-SRU | 91PCV607/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-02 | 2026-04-02 | 2026-05-05 | 2102360162 | 8202235230 |  | 8202216788#Cable & Lampu explosion proof |  |  | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 297190000 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-04-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-04-22 |  | 8202234002 |  | 8202216787#Kebutuhan material antisipasi | RU6-POC | 39-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 201455191 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233890 |  | 8202216776#Notifikasi Permintaan N2 untu | RU6-ITP | 41-LA-101/00 | 50 | REL MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 1900000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-04-28 |  | 8202232865 |  | 8202216771#Perbaikan Temp gauge di STG | RU6-UTL | 51-G-101B-E1/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 39600 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363607 | 8202232321 |  | 8202216757#KEBOCORAN LO HCGB 170 CT-54 | RU2-HOC | 170-CT-54/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-02 |  | 8202233496 |  | 8202216755#Penggantian Solenoid 52-XV-23 | RU6-UTL | 52-XV-232A/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 26450 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366057 | 8202239781 |  | 8202216750#24_Perbaikan kompresor 220K10 | RU4-LOC3 | 220K101/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 61557000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365495 | 8202239780 |  | 8202216737#24_Pengadaan Press Indikar di | RU4-KPC | PI-U80/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 176018000 | 158338000 | MA4-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363732 | 8202232530 |  | 8202216718#Membran coupling putus | RU2-HCC | 211-P-19A/00 | 60 | REL NMAT PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363788 | 8202232694 |  | 8202216716#Timing belt putus | RU2-HCC | 211-EF-20C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363787 | 8202232692 |  | 8202216714#Timing belt putus | RU2-HCC | 212-EF-20A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-04 | 2102363829 | 8202238080 |  | 8202216689#Pemasangan Hydrant Pada Line | RU2-PK | 970-HYD-FIRE-01/00 | 50 | REL NMAT PRC SETC | 2MR | D12/22/B6/NR-D2H | 1280000000 | 0 | MA3-STA |  | T_YUDIPRAS |  | 2026-02-09 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-05-29 |  | 8202236821 | 8202233977 | 8202216681#PM Grounding & Lightning Taha | RU6-ITP | GROUNDSYS42T101/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/24/B6/RT-C1H | 17 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365334 | 8202239779 |  | 8202216670#24_Perbaikan diafragm CV 520L | RU4-UTL | 520TV706/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 4000000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365860 | 8202239778 |  | 8202216659#24_81LT324 (kondisi korosif p | RU4-KPC | 81LT324/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 14612942 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-30 | 2025-12-30 |  | 8202235199 |  | 8202216643#Perbaikan LCS mixer D-20-06A | RU5-TBL | TM-24-06A/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 54542895 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365618 | 8202239777 |  | 8202216637#24_ganti belt 018E106 | RU4-FOC2 | 018E106/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 5426666 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-03 | 2026-02-02 | 2026-02-02 | 2102358228 | 8202234206 |  | 8202216634#PENGADAAN TOOLS RGA RU VII | RU7-OFF | 5-T-11/00 | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363584 | 8202232235 |  | 8202216627#Limit Switch Sootblower 110 | RU2-HOC | 110-BHMP-H1-54/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365646 | 8202239776 |  | 8202216626#24_Ganti Press.Transmitter Va | RU4-UTL | 054WS103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 26181382 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-10 | 2026-04-10 | 2026-12-29 | 2102360235 | 8202235196 |  | 8202216625#Penggantian ACB SS-69 LC | RU5-UTL | P-30-MC69LCD/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 610000000 | 0 | MA2-LIS |  | BERFASTIANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-07-13 | 2102361072 | 8202236216 |  | 8202216623#Perbaikan Blowndown sample 15 | RU4-RFCUTL | 151B501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-13-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358227 | 8202234189 |  | 8202216614#Pengadaan Lampu Sorot di Area |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-04 | 2026-02-07 | 2026-02-04 | 2026-02-06 |  | 8202238088 |  | 8202216613#LTSA Perbaikan Pompa 15-P-101 | RU6-RCC | 15-P-101C/00 | 60 | REL CSER NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 1 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363789 | 8202232698 |  | 8202216610#Tie In Perundam | RU2-UTL | 520-P-601A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 001
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202234707 |  | 8202216595#TGH1_24 PM elevator 011C101 | RU4-FOC2 | 011S104/00 | 60 WASR | REL CSER NMAT PRC SETC | 4ER | D14/24/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-11 | 2025-10-31 | 2025-10-31 | 2102360272 | 8202235193 |  | 8202216592#Perb. thermowell Tk. R-9 Rp R | RU5-TBL | IHLA-RP-R/00 | 60 | TECO CNF MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 73057500 | 0 | MA4-INT |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234035 |  | 8202216577#COA 32-V-106 A | RU6-HSC | 32-V-106A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 60 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-14 | 2025-12-29 | 2102360375 | 8202235191 |  | 8202216567#Perbaikan Lampu area OM Selat | RU5-TBL | PLANT-20-LIS/00 | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1612951594 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-14 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365492 | 8202239775 |  | 8202216561#24_[CR] 014K102A: high temp 3 | RU4-FOC2 | 014K102A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 17403318 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-16 | 2102365328 | 8202239774 |  | 8202216549#24_Pengadaan Bolt Untuk Senso | RU4-FOC2 | LN11-1001C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2102360544 | 8202235172 |  | 8202216546#perbaikan Mixer Y-8-02B | RU5-E15112 | Y-8-02B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 18526559 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-26 | 2102360635 | 8202235175 |  | 8202216523#MAT.PENGGANTIAN VALVE&PIPING | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1407234764 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363965 | 8202232648 |  | 8202216522#Pengadaan spare seal kit hydr | RU2-ITP |  | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-04-08 | 2026-02-02 | 2026-02-02 | 2102363254 | 8202232217 |  | 8202216521#Pengadaan Material Fluida Clo | RU2-ITP |  | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202233658 |  | 8202216518#Penggantian field signal loca | RU6-POC | 39-K-101-E1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202233657 |  | 8202216517#Penggantian field signal loca | RU6-POC | 39-K-101-E1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202233656 |  | 8202216516#Penggantian field signal loca | RU6-POC | 39-K-101-E1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-12 | 2026-05-06 |  | 8202233655 |  | 8202216515#Penggantian field signal loca | RU6-POC | 39-K-101-E1B/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-12 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233365 |  | 8202216513#Perbaikan 13-TE-158 | RU6-DHC | 13-R-102/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102352947 | 8202238081 |  | 8202216508#Pek. On/off Valve & Field Ins | RU3-UTL | RWCP2-PLC/00 | 60 | REL CSER NMAT PRC SETC | 3IR | D13/25/B6/NR-4-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-07-15 |  | 8202238024 | 8202238504 | 8202216504#Addendum Biaya Pek rewinding | RU6-DHC | 12-K-501C-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/24/B6/NR-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365503 | 8202239773 |  | 8202216498#24_(CR) Base Tie Bar Bolt Pat | RU4-KPC | 84K202C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365979 | 8202239772 |  | 8202216488#24_Kerusakan Body Valve 106FV | RU4-RFCGTO | 106FV006/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365932 | 8202239771 |  | 8202216485#24_Penggantian Control Valve | RU4-KPC | 88FV242/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 737032000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-14 | 2026-02-04 | 2026-02-04 | 2102352970 | 8202238507 |  | 8202216484#PEKERJAAN PEMBERSIHAN BAK SUM |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 32100000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-10-27 | 2102360941 | 8202237488 |  | 8202216463#Perbaikan Winding DEG 152-G-5 | RU4-RFCUTL | 152G502T/00 | 50 | REL NMAT PRC SETC | 4ER | D14/24/B6/RT-13-C2H | 3725000000 | 0 | MA5-LIS |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-06-05 | 2102358782 | 8202235169 |  | 8202216457#Penggantian I/P Transducer 23 | RU5-D&W | INT-CDU-V/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 39360569 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365611 | 8202239770 |  | 8202216448#24_[BK]Perbaikan Throttle Val | RU4-LOC3 | 240K102P1A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-9-C2H | 309926000 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363764 | 8202232610 |  | 8202216443#Perbaikan Pompa 550-P-102 | RU2-UTL | 550-P-01/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 17994252 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-09-17 | 2102360982 | 8202234455 |  | 8202216434#RKA24_Penggantian Level Glass | RU4-UTL | 52B3/00 | 60 WAMA | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102360983 | 8202234460 |  | 8202216433#RKA24_Penggantian Level Glass | RU4-UTL | 52B2/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102360984 | 8202234464 |  | 8202216432#RKA24_Penggantian Level Glass | RU4-UTL | 52B1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 |  | 2025-11-14 | 2025-12-04 | 2102360545 | 8202235167 |  | 8202216422#Material pelengkap pergantian |  |  | 01 | CRTD NMAT PRC | 5MR | D15/09/B6/RT1-SWNH | 192 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-11-14 | PM |  | 045
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363680 | 8202232424 |  | 8202216415#Conmon 905-TG-03 | RU2-UTL | 905-GT-3/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/RT-D2H | 0 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363712 | 8202232491 |  | 8202216411#Perbaikan 140 P-19B | RU2-HOC | 140-P-19B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 63400 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-24 | 2026-11-30 | 2026-12-30 | 2102360328 | 8202235150 |  | 8202216409#Pengadaan kabel power 110 VDC |  |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 74400000 | 0 | MA1-LIS |  | GHAGASP |  | 2026-02-11 | PT02 | 8 | 3 | 2026-11-30 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-12-01 |  | 8202232832 |  | 8202216403#Perbaikan Turbine 51-P-101A-T | RU6-UTL | 51-P-101A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26400 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-09-17 | 2102366053 | 8202239769 |  | 8202216400#24_[CR] Perbaikan pompa 41P12 | RU4-TRML | 41P10B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 93080800 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-11-05 | 2102365557 | 8202239768 |  | 8202216391#24_47P-504B, Pengantian Beari | LOC1-UP4 | 47P504B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 4645079 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102363801 | 8202238092 |  | 8202216388#Fabrikasi parts | RU2-HCC | 211-P-13BR/01 | 60 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/RT-D2H | 654000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-17 | 2026-02-02 | 2026-12-01 |  | 8202232803 |  | 8202216387#Permanent Repair Pompa 55-A-1 | RU6-UTL | 55-A-101B-P1-M/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 78419958 | 52800000 | MA4-ROT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365585 | 8202239767 |  | 8202216379#24_Kerusakan Control Valve 18 | RU4-GTO | 180KV608A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-14-C2H | 2 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365572 | 8202239766 |  | 8202216378#24_Kerusakan Control Valve 14 | RU4-GTO | 140PCV090/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365571 | 8202239765 |  | 8202216377#24_Kerusakan Control Valve 14 | RU4-GTO | 140PCV003/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365504 | 8202239764 |  | 8202216370#24_[CR] Spring unloader valve | RU4-KPC | 82K201B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233917 |  | 8202216361#Material Wire Mash 32-V-106AB | RU6-HSC | 32-V-106A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 161364000 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-08 | 2026-08-03 |  | 8202232904 |  | 8202216352#Perbaikan Pulley Finfan 33-E- | RU6-HSC | 33-E-118J1-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 5208314 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-07-09 | 2102360371 | 8202235139 |  | 8202216350#Penggantian pp 16" outlet CPI | RU5-D&W | E-34-08/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2027-06-03 |  | 8202233769 |  | 8202216349#Pengadaan New Motor Assy 63-M | RU6-ITP | 63-M-302-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 4609 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-09-15 | 2102365592 | 8202239763 |  | 8202216345#24_Pengadaan Pulley Motor Fin | RU4-RFCGTO | 105E501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-13-C2H | 0 | 0 | MA7-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-18 | 2026-01-02 | 2026-01-02 |  | 8202234942 | 8202238082 | 8202216340#KV PM Cleaning Pre Heater & R | RU3-CDGP |  | 60 | TECO CNF NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-01-09 | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-03 | 2026-01-01 | 2026-01-01 |  | 8202234832 | 8202234863 | 8202216336#KV Tambat Kapal Area SG 2023- |  |  | 60 | REL CNF PRT NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RAMADENY | 2026-06-08 | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-07 | 2026-02-04 | 2027-01-27 |  | 8202238506 |  | 8202216324#Retube HE LPSR (50-E-101) | RU6-UTL | 50-E-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 23444210 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202232871 |  | 8202216323#Perbaikan Strainer 39-STR-005 | RU6-POC | 39-K-101/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 1 | 98097000 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365978 | 8202239762 |  | 8202216321#24_Kerusakan Control Valve 18 | RU4-GTO | 180KV607A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 2 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365946 | 8202239761 |  | 8202216318#24_Pengecekan 101PDI030 | RU4-RFCC | 101PDT030/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 1 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363649 | 8202232379 |  | 8202216305#Perbaikan C-1A (Abnormal nois | RU2-HOC | 220-C-1A/00 | 50 | REL NMAT PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233869 |  | 8202216297#Pekerjaan Perbaikan Analyzer | RU6-UTL | 56-AT-001/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233724 |  | 8202216292#Penggantian 51-LIC-120 A/B/C/ | RU6-UTL | 51-LV-120A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-07 | 2025-11-07 |  | 8202233073 |  | 8202216291#Perbaikan modul tacho meter S | RU6-UTL | 51-G-101E-T/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K601 | 2026-02-02 | 2026-03-30 | 2026-02-02 | 2026-02-02 |  | 8202234039 |  | 8202216290#Cek / Perbaikan alarm bently | RU6-UTL | 51-G-101A/00 | 60 | REL CSER GMPS MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 1040938286 | 94419143 | MA4-INT |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 | 2102360452 | 8202235138 |  | 8202216279#Perbaikan line16" dr BAB ke C | RU5-D&W | GHDC/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102360967 | 8202236318 |  | 8202216274#Perb bottom tangki area kilan | RU4-TRML | 041T112/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365515 | 8202239759 |  | 8202216270#24_Sensor Temperature Winding | RU4-RFCUTL | 152G501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 6 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365382 | 8202239758 |  | 8202216265#25_Kendala Sistem TS XRay Rig | RU4-TRML | 30BD101CU2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 1 | 0 | WS-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365544 | 8202239757 |  | 8202216257#24_Penggantian LI Mekanis 71T | RU4-TRML | 71T10/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-4-C2H | 1 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202237277 |  | 8202216252#Cleaning Holding Basin Area 7 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364194 | 8202235374 |  | 8202216249#Perbaikan UPS DC 01EE1339A di |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361202 | 8202237292 |  | 8202216242#Celaning for internal inspect | RU4-TRML | 041T317/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361203 | 8202237306 |  | 8202216241#Buoy Marker SPM Rusak dan Hil | RU4-TRML | SPM/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361062 | 8202236127 |  | 8202216239#Perbaikan Check Valve 36P106A | RU4-TRML | 36P106A/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361207 | 8202237318 |  | 8202216238#Ball Valve 24" dibawah SPM Ru | RU4-TRML | SPM/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102360975 | 8202234534 |  | 8202216229#Struktur Platform, MD, BD dan | RU4-TRML | 70BD1IU1/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364369 | 8202235570 |  | 8202216227#NR_Perbaikan Dinding Parit Ki |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364205 | 8202235923 |  | 8202216218#RKAP 2024 RT PERBAIKAN PIPA D |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235991 |  | 8202216217#RKAP 2024 CLEANING ROOF TANKI |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364204 | 8202235846 |  | 8202216215#RKAP 2024 RT TSA METERING SYS |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364217 | 8202235951 |  | 8202216214#RKAP 2024 PERBAIKAN PIPA FIRE |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364366 | 8202235934 |  | 8202216213#RKAP 2024 RT PERBAIKAN PIPA A |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235901 |  | 8202216212#RKAP 2024 RT PERBAIKAN PLATFO |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364216 | 8202235960 |  | 8202216211#RKAP 2024 PERBAIKAN PIPA AREA |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364206 | 8202235835 |  | 8202216210#RKAP 2024 RT UP CLEANING TANK |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364209 | 8202235755 |  | 8202216209#RKAP 2024 RT UPC fire water, |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364213 | 8202235635 |  | 8202216208#RKAP 2024 RT UPC pipe support |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364207 | 8202235719 |  | 8202216207#RKAP 2024 RT UPC Gedung Area |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364210 | 8202235668 |  | 8202216206#RKAP 2024 RT UPC Pengecatan A |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364211 | 8202235873 |  | 8202216205#RKAP 2024 RT Perpipaan statio |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235810 |  | 8202216204#RKAP 2024 RT UPC bordes,handr |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364367 | 8202235591 |  | 8202216203#RKAP 2024 RT UPC Wrapping pip |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364208 | 8202235616 |  | 8202216202#RKAP 2024 RT UPC stripping Ar |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364203 | 8202235861 |  | 8202216201#RKAP 2024 RT Pondasi Tanki Ar |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364215 | 8202235790 |  | 8202216200#RKAP 2024 RT UPC Cleaning roo |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364368 | 8202235699 |  | 8202216199#RKAP 2024 RT UPC LA Area OM |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364214 | 8202235558 |  | 8202216198#RKAP 2024 RT UPC Wrapping tia |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363731 | 8202232529 |  | 8202216196#Penggantian Tube End Protecto | RU2-HOC | 110-E-54/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364212 | 8202235733 |  | 8202216194#RKAP 2024 RT UPC Floating hos |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363733 | 8202232531 |  | 8202216193#Penggantian Tube & Protector | RU2-HOC | 110-E-53/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235057 |  | 8202216187#RT_Perbaikan Tembok Pagar |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364218 | 8202236049 |  | 8202216186#UPC Bordes Area 70 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235043 |  | 8202216184#RT_Perbaikan Vacuum Truck |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361043 | 8202235922 |  | 8202216182#Perbaikan lampu penerangan ge | RU4-LOC3 | 200BD2/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364202 | 8202237029 |  | 8202216180#Pengg Valve 14''300 line Prop |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364200 | 8202234793 |  | 8202216179#Tali nylon pickup rope 8" SPM |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364201 | 8202234985 |  | 8202216178#Shackle Omega 17 tons (SPM) |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364199 | 8202236073 |  | 8202216175#Perbaikan crane dermaga 3 |  |  | 01 WENG | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361052 | 8202236045 |  | 8202216151#Kerusakan concrate 94S401 (St | RU4-SRU | 94S401/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364197 | 8202236169 |  | 8202216130#Perbaikan Building Control Ro |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361016 | 8202235319 |  | 8202216123#Pagar HB rusak (Stationary MA | RU4-TRML | 66HB101/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361143 | 8202236920 |  | 8202216121#penggantian Breather vent 43T | RU4-TRML | 43T102/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364362 | 8202235660 |  | 8202216117#NR_Pemangkasan Pohon Area Kil |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364363 | 8202236420 |  | 8202216113#Penggantian Valve 12" 300 di | RU4-REL |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364364 | 8202236021 |  | 8202216110#Upgrading dinding Control Roo |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364195 | 8202234958 |  | 8202216109#Penambahan Gate Valve 10" 31T |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361106 | 8202236505 |  | 8202216108#Penggantian PSV Pompa 33P2BD | RU4-WS | 33P2BD/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-12 | 2025-11-12 | 2102361166 | 8202237118 |  | 8202216107#D_24 014FT021 | RU4-FOC2 | 014FT021/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235246 |  | 8202216093#Perbaikn Sarana Bantu Navigas |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235210 |  | 8202216091#Pemasangan Atap Trafo All Sub |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361049 | 8202236027 |  | 8202216090#Kontrak Cleaning CPI 057S101 | RU4-UTL | 057S101/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363700 | 8202232461 |  | 8202216083#Perbaikan 410 E-15 Tube bundl | RU2-HCC | 410-E-15/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/22/B6/RT-D2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-10 |  | 8202233244 |  | 8202216080#Perbaikan Ampere Motor 11-P-1 | RU6-HSC | 11-P-114B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 6396489 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364361 | 8202235712 |  | 8202216065#NR_Kerusakan pada atap dindin |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236316 |  | 8202216060#Perb. crane jetty 3 A-70 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202234891 |  | 8202216053#Penambhan valve 14 300 line p |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364191 | 8202235860 |  | 8202216049#Perbaikan Line fresh water ex |  |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361034 | 8202235623 |  | 8202216041#Perbaikan pintu pagar (Stat M | RU4-SRU | 90CL002/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365505 | 8202239756 |  | 8202216026#24_(CR) Perbaikan pompa 14P65 | RU4-FOC1 | 14P650A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361019 | 8202235596 |  | 8202216025#Perbaikan pondasi 93K401A (St | RU4-SRU | 93K401A/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365918 | 8202239755 |  | 8202216008#24_[BD]Perbaikan Pompa ALOP 2 | RU4-LOC1 | 22K1P2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 901200 | 88150 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236019 |  | 8202216000#Perbaikan Halte |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365555 | 8202239754 |  | 8202215989#24_Kopling Speed Variator 24S | RU4-LOC1 | 24S1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 26537500 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365910 | 8202239753 |  | 8202215985#24_Penggantian Power Supply I | RU4-TRML | 70CIB-BD4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 5000000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361048 | 8202236025 |  | 8202215969#Perbaikan Gear box 47S508A (R | LOC1-UP4 | 47S508A/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364355 | 8202235180 |  | 8202215965#Pipe Support (Beam) di Dermag |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-05-21 | 2026-02-03 | 2026-02-03 | 2102360536 | 8202235758 |  | 8202215964#motor kaki 24P-3A patah | RU4-LOC1 | 24P3AM/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-LIS |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235595 |  | 8202215963#Perbaikan Pontoon CIB I dan C |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361011 | 8202235212 |  | 8202215962#Pemasangan atap pelindung 13K | RU4-FOC1 | 13K1A/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102360966 | 8202236266 |  | 8202215958#erbaikan / Penggantian valve | RU4-UTL | 52B3/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361015 | 8202235302 |  | 8202215957#Pasang Isolasi Cover Channel | RU4-FOC2 | 012E101-7/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364189 | 8202235354 |  | 8202215952#Perbaikan Valve 47T105 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-21 | 2025-11-21 | 2102361199 | 8202237281 |  | 8202215949#Cleaning HB 49 & Second Trap | RU4-TRML | 49HB1/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-21 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361027 | 8202235434 |  | 8202215948#Perbaikan Stationary 66P101C | RU4-TRML | 66P101C/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365977 | 8202239752 |  | 8202215946#24_Pengadaan Flow Transmitter | RU4-GTO | 140FT011/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 15 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363744 | 8202232555 |  | 8202215942#Penggantian Filter Lube Oil | RU2-HSC | 301-C-1/00 | 60 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 10185780 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2025-12-01 | 2025-12-31 |  | 8202235121 |  | 8202215941#Perbaikan Spoel Contactor Gm- | RU5-E15112 | GM-8-05C/00 | 60 | REL CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 4275266 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2025-12-01 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361193 | 8202237279 |  | 8202215925#Cleaning HB Timur 66HB101 (St | RU4-TRML | 66HB101/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-04-24 | 2026-03-30 | 2026-12-30 | 2102361214 | 8202237345 |  | 8202215922#85P207 cek valve passing | RU4-KPC | 85P207A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | TEGARPRAMUDY |  | 2026-03-31 | PT02 |  | 3 | 2026-03-30 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361073 | 8202236221 |  | 8202215920#Perbaikan baseplate 54WS2P1 | RU4-UTL | 054WS101/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-05 | 2102365603 | 8202239751 |  | 8202215911#24_Pengadaan Plug Valve 93E40 | RU4-SRU | 93E402A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-6-C2H | 2112 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202237289 |  | 8202215899#Cleaning CPI,COC,Sewer & Pari |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364188 | 8202237036 |  | 8202215897#Pengecetan external Coating 6 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102360829 | 8202235062 |  | 8202215894#Tabung 94LT065 buntu | RU4-SRU | 94LT065/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364187 | 8202237209 |  | 8202215885#Coating dinding luar tanki 43 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364354 | 8202236242 |  | 8202215879#Perbaikan All Substation di R |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361050 | 8202236033 |  | 8202215873#UPC Perb Perpipaan & Asesoris | RU4-TRML | LN71-1006AA/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-21 | 2025-11-21 |  | 8202235054 |  | 8202215871#Pnggantian Foam Chamber |  |  | 01 WENG | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA4-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-21 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236064 |  | 8202215870#UPC aksesoris stationary perp |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233847 |  | 8202215867#Pembuatan spool piece EBJ | RU6-ITP | 42-T-301A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236088 |  | 8202215866#Perbaikan crane 73X8 Jetty II |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364353 | 8202236518 |  | 8202215862#Penggantian PSV 43T2 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202234549 |  | 8202215860#Pengadaan opto matic glass Ar |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202235220 |  | 8202215856#Permintaan gasket buat TA |  |  | 01 | CRTD NMAT PRC | 4MT |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-13 | 2026-01-02 | 2027-01-22 | 2102366114 | 8202241363 |  | 8202215855#[PV] Fabrikasi Casing & Cover | RU4-RFCC | 102P510A/00 | 50 | CRTD CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 100000 | 0 | MA6-ROT |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360824 | 8202234961 |  | 8202215854#SOR & Overhaul 38T105 [RKAP 2 | RU4-TRML | 38T105/00 | 01 | CRTD CSER NMAT PRC | 4MO |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102360965 | 8202236264 |  | 8202215846#Perbaikan Analyzer 92AI143 ( | RU4-SRU | 92V402/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2027-03-10 |  | 8202233884 |  | 8202215841#Pegadaan motor baru 42-P-403A | RU6-ITP | 42-P-403A-M/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 3841 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2026-05-12 |  | 8202238087 |  | 8202215840#LTSA PM Tangki | RU6-ITP | 63-A-101-M/00 | 60 | CLSD NCMP NMAT PRC | 6MR | D16/24/B6/RT-C2H | 1 | 0 | MA4-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361201 | 8202237290 |  | 8202215831#Check Flow Product 520B401 me | RU4-UTL | 520B401/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363790 | 8202232704 |  | 8202215822#Suara mixer kasar | RU2-HCC | 211-ME-3/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/22/B6/NR-D2H | 149348314 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-11-23 | 2026-12-04 | 2102360542 | 8202235119 |  | 8202215819#Perbaikan Ea-231-01B (bering | RU5-D&W | KEA-231-01B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 44593703 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-23 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233792 |  | 8202215804#Pengadaan Material Gas Filter | RU6-HSC | 32-K-101/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365976 | 8202239750 |  | 8202215797#24_Pengadaan Pressure Transmi | RU4-GTO | 140PT034A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 10 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102361200 | 8202237283 |  | 8202215794#Cleaning Equalisasi 47S505 (S | LOC1-UP4 | 47S505/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365975 | 8202239749 |  | 8202215790#24_Pengadaan Positioner Fishe | RU4-GTO | 120FV002/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 14 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235235 |  | 8202215784#Peremajaan Line Dist Air Bers |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236198 |  | 8202215780#Ganti Line Status OLLS |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202234412 |  | 8202215768#Pengadaan steam coil Tanki OM |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364185 | 8202235116 |  | 8202215765#Pembuatan Atap Area Metering |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235066 |  | 8202215759#pembuatan shelter untk mushol |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202233003 |  | 8202215751#Perbaikan pompa 056-P-101B-T | RU6-UTL | 056-P-101B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26400 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-12 | 2026-02-03 | 2026-11-04 | 2102361152 | 8202237050 |  | 8202215745#D_24 Penggantian Flange Orifi | RU4-UTL | 54T4/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2025-12-05 |  | 8202233014 |  | 8202215744#Perbaikan Nozzle Distributor | RU6-HSC | 25-F-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363624 | 8202232224 |  | 8202215738#LOW PERFORM RECYCLE 220 C-1A | RU2-HOC | 220-C-1A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 19211890 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-22 | 2102360541 | 8202235117 |  | 8202215736#Perbaikan motor GM-201-13A | RU5-D&W | GM-201-13A/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 2065200 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-12-02 | 2026-12-02 | 2102360681 | 8202235109 |  | 8202215734#PENGGANTIAN BEARING POMPA 101 | RU5-TBL | 101-P-2C/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-12-02 | 2026-12-02 | 2102360680 | 8202235110 |  | 8202215732#PENGGANTIAN BEARING POMPA 101 | RU5-TBL | 101-P-1C/00 | 60 | CLSD CNF CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH | 2026-03-13 | 2026-02-11 | PT02 |  | 3 | 2026-03-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-12-02 | 2026-12-02 | 2102360669 | 8202235112 |  | 8202215731#PENGGANTIAN BEARING POMPA 101 | RU5-TBL | 101-P-1A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-12-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-05 | 2102365326 | 8202239748 |  | 8202215728#24_Mtl. Perbaikan Bocoran 023 | RU4-LOC2 | 023E113A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-8-C2H | 6524033 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-15 | 2025-12-15 | 2102360548 | 8202235108 |  | 8202215726#G-3-18A Bearing Defect | RU5-E15112 | G-3-18A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 6172777 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-11 |  | 8202233323 |  | 8202215723#Perbaikan 17-LSLL-011 | RU6-RCC | 17-V-104/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364343 | 8202235847 |  | 8202215721#Modifikasi Line Flush System |  |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361020 | 8202235091 |  | 8202215720#Pembuatan Atap di Area Injeks | RU4-TRML | 030PSV301/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364342 | 8202234429 |  | 8202215704#Pengadaan roof Leg seal OM 60 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-05 | 2026-07-23 | 2026-08-24 | 2102360755 | 8202235106 |  | 8202215691#Perbaikan turbin GS-202-05B | RU5-D&W | GS-202-05B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 137000000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-07-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-11-30 | 2026-12-18 | 2102360752 | 8202235104 |  | 8202215688#PM compressor emrg airman PDS |  |  | 60 | REL NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 198 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365937 | 8202239747 |  | 8202215683#24_80PT231 rusak | RU4-KPC | 80PT231/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 19677782 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365600 | 8202239746 |  | 8202215682#24_Perbaikan Limit Switch T&T | RU4-UTL | 51G2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365583 | 8202239745 |  | 8202215681#24_Perbaikan Probe Rpm Pompa | RU4-RFCUTL | 154P507B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 11300000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361151 | 8202237046 |  | 8202215680#Pengecatan Stack 520B401&520B | RU4-UTL | 520B401/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365582 | 8202239744 |  | 8202215679#24_Perbaikan probe RPM 154P50 | RU4-RFCUTL | 154P507A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-13-C2H | 11300000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361045 | 8202235965 |  | 8202215676#Perbaikan isolasi MA-1 | RU4-FOC1 | 11C1/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361051 | 8202236034 |  | 8202215675#Perbaikan fire profing di are | RU4-FOC1 | 11C7/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365589 | 8202239743 |  | 8202215672#24_Perbaikan 57FV301 HGO Cont | RU4-UTL | 057PSV011/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365348 | 8202239742 |  | 8202215668#24_Perbaikan Transmitter 63FT | RU4-RFCC | 101XA-U101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 23800000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365733 | 8202239741 |  | 8202215663#24_Perbaikan Transmitter 63-L | RU4-TRML | 63PSV301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 23800000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365957 | 8202239739 |  | 8202215660#24_Perbaikan Transmitter 63FT | RU4-RFCUTL | 63FT702/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 23800000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365542 | 8202239738 |  | 8202215657#24_Penggantian Selenoid 014BV | RU4-FOC2 | 014ZS50/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-2-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-09 | 2026-12-15 | 2026-12-15 | 2102360667 | 8202235107 |  | 8202215656#PENGGANTIAN BEARING POMPA 101 | RU5-TBL | 101-P-1B/00 | 60 | CLSD CNF CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH | 2026-03-10 | 2026-02-11 | PT02 |  | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364183 | 8202237058 |  | 8202215653#Pengecatan Dan Isolasi Area U |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364182 | 8202237044 |  | 8202215652#Pengecetan & Perbaikan Isolas | RU4-REL |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235226 |  | 8202215651#Pekerjaan Pengecatan Peralata |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235508 |  | 8202215648#Perbaikan Power House-1 UTL C |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364181 | 8202236279 |  | 8202215646#Perb. Structure Metering & Su |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202236572 |  | 8202215645#Penggantian Motor Fin fan |  |  | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361064 | 8202236186 |  | 8202215643#Unit 93, penggantian overload | RU4-SRU | 93E407AM/00 | 50 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361065 | 8202236187 |  | 8202215641#unit 92 penggantian overload | RU4-SRU | 92E407A1M/00 | 50 | CRTD NMAT PRC | 4ER |  | 0 | 0 | MA1-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-06-03 | 2026-02-03 | 2026-02-03 | 2102361066 | 8202236188 |  | 8202215640#Unit 91, penggantian overload | RU4-SRU | 91E402AM/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-6-C2H | 0 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235918 |  | 8202215633#Perbaikan Lantai SS & Basemen |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361012 | 8202235213 |  | 8202215631#Permintaan terpal kanvas untu | RU4-TRML | 041T303/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K201 | 2026-02-01 |  | 2026-02-02 | 2026-02-02 | 2102363616 | 8202232346 |  | 8202215628#POMPA VIBRASI ALARM 140 P-2A | RU2-HOC | 140-P-2A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/22/B6/NR-D2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202235395 |  | 8202215577#Overhaul 38T101 |  |  | 01 | CRTD CSER NMAT PRC | 4MO |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364169 | 8202235729 |  | 8202215576#Perbaikan Pemeliharaan Gedung |  |  | 01 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364180 | 8202235556 |  | 8202215575#Perbaikan Pontoon CIB I dan C |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364168 | 8202235534 |  | 8202215574#Perbaikan Pos Security |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235203 |  | 8202215566#Pintu Air C/9 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361047 | 8202236013 |  | 8202215564#valve LG rusak | RU4-TRML | 48V201/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235090 |  | 8202215561#Pembuatan Bak Saluran Pengedr |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-21 | 2025-11-21 | 2102361198 | 8202237278 |  | 8202215560#Cleaning Holding Basin 66 (st | RU4-TRML | 66HB101/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-21 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364167 | 8202235279 |  | 8202215558#Perbaikan/Penggantian PVRV ta |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202234857 |  | 8202215552#Resizeing Pipa Fresh Water |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361014 | 8202235300 |  | 8202215551#Pasang Isolasi FD Fan 52B1 | RU4-UTL | 52B1K/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202235278 |  | 8202215549#Pek Bathymetry pemeriksaan su | RU4-LOC147 |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361195 | 8202237261 |  | 8202215547#Cleaning perbaikan roof & bot | RU4-TRML | 041T313/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364166 | 8202237087 |  | 8202215545#Pengambilan material untuk ch |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364340 | 8202237073 |  | 8202215544#Pengantian hidrolik LA CIB 1 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236164 |  | 8202215542#UP Pengecatan Fire Water Line |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364269 | 8202235655 |  | 8202215540#Perbaikan pintu air parit jal |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364165 | 8202236182 |  | 8202215536#Unit Price Cleaning External |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361063 | 8202236166 |  | 8202215535#Ganti Tali Nylon 4" Fasilitas | RU4-TRML | SPM/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236238 |  | 8202215528#Fasilitas Perimeter Area Kila |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365577 | 8202239519 |  | 8202215524#24_93F401, Rotameter rusak | RU4-SRU | 93F401/00 | 50 WAMA | REL MACM PRC SETC | 4MR | D14/24/B6/RT-6-C2H | 598220000 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361196 | 8202237263 |  | 8202215523#Cleaning internal & pengecata | RU4-TRML | 47T105/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361197 | 8202237265 |  | 8202215521#Cleaning internal & pengecata | RU4-TRML | 47T103/00 | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102360587 | 8202235084 |  | 8202215519#Perbaikan 201-PCV-061 C | RU5-D&W | 201-PT-061/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 39360569 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358353 | 8202234171 |  | 8202215514#Perbaikan Mesin Las Maintenan |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102364164 | 8202235348 |  | 8202215510#Overhaul&cleaning tanki 42T10 |  |  | 01 | CRTD CSER NMAT PRC | 4MO |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-12-29 | 2026-12-29 | 2102363793 | 8202232713 |  | 8202215509#Penggantian Blower 310-C-1 | RU2-HSC | 310-C-1/00 | 50 | REL MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-29 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364233 | 8202236031 |  | 8202215505#UPC Stationary dan Perpipaan |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236171 |  | 8202215503#Unit Price Perbaikan Pondasi |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358354 | 8202234163 |  | 8202215501#Pengadaan Ring Oil 5-P-02A wi |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K601 | 2026-02-02 | 2026-02-26 | 2026-02-02 | 2026-12-01 |  | 8202234090 |  | 8202215496#15K101 Bocor L/o pada bearing | RU6-RCC | 15-K-101/00 | 50 WAMA | REL CSER MSPT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ERWINSURYAG |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360823 | 8202234960 |  | 8202215488#Special O Ring Gasket FO 87F2 | RU4-KPC | 87FE201/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 |  | 8202236302 |  | 8202215487#Perb. Patok dan Verifikasi Ja |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102364231 | 8202236180 |  | 8202215485#Ganti Roof Seal Tank 71T10, 7 |  |  | 01 | CRTD NMAT PRC | 4MR |  | 0 | 0 | MA3-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2025-11-28 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202233305 |  | 8202215476#Perbaikan 22-PT-610 | RU6-DHC | 22-PT-610/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202232833 |  | 8202215471#Perbaikan Turbine 51-G-101E-P | RU6-UTL | 51-G-101E-P2A-T/00 | 60 | REL NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363675 | 8202232366 |  | 8202215465#perbaikan coupling | RU2-HSC | 310-C-4/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 23412000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365528 | 8202239518 |  | 8202215448#24_[CR] 011P107A: Oil ring ov | RU4-FOC2 | 011P107A/01 | 60 | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-2-C2H | 64680000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-11 |  | 8202233324 |  | 8202215447#Perbaikan 17-LSLL-008 | RU6-RCC | 17-V-103/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365708 | 8202239517 |  | 8202215446#24_Monitor Vibrasi Rusak | RU4-KPC | 84K201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-10-C2H | 12387213 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-11 |  | 8202233326 |  | 8202215444#Perbaikan 17-LSLL-002 | RU6-RCC | 17-V-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365974 | 8202239516 |  | 8202215443#24_Pengadaan Level Transmitte | RU4-RFCGTO | 148V503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-02-02 | 2026-02-02 |  | 8202232768 |  | 8202215440#PM UPS & DC Charger 2024 | RU6-RCC | OS-14/00 | 50 | CLSD CSER NCMP NMAT PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365338 | 8202239515 |  | 8202215438#24_Penggantian 018PT024B | RU4-FOC2 | 018F102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-2-C2H | 1 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-30 | 2102366100 | 8202239514 |  | 8202215437#24_Penggantian Control valve | RU4-RFCGTO | 47FV008/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 74670000 | 0 | MA7-INT |  | YOHANESMVIS |  | 2026-03-10 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365353 | 8202239513 |  | 8202215435#24_Perbaikan Flow indicator c | RU4-RFCGTO | 47P511A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-05 | 2102365588 | 8202239512 |  | 8202215433#24_Pengadaan Check Valve 14K6 | RU4-FOC1 | 14K602BMV2B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-1-C2H | 2112 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 |  | 8202233596 |  | 8202215432#Penggantian level switch LO 5 | RU6-UTL | 56-K-101F/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 19833 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-09-23 |  | 8202232816 |  | 8202215431#Perbaikan/penggantian SI223 B | RU6-UTL | 51-G-101B-T/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 19833 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-07 | 2026-07-02 |  | 8202233479 |  | 8202215430#Penggantian thermocouple 52-T | RU6-UTL | 52-T-101/00 | 50 | REL NMAT PRC SETC | 6IR | D16/25/B6/NR-C2H | 1986 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-02-23 |  | 8202232842 |  | 8202215429#Perbaikan TSHH di 21-K-101A/B | RU6-DHC | AR-B12-13/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 768 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-30 |  | 8202232843 |  | 8202215425#Perbaikan TSHH di 14-K-102A/B | RU6-DHC | AR-B12-12/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-11 |  | 8202233325 |  | 8202215417#Perbaikan 17-LSLL-005 | RU6-RCC | 17-V-102/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202233203 |  | 8202215414#Perbaikan Coil Xelenoid Valve | RU6-HSC | 33-XV-033/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-03 | 2026-02-02 | 2026-02-02 | 2102358355 | 8202234161 |  | 8202215411#Perbaikan pompa 5-P-13 A/B |  |  | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-02-02 | 2102358431 | 8202234158 |  | 8202215407#Perbaikan 1-P-04 A |  |  | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SYAIPULANUAR | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-03-07 | PM |  | 005
| K701 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-02-02 | 2102358357 | 8202234155 |  | 8202215406#Penggantian line2-4-SC325 Are |  |  | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-ROT |  | SYAIPULANUAR | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-03-07 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-10 |  | 8202232763 |  | 8202215405#PmPdM Trafo di SS-12 | RU6-DHC | 12-PTR1-01A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 142420000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-08-12 |  | 8202238090 |  | 8202215404#Fasilitas Power DC Charger 51 | RU6-UTL | 51-PBC3-102/00 | 60 | REL NMAT PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-15 | 2026-02-02 | 2026-02-02 |  | 8202232771 |  | 8202215398#PM Peralatan Electr/Instr MA3 | RU6-POC | SS-18/00 | 50 | CLSD CSER NCMP NMAT PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA3-LIS |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-30 | 2102366084 | 8202239511 |  | 8202215385#24_166AI-551, Pengadaan anali | RU4-RFCUTL | 166M551/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/NR-14-C2H | 80000000 | 0 | MA7-INT |  | YOHANESMVIS |  | 2026-03-10 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366065 | 8202239510 |  | 8202215383#24_166FT-007B | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 14388000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-02 | 2025-12-22 |  | 8202235078 |  | 8202215381#Perbaikan Panel Trafo Flocula |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 31000192 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-10-28 | 2026-03-11 |  | 8202233315 |  | 8202215363#Perbaikan 19-PSL-703 dan 19-P | RU6-RCC | 19-K-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-12-02 |  | 8202233985 |  | 8202215345#LTSA ATG Tahap 10 11 12 | RU6-ITP | 42-LT-001/00 | 50 | CLSD NCMP NMAT PRC | 6IR | D16/24/B6/RT-C2H | 26400 | 0 | MA4-INT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363589 | 8202232254 |  | 8202215343#Kerusakan belting 211 EF-2 | RU2-HCC | 211-EF2R-1/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 89488000 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202232889 |  | 8202215339#Perbaikan Selenoid 51-XV-002A | RU6-UTL | 51-XV-002C/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 17193 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-03-17 | 2026-03-17 | 2102360628 | 8202235061 |  | 8202215330#Perbaikan Exciter STG's |  |  | 60 | CLSD CNF CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 39311410 | 0 | MA1-LIS |  | SAPBATCH | 2026-03-17 | 2026-02-11 | PT02 |  | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-09 | 2026-04-07 | 2026-04-29 | 2102365379 | 8202239509 |  | 8202215323#24_Perbaikan 14TI323 | RU4-FOC1 | 14TE323B/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 11334500 | 11334500 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-09 | 2026-04-07 | 2026-04-29 | 2102365378 | 8202239508 |  | 8202215322#24_Perbaikan 14TE323A | RU4-FOC1 | 14TE323A/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 11334500 | 11334500 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-09 | 2026-04-07 | 2026-04-29 | 2102365377 | 8202239507 |  | 8202215320#24_Perbaikan 14TE322B | RU4-FOC1 | 14TE322B/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 11334500 | 11334500 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-09 | 2026-04-07 | 2026-04-29 | 2102365376 | 8202239506 |  | 8202215319#24_Perbaikan 14TE322A | RU4-FOC1 | 14TE322A/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 11334500 | 11334500 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-09 | 2026-04-07 | 2026-04-29 | 2102365375 | 8202239505 |  | 8202215318#24_Perbaikan 14TE320 | RU4-FOC1 | 14TE320A/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 22669000 | 22669000 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365941 | 8202239504 |  | 8202215317#24_Penggantian Tachometer Tur | RU4-RFCC | 104K501T-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 17112218 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365631 | 8202239503 |  | 8202215316#24_Perbaikan 101-TT-606 | RU4-RFCC | 101TT-U101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 23998900 | 0 | MA6-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-23 | 2026-08-18 |  | 8202234089 |  | 8202215306#15K101,vibration sensor rusak | RU6-RCC | 15-K-101/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 1920 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-23 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363745 | 8202232556 |  | 8202215303#Plat CS Thick 6 mm Laboratori | RU2-LAB | LAB-LITBANG-8/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/RT-D2H | 0 | 0 | MA1-CIV |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202233636 |  | 8202215299#Penggantian Fusible Tube PSL | RU6-LK/KK | 66-CGD-01/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 17193 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-12-16 |  | 8202233973 |  | 8202215298#LTSA Pemeliharaan Elevator RU | RU6-RCC | 15-A-104/00 | 50 | CLSD CSER NCMP NMAT PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-20 | 2026-02-04 | 2026-02-04 | 2102363963 | 8202238089 |  | 8202215285#LTSA CLEANING SEPARATOR 1,2,3 | RU2-ITP |  | 60 | REL NMAT PRC SETC | 2MR | D12/24/B6/RT-D2H | 92764000 | 0 | MA4-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102366068 | 8202239502 |  | 8202215283#24_GC Lube Syn 100 tidak ters | RU4-KPC | 84K202A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 53000000 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-06-09 | 2026-04-04 | 2026-12-30 | 2102363967 | 8202238091 |  | 8202215279#PERBAIKAN FIRE PROOFING AREA | RU2-HSC |  | 50 | REL NMAT PRC SETC | 2MR | D12/24/B6/RT-D2H | 200000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-02-11 | PT02 |  | 3 | 2026-04-04 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202234036 |  | 8202215271#Cleaning Filter 62-PV-104B | RU6-UTL | 62-PV-104B/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-09 | 2026-12-15 | 2026-12-15 |  | 8202235026 |  | 8202215269#PENGGANTIAN BEARING POMPA 101 | RU5-TBL | 101-5-P-2B/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366079 | 8202239735 |  | 8202215265#24_166FT-005B, Penggantian tr | RU4-RFCGTO | 166P561B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 14388000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366064 | 8202239734 |  | 8202215262#24_166FT-002B, Display redup | RU4-RFCUTL | 166P502B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 14388000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366063 | 8202239733 |  | 8202215259#24_166FT-001B, Transmitter ma | RU4-RFCUTL | 166P501B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 14388000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366093 | 8202239732 |  | 8202215256#24_166FT-556 FT Rusak (Inst.M | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-09-23 | 2102360981 | 8202234449 |  | 8202215255#RKA24_Perb Expantion joint 51 | RU4-UTL | 51G2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366081 | 8202239731 |  | 8202215254#24_166FT-008B, Transmiter mat | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 14388000 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366080 | 8202239730 |  | 8202215253#24_166FT-008 Display redup (I | RU4-RFCUTL | 166FT-U166/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-15 | 2025-12-15 | 2102360661 | 8202235027 |  | 8202215251#G-3-03A Pelumas Keruh | RU5-E15112 | G-3-03A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 132383822 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K201 | 2026-02-06 |  | 2026-02-06 | 2026-02-06 | 2102363973 | 8202238701 |  | 8202215247#LTSA CLEANING BY HIGH PRESS J | RU2-HOC |  | 50 | CRTD NMAT PRC SETC | 2MR | D12/24/B6/RT-D2H | 1351197000 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-06 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365386 | 8202239729 |  | 8202215233#24_Penggantian PD Meter FW Je | RU4-TRML | 39FE202/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 10950000 | 0 | MA3-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-27 | 2025-11-27 | 2102361160 | 8202237094 |  | 8202215222#D_24 Anunciator Low Flow 021F | RU4-LOC2 | 021FT104/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-27 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-19 | 2025-11-19 | 2102361161 | 8202237096 |  | 8202215221#D_24 024TIC203 penunjukkan me |  | 024TT221/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-19 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-11-19 | 2102365640 | 8202239728 |  | 8202215217#24_Rejuvenate 166P560B (Rotat | RU4-RFCGTO | 166P560B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 45125000 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233231 |  | 8202215214#Perbaikan bearing motor 23-P- | RU6-HSC | 23-P-901A-M/00 | 60 | REL CSER GMPS MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 776827 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-12-02 | 2025-12-02 | 2102360633 | 8202235024 |  | 8202215201#MAT.PERB.LINE 116-P-B DI AREA | RU5-TBL | PIPE-ON-SHORE/00 | 60 | TECO CNF MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 95463880 | 0 | MA4-STA |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233710 |  | 8202215187#Penggantian analyzer 32-AT-01 | RU6-HSC | 32-C-103/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233555 |  | 8202215181#Penggantian pipa air limbah s | RU6-UTL | PIPAAIR/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/NR-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-29 | 2102361225 | 8202237486 |  | 8202215180#RKA24_Penggantian Kaca CR | RU4-UTL | 005BD102/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 0 | 0 | GEN-MEK |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233760 |  | 8202215178#Pengadaan Portable Humidity M | RU6-HSC | SS-17/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-12 | 2102360682 | 8202235021 |  | 8202215176#Perbaikan motor EaM-202-05A | RU5-D&W | EAM-202-05A/00 | 60 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 341600 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K701 | 2026-02-02 | 2026-04-03 | 2026-02-02 | 2026-02-02 | 2102358433 | 8202234147 |  | 8202215169#Penggantian PI di 2-R-02 |  |  | 60 | CLSD CNF NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358436 | 8202234135 |  | 8202215168#Penggantian Hose 11/2 #150 3- |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K701 | 2026-02-02 | 2026-04-03 | 2026-02-02 | 2026-02-02 | 2102358432 | 8202234130 |  | 8202215167#Rekomendasi Perbaikan 3-K-01A | RU7-CRU | 3-K-01A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH | 2026-02-02 | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-11 | 2026-01-21 | 2026-01-27 | 2102360662 | 8202235020 |  | 8202215163#PENGGANTIAN BEARING VALVE 6F | RU5-TBL | 101-5-T-01F/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 1506200 | 0 | MA4-STA |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-07 | 2026-06-03 |  | 8202233740 |  | 8202215159#Pengambilan material konsumab | RU6-UTL | 53-A-202A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/NR-C2H | 2903238 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-07-03 |  | 8202233456 |  | 8202215158#Penggantian transmitter 56-FT | RU6-UTL | 56-FT-005/00 | 50 | REL MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 23328597 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233725 |  | 8202215157#Penggantian 39-TG-049 | RU6-POC | 39-K-101/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-02 | 2026-03-05 | 2026-03-05 | 2102365821 | 8202239727 |  | 8202215127#24_Penggantian Tachometer Tur | RU4-RFCC | 101F503P2-T/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 17112218 | 0 | MA6-INT |  | RIOSUYADI |  | 2026-03-10 | PT02 |  | 3 | 2026-04-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-30 |  | 8202232838 |  | 8202215120#Perbaikan Turbin Kompresor 58 | RU6-UTL | 58-K-101C-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-15 | 2025-12-15 | 2102360759 | 8202235019 |  | 8202215100#perbaikan sight glass G-2-09B | RU5-E15112 | G-2-09B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 44145237 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361165 | 8202237115 |  | 8202215091#D_24 014P113A&B power terbali | RU4-FOC2 | 014P113AM/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202232844 |  | 8202215085#Perbaikan Triad kabel RTD are | RU6-HSC | 32-A-101/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-06-12 |  | 8202236817 | 8202233977 | 8202215084#PM Grounding & Lightning Taha | RU6-ITP | GROUNDSYS42T101/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/24/B6/RT-C1H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-07-13 |  | 8202233977 |  | 8202215083#LTSA Grounding&Lightning Syst | RU6-ITP | GROUNDSYS42T101/00 | 60 | CLSD NMAT PRC SETC | 6ER | D16/24/B6/RT-C1H | 13200 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 | 2102360685 | 8202235014 |  | 8202215082#MAT.PERB.21-P70-12"-B20 HVGO | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 32906263 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-10-26 | 2026-11-23 | 2102360753 | 8202235018 |  | 8202215081#Hose & Clamp Diesel Emg no.2 | RU5-UTL | D-EMERG-2-PPII/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 23900000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-06-11 |  | 8202233310 |  | 8202215078#Perbaikan 21-PV-011B | RU6-DHC | 21-PV-011B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365822 | 8202239726 |  | 8202215065#24_Perbaikan mech seal 14K652 | RU4-FOC1 | 14K652/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 2511663 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-03-03 |  | 8202233238 |  | 8202215061#Perbaikan bearing 050-P-301 | RU6-UTL | 050-P-301-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 2574 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-04 | 2026-02-07 | 2026-02-04 | 2026-02-04 | 2102363798 | 8202238041 |  | 8202215060#Perbaikan MLA LSWR Jetty 1 | RU2-ITP | 690-PX-2/01 | 50 | REL CSER MACM PRC SETC | 2MR | D12/24/B6/NR-D2H | 1 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202233500 |  | 8202215059#Penggantian smart positioner | RU6-UTL | 059-FV-783A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 17193 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-05 | 2026-02-03 | 2026-11-24 | 2102366113 | 8202239725 |  | 8202215052#24_Perbaikan Kompresor 260K10 | RU4-LOC3 | 260K101B/00 | 60 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 1506079814 | 140045311 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-07-03 |  | 8202233478 |  | 8202215051#Penggantian thermodial MAC A | RU6-UTL | 059-A-101A-K1/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1697 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365584 | 8202239724 |  | 8202215050#24_Transmitter 148LT001 Rusak | RU4-RFCGTO | 148LT001/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-09 | 2026-03-05 | 2026-03-05 | 2102365534 | 8202239723 |  | 8202215048#24_Perbaikkan Transmitter 13F | RU4-FOC1 | 13FT003/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 19250000 | 19000000 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365914 | 8202239722 |  | 8202215046#24_Perbaikan Solenoid T&T 051 | RU4-UTL | 051G102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 28612000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365920 | 8202239721 |  | 8202215044#24_Penunjukkan 021LT008 merag | RU4-LOC2 | 021LT008/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-07-10 |  | 8202233620 |  | 8202215043#Penggantian kabel feeder 38-E | RU6-POC | 38-TV-030/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 3216 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233494 |  | 8202215039#Penggantian solenoid Dryer 58 | RU6-UTL | 58-D-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 15873 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202233679 |  | 8202215036#Penggantian check valve 6" 51 | RU6-UTL | 51-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-10 | 2026-01-02 | 2026-01-02 | 2102360973 | 8202234443 |  | 8202215035#RKA24_Perbaikan Valve Top Tan | RU4-TRML | 47T104/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-30 |  | 8202233158 |  | 8202215033#Perbaikan Governor Turbine 51 | RU6-UTL | 51-G-101C-P1A-T/00 | 60 | REL CSER GMPS MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 88295000 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365543 | 8202239720 |  | 8202215031#24_Perbaikan ATG Lokal 35T5 | RU4-TRML | 35LT-U35/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-08-10 |  | 8202233918 | 8202233400 | 8202215028#Material Tambahan 12-FV-799 B | RU6-DHC | 12-FV-799/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-11 | 2025-11-25 | 2025-12-01 | 2102360756 | 8202235008 |  | 8202215019#MAT.BLIND FLANGE LINE JUMPER | RU5-TBL | PIPE-SHIP/00 | 60 | TECO CNF MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 12638312 | 0 | MA4-STA |  | SAPBATCH | 2026-05-11 | 2026-02-11 | PT02 |  | 3 | 2026-05-11 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363780 | 8202232660 |  | 8202215015#Pengadaan Part NMS8X ATG | RU2-ITP | RTU01A/00 | 50 | REL MACM PRC SETC | 2IR | D12/24/B6/NR-D2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-03-25 |  | 8202233886 |  | 8202215012#Overhaul motor 42-P-503B | RU6-ITP | 42-P-503B-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 149480 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2027-01-18 |  | 8202233980 |  | 8202215008#LTSA Conmon PLC dan MMS EIE | RU6-RCC | OS-14/00 | 50 | CLSD CSER NCMP NMAT PRC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233151 |  | 8202214997#Perbaikan instumentasi | RU6-ITP | 63-V-201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 15873 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  | 8202235011 |  | 8202214996#Bocoran pada throttle valve S | RU5-UTL | TG-1-PP2/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-10-21 | 2102360979 | 8202234498 |  | 8202214994#RKA24_Ganti Pre Filter 560DR6 | RU4-UTL | 560D601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-5-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-17 | 2026-03-17 | 2026-04-23 | 2102360776 | 8202234966 |  | 8202214990#Penggantian bearing motor pom |  |  | 60 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 578191 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-17 | PM |  | 045
| K201 | 2026-02-04 | 2026-02-21 | 2026-02-04 | 2026-02-04 | 2102363797 | 8202238039 |  | 8202214986#Preventive Maintanance Spring | RU2-HCC | 0-75CC21133MS11/00 | 50 | REL NMAT PRC SETC | 2MR | D12/24/B6/RT-D2H | 5000000 | 0 | MA2-STA |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-12-16 | 2102361224 | 8202237484 |  | 8202214978#Perb. Peralatan Kilang Area U | RU4-RFCUTL | 170PSV060B/00 | 60 | REL NMAT PRC SETC | 4RR | D14/24/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233481 |  | 8202214976#penggantian Thermo Dial 51-TI | RU6-UTL | 51-G-101A-T/00 | 60 | REL MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 13750000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2025-12-30 | 2025-12-30 | 2102360770 | 8202235004 |  | 8202214970#MOV Deaerator macet |  |  | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 2258940 | 0 | WS-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2025-12-30 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365700 | 8202239719 |  | 8202214965#24_Perbaikan 520PDT634 | RU4-UTL | 520B601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365907 | 8202239718 |  | 8202214964#24_Penggantian flow Transmitt | RU4-TRML | 46FT301/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 19511215 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-09 |  | 2026-02-09 | 2026-02-09 |  | 8202238780 |  | 8202214950#JASA SERTIFIKASI TERA ULANG M | RU2-ITP |  | 01 | CRTD NMAT PRC SETC | 2IR | D12/24/B6/RT-D2H | 950000000 | 0 | MA4-INT |  |  |  |  | PT02 |  | 2 | 2026-02-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365614 | 8202239717 |  | 8202214944#24_Pengadaan Suct. Heater 041 | RU4-TRML | 041T110/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-9-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365613 | 8202239716 |  | 8202214943#24_Pengadaan Suct. Heater 041 | RU4-TRML | 041T109/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-9-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365612 | 8202239715 |  | 8202214942#24_Pengadaan Suct. Heater 041 | RU4-TRML | 041T105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-9-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 |  | 2026-02-02 | 2026-12-01 | 2102364372 | 8202233824 |  | 8202214940#Pengadaan Coupling 51-G-101E- | RU6-UTL | 51-G-101E-P2B/00 | 50 WAMA | CRTD CSER MACM PRC | 6RR | D16/25/B6/RT-C2H | 26268 | 0 | MA4-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-30 | 2102366051 | 8202239714 |  | 8202214934#24_Perbaikan 180KV608AB | RU4-GTO | 180KV608A/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 71990000 | 0 | MA7-INT |  | YOHANESMVIS |  | 2026-03-10 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-30 | 2102366069 | 8202239713 |  | 8202214933#24_Perbaikan 180KV607AB | RU4-GTO | 180KV607A/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 71990000 | 0 | MA7-INT |  | YOHANESMVIS |  | 2026-03-10 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365919 | 8202239712 |  | 8202214931#24_Line tapping chamber 021LT | RU4-LOC2 | 021LT014/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-8-C2H | 14612942 | 0 | MA2-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-11-18 | 2025-11-18 | 2102363734 | 8202232534 |  | 8202214929#Penggantian thermodial & PG d | RU2-HCC | 211-C-2A/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-18 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233570 |  | 8202214921#Penggantian orbit valve 14-K- | RU6-DHC | 14-K-102A/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/NR-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202233135 |  | 8202214919#Perbaikan Kevakuman OS-11 | RU6-DHC | OS-11/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-24 | 2026-04-14 | 2102360778 | 8202234935 |  | 8202214917#Material Perbaikan E-202-08 | RU5-D&W | E-202-08/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C1H | 46720826 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-24 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363678 | 8202232421 |  | 8202214915#Conmon Coupling Rusak | RU2-HCC | 212-P-10B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-27 |  | 8202233192 |  | 8202214914#Perbaikan Control Valve 33-LV | RU6-HSC | 33-LV-015/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365512 | 8202239711 |  | 8202214910#24_Mixer 66M202 rusak | RU4-TRML | 66M202M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202234087 |  | 8202214908#15P120 Mech Seal rusak | RU6-RCC | 15-P-120A/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2025-12-09 | 2025-12-09 | 2102363777 | 8202232657 |  | 8202214884#Pengadaan Pressure Gauge Area | RU2-HOC | 110-C-1A/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/RT-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-09 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358439 | 8202234129 |  | 8202214878#Perbaikan Cabel Power BFW 4-P | RU7-UTL | 4-P-04B/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365527 | 8202239710 |  | 8202214854#24_Penggantian Control valve | RU4-LOC3 | 260FV053/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365924 | 8202239709 |  | 8202214853#24_Penggantian transmitter 26 | RU4-LOC3 | 260FT053/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 21345221 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-01-02 | 2102366102 | 8202239708 |  | 8202214847#24_perbaikan conductivity con | RU4-UTL | 054WS103/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 51262181 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-01-02 | 2026-01-02 | 2102366075 | 8202239707 |  | 8202214846#24_perbaikan conductivity pro | RU4-UTL | 054WS103/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 51262181 | 97177519 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2025-11-19 | 2025-11-19 | 2102361163 | 8202237099 |  | 8202214845#D_24 018LSH018 rusak | RU4-FOC2 | 018LSH018/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-19 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365873 | 8202239706 |  | 8202214842#24_Perbaikan sistem PSLL 155- | RU4-RFCUTL | 155PG-U155/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 5686122 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363610 | 8202232325 |  | 8202214830#Readiness Motor 140 P-9 | RU2-ITP | 140-PM-9A/00 | 50 | REL CSER NMAT PRC SETC | 2ER | D12/25/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102363648 | 8202232378 |  | 8202214829#211 EG 4D High Vibration | RU2-HCC | 212-EG-4D/00 | 50 | REL NMAT PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 |  | 8202234493 |  | 8202214820#RKA24_Matl Steam Trace RFCC | RU4-REL |  | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363637 | 8202232214 |  | 8202214818#Casing Pompa 701 P-2 Bocor | RU2-HCC | 701-P-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-11-30 | 2026-12-01 | 2102360779 | 8202234933 |  | 8202214813#Ganti bearing dan cek interna | RU5-UTL | DM-4-P103/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 4771333 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-07-09 | 2026-08-21 |  | 8202234930 |  | 8202214812#Perbaikan Band Screen A Coup | RU5-UTL | V-32-03A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 770000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-07-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 8202234927 |  | 8202214811#Perbaikan Blade Ea-201-01A | RU5-D&W | KEA-201-01A/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-13 | 2026-12-16 | 2026-12-16 | 2102360794 | 8202234931 |  | 8202214810#PENGGANTIAN BEARING PREPOST L | RU5-TBL | 101-PT-1C/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA4-ROT |  | YONZHETG |  | 2026-02-11 | PT02 |  | 3 | 2026-12-16 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-06-09 | 2026-07-15 |  | 8202234926 |  | 8202214809#Perbaikan Coupling Bar Screen | RU5-UTL | V-32-05A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 770000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202234924 |  | 8202214805#MAT.PERB.LINE 328-18" IDO Jl. | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 15309584 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-15 | 2026-06-15 | 2026-07-24 |  | 8202234920 |  | 8202214801#Perbaikan Level Transmi. LIC | RU5-UTL | 37-LCV-631A/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-06-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 | 2102360821 | 8202234922 |  | 8202214800#MAT.PERB.LINE INDUK DARI WTP1 | RU5-UTL | PIPA-WTP-PCR/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/24/B6/RT-C2H | 56008952 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-10-28 | 2026-03-12 |  | 8202233759 |  | 8202214795#Pengadaan Press Switch dan Pr | RU6-RCC | 15-R-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1152 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-10-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365325 | 8202239705 |  | 8202214785#24_Mtl. Cleaning 011E109C | RU4-FOC2 | 011E109C1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-2-C2H | 4461624 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365324 | 8202239704 |  | 8202214784#24_Mtl. Cleaning 011E109B | RU4-FOC2 | 011E109B1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365481 | 8202239703 |  | 8202214783#24_Mtl. Cleaning 011E109A | RU4-FOC2 | 011E109A1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-2-C2H | 24682409 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-09-22 | 2102366055 | 8202239702 |  | 8202214781#24_Mtl. Cleaning 011E108C | RU4-FOC2 | 011E108C1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 68145457 | 0 | MA2-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-19 | 2102365617 | 8202239701 |  | 8202214779#24_Mtl. Cleaning 011E107C | RU4-FOC2 | 011E107C/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-2-C2H | 18106398 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-11-17 | 2102365323 | 8202239700 |  | 8202214777#24_Mtl. Cleaning 011E103C | RU4-FOC2 | 011E103C1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-2-C2H | 5256000 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365689 | 8202239699 |  | 8202214758#24_Perbaikan 08LI002 | RU4-FOC1 | 16LT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/24/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-04 | 2026-02-13 | 2026-02-04 | 2026-02-04 | 2102361228 | 8202238037 |  | 8202214757#Rejuvenate Kabel Power Dan Ka | RU4-FOC2 | 001EE1211A/00 | 50 | CRTD CSER NMAT PRC | 4ER |  | 53328000 | 0 | MA2-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2025-11-28 | 2025-11-28 | 2102361158 | 8202237090 |  | 8202214756#D_24 LHCS FOC II modul proses | RU4-FOC2 | 014R104/00 | 60 | REL NMAT PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-28 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-10-22 | 2102365925 | 8202239698 |  | 8202214749#52B3-Penggantian Gasket Mud&S | RU4-UTL | 52B3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-5-C2H | 1038018 | 0 | MA5-STA |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 | 2102361082 | 8202236403 |  | 8202214744#penggantian valve 51G2 | RU4-UTL | 51G2/00 | 50 | CRTD CSER NMAT PRC | 4MR | D14/XX/B6/RT-C2NH | 0 | 0 | MA5-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233273 |  | 8202214721#Perbaikan 38-E-101 | RU6-POC | 38-E-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C3H | 2431732 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363660 | 8202232398 |  | 8202214720#Conmon High Vibrasi Gearbox 1 | RU2-HOC | 170-GG-58/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 5144962 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363548 | 8202232210 |  | 8202214701#Perbaikan Motor 930-PM-201 A | RU2-ITP | 930-PM-201A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-01 | 2026-02-01 |  | 8202233375 |  | 8202214685#Perbaikan 13-FV-030 | RU6-DHC | 13-FV-030/00 | 60 | REL NMAT PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-01 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-25 | 2026-03-25 | 2026-04-16 |  | 8202234917 |  | 8202214676#Perbaikan/kalibrasi TI Effect | RU5-UTL | 37A-TICSA-201/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 28721429 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365923 | 8202239697 |  | 8202214672#24_Pressure Gauge untuk gener | RU4-LOC3 | 240PIC024/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 25906913 | 0 | MA4-INT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365824 | 8202239696 |  | 8202214668#24_Perbaikan Sensor Conductiv | RU4-UTL | 054WS105/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-5-C2H | 40035300 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-01-02 | 2102366109 | 8202239695 |  | 8202214667#24_024LT002 |  | 024LT0020/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 95860000 | 0 | MA2-INT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202232866 |  | 8202214620#Perbaikan TDC Sensor Hydrocom | RU6-DHC | 12-K-501A/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202233401 |  | 8202214614#Perbaikan 12-FV-570 | RU6-DHC | 12-FV-570/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202233360 |  | 8202214613#Perbaikan 14-PSL-541 | RU6-DHC | 14-K-102A/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202232893 |  | 8202214611#perbaikan selenoid 22-KV-561 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202232890 |  | 8202214610#perbaikan selenoid 22-KV-578 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202232891 |  | 8202214609#perbaikan selenoid 22-KV-570 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202232892 |  | 8202214606#perbaikan selenoid 22-KV-566 | RU6-DHC | 22-A-105/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-24 | 2026-03-31 |  | 8202234081 |  | 8202214602#19-K-101 Speed indikator erro | RU6-RCC | 19-K-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1024 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353088 | 8202234510 |  | 8202214599#Perbaikan SRMGC 4 | RU3-CDGP | MCC-SRM-M-004/00 | 60 | REL CSER MACM PRC SETC | 3RR | D13/25/B6/NR-1-D2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202233671 |  | 8202214585#Penggantian Control Valve 052 | RU6-UTL | 052-PDV-922C/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 17193 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-06-14 | 2026-02-02 | 2026-02-02 |  | 8202234096 |  | 8202214580#14A-PTR1-01A LTSA trafo 2024 | RU6-RCC | 14A-PTR1-01A/00 | 60 | CLSD CSER NMAT PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-04-15 | PT02 |  | 3 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202233488 |  | 8202214578#Penggantian tachometer 52-B-1 | RU6-UTL | 52-B-101B-K1-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 |  | 2025-12-08 | 2025-12-08 |  | 8202233971 |  | 8202214556#LTSA PM PDM Peralatan Elect & | RU6-DHC | SS-13/00 | 50 | CRTD NMAT PRC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA2-LIS |  |  |  |  | PT02 |  | 2 | 2025-12-08 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363682 | 8202232427 |  | 8202214544#Conmon 520-P-601E | RU2-UTL | 520-P-601E/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/NR-D2H | 589000 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363687 | 8202232434 |  | 8202214543#Perbaikan 920-PT-2C | RU2-UTL | 920-PT-2C/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/24/B6/RT-D2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363595 | 8202232271 |  | 8202214541#Ganti Bearing Motor 140 PM-18 | RU2-HOC | 140-P-18/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/24/B6/RT-D2H | 169248 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233278 |  | 8202214534#Perbaikan 34-TI-050 | RU6-POC | 34-C-104/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-26 |  | 8202233472 |  | 8202214533#Penggantian transmitter 056- | RU6-UTL | 056-LV-501/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 17193 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202233840 |  | 8202214526#Penga.Sleeve Coupling Assy 51 | RU6-UTL | 51-G-101C-P2A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-08-14 | 2102360996 | 8202234781 |  | 8202214525#Pengadaan fuse control MCC ar | RU4-KPC | 82AT201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-12-02 |  | 8202234907 |  | 8202214520#Material Perbaikan Fender Jet | RU5-TBL | DER-JT-5-ABC/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 21318115 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-19 | 2026-07-17 |  | 8202234905 |  | 8202214517#Penggantian Control Valve 37- | RU5-UTL | 37A-LCV-211-5/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 100000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-25 | 2026-01-02 | 2026-01-02 | 2102358494 | 8202234128 |  | 8202214506#Perbaikan All area Kilang Feb | RU7-CRU | 3-K-01A/00 | 50 | REL CSER MACM PRC SETC | 7RT | D17/26/B6/RT-3-D1H | 0 | 0 | MA-STA |  | YAYANHER |  | 2026-02-24 | PT02 |  | 3 | 2026-01-02 | PM |  | 005
| K202 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102352347 | 8202234118 |  | 8202214505#Perpanjangan Boiler Sewa | RU2S-KIL | 900-08B3-FR-2/00 | 50 | REL GMPS NMAT PRC SETC | 2MS | D12/25/B6/RTZ-D2H | 1960200000 | 577170000 | MAS-ME1 |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202237471 |  | 8202214487#Material Pemasangan Air Compr | RU2S-KIL | 900-06AC-1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/24/B6/RTZ-D2H | 0 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-09-23 |  | 8202233624 |  | 8202214483#Penggantian isolator 51-ZY-21 | RU6-UTL | 51-G-101E/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 19833 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-09 |  | 8202233272 |  | 8202214481#Perbaikan 38-FT-903 B | RU6-POC | 38-K-101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-12-08 | 2026-07-31 |  | 8202233595 |  | 8202214480#Penggantian level switch tank | RU6-UTL | 052-B-101A-A1/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 1953 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-29 | 2102361223 | 8202237482 |  | 8202214479#Pasang MCC & power 47P507C | LOC1-UP4 | 47P507A/00 | 60 | REL NMAT PRC SETC | 4ER | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 |  | 2026-02-02 | 2026-07-27 |  | 8202233274 |  | 8202214475#Perbaikan 36-TI-009 B | RU6-POC | 36-C-101/00 | 50 | CRTD CSER MACM PRC | 6IR | D16/XX/B6/RT-C2NH | 0 | 0 | MA3-INT |  |  |  |  | PT02 |  | 2 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-27 |  | 8202233268 |  | 8202214474#Perbaikan 38-TI-043 | RU6-POC | 38-F-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-07-27 |  | 8202233282 |  | 8202214473#Perbaikan 34-FI-015/016/017 | RU6-POC | 34-C-102/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-09-23 |  | 8202233275 |  | 8202214472#Perbaikan 36-TI-007 | RU6-POC | 36-C-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-30 |  | 8202232809 |  | 8202214463#Permanen Repair Root Blower 3 | RU6-POC | 38-K-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-05-20 | 2026-06-08 |  | 8202234875 |  | 8202214462#Penggantian VCCB GM-37-205B S |  |  | 50 | REL CSER MSPT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360977 | 8202234557 |  | 8202214452#Pengadaan Motor BARU 48P1M | RU4-TRML | 48P1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202233836 |  | 8202214450#Pengadaan 4 set sleeve bearin | RU6-POC | 37-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102358495 | 8202238012 |  | 8202214446#COMMON ROTATING RU VII KASIM |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-06-29 |  | 8202233503 |  | 8202214435#Penggantian slide gate 56-CT- | RU6-UTL | 56-CT-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/NR-C2H | 11880 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202237954 |  | 8202214413#RESERTIFIKASI PERALATAN DAN A |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 289422805 | 0 | MA-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358496 | 8202237953 |  | 8202214412#Izin Tersus Lanjutan 2023 |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/NR-1-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 | 2102358499 | 8202237952 |  | 8202214399#Perbaikan Peralatan Unit CDU |  |  | 60 | REL CSER MACM PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 2481583 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-09-23 |  | 8202233831 |  | 8202214392#Pengadaan Battery Cell UPS 14 | RU6-RCC | 14X-UPS3-01A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-30 |  | 8202232839 |  | 8202214383#Perbaikan Turbin 15-P-118A-T | RU6-RCC | 15-P-118A-T/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352314 | 8202234117 |  | 8202214381#ESD 101-H2 | RU2S-KIL | 101-SOV-H2/00 | 50 | REL CSER MACM PRC SETC | 2ES | D12/25/B6/NRZ-D1H | 0 | 0 | MAS-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-08-10 |  | 8202233992 |  | 8202214380#Kerusakn Battery DC Charger 1 | RU6-DHC | 13A-PBA3-01/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 12975000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-08-10 |  | 8202233995 |  | 8202214379#Kerusakan Battery DC Charger | RU6-DHC | 13-PBA3-01/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 6315000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365696 | 8202239694 |  | 8202214374#23_Pengadaan gasket dan bolt | RU4-FOC2 | 011E107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 2135314 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202233893 |  | 8202214363#Notifikasi Perbaikan Coupling | RU6-ITP | 42-P-106B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-03-25 | 2102364220 | 8202233625 |  | 8202214350#Penggantian Internal Part 20- | RU6-RCC | 20-S-102C/00 | 60 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-01 |  | 8202233683 |  | 8202214346#Penggantian butterfly valve u | RU6-UTL | 53-P-102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-27 |  | 8202233776 |  | 8202214315#Pengadaan Modul Isolator Temp | RU6-POC | 39-K-101/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365945 | 8202239693 |  | 8202214313#23_Penggantian Power Supply 1 | RU4-GTO | 140PV032/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-12-C2H | 10000000 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365721 | 8202239692 |  | 8202214312#24_Penggantian Ampere Display | RU4-RFCUTL | 156K501B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-13-C2H | 19073206 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365381 | 8202239691 |  | 8202214309#23_39HV209B relay rusak | RU4-TRML | 39T210/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 12981352 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-01 | 2026-02-01 |  | 8202232192 |  | 8202214308#Technical Support Relay Prote | RU6-UTL | 01-PMC2-01A-00/00 | 60 | REL NMAT PRC SETC | 6ER | D16/24/B6/RT-C2H | 0 | 0 | MA4-LIS |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-01 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-01 |  | 8202234029 |  | 8202214301#DC Pengadaan Condensate Coole | RU6-UTL | 050-E-602/00 | 50 WAMA | REL NMAT PRC SETC | 6MR | D16/25/B6/RT-C2H | 31680 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-19 | 2025-12-29 |  | 8202234704 |  | 8202214298#Perbaikan Kabel Feeder 6,6kV |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 508000064 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-19 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2027-02-15 |  | 8202233850 |  | 8202214290#Pembelian baru motor 42-P-403 | RU6-ITP | 42-P-403D-M/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 8415000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-11 | 2025-12-08 | 2026-01-12 |  | 8202234004 |  | 8202214286#Kabel Feeder Baru LAB-PDB3-02 | RU6-LAB | LABORATORIUM/00 | 50 WAMA | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 731776211 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-04-02 | 2026-02-02 | 2026-05-07 |  | 8202232826 |  | 8202214283#Perbaikan Valve outlet 38-E-1 | RU6-POC | 38-E-110/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 6MR | D16/26/B6/RT-C3H | 55382000 | 74259000 | MA3-STA |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-02 |  | 8202234592 |  | 8202214238#Perb Loop Up Regulator CV Fee | RU5-UTL | B1-HIC-102/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 37200000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-17 | 2026-03-17 | 2026-04-17 |  | 8202234639 |  | 8202214237#Penggantian Temp Indicator TI |  |  | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 30721268 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-17 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-05 |  | 8202234579 |  | 8202214221#Penggantian Kabel Gland 201-T | RU5-D&W | 201-AIT-001/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 500230 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-10 |  | 8202233772 |  | 8202214203#Pengadaan Motor Assy 20-P-103 | RU6-RCC | 20-P-103A-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365514 | 8202239690 |  | 8202214199#23_Pengadaan drawer untuk MOV |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365513 | 8202239689 |  | 8202214197#23_Pengadaan panel MOV area 3 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-01 | 2026-03-04 | 2026-03-04 | 2026-07-27 |  | 8202233240 |  | 8202214187#Perbaikan Battery 17B-UPS3-01 | RU6-HSC | SS-17/00 | 50 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 24500000 | 24500000 | MA3-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K601 | 2026-02-01 | 2026-03-04 | 2026-03-04 | 2026-07-27 |  | 8202233241 |  | 8202214186#Perbaikan Battery 17A-UPS3-01 | RU6-HSC | SS-17/00 | 50 | REL CSER GMPS MANC PRC SETC | 6ER | D16/26/B6/RT-C2H | 24500000 | 24500000 | MA3-LIS |  | DANDARWANI |  | 2026-02-07 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-09 | 2026-04-07 | 2026-09-29 | 2102363974 | 8202239688 |  | 8202214175#23_Penggantian PSD 14P611 | RU4-FOC1 | 14P611LCS/00 | 60 | CLSD CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1219906 | 1219906 | MA1-INT |  | SAPBATCH | 2026-04-10 | 2026-03-10 | PT02 |  | 3 | 2026-04-10 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-27 |  | 8202234028 |  | 8202214163#DC Pengadaan Condensate Pump | RU6-RCC | 15-P-112A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-27 |  | 8202238036 |  | 8202214144#Perbaikan Oxygen Analyzer N2 | RU6-UTL | 059-A-101A-C1/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2027-01-20 |  | 8202238035 |  | 8202214101#Reverse engineering PLC N2 tr | RU6-UTL | 059-A-101A-K1/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361139 | 8202236882 |  | 8202214088#Penggantian Exiter 14K602B | RU4-FOC1 | 14K602BM-P2M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-02 |  | 8202234376 |  | 8202214085#Perb.Seal Actuator Inlet Damp |  |  | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 109200 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-17 | 2026-03-17 | 2026-04-17 |  | 8202234379 |  | 8202214084#Penggantian PI Disch. Pompa G | RU5-D&W | G-231-01A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 2030000 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-17 | PM |  | 045
| K501 | 2026-02-02 | 2026-03-25 | 2026-03-25 | 2026-04-24 |  | 8202234354 |  | 8202214083#Perbaikan Selenoid 202-XCV-00 | RU5-D&W | 202-FT-001/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/25/B6/RT-C2H | 69600000 | 0 | MA1-INT |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358615 | 8202234125 |  | 8202214081#Peng Coupling dan Mech Seal 4 | RU7-UTL | 4-PM-04A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365745 | 8202239687 |  | 8202214072#23_[CR] perbaikan 024P111A | RU4-LOC2 | 024P111A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 3802376 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358570 | 8202234124 |  | 8202214061#Pengadaan Flame Scanner 1-F-0 | RU7-CDU | 1-F-01/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365973 | 8202239686 |  | 8202214056#23_[PV] PM 32000h turbin expa | RU4-GTO | 180A601A5/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 0 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102366009 | 8202239685 |  | 8202214043#23_[CR] Turbine 051P103AT Bea | RU4-UTL | 051P103A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 5702507 | 0 | MA5-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-17 | 2026-01-02 | 2026-01-02 | 2102353108 | 8202234908 |  | 8202214036#Pemeliharaan Sepeda Kilang RU | RU3-WS | BEN-TOOL/00 | 60 | CLSD CNF GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | WS-SG |  | APUGUHA | 2026-05-07 | 2026-02-07 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-09-08 |  | 8202232751 |  | 8202214012#Refill Tabung FM-200 di SS-19 | RU6-ITP | 66-HCP-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C1H | 0 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361133 | 8202236812 |  | 8202213973#Penggantian heater 14E654 | RU4-FOC1 | 14E654/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/24/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361053 | 8202236052 |  | 8202213911#Kerusakan 91K-402BPM (List-MA | RU4-SRU | 91K402BPM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/25/B6/RTC-10-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202233965 |  | 8202213881#Major Repair Turbine 11-P-104 | RU6-HSC | 11-P-104A-T/00 | 60 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2026-02-04 |  | 8202238034 |  | 8202213847#Pengadaan Sewa Crane | RU6-RCC | 15-A-204-M2/00 | 50 | CLSD NCMP NMAT PRC | 6MR | D16/24/B6/RT-C2H | 415310000 | 0 | MA3-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-30 |  | 8202232974 |  | 8202213845#Perbaikan Pompa 24-P-103B | RU6-HSC | 24-P-103B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2025-12-08 | 2026-05-05 |  | 8202233661 |  | 8202213843#Penggantian Fan Panel 33-F-10 | RU6-HSC | 33-F-101/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 7643456 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-09-23 | 2102361181 | 8202237188 |  | 8202213831#D_23 [PV] Cooler mechseal 87 | RU4-KPC | 87V230P1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-04 |  | 2026-02-04 | 2026-07-01 |  | 8202238013 |  | 8202213827#Perbaikan bocoran line salamd | RU6-PLM | 2-LR-DO-103A/00 | 50 | CRTD NMAT PRC | 6MR | D16/24/B6/NR-C2H | 7786500 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2025-11-07 | 2026-09-10 |  | 8202233688 |  | 8202213820#Penggantian Belt Mixer 42-M-3 | ITP-UP6 | 42-M-301B/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 2547 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-09-23 |  | 8202233622 |  | 8202213817#Penggantian Kabel 17-PTR2-01B | RU6-HSC | 17-PTR2-01B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 90 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2025-12-08 | 2026-07-30 |  | 8202233623 |  | 8202213816#Penggantian Kabel 17-PTR2-01A | RU6-HSC | 17-PTR2-01A/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 3546 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-07-14 |  | 8202233621 |  | 8202213815#Penggantian Kabel 17-PTR2-02A | RU6-HSC | 17-PTR2-02A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 45 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-06-26 |  | 8202233190 |  | 8202213804#Perbaikan Control Valve No. 3 | RU6-DHC | 22-A-101/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-11-30 |  | 8202232830 |  | 8202213803#Perbaikan Turbine FDF Boiler | RU6-UTL | 052-B-101B-K-101/0 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 26268 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202237467 | 8202234928 | 8202213773#MAT.PIPESUPPORT PIPELINE SOMB | RU5-UTL | DAM-SEIWAIN/00 | 50 | REL MSPT PRC SETC | 5MR | D15/23/B6/RT-C2H | 5111303215 | 0 | MA4-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-02 |  | 8202237466 |  | 8202213771#Penggantian Pres Gauge PI G-2 | RU5-D&W | G-201-09A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 1920000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361114 | 8202236538 |  | 8202213768#Penggantian NGR Trafo 70EE111 | RU4-TRML | 70EE1111B/00 | 50 WAMA | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA3-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360533 | 8202235732 |  | 8202213767#Perbaikan NGR 30EE1211 A/B | RU4-TRML | 30EE1211A/00 | 50 WAMA | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA3-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360534 | 8202235734 |  | 8202213766#Perbaikan NGR 30EE1111 A/B | RU4-TRML | 30EE1111A/00 | 50 WAMA | CRTD CSER MACM PRC | 4ER |  | 0 | 0 | MA3-LIS |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-14 | 2025-12-08 | 2025-12-24 |  | 8202233580 |  | 8202213758#Penggantian modul Heater N2 t | RU6-UTL | 059-A-101A-D1/00 | 50 WAMA | REL MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 11555815 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-08 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 |  | 8202233753 |  | 8202213751#Pengadaan Round Bar Sbg Fabr | RU6-RCC | 18-P-104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-02-03 | 2026-02-05 | 2102364219 | 8202237465 |  | 8202213749#Perbaikan EM-17-04B | RU5-E15112 | EM-17-04B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 513764 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-19 | 2026-04-17 |  | 8202237464 |  | 8202213746#Perbaikan positioner LCV 631A | RU5-UTL | 37-LCV-401B/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-19 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202232761 |  | 8202213744#Pngdaan Mat Permanent Repair | RU6-UTL | 056-K-101-A1/00 | 50 WAMA | REL NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202235065 |  | 8202213725#RT_Perbaikan Lampu Penerangan |  |  | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/23/B6/RT-4-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202232979 |  | 8202213723#Perbaikan Pompa 19-P-111B | RU6-RCC | 19-P-111B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 |  | 8202233958 |  | 8202213718#Mat LTSA Per Turbine 52-P-103 | RU6-UTL | 52-P-103B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-05-23 | 2026-02-03 | 2026-02-03 | 2102358611 | 8202237945 |  | 8202213715#LTSA PEKERJAAN INSPEKSI PER. |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/NR-1-D2H | 1 | 0 | MA-ROT |  | MALFANF |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-01-02 | 2102366098 | 8202239684 |  | 8202213689#23_Perbaikan 154_LT601C | RU4-RFCUTL |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 76200000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-30 | 2102366099 | 8202239683 |  | 8202213642#24_Perbaikan 166LT003 (Instr | RU4-RFCUTL | 166T501/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 86905350 | 0 | MA7-INT |  | YOHANESMVIS |  | 2026-03-10 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-03-25 |  | 8202237463 |  | 8202213631#Perbaikan Motor EM-17-04B | RU5-E15112 | EM-17-04B/00 | 60 | CLSD CSER MACM PRC SETC | 5ER | D15/23/B6/NR-C2H | 513764 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-03-25 |  | 8202237462 |  | 8202213630#Perbaikan Motor EM-8-10H | RU5-E15112 | EM-8-10H/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/NR-C2H | 1122247 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-09 |  | 8202232907 |  | 8202213612#Perbaikan Probe Housing Vibra | RU6-DHC | 13-P-101/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-07 | 2026-04-13 |  | 8202233451 |  | 8202213585#Penggantian valve 056-CWS-500 | RU6-PLM | UTL-PIPE/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 1280 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202233011 |  | 8202213584#Perbaikan Permanen Turbine 51 | RU6-UTL | 51-P-101A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2025-11-07 | 2026-04-13 |  | 8202233445 |  | 8202213570#Penggantian valve acid demin | RU6-UTL | 055-A-101-V3/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/24/B6/NR-C2H | 1280 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102353259 | 8202234700 |  | 8202213556#Penyediaan Junction Box IHLA |  |  | 50 WAMA | REL CSER MACM PRC SETC | 3MR |  | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2025-11-24 | 2025-12-05 |  | 8202233400 |  | 8202213545#perbaikan 12-FV-799 | RU6-DHC | 12-FV-799/00 | 60 | REL CSER MACM PRC SETC | 6IR | D16/24/B6/RT-C2H | 128 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-24 | PM |  | 004
| K201 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102363754 | 8202232575 |  | 8202213537#Penggantian Control 140 LV-42 | RU2-HOC | 140-LV-425/00 | 50 | REL NMAT PRC SETC | 2IR | D12/25/B6/NR-D2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2025-11-17 | 2025-12-30 |  | 8202237460 |  | 8202213534#Perbaikan Motor GM-2-14B | RU5-E15112 | GM-2-14B/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 245612 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2025-11-17 | 2025-12-30 |  | 8202237461 |  | 8202213533#Perbaikan Motor EM-31-21J | RU5-E15112 | EM-31-21J/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 8308061 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102358619 | 8202237942 |  | 8202213518#2023-2026_LTSA DCS Yokogawa C |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D2H | 613000000 | 0 | MA-STA |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202232724 | 8202232983 | 8202213517#SWO Perbaikan Pompa 16-P-101A | RU6-RCC | 16-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202232983 |  | 8202213515#Perbaikan Pompa 16-P-101A | RU6-RCC | 16-P-101A/00 | 50 WAMA | REL CSER NMAT PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238085 |  | 8202213496#Jasa perbaikan 38-K-101 A | RU6-POC | 38-K-101A/00 | 60 | REL NMAT PRC SETC | 6RR | D16/24/B6/RT-C2H | 0 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-19 | 2025-12-29 |  | 8202237459 |  | 8202213492#Perbaikan VCB GM-20-09 A di S |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 637419289 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-19 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2025-12-12 | 2025-12-16 | 2102364259 | 8202237458 |  | 8202213470#Perbaikan GM-4-03 A | RU5-E15111 | GM-4-03A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 453091 | 0 | MA2-LIS |  | SAPBATCH | 2026-06-03 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102353271 | 8202235189 |  | 8202213411#Kontrak Volume Pekerjaan List |  |  | 60 | REL NMAT PRC SETC | 3ER | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-08-26 | 2102364370 | 8202237457 |  | 8202213393#Penggantian Transmitter 02-FA | RU5-E15112 | 02-FT-025A/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/23/B6/RT-C2H | 11979990 | 0 | MA3-INT |  | HASRUDDINA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2025-12-05 | 2026-09-11 |  | 8202232863 |  | 8202213377#Perbaikan temporary turbine 5 | RU6-UTL | 51-P-101A-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 2304 | 0 | WS-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102366001 | 8202239682 |  | 8202213344#23_PeNGGANTIAN FT-544 | RU4-FOC1 | 14FT544/00 | 60 | REL MACM PRC SETC | 4IR | D14/25/B6/RTC-1-C2H | 18500000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2025-12-30 | 2025-12-30 | 2102364258 | 8202237456 |  | 8202213325#Perbaikan Gm-3-39B Bearing | RU5-E15112 | GM-3-39B/00 | 60 | CLSD CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 459864 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-05-20 | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-03-25 |  | 8202237455 |  | 8202213311#Perbaikan Em-3-20D Spare Moto | RU5-E15112 | EA-3-20D/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 1366640 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-03-25 |  | 8202237454 |  | 8202213309#perbaikan motor finfan Em-8-1 | RU5-E15112 | EM-8-15D/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 727491 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 |  | 8202233930 |  | 8202213283#Material Overdue Spherical Ta | RU6-ITP | 42-T-404H/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-11 |  | 8202237453 |  | 8202213281#GM-3-10A Indicator Ampere Rus | RU5-E15112 | GM-3-10A/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 10908579 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-05 |  | 8202237452 |  | 8202213280#Perbaikan GM-31-39C | RU5-E15112 | GM-31-39C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 8549764 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102364365 | 8202237451 |  | 8202213275#Penggantian Press Gauge Area |  |  | 60 | REL CSER MACM PRC SETC | 5IR | D15/23/B6/RT-C2H | 30394408 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-05-08 |  | 8202237450 |  | 8202213268#Perbaikan EM-31-21D | RU5-E15112 | EM-31-21D/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 1417450 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237446 |  | 8202213265#Material Perbaikan line G-1-3 | RU5-E15111 | G-1-32B/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-01NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237443 |  | 8202213264#Penggantian check valve GM-34 | RU5-D&W | G-34-50/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-EWNH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237441 |  | 8202213263#Perbaikan Line Sampling E-1-0 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-01NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237445 |  | 8202213262#Pebaikan line Pompa OC DHP, O |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-EWNH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237449 |  | 8202213259#Mat. Perbaikan strainer E-5-1 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-05NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237447 |  | 8202213257#Mat.Perbaikan line scw G-1-03 | RU5-E15111 | G-1-03B/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-01NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-13 |  | 8202237442 |  | 8202213245#Perbaikan Air Dryer Boiler 5 | RU5-UTL | HHP-5/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-S3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 |  | 8202237365 |  | 8202213241#Penggantian Positioner Koso 2 | RU5-D&W | 201-FCV-023/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 51000000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237298 |  | 8202213239#Perbaikan dinding hidrolik 32 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SCNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237361 |  | 8202213232#Penggantian Strainer SWD 1 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SWNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237266 |  | 8202213231#Perbaikan Line 4 inch condens |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SWNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237343 |  | 8202213229#Perb. Line discharge degaser |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-23 | 2026-12-14 |  | 8202237322 |  | 8202213228#Perbaikan bocoran inlet polis |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-PDNH | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  |  | PT02 |  | 2 | 2026-11-23 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2102364254 | 8202237438 |  | 8202213221#GT-3-46B: Turbin,shaft,govern | RU5-E15112 | GT-3-46B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 334933675 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-11-25 | 2025-12-22 |  | 8202237354 |  | 8202213219#Penggantian Valve Pompa G-37- |  |  | 01 | CRTD NMAT PRC | 5MR | D15/09/B6/RT1-SWNH | 256 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2025-11-25 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-28 |  | 8202237380 |  | 8202213218#Material Sal. outfall straine |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-P1NH | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  |  | PT02 |  | 2 | 2026-12-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-11-03 | 2026-11-24 |  | 8202237286 |  | 8202213216#Perbaikan elbow inlet cation |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-PDNH | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  |  | PT02 |  | 2 | 2026-11-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2025-12-29 | 2025-12-29 | 2102364193 | 8202237436 |  | 8202213211#kalibrasi Governor KT-35-02B | RU5-E15112 | KT-35-02B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 5039478 | 0 | MA3-ROT |  | DANANGIBNUM | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-13 |  | 8202237227 |  | 8202213201#Perbaikan Overhead Crane Demi |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-PDNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237219 |  | 8202213199#Perbaikan Pendingin pompa GM- |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SCNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 |  | 8202237215 |  | 8202213190#Perbaikan Saluran Discharge P |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237251 |  | 8202213189#Perbaikan line di discharge 3 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SWNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237325 |  | 8202213188#Perb.line Discharge&suction T | RU5-TBL | OFC03401/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-FJNH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237216 |  | 8202213182#Perbaikan Sal.suction & disch | RU5-UTL | BFW-P-9/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-S3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-28 |  | 8202237276 |  | 8202213179#Perbaikan Inlet steam gland S |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-P2NH | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  |  | PT02 |  | 2 | 2026-12-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-01-02 | 2027-01-20 |  | 8202237214 |  | 8202213176#Perbaikan Saluran Pendingin G | RU5-UTL | G-32-05C/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/25/B6/NR-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-04 |  | 8202237213 |  | 8202213166#PM Band Screen B (tag no. V-3 | RU5-UTL | V-32-03B/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237437 |  | 8202213164#Jasa Reroute Line Distribusi | RU5-UTL | OFC03203/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-W2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 001
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-04 |  | 8202237440 |  | 8202213163#Ganti karet kopling Bar Scree | RU5-UTL | V-32-05C/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237377 |  | 8202213161#Pebaikan Valve Discharge P7 |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-SRNH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-01-21 | 2026-03-26 | 2102364184 | 8202237439 |  | 8202213160#Ganti Valve Three way oil coo |  |  | 50 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 20930348 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-21 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237235 |  | 8202213159#Perbaikan Line NCG 4" area HV |  |  | 01 | CRTD NMAT PRC | 5MR | D15/09/B6/RT1-DVNH | 620 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-04 |  | 8202237324 |  | 8202213157#Perbaikan Bar screen A CWI (U | RU5-UTL | V-32-05A/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-21 |  | 8202237173 |  | 8202213153#Perb. Band Screen A (UR) | RU5-UTL | V-32-03A/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  |  | PT02 |  | 2 | 2026-12-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202237212 |  | 8202213151#Balancing Rotor Blower No. 2 | RU5-UTL | OUA-11-D003/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/10/B6/RT1-PDNH | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2027-02-17 |  | 8202237210 |  | 8202213144#Lantai Bangunan Power Plant |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2027-03-25 | 2027-03-30 |  | 8202237175 |  | 8202213141#Penggantian pompa G-3-35C | RU5-E15112 | G-3-35C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 538258000 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2027-03-25 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-15 |  | 8202237172 |  | 8202213138#Perb. Cyl. 4 Kompresor K-3-02 | RU5-E15112 | K-3-02A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 15176527 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2028-02-02 |  | 8202237170 |  | 8202213136#Perb. Pompa G-34-68 (UR) | RU5-D&W | G-34-68/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-05 |  | 8202237171 |  | 8202213134#Perb. Pompa G-34-112A (UR-Mec | RU5-D&W | G-34-112A/00 | 50 | CRTD CSER NMAT PRC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202237202 |  | 8202213133#Pengantian bering pompa OC 10 | RU5-TBL | 101-5-P-8A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3072978 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-05 | 2026-11-30 | 2026-12-01 |  | 8202237211 |  | 8202213127#Ganti Bearing Split Shell BFW | RU5-UTL | 3RL-20-D001/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 8202237203 |  | 8202213123#Pengadaan insulasi turbin G-2 | RU5-D&W | GS-202-05B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-02-03 | 2026-02-05 |  | 8202237154 |  | 8202213118#Perbaikan HM-41-10A | RU5-E15112 | 41-AC-RR-RPPK/00 | 60 | CLSD PCNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 174600 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-05 |  | 8202237152 |  | 8202213117#Perbaikan HM-41-10B | RU5-E15112 | 41-AC-CENTRPPK/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 174600 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-04-02 |  | 8202237132 |  | 8202213108#Perb.Akses.Control Valve 08-F | RU5-E15112 | E-8-08A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/23/B6/RT-C2H | 6602387 | 0 | MA3-INT |  | HASRUDDINA | 2026-05-26 | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102364256 | 8202237134 |  | 8202213107#Pengadaan Unit UPS untuk CEMS | RU5-E15500 | CEMS-SYSTEM-INT/00 | 50 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 53000000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202237149 |  | 8202213098#MAT. Perbaikan Pipa Hydrant d |  |  | 50 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 93742404 | 0 | MA2-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102364232 | 8202237130 |  | 8202213089#Perbaikan switch on off mixer |  |  | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 10908579 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-04-20 |  | 8202237136 |  | 8202213082#Pembuatan sal. bypass peredam | RU5-UTL | HHP-2/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/10/B6/RT1-S3NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365909 | 8202239681 |  | 8202213071#23_Penggantian Tubing Air Ins | RU4-TRML | 33P1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-4-C2H | 23500000 | 0 | MA3-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 |  | 8202237110 |  | 8202213055#MAT.Perbaikan pp outlet Tk D- | RU5-D&W | D-34-28/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 13776777 | 0 | MA2-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202232955 |  | 8202213053#Perbaikan Pompa 42-P-501C | RU6-ITP | 42-P-501C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-04 | 2026-04-15 | 2026-02-04 | 2027-01-27 |  | 8202238084 |  | 8202213051#Jumper Line TPA ke Line Inlet | RU6-HSC | 11-P-104A/00 | 60 | CLSD NCMP NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 288585000 | 0 | MA1-STA |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-13 |  | 8202237097 |  | 8202213046#Perbaikan Motor EM-3-20G | RU5-E15112 | EA-3-20G/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 5256569 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2025-12-04 | 2026-02-03 |  | 8202237070 |  | 8202213016#Perb Level Switch C-2-10,C-3- | RU5-E15112 | C-2-10/00 | 60 | TECO CNF NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 768 | 0 | MA3-INT |  | HASRUDDINA | 2026-05-18 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-07 |  | 8202237068 |  | 8202213012#Perbaikan Genset RPPK BPP II | RU5-UTL | 74201-L1/00 | 50 | REL CSER MSPT PRC SETC | 5ER | D15/23/B6/RT-C2H | 150250000 | 0 | MA3-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 |  | 8202237067 |  | 8202213011#Perbaikan Level Switch Steam | RU5-UTL | HHP-6-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 300000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202237066 |  | 8202212990#MAT.KT-35-02B pipa 3/4 dan 1/ | RU5-E15112 | KT-35-02B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 10432650 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2025-12-29 | 2025-12-31 |  | 8202237065 |  | 8202212984#penarikan power ups ke SS 63 | RU5-E15112 | UPS-41-01A/00 | 60 | TECO CNF MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 1654710030 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102353334 | 8202234507 |  | 8202212969#Perbaikan Swivel Joint L. Arm | RU3-ITP | ITP-JETTY-004/00 | 60 | REL NMAT PRC SETC | 3PM | D13/25/B6/NR-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 |  | 8202237048 |  | 8202212964#2erbaikan mechseal pompa P13 | RU5-TBL | P-13RP-A-HITAM/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 11400369 | 0 | MA4-ROT |  | SAPBATCH | 2026-05-06 | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-29 | 2026-06-30 | 2026-06-30 | 2102364251 | 8202237045 |  | 8202212962#Perg. Coupling G34-86A penang | RU5-D&W | G-34-86A/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | JANDIKUR |  | 2026-02-11 | PT02 |  | 3 | 2026-06-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-03-25 | 2026-03-25 | 2102364255 | 8202237047 |  | 8202212959#Pengadaan material repair kit | RU5-TBL | 101-PT-1C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 0 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-03-25 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202237035 |  | 8202212915#material filter GENSET-RPPK | RU5-E15112 | GENSET-RPPK/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 1896450 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-08 |  | 2026-01-02 | 2026-12-28 |  | 8202238765 | 8202237182 | 8202212912#23_Kontrak Penyehatan 20 Finf | RU4-FOC2 | 011E110K01/00 | 50 | CRTD NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 7990000 | 0 | MA2-ROT |  |  |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-05-06 | 2026-06-11 |  | 8202237006 |  | 8202212873#Material Perb. Skid & Support | RU5-UTL | DM-4-P111/00 | 60 | CLSD CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-28 | 2102365685 | 8202239680 |  | 8202212871#23_[CR] perbaikan coupling 00 | RU4-LOC2 | 002P101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-8-C2H | 650000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-12-01 |  | 8202233133 |  | 8202212861#Perbaikan Kompresor 58-K-101C | RU6-UTL | 58-K-101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 26400 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-07-21 | 2026-09-04 |  | 8202232150 |  | 8202212851#12-P-601A | RU6-DHC | 12-P-601A/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/24/B6/RT-C2H | 159001 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-07-21 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-05-04 | 2026-06-08 |  | 8202237005 |  | 8202212849#Material Perb. Bocoran Line N |  |  | 60 | CLSD CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-04-02 | 2102364196 | 8202237000 |  | 8202212844#Penggantian Temp Indicator TI | RU5-E15112 | K-3-02A-INST/00 | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/23/B6/RT-C2H | 2180000 | 0 | MA3-INT |  | SAPBATCH | 2026-05-26 | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-07-24 |  | 8202237001 |  | 8202212842#Penggantian PI Discharge G-3- | RU5-E15112 | G-3-01A-INST/00 | 60 | REL CSER MSPT PRC SETC | 5IR | D15/23/B6/RT-C2H | 5026000 | 0 | MA3-INT |  | HASRUDDINA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202236999 |  | 8202212823#PENGGANTIAN.Filter packinox E | RU5-E15111 | E-5-01/00 | 50 | REL CSER MSPT PRC SETC | 5MR | D15/23/B6/RT-C2H | 47120000 | 0 | MA2-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202236986 |  | 8202212809#MAT.FABRIKASI.LINE.C-8-09B |  |  | 50 | REL CSER MSPT PRC SETC | 5MR | D15/23/B6/RT-C2H | 200618479 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361185 | 8202237197 |  | 8202212805#D_23 [CR] 054WS105P3 : Ganti | RU4-UTL | 054WS105P3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 |  | 8202236997 |  | 8202212790#MAT.003 PSV 1101C: PSV Rusak | RU5-HSC |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 26534000 | 0 | MA2-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-05 |  | 8202236970 |  | 8202212783#Perbaikan pompa G-3-15D | RU5-E15112 | G-3-15D/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 10519735 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-10-30 | 2025-12-29 | 2102364252 | 8202236968 |  | 8202212778#Reroute Kabel Power Mixer Tan | RU5-TBL | PLANT-20-LIS/00 | 60 | REL NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 768 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-10-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 |  | 8202236964 |  | 8202212772#Perbaikan pipa steam ke Dryin | RU5-D&W | GHDC/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202236966 |  | 8202212769#Penggantian HP Gland STG 2.2 | RU5-UTL | TG-2-PP2/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 233945000 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-05-08 | 2102364198 | 8202236955 |  | 8202212745#Perbaikan T-Dus Lampu Catwalk | RU5-TBL | PLANT-22-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 141750000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-12-07 |  | 8202234068 |  | 8202212740#24-M-301 Pengadaan Multi Top | RU6-HSC | 24-M-301/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C1H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236962 |  | 8202212733#Ganti Material Filter I2 WTP |  |  | 60 | REL MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 55200000 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202236956 |  | 8202212713#Penggantian Carbon Ring GT-3- | RU5-E15112 | GT-3-17A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 1820000 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361175 | 8202237179 |  | 8202212707#D_23[CR] Peng Mech seal 011P1 | RU4-FOC2 | 011P107A/01 | 60 | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202236938 |  | 8202212649#Perbaikan Pompa G-2-08A | RU5-E15112 | G-2-08A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 48934269 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 |  | 8202236928 |  | 8202212632#Gasket Cover Valve Suction St | RU5-E15111 | K-1-01A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2027-02-01 |  | 8202236910 |  | 8202212594#Perbaikan kabel Panel Bently | RU5-E15111 | K-5-02B-INST/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/23/B6/RT-C2H | 25391258 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 |  | 8202233440 |  | 8202212582#Penggantian valve drain 42-T- | RU6-ITP | 42-T-301B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 739435 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2025-12-05 | 2026-09-11 |  | 8202233781 |  | 8202212572#Pengadaan Material Strainer P | RU6-ITP | 42-P-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/NR-C2H | 2304 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-12-05 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-12-01 |  | 8202232815 |  | 8202212571#Perbaikkan atau penggantian l | RU6-POC | 39-K-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 266808 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202236905 |  | 8202212565#Perbaikan Bearing Pompa no. | RU5-UTL | P-16-WTP/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 6144315 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-08 |  | 8202236903 |  | 8202212562#Perbaikan Degaser pump no. 3 | RU5-UTL | 3UA-03-D002/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 9335100 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-05-13 | 2026-06-19 |  | 8202236900 |  | 8202212541#Material MOC Bypass E-201-22B | RU5-D&W | E-201-22B/00 | 60 | CLSD CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-12-15 | 2102361183 | 8202237191 |  | 8202212533#D_23 [CR] MS 101P523B leak | RU4-RFCC | 101P523B/00 | 60 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/NR-12-C2H | 0 | 0 | MA6-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-13 |  | 8202236898 |  | 8202212532#Material Resertifikasi HHP Bo | RU5-UTL | HHP-4/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-08 |  | 8202236894 |  | 8202212527#Pengadaan insulasi turbin G-2 | RU5-D&W | G-201-01B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 2199663000 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-07 |  | 8202236890 |  | 8202212526#Perbaikan IDF K-202-02 | RU5-D&W | K-202-02/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/23/B6/RT-C2H | 8729140 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-11-30 |  | 8202233086 |  | 8202212505#Perbaikan Membrane Coupling 1 | RU6-HSC | 11-P-104A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-08-10 | 2102364192 | 8202236866 |  | 8202212494#Mat. Perbaikan pipa ACW di G- | RU5-D&W | GS-202-08B/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 8273676 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 | 2102364253 | 8202236863 |  | 8202212486#Perb Temp Indikator 313-TI-80 | RU5-UTL | HHP-3-INST/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-02-03 | 2026-06-29 |  | 8202236789 |  | 8202212452#Perbaikan Motor EM-3-20D | RU5-E15112 | EM-17-04B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 683320 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 |  | 8202236784 |  | 8202212426#Perbaikan Motor GM-220-03B ST | RU5-TBL | GM-220-03B/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 592690 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 |  | 8202236786 |  | 8202212425#Perbaikan Motor GM-220-03A ST | RU5-TBL | GM-220-03A/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 592690 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-12 | 2026-01-02 | 2026-01-02 | 2102361186 | 8202237198 |  | 8202212405#D_23 [CR] 054WS102P3 : High V | RU4-UTL | 054WS102P3/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 0 | 0 | MA5-ROT |  | TONNYADI | 2026-06-02 | 2026-02-07 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K601 | 2026-02-02 | 2026-04-15 | 2026-02-02 | 2026-02-02 |  | 8202233972 |  | 8202212400#LTSA Pengukuran Grounding All | RU6-RCC | GROUNDSYS-SS14A/00 | 50 | CLSD CSER NCMP NMAT PRC | 6ER |  | 0 | 0 | MA1-LIS |  | DANDARWANI |  |  | PT02 |  | 2 | 2026-04-15 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202236737 |  | 8202212387#Penyehatan Waduk dan Equipmen |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-W1NH | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202236693 |  | 8202212369#Preventive Mtc trip system KT | RU5-E15112 | KT-3-02B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 51249000 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 |  | 8202236687 |  | 8202212349#Perb ICPS iCAP 7400 Duo Analy | RU5-LAB | ICPS-ALZ-LAB/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 0 | 0 | LAB |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-01-02 | 2026-09-17 | 2102366052 | 8202239679 |  | 8202212346#23_Penggantian modul kontrol | RU4-KPC | PI-U84/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 55500000 | 0 | MA4-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-12-01 |  | 8202233474 |  | 8202212303#Penggantian Toothbelt 11-E-13 | RU6-HSC | 11-E-131D/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202235410 | 8202234540 | 8202212302#NRKAP 2020_Pemeliharaan Pipin | RU4-FOC2 | 014C101/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202236658 |  | 8202212294#Perbaikan Link Trip Valve GT- | RU5-E15111 | GT-5-21A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 131000000 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-03-06 | 2026-04-06 |  | 8202236565 |  | 8202212276#Perbaikan TI-806 HHP Boiler 3 | RU5-UTL | HHP-3-INST/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5IR | D15/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH | 2026-03-06 | 2026-02-11 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-05-19 | 2026-05-21 | 2102364250 | 8202236560 |  | 8202212175#Pengadaan insulasi turbin GS- | RU5-D&W | GS-201-08B/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/25/B6/RT-C2H | 366610500 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-23 | 2102364359 | 8202236516 |  | 8202212172#Perbaikan Temperature gauge T | RU5-UTL | U-10/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/23/B6/RT-C2H | 7477334 | 0 | MA1-INT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-26 | 2026-05-26 | 2026-06-26 | 2102364360 | 8202236556 |  | 8202212165#3B-FC-313A Transmitter Rusak | RU5-E15112 | 03B-LT-308/00 | 60 | REL CSER MSPT NTUP PRC SETC | 5IR | D15/23/B6/RT-C2H | 11979990 | 0 | MA3-INT |  | HASRUDDINA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 | 2102364356 | 8202236475 |  | 8202212144#Perbaikan motor Fan P20 RPA h | RU5-TBL | P-20RP-A-HITAM/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 955967 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-05 |  | 8202236478 |  | 8202212109#Material Piping Pompa P-2B (C | RU5-D&W | P-2B-CPI/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 |  | 8202237159 |  | 8202212091#D_23Perbaikan pompa inline sa |  |  | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361169 | 8202237181 |  | 8202212081#D_23 Perbaikan Pompa Chemical | RU4-UTL | 54WS201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-4-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-04 |  | 8202236375 |  | 8202211990#Ganti L O Filter K-35-02C | RU5-E15112 | K-35-02C/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 5570274 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202236374 |  | 8202211988#Ganti V-Belt EA-3-02K | RU5-E15112 | EA-3-02K/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 2207935 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2102364357 | 8202236365 |  | 8202211981#Penggantian rubber coupling P | RU5-UTL | P-14PAMPANCUR/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 7020000 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202236336 |  | 8202211976#Perbaikan Motor GM-3-19C | RU5-E15112 | GM-3-19C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 791453 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-19 | 2026-02-11 | PT02 |  | 3 | 2026-05-19 | PM |  | 005
| K501 | 2026-02-02 | 2026-06-02 | 2026-08-13 | 2026-08-13 | 2102364358 | 8202236364 |  | 8202211974#penggantian V-belt EA-1-23A | RU5-E15111 | EA-1-23A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3259628 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-11 | PT02 |  | 3 | 2026-08-13 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-10-02 | 2102361182 | 8202237190 |  | 8202211959#D_23 [CR] Penggantian Mech Se | RU4-TRML | 33P1C/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361174 | 8202237178 |  | 8202211943#D_23[PV] Fabrikasi Shaft dan | RU4-LOC1 | 24P2B/00 | 60 | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 | 2102361171 | 8202237162 |  | 8202211942#D_23Penggantian Cooler Mech S | RU4-FOC1 | 11P4A/00 | 50 WAMA | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202236315 |  | 8202211894#Perbaikan Fin-Fan EA-32-01P | RU5-E15112 | EA-32-01P/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 978024452 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202236313 |  | 8202211893#Perbaikan Pompa G-25-01B | RU5-E15112 | G-25-01B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 2143722 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K201 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-02-02 | 2102363634 | 8202232350 |  | 8202211854#Pompa rusak | RU2-HCC | 410-P-6/00 | 50 | REL GMPS MACM PRC SETC | 2RR | D12/25/B6/NR-D2H | 0 | 445000000 | MA2-ROT |  | T_YUDIPRAS |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202236311 |  | 8202211845#EA-3-16C V Belt | RU5-E15112 | EA-3-16C/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 1226184 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202236274 |  | 8202211812#Perbaikan pompa G-202-04A | RU5-D&W | G-202-04A/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/24/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 |  | 8202236290 |  | 8202211809#Filter L/O K-19-01A kotor | RU5-E15112 | K-19-01A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 31495824 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 |  | 2025-12-23 | 2025-12-29 |  | 8202236273 |  | 8202211797#Perbaikan pompa G-3-24D | RU5-E15112 | G-3-24D/00 | 01 | CRTD CSER MACM PRC | 5RR | D15/25/B6/RT-C2H | 115 | 0 | MA3-ROT |  |  |  |  | PT02 |  | 2 | 2025-12-23 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-05 | 2026-02-03 | 2026-12-16 | 2102361176 | 8202237182 |  | 8202211763#D_23 Penyehatan fin-fan aspek | RU4-FOC2 | 011E110K01/00 | 60 WAMA | REL CSER GMCO GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 6671185367 | 3197148038 | MA2-ROT |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202236271 |  | 8202211750#K-3-01A Hub Coupling, Bolt, N | RU5-E15112 | K-3-01A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 61272000 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-03-04 | 2026-03-04 | 2026-04-23 |  | 8202236239 |  | 8202211743#Perbaikan Rotor Spare STG 2.1 |  |  | 50 | REL CSER MANC PRC SETC | 5ER | D15/25/B6/RT-C2H | 17039794 | 0 | MA1-LIS |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-03-04 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202236232 |  | 8202211711# Material Perbaikan pompa G-2 | RU5-D&W | G-201-11A/00 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 20600000 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-23 | 2026-02-23 | 2026-04-29 | 2102361172 | 8202237176 |  | 8202211652#D_23[PV] penggantian coupling | RU4-LOC2 | 024P103B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/23/B6/RT-7-C2H | 24386750 | 24386750 | MA2-ROT |  | WAHYUCATUR |  | 2026-02-07 | PT02 |  | 3 | 2026-02-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-02-03 | 2026-02-11 |  | 8202236192 |  | 8202211629#Perbaikan Motor GM-17-03A | RU5-HSC |  | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102361216 | 8202237481 |  | 8202211618#Perbaikan Turbine 52P2B | RU4-UTL | 52P2B-T/00 | 50 WASR | REL CSER NMAT PRC SETC | 4RR | D14/24/B6/RT-5-C2H | 410000000 | 0 | MA5-ROT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202236144 |  | 8202211600#Ganti Auxiliary Oil Pump K-23 | RU5-D&W | G-235-02B/00 | 01 | CRTD CSER NMAT PRC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA1-ROT |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236141 |  | 8202211598#MAT. GANTI PICK UP ROPE 10" C | RU5-TBL | PIPE-ON-SHORE/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/22/B6/RT-C2H | 81669891 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-05 | 2026-02-03 | 2026-08-14 | 2102361194 | 8202237189 |  | 8202211496#D_23 [CR] Penggantian Pompa 1 | RU4-GTO | 100P602A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA7-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-05 |  | 8202236137 |  | 8202211477#Material Perbaikan pompa G-3- | RU5-E15112 | G-3-13A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 18272515 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-17 | 2025-12-29 |  | 8202236107 |  | 8202211470#Perbaikan Kabel Feeder 380V J |  |  | 60 | REL MACM PRC SETC | 5ER | D15/25/B6/RT-C2H | 145825090 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-17 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-05 |  | 8202236111 |  | 8202211463#Ganti Material filter G-3-01B | RU5-E15112 | G-3-01B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 29493065 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-05 |  | 8202236109 |  | 8202211462#Material Perbaikan pompa G-8- | RU5-E15112 | G-8-07A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 3939300 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-11 | 2026-02-03 | 2026-02-03 | 2102352637 | 8202235222 |  | 8202211407#Kontrak Volume Mekanik Utilit |  |  | 60 | CLSD CNF NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-27 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-08-11 |  | 8202233994 |  | 8202211357#Kerusakan Housing Motor 15-K- | RU6-RCC | 15-K-101-K1B-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102352670 | 8202235912 |  | 8202211347#RRKAP2023-Pemeliharaan RPA 1- |  |  | 60 | REL CNF NMAT PRC SETC | 3MR |  | 0 | 0 | MA2-STA |  | SAPBATCH | 2026-02-27 | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-13 |  | 8202236048 |  | 8202211336#GANTI WATER LEVEL GAUGES HHP | RU5-UTL | HHP-5/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-05-22 | 2026-12-29 |  | 8202236001 |  | 8202211332#RK_Pembelian 5 Motor 22/18.5/ | RU5-E15111 | EM-7-03A/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-05-22 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-12 | 2026-07-03 | 2026-08-03 |  | 8202236046 |  | 8202211316#Material Perb.Saluran Pending |  |  | 60 | CLSD CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-03-03 | 2026-04-22 |  | 8202236030 |  | 8202211314#Material Perbaikan Cover Pomp |  |  | 60 | TECO CNF CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | SAPBATCH | 2026-05-02 | 2026-02-11 | PT02 |  | 3 | 2026-05-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-08-13 | 2102361173 | 8202237177 |  | 8202211299#D_23[PV] Pengantian MLOP & AL | RU4-LOC1 | 25P1A-T/00 | 50 WAMA | REL NMAT PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 1624 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202236004 |  | 8202211298#Perbaikan G-5-09 B | RU5-E15111 | G-5-09B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/23/B6/RT-C2H | 2380103 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2025-12-11 | 2025-12-11 |  | 8202236067 |  | 8202211290#G-34-111A Perbaikan pompa | RU5-D&W | G-34-111A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 96800000 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2025-12-22 | 2025-12-24 |  | 8202236007 |  | 8202211281#Perb. Generator diesel RPPK B | RU5-E15112 | 41-R-RPP/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 10680770 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-04-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-04-22 | 2026-04-22 | 2026-04-28 |  | 8202236020 |  | 8202211280#Material Perbaikan Fin-Fan EA | RU5-E15112 | EF-32-01R/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 975377052 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-04-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-09 | 2026-06-09 | 2026-06-12 |  | 8202235982 |  | 8202211277#Perbaikan pompa G-15-01B | RU5-TBL | G-15-01B/01 | 60 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 2895820 | 0 | MA4-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2025-12-22 | 2025-12-29 |  | 8202235958 |  | 8202211275#PM Fin-Fan EA-8-10F | RU5-E15112 | EF-8-10F/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 18261732 | 0 | MA3-ROT |  | SAPBATCH | 2026-04-23 | 2026-02-11 | PT02 |  | 3 | 2026-04-23 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-05 |  | 8202235980 |  | 8202211266#Perbaikan Pompa G-2-05B | RU5-E15112 | G-2-05B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 54693890 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361180 | 8202237186 |  | 8202211260#D_23 011P103 BT pelumas turbi | RU4-FOC2 | 011P103B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-05 |  | 8202235956 |  | 8202211247#Temuan PM Battery charger 30T | RU5-UTL | P-BC-61/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-05-18 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 |  | 8202235931 |  | 8202211239#Penambahan lampu pd Bordes L/ | RU5-TBL | PLANT-20-LIS/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 3143000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-11 | 2026-02-03 | 2026-02-05 |  | 8202235927 |  | 8202211225#Temuan PM Battery charger 30T | RU5-UTL | P-BC-63/00 | 60 | CLSD PCNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-18 |  | 8202235929 |  | 8202211213#Perbaikan Motor EM-32-01B | RU5-E15112 | EM-32-01B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365940 | 8202239677 |  | 8202211171#[PV] Antisipasi Matl 101F503P | RU4-RFCC | 101F503P2-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 |  | 8202235925 |  | 8202211139#MAT.TMBH VLV&FLG JALUR TANK A | RU5-TBL | 022-R-RP-PSA/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 452299426 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360986 | 8202234540 |  | 8202211035#RKA23_UP_CUI_MA2 | RU4-FOC2 | 014C101/00 | 60 | REL CSER NMAT PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-29 | 2102361222 | 8202237480 |  | 8202211017#Rejuvenate Kabel 011K-101A/B/ | RU4-FOC2 | 011K101AM/00 | 50 WASR | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2026-01-02 | 2026-01-02 |  | 8202235869 |  | 8202210984#Belt K-5-20 Rusak | RU5-E15111 | K-5-20/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 1089780 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-11 |  | 8202235853 |  | 8202210953#Perbaikan Mixer A32 A & B | RU5-TBL | TM-24-06B/00 | 60 | REL CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 500470 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-11 |  | 8202235851 |  | 8202210950#Perbaikan Motor GM-3-49D | RU5-E15112 | GM-3-49D/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 52870 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365468 | 8202239676 |  | 8202210942#23_Perbaikan Solenoid Pompa 1 | RU4-RFCUTL | 154P503A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/23/B6/RT-12-C2H | 1 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358746 | 8202234122 |  | 8202210933#Ganti Thermocouple Area CDU, |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-2-D2H | 0 | 0 | MA-ROT |  | T_FATAHY |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 005
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-08 |  | 8202235849 |  | 8202210907#Ganti Material filter pompa k | RU5-D&W | A-235-01/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 3399068 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361178 | 8202237184 |  | 8202210899#D_23 Penggantian intake filte | RU4-RFCUTL | 156A502B-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-12-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361179 | 8202237185 |  | 8202210898#D_23 Penggantian intake filte | RU4-RFCUTL | 156A502A-K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-12-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365511 | 8202239675 |  | 8202210882#23_520B401 penggantian transm |  |  | 60 | REL CSER MACM PRC SETC | 4IR | D14/23/B6/RT-4-C2H | 18500000 | 0 | MA5-INT |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2025-12-23 | 2025-12-29 |  | 8202235826 |  | 8202210869#Perbaikan Turbine GT-3-35A | RU5-E15112 | GT-3-35A/00 | 60 | CLSD MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 164438686 | 0 | MA3-ROT |  | MKASPUDDIN |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202235845 |  | 8202210843#G-3-30A Spare Pump not Ready | RU5-E15112 | G-3-30A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 29209934 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-14 | 2026-04-10 | 2026-07-15 |  | 8202232149 |  | 8202210839#21-P-103A | RU6-DHC | 21-P-103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/24/B6/RT-C2H | 7221474 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-04-10 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-11 | 2026-01-02 | 2026-01-02 | 2102360950 | 8202234116 |  | 8202210809#perb. rele proteksi breaker i | RU2S-KIL | 900-06PD1-TRH1/00 | 60 | REL NMAT PRC SETC | 2MS | D12/26/B6/NRZ-D3H | 350000000 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-01-02 | PM |  | 004
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235787 |  | 8202210790#Mat.Perb.Insulasi 5P57 overhe | RU5-E15111 | C-5-07/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-06-29 |  | 8202233441 |  | 8202210770#Penggantian valve downstream | RU6-UTL | 52-B-101F/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 11880 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202235785 |  | 8202210751#Perbaikan Motor GM-17-01B | RU5-E15112 | GM-17-01B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-18 | 2026-09-24 |  | 8202235781 |  | 8202210744#Perbaikan Control Valve 201-X | RU5-D&W | 201-XCV-008/00 | 50 | REL MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 200002304 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-18 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202235783 |  | 8202210741#MAT.PERB.LINE STEAM PEMANAS T | RU5-TBL | O-1/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/23/B6/RT-C2H | 5901187 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2027-02-01 |  | 8202235778 |  | 8202210737#Perbaikan Control Valve 202-X | RU5-D&W | 202-XCV-001/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 1413250000 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-12-30 | 2027-08-27 |  | 8202235774 |  | 8202210733#Perbaikan Pompa G-2-16D | RU5-E15112 | G-2-16D/00 | 50 | REL MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 51144336 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-12-30 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 |  | 8202235764 |  | 8202210701#MAT.PERB.LINE STEAM PUMP OC & | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 63438395 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-05 |  | 8202235770 |  | 8202210692#Gm-3-25F Rusak | RU5-E15112 | PLANT-3C-LIS/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 748264 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 |  | 8202235731 |  | 8202210673#MAT.PMSGAN.ISOLASI.K-3-02 | RU5-E15112 | K-3-02A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 25699205 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102361217 | 8202237193 |  | 8202210652#D_23 [CR] 57P201A: Mechanical | RU4-UTL | 57P201A/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | SAPBATCH | 2026-06-11 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-10-05 | 2026-11-16 |  | 8202235703 |  | 8202210645#Material Penyehatan Demin Cha | RU5-UTL | D4-XSV-402/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/26/B6/RT-C2H | 69509563 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-10-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202235648 |  | 8202210621#K-3-01B Hub Coupling, Bolt, N | RU5-E15112 | K-3-01B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 61272000 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235645 |  | 8202210619#perbaikan o ring casing G-7-0 | RU5-E15111 | G-7-03A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202235652 |  | 8202210616#G-3-09 Purifier MAB104B-14/24 | RU5-E15112 | G-3-09A/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 6864938 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 |  | 8202235698 |  | 8202210594# Perbaikan I/P 02 FCV 133A | RU5-E15112 | 02-FCV-133A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/23/B6/RT-C2H | 39360569 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-02-05 |  | 8202235610 |  | 8202210567#Pembelian Motor Set Pompa GM- | RU5-E15112 | GM-3-49A/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 |  | 8202233922 |  | 8202210554#Material RAFI 2023 Untuk Inst | RU6-HSC | 32-R-101-UP6/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/25/B6/RT-C2H | 288536252 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202235530 |  | 8202210515#MAT. GANTI EXPANSION JOINT DU | RU5-UTL | K-32-01A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 34719600 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2026-02-02 |  | 8202232864 |  | 8202210491#Perbaikan Temp. Monitoring 14 | RU6-DHC | 14-K-102A-LP/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA2-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365305 | 8202239674 |  | 8202210453#[CR] Penggantian Impeller 82P | RU4-KPC | 82P203A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-10-C2H | 6 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-04 |  | 8202235418 |  | 8202210434#Ganti Material Valve Strainer |  | FA-201/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202235415 |  | 8202210433#MAT. VALVE TANK WTP GN. 4 TAN | RU5-UTL | OFC03203/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 88487014 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235413 |  | 8202210429#Pengambilan material gasket A |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 10761535 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 |  | 8202233681 |  | 8202210415#Penggantian Camlock Coupling | RU6-ITP | 41-LA-101/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-08-10 | 2102364137 | 8202233711 |  | 8202210390#Penggantian Analisa Conductiv | RU6-UTL | 51-G-101E/00 | 60 | REL NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 15840 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 |  | 8202235338 |  | 8202210376#MAT.LINE STEAMTRACE LINE SLOP | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C4H | 105797952 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202235313 |  | 8202210339#MAT.PERB.LINE 617-4" SLOP RPA | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 1439040 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365510 | 8202239673 |  | 8202210337#23_Perbaikan 154 XV 763 C | RU4-RFCUTL | 154A503C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/23/B6/RT-12-C2H | 9500000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365469 | 8202239672 |  | 8202210336#23_Perbaikan 154XV808 SOV Cau | RU4-RFCUTL |  | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/23/B6/RT-12-C2H | 9500000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 |  | 8202235311 |  | 8202210307#MAT.PERB.LINE HEADER PENDINGI | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 256810119 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202235312 |  | 8202210297#GM-34-64 Bearing Defect | RU5-E15112 | GM-34-64/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 7741525 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361188 | 8202237200 |  | 8202210266#D_23 [CR] 018K101A : Mlop tid | RU4-FOC2 | 018K101A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2025-11-07 | 2026-04-13 |  | 8202233600 |  | 8202210250#Penggantian level glass boile | RU6-UTL | 52-B-101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/24/B6/RT-C2H | 1280 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | 8202235307 |  | 8202210245#MAT.E-3-49B Cleaning | RU5-E15112 | E-3-49B/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 1518154 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | 8202235309 |  | 8202210244#MAT.E-3-48C Cleaning | RU5-E15112 | E-3-48C/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 913958 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 |  | 8202235310 |  | 8202210242#MAT.E-3-47B Cleaning | RU5-E15112 | E-3-47B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 690372 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-05-29 |  | 8202233804 |  | 8202210206#Pengadaan Lampu Area RCC | RU6-RCC | SS-14B/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 304459095 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365482 | 8202239671 |  | 8202210194#23_Pengadaan Material Relokas |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/24/B6/RT-2-C2H | 157132153 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202235262 |  | 8202210184#Perbaikan throttle valve GT-5 | RU5-E15111 | GT-5-18A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/23/B6/RT-C2H | 112843000 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 |  | 8202235257 |  | 8202210169#Perbaikan I/P Transducer CV 4 | RU5-UTL | 37-LCV-401A/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/25/B6/RT-C2H | 157442276 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202235254 |  | 8202210150#MAT.Pemasangan blind off E-2- | RU5-E15112 | E-2-16A/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 950692 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-06-29 |  | 8202235223 |  | 8202210104#Perbaikan Motor EAM-202-04B | RU5-D&W | EAM-202-04B/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-02-03 | 2026-02-11 |  | 8202235154 |  | 8202210063#Pembelian Motor Deep Well P-1 |  |  | 60 | TECO CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH | 2026-06-11 | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-01-25 |  | 8202233650 |  | 8202210036#Penggantian Filter CO 51-G-10 | RU6-UTL | 51-G-101E-SRB2B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 31020 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202235135 |  | 8202209958#Perbaikan Motor GM-3-49B | RU5-E15112 | GM-3-34F/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 104360 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102352678 | 8202235040 |  | 8202209926#Pekerjaan Stationary Emergenc | RU3-CDGP |  | 60 | REL CSER MACM PRC SETC | 3MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202235127 |  | 8202209920#G-8-01C mech. seal bocor dera | RU5-E15112 | G-8-01C/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 3687934 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-05-04 | 2026-05-26 |  | 8202235129 |  | 8202209911#G-201-06B Perbaikan pompa | RU5-D&W | G-201-06B/00 | 60 | CLSD CSER PRC SETC | 5RR | D15/26/B6/RT-C2H | 93836667 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-02-02 | 2026-05-26 | 2026-01-02 | 2026-01-02 | 2102361177 | 8202237183 |  | 8202209903#D_23 Penggantian pompa 054WS1 | RU4-UTL | 054WS101P2/00 | 60 | TECO CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | TONNYADI | 2026-03-30 | 2026-02-07 | PT02 |  | 3 | 2026-05-26 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-02 |  | 8202235075 |  | 8202209863#Perbaikan ATG u/ material&Gla | RU5-D&W | 13-LT-D20-05D/00 | 60 | REL CSER NMAT PRC SETC | 5IR | D15/23/B6/RT-C2H | 0 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K701 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102358744 | 8202234119 |  | 8202209850# Estimasi Pengadaan Trafo Dis | RU7-CDU | 1-C-01/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235082 |  | 8202209847#MAT.E-1-31.BOCOR | RU5-E15111 | E-1-31A/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 310741 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202235079 |  | 8202209841#MAT.PERB.LINE DRAIN BAK SLOP | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 4485642 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102357955 | 8202237926 |  | 8202209837#2023-2026_LTSA ATG Endress+Ha |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D3H | 1 | 0 | MA-LINT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202235051 |  | 8202209819#Perbaikan Motor GM-3-49B | RU5-E15112 | GM-3-49B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202235053 |  | 8202209818#Perbaikan Motor GM-25-01B | RU5-E15112 | GM-25-01B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K501 | 2026-02-04 | 2026-06-15 | 2026-02-04 | 2026-07-03 | 1102330029 | 8202238083 |  | 8202209795#NRK_RLA&Sertifikasi Metering | RU5-TBL | 22-716B/00 | 60 | CRTD NMAT PRC SETC | 5IR | D15/23/B6/RT-C2H | 1 | 0 | ENG-STA |  | ANTONIUSAD |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202235050 |  | 8202209788#MAT.F-8-01A Line Pilot Bocor | RU5-E15112 | F-8-01A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 2179256 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 |  | 8202235048 |  | 8202209786#MAT.PLUG.TUBE.E-35-02 | RU5-E15112 | E-35-02C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 6710720 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202235046 |  | 8202209764#Material MOC Block Valve 6" i | RU5-D&W | D-34-01/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 357494502 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102361025 | 8202235306 |  | 8202209748#Perbaikan Valve Sample Point | RU4-RFCC | 103SN516/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202235012 |  | 8202209745#MAT.PERB.LINE 21P-944-8 JL 11 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 772106 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202234950 |  | 8202209709#Perbaikan Motor GM-3-21A | RU5-E15112 | GM-3-21A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 426000 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K701 | 2026-02-03 | 2026-03-12 | 2026-02-03 | 2026-02-03 | 2102357956 | 8202237905 |  | 8202209579#Pekerjaan LTSA Trafo |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D1H | 1 | 0 | MA-LINT |  | RYANMANGGASA |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202234928 |  | 8202209569#MAT.PIPELINE SUNGAI WAIN (SOM | RU5-UTL | DAM-SEIWAIN/00 | 50 | REL MSPT PRC SETC | 5MR | D15/23/B6/RT-C2H | 6400039800 | 0 | MA4-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202234946 |  | 8202209566#Line SCW Return header K-35-0 |  |  | 50 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 4961528 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-04 | 2026-05-19 |  | 8202234948 |  | 8202209564#Ganti pipa C-201-07 to PSV-00 | RU5-D&W | 201-P014-8-C3/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN | 2026-05-07 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202234838 |  | 8202209551#Perbaikan Motor GM-3-34F | RU5-E15112 | GM-3-34F/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 |  | 8202234841 |  | 8202209525#perbaikan K-1-01A | RU5-E15111 | K-1-01A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 152584895 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-03-03 | 2026-04-22 |  | 8202234772 |  | 8202209522#MAT.SUPPORT PEK. JUMPERLINE G | RU5-UTL | G-32-05B/00 | 60 | CLSD CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-05-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-02-03 | 2026-06-29 |  | 8202234739 |  | 8202209515#Perbaikan Motor GM-2-14 | RU5-E15112 | GM-2-14B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/25/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-07-13 |  | 8202234703 |  | 8202209458#Perbaikan Motor GM-3-08C | RU5-E15112 | GM-3-08C/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 680650 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202234647 |  | 8202209440#Perbaikan Motor Em-32-01I | RU5-E15112 | EM-32-01A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 831895 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202234651 |  | 8202209428#Perbaikan Motor Em-3-20F | RU5-E15112 | EF-3-20M/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 683320 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 |  | 8202234657 |  | 8202209423#MAT.PERB.PIPING OIL CATCHER O | RU5-TBL | OC-RP-A/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 57794100 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202234652 |  | 8202209415#Perbaikan Motor EM-2-12A | RU5-E15112 | EM-2-12A/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 |  | 8202234617 |  | 8202209410#MAT.PERB. LINE STEAM OC DI JE | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 137132101 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-03 | 2026-06-29 |  | 8202234609 |  | 8202209406#Perbaikan Motor GM-3-07A | RU5-E15112 | GM-3-07A/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-01-02 | 2026-01-02 |  | 8202234115 |  | 8202209359#Perbaikan bolt rubbercoupling | RU2S-KIL | 900-08P-1C/00 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/NRZ-C2H | 4956000 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-25 | 2026-04-28 | 2026-04-30 |  | 8202234522 |  | 8202209333#Pembelian Motor Pompa Injeksi | RU5-TBL | G-24-02D/00 | 60 | CLSD CSER NCMP NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 0 | 0 | MA4-LIS |  | BERNANDOP |  |  | PT02 |  | 2 | 2026-05-25 | PM |  | 045
| K701 | 2026-02-03 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102357959 | 8202237888 |  | 8202209326#Perkerjaan LTSA pemeliharaan |  |  | 60 | REL GMPS NMAT PRC SETC | 7RT | D17/24/B6/RT-1-D3H | 1733234000 | 61425000 | MA-LINT |  | T_YUDIPRAS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-02 | 2026-06-29 |  | 8202234519 |  | 8202209325#Perbaikan Motor GM-38-06A | RU5-E15112 | GM-38-06A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 5ER | D15/23/B6/RT-C2H | 3736743 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-05 | 2026-02-11 | PT02 |  | 3 | 2026-02-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | 8202234480 |  | 8202209312#MAT.PERB. LINE 21-P934-12" PE | RU5-TBL | PIPE-SHIP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 81589969 | 0 | MA4-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-11-30 |  | 8202234479 |  | 8202209311#MAT.PERB.LINE MP STEAM PUMP E | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 7217709 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-19 | 2026-02-02 | 2026-06-29 |  | 8202234425 |  | 8202209285#Perbaikan Motor EM-31-21B | RU5-E15112 | EM-31-21B/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-04 | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-02-02 | 2026-05-12 |  | 8202234436 |  | 8202209260#perbaikan EA-1-21z | RU5-E15111 | EF-1-21Z/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 4106325 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  | 8202234441 |  | 8202209259#perbaikan EA-1-21V | RU5-E15111 | EF-1-21V/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 4106325 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 8202234445 |  | 8202209257#perbaikan EA-1-21U | RU5-E15111 | EF-1-21U/00 | 50 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 13624925 | 0 | MA2-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-20 | 2026-02-03 | 2026-06-29 |  | 8202236969 |  | 8202209234#Perbaikan Motor GM-17-01A | RU5-E15112 | GM-17-01A/00 | 60 | CLSD CNF CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA3-LIS |  | SAPBATCH | 2026-02-10 | 2026-02-11 | PT02 |  | 3 | 2026-02-10 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236967 |  | 8202209209#MAT.PERB. LINE DRAIN BAK SLOP | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/23/B6/RT-C2H | 5266260 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-09 | 2102364138 | 8202236965 |  | 8202209175#MAT.PERB. VLV STEAM 2" DI Jl. | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 661968 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K202 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | 2102352342 | 8202234114 |  | 8202209164#Kebutuhan Gliserin Area CDU | RU2S-KIL | 101-P-2A/00 | 50 | REL MACM PRC SETC | 2MS | D12/25/B6/RTZ-C2H | 9000000 | 0 | MAS-ME1 |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-05 | 2102364186 | 8202236931 |  | 8202209155#Perbaikan K-3-02C | RU5-E15112 | K-3-02C/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 71216401 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202236954 |  | 8202209153#MAT.PERB.ISOLASI.EA-3-02 |  |  | 50 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 6892720 | 0 | MA3-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202236935 |  | 8202209143#Perbaikan Cooler G-1-04B | RU5-E15111 | G-1-04B/00 | 60 | REL CSER NMAT PRC SETC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 |  | 8202236933 |  | 8202209139#Perbaikan EA-1-28C | RU5-E15111 | EA-1-28C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 3260602 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365320 | 8202239670 |  | 8202209133#23_Modifikasi Jumper Line D/S |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 6405053 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-16 | 2102364348 | 8202237710 |  | 8202209099#RLA & PLO Instalasi OM | RU5-TBL | 022-R-RP-PSA/00 | 60 | REL NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | ENG-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-04-16 | 2102364349 | 8202237709 |  | 8202209098#RLA & PLO Instalasi Lawe Lawe | RU5-TBL | PIPE-ON-SHORE/00 | 60 | REL NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | ENG-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-06-02 |  | 8202236880 |  | 8202209062#Perbaikan Master Meter Naphth | RU5-TBL | TURBINMTR-855A/00 | 60 | REL NMAT PRC SETC | 5IR | D15/24/B6/RT-C2H | 4752 | 0 | MA4-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-02-03 | 2026-02-03 |  | 8202236883 |  | 8202209060#EA-17-04BV | RU5-E15112 | EA-17-04B/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 119342168 | 0 | MA3-ROT |  | DANANGIBNUM |  | 2026-02-11 | PT02 |  | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365299 | 8202239669 |  | 8202209009#23_Pengadaan Baut dan Gasket |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 39280647 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365298 | 8202239668 |  | 8202209008#23_Pengadaan Baut dan Gasket |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 40178761 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-06 |  | 8202236808 |  | 8202208999#Mat.Cleaning Surface Condenso | RU5-TBL | E-20-01A/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA4-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202236774 |  | 8202208995#O-Ring Actuator STG 1.5A rusa | RU5-UTL | TG-5A-PP1/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 |  | 8202236769 |  | 8202208993#Penggantian Coupling Pompa G- | RU5-E15111 | G-4-11B/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 4000000 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-07 | 2026-05-07 | 2026-05-11 |  | 8202236766 |  | 8202208978#Perbaikan Motor EAM-202-04A | RU5-D&W | EAM-202-04A/00 | 60 | REL CSER NMAT PRC SETC | 5ER | D15/23/B6/RT-C2H | 0 | 0 | MA1-LIS |  | HELDIPRANATA |  | 2026-02-11 | PT02 |  | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-02-08 | 2026-03-09 | 2026-02-09 | 2026-12-30 | 2102363931 | 8202238764 |  | 8202208977#[PV] Assessment kondisi udara | RU4-RFCUTL | 156K502B/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 320000000 | 272000000 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-09 | PT02 |  | 3 | 2026-02-09 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2025-11-03 | 2026-03-16 |  | 8202236771 |  | 8202208967#Pemas. Pressure TX di in/out | RU5-E15111 | 01-FT-182/00 | 60 | REL MSPT PRC SETC | 5IR | D15/23/B6/RT-C2H | 25522050 | 0 | MA2-INT |  | RUDIEKO |  | 2026-02-07 | PT02 |  | 3 | 2025-11-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-06 |  | 8202236797 |  | 8202208965#Material Perbaikan Jalur Line |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 2636901 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202236804 |  | 8202208963#Material Perb. line 201-SCW02 | RU5-D&W | 201-SCWR02-1-A3/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 5897059 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202236801 |  | 8202208962#Material Perb. line 201-SCW06 | RU5-D&W | 201-SCWR06-8-A3/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 65535720 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202235528 |  | 8202208932#NRK23_Perbaikan Electric Heat | RU4-TRML | 041E313D/00 | 60 | REL NMAT PRC SETC | 4ER | D14/24/B6/RT-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-01-02 | 2102360990 | 8202234954 |  | 8202208864#Preventive Maintenance 180-A- | RU4-GTO | 180A601K1A/00 | 60 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA7-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-07-31 | 2102364350 | 8202236650 |  | 8202208859#Perbaikan Speed Sensor K-3-02 | RU5-E15112 | KT-3-02B/00 | 60 | TECO CNF CSER NMAT PRC SETC | 5IR | D15/23/B6/RT-C2H | 0 | 0 | MA3-INT |  | SAPBATCH | 2026-05-18 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365524 | 8202239667 |  | 8202208853#23_[PV]Pengadaan Grid Nylon F | RU4-LOC2 | 024S101D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-8-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365698 | 8202239666 |  | 8202208850#23_[CR] Perbaikan 023P115B | RU4-LOC2 | 023P115B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-7-C2H | 5187800 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-12 | 2026-02-03 | 2026-02-03 | 2102361184 | 8202237195 |  | 8202208846#D_23 [CR] 057P101BT : Ganti G | RU4-UTL | 057P101B-T/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/23/B6/RT-4-C2H | 0 | 0 | MA5-ROT |  | TONNYADI | 2026-06-02 | 2026-02-07 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-02-02 | 2026-06-12 | 2026-02-03 | 2026-02-06 | 2102361187 | 8202237199 |  | 8202208842#D_23 [CR] 052P102AT : Ganti G | RU4-UTL | 052P102A-T/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/24/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | TONNYADI | 2026-06-02 | 2026-02-07 | PT02 |  | 3 | 2026-06-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 8202236579 |  | 8202208812#G-3-02B: Gland Packing Bocor, | RU5-E15112 | G-3-02B/01 | 50 | REL CSER MANC PRC SETC | 5RR | D15/24/B6/RT-C2H | 382799400 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202236531 |  | 8202208795#Material Perbaikan line 201-S | RU5-D&W | 201-SCWR01-6-A3/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/24/B6/NR-C2H | 13498255 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-06-03 | 2026-07-16 | 2102364345 | 8202236527 |  | 8202208794#Perbaikan line 201-SCW04-6”-A | RU5-D&W | 201-SCWR04-6-A3/00 | 60 | REL CNF CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN | 2026-06-04 | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 | 2102364346 | 8202236574 |  | 8202208793#Material Perb. line 202-SCW-0 |  |  | 60 | REL NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 396 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-07 | 2026-02-02 | 2027-01-22 |  | 8202233210 |  | 8202208734#Perbaikan boiler 52-B-101F | RU6-UTL | 52-B-101F/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 31020 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2102364351 | 8202236517 |  | 8202208727#G-34-112B Perbaikan (mecseal) | RU5-D&W | G-34-112B/00 | 60 | REL CSER MSPT PRC SETC | 5RR | D15/23/B6/RT-C2H | 26200000 | 0 | MA2-ROT |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-07-02 |  | 8202236431 |  | 8202208704#Perbaikan Auto Start Sump Pum | RU5-E15112 | G-34-100B/00 | 60 | REL CSER MACM PRC SETC | 5IR | D15/24/B6/RT-C2H | 1990265456 | 0 | MA3-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-03 | 2102364347 | 8202236405 |  | 8202208645#Perbaikan Cooler GT-5-17A | RU5-E15111 | GT-5-17A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 597650000 | 0 | MA2-STA |  | BAMBANGSS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236408 |  | 8202208624#MAT.TIE IN JUMPER LINE TANK O | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MSPT PRC SETC | 5MR | D15/23/B6/RT-C2H | 6704961 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202236373 |  | 8202208526#Perbaikan Breather Valve TK.T | RU5-D&W | T-1A/00 | 01 | CRTD NMAT PRC | 5MR | D15/10/B6/RT1-D5NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2025-11-05 | 2026-01-06 |  | 8202236376 |  | 8202208525#Mat. Perbaikan Line Suction G | RU5-D&W | D-34-11/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/25/B6/RT-C2H | 389245794 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2025-11-05 | PM |  | 003
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202236362 | 8202235967 | 8202208523#PEMBUATAN TIE IN JALUR STORM | RU5-D&W | D-34-10/00 | 50 | CRTD CSER NMAT PRC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-12 | 2025-12-15 | 2025-12-15 |  | 8202236360 |  | 8202208488#Perbaikan G-5-09A | RU5-E15111 | G-5-09A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 27641052 | 0 | MA2-ROT |  | SAPBATCH | 2026-05-12 | 2026-02-11 | PT02 |  | 3 | 2026-05-12 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 8202236372 |  | 8202208479#Ea-32-01B Blade Rusak | RU5-E15112 | EA-32-01B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/23/B6/RT-C2H | 1009989946 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-05-06 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-06-02 | 2026-06-03 |  | 8202236358 |  | 8202208473#Pengadaan Governor Linkage Tu | RU5-D&W | GS-202-08B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 166400001 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202236334 |  | 8202208446#MAT.Perbaikan Line MS Steam k |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 4488295 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-26 | 2026-02-03 | 2026-03-02 |  | 8202236267 |  | 8202208435#Penggantian Limit Switch K-3- | RU5-E15112 | K-3-02A-INST/00 | 60 | TECO CNF CSER MACM PRC SETC | 5IR | D15/23/B6/RT-C2H | 6892615 | 0 | MA3-INT |  | HASRUDDINA | 2026-05-26 | 2026-02-11 | PT02 |  | 3 | 2026-05-26 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-03 | 2026-06-03 | 2026-11-30 |  | 8202236269 |  | 8202208423#MAT.TMBHN LN 21-P952;EMOC-059 | RU5-TBL | PIPE-TANK-PUMP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 971000 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-12 | 2026-02-03 | 2026-02-09 |  | 8202236272 |  | 8202208397#MAT. PENGGANTIAN LINE METERIN | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MANC PRC SETC | 5MR | D15/23/B6/RT-C2H | 634633576 | 0 | MA4-STA |  | OCTARIOHS |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-04 | 2026-11-03 | 2026-12-15 |  | 8202236254 |  | 8202208371#Ganti BV Ejektor no.2 STG 2.4 | RU5-UTL | TG2-PP2-2RF04-S/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 12103357 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-11-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-22 | 2026-06-22 | 2026-11-23 |  | 8202236252 |  | 8202208369#Ganti valve discharge pompa n |  |  | 60 | REL CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA4-STA |  | SUDARMANTO |  | 2026-02-11 | PT02 |  | 3 | 2026-06-22 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-03-25 |  | 8202236226 |  | 8202208363#Penggantian condensate cooler |  | S-37-01A/00 | 01 | CRTD CSER NMAT PRC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-08 |  | 8202236227 |  | 8202208359#Pengadaan Governor Linkage Tu | RU5-D&W | GS-202-05B/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 7 | 0 | MA1-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365540 | 8202239665 |  | 8202208327#23_[PV] Perbaikan Pompa 023P1 | RU4-LOC2 | 023P110A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-03-05 | 2102365565 | 8202239664 |  | 8202208320#23_Perbaikan 93P401B | RU4-SRU | 93P401B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-6-C2H | 6100300 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-18 | 2026-02-03 | 2026-02-10 |  | 8202236222 |  | 8202208319#Penggantian Panel DCS HIS 642 | RU5-HSC |  | 60 | TECO CNF CSER NMAT PRC SETC | 5IR | D15/23/B6/RT-C2H | 0 | 0 | MA3-INT |  | HASRUDDINA | 2026-05-18 | 2026-02-11 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202236080 |  | 8202208247#Ganti Material Valve Drain K- | RU5-E15112 | K-19-01A/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/23/B6/RT-C2H | 580792 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-08 | 2026-12-03 | 2026-12-28 |  | 8202236018 |  | 8202208169#Terdapat bocoran lube oil dia | RU5-UTL | TG-6-PP1/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/24/B6/RT-C2H | 115132000 | 0 | MA1-ROT |  | JOYOPRATIKN |  | 2026-02-11 | PT02 |  | 3 | 2026-12-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-06-11 | 2026-06-09 | 2026-06-11 |  | 8202236017 |  | 8202208162#Gm-3-49A Motor Rusak | RU5-E15112 | GM-3-49A/00 | 60 | TECO CNF CSER MACM PRC SETC | 5ER | D15/26/B6/RT-C2H | 37800 | 0 | MA3-LIS |  | MKASPUDDIN | 2026-06-11 | 2026-02-11 | PT02 |  | 3 | 2026-06-11 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 |  | 8202236014 |  | 8202208157#MAT.PENGGANTIAN.ISOLASI.F-3-0 |  |  | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 24297535 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-05-06 | 2026-02-03 | 2026-02-03 |  | 8202236016 |  | 8202208149#MAT.FILTER.PACKINOX&K-5-02ABC | RU5-E15111 | E-5-01/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 42746613 | 0 | MA2-STA |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202235967 |  | 8202208110#MAT.Pembuatan By Pass SWB ke | RU5-D&W | D-34-10/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 914832252 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-04-09 |  | 8202235964 |  | 8202208088#Material Cleaning & Perbaikan | RU5-E15111 | E-1-08A1/00 | 60 | REL CSER NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-07 | 2026-12-22 | 2026-12-29 |  | 8202235822 |  | 8202208028#Perbaikan bocoran steam di TT | RU5-E15111 | KT-5-02C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 82116807 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-12-22 | PM |  | 003
| K501 | 2026-02-02 | 2026-05-13 | 2026-02-03 | 2026-02-03 |  | 8202235824 |  | 8202208025#PERB.TUBE.E-3-59C.BOCOR | RU5-E15112 | E-3-59C/00 | 60 | TECO CNF CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 30308000 | 0 | MA3-STA |  | SAPBATCH | 2026-05-13 | 2026-02-11 | PT02 |  | 3 | 2026-05-13 | PM |  | 045
| K501 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 2026-06-08 |  | 8202235819 |  | 8202208019#Perbaikan Pompa G-31-41A | RU5-E15112 | G-31-41A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/25/B6/RT-C2H | 619585 | 0 | MA3-ROT |  | BERNANDOP |  | 2026-02-11 | PT02 |  | 3 | 2026-06-02 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202235919 |  | 8202208015#Mat. Perbaikan Line 16 inch D |  |  | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 181608250 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K501 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202235870 |  | 8202208008#Material Perbaikan TK.V-17B |  |  | 01 | CRTD CSER NMAT PRC | 5MR | D15/09/B6/RT1-DHNH | 0 | 0 | MA2-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-14 | 2026-02-02 | 2026-02-02 |  | 8202233786 |  | 8202207999#Pengadaan material perbaikan | RU6-ITP | 41-A-104/00 | 50 WAMA | REL CSER MACM PRC SETC | 6MR | D16/25/B6/RT-C2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-02 | 2026-02-14 | 2026-01-05 | 2026-02-27 |  | 8202233773 |  | 8202207993#Pengadaan Motor 32-E-112A2 | RU6-HSC | 32-E-112A2-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 2 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-05 | PM |  | 003
| K501 | 2026-02-02 | 2026-02-11 | 2026-02-03 | 2026-03-25 |  | 8202235777 |  | 8202207977#MAT. TAMBAHAN MODIF LINE 21-P | RU5-TBL | PIPE-SHIP/00 | 60 | REL CSER MACM PRC SETC | 5MR | D15/23/B6/RT-C2H | 32024560 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365297 | 8202239663 |  | 8202207963#23_Cleaning dan Pemeriksaan 0 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 503692 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365296 | 8202239662 |  | 8202207962#23_Cleaning dan Pemeriksaan 0 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 1155723 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365295 | 8202239661 |  | 8202207960#23_CLEANING 012E-101 NO 8 | RU4-FOC2 | 012E101-8/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-2-C2H | 3304985 | 0 | MA2-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K301 | 2026-02-04 | 2026-05-18 | 2026-01-02 | 2026-01-02 | 2102364341 | 8202238082 |  | 8202207459#KV PM Cleaning Pre Heater & R | RU3-CDGP |  | 60 | TECO CNF GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-01-06 | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-02-02 |  | 8202233226 |  | 8202207416#Perbaikan Bearing Pompa 11-P- | RU6-HSC | 11-P-109A-T/00 | 50 | REL CSER MACM PRC SETC | 6RR | D16/25/B6/RT-C2H | 0 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2102365466 | 8202239660 |  | 8202207393#22_Multi Protection Relay rus |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-8-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365417 | 8202239659 |  | 8202207371#22_[BD]Perbaikan Pompa 014K10 | RU4-FOC2 | 014K102C-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-03-12 | 2026-02-03 | 2026-02-03 |  | 8202235988 |  | 8202206878#Perbaikan Isolasi Fuel Gas to |  |  | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-03-05 | 2102365740 | 8202239658 |  | 8202206660#22_[PV] Penggantian Mech Seal | LOC1-UP4 | 47P505A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 0 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202235351 | 8202235377 | 8202206601#Kontr.Vol Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365430 | 8202239657 |  | 8202206454#22_[CR] Perbaikan Pompa 041P1 | RU4-TRML | 041P103A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 159358764 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K701 | 2026-02-03 | 2026-02-11 | 2026-02-03 | 2026-02-03 |  | 8202237868 |  | 8202206415#Perbaikan Crane Link Belt RTC |  |  | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-5-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365369 | 8202239656 |  | 8202206350#22_[CR] Penggantian Coupling | RU4-FOC2 | 014P101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 31200000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365479 | 8202239500 |  | 8202206349#22_[PV] Coupling 022P104B | RU4-LOC2 | 022P104B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 30875000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365337 | 8202239499 |  | 8202206302#22_[CR] Perbaikan 041P103A | RU4-TRML | 041P103A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-5-C2H | 389271093 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365850 | 8202239498 |  | 8202206267#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P102C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 209700000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365930 | 8202239497 |  | 8202206266#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P102B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 209700000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365929 | 8202239496 |  | 8202206265#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P110C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365849 | 8202239495 |  | 8202206264#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P110B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365848 | 8202239494 |  | 8202206263#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P119B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365847 | 8202239493 |  | 8202206261#22_[PV] Penggantian Coupling | RU4-FOC2 | 017P106B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365928 | 8202239492 |  | 8202206260#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P103C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365846 | 8202239491 |  | 8202206259#22_[PV] Penggantian Coupling | RU4-FOC2 | 012P101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365845 | 8202239490 |  | 8202206257#22_[PV] Penggantian Coupling | RU4-FOC2 | 012P103B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365844 | 8202239489 |  | 8202206256#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P123B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365853 | 8202239488 |  | 8202206255#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P112B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365843 | 8202239487 |  | 8202206254#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P111B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365842 | 8202239486 |  | 8202206251#22_[PV] Penggantian Coupling | RU4-FOC2 | 017P104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365841 | 8202239485 |  | 8202206250#22_[PV] Penggantian Coupling | RU4-FOC2 | 014P107B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365840 | 8202239484 |  | 8202206249#22_[PV] Penggantian Coupling | RU4-FOC2 | 019P122B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365839 | 8202239483 |  | 8202206243#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P123A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365852 | 8202239650 |  | 8202206242#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P112A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365838 | 8202239649 |  | 8202206241#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P107A/01 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365837 | 8202239648 |  | 8202206240#22_[PV] Penggantian Coupling | RU4-FOC2 | 017P106A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365836 | 8202239647 |  | 8202206239#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P119A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365835 | 8202239646 |  | 8202206237#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P103B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365834 | 8202239645 |  | 8202206236#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365927 | 8202239644 |  | 8202206235#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P110A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365506 | 8202239643 |  | 8202206233#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P102A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/24/B6/RT-2-C2H | 209700000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365833 | 8202239642 |  | 8202206182#22_[PV] Penggantian Coupling | RU4-FOC2 | 019P122A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365926 | 8202239641 |  | 8202206180#22_[PV]Penggantian Coupling 0 | RU4-FOC2 | 017P106C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365832 | 8202239640 |  | 8202206179#22_[PV] Penggantian Coupling | RU4-FOC2 | 017P104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365831 | 8202239639 |  | 8202206178#22_[PV] Penggantian Coupling | RU4-FOC2 | 014P107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365830 | 8202239638 |  | 8202206177#22_[PV] Penggantian Coupling | RU4-FOC2 | 014P101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 31200000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365851 | 8202239637 |  | 8202206176#22_[PV] Penggantian Coupling | RU4-FOC2 | 013P104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365854 | 8202239636 |  | 8202206175#22_[PV] Penggantian Coupling | RU4-FOC2 | 012P103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365829 | 8202239635 |  | 8202206174#22_[PV] Penggantian Coupling | RU4-FOC2 | 012P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365931 | 8202239634 |  | 8202206173#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P120A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365828 | 8202239633 |  | 8202206172#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P115A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365827 | 8202239632 |  | 8202206171#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P111A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365363 | 8202239631 |  | 8202206101#22_[CR] Perbaikan soot blower | RU4-RFCUTL | 151B501C-K4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-10-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365416 | 8202239630 |  | 8202206100#22_[PV] Pengadaan Auto Grease | RU4-FOC2 | 019K102A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 13000000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365625 | 8202239629 |  | 8202206074#22_[CR] Perbaikan Pompa 041P1 | RU4-TRML | 041P122A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 157546586 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365465 | 8202239628 |  | 8202206043#23_Perbaikan Pintu Panel LCP | RU4-UTL | 510G601T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 625000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202236003 |  | 8202206009#Lampu perangan di area proses |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-8-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-10-02 |  | 8202238504 |  | 8202205961#Overhaul Motor 12-K-501 C | RU6-DHC | 12-K-501C-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/24/B6/NR-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K301 | 2026-02-02 | 2026-06-10 | 2026-01-02 | 2026-01-02 | 2102364229 | 8202235240 |  | 8202205959#Kontrak Volume Mekanik PP |  |  | 60 | REL CNF GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA2-STA |  | HARISASEPWIJ | 2026-01-30 | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-06-29 | 2102361221 | 8202237479 |  | 8202205896#Perbaikan Motor 011P112A | RU4-FOC2 | 011P112A/00 | 50 WASR | REL NMAT PRC SETC | 4ER | D14/22/B6/NR-2-C2H | 40000000 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235446 |  | 8202205862#Kontr.Vol Cleaning Tangki & S |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365464 | 8202239627 |  | 8202205860#22_Perbaikan Speed Indicator | RU4-UTL | 510G601T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 32000000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K701 | 2026-02-02 | 2026-02-11 | 2026-02-02 | 2026-02-02 |  | 8202234181 |  | 8202205806#LTSA Air Compressor 4-K-02A/B | RU7-UTL | 4-K-02A/00 | 60 | REL NMAT PRC SETC | 7RT | D17/24/B6/RT-4-D2H | 0 | 0 | MA-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365463 | 8202239626 |  | 8202205770#23_Perbaikan Local Speed Indi | RU4-UTL | 530P601A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 32000000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365406 | 8202239625 |  | 8202205769#22_NRK [PV]Material preventiv | RU4-UTL | 051P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/NR-6-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365404 | 8202239624 |  | 8202205767#22_NRK [CR] Perbaikan 051P102 | RU4-UTL | 051P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/NR-6-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365622 | 8202239623 |  | 8202205736#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P111B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/NR-4-C2H | 19099000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365621 | 8202239622 |  | 8202205696#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P103D/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/NR-4-C2H | 24386750 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365321 | 8202239621 |  | 8202205676#23_Pengadaan mtl PSV 84PSV553 | RU4-KPC | 84PSV553B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/23/B6/RT-9-C2H | 0 | 0 | MA4-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365368 | 8202239620 |  | 8202205642#22_[PV] Penggantian Coupling | RU4-FOC2 | 018P101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365367 | 8202239619 |  | 8202205641#22_[PV] Penggantian Coupling | RU4-FOC2 | 018P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365366 | 8202239618 |  | 8202205640#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P113B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365365 | 8202239617 |  | 8202205638#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P113A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365364 | 8202239616 |  | 8202205637#22_[PV] Penggantian Coupling | RU4-FOC2 | 011P106B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365405 | 8202239615 |  | 8202205583#[PV] Penggantian coupling 57P | RU4-UTL | 57P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/NR-6-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365462 | 8202239614 |  | 8202205416#22_Perbaikan 510ZSC804 Proxim | RU4-UTL | 510G601T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 3900000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365461 | 8202239613 |  | 8202205415#22_Perbaikan 510VEY810 Radial | RU4-UTL | 510G601T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 92976000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365620 | 8202239612 |  | 8202205406#22_Penggantian Valve 43T2 & 4 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/22/B6/RT-7-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-14 | 2026-02-04 | 2027-01-28 |  | 8202238076 |  | 8202205270#Penggantian Part Mat. Online | RU6-HSC | 11-C-101/00 | 60 | REL CSER NMAT PRC SETC | 6MR | D16/25/B6/RT-C4H | 929753000 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-02-03 | 2026-04-27 | 2026-01-02 | 2026-01-02 | 2102361220 | 8202237478 |  | 8202205224#pemasangan MOV Tanki Day Tank | RU4-TRML | 39T204/00 | 50 WASR | CRTD CSER NMAT PRC RELR SETC | 4ER | D14/26/B6/RT-10-C2H | 100 | 0 | MA4-LIS |  | WAHYUCATUR |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365695 | 8202239611 |  | 8202205109#22_[PV] Penggantian Coupling | RU4-TRML | 041P106B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 31760000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365694 | 8202239610 |  | 8202205108#22_[PV] Penggantian Coupling | RU4-TRML | 041P106A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 31760000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365693 | 8202239609 |  | 8202205107#22_[PV] Penggantian Coupling | RU4-TRML | 041P104B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365692 | 8202239608 |  | 8202205106#22_[PV] Penggantian Coupling | RU4-TRML | 041P104A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365691 | 8202239607 |  | 8202205105#22_[PV] Penggantian Coupling | RU4-LOC2 | 025P101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 91056000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365690 | 8202239606 |  | 8202205104#22_[PV] Penggantian Coupling | RU4-LOC2 | 025P101A-G/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 91056000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365679 | 8202239605 |  | 8202205103#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P117B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23552000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365678 | 8202239604 |  | 8202205102#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P117A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23552000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365478 | 8202239603 |  | 8202205100#22_ Penggantian Coupling 024P | RU4-LOC2 | 024P116A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365677 | 8202239602 |  | 8202205098#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P115/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365676 | 8202239601 |  | 8202205097#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P113B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365675 | 8202239600 |  | 8202205096#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P113A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365674 | 8202239599 |  | 8202205095#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P112/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365673 | 8202239598 |  | 8202205094#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P111A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 19099000 | 19099000 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365672 | 8202239597 |  | 8202205093#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P110/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 19099000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365671 | 8202239596 |  | 8202205091#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P109A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365670 | 8202239595 |  | 8202205090#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P108/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23464000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365659 | 8202239594 |  | 8202205089#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P107B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23464000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-06-03 | 2026-03-05 | 2026-03-05 | 2102365658 | 8202239593 |  | 8202205088#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P107A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23464000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365657 | 8202239592 |  | 8202205087#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P103C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 24386750 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365656 | 8202239591 |  | 8202205086#22_[PV] Penggantian Coupling | RU4-LOC2 | 024P103B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 24386750 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365655 | 8202239590 |  | 8202205085#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P116B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 21062000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365467 | 8202239589 |  | 8202205042#23_Perbaikan control Valve152 | RU4-RFCUTL | 152PV065/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-9-C2H | 37326000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365415 | 8202239588 |  | 8202204999#22_[PV] Penggantian Coupling | RU4-FOC2 | 018P103B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 31760000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365414 | 8202239587 |  | 8202204979#22_[PV] Penggantian Coupling | RU4-FOC2 | 018P103A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 31760000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365413 | 8202239586 |  | 8202204978#22_[PV] Penggantian Coupling | RU4-FOC2 | 015P101B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365412 | 8202239585 |  | 8202204977#22_[PV] Penggantian Coupling | RU4-FOC2 | 015P101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 17136000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365624 | 8202239584 |  | 8202204976#22_[PV] Penggantian Coupling | TRML-UP4 |  | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 19099000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365623 | 8202239581 |  | 8202204975#22_[PV] Penggantian Coupling | TRML-UP4 |  | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 19099000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365411 | 8202239580 |  | 8202204974#22_[PV] Penggantian Coupling | RU4-FOC2 |  | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 31760000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365410 | 8202239579 |  | 8202204973#22_[PV] Penggantian Coupling | RU4-FOC2 |  | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-2-C2H | 31760000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365654 | 8202239578 |  | 8202204971#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P116A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 21062000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365653 | 8202239577 |  | 8202204968#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P114/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365652 | 8202239576 |  | 8202204967#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P110B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365651 | 8202239575 |  | 8202204966#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P110A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365650 | 8202239574 |  | 8202204965#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P109A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365629 | 8202239573 |  | 8202204964#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P108/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 21062000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365628 | 8202239572 |  | 8202204963#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P107B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365627 | 8202239571 |  | 8202204962#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P107A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 23025000 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365626 | 8202239570 |  | 8202204961#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P105B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 31550000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365477 | 8202239569 |  | 8202204959#22_[PV] Penggantian Coupling | RU4-LOC2 | 023P103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365476 | 8202239568 |  | 8202204958#22_[PV] Penggantian Coupling | RU4-LOC2 | 022P106B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365475 | 8202239567 |  | 8202204957#22_[PV] Penggantian Coupling | RU4-LOC2 | 022P106A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365474 | 8202239566 |  | 8202204956#22_[PV] Penggantian Coupling | RU4-LOC2 | 022P104A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 30875000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365473 | 8202239565 |  | 8202204955#22_[PV] Penggantian Coupling | RU4-LOC2 | 022P102B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365472 | 8202239564 |  | 8202204954#22_[PV] Penggantian Coupling | RU4-LOC2 | 022P102A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365471 | 8202239563 |  | 8202204953#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P114B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365470 | 8202239562 |  | 8202204952#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P114A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23025000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365439 | 8202239561 |  | 8202204950#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P110B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 19099000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365438 | 8202239560 |  | 8202204949#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P110A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 19099000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365437 | 8202239559 |  | 8202204948#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P109B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 28125000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365436 | 8202239558 |  | 8202204947#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P109A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 28125000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365435 | 8202239557 |  | 8202204945#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365434 | 8202239556 |  | 8202204943#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P106A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 42750000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365433 | 8202239555 |  | 8202204942#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P104/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 23552000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-20 | 2026-03-05 | 2026-03-05 | 2102365432 | 8202239554 |  | 8202204941#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P103/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 24386750 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365431 | 8202239553 |  | 8202204939#22_[PV] Penggantian Coupling | RU4-LOC2 | 021P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-4-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365460 | 8202239552 |  | 8202204897#22_052B104 Perbaikan Relay Bo | RU4-UTL | 052B104/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 5025296 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365449 | 8202239551 |  | 8202204896#22_052B104 Perbaikan Fitting | RU4-UTL | 052B104/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 21 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365448 | 8202239550 |  | 8202204895#22_052B103 Perbaikan Relay Bo | RU4-UTL | 052B103/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 5025296 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365447 | 8202239549 |  | 8202204893#22_052B102 Perbaikan Fitting | RU4-UTL | 052B102/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 21 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365446 | 8202239548 |  | 8202204892#22_052B103 Perbaikan Fitting | RU4-UTL | 052B103/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 21 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365445 | 8202239547 |  | 8202204890#22_052B102 Perbaikan Relay Bo | RU4-UTL | 052B102/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 946236 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365444 | 8202239546 |  | 8202204889#22_052B101 Perbaikan Relay Bo | RU4-UTL | 052B101/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 0 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365407 | 8202239545 |  | 8202204750#22_Penggantian 54TV309 | RU4-UTL | 54WS201/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/NR-6-C2H | 54675200 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-11-03 | 2102360976 | 8202234554 |  | 8202204615#RKA23__RKAP 2023 Ganti LT DI | RU4-FOC1 | 13LT017/00 | 50 WAMA | REL NMAT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 2640 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202234649 |  | 8202204603#RKA_PERB Oil Trip Burner Aux | RU4-RFCUTL |  | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/22/B6/RT-9-C2H | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360988 | 8202234778 |  | 8202204552#pengadaan Fuse heater CCR PL2 | RU4-FOC2 | 014E114-CB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365409 | 8202239544 |  | 8202204429#22_Pengadaan Press Gauge Area | RU4-REL |  | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-11-C2H | 34000040 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365443 | 8202239542 |  | 8202204326#22_052B101 Perbaikan Fitting | RU4-UTL | 052B101/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-6-C2H | 315786219 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360991 | 8202234560 |  | 8202204066#RKA22_Penggantian motor 022K1 | RU4-LOC2 | 022K101P2M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-3-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2027-01-29 | 2102361219 | 8202237477 |  | 8202203796#Perbaikan Woodward 505XT 051G | RU4-UTL | 051G103/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/25/B6/RTC-4-C2H | 100000 | 0 | MA5-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2027-01-05 | 2102365314 | 8202239541 |  | 8202203698#22_[CR] Penggantian Shaft dan | RU4-LOC1 | 23E8K-A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-7-C2H | 10801400 | 0 | MA1-ROT |  | TEGARPRAMUDY |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365441 | 8202239540 |  | 8202203663#22_Pengadaan PCV nitrogen di | RU4-RFCGTO | 47T573/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-11-C2H | 293252400 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365440 | 8202239539 |  | 8202203662#22_Pengadaan PCV Nitrogen di | RU4-RFCGTO | 47T571/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-11-C2H | 293252400 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365408 | 8202239538 |  | 8202203661#22_Penggantian selenoid 180XV | RU4-GTO | 180XV601A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/22/B6/RT-10-C2H | 104000000 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102360978 | 8202234656 |  | 8202203613#RKA_Pengadaan Motor 260E120M4 | RU4-LOC3 | 260E120M4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-5-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 | 2102364136 | 8202234824 |  | 8202203191#Pengerukan Under ground Sewer |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-11-03 | 2102366060 | 8202239537 |  | 8202202785#22_[PV] Pengadaan Kompressor | RU4-GTO | 180A601A1K2B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 12300000 | 0 | MA7-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-01-02 | 2026-01-02 | 2102366095 | 8202239536 |  | 8202202744#[PV] Peremajaan Pully Finfan | RU4-RFCGTO | 105E504A-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-14-C2H | 548600408 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361006 | 8202235118 |  | 8202202659#RKAP22_Pengadaan digitrip 10E | RU4-FOC1 | 10EE0308B-CB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365500 | 8202239535 |  | 8202202613#22_[BD] Gearbox Ngejammed 260 | RU4-LOC3 | 260K101-2BP2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-5-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365442 | 8202239534 |  | 8202202590#22_[CR] Perbaikan MLOP Gearbo | RU4-UTL | 053P201C-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-6-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365419 | 8202239533 |  | 8202202562#22_[PV] Pengadaan coupling 90 | RU4-SRU | 90P401B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-3-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365418 | 8202239532 |  | 8202202561#22_[PV] Pengadaan coupling 90 | RU4-SRU | 90P401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-3-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361208 | 8202237321 |  | 8202202288#AC Capacitor UPS 80EE0043 | RU4-KPC | 80EE0043-CB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-8-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 | 2102361209 | 8202237323 |  | 8202202287#AC Capacitor UPS 80EE0041 | RU4-KPC | 80EE0041-PNL/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/22/B6/RT-8-C2H | 0 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2027-01-05 | 2102365944 | 8202239531 |  | 8202201937#22_Filter Dust Control Unit 1 | RU4-RFCC | 101A501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-04 | 2026-06-02 | 2026-02-04 | 2026-03-12 | 2102364268 | 8202238077 |  | 8202201895#RUBBER LINING SCREEN PLATE PO | RU5-UTL | D5-CK-2-1/00 | 60 | CLSD NMAT PRC SETC | 5MR | D15/23/B6/RT-C2H | 0 | 0 | MA1-STA |  | JOYOPRATIKN |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-03 | 2026-02-13 | 2026-02-03 | 2026-12-03 | 2102361218 | 8202237476 |  | 8202201650#RKA22L_Recoating Volute 2nd 3 | RU4-RFCUTL | 156K502A/00 | 50 WASR | REL CSER NMAT PRC SETC | 4RR | D14/23/B6/RT-11-C2H | 1 | 0 | MA5-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-03-05 | 2102365501 | 8202239530 |  | 8202201486#22_[CR] [PV] Cooling Tower N2 |  |  | 60 | REL CSER MACM PRC SETC | 4RR | D14/22/B6/RT-8-C2H | 6720000 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K501 | 2026-02-03 | 2026-02-07 | 2026-02-03 | 2026-02-19 |  | 8202237475 |  | 8202201372#Selang Hidrolik Gangway Jetty | RU5-TBL | 22-GANGWAY-5BC/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/25/B6/RT-C2H | 35426012 | 0 | MA4-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235070 |  | 8202200375#Pekerjaan Pengukuran Peralata | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-06-03 | 2026-01-01 | 2026-01-01 |  | 8202234863 |  | 8202038344#KV Tambat Kapal Area SG |  |  | 60 | REL CNF PRT NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RAMADENY | 2026-06-08 | 2026-02-07 | PT02 |  | 3 | 2026-01-01 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202235377 | 8202235420 | 8202038288#Kontr.Vol Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 |  | 2026-02-03 | 2026-02-03 |  | 8202235598 | 8202238460 | 8202038105#Pekerjaan Kont. Vol Sipil ARe | RU3-CDGP |  | 50 | CRTD NMAT PRC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  |  |  |  | PT02 |  | 2 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | 8202235125 |  | 8202038076#KV Isolasi Area CDGP OM Plaju | RU3-CDGP |  | 60 | REL GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2102364230 | 8202235085 |  | 8202038074#KV Isolasi Area CDL UTL OM SG |  |  | 60 | REL GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA4-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-20 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202234973 |  | 8202038035#Pembayaran Kontr.Vol.Pemasang |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235331 | 8202235420 | 8202038027#Kontr.Vol Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235404 |  | 8202038026#Kontr.Vol Steam Leak Non Trap |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-07 | 2102365360 | 8202239529 |  | 8202037830#[BD] Penggantian Hidrolik Jac | RU4-LOC2 | 024S101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-7-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202235881 |  | 8202036634#Perbaikan Level Glass Boiler | RU4-UTL | 520B601/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR |  | 0 | 0 | MA5-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-06 | 2102365710 | 8202239528 |  | 8202035564#[PV] Perbaiki pompa 041P101B | RU4-TRML | 041P101B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-7-C2H | 11433501 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202234835 |  | 8202035219#Pengadaan Cap 3/4" di FOC II |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-01-02 | 2026-11-03 | 2102366061 | 8202239527 |  | 8202035030#[BD] Jammed Pompa 540P401B | RU4-UTL1 | 540P401B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 141747872 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 |  | 8202234478 |  | 8202034770#Pngadaan material Proof Coole | RU3-CDGP |  | 50 | REL CSER MACM PRC SETC | 3MR |  | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-13 | 2026-02-02 | 2026-02-02 | 2102360924 | 8202234418 |  | 8202034568#Vibrating screen (NRKAP) | RU3-PP | 23-ZS-2507/00 | 50 | REL CSER MACM PRC SETC | 3RR |  | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-11-03 | 2102360828 | 8202235017 |  | 8202034185#Pompa 71P1A Fail saat Beropea | RU4-TRML | 71P1A/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-07-23 | 2102365699 | 8202239526 |  | 8202031258#[PV] Pengadaan Coupling 024P1 | RU4-LOC2 | 024P103B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-7-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2026-08-05 | 2102365697 | 8202239525 |  | 8202031257#[PV] Pengadaan Coupling 024P1 | RU4-LOC2 | 024P103A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202236913 |  | 8202031204#Penggantian Check Valve 011P1 | RU4-FOC2 | 011P103B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR |  | 0 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2102364266 | 8202235477 |  | 8202030536#Kontr. Vol Perbaikan Sarana T |  |  | 60 | REL GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | RRAMADHANI |  | 2026-02-07 | PT02 |  | 3 | 2026-04-30 | PM |  | 045
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235632 |  | 8202030505#Cleaning Cooler&Cond. CD II, | RU3-CDGP |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 |  | 8202236425 |  | 8202030307#Penggantian tube inlet conv. | RU4-FOC2 | 011F101A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR |  | 76501000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-05-11 |  | 8202234021 |  | 8202029724#Ganti lampu picture TL easy d | RU6-HSC | SS-17/00 | 60 | REL CSER MACM PRC SETC | 6ER | D16/25/B6/RT-C2H | 1839743 | 0 | MA3-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2026-02-03 |  | 8202236428 |  | 8202029323#Penggantian tube 021E122B | RU4-LOC2 | 021E122B/00 | 60 | REL CSER MACM PRC SETC | 4MR |  | 582680000 | 0 | MA2-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K301 | 2026-02-02 | 2026-05-18 | 2026-01-02 | 2026-01-02 |  | 8202235285 |  | 8202028900#Kontrak Volume Cleaning & Gan | RU3-CDGP |  | 60 | TECO CNF GMCO NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | MULYONO701 | 2026-01-09 | 2026-02-07 | PT02 |  | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-20 | 2026-01-02 | 2026-11-03 | 2102366062 | 8202239524 |  | 8202028694#[CR] Perbaikan Jangka Pendek | RU4-LOC3 | 240S101A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 47018025 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 |  | 8202238040 |  | 8202028418#Kontr.Vol.Mekanik area Utara |  |  | 60 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 1 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K301 | 2026-02-04 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2102364267 | 8202238038 |  | 8202027835#Pengecatan Tangki PL-SG 24 Bu |  |  | 60 | CRTD NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 1 | 0 | MA1-STA |  | SAPBATCH |  |  | PT02 |  | 2 | 2026-02-04 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-23 | 2026-03-05 | 2027-02-23 | 2102365502 | 8202239523 |  | 8202027333#[CR] Penggantian Coupling 70P | RU4-K3LL | 70P2B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/23/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-10 | PT02 |  | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-01-02 | 2026-11-03 | 2102361135 | 8202236823 |  | 8202026890#Penggantian gland mech seal 3 | RU4-TRML | 33P1B/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-05-08 |  | 8202233199 |  | 8202026823#Perbaikan Control 16-LV-008 | RU6-RCC | 16-LV-008/00 | 60 | REL CSER NMAT PRC SETC | 6IR | D16/25/B6/RT-C2H | 0 | 0 | MA1-INT |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2027-01-11 |  | 8202235611 |  | 8202026555#Perbaikan pompa 017P106B mech | RU4-FOC2 | 017P106B/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR |  | 0 | 0 | MA2-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-07 | 2026-02-03 | 2026-02-03 |  | 8202235173 |  | 8202026270#Kontrak Volume Sipil Area 3 K |  |  | 60 | REL NMAT PRC SETC | 3MR | D13/25/B6/RT-2-D2H | 0 | 0 | MA3-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-04-24 | 2026-01-02 | 2026-12-22 | 2102360952 | 8202236940 |  | 8202025599#Penggantian Alop Pompa 37P101 | RU4-TRML | 37P101A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 90440000 | MA3-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-04-24 | 2026-01-02 | 2026-08-07 | 2102360953 | 8202236942 |  | 8202025597#Penggantian Alop Pompa 32P101 | RU4-TRML | 32P101A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 90440000 | MA3-ROT |  | YMOHAMMAD |  | 2026-02-07 | PT02 |  | 3 | 2026-01-02 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2027-02-08 |  | 8202234761 |  | 8202025357#STOP FOC I 2020_Pengadaan Mat | RU4-FOC1 | 15E4/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR |  | 2081452 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2027-02-08 |  | 8202234842 |  | 8202024876#Pengadaan 12PSV008 | RU4-FOC1 | 12K1B-P1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR |  | 3234 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2027-02-08 |  | 8202234844 |  | 8202024875#Pengadaan 12PSV006 | RU4-FOC1 | 12K1AP2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR |  | 3234 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2027-02-08 |  | 8202235875 |  | 8202024733#MLOP 13K1 B rusak | RU4-FOC1 | 13K1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR |  | 3234 | 0 | MA1-ROT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-01 | 2026-02-13 | 2025-11-11 | 2026-05-19 |  | 8202232742 |  | 8202024301#Retrofit Kontrol Sootblower 1 | RU6-RCC | 15-B-101/00 | 60 | REL NMAT PRC SETC | 6ER |  | 1536 | 0 | MA1-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2025-11-11 | PM |  | 004
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2027-02-15 |  | 8202236236 |  | 8202024062#Perbaikan Auto Titrator KEM |  |  | 50 WAMA | REL CSER NMAT PRC SETC | 4IR |  | 0 | 0 | WS-INT |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-13 | 2026-02-03 | 2027-02-08 |  | 8202236442 |  | 8202022990#Penggantian tip burner 11F-1 | RU4-FOC1 | 11F1/00 | 60 | REL CSER MACM PRC SETC | 4MR |  | 614271696 | 0 | MA1-STA |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-01 | 2026-02-14 | 2026-02-02 | 2026-09-22 |  | 8202232729 | 8202238033 | 8202022578#SWO BAU Mooring Hawser 12" | RU6-ITP | 41-A-101/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/25/B6/NR-C2H | 19800 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-02-02 | 2026-02-25 | 2026-01-02 | 2026-01-02 | 2102364265 | 8202235563 |  | 8202022471#Pekerjaan Kontrak NDT Tahun 2 |  |  | 50 | CRTD GMCO NMAT PRC | 3MR | D13/26/B6/RT-2-D2H | 0 | 0 | MA1-STA |  | RRAMADHANI |  |  | PT02 |  | 2 | 2026-01-02 | PM |  | 045
| K401 | 2026-02-02 | 2026-02-14 | 2026-02-03 | 2026-02-03 | 2102364228 | 8202235465 |  | 8202022266#Perbaikan Pulley FinFan 240E1 | RU4-LOC3 | 240E123/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER |  | 8700000 | 0 | MA4-LIS |  | SAPBATCH |  | 2026-02-11 | PT02 |  | 3 | 2026-02-03 | PM |  | 045
| K601 | 2026-02-04 | 2026-02-14 | 2026-02-04 | 2026-12-04 |  | 8202238033 |  | 8202022177#Penggaanti PO 3950005269 | RU6-ITP | 41-A-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/25/B6/NR-C2H | 493000000 | 0 | MA4-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2027-02-24 |  | 8202234371 |  | 8202018291#Pengadaan tube bundle assy 10 | RU4-RFCC |  | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/25/B6/RTC-12-C2H | 0 | 0 | MA6-STA |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-07-07 |  | 8202234042 |  | 8202013114#Bearing Motor 12-K-501AM | RU6-DHC | 12-K-501A-M/00 | 60 | REL CSER NMAT PRC SETC | 6ER | D16/25/B6/RT-C2H | 0 | 0 | MA2-LIS |  | SAPBATCH |  | 2026-02-07 | PT02 |  | 3 | 2026-02-02 | PM |  | 004
| K201 | 2026-03-12 | 2026-04-10 | 2026-03-12 | 2026-03-12 | 2102364557 | 8202241642 |  | 701-P 4A High Vibrasi | RU2-HCC | 701-P-4A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 9552698 | 9491092 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-04-10 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K601 | 2026-03-17 | 2026-05-20 | 2026-03-12 | 2026-08-04 | 2102366585 | 8202241789 |  | 6esertifikasi Boiler 52-B-101E | RU6-UTL | 52-B-101E/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 31967886 | 12960416 | MA4-STA |  | PUTRIMAMELLI |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K201 | 2026-03-03 | 2026-05-26 | 2026-04-01 | 2026-04-01 | 2102364418 | 8202239361 |  | 610-PM-202A (rewinding) | RU2-ITP | P-202A-M/00 | 60 | REL CSER GMPS MSPT PRC SETC | 2ER | D12/26/B6/RT-D2H | 10922628 | 6888306 | MA4-LIS |  | AZIZFATONI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K201 | 2026-05-07 | 2026-05-07 | 2026-05-12 | 2026-08-11 | 2102368581 | 8202243055 |  | 510-P-1A Refurbishment Unit Pompa | RU2-UTL | 510-P-01A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | MDSYAHPUTRA |  |  | PT02 | 3 | 2 | 2026-05-12 | PM |  | 003
| K201 | 2026-04-15 | 2026-06-18 | 2026-04-15 | 2026-04-15 | 2102366372 | 8202242455 |  | 410-P 2A Mech Seal Bocor | RU2-HCC | 410-P-2A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 58027683 | 56022350 | MA2-ROT |  | NURFADHILLA |  | 2026-05-04 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 003
| K201 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2102366326 | 8202241493 |  | 410-F1 Penggantian | RU2-HCC | 410-F-1A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA2-STA |  | STEVANEKOPP |  | 2026-03-09 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K201 | 2026-03-11 | 2026-03-26 | 2026-03-11 | 2026-03-11 | 2102364469 | 8202241586 |  | 410-E8 Bocor | RU2-HCC | 410-E-8/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MR | D12/26/B6/RT-D2H | 29934771 | 2675035 | MA2-STA |  | CHANRARD |  | 2026-03-11 | PT02 | 5 | 3 | 2026-03-11 | PM |  | 003
| K201 | 2026-04-22 | 2026-06-15 | 2026-04-22 | 2026-04-28 | 2102366394 | 8202242664 |  | 410 CM-1B Thermodial rusak | RU2-HCC | 410-CM-1B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 4420000 | 4420000 | MA2-INT |  | NURFADHILLA |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 005
| K501 | 2026-02-18 | 2026-03-05 | 2026-02-13 | 2026-04-30 | 2102364459 | 8202238942 |  | 3C G-3-25F vibrari tinggi | RU5-E15112 | G-3-25F/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 25560648 | 0 | MA3-ROT |  | ANDREAYR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-07-02 | 2102369010 | 8202243199 |  | 32-P-104 B- Perbaikan Mech Seal | RU6-HSC | 32-P-104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 11524465 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-13 | PT02 | 5 | 3 | 2026-05-13 | PM |  | 003
| K601 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-07-02 | 2102368949 | 8202243198 |  | 32-P-104 A - Perbaikan Mech Seal | RU6-HSC | 32-P-104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 11524465 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-05-13 | PT02 | 5 | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-04-02 | 2026-06-19 | 2026-04-02 | 2026-12-30 |  | 8202242047 | 8202241623 | 26L_Kontrak Jasa Tenaga Bantu Perb. Comp | RU4-LOC3 | 260K101B/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 100000 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-04-02 | PT02 | 4 | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-04-02 | 2026-06-19 | 2026-04-01 | 2026-12-30 | 2102367206 | 8202242048 |  | 26L_Base Plate Claus Air Blower 93K401A | RU4-SRU | 93K401A/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 100000 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 045
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102370140 | 8202244007 |  | 26_Transmitter 024FT-037 Rusak | RU4-LOC2 | 024FT037/00 | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 16800000 | 0 | MA2-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-03 | 2026-06-19 | 2026-06-19 | 2026-12-30 | 2102369224 | 8202243590 |  | 26_Tghn 3 Perbaikan Overhead Crane di Ar | RU4-RFCUTL |  | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 87500000 | 0 | MA5-LIS |  | FARIZSETYANA |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 045
| K401 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-12-30 | 2102364899 | 8202239302 |  | 26_TG Line B/L MP Steam 106-TG-031 Rusak | RU4-RFCGTO | 106TG-U106/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-11 | 2026-03-11 | 2026-12-30 | 2102364910 | 8202239303 |  | 26_TG Line B/L LP Steam 106-TG-034 Rusak | RU4-RFCGTO | 106TG-U106/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K401 | 2026-03-31 | 2026-05-12 | 2026-05-12 | 2026-12-22 | 2102366903 | 8202241979 |  | 26_Temp Indikator MCB 101-TI-242 Meraguk | RU4-RFCC | 101C521/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2102364829 | 8202239115 |  | 26_Tagihan Termin I Kabel Feeder 63EE111 |  |  | 50 | CLSD NCMP NMAT PRC | 4ER |  | 3800000000 | 0 | MA5-LIS |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-02-24 | PM |  | 045
| K401 | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-23 | 2102364801 | 8202239080 |  | 26_tagihan Perbaikan overspeed Protech G | RU4-REL |  | 50 | CLSD NCMP NMAT PRC | 4ER |  | 1298000000 | 0 | MA5-LIS |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-02-24 | PM |  | 045
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-09-29 | 2102366191 | 8202241771 |  | 26_surge arrester di 01SS11 | RU4-FOC2 | 01SS11/00 | 50 WAMA | CRTD CSER MACM PRC | 4ER |  | 15 | 0 | MA2-LIS |  | AKHMADIS77 |  |  | PT02 | 3 | 2 | 2026-03-16 | PM |  | 045
| K401 | 2026-05-18 | 2026-06-19 | 2026-05-18 | 2026-12-29 | 2102369001 | 8202243239 |  | 26_Slow Moving Perbaikan Level TX RFCC | RU4-RFCC | 101LI-U101/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 8 | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-03-03 | 2026-05-19 | 2026-05-13 | 2026-12-30 | 2102364447 | 8202239392 |  | 26_Service dan Refill Media 05SS-11 | RU4-UTL | 05SS11/00 | 50 WAMA | CLSD CSER MACM NCMP PRC | 4IR |  | 87279003 | 0 | MA5-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-05-19 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-24 | 2026-03-09 | 2026-12-30 | 2102364631 | 8202241377 |  | 26_rusak spring hanger SH84008 84R201A | RU4-KPC | 84R201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-STA |  | TEGARPRAMUDY |  | 2026-03-09 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-04-13 | 2026-04-21 | 2026-04-17 | 2026-12-29 | 2102367751 | 8202242361 |  | 26_Rotameter 84FT363 dan 84FT382 rusak 4 | RU4-KPC | 84FT363/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-12 | 2026-03-02 | 2026-12-30 | 2102354139 | 8202239019 |  | 26_RKU Retrofit AVR 051G102 | RU4-UTL | 051G102/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 100000 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-02-25 | 2026-05-19 | 2026-03-02 | 2026-12-30 | 2102364946 | 8202239157 |  | 26_Retrofit Foam Monitor Dermaga & CIB A | RU4-TRML | 72FMMOV101AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-LIS |  | FARIZSETYANA |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 004
| K401 | 2026-03-17 | 2026-03-31 | 2026-03-04 | 2026-03-04 | 2102365294 | 8202241800 |  | 26_Retrofit Foam Monitor CIB I & II A.70 |  |  | 50 | CLSD NCMP NMAT PRC | 4ER |  | 3000000000 | 0 | MA3-LIS |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-31 | PM |  | 045
| K401 | 2026-04-27 | 2026-06-02 | 2026-05-11 | 2026-12-29 | 2102367975 | 8202242759 |  | 26_Regulator Selector Rusak 140AT004 | RU4-GTO | 140C602/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 3 | 0 | MA7-INT |  | DWIHIZZKI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-18 | 2026-06-10 | 2026-12-29 | 2102369654 | 8202243645 |  | 26_Regulator 91KV322C | RU4-SRU | 91KV322C/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 3690000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-18 | 2026-06-10 | 2026-12-29 | 2102369653 | 8202243644 |  | 26_Regulator 91KV322B | RU4-SRU | 91KV322B/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 3690000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-18 | 2026-06-10 | 2026-12-28 | 2102369652 | 8202243643 |  | 26_Regulator 91KV322A | RU4-SRU | 91KV322A/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 3690000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-04-08 | 2026-06-19 | 2026-04-08 | 2026-12-30 | 2102367594 | 8202242224 |  | 26_Refill tabung FSS FM-200 05BD-102 | RU4-UTL | 005BD102/00 | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 382824000 | 0 | MA2-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-04-08 | PM |  | 003
| K401 | 2026-02-24 | 2026-03-06 | 2026-02-24 | 2026-05-21 | 2102364396 | 8202239105 |  | 26_Pulley motor KPC rusak |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 163866580 | 0 | MA4-LIS |  | YMOHAMMAD |  | 2026-02-25 | PT02 | 5 | 3 | 2026-02-24 | PM |  | 045
| K401 | 2026-02-18 | 2026-05-19 | 2026-02-18 | 2026-06-30 | 2102364065 | 8202238932 |  | 26_Prbaikan Motor 63A501CM2M | RU4-RFCUTL | 63A501C-M2/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 559700 | 559700 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-02-18 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-02-06 | 2026-03-12 | 2026-03-12 | 2026-12-30 | 2102357494 | 8202238720 |  | 26_Power Supp & Transmitter 140TV008 Rus | RU4-GTO | 140TV008A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 3 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-02-09 | 2026-04-24 | 2026-02-10 | 2026-12-30 | 2102355815 | 8202238796 |  | 26_PI di line disch pompa rusa | RU4-KPC | 80P202A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 66693102 | 0 | MA4-INT |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 5 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-16 | 2026-03-16 | 2026-12-30 | 2102364915 | 8202239292 |  | 26_PG Rusak 47-PG-091 | RU4-RFCGTO | 47PG-U47/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 2 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-12 | 2026-03-06 | 2026-12-30 | 2102364897 | 8202239300 |  | 26_PG Line B/L Plant Air 106-PG-061 Rusa | RU4-RFCGTO | 106PG-U106/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1370895 | 0 | MA7-INT |  | YMOHAMMAD |  | 2026-03-06 | PT02 | 2 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-12 | 2026-03-06 | 2026-12-30 | 2102364911 | 8202239304 |  | 26_PG Line B/L MPC 6" 107-PG-050 Rusak | RU4-RFCGTO | 107PG-U107/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1203448 | 0 | MA7-INT |  | YMOHAMMAD |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-02 | 2026-05-21 | 2026-03-06 | 2026-12-30 | 2102364898 | 8202239301 |  | 26_PG Line B/L MP Steam 106-PG-049 Rusak | RU4-RFCGTO | 106PG-U106/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1219906 | 0 | MA7-INT |  | YMOHAMMAD |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-10-29 | 2102354733 | 8202239436 |  | 26_Perlengkapan Kabel Power Mixer 34M1B |  |  | 01 WENG | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA3-LIS |  | DHANANGDH |  |  | PT02 | 5 | 2 | 2026-03-04 | PM |  | 045
| K401 | 2026-03-06 | 2026-04-24 | 2026-03-06 | 2026-10-29 | 2102355232 | 8202241330 |  | 26_perbaikan VMS 86K201 | RU4-KPC | 86K201/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 545915667 | 153385667 | MA4-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-12-29 | 2102368172 | 8202242758 |  | 26_Perbaikan vibrasi sensor dan Speed | RU4-UTL | 051G103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 91875007 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-12-29 | 2102366787 | 8202241945 |  | 26_Perbaikan Valve 156UV706A | RU4-RFCUTL | 156SV-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 7072787 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-17 | 2026-04-15 | 2026-11-12 | 2102367560 | 8202242297 |  | 26_Perbaikan transmitter 13FT015 | RU4-FOC1 | 13FT015/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 18950000 | 18950000 | MA1-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-17 | 2026-04-15 | 2026-11-19 | 2102367561 | 8202242296 |  | 26_Perbaikan transmitter 12PDT008 | RU4-FOC1 | 12PDT008/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 18950000 | 18950000 | MA1-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-28 | 2026-04-15 | 2026-11-19 | 2102367562 | 8202242295 |  | 26_Perbaikan transmitter 11FT056 | RU4-FOC1 | 11FT056/00 | 60 | TECO CNF GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 19250000 | 19250000 | MA1-INT |  | SAPBATCH | 2026-04-28 | 2026-04-17 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-03-17 | 2026-05-22 | 2026-05-19 | 2026-12-22 | 2102366424 | 8202241808 |  | 26_Perbaikan Transmitter 101TI281 (Temp | RU4-RFCC | 101V532/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-10-29 | 2102366513 | 8202241788 |  | 26_Perbaikan Trafo Ign Brner No.4 52B3 | RU4-UTL | 52B3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | DHANANGDH |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-10-29 | 2102366512 | 8202241798 |  | 26_Perbaikan Trafo Ign Brner No.2 52B3 | RU4-UTL | 52B3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | DHANANGDH |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-04-06 | 2026-04-24 | 2026-04-10 | 2026-11-26 | 2102367141 | 8202242106 |  | 26_Perbaikan Tombol Reset 180PSL633A | RU4-GTO | 180A601/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | TEGARPRAMUDY |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-03 | 2026-03-02 | 2026-12-30 | 2102364413 | 8202239068 |  | 26_Perbaikan switch 156UV754A & 156UV755 | RU4-RFCUTL | 156ZS-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 2 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-02-25 | 2026-06-18 | 2026-02-25 | 2026-12-30 | 2102364961 | 8202239163 |  | 26_Perbaikan Steam Trap Area GTO | RU4-RFCC | 105-WT0828-3-4/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/NR-12-C2H | 390000000 | 390000000 | MA7-STA |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 045
| K401 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-12-30 | 2102367163 | 8202242026 |  | 26_Perbaikan Steam Trace line Block Mode |  |  | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 99000000 | 99000000 | MA3-STA |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 4 | 3 | 2026-04-02 | PM |  | 045
| K401 | 2026-06-22 | 2026-06-23 | 2026-06-22 | 2026-12-30 | 2102369557 | 8202244026 |  | 26_perbaikan Steam area OM 60 & NBM |  |  | 50 | CRTD CSER MACM PRC | 4MR |  | 66000000 | 0 | MA3-STA |  | WAHYUCATUR |  |  | PT02 | 4 | 2 | 2026-06-22 | PM |  | 045
| K401 | 2026-02-23 | 2026-05-04 | 2026-05-04 | 2026-12-29 | 2102364415 | 8202239072 |  | 26_Perbaikan SOV 156UV701A, 703A | RU4-RFCUTL | 156UY-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 33728002 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-05-04 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-13 | 2026-05-26 | 2026-05-26 | 2026-12-30 | 2102368946 | 8202243196 |  | 26_Perbaikan solenoide valve 14XV561 | RU4-FOC1 | 14XV561/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-05-13 | 2026-05-26 | 2026-05-26 | 2026-12-30 | 2102368947 | 8202243195 |  | 26_Perbaikan solenoide valve 14XV540 | RU4-FOC1 | 14XV540/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-10-22 | 2102367960 | 8202242498 |  | 26_Perbaikan Solenoid Valve 102UV103 | RU4-RFCC | 102UV103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 47300000 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-14 | 2026-06-05 | 2026-05-22 | 2026-12-22 | 2102367764 | 8202242413 |  | 26_Perbaikan Solenoid Automator 220V 91K | RU4-SRU | 91K401B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | DWIHIZZKI |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-04-14 | 2026-06-05 | 2026-05-22 | 2026-12-22 | 2102367765 | 8202242415 |  | 26_Perbaikan Solenoid Automator 220V 91K | RU4-SRU | 91K402B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | DWIHIZZKI |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-04-13 | 2026-06-04 | 2026-05-22 | 2026-12-29 | 2102367526 | 8202242373 |  | 26_Perbaikan Solenoid 220VAC11K401A | RU4-FOC1 | 11K401A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | DWIHIZZKI |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-04-13 | 2026-06-04 | 2026-05-22 | 2026-12-29 | 2102367527 | 8202242374 |  | 26_Perbaikan Solenoid 220VAC 11K401B | RU4-FOC1 | 11K401B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | DWIHIZZKI |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-02-23 | 2026-04-24 | 2026-04-23 | 2026-12-29 | 2102364414 | 8202239069 |  | 26_Perbaikan solenoid 156UV702A | RU4-RFCUTL | 156UY-U156/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-12 | 2026-12-30 | 2102355690 | 8202238727 |  | 26_Perbaikan selenoid SOV 47HV304 & 47HV | RU4-TRML | 47HV304/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 2 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-09 | 2026-03-09 | 2026-12-30 | 2102357038 | 8202239432 |  | 26_Perbaikan RTD 14TI_325B | RU4-FOC1 | 14K602B/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 11334500 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-27 | 2026-03-06 | 2026-02-27 | 2026-12-30 | 2102364953 | 8202239267 |  | 26_Perbaikan Redundancy Module PLC IPAL | RU4-SRU | YIC9101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-06 | 2026-03-05 | 2026-09-29 | 2102364412 | 8202239220 |  | 26_Perbaikan pwr supply positioner 152TV | RU4-RFCUTL | 152TV032/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-06-03 |  | 2026-04-24 | 2026-04-24 | 2102368343 | 8202243583 |  | 26_Perbaikan push button LCS 106P501 | RU4-RFCGTO | 106P501A/00 | 01 WENG | CRTD CSER NMAT PRC | 4ER | D14/XX/B6/RT-C2NH | 0 | 0 | MA7-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-04-24 | PM |  | 045
| K401 | 2026-03-12 | 2026-04-16 | 2026-03-12 | 2026-12-22 | 2102366247 | 8202241609 |  | 26_Perbaikan Pulley Motor 102E517AM2 | RU4-RFCC | 102E517AM2/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 83278570 | 60678571 | MA6-LIS |  | WAHYUCATUR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-02-12 | 2026-03-06 | 2026-02-19 | 2026-08-27 | 2102364126 | 8202238901 |  | 26_Perbaikan Press Gauge Range 60kg RFCC | RU4-RFCC | 101F503/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 13286140 | 13286140 | MA6-INT |  | YMOHAMMAD |  | 2026-02-26 | PT02 | 8 | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-02-12 | 2026-04-24 | 2026-02-12 | 2026-08-27 | 2102364127 | 8202238898 |  | 26_Perbaikan Press Gauge Range 40kg RFCC | RU4-RFCC | 101F503/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 24398123 | 6099531 | MA6-INT |  | YMOHAMMAD |  | 2026-02-18 | PT02 | 8 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-02-12 | 2026-04-24 | 2026-02-19 | 2026-08-27 | 2102364128 | 8202238895 |  | 26_Perbaikan Press Gauge Range 25kg RFCC | RU4-RFCC | 101F503/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 27110681 | 6777670 | MA6-INT |  | YMOHAMMAD |  | 2026-02-26 | PT02 | 8 | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-02-12 | 2026-03-06 | 2026-02-12 | 2026-08-26 | 2102364129 | 8202238894 |  | 26_Perbaikan Press Gauge Range 16kg RFCC | RU4-RFCC | 101F503/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 13708954 | 13708954 | MA6-INT |  | YMOHAMMAD |  | 2026-02-18 | PT02 | 8 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-02-12 | 2026-04-24 | 2026-02-12 | 2026-08-27 | 2102364240 | 8202238896 |  | 26_Perbaikan Press Gauge Range 10kg RFCC | RU4-RFCC | 101F503/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 12034482 | 6017241 | MA6-INT |  | YMOHAMMAD |  | 2026-02-18 | PT02 | 8 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-02-12 | 2026-03-06 | 2026-02-12 | 2026-08-27 | 2102364125 | 8202238899 |  | 26_Perbaikan Press Gauge Range 100kg RFC | RU4-RFCC | 101F503/00 | 60 | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 6309835 | 8318835 | MA6-INT |  | YMOHAMMAD |  | 2026-02-18 | PT02 | 8 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-12-30 | 2102366627 | 8202241743 |  | 26_Perbaikan Positioner Assy 101FV062 | RU4-RFCC | 101FV062/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 101000000 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-21 | 2026-06-15 | 2026-12-30 | 2102368610 | 8202243860 |  | 26_Perbaikan Perpipaan Rutin MA-6 2026 | RU4-REL |  | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 291 | 0 | MA6-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 045
| K401 | 2026-02-25 | 2026-05-13 | 2026-03-02 | 2026-12-30 | 2102357843 | 8202239153 |  | 26_Perbaikan MOV Area OM 60 | RU4-TRML | 32MOV102-30/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 100 | 0 | MA3-LIS |  | FARIZSETYANA |  | 2026-03-02 | PT02 | 5 | 3 | 2026-03-02 | PM |  | 004
| K401 | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-12-21 | 2102366649 | 8202243029 |  | 26_Perbaikan Motor Mesin Bubut Workshop | RU4-WS | 037BD101-MCT/00 | 50 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-15-C2H | 29111126 | 29111126 | WS-LIS |  | WAHYUCATUR |  | 2026-05-07 | PT02 | 4 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-19 | 2026-05-13 | 2026-08-24 | 2102368854 | 8202243176 |  | 26_perbaikan motor EX 54P1BP2M | RU4-UTL | 54P1B/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 190300 | 190300 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-05-13 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-04-09 | 2026-06-09 | 2026-04-09 | 2026-11-30 | 2102367224 | 8202242245 |  | 26_Perbaikan motor 63P2AM | RU4-UTL | 63P2AM/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 28177300 | 28177300 | MA5-LIS |  | SAPBATCH | 2026-04-10 | 2026-04-09 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 045
| K401 | 2026-04-15 | 2026-05-21 | 2026-04-15 | 2026-07-20 | 2102367933 | 8202242445 |  | 26_Perbaikan Motor 63P1CM | RU4-TRML | 63P1C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 28397467 | 0 | MA5-LIS |  | YMOHAMMAD |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-03-30 | 2026-05-19 | 2026-03-30 | 2026-12-29 | 2102366924 | 8202241938 |  | 26_Perbaikan motor 63A502P1AM | RU4-RFCUTL | 63A502P1A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 128200 | 128200 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-03-31 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-04-07 | 2026-06-13 | 2026-04-08 | 2026-08-12 | 2102367465 | 8202242168 |  | 26_perbaikan motor 57P201BM |  |  | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1224000 | 1224000 | MA5-LIS |  | SAPBATCH | 2026-04-14 | 2026-04-07 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-12-30 | 2102366780 | 8202242242 |  | 26_Perbaikan Motor 56K102 | RU4-UTL | 56K102/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 100000 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-02-18 | 2026-04-30 | 2026-02-18 | 2026-06-30 | 2102364056 | 8202238931 |  | 26_Perbaikan motor 54WS201P3M | RU4-UTL | 54WS201/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 11260850 | 11260850 | MA5-LIS |  | AHMADZAENURI | 2026-04-30 | 2026-02-18 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 045
| K401 | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-07-13 | 2102367226 | 8202242075 |  | 26_Perbaikan motor 54P2CM | RU4-UTL | 54P2CM/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1638750 | 1638750 | MA5-LIS |  | AHMADZAENURI | 2026-04-30 | 2026-04-06 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-30 | 2026-04-06 | 2026-07-13 | 2102367225 | 8202242076 |  | 26_Perbaikan motor 54P2AP2M | RU4-UTL | 54P2A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 156300 | 156300 | MA5-LIS |  | AHMADZAENURI | 2026-04-30 | 2026-04-06 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-03-17 | 2026-05-19 | 2026-03-17 | 2026-06-22 | 2102366682 | 8202241780 |  | 26_Perbaikan motor 54P1BP2M | RU4-UTL | 54P1B/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 190300 | 190300 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-03-17 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-19 | 2026-05-08 | 2026-08-26 | 2102368627 | 8202243084 |  | 26_Perbaikan Motor 54P1AP2M | RU4-UTL | 54P1A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C1H | 190300 | 190300 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-05-08 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-02-18 | 2026-04-30 | 2026-02-18 | 2026-04-09 | 2102364276 | 8202238929 |  | 26_Perbaikan motor 54E201FM | RU4-UTL | 54E201FM/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1021700 | 1021700 | MA5-LIS |  | AHMADZAENURI | 2026-04-30 | 2026-02-18 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 045
| K401 | 2026-03-12 | 2026-05-19 | 2026-03-12 | 2026-07-30 | 2102366518 | 8202241612 |  | 26_perbaikan motor 54E201EM | RU4-UTL | 54E201A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1021700 | 1021700 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-03-12 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-04-16 | 2026-05-19 | 2026-04-17 | 2026-07-30 | 2102367972 | 8202242478 |  | 26_perbaikan motor 54E201BM |  |  | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1021700 | 1021700 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-05-11 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-06-11 | 2026-06-21 | 2026-06-11 | 2026-12-22 | 2102369824 | 8202243758 |  | 26_Perbaikan Motor 53P2AM | RU4-UTL | 53P2AM/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 53664188 | 53664188 | MA5-LIS |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 045
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 2026-08-20 | 2102369170 | 8202243292 |  | 26_Perbaikan Motor 52B2KBM | RU4-UTL | 52B2KBM/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 138200 | 138200 | MA5-LIS |  | AHMADZAENURI | 2026-05-20 | 2026-05-19 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 045
| K401 | 2026-03-03 | 2026-05-24 | 2026-03-03 | 2026-08-27 | 2102365228 | 8202239386 |  | 26_perbaikan motor 510G301A1M |  |  | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 156300 | 156300 | MA5-LIS |  | SAPBATCH | 2026-03-25 | 2026-03-04 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 045
| K401 | 2026-03-30 | 2026-04-23 | 2026-03-30 | 2026-12-29 | 2102366900 | 8202241934 |  | 26_Perbaikan motor 47P-101BM | RU4-TRML | 47P101BM/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 1987300 | 1987300 | MA1-LIS |  | FARIZSETYANA |  | 2026-03-31 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K401 | 2026-03-31 |  | 2026-03-31 | 2026-07-30 | 2102365012 | 8202241970 |  | 26_Perbaikan motor 47P-101BM | RU4-FOC1 | 14K602AM-P2M/00 | 50 WAMA | CRTD MACM PRC | 4ER |  | 231700 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-03-31 | PM |  | 003
| K401 | 2026-02-27 | 2026-04-06 | 2026-02-27 | 2026-12-30 | 2102365041 | 8202239246 |  | 26_Perbaikan Motor 180A601K1 Servis | RU4-GTO | 180A601K1AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 100000 | 0 | MA7-LIS |  | WAHYUCATUR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 004
| K401 | 2026-02-18 | 2026-05-24 | 2026-02-18 | 2026-06-30 | 2102364066 | 8202238930 |  | 26_Perbaikan Motor 157P503 | RU4-RFCUTL | 157P503M/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 463400 | 463400 | MA5-LIS |  | SAPBATCH | 2026-03-25 | 2026-02-18 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 045
| K401 | 2026-03-03 | 2026-04-30 | 2026-03-03 | 2026-08-27 | 2102365131 | 8202239389 |  | 26_perbaikan motor 154A505CM2M | RU4-RFCUTL | 154A505C-M2/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 124234 | 123896 | MA5-LIS |  | AHMADZAENURI | 2026-04-30 | 2026-03-11 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 045
| K401 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-08-24 | 2102369263 | 8202243504 |  | 26_perbaikan motor 154A503P1AM | RU4-RFCUTL | 154A504/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 1308900 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 045
| K401 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-07-20 | 2102367897 | 8202242449 |  | 26_perbaikan motor 153A501BK1M | RU4-RFCUTL | 153A501A-K1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 13700000 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-04-17 | 2026-05-19 | 2026-04-17 | 2026-07-20 | 2102367976 | 8202242543 |  | 26_perbaikan motor 152P502CM | RU4-RFCUTL |  | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 902137 | 902137 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-04-17 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-03-31 |  | 2026-03-31 | 2026-12-29 | 2102364977 | 8202241971 |  | 26_PERBAIKAN MOTOR 14P611 | RU4-FOC1 | 14P611M/00 | 50 WAMA | CRTD MACM PRC | 4ER |  | 17015000 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-03-31 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-08-31 | 2102367605 | 8202242244 |  | 26_Perbaikan Motor 140E607 LBM | RU4-GTO | 140E607L-B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 1194650 | 0 | MA7-LIS |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-08-31 | 2102367604 | 8202242243 |  | 26_Perbaikan Motor 140E607 LAM | RU4-GTO | 140E607L-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 1194650 | 0 | MA7-LIS |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-03-31 | 2026-04-23 | 2026-03-31 | 2026-06-29 | 2102364810 | 8202241972 |  | 26_Perbaikan motor 11P10AM | RU4-FOC1 | 11P10AM/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 1195300 | 1195300 | MA1-LIS |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-04-10 | 2026-06-13 | 2026-04-10 | 2026-07-13 | 2102367554 | 8202242340 |  | 26_Perbaikan Motor 110P502B | RU4-RFCUTL | 110P502BM/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 463400 | 463400 | MA5-LIS |  | SAPBATCH | 2026-04-14 | 2026-04-10 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 045
| K401 | 2026-04-10 | 2026-06-13 | 2026-04-10 | 2026-07-13 | 2102367553 | 8202242339 |  | 26_Perbaikan Motor 110P502A | RU4-RFCUTL | 110P502AM/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 463400 | 463400 | MA5-LIS |  | SAPBATCH | 2026-04-14 | 2026-04-10 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 045
| K401 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-12-30 | 2102356571 | 8202239028 |  | 26_Perbaikan Motor 105P506 AM | RU4-RFCGTO | 105P506AM/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 412000 | 0 | MA7-LIS |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 045
| K401 | 2026-03-25 | 2026-05-22 | 2026-03-25 | 2026-12-21 | 2102366841 | 8202241874 |  | 26_Perbaikan Motor 063P101CM | RU4-UTL | 63P101CM/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 334225111 | 167112556 | MA5-LIS |  | WAHYUCATUR | 2026-05-19 | 2026-03-25 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-18 | 2026-06-05 | 2026-12-22 | 2102369559 | 8202243666 |  | 26_perbaikan motor 054WS103P4BM |  |  | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 125600 | 125600 | MA5-LIS |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-05 | PM |  | 045
| K401 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-11-30 | 2102368295 | 8202242828 |  | 26_Perbaikan Motor 054WS103P3M | RU4-UTL | 054WS103P3M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1195300 | 0 | MA5-LIS |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K401 | 2026-04-29 | 2026-06-03 | 2026-04-29 | 2026-11-30 | 2102368294 | 8202242827 |  | 26_Perbaikan Motor 054WS102P3M | RU4-UTL | 054WS102P3M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 2712006 | 2712005 | MA5-LIS |  | AHMADZAENURI | 2026-06-03 | 2026-04-30 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 045
| K401 | 2026-04-17 | 2026-05-19 | 2026-04-17 | 2026-07-20 | 2102368082 | 8202242542 |  | 26_Perbaikan motor 054WS101P3M | RU4-UTL | 054WS101P3M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1195300 | 1195300 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-04-17 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-05-26 | 2026-05-29 | 2026-05-26 | 2026-08-24 | 2102369286 | 8202243501 |  | 26_Perbaikan motor 054WS101P3M | RU4-UTL | 054WS101P3M/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 2360124 | 2360124 | MA5-LIS |  | AHMADZAENURI | 2026-05-29 | 2026-05-26 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 045
| K401 | 2026-06-05 | 2026-06-20 | 2026-06-05 | 2026-12-22 | 2102369676 | 8202243665 |  | 26_Perbaikan motor 054WS101P3M | RU4-UTL | 054WS101P3M/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1060500 | 1060500 | MA5-LIS |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-05 | PM |  | 045
| K401 | 2026-04-29 | 2026-05-19 | 2026-04-29 | 2026-11-30 | 2102368297 | 8202242826 |  | 26_Perbaikan Motor 052P302AM | RU4-UTL | 052P302A/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1315550 | 1315550 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-04-30 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-05-26 | 2026-05-29 | 2026-05-26 | 2026-08-24 | 2102369285 | 8202243500 |  | 26_Perbaikan motor 052E101M2M | RU4-UTL | 052E101M2/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 823400 | 823400 | MA5-LIS |  | AHMADZAENURI | 2026-05-29 | 2026-05-26 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 045
| K401 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 2026-12-29 | 2102368768 | 8202243116 |  | 26_Perbaikan Modul Flame Relay Control | RU4-GTO | 120F601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-06 | 2026-03-05 | 2026-09-29 | 2102364275 | 8202239221 |  | 26_Perbaikan LT 52LIC006 (52T2) | RU4-UTL | 52T2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 18083334 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-04-29 | 2026-05-21 | 2026-03-03 | 2026-12-08 | 2102367161 | 8202242825 |  | 26_perbaikan LPS Area OM 60 NBM | RU4-TRML | 42TF2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 181755230 | 181755230 | MA3-LIS |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-05-13 | 2026-06-03 | 2026-05-26 | 2026-12-30 | 2102368985 | 8202243192 |  | 26_Perbaikan level transmitter 14LT253 | RU4-FOC1 | 14LT253/00 | 60 | REL MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 18970981 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-05-13 | 2026-06-03 | 2026-05-26 | 2026-12-30 | 2102368984 | 8202243191 |  | 26_Perbaikan level transmitter 14LT252 | RU4-FOC1 | 14LT252/00 | 60 | REL MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 18970981 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-04-20 | 2026-12-29 | 2102367529 | 8202242375 |  | 26_Perbaikan LCD 11K401B | RU4-FOC1 | 11K401B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 2 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-06-03 |  | 2026-04-02 | 2026-04-02 | 2102367212 | 8202243584 |  | 26_Perbaikan Lampu Penerangan Area GTO | RU4-REL |  | 01 WENG | CRTD CSER NMAT PRC | 4ER | D14/XX/B6/RT-C2NH | 0 | 0 | MA7-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-04-02 | PM |  | 045
| K401 | 2026-05-26 | 2026-06-10 | 2026-05-26 | 2026-12-21 | 2102369384 | 8202243506 |  | 26_Perbaikan Lampu Penerangan A.500 | RU4-UTL | 590K1M/00 | 60 | TECO CNF CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 600000 | 0 | MA5-LIS |  | AHMADZAENURI | 2026-06-10 | 2026-05-26 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 045
| K401 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-08-27 | 2102364533 | 8202239425 |  | 26_Perbaikan Lampu Indikator On/Off 140P | RU4-GTO | 140P604B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | DHANANGDH |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-08-27 | 2102364534 | 8202239427 |  | 26_Perbaikan Lampu Indikator On/Off 140P | RU4-GTO | 140P608A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | DHANANGDH |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-02-23 |  | 2026-02-02 | 2026-02-02 | 2102355116 | 8202239030 |  | 26_Perbaikan Lampu Area GTO | RU4-REL |  | 01 WENG | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA7-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-04 | 2026-03-03 | 2026-03-03 | 2102365212 | 8202239357 |  | 26_Perbaikan kabel intertriping 10EE0310 | UTL-UP4 | 10EE0310AB/00 | 50 | CRTD NMAT PRC | 4ER |  | 4000000000 | 0 | MA1-LIS |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-03-03 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-11-19 | 2102367925 | 8202242497 |  | 26_Perbaikan Indikator Seal Air Fan COB | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 6 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-07 |  | 2026-04-08 | 2026-07-30 | 2102367447 | 8202242167 |  | 26_Perbaikan heater dryer 156A502A | RU4-RFCUTL | 156A502A/00 | 50 WAMA | CRTD CSER MACM PRC | 4ER |  | 1875000000 | 0 | MA5-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-04-08 | PM |  | 045
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102364022 | 8202238825 |  | 26_Perbaikan Flame Relay 14BA-210M | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102364021 | 8202238828 |  | 26_Perbaikan Flame Relay 14BA-210K | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102364020 | 8202238829 |  | 26_Perbaikan Flame Relay 14BA-210J | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102364009 | 8202238831 |  | 26_Perbaikan Flame Relay 14BA-210I | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-03 | 2026-11-26 | 2102364008 | 8202238824 |  | 26_Perbaikan Flame Relay 14BA-210H | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102364007 | 8202238826 |  | 26_Perbaikan Flame Relay 14BA-210D | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102364025 | 8202238827 |  | 26_Perbaikan Flame Relay 14BA-210B | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102364024 | 8202238830 |  | 26_Perbaikan Flame Relay 14BA-210A | RU4-FOC1 | 14LCPSF602FR/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-21 | 2026-04-01 | 2027-01-04 | 2102367233 | 8202243371 |  | 26_Perbaikan Fire Alarm Area 70 | RU4-TRML | 70PVN3/00 | 50 | CRTD CSER NMAT PRC | 4IR |  | 2000000000 | 0 | MA3-INT |  | DWIHIZZKI |  |  | PT02 | 3 | 2 | 2026-04-01 | PM |  | 003
| K401 | 2026-04-16 | 2026-05-19 | 2026-04-17 | 2026-07-30 | 2102367932 | 8202242477 |  | 26_Perbaikan Fan motor 560K301 | RU4-UTL | 560K301/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 555000 | 555000 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-04-16 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 045
| K401 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-11-30 | 2102367416 | 8202242187 |  | 26_Perbaikan fan motor 140P610A | RU4-GTO | 140P610A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 045
| K401 | 2026-04-08 | 2026-04-30 | 2026-04-08 | 2026-09-29 | 2102364461 | 8202242185 |  | 26_Perbaikan Elevator 011S104 CDU II | RU4-FOC2 | 011S104/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4ER | D14/25/B6/RTC-2-C2H | 110 | 0 | MA2-LIS |  | AKHMADIS77 |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 045
| K401 | 2026-03-16 | 2026-04-24 | 2026-03-16 | 2026-12-30 | 2102366307 | 8202241733 |  | 26_Perbaikan Discharge Valve 108K501 | RU4-RFCGTO | 108K501A-T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 3 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 045
| K401 | 2026-06-03 | 2026-06-20 | 2026-06-03 | 2026-11-30 | 2102364017 | 8202243582 |  | 26_Perbaikan Coupling Motor 42P101A | RU4-TRML | 42P101A/00 | 50 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-LIS |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 045
| K401 | 2026-02-09 | 2026-02-18 | 2026-02-12 | 2026-08-26 | 2102363553 | 8202238785 |  | 26_Perbaikan CEMS RFCC - SO2 T100 | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-02-18 | PT02 | 8 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-03-16 | 2026-04-09 | 2026-04-09 | 2026-12-29 | 2102366423 | 8202241751 |  | 26_Perbaikan Cat.Hopper - PDI Dust Colle | RU4-RFCC | 101V501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 35233290 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-06-03 |  | 2026-06-03 | 2026-06-12 | 2102366635 | 8202243603 |  | 26_Perbaikan ARC pompa 052P102C |  |  | 50 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA5-STA |  |  |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 045
| K401 | 2026-02-09 | 2026-02-26 | 2026-02-26 | 2026-12-30 | 2102353531 | 8202238794 |  | 26_Perbaikan Air Latch SOV F.O BN-2 052B | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 36300000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-09 | 2026-02-26 | 2026-02-26 | 2026-12-30 | 2102353532 | 8202238793 |  | 26_Perbaikan Air Latch SOV F.G BN-2 052B | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 36300000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-10-05 | 2102357675 | 8202239520 |  | 26_Perbaikan 91LV-112 | RU4-SRU | 91LV112/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 4 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-03 | 2026-06-21 | 2026-06-15 | 2026-12-30 | 2102364057 | 8202239393 |  | 26_Perbaikan 560UV855 SOV Inlet 560DR601 | RU4-UTL | 560D601/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-12-29 | 2102368401 | 8202242948 |  | 26_Perbaikan 102LT020 ABC & 102SI643 | RU4-RFCC | 102LT-U102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 149189626 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-11-19 | 2102367928 | 8202242504 |  | 26_Perbaikan 101PDG891 (Diverter valve) | RU4-RFCC | 101A515/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 2 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-12-29 | 2102369130 | 8202243475 |  | 26_Perbaikan 101LIC214 - Power Supply Co | RU4-RFCC | 101LT214/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 50000000 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-25 | 2026-06-08 | 2026-05-25 | 2026-05-25 | 2102369326 | 8202243465 |  | 26_Perbaikan 101F503 - Flame Scanner COB | RU4-RFCC | 101F503/00 | 50 | CLSD CSER MACM NCMP PRC | 4IR |  | 919363200 | 0 | MA6-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-06-08 | PM |  | 003
| K401 | 2026-04-29 | 2026-06-20 | 2026-06-05 | 2026-12-30 | 2102368176 | 8202242842 |  | 26_Perbaikan 100PCV632 membran sobek | RU4-GTO | 100T631/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 3 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-05 | PM |  | 003
| K401 | 2026-02-23 | 2026-02-26 | 2026-02-26 | 2026-12-30 | 2102364044 | 8202239077 |  | 26_Perbaikan 057PV009 Fuel Oil Return Co | RU4-UTL | 057PV009/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-18 | 2026-04-02 | 2026-03-06 | 2026-10-05 | 2102364058 | 8202238928 |  | 26_Perbaikan 054FT018 Flow Cond 054WS101 | RU4-UTL | 054WS101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-31 | 2026-04-02 | 2026-04-02 | 2026-12-30 | 2102353743 | 8202241987 |  | 26_Perb Sbstandard Lighting Pnl 30EE3128 |  |  | 50 | REL NMAT PRC SETC | 4MR | D14/25/B6/RTC-3-C2H | 1000000000 | 0 | MA3-LIS |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 5 | 3 | 2026-04-02 | PM |  | 045
| K401 | 2026-05-06 | 2026-06-19 | 2026-05-06 | 2026-12-21 | 2102364975 | 8202243006 |  | 26_PERB & PENGGUNAAN LAMPU PENERANGAN FO | RU4-FOC1 | 11P18M-CB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-03-02 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102364892 | 8202239296 |  | 26_Penunjukkan PG Meragukan 105-PG-162 | RU4-RFCGTO | 105F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 9000000 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-17 | 2026-03-17 | 2026-10-29 | 2102364856 | 8202239364 |  | 26_Penunjukkan PG Meragukan 105-PG-161 | RU4-RFCGTO | 105F502/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 9000000 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-17 | 2026-03-17 | 2026-10-29 | 2102364843 | 8202239374 |  | 26_Penunjukkan PG Meragukan 105-PG-087 | RU4-RFCGTO | 105PG-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 9000000 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K401 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-11-19 | 2102368185 | 8202242681 |  | 26_Penunjukkan 105TI-118 NaN | RU4-RFCGTO | 105TI-U105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-12-30 | 2102364610 | 8202239052 |  | 26_Penunjukkan 101-TI-761 COB meragukan | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 26685500 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-18 | 2026-06-15 | 2026-12-29 | 2102369838 | 8202243851 |  | 26_Penunjukkan 024FT-020 | RU4-LOC2 | 024FT020/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16800000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-03-03 | 2026-05-12 | 2026-05-12 | 2026-12-22 | 2102364791 | 8202239387 |  | 26_Penunjukan NaN 260PT057 | RU4-LOC3 | 260PT057/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-11-05 | 2102357989 | 8202242175 |  | 26_Penunjukan NaN 260PDI_090 | RU4-LOC3 | 260PDT090/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-19 | 2026-02-20 | 2026-02-19 | 2026-12-30 | 2102356277 | 8202238975 |  | 26_Penunjukan 024LT058 error | RU4-LOC2 | 024LT058/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-20 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-12-17 | 2102368451 | 8202242979 |  | 26_Penggantian VSD Clarifier UTL RFCC | RU4-RFCUTL |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-13-C2H | 20 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-21 | 2026-06-17 | 2026-12-30 | 2102367162 | 8202243883 |  | 26_Penggantian Valve Suc & Disc 47P102 |  |  | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 72442860 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-10 | 2026-06-21 | 2026-06-10 | 2026-12-30 | 2102369200 | 8202243731 |  | 26_Penggantian valve MOV 16" di 47T511F | RU4-RFCGTO | 47T511F/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 045
| K401 | 2026-06-08 | 2026-06-18 | 2026-06-10 | 2026-12-29 | 2102369589 | 8202243691 |  | 26_Penggantian transmitter 24PT036 | RU4-LOC1 | 24PT036/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 15000000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-23 | 2026-04-07 | 2026-11-19 | 2102366692 | 8202241897 |  | 26_Penggantian Transmitter 153FT001 | RU4-RFCUTL | 153TT001/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 20000000 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-11-05 | 2102355241 | 8202242173 |  | 26_Penggantian Transmitter 024LT-026 | RU4-LOC2 | 024LT026/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-04-15 | 2026-05-26 | 2026-05-25 | 2026-12-30 | 2102367775 | 8202242466 |  | 26_Penggantian Transmitter 011FT-007 | RU4-FOC2 | 011FT007/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 19500000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-18 | 2026-03-10 | 2026-03-06 | 2026-10-05 | 2102363935 | 8202238933 |  | 26_Penggantian TI dial 14P5 | RU4-FOC1 | 14P5A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 6 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369588 | 8202243686 |  | 26_Penggantian thermowell 21TW719 | RU4-LOC1 | TEMP-U21/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369587 | 8202243688 |  | 26_Penggantian thermowell 21TW718 | RU4-LOC1 | TEMP-U21/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369586 | 8202243687 |  | 26_Penggantian thermowell 21TW023 | RU4-LOC1 | TEMP-U21/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369612 | 8202243689 |  | 26_Penggantian thermowell 21TW007 | RU4-LOC1 | TEMP-U21/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-03-16 | 2026-04-09 | 2026-04-09 | 2026-12-29 | 2102366427 | 8202241750 |  | 26_Penggantian TG Casing 101P502ABC | RU4-RFCC | 101P502A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 6 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-03-16 | 2026-04-09 | 2026-04-09 | 2026-12-29 | 2102366426 | 8202241749 |  | 26_Penggantian TG Casing 101P501ABC | RU4-RFCC | 101P501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 2 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-25 | 2026-05-25 | 2026-12-30 | 2102369206 | 8202243392 |  | 26_Penggantian Temp Indikator Tanki 36T1 | RU4-TRML | 36T106/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-05-25 | PT02 | 5 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102364570 | 8202239055 |  | 26_Penggantian Temp Indikator Tanki 34T2 | RU4-TRML | 34T2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-12-22 | 2102369107 | 8202243520 |  | 26_Penggantian tachometer 101P501A | RU4-RFCC | 101P501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 26515819 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 8 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-22 | 2026-05-22 | 2026-12-29 | 2102368631 | 8202242936 |  | 26_Penggantian Speed Meter Local Indicat | RU4-RFCUTL | 153P501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369865 | 8202243852 |  | 26_Penggantian Sensor 14TXI672 | RU4-FOC1 | 14TXE672/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-18 | 2026-06-15 | 2026-12-22 | 2102369106 | 8202243577 |  | 26_Penggantian sensor 101TT771 | RU4-RFCC | 101TT771/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 8 | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-09 | 2026-02-23 | 2026-02-23 | 2026-12-30 | 2102356364 | 8202238792 |  | 26_Penggantian selector switch start F.G | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-02-09 | 2026-02-23 | 2026-02-23 | 2026-12-30 | 2102356366 | 8202238791 |  | 26_Penggantian selector switch | RU4-UTL | 052B103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-23 | 2026-06-23 | 2026-12-29 | 2102369783 | 8202243855 |  | 26_Penggantian Resistance Isolator 152TI | RU4-RFCUTL |  | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 1 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-23 | PM |  | 045
| K401 | 2026-06-15 | 2026-06-23 | 2026-06-23 | 2026-12-29 | 2102369781 | 8202243856 |  | 26_Penggantian Resistance Isolator 152TI | RU4-RFCUTL |  | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 1 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-23 | PM |  | 045
| K401 | 2026-06-15 | 2026-06-23 | 2026-06-23 | 2026-12-29 | 2102369782 | 8202243857 |  | 26_Penggantian Resistance Isolator 152TI | RU4-RFCUTL |  | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 1 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-23 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-09-29 | 2102365058 | 8202241469 |  | 26_Penggantian PSU Rotoguard 510G601 | RU4-UTL | 510G601-E1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-05-05 | 2026-06-10 | 2026-05-05 | 2026-10-08 | 2102367066 | 8202242992 |  | 26_Penggantian pres rise trfo 63EE1112AB |  |  | 60 | TECO CNF CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 32000000 | 0 | MA5-LIS |  | AHMADZAENURI | 2026-06-10 | 2026-05-05 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 045
| K401 | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-12-29 | 2102368166 | 8202242757 |  | 26_Penggantian Positioner 151FV660 | RU4-RFCUTL | 151FV660/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-18 | 2026-06-10 | 2026-12-29 | 2102369638 | 8202243685 |  | 26_Penggantian Positioner 013PIC-011 | RU4-FOC2 | 013PT011/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 2 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-23 | 2026-03-10 | 2026-11-26 | 2102365192 | 8202241478 |  | 26_Penggantian PI pompa sundyne | RU4-TRML | 41P4B/00 | 60 | REL MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1203448 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-06 | 2026-03-05 | 2026-09-29 | 2102364434 | 8202239219 |  | 26_Penggantian PI & Power Supply HVI 60/ | RU4-TRML | 71P13A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 57485714 | 69526750 | MA3-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-11 | 2026-04-02 | 2026-03-06 | 2026-10-05 | 2102363887 | 8202238860 |  | 26_Penggantian PD Meter Wellpump 30P107 | RU4-TRML | 30PSH107A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-3-C2H | 1 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 4 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-09-23 | 2102357584 | 8202239126 |  | 26_Penggantian panel FGDS | RU4-TRML | 71T21/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 9 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-14 | 2026-04-14 | 2026-12-29 | 2102367157 | 8202242095 |  | 26_Penggantian orifice 21FE005 | RU4-LOC1 | 21FE005/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-11-19 | 2102367763 | 8202242584 |  | 26_Penggantian Motor 91K402BPM LIS-MA1 | RU4-SRU | 91K402BPM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-04-20 | PT02 | 5 | 3 | 2026-04-20 | PM |  | 005
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-11-19 | 2102367762 | 8202242583 |  | 26_Penggantian Motor 91K401BPM LIS-MA1 | RU4-SRU | 91K401BPM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-04-20 | PT02 | 5 | 3 | 2026-04-20 | PM |  | 005
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-11-19 | 2102367761 | 8202242582 |  | 26_Penggantian Motor 91K401APM LIS-MA1 | RU4-SRU | 91K401APM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-04-20 | PT02 | 5 | 3 | 2026-04-20 | PM |  | 005
| K401 | 2026-02-09 | 2026-02-13 | 2026-02-09 | 2026-12-03 | 2102357062 | 8202238771 |  | 26_Penggantian Motor 38P113AM | RU4-TRML | 38P113A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-LIS |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-12-30 | 2102366757 | 8202242271 |  | 26_Penggantian motor 20P-1M | RU4-LOC1 | 20P1M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 2 | 0 | MA1-LIS |  | TEGARPRAMUDY |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-05-26 | 2026-05-29 | 2026-05-26 | 2026-12-21 | 2102369310 | 8202243503 |  | 26_Penggantian Motor 052E102M2M | RU4-UTL | 052E102M02/00 | 60 | TECO CNF CSER MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 119691000 | 0 | MA5-LIS |  | AHMADZAENURI | 2026-05-29 | 2026-05-26 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 045
| K401 | 2026-04-10 | 2026-04-20 | 2026-04-10 | 2026-11-09 | 2102367475 | 8202242303 |  | 26_Penggantian motor 021P113BM | RU4-LOC2 | 021P113B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-04-20 | PT02 | 6 | 3 | 2026-04-10 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-17 | 2026-04-15 | 2026-11-19 | 2102367200 | 8202242299 |  | 26_Penggantian Module STIM DCS LOC I | RU4-LOC1 | 24K2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-30 | 2026-05-19 | 2026-05-18 | 2026-12-29 | 2102366966 | 8202241944 |  | 26_Penggantian Module HLAI DCS | RU4-KPC | DCS-KPC/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-05-19 | PT02 | 4 | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-02-12 | 2026-04-28 | 2026-02-18 | 2026-12-30 | 2102357468 | 8202238897 |  | 26_Penggantian MCCB 500EE0221B | RU4-UTL | 500EE0206A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 300000000 | 0 | MA5-LIS |  | FARIZSETYANA |  | 2026-02-18 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 045
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-12-29 | 2102367993 | 8202242581 |  | 26_Penggantian Local Indicator 93LI180 | RU4-SRU | LI-U93/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-12-29 | 2102367994 | 8202242575 |  | 26_Penggantian Local Indicator 93LI137 | RU4-SRU | 93LI137/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-12-29 | 2102367992 | 8202242574 |  | 26_Penggantian Local Indicator 93LI131 | RU4-SRU | 93LI131/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-12-29 | 2102367991 | 8202242573 |  | 26_Penggantian Local Indicator 93FI132 | RU4-SRU | 93FI132/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-12-29 | 2102367990 | 8202242580 |  | 26_Penggantian Local Indicator 93FI081 | RU4-SRU | FI-U93/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-12-29 | 2102367969 | 8202242577 |  | 26_Penggantian Local Indicator 93FI059 | RU4-SRU | FI-U93/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 5 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-03-04 | 2026-06-21 | 2026-06-18 | 2026-12-30 | 2102365233 | 8202239458 |  | 26_Penggantian LI Mekanis Tanki 37T103 | RU4-TRML | 37T103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-12-29 | 2102367159 | 8202242093 |  | 26_Penggantian Level Transmitter 24LT007 | RU4-LOC1 | 24LT007/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 18950000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-06-09 | 2026-06-21 | 2026-06-10 | 2026-12-22 | 2102369760 | 8202243724 |  | 26_Penggantian level transmitter 024S101 | RU4-LOC2 | 024S101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 124912711 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-05-13 | 2026-06-10 | 2026-06-10 | 2026-12-30 | 2102368925 | 8202243197 |  | 26_Penggantian Level Transmitter 011-LT- | RU4-FOC2 | 011LT006/00 | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 1 | 0 | MA2-INT |  | DWIHIZZKI |  |  | PT02 | 3 | 2 | 2026-06-10 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-10 | 2026-12-30 | 2102355705 | 8202238708 |  | 26_Penggantian Level Indicator 49T1 | RU4-TRML | 49T1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1 | 0 | MA3-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-21 | 2026-08-21 | 2026-12-30 | 2102369125 | 8202243394 |  | 26_Penggantian LCS Area OM70 | RU4-TRML | 70P1AM/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 100000 | 0 | MA3-LIS |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-08-21 | PM |  | 003
| K401 | 2026-03-04 | 2026-04-23 | 2026-03-04 | 2026-10-29 | 2102365032 | 8202239434 |  | 26_Penggantian Lampu area OM 60 & NBM Bo | RU4-TRML | 67JT1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 792000000 | 792000000 | MA3-LIS |  | FARIZSETYANA |  | 2026-03-05 | PT02 | 4 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-02-26 | 2026-04-02 | 2026-02-26 | 2026-12-30 | 2102364682 | 8202239182 |  | 26_Penggantian Kabel Power 47S507BM1 LIS | LOC1-UP4 | 47S507B-M1/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-7-C2H | 100000 | 0 | MA1-LIS |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-26 | PM |  | 045
| K401 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-12-30 | 2102368228 | 8202242649 |  | 26_Penggantian Kabel MPU STG 510G301 | RU4-UTL | 510G301/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 100000 | 0 | MA5-LIS |  | FARIZSETYANA |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 045
| K401 | 2026-02-26 | 2026-03-12 | 2026-02-26 | 2026-12-30 | 2102364968 | 8202239188 |  | 26_Penggantian kabel motor 46P1AB | RU4-TRML | 46P1A/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 100000 | 0 | MA4-LIS |  | WAHYUCATUR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-12-30 | 2102354721 | 8202240696 |  | 26_Penggantian Gasket dan Bolting 140V60 | RU4-GTO | 140V603/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 1814922 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-12-30 | 2102354681 | 8202240553 |  | 26_Penggantian Gasket dan Bolting 140D60 | RU4-GTO | 140D601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 17700241 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-12-30 | 2102354684 | 8202240693 |  | 26_Penggantian Gasket dan Bolting 140D60 | RU4-GTO | 140D601B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 17660674 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-12-30 | 2102354687 | 8202240694 |  | 26_Penggantian Gasket dan Bolting 140D60 | RU4-GTO | 140D602A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 38098426 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-05-07 | 2026-06-19 | 2026-05-08 | 2026-12-29 | 2102368318 | 8202243076 |  | 26_penggantian fuse electric heater CCRF | RU4-FOC1 | 14E652/00 | 50 WAMA | REL MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-LIS |  | FARIZSETYANA |  | 2026-05-08 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 045
| K401 | 2026-02-18 | 2026-04-02 | 2026-03-06 | 2026-10-05 | 2102364118 | 8202238926 |  | 26_Penggantian Flow Transmitter 93FI135 | RU4-SRU | 93LV137/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-17 | 2026-04-15 | 2026-11-05 | 2102367182 | 8202242300 |  | 26_Penggantian Flow Transmitter 21FT020 | RU4-LOC1 | 21FT020/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 17300000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-05-20 | 2026-06-10 | 2026-06-10 | 2026-12-30 | 2102369082 | 8202243342 |  | 26_Penggantian Flow Transmitter 012FT007 | RU4-FOC2 | 012FT007A/00 | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 0 | 0 | MA2-INT |  | DWIHIZZKI |  |  | PT02 | 3 | 2 | 2026-06-10 | PM |  | 003
| K401 | 2026-04-14 | 2026-04-24 | 2026-04-14 | 2026-12-30 | 2102367756 | 8202242402 |  | 26_Penggantian Filter Dust Control 101V5 | RU4-RFCC | 101V501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 25727140 | 0 | MA6-STA |  | TEGARPRAMUDY |  | 2026-04-16 | PT02 | 8 | 3 | 2026-04-14 | PM |  | 045
| K401 | 2026-06-08 | 2026-06-21 | 2026-06-18 | 2026-12-29 | 2102369447 | 8202243697 |  | 26_Penggantian FI local area LOC 2 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 5 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 045
| K401 | 2026-03-02 | 2026-03-03 | 2026-03-03 | 2026-12-30 | 2102364578 | 8202239324 |  | 26_Penggantian Contactor NE ATS 05EE1228 | RU4-UTL | 05EE1228CZ/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 045
| K401 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369198 | 8202243414 |  | 26_Penggantian Belt 14E605B | RU4-FOC1 | 14E605/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3525955 | 2990000 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369197 | 8202243413 |  | 26_Penggantian Belt 14E605A | RU4-FOC1 | 14E605/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3525955 | 2990000 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 2026-11-30 | 2102369199 | 8202243416 |  | 26_Penggantian Belt 14E605A | RU4-FOC1 | 14E605/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 56415280 | 2990000 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-06-19 | 2026-05-25 | 2026-11-30 | 2102369196 | 8202243412 |  | 26_Penggantian Belt 11E50T | RU4-FOC1 | 11E50K-T/00 | 60 | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075464 | MA1-ROT |  | ABDULFM |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-06-19 | 2026-05-25 | 2026-11-30 | 2102369195 | 8202243411 |  | 26_Penggantian Belt 11E50S | RU4-FOC1 | 11E50K-S/00 | 60 | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | ABDULFM |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-06-19 | 2026-05-25 | 2026-11-30 | 2102369194 | 8202243410 |  | 26_Penggantian Belt 11E50R | RU4-FOC1 | 11E50K-R/00 | 60 | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075464 | MA1-ROT |  | ABDULFM |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-06-19 | 2026-05-25 | 2026-11-30 | 2102369193 | 8202243409 |  | 26_Penggantian Belt 11E50Q | RU4-FOC1 | 11E50K-Q/00 | 60 | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | ABDULFM |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-06-19 | 2026-05-25 | 2026-11-30 | 2102369192 | 8202243408 |  | 26_Penggantian Belt 11E50P | RU4-FOC1 | 11E50K-P/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | AGHANIAKBAR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-05-22 | 2026-06-19 | 2026-05-25 | 2026-11-30 | 2102369191 | 8202243407 |  | 26_Penggantian Belt 11E50O | RU4-FOC1 | 11E50K-O/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | AGHANIAKBAR |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-09 | 2026-02-12 | 2026-02-09 | 2026-08-31 | 2102355552 | 8202238778 |  | 26_Penggantian Amperemeter Rusak 47P522 | RU4-RFCGTO | 47P522M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 045
| K401 | 2026-02-09 | 2026-02-12 | 2026-02-09 | 2026-08-31 | 2102355489 | 8202238777 |  | 26_Penggantian Ammeter Rusak 108K501 A | RU4-RFCGTO | 108K501AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 045
| K401 | 2026-05-25 | 2026-06-21 | 2026-06-08 | 2026-12-29 | 2102369128 | 8202243473 |  | 26_Penggantian 155LI002B | RU4-RFCUTL | 155LI002B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-08 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-11-26 | 2102365227 | 8202239433 |  | 26_Pengg lamp navigasi SPM & Solar Panel | RU4-TRML | SPM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 3 | 0 | MA3-LIS |  | DHANANGDH |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-21 | 2026-06-17 | 2026-12-30 | 2102369068 | 8202243896 |  | 26_Pengambilan material Tag No H44020066 | RU4-RFCUTL |  | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 50000000 | 0 | MA5-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369069 | 8202243897 |  | 26_Pengambilan material Tag No H44020066 | RU4-RFCUTL |  | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 65000000 | 0 | MA5-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369210 | 8202243899 |  | 26_Pengambilan material Tag No H44020066 | RU4-RFCUTL |  | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 51000000 | 0 | MA5-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-05-05 | 2026-05-21 | 2026-05-05 | 2026-11-05 | 2102368582 | 8202242986 |  | 26_Pengambilan material Slow Moving Inst |  |  | 60 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-1-C2H | 562823999 | 109981280 | MA1-INT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 045
| K401 | 2026-04-29 | 2026-05-06 | 2026-05-06 | 2026-05-29 | 2102368515 | 8202242840 |  | 26_Pengambilan material slow moving INST | RU4-LOC3 | 240PT255/00 | 60 | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 728831724 | 731229407 | MA1-INT |  | TYFFANIM |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-04-29 | 2026-06-05 | 2026-05-06 | 2026-05-29 | 2102368498 | 8202242841 |  | 26_Pengambilan material Slow Moving | RU4-GTO | 120AT003/00 | 60 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1352141748 | 134574000 | MA1-INT |  | WAHYUCATUR |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-12-21 | 2102367146 | 8202243018 |  | 26_Pengambilan Material MOTOR,15HP,380VA | RU4-FOC1 | 14P1AM-CB/00 | 50 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 78793000 | 78793000 | MA1-LIS |  | WAHYUCATUR |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-05 | 2026-06-19 | 2026-05-05 | 2026-12-21 | 2102364927 | 8202242994 |  | 26_Pengambilan material MA4-List | RU4-KPC | 81K102M-CB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | FARIZSETYANA |  | 2026-05-07 | PT02 | 5 | 3 | 2026-05-05 | PM |  | 045
| K401 | 2026-05-05 | 2026-05-21 | 2026-05-05 | 2026-12-21 | 2102364928 | 8202242997 |  | 26_Pengambilan material MA4-List | RU4-KPC | 84K201P1BM-CB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 80352000 | 0 | MA4-LIS |  | YMOHAMMAD |  | 2026-05-07 | PT02 | 5 | 3 | 2026-05-05 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-21 | 2026-05-06 | 2026-12-21 | 2102367147 | 8202243028 |  | 26_Pengambilan Material DEVICE,PRESS REL | RU4-FOC1 | 10K1M-CB/00 | 60 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 64000000 | 64000000 | MA1-STA |  | YMOHAMMAD |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-12-30 | 2102365890 | 8202241683 |  | 26_Pengambilan cartridge 70MF103 (SL) | RU4-TRML | 70RF1/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 550000000 | 550000000 | MA3-STA |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 045
| K401 | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-12-30 | 2102364847 | 8202239262 |  | 26_pengadn transmitter flowmeter flare | RU4-FOC2 | 048A101/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 2 | 0 | MA2-INT |  | YOHANESMVIS |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 003
| K401 | 2026-02-06 | 2026-05-21 | 2026-02-06 | 2026-06-29 | 2102356610 | 8202238698 |  | 26_Pengadaan Valve outlet 47S504AB | LOC1-UP4 | 47S504A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | YMOHAMMAD |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102353387 | 8202238882 |  | 26_Pengadaan Valve outlet 47S501A | LOC1-UP4 | 47S501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-05-07 | 2026-05-08 | 2026-05-07 | 2026-12-30 | 2102368326 | 8202243089 |  | 26_Pengadaan Plug Valve Sirkulasi 93T402 | RU4-SRU | 93T402/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-07 | PM |  | 045
| K401 | 2026-05-07 | 2026-05-08 | 2026-05-07 | 2026-12-30 | 2102368325 | 8202243088 |  | 26_Pengadaan Plug Valve Sirkulasi 93T401 | RU4-SRU | 93T401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-07 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-12-30 | 2102368322 | 8202243008 |  | 26_Pengadaan Plug Valve Outlet 93E405 | RU4-SRU | 93E405/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-12-30 | 2102368321 | 8202243009 |  | 26_Pengadaan Plug Valve Outlet 93E402B | RU4-SRU | 93E402B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-12-30 | 2102368320 | 8202243012 |  | 26_Pengadaan Plug Valve Outlet 93E402A | RU4-SRU | 93E402A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-12-30 | 2102368327 | 8202243020 |  | 26_Pengadaan Plug Valve Loading Arm | RU4-SRU | 93P403A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-12-30 | 2102368324 | 8202243017 |  | 26_Pengadaan Plug Valve In Out 93J401B | RU4-SRU | 93J401B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-12-30 | 2102368323 | 8202243015 |  | 26_Pengadaan Plug Valve In Out 93J401A | RU4-SRU | 93J401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-10-29 | 2102364075 | 8202242656 |  | 26_Pengadaan Plug Valve Discharge 93P402 | RU4-SRU | 93P402B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 045
| K401 | 2026-02-19 | 2026-03-10 | 2026-03-10 | 2026-12-30 | 2102357268 | 8202238963 |  | 26_Pengadaan PC EWS Area COB RFCC | RU4-RFCC | 101F503/00 | 50 WAMA | CRTD CSER MACM PRC | 4IR |  | 70988000 | 0 | MA6-INT |  | FARIZSETYANA |  |  | PT02 | 8 | 2 | 2026-03-10 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-09-29 | 2102364990 | 8202239311 |  | 26_Pengadaan Part Trafo Area RFCC | RU4-RFCC | 100SS1EE0011A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-LIS |  | AKHMADIS77 |  | 2026-03-03 | PT02 | 8 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-05-29 | 2102365797 | 8202241530 |  | 26_Pengadaan Mtl. Valve LT dan LG 12V3 | RU4-FOC1 | 12V3/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | ADITYAH85 |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 045
| K401 | 2026-04-16 | 2026-05-06 | 2026-04-16 | 2026-06-29 | 2102366751 | 8202242479 |  | 26_Pengadaan Mtl. Perbaikan 023E108 | RU4-LOC2 | 023E108/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-02-10 | 2026-02-17 | 2026-02-10 | 2026-03-30 | 2102355146 | 8202238809 |  | 26_Pengadaan Mtl. Line Seal Oil 14K1 | RU4-FOC1 | 14K1F2A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 5513265 | 0 | MA1-STA |  | ADITYAH85 |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 045
| K401 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-04-29 | 2102364244 | 8202239042 |  | 26_Pengadaan Mtl. line Hydrogen 14K602 | RU4-FOC1 | 14K602A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 17934376 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 045
| K401 | 2026-06-04 | 2026-06-21 | 2026-06-04 | 2026-12-22 | 2102366968 | 8202243625 |  | 26_Pengadaan Mtl. Globe Valve 014 F 101 | RU4-FOC2 | 014F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 1135862 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 045
| K401 | 2026-02-23 | 2026-02-23 | 2026-02-02 | 2026-09-29 | 2102355580 | 8202239039 |  | 26_Pengadaan Mtl. Flame Arrester HVU II | RU4-LOC2 | 021P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-05-12 | 2102367660 | 8202242310 |  | 26_Pengadaan Mtl. Cleaning 21E-22A | RU4-LOC1 | 21E22A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 7407600 | 1581950 | MA1-STA |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 045
| K401 | 2026-04-10 | 2026-06-03 | 2026-04-10 | 2026-05-12 | 2102367599 | 8202242308 |  | 26_Pengadaan Mtl. Cleaning 21E-21B | RU4-LOC1 | 21E21B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 26858100 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 045
| K401 | 2026-04-10 | 2026-06-03 | 2026-04-10 | 2026-05-12 | 2102367598 | 8202242307 |  | 26_Pengadaan Mtl. Cleaning 21E-21A | RU4-LOC1 | 21E21A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 26858100 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 045
| K401 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-05-12 | 2102367597 | 8202242305 |  | 26_Pengadaan Mtl. Cleaning 21E-20 | RU4-LOC1 | 21E20/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 16043700 | 16043700 | MA1-STA |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-08-31 | 2102365216 | 8202241379 |  | 26_Pengadaan Mtl. Check Valve 47P503A | LOC1-UP4 | 47P503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-02-27 | 2026-03-12 | 2026-03-04 | 2026-12-30 |  | 8202239268 | 8202238983 | 26_Pengadaan Mtl Pipa Inlet 52E1 | RU4-UTL | 52E1/00 | 50 WAMA | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 1015385 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-03-03 | 2026-03-12 | 2026-03-03 | 2026-12-28 | 2102365264 | 8202239403 |  | 26_Pengadaan Mtl Gasket 156-K-501A | RU4-RFCUTL | 156K501AT-E1/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 005
| K401 | 2026-03-03 | 2026-03-12 | 2026-03-03 | 2026-11-24 | 2102364921 | 8202239402 |  | 26_Pengadaan Mtl Filter Mushroom 154A503 | RU4-RFCUTL | 154A503A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 1262 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-03-04 | PT02 | 2 | 3 | 2026-03-03 | PM |  | 005
| K401 | 2026-03-26 | 2026-04-24 | 2026-03-26 | 2026-12-30 | 2102366621 | 8202241880 |  | 26_Pengadaan Material Water Separator | RU4-TRML | 70P10M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 93000000 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-26 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 045
| K401 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-12-22 | 2102367950 | 8202242591 |  | 26_Pengadaan Material Rigaku ZSX Primus | RU4-FOC2 | 30BD12EE0012B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 3 | 0 | WS-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-24 | 2026-03-26 | 2026-12-30 | 2102366619 | 8202241882 |  | 26_Pengadaan Material Microfilter | RU4-TRML | 70P11/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 124200000 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-26 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 045
| K401 | 2026-04-16 | 2026-06-02 | 2026-04-16 | 2026-08-27 | 2102355070 | 8202242480 |  | 26_Pengadaan material consumabble | RU4-FOC2 | 013P103BM/00 | 50 WAMA | REL CSER MANC PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 201221095 | 0 | WS-LIS |  | AKHMADIS77 |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-03-26 | 2026-05-22 | 2026-03-26 | 2026-12-30 | 2102366620 | 8202241881 |  | 26_Pengadaan Material Coalescer | RU4-TRML | LN70-1020LB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-03-26 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 045
| K401 | 2026-05-07 | 2026-06-18 | 2026-06-04 | 2026-12-29 | 2102368644 | 8202243070 |  | 26_Pengadaan Material & Perbaikan iCAP74 | RU4-FOC2 | 30BD12EE0012B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 3 | 0 | WS-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-04 | PM |  | 003
| K401 | 2026-03-10 | 2026-04-15 | 2026-03-10 | 2026-03-10 | 2102366397 | 8202241543 |  | 26_Pengadaan Load Center & Receptacle |  |  | 50 | CLSD NCMP NMAT PRC | 4ER |  | 9000000000 | 0 | WS-TLS |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-04-15 | PM |  | 045
| K401 | 2026-06-15 | 2026-06-21 | 2026-06-15 | 2026-12-30 | 2102367892 | 8202243844 |  | 26_Pengadaan Gasket L.O Cooler 105K501E1 | RU4-RFCGTO | 105K501T-E1/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 10 | 0 | MA7-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 045
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-08-31 | 2102365716 | 8202241742 |  | 26_Pengadaan Gasket Finfan 11E50 | RU4-FOC1 | 11E50AB/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 30000000 | 40000000 | MA1-STA |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367889 | 8202242502 |  | 26_Pengadaan Gasket Fin Fan 11E55AB | RU4-FOC1 | 11E55AB/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-06-29 | 2102368218 | 8202242677 |  | 26_Pengadaan Gasket 11E61 | RU4-FOC1 | 11E61AB/00 | 50 WAMA | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 7878748 | 0 | MA1-STA |  | ADITYAH85 |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 045
| K401 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-07-30 | 2102368219 | 8202242673 |  | 26_Pengadaan Gasket 11E18 | RU4-FOC1 | 11E18A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 17881064 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 045
| K401 | 2026-03-17 | 2026-03-25 | 2026-03-17 | 2026-07-30 | 2102364338 | 8202241816 |  | 26_Pengadaan Fourway Valve 14K1 | RU4-FOC1 | 14K1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 1 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-02-20 | 2026-03-06 | 2026-02-20 | 2026-12-30 | 2102356422 | 8202238983 |  | 26_Pengadaan Floating Head 52E1 | RU4-UTL | 52E1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 045
| K401 | 2026-02-26 | 2026-05-05 | 2026-03-12 | 2026-12-30 | 2102353413 | 8202239231 |  | 26_Pengadaan Filter Coalescer 91K401B | RU4-SRU | 91K401B/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 1764000000 | 630000000 | MA1-STA |  | WAHYUCATUR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-05-11 | 2026-06-20 | 2026-06-02 | 2026-12-29 | 2102368753 | 8202243117 |  | 26_Pengadaan Fieldbus Power Supply | RU4-REL |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 5 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 045
| K401 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-10-29 | 2102354316 | 8202239283 |  | 26_Pengadaan Expansion Joint 014V116 | RU4-FOC2 | 014V116/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-09-01 | 2102368574 | 8202243040 |  | 26_Pengadaan Check Valve Line N2 SRU | RU4-SRU | 93FV053/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 9450000 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 5 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-04-24 | 2026-04-27 | 2026-04-24 | 2026-07-30 | 2102368237 | 8202242722 |  | 26_Pengadaan Butt. Valve CWR 21E22A | RU4-LOC1 | 21E22A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 4875000 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 045
| K401 | 2026-04-24 | 2026-04-27 | 2026-04-24 | 2026-06-29 | 2102368236 | 8202242720 |  | 26_Pengadaan Butt. Valve CWR 21E20 | RU4-LOC1 | 21E20/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102353400 | 8202238876 |  | 26_Pengadaan Butt. Valve 47S505 | LOC1-UP4 | 47S505/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102353389 | 8202238883 |  | 26_Pengadaan Butt. Valve 47S505 | LOC1-UP4 | 47S505/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-12-22 | 2102365215 | 8202241374 |  | 26_Pengadaan Butt. Valve 47P507A | LOC1-UP4 | 47P507A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102353385 | 8202238879 |  | 26_Pengadaan Butt. Valve 47P506AB | LOC1-UP4 | 47P506A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 4 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102353384 | 8202238878 |  | 26_Pengadaan Butt. Valve 47P505ABC | LOC1-UP4 | 47P505A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102357591 | 8202238880 |  | 26_Pengadaan Butt. Valve 47P504AB | LOC1-UP4 | 47P504A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102353388 | 8202238881 |  | 26_Pengadaan Butt. Valve 47P501AB | LOC1-UP4 | 47S501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-03-09 | 2026-05-18 | 2026-03-16 | 2026-12-30 | 2102354647 | 8202241481 |  | 26_Pengadaan / pemasangan PI & TI | RU4-FOC2 | TRANSDUCER-U012/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 48796271 | 0 | MA2-INT |  | FATAHALFI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367924 | 8202242519 |  | 26_Pengadaaan Gasket HE 13E1D | RU4-FOC1 | 13E1D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367923 | 8202242518 |  | 26_Pengadaaan Gasket HE 13E1C | RU4-FOC1 | 13E1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367922 | 8202242517 |  | 26_Pengadaaan Gasket HE 13E1B | RU4-FOC1 | 13E1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367921 | 8202242516 |  | 26_Pengadaaan Gasket HE 13E1A | RU4-FOC1 | 13E1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-05-21 | 2026-04-16 | 2026-06-29 | 2102367919 | 8202242514 |  | 26_Pengadaaan Gasket HE 12E1J | RU4-FOC1 | 12E1J/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 17356000 | 0 | MA1-STA |  | YMOHAMMAD |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-05-21 | 2026-04-16 | 2026-06-29 | 2102367918 | 8202242513 |  | 26_Pengadaaan Gasket HE 12E1I | RU4-FOC1 | 12E1I/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 17356000 | 0 | MA1-STA |  | YMOHAMMAD |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367917 | 8202242512 |  | 26_Pengadaaan Gasket HE 12E1H | RU4-FOC1 | 12E1H/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 8840139 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367916 | 8202242511 |  | 26_Pengadaaan Gasket HE 12E1G | RU4-FOC1 | 12E1G/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 8840139 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367915 | 8202242510 |  | 26_Pengadaaan Gasket HE 12E1F | RU4-FOC1 | 12E1F/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 8840139 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-05-21 | 2026-04-16 | 2026-06-29 | 2102367914 | 8202242509 |  | 26_Pengadaaan Gasket HE 12E1E | RU4-FOC1 | 12E1E/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 36967333 | 0 | MA1-STA |  | YMOHAMMAD |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-05-21 | 2026-04-16 | 2026-06-29 | 2102367913 | 8202242508 |  | 26_Pengadaaan Gasket HE 12E1D | RU4-FOC1 | 12E1D/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 36967333 | 0 | MA1-STA |  | YMOHAMMAD |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367912 | 8202242507 |  | 26_Pengadaaan Gasket HE 12E1C | RU4-FOC1 | 12E1C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367911 | 8202242506 |  | 26_Pengadaaan Gasket HE 12E1B | RU4-FOC1 | 12E1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367910 | 8202242505 |  | 26_Pengadaaan Gasket HE 12E1A | RU4-FOC1 | 12E1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-29 | 2102367920 | 8202242515 |  | 26_Pengadaaan Gasket Fin Fan 12E2AB | RU4-FOC1 | 12E2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 045
| K401 | 2026-02-27 | 2026-05-06 | 2026-02-27 | 2026-11-26 | 2102356603 | 8202239251 |  | 26_Peng Pilot ign 105F501/502/503 - BonP | RU4-RFCGTO | 105F501/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | WAHYUCATUR |  | 2026-02-27 | PT02 | 2 | 3 | 2026-02-27 | PM |  | 045
| K401 | 2026-03-04 | 2026-05-13 | 2026-02-20 | 2026-02-20 | 2102364674 | 8202239437 |  | 26_Penambahan UPS 1 Phase Metring System |  |  | 50 WENG | CRTD CSER NMAT PRC | 4ER | D14/09/B6/RTNH | 0 | 0 | MA3-LIS |  | DHANANGDH |  |  | PT02 | 5 | 2 | 2026-02-20 | PM |  | 045
| K401 | 2026-05-25 | 2026-06-21 | 2026-06-10 | 2026-12-29 | 2102369156 | 8202243469 |  | 26_Penambahan Pressure Gauge di 024K-101 | RU4-LOC2 | 024K101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 30 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-03-12 |  | 2026-03-02 | 2026-03-02 | 2102365195 | 8202241613 |  | 26_Pembuatan Fasilitas Power Temporary R | RU4-REL |  | 50 | CRTD NMAT PRC | 4ER |  | 5000000000 | 0 | MA6-LIS |  |  |  |  | PT02 | 8 | 2 | 2026-03-02 | PM |  | 045
| K401 | 2026-02-11 | 2026-04-13 | 2026-03-06 | 2026-10-05 | 2102363997 | 8202238861 |  | 26_pemasangan PI manual di 014F101/102 | RU4-FOC2 | 014F101/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 47717539 | 0 | MA2-INT |  | TYFFANIM |  | 2026-04-02 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-05-29 | 2026-06-22 | 2026-05-29 | 2026-12-30 | 2102368269 | 8202243540 |  | 26_Pemasangan DBB Drain Tanki Area OM 60 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | FARIZSETYANA |  | 2026-05-29 | PT02 | 5 | 3 | 2026-05-29 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-21 | 2026-05-06 | 2026-12-21 | 2102367776 | 8202243019 |  | 26_PEK. TRAFO DI AREA FOC 2 | RU4-FOC2 | 012K101AP2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 64000000 | 64000000 | MA2-LIS |  | YMOHAMMAD |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-21 | 2026-05-06 | 2026-12-21 | 2102367777 | 8202243021 |  | 26_PEK. TRAFO DI AREA FOC 2 | RU4-FOC2 | 014P108ABM-CB/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 96000000 | 0 | MA2-LIS |  | YMOHAMMAD |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-09-29 | 2102366317 | 8202241691 |  | 26_Overload Control Soot Blower 025F101 | RU4-LOC2 | 025F101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-8-C2H | 18 | 0 | MA2-LIS |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 6 | 3 | 2026-03-13 | PM |  | 045
| K401 | 2026-03-04 | 2026-06-03 | 2026-03-04 | 2026-09-29 | 2102364579 | 8202239420 |  | 26_Noise pada motor 240P102BM | RU4-LOC3 | 240P102BM/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-9-C2H | 7625859 | 5160700 | MA4-LIS |  | FARIZSETYANA |  | 2026-03-04 | PT02 | 1 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-04-30 |  | 2026-04-10 | 2026-04-10 | 2102367782 | 8202242875 |  | 26_Mtl. Perbaikan line CWR 23E-10 | RU4-LOC1 |  | 50 | CRTD CSER MACM PRC | 4MR |  | 0 | 0 | MA1-STA |  |  |  |  | PT02 | 3 | 2 | 2026-04-10 | PM |  | 045
| K401 | 2026-05-25 | 2026-06-03 | 2026-05-25 | 2026-08-31 | 2102368865 | 8202243447 |  | 26_Mtl. Penggantian Microfilter 013MF-10 | RU4-FOC2 | 013C101/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 51360000 | 51360000 | MA2-STA |  | FARIZSETYANA |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 045
| K401 | 2026-02-26 |  | 2026-02-02 | 2026-02-02 | 2102357780 | 8202239230 |  | 26_Mtl. Penggantian Filter Coalescer | RU4-SRU | 91K403A/00 | 50 | CRTD CSER MACM PRC | 4MR |  | 128803500 | 0 | MA1-STA |  |  |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-17 | 2026-04-23 | 2026-04-17 | 2026-11-23 | 2102366961 | 8202242552 |  | 26_Mtl. Penggantian Filter 91S405 | RU4-SRU | 91S405/00 | 60 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 13825000 | 13825000 | MA1-STA |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-21 | 2026-03-02 | 2026-10-20 | 2102355167 | 8202243027 |  | 26_Mtl. Penggantian Catridge 94S403 | RU4-SRU | 91S403/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 52080000 | 1860000 | MA1-STA |  | YMOHAMMAD |  | 2026-05-08 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-02-12 | 2026-02-23 | 2026-02-12 | 2026-06-29 | 2102363934 | 8202238887 |  | 26_Mtl. Penggantian Boardesk Unit 21 | RU4-LOC1 | 21P2A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 045
| K401 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-09-29 | 2102357238 | 8202239189 |  | 26_Mtl. Microfilter 013MF101A/B | RU4-FOC2 | 013C101/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 51360000 | 51360000 | MA2-STA |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 045
| K401 | 2026-06-18 | 2026-06-21 | 2026-06-18 | 2026-08-31 | 2102366889 | 8202243942 |  | 26_Mtl. Ganti Catridge Filter 91S403 | RU4-SRU | 91S403/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-6-C2H | 52080000 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 045
| K401 | 2026-06-09 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102366632 | 8202243716 |  | 26_Mtl valve JW buterfly 054E102A/B | RU4-UTL | 054E102A/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 10534261 | 0 | MA5-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-07-29 | 2102366166 | 8202242256 |  | 26_Mtl STEAM,TRAP,TRMODYNMC,CS,SS,1IN,HP |  |  | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 18800000 | 18800000 | MA5-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-09-29 | 2102366164 | 8202242252 |  | 26_Mtl STEAM,TRAP,TRMODYNMC,CS,SS,1/2IN |  |  | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 8200000 | 8200000 | MA5-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-11-30 | 2102366167 | 8202242257 |  | 26_Mtl STEAM,TRAP,TRMODYNMC,3/4IN,MP |  |  | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 124200000 | 124200000 | MA5-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-09-29 | 2102366165 | 8202242254 |  | 26_Mtl STEAM,TRAP,TRMODYNMC,1/2IN,MP |  |  | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 93800000 | 93800000 | MA5-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-07-29 | 2102366168 | 8202242259 |  | 26_Mtl STEAM,TRAP,THERMODYNAMIC,3/4,HP |  |  | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 5133333 | 5133333 | MA5-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-09-29 | 2102366929 | 8202242246 |  | 26_Mtl Steam Trace area RFCC | RU4-REL |  | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 33297979 | 0 | MA6-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2102353465 | 8202243608 |  | 26_Mtl Level Glass Assy 52B1 | RU4-UTL | 52B1/00 | 50 | CRTD CSER MACM PRC | 4MR |  | 259000000 | 0 | MA5-STA |  |  |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 045
| K401 | 2026-06-09 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102369187 | 8202243712 |  | 26_Mtl LEVEL GLASS 520B301 | RU4-UTL | 520B301/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 97500000 | 0 | MA5-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-03 | 2026-06-20 | 2026-06-17 | 2026-12-22 | 2102368113 | 8202243599 |  | 26_Mtl Gasket Hand&Master Hole 52B201 | RU4-UTL | 52B201/00 | 50 | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 10197871 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-09 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368724 | 8202243711 |  | 26_Mtl Gasket 101E526B | RU4-RFCC | 101E526B/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 41562341 | 0 | MA6-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-09 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102368723 | 8202243710 |  | 26_Mtl Gasket 101E526A | RU4-RFCC | 101E526A/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 41661395 | 0 | MA6-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-03 | 2026-06-20 | 2026-06-17 | 2026-12-22 | 2102353612 | 8202243607 |  | 26_Mtl 52B1/2/3 & 051B101/102/103 |  |  | 50 | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 159057600 | 0 | MA5-STA |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-08 | 2026-10-13 | 2102366928 | 8202242248 |  | 26_Matl Bladder Valve 103P501 | RU4-RFCC | 103P501A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 045
| K401 | 2026-06-18 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102369367 | 8202243928 |  | 26_Material Separator CPI 011S105 | RU4-FOC2 | 011S107-CB/00 | 50 | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-05 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102368569 | 8202243669 |  | 26_Material Isolasi MA 1 | RU4-LOC1 | LN20-146K/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 247860946 | 0 | MA1-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-06-04 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369630 | 8202243640 |  | 26_Material Isolasi 151B501C | RU4-RFCUTL | 151B501C/00 | 50 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-13-C2H | 16718456 | 0 | MA5-STA |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 045
| K401 | 2026-03-06 | 2026-04-21 | 2026-03-06 | 2026-10-29 | 2102365223 | 8202241293 |  | 26_master relay (MR) 011P123AM rusak | RU4-FOC2 | 011P123AM/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | AKHMADIS77 |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-30 | 2026-04-15 | 2026-03-30 | 2026-07-29 | 2102365224 | 8202241933 |  | 26_master relay (MR) 011P123 BM rusak | RU4-FOC2 | 011P123BM/00 | 60 | CLSD CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-03-03 | 2026-04-08 | 2026-04-07 | 2026-12-07 | 2102364914 | 8202239369 |  | 26_Layar PI 108-PG-754 A Pecah | RU4-RFCGTO | 108PI-U108/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 2 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-08 | 2026-04-07 | 2026-12-07 | 2102364913 | 8202239367 |  | 26_Layar PG 108-PG-753 A Pecah | RU4-RFCGTO | 108PG-U108/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 2 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-23 | 2026-06-22 | 2026-12-30 | 2102370188 | 8202244039 |  | 26_Keperluan Material Tanki 32T103 |  |  | 50 | CRTD CSER MACM PRC | 4MR |  | 107983333 | 0 | MA3-STA |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-06-22 | PM |  | 045
| K401 | 2026-03-17 | 2026-05-12 | 2026-05-12 | 2026-12-22 | 2102366415 | 8202241807 |  | 26_Kalibrasi pembacaan flow 013FT-005 | RU4-FOC2 | 013FT005/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-17 | 2026-05-12 | 2026-05-12 | 2026-12-22 | 2102366416 | 8202241806 |  | 26_Kalibrasi pembacaan flow 013FT-004 | RU4-FOC2 | 013FT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-24 | 2026-03-02 | 2026-10-19 | 2102365196 | 8202242500 |  | 26_Isolasi Rutin MA 4 | RU4-UTL | LN57-FG8001A1A1/00 | 50 WAMA | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 76122824 | 0 | MA4-STA |  | TEGARPRAMUDY |  | 2026-04-16 | PT02 | 5 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-04-06 | 2026-04-16 | 2026-04-16 | 2026-12-30 | 2102367055 | 8202242115 |  | 26_Indikator 104-PDG-613 di HPC rusak | RU4-RFCC | 104K501T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 1 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-06-03 |  | 2026-05-05 | 2026-05-05 | 2102368585 | 8202243585 |  | 26_Ignnitor pilot 120-F-601 D tidak nyal | RU4-GTO | 120F601BEP/00 | 01 WENG | CRTD CSER NMAT PRC | 4ER | D14/XX/B6/RT-C2NH | 0 | 0 | MA7-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-05-05 | PM |  | 045
| K401 | 2026-05-07 | 2026-05-25 | 2026-05-21 | 2026-12-30 | 2102368693 | 8202243071 |  | 26_Hart Communicator Rusak | RU4-LOC2 | 022K101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-05-25 | PT02 | 6 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-06 | 2026-02-23 | 2026-12-22 | 2102355985 | 8202239032 |  | 26_ganti hub coupling 33P4B-Ambil Gudang | RU4-TRML | 33P4B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-3-C2H | 451630 | 0 | MA3-LIS |  | YMOHAMMAD |  | 2026-02-23 | PT02 | 5 | 3 | 2026-02-23 | PM |  | 045
| K401 | 2026-02-23 | 2026-03-16 | 2026-03-16 | 2026-12-30 | 2102364551 | 8202239065 |  | 26_Error reading 260TSH442 | RU4-LOC3 | 260TSH442/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-16 | 2026-03-16 | 2026-12-30 | 2102364550 | 8202239063 |  | 26_Error reading 260TSH242 | RU4-LOC3 | 260TSH242/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102364509 | 8202239062 |  | 26_Error reading 260PDSH471 | RU4-LOC3 | 260PDSH471/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102364508 | 8202239061 |  | 26_Error reading 260PDSH271 | RU4-LOC3 | 260PDSH271/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-03 | 2026-03-02 | 2026-12-30 | 2102364553 | 8202239053 |  | 26_Error reading 260FSLL181 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-02-23 | 2026-03-03 | 2026-03-02 | 2026-12-30 | 2102364552 | 8202239054 |  | 26_Error reading 260FSLL081 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-03-02 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-21 | 2026-05-06 | 2026-12-21 | 2102367065 | 8202243022 |  | 26_DEVICE,PRESS RELIEF,VITON,2.5,50/60,1 | RU4-UTL | 054P102CM-CB/00 | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 32000000 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-06-08 | 2026-06-22 | 2026-06-19 | 2026-12-22 | 2102369554 | 8202243692 |  | 26_Control Valve Assy 91LV214 | RU4-SRU | 91LV214/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 4 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-03-27 | 2026-04-24 | 2026-04-06 | 2026-12-30 | 2102366144 | 8202241910 |  | 26_CM_Valve fasilitas Loading 180A601V2B | RU4-GTO | 180A601V2B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-03-27 | 2026-04-24 | 2026-04-06 | 2026-12-30 | 2102366707 | 8202241911 |  | 26_CM_Check valve passing di 180A601V2B | RU4-GTO | 180A601V2B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 2 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-08-26 | 2102367661 | 8202242311 |  | 26_Cleaning & perbaikan 21E-22B | RU4-LOC1 | 21E22B/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-STA |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-10 | PM |  | 045
| K401 | 2026-03-03 | 2026-05-22 | 2026-05-22 | 2026-12-22 | 2102364599 | 8202239390 |  | 26_Chamber 82LT207 korosif | RU4-KPC | 82LT207/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-05-22 | PT02 | 5 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-02-23 | 2026-06-21 | 2026-06-12 | 2026-12-29 | 2102364507 | 8202239059 |  | 26_Chamber 240LT009C korosi | RU4-LOC3 | 240LT009C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-23 | 2026-03-26 | 2026-12-30 | 2102366234 | 8202241883 |  | 26_catridge 85S201 - ganti | RU4-KPC | 85S201/00 | 60 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 44425372 | 44425372 | MA4-STA |  | FARIZSETYANA |  | 2026-03-26 | PT02 | 5 | 3 | 2026-03-26 | PM |  | 045
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102370113 | 8202243995 |  | 26_BONPNJM_Modif Transmitter 54PT103 | RU4-UTL | 54P1A/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 16500000 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369998 | 8202244006 |  | 26_BONPNJM_MOC Flow Meter Air Inst ke A1 | RU4-UTL | 054LIT501/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 18687500 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102370112 | 8202244012 |  | 26_BONPNJM_Limit Switch SOV 52XV201 | RU4-UTL | 52XV201/00 | 50 | CRTD CSER MACM PRC | 4IR | D14/XX/B6/RT-C2NH | 42000000 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-18 | 2026-06-18 | 2102370111 | 8202244009 |  | 26_BONPNJM_Limit Switch SOV 052XV209A | RU4-UTL | 052XV209A/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 42000000 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-18 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102370114 | 8202244010 |  | 26_BONPNJM_52PV202A-1 Control MP/LP LD | RU4-UTL | 52PV202A1/00 | 50 WAMA | CRTD CSER MACM PRC | 4IR | D14/XX/B6/RT-C2NH | 136600278 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-20 | 2026-08-03 | 2026-12-30 | 2102368884 | 8202243624 |  | 26_Assessment Actuator TM25LP | RU4-UTL | 051G101T/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 160500000 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 045
| K401 | 2026-04-09 | 2026-04-23 | 2026-04-22 | 2026-10-21 | 2102364740 | 8202242294 |  | 26_analyzer 84AI201 rusak | RU4-KPC | 84AT201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-23 | PT02 | 5 | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-21 | 2026-06-18 | 2026-12-29 | 2102369568 | 8202243695 |  | 26_Aktuator 92HV200 | RU4-SRU | 92HV200/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-18 | 2026-06-12 | 2026-12-29 | 2102369570 | 8202243694 |  | 26_Aktuator 91PV510B di 91V409 | RU4-SRU | 91PV510B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-18 | 2026-06-12 | 2026-12-29 | 2102369569 | 8202243693 |  | 26_Aktuator 91PV510A di 91V409 | RU4-SRU | 91PV510A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-12 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-18 | 2026-06-10 | 2026-12-29 | 2102369651 | 8202243642 |  | 26_Aktuator 91KV311C | RU4-SRU | 91KV311C/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 3690000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-21 | 2026-06-10 | 2026-12-29 | 2102369650 | 8202243641 |  | 26_Aktuator 91KV311B | RU4-SRU | 91KV311B/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 3690000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-18 | 2026-06-10 | 2026-12-30 | 2102369555 | 8202243646 |  | 26_Aktuator 91KV311A | RU4-SRU | 91KV311A/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 3690000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-03-03 | 2026-05-26 | 2026-05-26 | 2026-12-22 | 2102365099 | 8202239363 |  | 26_89TI525 steam chest rusak | RU4-KPC | 89K201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-02-06 | 2026-04-24 | 2026-02-09 | 2026-12-30 | 2102353410 | 8202238725 |  | 26_87P202C Press indicator line flush ru | RU4-KPC | 87P202C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1355534 | 0 | MA4-INT |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 4 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-02-06 | 2026-04-24 | 2026-02-09 | 2026-12-30 | 2102353408 | 8202238724 |  | 26_87P202B Press indicator line flush ru | RU4-KPC | 87P202B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1355534 | 0 | MA4-INT |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 4 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-02-06 | 2026-04-24 | 2026-02-09 | 2026-12-30 | 2102353406 | 8202238723 |  | 26_87P202A Press indicator line flush ru | RU4-KPC | 87P202A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1355534 | 0 | MA4-INT |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 4 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-17 | 2026-04-15 | 2026-10-21 | 2102366664 | 8202241898 |  | 26_87FV204D positioner rusak | RU4-KPC | 87FV204D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 4 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-02-19 | 2026-03-06 | 2026-02-19 | 2026-12-30 | 2102364452 | 8202238956 |  | 26_87F201 gas tip buntu & riser | RU4-KPC | 87F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 21 | 0 | MA4-STA |  | YMOHAMMAD |  | 2026-02-19 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 045
| K401 | 2026-02-06 | 2026-02-19 | 2026-02-19 | 2026-12-30 | 2102357786 | 8202238728 |  | 26_86PDI204A/B rusak | RU4-KPC | 86P201A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 2 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-02-19 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-27 | 2026-04-27 | 2026-12-29 | 2102367510 | 8202242379 |  | 26_84TI403B TST 84F203 indikasi rusak | RU4-KPC | 84F203/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 5 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-28 | 2026-05-12 | 2026-05-12 | 2026-12-22 | 2102368241 | 8202242801 |  | 26_84TI403A TST 84F203 indikasi rusak | RU4-KPC | 84F203/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-27 | 2026-04-27 | 2026-12-29 | 2102367511 | 8202242378 |  | 26_84TI201C TST 84F201 IH1 indikasi rusa | RU4-KPC | 84F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 5 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-16 | 2026-04-14 | 2026-04-14 | 2026-12-29 | 2102366311 | 8202241763 |  | 26_84PSL465 di 84K251 rusak | RU4-KPC | 84K251/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-14 | PT02 | 5 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-04-20 | 2026-12-29 | 2102367752 | 8202242363 |  | 26_84PCV406 rusak | RU4-KPC | 84PCV406/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-04-07 | 2026-05-21 | 2026-04-07 | 2026-12-30 | 2102367452 | 8202242141 |  | 26_84P202B line drain bocor - bel wrap |  |  | 60 | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 80476335 | 0 | MA4-STA |  | YMOHAMMAD |  | 2026-04-07 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 045
| K401 | 2026-05-05 | 2026-06-20 | 2026-06-05 | 2026-12-22 | 2102368174 | 8202242995 |  | 26_82F202 82TI260A dan D pembacaan NAN | RU4-KPC | 82F202/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-05 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-12-22 | 2102365607 | 8202241317 |  | 26_8202230264#84E202D V-Belt Rusak | RU4-KPC | 84E202KD/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 6750000 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-12-30 | 2102354206 | 8202242261 |  | 26_8202230096#Perbaikan Over Head Crane | RU4-TRML | 63A1/00 | 50 | REL NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 1010000000 | 0 | MA5-LIS |  | WAHYUCATUR |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-03-05 | 2026-04-22 | 2026-03-06 | 2026-03-06 | 2102357363 | 8202241208 |  | 26_8202229573#[PV] Penyiapan Material 63 | RU4-TRML | 63P1A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-5-C2H | 133292842 | 0 | MA5-ROT |  | ABDULFM |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-22 | 2026-03-06 | 2026-03-06 | 2102357367 | 8202241045 |  | 26_8202229185#[PV] Penyiapan Material 63 | RU4-UTL | 63P601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-4-C2H | 0 | 0 | MA5-ROT |  | ABDULFM |  | 2026-03-10 | PT02 |  | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-12-30 | 2102367361 | 8202242241 |  | 26_80P202A check valve passing - ganti | RU4-KPC | 80P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-02-26 | 2026-03-12 | 2026-02-26 | 2026-12-30 | 2102353587 | 8202239195 |  | 26_2350501#Penggantian material operasio | RU4-TRML | SPM/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-4-C2H | 54594081 | 54594081 | MA3-STA |  | YMOHAMMAD |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 045
| K401 | 2026-02-13 | 2026-04-20 | 2026-02-26 | 2026-11-26 | 2102354997 | 8202238915 |  | 26_2102350947#[CR] 012E-105-M01 belt put | RU4-FOC2 | 012E105K01/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1298879 | 1298879 | MA2-ROT |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-13 | 2026-04-20 | 2026-02-26 | 2026-11-26 | 2102354990 | 8202238913 |  | 26_2102350945#[CR] 011E-125 K10 belt put | RU4-FOC2 | 011E125K10/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3209123 | 3209123 | MA2-ROT |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-13 | 2026-03-13 | 2026-02-02 | 2026-11-30 | 2102354878 | 8202238912 |  | 26_2102350944#[CR] 011E-117 K06 belt put | RU4-FOC2 | 011E117K06/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3525956 | 3525955 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-09 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-13 | 2026-03-13 | 2026-03-05 | 2026-12-22 | 2102354877 | 8202238911 |  | 26_2102350942#[CR] 011E-117 K04 belt put | RU4-FOC2 | 011E117K04/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3525956 | 3525956 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-02 | 2026-04-20 | 2026-03-02 | 2026-05-29 | 2102355142 | 8202239319 |  | 26_2102350935#[CR] Perbaikan coupling 11 | RU4-FOC1 | 11P17A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 51500000 | 51500000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-02-13 | 2026-04-24 | 2026-02-02 | 2026-12-28 | 2102355237 | 8202238917 |  | 26_2102350932#[CR] 85E214KA Vbelt rusak | RU4-KPC | 85E214KA/00 | 60 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 3375000 | 3375000 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-09 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-13 | 2026-03-12 | 2026-02-02 | 2026-11-24 | 2102355350 | 8202238918 |  | 26_2102350931#[CR] 86E202KB Vbelt rusak | RU4-KPC | 86E202KB/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2223967 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-09 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-23 | 2026-06-19 | 2026-03-25 | 2026-08-31 | 2102355074 | 8202241861 |  | 26_2102350873#[CR] ⁠ganti cooler 017P104 | RU4-FOC2 | 017P104A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 130000000 | 0 | MA2-ROT |  | KURNIAWANDWI |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-23 | 2026-06-08 | 2026-03-25 | 2026-08-31 | 2102354995 | 8202241860 |  | 26_2102350872#[CR]Upgrade API Plan 011P1 | RU4-FOC2 | 011P112A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | KURNIAWANDWI |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-23 | 2026-06-04 | 2026-03-25 | 2026-06-29 | 2102354994 | 8202241859 |  | 26_2102350871#[CR]Upgrade API Plan 011P1 | RU4-FOC2 | 011P110C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | KURNIAWANDWI |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-08-27 | 2102354992 | 8202241858 |  | 26_2102350870#[CR]Upgrade API Plan 011P1 | RU4-FOC2 | 011P110B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-02-26 | 2026-05-21 | 2026-02-02 | 2026-02-02 | 2102355626 | 8202239226 |  | 26_2102350851#[CR] Perbaikan Blade Fin-f | RU4-RFCC | 102E520A-K1/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-22 | 2026-05-19 | 2026-03-25 | 2026-05-29 | 2102355622 | 8202241851 |  | 26_2102350850#[CR] Perbaikan Spring Soot | RU4-RFCC | 101F503/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 200000 | 9000000 | MA6-ROT |  | LUQMANULH | 2026-03-25 | 2026-03-25 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-06-29 | 2102355544 | 8202241850 |  | 26_2102350810#[CR] 011P-108A Excessive A | RU4-FOC2 | 011P108A/01 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 9253309 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-09-17 | 2102355790 | 8202242284 |  | 26_2102350796#[CR] 84P206A mechanical se | RU4-KPC | 84P206A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 28980000 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-04-10 | PT02 | 4 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-02-23 | 2026-04-28 | 2026-02-23 | 2026-10-29 | 2102355548 | 8202239025 |  | 26_2102350763#[CR] Perbaikan 021P102A | RU4-LOC2 | 021P102A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 8118150 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-09 | PT02 | 5 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-06-09 | 2102356420 | 8202242285 |  | 26_2102350726#[CR] Packing rod 3rd stg 2 | RU4-LOC3 | 260K101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 52818611 | 0 | MA4-ROT |  | TEGARPRAMUDY |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-09-29 | 2102357436 | 8202242626 |  | 26_2102350689#[CR] High Vibration 021P12 | RU4-LOC2 | 024P121A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 75676684 | 0 | MA2-ROT |  | YUNITAMR |  | 2026-04-28 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-09 | 2026-03-09 | 2026-11-26 | 2102357437 | 8202239422 |  | 26_2102350665#[CR] Perbaikan Pompa 024P1 | RU4-LOC2 | 024P121B/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 53000000 | 53000000 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 4 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-27 | 2026-03-03 | 2026-05-29 | 2102357492 | 8202239331 |  | 26_2102350580#[CR] Penggantian belt finf | RU4-RFCC | 102E518A1/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 10970000 | MA6-ROT |  | LUQMANULH | 2026-03-03 | 2026-03-03 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-10-29 | 2102357590 | 8202242548 |  | 26_2102350562#[CR]Loader valve 260K101/1 | RU4-LOC3 | 260K101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-03-04 | 2026-06-23 | 2026-03-09 | 2026-11-27 | 2102353581 | 8202239429 |  | 26_2102350560#[CR] 86P206A mech seal boc | RU4-KPC | 86P206A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 8361300 | 8361300 | MA4-ROT |  | FARENFINIAN |  | 2026-03-09 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-29 | 2026-04-21 | 2026-07-30 | 2102353586 | 8202242605 |  | 26_2102350559#[CR] 87P205A membran coupl | RU4-KPC | 87P205A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 20 | 0 | MA4-ROT |  | ABDULFM |  | 2026-04-28 | PT02 | 4 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-20 | 2026-03-03 | 2026-05-29 | 2102357496 | 8202239332 |  | 26_2102350549#[CR] Pengadaan gear piston | RU4-RFCGTO | 166P561A/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 13361750 | 13361750 | MA7-ROT |  | FARIZSETYANA | 2026-06-04 | 2026-03-03 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-06-25 | 2102353533 | 8202242549 |  | 26_2102350516#[CR] Perbaikan Kompresor 1 | RU4-FOC1 | 13K1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 14506736 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-11-26 | 2102354723 | 8202241505 |  | 26_2102350396#[CR] Perbaikan pompa 154P5 | RU4-RFCUTL | 154P506A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-03-02 | 2026-05-31 | 2026-03-02 | 2026-05-29 | 2102355287 | 8202239322 |  | 26_2102350357#[CR] Penggantian cooler po | RU4-LOC1 | 21P9B/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 65000000 | 65000000 | MA1-ROT |  | SAPBATCH | 2026-04-01 | 2026-03-03 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-09-24 | 2102355289 | 8202242617 |  | 26_2102350356#[CR] Penggantian cooler po | RU4-LOC1 | 22P4A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 65000000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-09-24 | 2102355285 | 8202242616 |  | 26_2102350355#[CR] Penggantian cooler po | RU4-LOC1 | 21P5/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 65000000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-11 |  | 2026-02-02 | 2026-02-02 | 2102355604 | 8202241580 |  | 26_2102350335#Kabel pwr pompa purifier 8 |  |  | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-02-02 | PM |  | 045
| K401 | 2026-05-18 | 2026-06-20 | 2026-06-03 | 2026-12-29 | 2102355657 | 8202243250 |  | 26_2102350302#TI after cooler pompa bany | RU4-KPC | 87P203A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 22 | 0 | MA4-INT |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-09-24 | 2102355868 | 8202242641 |  | 26_2102350259#[CR] Plunger 260P104A boco | RU4-LOC3 | 260P104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 45012034 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 1 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-04-17 | 2026-04-24 | 2026-04-23 | 2026-08-27 | 2102355779 | 8202242527 |  | 26_2102350236#[CR] Perbaikan Turbin 052P | RU4-UTL | 052P102B-T/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 700000 | 700000 | MA5-ROT |  | ABDULFM |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-09-24 | 2102355895 | 8202241778 |  | 26_2102350234#[CR] Perbaikan Deflektor 5 | RU4-UTL | 52P2B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 33381695 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-09-24 | 2102355891 | 8202241777 |  | 26_2102350233#[CR] Perbaikan Deflektor 5 | RU4-UTL | 52P2A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 33381695 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-04-20 | 2026-05-11 | 2026-04-21 | 2026-09-29 | 2102355602 | 8202242554 |  | 26_2102350214#[CR] 39P210A Bearing Defec | RU4-TRML | 39P210A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 309900 | 309900 | MA4-ROT |  | ABDULFM |  | 2026-04-21 | PT02 | 4 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-09-10 | 2102356574 | 8202239430 |  | 26_2102350190#Perbaikan 166K551 2AM WWT- | RU4-RFCUTL | 166A553/00 | 50 | REL CSER NMAT PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | DHANANGDH |  | 2026-03-04 | PT02 | 2 | 3 | 2026-03-04 | PM |  | 045
| K401 | 2026-03-04 | 2026-05-20 | 2026-03-04 | 2026-12-30 | 2102357032 | 8202239453 |  | 26_2102350052#[CR] Perbaikan Leak Mech S | RU4-RFCC | 101P501A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 46149007 | 0 | MA6-ROT |  | ABDULFM |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-02-23 | 2026-05-21 | 2026-02-23 | 2026-10-29 | 2102357809 | 8202239023 |  | 26_2102350031#[CR] 012K101A MLOP Low Pre | RU4-FOC2 | 012K101A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 256483332 | 356414048 | MA2-ROT |  | YMOHAMMAD |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-09-24 | 2102357981 | 8202242644 |  | 26_2102349973#[CR] Perbaikan Chain Sootb | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | YUNITAMR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-16 | 2026-03-04 | 2026-12-30 | 2102357982 | 8202239454 |  | 26_2102349971#[CR] Perbaikan Leak Mechse | RU4-RFCC | 101P502A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 35281200 | 0 | MA6-ROT |  | ABDULFM |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-04-16 | 2026-05-19 | 2026-04-16 | 2026-12-29 | 2102357921 | 8202242492 |  | 26_2102349962#[CR] Perbaikan Pompa 054A- | RU4-UTL | 054A101P2/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 3400000000 | 0 | MA5-ROT |  | YUNITAMR |  |  | PT02 | 3 | 2 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-28 | 2026-04-20 | 2026-09-24 | 2102355437 | 8202242599 |  | 26_2102349877#[PV] Pengadaan coupling 12 | RU4-FOC1 | 12P2A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-12-30 | 2102356327 | 8202239161 |  | 26_2102349811#PENGGANTIAN HP STEAM TRAP | RU4-RFCC | 101-ATM0006-40/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 10266666 | 10266666 | MA6-STA |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 8 | 3 | 2026-02-25 | PM |  | 045
| K401 | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-12-30 | 2102356370 | 8202239160 |  | 26_2102349810#PENGGANTIAN MP STEAM TRAP | RU4-RFCC | 101-ATM0002-14/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-12-C2H | 93150000 | 93150000 | MA6-STA |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 8 | 3 | 2026-02-25 | PM |  | 045
| K401 | 2026-03-17 | 2026-04-24 | 2026-03-17 | 2026-12-30 | 2102356287 | 8202241793 |  | 26_2102349792#Penggantian Check Valve 38 | RU4-TRML | 30P104A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-17 | PT02 | 5 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-08-31 | 2102356479 | 8202241871 |  | 26_2102349752#[CR] Perbaikan Mech Seal 1 | RU4-RFCC | 103P503B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 18043000 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-19 | 2026-05-18 | 2026-07-30 | 2102357642 | 8202243212 |  | 26_2102349705#[CR] 013K101A Low Flow | RU4-FOC2 | 013K101A/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-30 | 2026-03-05 | 2026-06-18 | 2102357645 | 8202239501 |  | 26_2102349704#[CR] 013S105B bearing mixe | RU4-FOC2 | 013S105BM/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-25 | 2026-03-06 | 2026-02-25 | 2026-12-30 | 2102357688 | 8202239159 |  | 26_2102349692#VALVE,PRESURE SAFETY,RF,2I | RU4-UTL | 520B301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 97700000 | 0 | MA5-STA |  | YMOHAMMAD |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 045
| K401 | 2026-02-25 | 2026-03-06 | 2026-02-25 | 2026-12-30 | 2102357687 | 8202239158 |  | 26_2102349691#VALVE,PRESURE SAFETY,RF,1. | RU4-UTL | 520B301/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 118200000 | 118200000 | MA5-STA |  | YMOHAMMAD |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 045
| K401 | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-12-30 | 2102357689 | 8202239156 |  | 26_2102349690#VALVE,PRESURE SAFETY,RF,1. | RU4-UTL | 520B301/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-5-C2H | 83900000 | 83900000 | MA5-STA |  | WAHYUCATUR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 045
| K401 | 2026-04-21 | 2026-05-06 | 2026-04-21 | 2026-09-29 | 2102357649 | 8202242636 |  | 26_2102349659#[CR] High Temp Discharge 2 | RU4-LOC2 | 022K101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-24 | 2026-04-23 | 2026-03-25 | 2026-07-30 | 2102354485 | 8202241870 |  | 26_2102349622#[CR] 84P204B mech seal boc | RU4-KPC | 84P204B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 70038879 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 4 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-08-20 | 2102354483 | 8202242614 |  | 26_2102349621#[CR] 84P203A mech seal boc | RU4-KPC | 84P203A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4055813 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 4 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-30 |  | 2026-03-30 | 2026-06-29 | 2102354356 | 8202241931 |  | 26_2102349593#Substandard LCS dan Ampere |  |  | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-03-30 | PM |  | 045
| K401 | 2026-04-20 | 2026-05-21 | 2026-04-20 | 2026-06-25 | 2102357609 | 8202242600 |  | 26_2102349586#[CR] 011P112B pelumas o/b | RU4-FOC2 | 011P112B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 6524400 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-03-17 | 2026-04-24 | 2026-03-17 | 2026-12-30 | 2102355481 | 8202241787 |  | 26_2102349546#Penggantian Valve LPG 47T1 | RU4-TRML | 47T103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-17 | PT02 | 4 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-04-21 | 2026-05-21 | 2026-04-21 | 2026-06-25 | 2102355554 | 8202242615 |  | 26_2102349537#26_[CR] Penggantian V-Belt | RU4-KPC | 80E202KD/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2891761 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-04-28 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-09-29 | 2102355486 | 8202241869 |  | 26_2102349509#[CR] Perbaikan Vibrasi 051 | RU4-UTL | 051P101A-T/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-12 | 2026-02-02 | 2026-11-24 | 2102357283 | 8202238729 |  | 26_2102349328#[CR] Perbaikan Bocoran Mec | RU4-RFCC | 101P502A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 8818201 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-04-20 | 2026-03-03 | 2026-05-29 | 2102355189 | 8202239309 |  | 26_2102349324#[CR] Penggantian Belt 16 K | RU4-FOC1 | 16K2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 210600 | 210600 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-02 | 2026-04-20 | 2026-03-02 | 2026-05-29 | 2102355844 | 8202239310 |  | 26_2102349323#[CR] Penggantian Belt 16 K | RU4-FOC1 | 16K1/01 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 210600 | 210600 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-19 | 2026-04-23 | 2026-03-25 | 2026-05-29 | 2102354789 | 8202241820 |  | 26_2102349269#[CR] 011E-110 K24 Blade go | RU4-FOC2 | 011E110K24/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 12564539 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-30 |  | 2026-03-30 | 2026-06-29 | 2102355304 | 8202241930 |  | 26_2102349207#o-box di 84V221 rusak | RU4-KPC | 84V221/00 | 01 | CRTD CSER NMAT PRC | 4ER |  | 0 | 0 | MA4-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-03-30 | PM |  | 045
| K401 | 2026-03-06 | 2026-06-03 | 2026-03-06 | 2026-12-30 | 2102355591 | 8202241351 |  | 26_2102349170#[CR]Perbaikan Mech Seal 91 | RU4-SRU | 91K401A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 66700000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-05-29 | 2102356687 | 8202239313 |  | 26_2102349091#[CR] Penggantian Belt 11E5 | RU4-FOC1 | 11E50K-Q/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-05-29 | 2102356726 | 8202239316 |  | 26_2102349090#[CR] Penggantian Belt 16K1 | RU4-FOC1 | 16K1/01 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 70200 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-04-29 | 2102356968 | 8202239312 |  | 26_2102349065#[CR] Penggantian Belt 11E5 | RU4-FOC1 | 11E56CD/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1740000 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 4 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-05-29 | 2102354378 | 8202239318 |  | 26_2102349063#[CR] Penggantian Belt 11E5 | RU4-FOC1 | 11E50K-N/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-04-23 | 2026-03-02 | 2026-06-29 | 2102357716 | 8202239317 |  | 26_2102349059#[CR] Penggantian Lube Oil | RU4-FOC1 | 16K1/01 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-12 | 2026-03-02 | 2026-05-29 | 2102357057 | 8202239314 |  | 26_2102349058#[CR] Penggantian Belt 16K1 | RU4-FOC1 | 16K1/01 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 70200 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-02-25 | 2026-05-11 | 2026-02-25 | 2026-11-26 | 2102357048 | 8202239144 |  | 26_2102349056#[BD] Kebocoran Mech Seal 3 | RU4-TRML | 39P206A/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 9783559 | 0 | MA4-ROT |  | SAPBATCH | 2026-03-12 | 2026-02-25 | PT02 | 4 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-02-13 | 2026-03-06 | 2026-02-13 | 2026-12-30 | 2102357209 | 8202238905 |  | 26_2102349016#87F201 tip burner fuel oil | RU4-KPC | 87F201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 9 | 0 | MA4-STA |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 6 | 3 | 2026-02-13 | PM |  | 045
| K401 | 2026-04-17 | 2026-05-25 | 2026-04-24 | 2026-11-30 | 2102355903 | 8202242530 |  | 26_2102348831#[CR]Mech Seal 90P401B-ROT | RU4-SRU | 90P401B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 1851850 | 1851850 | MA4-ROT |  | YUNITAMR |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-02-10 | 2026-02-12 | 2026-02-02 | 2026-11-18 | 2102358295 | 8202238818 |  | 26_2102348682#[CR]Penggantian membrane c | RU4-UTL | 54P1B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C1H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-10 | 2026-02-12 | 2026-02-02 | 2026-09-21 | 2102358292 | 8202238817 |  | 26_2102348681#[CR]Penggantian membrane c | RU4-UTL | 54P1A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C1H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-04-22 | 2026-04-28 | 2026-04-22 | 2026-11-30 | 2102358101 | 8202242662 |  | 26_2102348662#[CR] Perbaikan 63P502A - H | RU4-RFCUTL | 63P502A/00 | 50 | CLSD CSER MACM NCMP PRC | 4RR | D14/XX/B6/RT-C2NH | 2200000000 | 0 | MA5-ROT |  | YUNITAMR |  |  | PT02 | 3 | 2 | 2026-04-28 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-24 | 2026-03-16 | 2026-12-22 | 2102358283 | 8202241712 |  | 26_2102348640#[CR] 180T602P1A Bearing Ru | RU4-GTO | 180T602P1A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 2482850 | 2482850 | MA7-ROT |  | YMOHAMMAD |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2102356957 | 8202244045 |  | 26_2102348536#[CR] 013K101B main LO pump | RU4-FOC2 | 013K101B/00 | 50 | CRTD CSER NMAT PRC | 4RR |  | 0 | 0 | MA2-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-23 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-21 | 2026-02-24 | 2026-11-25 | 2102354116 | 8202242969 |  | 26_2102348420#[PV] Penggantian belt fin | RU4-LOC2 | 023E101K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 936667 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-05-11 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-05 | 2026-03-10 | 2026-12-30 | 2102354112 | 8202238925 |  | 26_2102348400#[CR] Perbaikan Pompa 67FP- |  |  | 50 WAMA | REL MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 1 | 0 | GEN-MEK |  | FARIZSETYANA |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 045
| K401 | 2026-05-21 | 2026-06-19 | 2026-05-22 | 2026-12-30 | 2102356994 | 8202243372 |  | 26_2102348049#[BD] 048K101C kompressor n | RU4-TRML | 048K101C/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-05-22 | PT02 | 6 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-12 | 2026-03-03 | 2026-05-29 | 2102357930 | 8202239335 |  | 26_2102347980#[CR]91E409B2, Penggantian | RU4-SRU | 91E409B2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 10798760 | 10798760 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 4 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-10 | 2026-04-20 | 2026-02-02 | 2026-11-24 | 2102358320 | 8202238834 |  | 26_2102347692#[CR] Perbaikan 51P3AT | RU4-UTL | 51P3A-T/00 | 60 | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C1H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-31 | 2026-02-02 | 2026-11-17 | 2102358343 | 8202238811 |  | 26_2102347682#[CR] Penggantian oil filte | RU4-UTL | 053P101B/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C1H | 27099099 | 0 | MA5-ROT |  | TONNYADI | 2026-03-24 | 2026-02-12 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-31 | 2026-02-02 | 2026-11-16 | 2102358342 | 8202238810 |  | 26_2102347681#[CR] Penggantian oil filte | RU4-UTL | 053P101A/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C1H | 27099099 | 0 | MA5-ROT |  | TONNYADI | 2026-03-24 | 2026-02-12 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-31 | 2026-02-02 | 2026-11-24 | 2102358341 | 8202238808 |  | 26_2102347680#[CR] Penggantian oil filte | RU4-UTL | 051G103/00 | 60 | CLSD CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C1H | 27099099 | 0 | MA5-ROT |  | TONNYADI | 2026-03-24 | 2026-02-12 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-02-10 | 2026-02-12 | 2026-02-02 | 2026-11-24 | 2102358312 | 8202238819 |  | 26_2102347672#[CR] Penggantian bearing 2 | RU4-LOC1 | 21P17/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-7-C1H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-10 | 2026-02-27 | 2026-03-25 | 2026-10-20 | 2102358291 | 8202238815 |  | 26_2102347663#[CR] 014K102A high tempera | RU4-FOC2 | 014K102A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-2-C1H | 9732252 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-02-10 | 2026-03-12 | 2026-02-02 | 2026-11-24 | 2102358344 | 8202238812 |  | 26_2102347619#[CR] Penggantian oil filte | RU4-UTL | 51G201/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 23358162 | 7786054 | MA5-ROT |  | YMOHAMMAD | 2026-03-30 | 2026-03-09 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-04-09 | 2026-06-22 | 2026-03-03 | 2026-12-22 | 2102356452 | 8202242239 |  | 26_2102347473#[CR] Mech Seal IB Pompa 54 | RU4-UTL1 | 540P401A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 530250 | 0 | MA5-ROT |  | SAMSUDINH |  | 2026-06-22 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-03 | 2026-02-18 | 2026-11-23 | 2102357018 | 8202239326 |  | 26_2102347327#[CR] Perbaikan pompa 47P10 | RU4-TRML | 47P101A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 159358764 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-11-30 | 2102357211 | 8202242792 |  | 26_2102347287#[PV] Penggantian Connector | RU4-RFCC | 101K501/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 1648843 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-08 | 2026-02-02 | 2026-08-03 | 2102355029 | 8202242219 |  | 26_2102347003#Hidraulik 024S-101C bengko | RU4-LOC2 | 024S101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-STA |  | WAHYUCATUR |  | 2026-04-08 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-20 | 2026-03-13 | 2026-03-05 | 2026-12-30 | 2102356695 | 8202238988 |  | 26_2102346822#[PV] Pemeliharaan FT-42 | RU4-K3LL | FT42/00 | 50 | REL GMCO NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 113749065 | 0 | WS-KAB |  | AGHANIAKBAR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-13 | 2026-03-17 | 2026-03-17 | 2026-12-30 |  | 8202241674 | 8202238988 | 26_2102346822#[PV] Pemeliharaan FT-42 | RU4-K3LL | FT42/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 7897396 | 7897396 | WS-KAB |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-02-19 | 2026-03-13 | 2026-02-23 | 2026-12-30 | 2102356691 | 8202238969 |  | 26_2102346804#[PV] Pemeliharaan FT-39 | RU4-K3LL | FT39/00 | 50 | REL GMCO NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 254087933 | 0 | WS-KAB |  | AGHANIAKBAR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-03-13 | 2026-03-17 | 2026-03-17 | 2026-12-30 |  | 8202241676 | 8202238969 | 26_2102346804#[PV] Pemeliharaan FT-39 | RU4-K3LL | FT39/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 4636137 | 4636137 | WS-KAB |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-02-19 | 2026-03-16 | 2026-02-10 | 2026-12-30 | 2102356615 | 8202238967 |  | 26_2102346801#[PV] Pemeliharaan FT-27 | RU4-K3LL | FT27/00 | 50 | REL GMCO NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C1H | 37343144 | 0 | WS-KAB |  | AGHANIAKBAR |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-11 | 2026-02-12 | 2026-02-02 | 2026-09-22 | 2102357248 | 8202238856 |  | 26_2102346732#[CR] Perbaikan Turbin 101P | RU4-RFCC | 101P501A-T/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 33942000 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-19 | 2026-02-19 | 2026-02-02 | 2026-02-02 | 2102354659 | 8202238962 |  | 26_2102345949#[CR] Perbaikan FT 27 | RU4-K3LL | FT27/00 | 50 | CLSD NCMP NMAT PRC | 4RR |  | 37343144 | 0 | WS-KAB |  | YUNITAMR |  |  | PT02 | 3 | 2 | 2026-02-19 | PM |  | 003
| K401 | 2026-02-19 | 2026-03-05 | 2026-03-05 | 2026-12-30 | 2102354655 | 8202238970 |  | 26_2102345948#[CR] Perbaikan FT 29 | RU4-K3LL | FT29/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 136172301 | 0 | WS-KAB |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-19 | 2026-03-05 | 2026-03-05 | 2026-12-30 | 2102354657 | 8202238971 |  | 26_2102345946#[CR] Perbaikan FT 40 | RU4-K3LL | FT40/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 4799539 | 0 | WS-KAB |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-02-19 | 2026-03-05 | 2026-03-05 | 2026-12-30 | 2102354653 | 8202238972 |  | 26_2102345945#[CR] Perbaikan FT 41 | RU4-K3LL | FT41/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 4799539 | 0 | WS-KAB |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-12 | 2026-05-07 | 2026-12-30 | 2102353827 | 8202243069 |  | 26_2102345397#[CR] Penggantian purifier | RU4-UTL | 51G1T/00 | 01 | CLSD CSER NCMP NMAT PRC | 4RR | D14/XX/B6/RT-C2NH | 0 | 0 | MA3-ROT |  | ABDULFM |  |  | PT02 | 3 | 2 | 2026-05-12 | PM |  | 045
| K401 | 2026-02-13 | 2026-03-06 | 2026-02-13 | 2026-12-30 | 2102354374 | 8202238906 |  | 26_2102344776#Spare Oil Gun Dapur KPC - |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 20 | 0 | MA4-STA |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 5 | 3 | 2026-02-13 | PM |  | 045
| K401 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-11-30 | 2102357365 | 8202242678 |  | 26_2102344443#[PV] Penyiapan Material 63 | RU4-RFCUTL | 63P501A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-11-30 | 2102357361 | 8202242675 |  | 26_2102344442#[PV] Penyiapan Material 63 | RU4-TRML | 63P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-03 | 2026-02-04 | 2026-12-22 | 2102357267 | 8202239327 |  | 26_2102344413#[CR] Perbaikan 47P101B (ge | RU4-TRML | 47P101B/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 159358764 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-04 | PM |  | 003
| K401 | 2026-02-26 | 2026-04-29 | 2026-02-02 | 2026-10-27 | 2102357612 | 8202239175 |  | 26_2102344408#[CR] 018P702B mechseal boc | RU4-FOC2 | 018P102B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 47883471 | 12741335 | MA2-ROT |  | YUNITAMR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2102358036 | 8202244046 |  | 26_2102344283#[CR] 013K101A low flow | RU4-FOC2 | 013K101A/01 | 50 | CRTD CSER MACM PRC | 4RR |  | 674799114 | 0 | MA2-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-23 | PM |  | 003
| K401 | 2026-05-06 | 2026-06-03 | 2026-05-06 | 2026-11-26 | 2102357792 | 8202243041 |  | 26_2102343803#[CR] Follow Up Temuan PM 5 | RU4-UTL | 590A301K2/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 3 | 0 | MA5-ROT |  | ABDULFM |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-04-21 | 2026-11-26 | 2102354064 | 8202242381 |  | 26_2102342126#[CR] Perbaikan Purifier Pu | RU4-FOC1 | 14K1-OP/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-02 | 2026-04-24 | 2026-02-10 | 2026-11-25 | 2102353814 | 8202239325 |  | 26_2102341325#Penggantian filter pelumas | RU4-TRML | 47P101B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 3300000 | 3300000 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 2 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-02-26 | 2026-02-27 | 2026-02-02 | 2026-11-23 | 2102354170 | 8202239185 |  | 26_2102341137#[CR] 018P103A mechseal boc | RU4-FOC2 | 018P103A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 89508800 | 89508800 | MA2-ROT |  | ABDULFM |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-11-26 | 2102353481 | 8202241716 |  | 26_2102340303#Blade Finfan 140E607 DBM P | RU4-GTO | 140E607D-B/00 | 60 | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 141355165 | 0 | MA7-ROT |  | ABDULFM |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-02-13 | 2026-02-18 | 2026-02-18 | 2026-12-22 | 2102353498 | 8202238914 |  | 26_2102340118#[CR] Penggantian belt 16K1 | RU4-FOC1 | 16K1/01 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-02-18 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-25 | 2026-11-26 | 2102354036 | 8202239110 |  | 26_2102339994# Gearbox 66M201B Rusak | RU4-TRML | 66M201B/00 | 60 | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 42417750 | 0 | MA4-ROT |  | BADIPUTRO |  | 2026-02-25 | PT02 | 5 | 3 | 2026-02-25 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-22 | 2026-06-15 | 2026-12-29 | 2102354808 | 8202243859 |  | 26_2102339765#91K401B, perbaikan finfan | RU4-SRU | 91K401BEM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 4 | 3 | 2026-06-15 | PM |  | 003
| K401 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-11-26 | 2102356189 | 8202239143 |  | 26_2102339414#[CR] 11P8A Vibrasi dan Ind | RU4-FOC1 | 11P8A/00 | 60 | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2645737 | 2645737 | MA1-ROT |  | BADIPUTRO |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 003
| K401 | 2026-03-17 | 2026-03-25 | 2026-03-25 | 2026-10-29 | 2102353563 | 8202241814 |  | 26_2102338162#89E207D belt fin fan rusak | RU4-KPC | 89E207KD/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 335303 | 0 | MA4-ROT |  | ABDULFM |  | 2026-03-25 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-11-26 | 2102365734 | 8202241319 |  | 26_2102326314#[CR] Penggantian belt mixe | RU4-TRML | 36M105A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 1900000 | 0 | MA3-ROT |  | ABDULFM |  | 2026-03-06 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-11-02 | 2102367638 | 8202242264 |  | 26_180T602P1BM noise di motor | RU4-GTO | 180T602P1BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | TEGARPRAMUDY |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 045
| K401 | 2026-03-09 | 2026-04-27 | 2026-04-27 | 2026-12-29 | 2102366256 | 8202241466 |  | 26_140TG102 rusak | RU4-GTO | 140TI102/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-27 | 2026-04-27 | 2026-12-29 | 2102366255 | 8202241465 |  | 26_140TG030 penunjukkan hunting | RU4-GTO | 140TI030/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-11-30 | 2102367779 | 8202242832 |  | 26_140E607 JBM indikasi noise dimotor | RU4-GTO | 140E607J-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 1194650 | 0 | MA7-LIS |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K401 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-09-30 | 2102368184 | 8202242829 |  | 26_140E607 FBM indikasi noise dimotor | RU4-GTO | 140E607F-B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-LIS |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K401 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-11-30 | 2102367770 | 8202242831 |  | 26_140E607 DAM indikasi noise dimotor | RU4-GTO | 140E607D-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 1194650 | 0 | MA7-LIS |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K401 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-11-30 | 2102368160 | 8202242830 |  | 26_140-E-607 LBM pulley motor rusak | RU4-GTO | 140E607L-B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-14-C2H | 1194650 | 0 | MA7-LIS |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K401 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-10-29 | 2102366314 | 8202241809 |  | 26_120K601B Module Kondisi Unhealthy | RU4-GTO | 120K601B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-27 | 2026-04-27 | 2026-12-29 | 2102365292 | 8202241476 |  | 26_100TG620 rusak | RU4-GTO | 100TI620/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-27 | 2026-04-27 | 2026-12-29 | 2102365787 | 8202241472 |  | 26_100TG609 rusak | RU4-GTO | 100TI609/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-14 | 2026-04-14 | 2026-12-29 | 2102365293 | 8202241474 |  | 26_100PG602B rusak | RU4-GTO | 100PI603B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102368643 | 8202243075 |  | 26_025PV007A Positioner Rusak | RU4-LOC2 | 025PV007A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-19 | 2026-02-19 | 2026-12-30 | 2102356279 | 8202238711 |  | 26_024PT024 Error | RU4-LOC2 | 024PT024/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-19 | PT02 | 5 | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102368642 | 8202243074 |  | 26_024LV009A Positioner Rusak | RU4-LOC2 | 024LV009A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-25 | 2026-05-25 | 2026-12-30 | 2102368641 | 8202243073 |  | 26_024LT021 Transmitter Rusak | RU4-LOC2 | 024LT021/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-04-16 | 2026-05-21 | 2026-04-22 | 2026-12-10 | 2102367844 | 8202242499 |  | 26_024LT-049 Rusak | RU4-LOC2 | 024LT049/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 20056471 | 0 | MA2-INT |  | YMOHAMMAD |  | 2026-04-23 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-06 | 2026-05-05 | 2026-12-29 | 2102368557 | 8202242939 |  | 26_024FV-029 Positioner Rusak | RU4-LOC2 | 024FV029/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-05-06 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-09 | 2026-12-30 | 2102357435 | 8202238719 |  | 26_023LT-702 Rusak |  | 023LT702/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-09 | 2026-12-30 | 2102357434 | 8202238718 |  | 26_023LT-012 Rusak | RU4-LOC2 | 023LT012/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-09 | 2026-12-30 | 2102357431 | 8202238716 |  | 26_023FT-705 Rusak | RU4-LOC2 | 023FT704/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-09 | 2026-12-30 | 2102357379 | 8202238717 |  | 26_023FT-704 Rusak | RU4-LOC2 | 023FT704/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-12-22 | 2102369343 | 8202243518 |  | 26_022LT022 Penunjukkan Error | RU4-LOC2 | 022LT022/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-02-23 | 2026-02-25 | 2026-02-25 | 2026-12-30 | 2102364532 | 8202239057 |  | 26_021LT-016 Penunjukan Error | RU4-LOC2 | 021LT016/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-09 | 2026-12-30 | 2102357375 | 8202238715 |  | 26_021LT-013 Rusak | RU4-LOC2 | 021LT013/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-02-06 | 2026-02-13 | 2026-02-09 | 2026-12-30 | 2102357373 | 8202238714 |  | 26_021LT-012 Rusak | RU4-LOC2 | 021LT012/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-10-29 | 2102366680 | 8202241801 |  | 26_021FV-057A Rusak |  | 021FV012/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-08 | 2026-04-07 | 2026-10-22 | 2102366774 | 8202241890 |  | 26_021FT105 Rusak | RU4-LOC2 | 021FT105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-02-27 | 2026-03-27 | 2026-02-27 | 2026-12-30 | 2102364939 | 8202239264 |  | 26_021FT-042 Penunjukan Error | RU4-LOC2 | 021FT042/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 1 | 0 | MA2-INT |  | YOHANESMVIS |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 003
| K401 | 2026-05-07 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102368559 | 8202243072 |  | 26_021FT-004 Penunjukan Error | RU4-LOC2 | 021FT004/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-06 | 2026-03-05 | 2026-09-29 | 2102364797 | 8202239212 |  | 26_018LT033 rusak | RU4-FOC2 | 018LTC033/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 1 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-12-29 | 2102368040 | 8202242569 |  | 26_017FI_007 rusak | RU4-FOC2 | 017FI007/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-12-30 | 2102365080 | 8202239291 |  | 26_015FT-007 penunjukan ngacau | RU4-FOC2 | 015FT007/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 16650000 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-08 | 2026-04-07 | 2026-10-22 | 2102367019 | 8202242108 |  | 26_014FT382 eror | RU4-FOC2 | 014FT382/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-08 | 2026-04-07 | 2026-10-22 | 2102367050 | 8202242107 |  | 26_014FT379 eror | RU4-FOC2 | 014FT379/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-06-04 | 2026-06-21 | 2026-06-08 | 2026-12-30 | 2102369477 | 8202243639 |  | 26_014FT011B Transmitter Rusak | RU4-FOC2 | 014FT011B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-08 | PM |  | 003
| K401 | 2026-06-15 | 2026-06-19 | 2026-06-17 | 2026-12-29 | 2102369825 | 8202243853 |  | 26_014FT009 penunjukan meragukan | RU4-FOC2 | 014F103/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 33600000 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-08 | 2026-04-07 | 2026-10-22 | 2102367051 | 8202242105 |  | 26_014FT 362 eror | RU4-FOC2 | 014FT362/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-03-30 | 2026-04-15 | 2026-03-30 | 2026-07-29 | 2102366511 | 8202241942 |  | 26_013P108AM : Motor vibrasi 6,69 | RU4-FOC2 | 013P108AM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 893400 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 045
| K401 | 2026-02-12 | 2026-03-06 | 2026-02-26 | 2026-12-22 | 2102364102 | 8202238893 |  | 26_012FT014 Penunjukan meragukan | RU4-FOC2 | 012FT014/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-12-29 | 2102368098 | 8202242560 |  | 26_012FT-024 rusak | RU4-FOC2 | 012FT024/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 16650000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-03-06 | 2026-04-23 | 2026-03-06 | 2026-10-29 | 2102364834 | 8202241295 |  | 26_011P128BM couplin motor rusak | RU4-FOC2 | 011P128BM/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 901200 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-24 | 2026-06-29 | 2102364042 | 8202239134 |  | 26_011P106AM vibrasi | RU4-FOC2 | 011P106AM/00 | 50 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 21500000 | 21500000 | MA2-LIS |  | WAHYUCATUR |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 045
| K401 | 2026-05-06 | 2026-06-19 | 2026-05-06 | 2026-12-21 | 2102367773 | 8202243030 |  | 26_011P-120A SUB STANDART LAMPU AREA FOC | RU4-FOC2 | 011P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-05-06 | 2026-06-19 | 2026-05-06 | 2026-12-21 | 2102367774 | 8202243032 |  | 26_011P-120A SUB STANDART LAMPU AREA FOC | RU4-FOC2 | 011P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-05-07 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 045
| K401 | 2026-04-06 | 2026-04-08 | 2026-04-07 | 2026-10-22 | 2102367197 | 8202242104 |  | 26_011FT-032 rusak | RU4-FOC2 | 011FT032/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 0 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-03-06 | 2026-06-03 | 2026-03-06 | 2026-10-29 | 2102364878 | 8202241294 |  | 26_011E110K29 Hub Pulley motor aus | RU4-FOC2 | 011E110K29/00 | 60 | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-LIS |  | FARIZSETYANA |  | 2026-04-15 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-06-17 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369066 | 8202243888 |  | 26_[UPGRD] API Plan 011P112B | RU4-FOC2 | 011P112B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 130000002 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369065 | 8202243887 |  | 26_[UPGRD] API Plan 011P110A | RU4-FOC2 | 011P110A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 130000002 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-14 | 2026-06-03 | 2026-05-18 | 2026-07-15 | 2102367944 | 8202243206 |  | 26_[SL] Peremajaan Pully Finfan 107E50 | RU4-RFCGTO | 107E503A-K1/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 47403348 | 2031000 | MA7-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-03 | 2026-05-12 | 2026-07-30 | 2102368661 | 8202243138 |  | 26_[SL] Perbaikan 11P8B | RU4-FOC1 | 11P8B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 74490000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-19 | 2026-05-12 | 2026-07-30 | 2102368660 | 8202243137 |  | 26_[SL] Penyehatan fin fan 11E52E | RU4-FOC1 | 11E52K-E/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-20 | 2026-03-12 | 2026-06-29 | 2102366132 | 8202241646 |  | 26_[SL] Penggantian shearpin 24E-1A (pat | RU4-LOC1 | 24E1A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 12000000 | 12000000 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-03 | 2026-05-12 | 2026-07-30 | 2102368629 | 8202243136 |  | 26_[SL] Penggantian pully fin 11E50Q | RU4-FOC1 | 11E50K-Q/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 117000000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102368473 | 8202243556 |  | 26_[SL] Penggantian mechanical seal 17P1 | RU4-FOC1 | 17P1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 57000000 | 0 | MA1-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-19 | 2026-05-12 | 2026-07-30 | 2102368472 | 8202243150 |  | 26_[SL] Penggantian mechanical seal 11P5 | RU4-FOC1 | 11P5/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102368496 | 8202243557 |  | 26_[SL] Penggantian cooler 11P4B | RU4-FOC1 | 11P4B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 659350000 | 0 | MA1-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-12 | 2026-05-21 | 2026-05-12 | 2026-07-30 | 2102367945 | 8202243158 |  | 26_[SL] Penggantian Belt Fin-Fan Area GT | RU4-RFCGTO |  | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 1874321 | 1874321 | MA7-ROT |  | AGHANIAKBAR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-05-12 | 2026-06-22 | 2026-04-28 | 2026-11-24 | 2102368374 | 8202243144 |  | 26_[SL] Penggantian Belt 11E61A | RU4-FOC1 | 11E61K-A/00 | 60 | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-05-14 | 2026-06-03 | 2026-05-18 | 2026-07-29 | 2102367942 | 8202243207 |  | 26_[SL] Pengadaan Kopkit 107-A-501 P1&P2 | RU4-RFCGTO | 107A501P1/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 93812000 | 46906000 | MA7-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-22 | 2026-06-19 | 2026-12-22 | 2102368663 | 8202243681 |  | 26_[SL] Overhaul pompa 13P2 | RU4-FOC1 | 13P2/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 216846000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-22 | 2026-05-04 | 2026-05-04 | 2102368662 | 8202243680 |  | 26_[SL] Overhaul Pompa 12P1 | RU4-FOC1 | 12P1/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 1042395056 | 0 | MA1-ROT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-29 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102368375 | 8202243545 |  | 26_[SL] Overhaul 11P-23A | RU4-FOC1 | 11P23A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 143272680 | 0 | MA1-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-14 | 2026-06-03 | 2026-05-18 | 2026-07-30 | 2102367943 | 8202243208 |  | 26_[SL] 148P503A Mech Seal Bocor | RU4-RFCGTO | 148P503A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 90000000 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-12-30 | 2102365810 | 8202241670 |  | 26_[PV] Preventive Maintenance 180A601K1 | RU4-GTO | 180A601K1A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 33 | 0 | MA7-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-12-30 | 2102365811 | 8202241671 |  | 26_[PV] Preventive Maintenance 180A601K1 | RU4-GTO | 180A601K1B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 33 | 0 | MA7-ROT |  | YUNITAMR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-27 | 2026-04-22 | 2026-09-29 | 2102365142 | 8202242634 |  | 26_[PV] Perbaikan pompa 63P1C | RU4-TRML | 63P1C/00 | 50 | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA5-ROT |  | YUNITAMR |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-27 | 2026-04-22 | 2026-09-29 | 2102365141 | 8202242632 |  | 26_[PV] Perbaikan pompa 63P1B | RU4-TRML | 63P1B/00 | 50 | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | YUNITAMR |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-10-29 | 2102365140 | 8202242631 |  | 26_[PV] Perbaikan pompa 63P1A | RU4-TRML | 63P1A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 4 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-22 | PT02 | 3 | 3 | 2026-04-22 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-15 | 2026-04-06 | 2026-11-30 | 2102364560 | 8202242103 |  | 26_[PV] Perbaikan Pompa 54P202D | RU4-UTL | 54P202D/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 17527742 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-15 | 2026-04-06 | 2026-12-22 | 2102364549 | 8202242102 |  | 26_[PV] Perbaikan Pompa 54P202C | RU4-UTL | 54P202C/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 17527742 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-15 | 2026-04-06 | 2026-11-30 | 2102364548 | 8202242100 |  | 26_[PV] Perbaikan Pompa 54P202B | RU4-UTL | 54P202B/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 17527742 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-08 | 2026-04-07 | 2026-10-22 | 2102366135 | 8202241655 |  | 26_[PV] Penggantian PI rusak Area FOC II | RU4-FOC2 | 011P121A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/25/B6/RTC-2-C2H | 2439818 | 0 | MA2-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-04-27 | 2026-05-21 | 2026-04-27 | 2026-06-29 | 2102368109 | 8202242741 |  | 26_[PV] Penggantian filter lube oil 54P1 | RU4-UTL | 54P1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 11743000 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-27 | 2026-05-21 | 2026-04-27 | 2026-06-29 | 2102368127 | 8202242742 |  | 26_[PV] Penggantian Filter Lube Oil 510G | RU4-UTL | 510G601-S1A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 207000000 | 51750000 | MA5-ROT |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-20 | 2026-03-03 | 2026-05-29 | 2102364172 | 8202239340 |  | 26_[PV] Penggantian coupling 11P10A | RU4-FOC1 | 11P10A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 31550000 | 31550000 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-05-29 | 2026-06-20 | 2026-06-17 | 2026-12-22 | 2102368397 | 8202243546 |  | 26_[PV] Pengadaan Coupling 11P7A | RU4-FOC1 | 11P7A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-03 | 2026-05-12 | 2026-09-29 | 2102368402 | 8202243146 |  | 26_[PV] Pengadaan Coupling 11P7 | RU4-FOC1 | 11P7/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368282 | 8202242914 |  | 26_[PV] Pengadaan Carbon Ring 14P607AT | RU4-FOC1 | 14P607A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 9984000 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-04-21 | 2026-05-21 | 2026-04-21 | 2026-07-20 | 2102368013 | 8202242621 |  | 26_[PV] Mech Seal Pompa 103-P-514B Bocor | RU4-RFCC | 103P514B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 138027146 | 0 | MA6-ROT |  | YMOHAMMAD |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-04-21 | 2026-05-21 | 2026-04-21 | 2026-07-20 | 2102368011 | 8202242620 |  | 26_[PV] Mech Seal Pompa 103-P-514A Bocor | RU4-RFCC | 103P514A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 147223504 | 0 | MA6-ROT |  | YMOHAMMAD |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369301 | 8202243798 |  | 26_[PV] Desicant Breather 89P208B tidak | RU4-KPC | 89P208B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369300 | 8202243797 |  | 26_[PV] Desicant Breather 89P208A tidak | RU4-KPC | 89P208A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369296 | 8202243791 |  | 26_[PV] Desicant Breather 85P217B tidak | RU4-KPC | 85P217B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4913172 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369295 | 8202243790 |  | 26_[PV] Desicant Breather 85P217A tidak | RU4-KPC | 85P217A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4913172 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369294 | 8202243787 |  | 26_[PV] Desicant Breather 84P206B tidak | RU4-KPC | 84P206B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4913172 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369293 | 8202243786 |  | 26_[PV] Desicant Breather 84P206A tidak | RU4-KPC | 84P206A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4913172 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369299 | 8202243795 |  | 26_[PV] Desicant Breather 84P203B tidak | RU4-KPC | 84P203B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369298 | 8202243793 |  | 26_[PV] Desicant Breather 84P203A tidak | RU4-KPC | 84P203A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369297 | 8202243792 |  | 26_[PV] Desicant Breather 82P205 tidak | RU4-KPC | 82P205/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369292 | 8202243785 |  | 26_[PV] Desicant Breather 39P204B tidak | RU4-KPC | 39P204B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4913172 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369291 | 8202243784 |  | 26_[PV] Desicant Breather 39P204A tidak | RU4-KPC | 39P204A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4913172 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369302 | 8202243800 |  | 26_[PV] Desicant Breather 39P201 tidak a | RU4-KPC | 39P201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4913172 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369380 | 8202243561 |  | 26_[PV] 041P106A Penggantian Cyclone | RU4-TRML | 041P106A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369080 | 8202243889 |  | 26_[PV] 018K101A - PM kompressor | RU4-FOC2 | 018K101A/00 | 60 | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 96831864 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369031 | 8202243813 |  | 26_[PV] 011K101BP2 coupling rusak | RU4-FOC2 | 011K101B-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-21 | 2026-06-17 | 2026-12-30 | 2102369030 | 8202243812 |  | 26_[PV] 011K101AP2 coupling rusak | RU4-FOC2 | 011K101A-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-09-29 | 2102368227 | 8202242743 |  | 26_[PD]Pengadaan impeler 240P119 | RU4-LOC3 | 240P119/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 4 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-06-29 | 2102363906 | 8202241855 |  | 26_[NP] Pompa mixer ASA: noise & vib tin | RU4-FOC2 | 013S105BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-10-28 | 2102363569 | 8202241965 |  | 26_[CR]Tetesan lubricator 260K101A tidak | RU4-LOC3 | 260K101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-31 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-03-22 | 2026-03-25 | 2026-03-25 | 2026-07-30 | 2102363568 | 8202241846 |  | 26_[CR]Tetesan lubricator 220K101 tidak | RU4-LOC3 | 220K101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-16 | 2026-03-12 | 2026-11-30 | 2102366147 | 8202241645 |  | 26_[CR]Tandem seal bocor out board 220P1 | RU4-LOC3 | 220P104A/00 | 60 | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 6524400 | 6524400 | MA4-ROT |  | ABDULFM |  | 2026-03-13 | PT02 | 2 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-26 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368226 | 8202243517 |  | 26_[CR]Shoulder half ring 260k101/102B | RU4-LOC3 | 260K101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-31 | 2026-04-06 | 2026-03-31 | 2026-10-30 | 2102363560 | 8202241964 |  | 26_[CR]Pompa goyang & under perform 200P | RU4-LOC3 | 200P101A/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | ABDULFM |  | 2026-03-31 | PT02 | 4 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-24 | 2026-03-13 | 2026-06-29 | 2102365156 | 8202241693 |  | 26_[CR]Perlumas gearbox 240P105 rembes | RU4-LOC3 | 240P105/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 20701800 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-16 | PT02 | 2 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-10-28 | 2102365238 | 8202242571 |  | 26_[CR]Perbaikan Pompa Injeksi 106A502P2 | RU4-RFCGTO | 106A502P2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 98100000 | 98100000 | MA7-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102366978 | 8202242613 |  | 26_[CR]Penggantian Membran Kopling 153P5 | RU4-RFCUTL | 153P501A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 115000000 | 115000000 | MA5-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-09-10 | 2102367576 | 8202243215 |  | 26_[CR]Penggantian Filter LO 11K401 (Tim | RU4-FOC1 | 11K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 36801000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-09 | 2026-02-24 | 2026-12-28 | 2102364881 | 8202241329 |  | 26_[CR]Noise pada bearing scroll 240S101 | RU4-LOC3 | 240S101AM2/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-09 | PT02 | 2 | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-10-29 | 2102368315 | 8202243249 |  | 26_[CR]Modul straight flow valve 220K101 | RU4-LOC3 | 220K101/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-06 | 2026-05-04 | 2026-03-06 | 2026-05-29 | 2102364279 | 8202241300 |  | 26_[CR]Mechanical seal bocor 260P159A | RU4-LOC3 | 260P159A/00 | 60 | REL CSER GMCO GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4596140 | 4596140 | MA4-ROT |  | AGHANIAKBAR |  | 2026-03-06 | PT02 | 2 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-05-25 | 2026-06-19 | 2026-05-25 | 2026-11-30 | 2102367697 | 8202243442 |  | 26_[CR]Mechanical seal bocor 240P105 | RU4-LOC3 | 240P105/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 4 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-06-29 | 2102363562 | 8202241847 |  | 26_[CR]Mechanical seal bocor 240P102B | RU4-LOC3 | 240P102B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 50600000 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-10-29 | 2102364278 | 8202241967 |  | 26_[CR]Kerusakan loader valve 1st, recy | RU4-LOC3 | 260K101A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-31 | PT02 | 6 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-03-09 | 2026-11-03 | 2102366392 | 8202242383 |  | 26_[CR]Kawat filter 240S101D kendor | RU4-LOC3 | 240S101D/00 | 60 | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 48495919 | 0 | MA4-ROT |  | ABDULFM |  | 2026-04-20 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-24 | 2026-04-09 | 2026-07-30 | 2102364100 | 8202242278 |  | 26_[CR]Gearbox scroll macet 240S101AM2 | RU4-LOC3 | 240S101AM2/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 130500000 | 130500000 | MA4-ROT |  | YMOHAMMAD |  | 2026-04-10 | PT02 | 2 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-06-03 | 2026-06-22 | 2026-06-17 | 2026-12-22 | 2102368512 | 8202243612 |  | 26_[CR]Cap main bearing, bushing 260K101 | RU4-LOC3 | 260K101B/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 880800000 | 0 | MA4-ROT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-06-29 | 2102364099 | 8202241839 |  | 26_[CR]Bocoran plunger timur 260P104A | RU4-LOC3 | 260P104A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 5385165 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 1 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-08-27 | 2102364449 | 8202241968 |  | 26_[CR]Bocoran packing rod 3rd stg 260K1 | RU4-LOC3 | 260K101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 32868000 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-31 | PT02 | 5 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-03-13 | 2026-05-19 | 2026-03-13 | 2026-12-30 | 2102364760 | 8202241707 |  | 26_[CR]Bocoran mechanical seal 240P102A | RU4-LOC3 | 240P102A/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 82702450 | 82702450 | MA4-ROT |  | SAMSUDINH |  | 2026-03-16 | PT02 | 4 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-17 | 2026-03-25 | 2026-03-25 | 2026-12-22 | 2102366761 | 8202241817 |  | 26_[CR]Belt finfan putus 260E122B | RU4-LOC3 | 260E122BK/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 2400000 | 2400000 | MA4-ROT |  | ABDULFM |  | 2026-03-25 | PT02 | 1 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-11-25 | 2102365259 | 8202241303 |  | 26_[CR]Belt fin fan putus 260E122A | RU4-LOC3 | 260E122AK/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 1200000 | 1200000 | MA4-ROT |  | ABDULFM |  | 2026-03-06 | PT02 | 1 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-13 | 2026-05-04 | 2026-07-30 | 2102367768 | 8202242918 |  | 26_[CR]Belt fin fan putus 240E116A | RU4-LOC3 | 240E116K1/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 7270939 | 7270939 | MA4-ROT |  | ABDULFM |  | 2026-05-05 | PT02 | 1 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-12-31 | 2102367450 | 8202243374 |  | 26_[CR] Speed Variator 024S101D Low Perf | RU4-LOC2 | 024S101D/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA2-ROT |  | ABDULFM |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-05-11 | 2026-05-18 | 2026-03-25 | 2026-12-31 | 2102366883 | 8202243111 |  | 26_[CR] Speed Variator 024S101C Noise | RU4-LOC2 | 024S101C/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/NR-8-C2H | 0 | 0 | MA2-ROT |  | ABDULFM |  | 2026-05-18 | PT02 | 4 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-06-03 | 2026-03-25 | 2026-05-29 | 2102366388 | 8202241829 |  | 26_[CR] Shearpin 024E102B Patah | RU4-LOC2 | 024E102B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 2546160 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 2026-11-30 | 2102367703 | 8202243226 |  | 26_[CR] Regreasing T&T Valve 104K501 | RU4-RFCC | 104K501/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 71250000 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 2026-11-30 | 2102367702 | 8202243227 |  | 26_[CR] Regreasing T&T Valve 102K501 | RU4-RFCC | 102K501/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 71250000 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 8 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-06 | 2026-04-01 | 2026-12-30 | 2102367232 | 8202242078 |  | 26_[CR] Refurbishment Rotor FD Fan 52B3K | RU4-UTL | 52B3K/00 | 50 WAMA | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 100000 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-17 | 2026-04-15 | 2026-11-19 | 2102364912 | 8202241899 |  | 26_[CR] Pressure Switch 107-PAH902B Rusa | RU4-RFCC | 107FT002/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-11 | 2026-03-17 | 2026-11-17 | 2102366744 | 8202242972 |  | 26_[CR] Pompa 87P203A Noise Bearing sisi | RU4-KPC | 87P203A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 534587 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-05-11 | PT02 | 5 | 3 | 2026-03-17 | PM |  | 003
| K401 | 2026-03-10 | 2026-04-24 | 2026-03-10 | 2026-10-29 | 2102366284 | 8202241553 |  | 26_[CR] Pompa 39P208B Mech Seal IB Leak | RU4-TRML | 39P208B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 338066576 | 338066576 | MA4-ROT |  | YMOHAMMAD |  | 2026-03-11 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-20 | 2026-03-13 | 2026-08-31 | 2102366283 | 8202241686 |  | 26_[CR] Pompa 39P205B Mech Seal Leak | RU4-TRML | 39P205B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 73505546 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-05-11 | 2026-05-18 | 2026-04-14 | 2026-12-14 | 2102366794 | 8202243108 |  | 26_[CR] permintaan level glass pelumas p | RU4-FOC2 | 014P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 045
| K401 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-09-29 | 2102364563 | 8202241866 |  | 26_[CR] Perbaikan Turbine 57P102AT | RU4-UTL | 57P102AT/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 26172471 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-09-29 | 2102364562 | 8202241867 |  | 26_[CR] Perbaikan Turbine 54P202DT | RU4-UTL | 54P202D-T/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 27632440 | 3454055 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-26 | 2026-04-17 | 2026-03-26 | 2026-09-29 | 2102364561 | 8202241896 |  | 26_[CR] Perbaikan Turbine 54P202CT | RU4-UTL | 54P202C-T/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 1011100 | 1011100 | MA5-ROT |  | ABDULFM |  | 2026-03-26 | PT02 | 3 | 3 | 2026-03-26 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-21 | 2026-05-18 | 2026-09-29 | 2102367595 | 8202243222 |  | 26_[CR] Perbaikan Turbin BFW 154P507BT | RU4-RFCUTL | 154P507B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 85115278 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 5 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-22 | 2026-05-21 | 2026-03-25 | 2026-08-31 | 2102364539 | 8202241835 |  | 26_[CR] Perbaikan Turbin 54P202CT | RU4-UTL | 54P202C-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-05-21 | 2026-03-25 | 2026-05-29 | 2102365229 | 8202241831 |  | 26_[CR] Perbaikan Turbin 530P601AT | RU4-UTL | 530P601A-T/00 | 60 | REL CNF CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 279850 | 279850 | MA5-ROT |  | YMOHAMMAD | 2026-06-12 | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-21 | 2026-04-08 | 2026-08-27 | 2102365007 | 8202242199 |  | 26_[CR] Perbaikan Turbin 52P2AT | RU4-UTL | 52P2A-T/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 33831793 | 21810393 | MA3-ROT |  | ABDULFM |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-23 | 2026-04-09 | 2026-09-29 | 2102365898 | 8202242275 |  | 26_[CR] Perbaikan Turbin 154P505AT | RU4-RFCUTL | 154P505A-T/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 10018665 | 34665 | MA5-ROT |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-16 | 2026-04-08 | 2026-12-09 | 2102367227 | 8202242223 |  | 26_[CR] Perbaikan Turbin 057P101BT | RU4-UTL | 057P101B-T/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 34061891 | 7889420 | MA5-ROT |  | ABDULFM |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-24 | 2026-02-12 | 2026-02-12 | 2102364273 | 8202239342 |  | 26_[CR] Perbaikan Turbin 054P102BT | RU4-UTL | 054P102B-T/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 1414544 | 647100 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-24 | 2026-03-12 | 2026-04-29 | 2102365260 | 8202241660 |  | 26_[CR] Perbaikan Turbin 052P102AT | RU4-UTL | 052P102A-T/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 350000 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-09-29 | 2102367729 | 8202243228 |  | 26_[CR] Perbaikan Turbin 051P101AT | RU4-UTL | 051P101A-T/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 5696593 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-05-12 | 2026-05-21 | 2026-05-12 | 2026-09-29 | 2102368032 | 8202243157 |  | 26_[CR] Perbaikan Temporer 560K301 | RU4-UTL | 560K301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 820051 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-04-02 | 2026-06-12 | 2026-04-02 | 2026-07-29 | 2102364408 | 8202242043 |  | 26_[CR] Perbaikan Sootblower No. 33 COB | RU4-RFCC | 101F503A33/00 | 60 | CLSD CNF CSER GMPS PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 15505500 | 15505500 | MA6-ROT |  | SAPBATCH | 2026-04-13 | 2026-04-02 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-09-29 | 2102364440 | 8202242045 |  | 26_[CR] Perbaikan Sootblower No. 11 COB | RU4-RFCC | 101F503A11/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 3954400 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-03 | 2026-05-12 | 2026-08-31 | 2102368221 | 8202243155 |  | 26_[CR] Perbaikan Seal Oil 14K1 | RU4-FOC1 | 14K1F2A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 87758616 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102368756 | 8202243886 |  | 26_[CR] Perbaikan rotor FD Fan 52B201K | RU4-UTL | 52B201K1/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 3 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-08-31 | 2102367088 | 8202243216 |  | 26_[CR] Perbaikan Pompa MLOP 051G101P1 | RU4-UTL | 051G101P1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 142478442 | 142478442 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-04-27 | 2026-05-04 | 2026-04-29 | 2026-11-30 | 2102367532 | 8202242767 |  | 26_[CR] Perbaikan Pompa Fire 155P503 | RU4-RFCUTL |  | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 236392 | 236392 | MA5-ROT |  | ABDULFM |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 045
| K401 | 2026-04-29 | 2026-05-21 | 2026-04-29 | 2026-08-31 | 2102368055 | 8202242836 |  | 26_[CR] Perbaikan Pompa ex run 054WS101P | RU4-UTL | 054WS101P3/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 18898950 | 18898950 | MA5-ROT |  | ABDULFM |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-11-30 | 2102369499 | 8202243895 |  | 26_[CR] Perbaikan Pompa Equalisasi 47P50 | LOC1-UP4 | 47P504B/00 | 50 WAMA | CRTD CSER MACM PRC | 4MR |  | 12183667 | 0 | MA1-ROT |  | FARENFINIAN |  |  | PT02 | 4 | 2 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-28 | 2026-06-19 | 2026-04-29 | 2026-11-30 | 2102367720 | 8202242795 |  | 26_[CR] Perbaikan Pompa Alop 54P1B | RU4-UTL | 54P1B-P1/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-07-29 | 2102367466 | 8202242751 |  | 26_[CR] Perbaikan Pompa 57P201B | RU4-UTL | 57P201B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 81209643 | 562400 | MA3-ROT |  | WAHYUCATUR |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-10-29 | 2102365008 | 8202242200 |  | 26_[CR] Perbaikan Pompa 57P201A | RU4-UTL | 57P201A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 202362293 | 7568727 | MA5-ROT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-04-23 | 2026-05-21 | 2026-04-24 | 2026-11-30 | 2102366411 | 8202242687 |  | 26_[CR] Perbaikan Pompa 57P1 | RU4-UTL | 57P1/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 414068201 | 128750000 | MA5-ROT |  | YMOHAMMAD |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-19 | 2026-05-18 | 2026-12-30 | 2102367590 | 8202243221 |  | 26_[CR] Perbaikan Pompa 54WS2P3 Leak | RU4-UTL | 54WS2P3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-20 | 2026-03-13 | 2026-06-29 | 2102365060 | 8202241696 |  | 26_[CR] Perbaikan Pompa 54WS2P2 (Spare) | RU4-UTL | 54WS2P2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 30730208 | 4504398 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-07-30 | 2102365125 | 8202241666 |  | 26_[CR] Perbaikan Pompa 54WS1P2 | RU4-UTL | 54WS1P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 4549990 | 0 | MA3-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-04-06 | 2026-05-22 | 2026-04-06 | 2026-11-30 | 2102364547 | 8202242098 |  | 26_[CR] Perbaikan Pompa 54P202A | RU4-UTL | 54P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-20 | 2026-06-17 | 2026-12-22 | 2102368626 | 8202243381 |  | 26_[CR] Perbaikan Pompa 54P1A | RU4-UTL | 54P1A/00 | 60 | CLSD CSER MACM NCMP PRC | 4RR |  | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-06-18 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-24 | 2026-03-12 | 2026-11-25 | 2102364864 | 8202241631 |  | 26_[CR] Perbaikan pompa 47P502B | RU4-RFCGTO | 47P502B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 455416653 | 319848127 | MA7-ROT |  | YMOHAMMAD |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-14 | 2026-06-03 | 2026-05-18 | 2026-09-29 | 2102368000 | 8202243209 |  | 26_[CR] Perbaikan pompa 47P502A | RU4-RFCGTO | 47P502A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 156252106 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-06-03 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102368568 | 8202243614 |  | 26_[CR] Perbaikan Pompa 38P113A | RU4-TRML | 38P113A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 12162350 | 0 | MA3-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102366453 | 8202242601 |  | 26_[CR] Perbaikan Pompa 38P-111B | RU4-TRML | 38P111B/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 7468605 | 7468600 | MA3-ROT |  | WAHYUCATUR |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-04-27 | 2026-05-21 | 2026-04-27 | 2026-07-30 | 2102368267 | 8202242746 |  | 26_[CR] Perbaikan Pompa 37P102B | RU4-TRML | 37P102B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 78838350 | 6928350 | MA3-ROT |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 5 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-02 | 2026-04-20 | 2026-02-02 | 2026-02-02 | 2102355148 | 8202239320 |  | 26_[CR] Perbaikan Pompa 32P102B | RU4-TRML | 32P102B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 12183451 | 12183451 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-23 | 2026-04-28 | 2026-03-25 | 2026-08-27 | 2102360597 | 8202241857 |  | 26_[CR] Perbaikan Pompa 32P102A | RU4-TRML | 32P102A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 12183451 | 0 | MA3-ROT |  | BADIPUTRO |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-19 | 2026-05-22 | 2026-12-30 | 2102368836 | 8202243382 |  | 26_[CR] Perbaikan pompa 260p154a high vi | RU4-LOC3 | 260P154A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-05-22 | PT02 | 2 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-20 | 2026-03-13 | 2026-06-29 | 2102364972 | 8202241698 |  | 26_[CR] Perbaikan pompa 24P-13A | RU4-LOC1 | 24P13A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 6380800 | 6594125 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-20 | 2026-03-03 | 2026-05-29 | 2102364668 | 8202239345 |  | 26_[CR] Perbaikan pompa 21P-9A | RU4-LOC1 | 21P9A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 69355277 | 70148927 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-17 | 2026-03-25 | 2026-03-25 | 2026-12-22 | 2102365239 | 8202241815 |  | 26_[CR] Perbaikan Pompa 180T602 | RU4-GTO | 180T602P1A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-23 | 2026-04-08 | 2026-06-18 | 2102366970 | 8202242232 |  | 26_[CR] perbaikan pompa 154A501CP2 | RU4-RFCUTL | 154A501C-P2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 829350 | 829350 | MA5-ROT |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-18 | 2026-05-18 | 2026-10-29 | 2102367531 | 8202243224 |  | 26_[CR] Perbaikan Pompa 152P502C | RU4-RFCUTL | 152P502C/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 90332700 | 90332700 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-09-29 | 2102366768 | 8202241902 |  | 26_[CR] Perbaikan Pompa 11P8A | RU4-FOC1 | 11P8A/00 | 60 | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 9279607 | 9279607 | MA1-ROT |  | ABDULFM |  | 2026-03-27 | PT02 | 3 | 3 | 2026-03-27 | PM |  | 003
| K401 | 2026-03-13 | 2026-06-21 | 2026-03-13 | 2026-12-30 | 2102364966 | 8202241703 |  | 26_[CR] Perbaikan pompa 11P8A | RU4-FOC1 | 11P8A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 274289846 | 227576397 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-22 | 2026-06-19 | 2026-12-22 | 2102368740 | 8202243684 |  | 26_[CR] Perbaikan Pompa 105P501A Noise | RU4-RFCGTO | 105P501A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 11722300 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-03-06 | 2026-04-23 | 2026-02-20 | 2026-12-22 | 2102364681 | 8202241321 |  | 26_[CR] Perbaikan Pompa 101P502A | RU4-RFCC | 101P502A/00 | 60 | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 26463000 | 19686000 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 3 | 3 | 2026-02-20 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-03-10 | 2026-11-11 | 2102366420 | 8202242380 |  | 26_[CR] Perbaikan Pompa 101A520P5 | RU4-RFCC | 101A520P5/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | ABDULFM |  | 2026-04-20 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-07-29 | 2102368054 | 8202242834 |  | 26_[CR] Perbaikan Pompa 054WS101P2 | RU4-UTL | 054WS101P2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 6688915 | 6688875 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-02-12 | 2026-02-13 | 2026-02-12 | 2026-10-29 | 2102353616 | 8202238890 |  | 26_[CR] Perbaikan Pompa 054P101 Spare | RU4-UTL | 054P101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C1H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-02-13 | PT02 | 7 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-02-26 | 2026-05-22 | 2026-02-26 | 2026-09-29 | 2102364141 | 8202239197 |  | 26_[CR] Perbaikan Pompa 053P101B | RU4-UTL | 053P101B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-26 | 2026-05-22 | 2026-02-26 | 2026-07-29 | 2102364142 | 8202239196 |  | 26_[CR] Perbaikan Pompa 053P101A | RU4-UTL | 053P101A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-05-20 | 2026-05-21 | 2026-05-20 | 2026-08-31 | 2102368771 | 8202243344 |  | 26_[CR] Perbaikan Pompa 052P302A | RU4-UTL | 052P302A/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 7046651 | 7046651 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-05-04 | 2026-06-03 | 2026-05-05 | 2026-10-28 | 2102366683 | 8202242933 |  | 26_[CR] Perbaikan Pompa 052P102B | RU4-UTL | 052P102B/00 | 60 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 2375334 | 2375334 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-08-06 | 2102368855 | 8202243097 |  | 26_[CR] Perbaikan MS IB Pompa 87P204A | RU4-KPC | 87P204A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 28011500 | 4899500 | MA4-ROT |  | WAHYUCATUR |  | 2026-05-08 | PT02 | 4 | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-06-29 | 2102365133 | 8202241323 |  | 26_[CR] Perbaikan MLOP 560K301 | RU4-UTL | 560K301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-06-03 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102368523 | 8202243613 |  | 26_[CR] Perbaikan Mixer 34M2 | RU4-TRML | 34M2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 37326554 | 24109167 | MA3-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-12 | 2026-02-26 | 2026-07-30 | 2102364080 | 8202239199 |  | 26_[CR] Perbaikan membran coupling 57P10 | RU4-UTL | 57P102B/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 67750000 | 33875000 | MA5-ROT |  | AGHANIAKBAR |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-05-11 | 2026-05-18 | 2026-03-31 | 2026-11-25 | 2102367047 | 8202243114 |  | 26_[CR] Perbaikan membran 166P562B | RU4-RFCGTO | 166P562B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-ROT |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-05-11 | 2026-05-18 | 2026-03-31 | 2026-11-24 | 2102367046 | 8202243113 |  | 26_[CR] Perbaikan membran 166P561B | RU4-RFCGTO | 166P561B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-ROT |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-20 | 2026-03-25 | 2026-06-29 | 2102364479 | 8202241838 |  | 26_[CR] Perbaikan MechSeal IB Pompa 46P1 | RU4-TRML | 46P101B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 3375000 | 3375000 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-12-28 | 2102366198 | 8202241335 |  | 26_[CR] Perbaikan Mechseal 101P502A NonO | RU4-RFCC | 101P502A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 302333334 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-05-21 | 2026-03-06 | 2026-12-29 | 2102366199 | 8202241336 |  | 26_[CR] Perbaikan Mechseal 101P501A NonO | RU4-RFCC | 101P501A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-22 | 2026-05-21 | 2026-07-31 | 2102368812 | 8202243390 |  | 26_[CR] Perbaikan Mech Seal Pompa 154P50 | RU4-RFCUTL | 154P505A/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-04-29 | 2102364034 | 8202241843 |  | 26_[CR] Perbaikan mech seal 91P403A-ROT | RU4-SRU | 91P403A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 84209815 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 4 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-21 | 2026-04-20 | 2026-09-29 | 2102366890 | 8202242467 |  | 26_[CR] Perbaikan Mech Seal 47P505A ROT- | LOC1-UP4 | 47P505A/00 | 60 | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 45381742 | 45381031 | MA1-ROT |  | ABDULFM |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369371 | 8202243560 |  | 26_[CR] Perbaikan Mech Seal 105P505A Lea | RU4-RFCGTO | 105P505A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 574402400 | 0 | MA7-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-12-30 | 2102366156 | 8202241644 |  | 26_[CR] Perbaikan Mech Seal 025P101B | RU4-LOC2 | 025P101B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 163047150 | 163047150 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-13 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-05-11 | 2026-03-12 | 2026-10-29 | 2102366155 | 8202241643 |  | 26_[CR] Perbaikan Mech Seal 023P105A | RU4-LOC2 | 023P105A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 12074670 | 12074670 | MA2-ROT |  | EDWINK |  | 2026-03-13 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-09-29 | 2102366154 | 8202241641 |  | 26_[CR] Perbaikan Mech Seal 021P102C | RU4-LOC2 | 021P102C/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 106606850 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-13 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-09-29 | 2102366153 | 8202241640 |  | 26_[CR] Perbaikan Mech Seal 021P102B | RU4-LOC2 | 021P102B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 106606850 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-13 | PT02 | 5 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-03-13 | 2026-03-13 | 2102366657 | 8202242390 |  | 26_[CR] Perbaikan Main Lube Oil Pump 36P | RU4-TRML | 36P101A-P1/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 90440000 | 90440000 | MA4-ROT |  | ABDULFM |  | 2026-04-21 | PT02 | 5 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-22 | 2026-03-25 | 2026-03-25 | 2026-12-30 | 2102364615 | 8202241834 |  | 26_[CR] Perbaikan Loader valve 13K1B | RU4-FOC1 | 13K1B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 9300000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-06-18 | 2026-06-22 | 2026-06-19 | 2026-12-22 | 2102369185 | 8202243935 |  | 26_[CR] Perbaikan Kopling Pompa 053P102B | RU4-UTL | 053P102B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 23464000 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-11 | 2026-03-13 | 2026-11-17 | 2102366686 | 8202242971 |  | 26_[CR] Perbaikan kompressor 56K102 | RU4-UTL | 56K102/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 144896717 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-11 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-10 | 2026-04-08 | 2026-07-30 | 2102367067 | 8202242228 |  | 26_[CR] Perbaikan Kompressor 560K301 | RU4-UTL | 560K301/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 8 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-05-05 | 2026-06-19 | 2026-03-10 | 2026-11-24 | 2102366443 | 8202242970 |  | 26_[CR] Perbaikan I/B Turbine Noise 101F | RU4-RFCC | 101F503P2-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-05-11 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 2026-11-30 | 2102367934 | 8202243231 |  | 26_[CR] Perbaikan Hub City 054P102AT | RU4-UTL | 054P102A-T/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 2052162 | 2052162 | MA3-ROT |  | AGHANIAKBAR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-04-17 | 2026-05-21 | 2026-04-17 | 2026-06-29 | 2102367207 | 8202242547 |  | 26_[CR] Perbaikan Gland Seal 90P404B ROT | RU4-SRU | 90P404B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 945000 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-12-30 | 2102366312 | 8202241494 |  | 26_[CR] Perbaikan FT-39 | RU4-K3LL | FT39/00 | 50 | CRTD NMAT PRC | 4RR |  | 2000000000 | 0 | WS-KAB |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-03-10 | PM |  | 045
| K401 | 2026-02-26 | 2026-05-18 | 2026-02-27 | 2026-11-26 | 2102363577 | 8202239228 |  | 26_[CR] Perbaikan Finfan 102E520A-K2 | RU4-RFCC | 102E520A-K2/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 59199996 | 59199996 | MA6-ROT |  | FARIZSETYANA | 2026-05-18 | 2026-02-27 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369005 | 8202243747 |  | 26_[CR] Perbaikan Fin-Fan 91K401BEM | RU4-SRU | 91K401BEM/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 252400 | 0 | MA1-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-22 | 2026-05-21 | 2026-12-22 | 2102364639 | 8202243380 |  | 26_[CR] Perbaikan fin fan 24E-23A | RU4-LOC1 | 24E23K-A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 30798759 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 5 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-22 | 2026-05-21 | 2026-07-30 | 2102364638 | 8202243377 |  | 26_[CR] Perbaikan fin fan 24E-12B | RU4-LOC1 | 24E12K-B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 30798759 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 5 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-22 | 2026-05-21 | 2026-07-30 | 2102364637 | 8202243375 |  | 26_[CR] Perbaikan fin fan 24E-12A | RU4-LOC1 | 24E12K-A/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 30798759 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 5 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-04-28 | 2026-05-20 | 2026-04-29 | 2026-11-30 | 2102364691 | 8202242793 |  | 26_[CR] Perbaikan fin fan 21E-30E (MG) | RU4-LOC1 | 21E30KE/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 77131236 | 53592308 | MA1-ROT |  | YUNITAMR |  | 2026-04-29 | PT02 | 5 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-25 | 2102367243 | 8202242491 |  | 26_[CR] Perbaikan fin fan 12E2B | RU4-FOC1 | 12E2K-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 14180514 | 10798760 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-25 | 2102367242 | 8202242490 |  | 26_[CR] Perbaikan fin fan 12E2A | RU4-FOC1 | 12E2K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 14180514 | 10798759 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-18 | 2102367241 | 8202242489 |  | 26_[CR] Perbaikan fin fan 11E55B | RU4-FOC1 | 11E55K-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 12718059 | 10798760 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-18 | 2102367240 | 8202242488 |  | 26_[CR] Perbaikan fin fan 11E55A | RU4-FOC1 | 11E55K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 12718059 | 10798759 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-06-11 | 2102367221 | 8202242487 |  | 26_[CR] Perbaikan fin fan 11E54B | RU4-FOC1 | 11E54K-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 13874222 | 13874222 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-20 | 2026-04-16 | 2026-05-21 | 2102367220 | 8202242486 |  | 26_[CR] Perbaikan fin fan 11E54A | RU4-FOC1 | 11E54K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 13874222 | 13874223 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-09-29 | 2102367036 | 8202242220 |  | 26_[CR] Perbaikan fin fan 11E50N | RU4-FOC1 | 11E50K-N/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 53592308 | 53592308 | MA1-ROT |  | ABDULFM |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102364733 | 8202242559 |  | 26_[CR] Perbaikan fin fan 11E50N | RU4-FOC1 | 11E50K-N/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 53592308 | 53592308 | MA1-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-10-29 | 2102367037 | 8202242221 |  | 26_[CR] Perbaikan fin fan 11E50K | RU4-FOC1 | 11E50K-K/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 53592308 | 53592308 | MA1-ROT |  | ABDULFM |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102364731 | 8202242556 |  | 26_[CR] Perbaikan fin fan 11E50K | RU4-FOC1 | 11E50K-K/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 53592308 | 53592308 | MA1-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-18 | 2026-05-18 | 2026-07-30 | 2102367494 | 8202243220 |  | 26_[CR] Perbaikan fin fan 11E50J | RU4-FOC1 | 11E50K-J/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 33758759 | 20000000 | MA1-ROT |  | APARAMAPUTRA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-06-23 |  | 2026-05-05 | 2026-05-05 | 2102368728 | 8202244048 |  | 26_[CR] Perbaikan Coupling Membran 38P-1 | RU4-TRML | 38P111A/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 48 | 0 | MA3-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-05-05 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-12-30 | 2102367063 | 8202243373 |  | 26_[CR] Perbaikan Coupling 63P2B (Fire) | RU4-TRML | 63P2B/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-22 | PT02 | 1 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-08-31 | 2102368263 | 8202242973 |  | 26_[CR] Perbaikan Coupling 520P401B | RU4-UTL1 | 520P401B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 40 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-11-30 | 2102364807 | 8202242150 |  | 26_[CR] perbaikan coupling 11P17A | RU4-FOC1 | 11P17A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/25/B6/RTC-1-C2H | 11738384 | 0 | MA1-ROT |  | ABDULFM |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 2026-11-30 | 2102367507 | 8202243223 |  | 26_[CR] Perbaikan Coupling 105P504A | RU4-RFCGTO | 105P504A/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 129000000 | 163930000 | MA7-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-02-18 | 2026-02-19 | 2026-02-13 | 2026-11-24 | 2102364436 | 8202238954 |  | 26_[CR] Perbaikan Coupling 041M122 | RU4-TRML | 041M122/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 12 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-02-19 | PT02 | 4 | 3 | 2026-02-13 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-12-30 | 2102363579 | 8202239337 |  | 26_[CR] Perbaikan Coupling & Pompa 101P5 | RU4-RFCC | 101P501B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 36000000 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-06-23 |  | 2026-06-23 | 2026-12-30 | 2102370103 | 8202244049 |  | 26_[CR] Perbaikan Cooler 011P106B | RU4-FOC2 | 011P106B/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 0 | 0 | MA2-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-23 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-17 | 2026-03-13 | 2026-07-31 | 2102365181 | 8202241692 |  | 26_[CR] Perbaikan bocoran seal 11P7 | RU4-FOC1 | 11P7/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 4598803 | 4598800 | MA1-ROT |  | AGHANIAKBAR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-21 | 2026-04-13 | 2026-11-09 | 2102367814 | 8202243230 |  | 26_[CR] Perbaikan bocoran MS 11P14A | RU4-FOC1 | 11P14A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 4181848 | 4181848 | MA1-ROT |  | AGHANIAKBAR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-02-12 | 2026-03-09 | 2026-02-18 | 2026-11-26 | 2102363578 | 8202238903 |  | 26_[CR] Perbaikan Bocoran Mechseal 101P5 | RU4-RFCC | 101P501A/00 | 60 | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | EDWINK |  | 2026-02-18 | PT02 | 3 | 3 | 2026-02-18 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-29 | 2026-03-13 | 2026-05-29 | 2102364967 | 8202241700 |  | 26_[CR] Perbaikan bocoran mech seal 11K4 | RU4-FOC1 | 11K401A/00 | 60 | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 251888000 | 157487000 | MA1-ROT |  | AGHANIAKBAR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-06-02 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368505 | 8202243559 |  | 26_[CR] Perbaikan Bocoran LO Pompa 63P50 | RU4-RFCUTL | 63P502A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 65750000 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-12 | 2026-05-21 | 2026-05-12 | 2026-07-30 | 2102367331 | 8202243132 |  | 26_[CR] Perbaikan bocoran LO 63P502B | RU4-RFCUTL | 63P502B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/NR-13-C2H | 65750000 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-05-14 | 2026-05-19 | 2026-05-18 | 2026-07-30 | 2102367888 | 8202243210 |  | 26_[CR] Perbaikan bocoran casing pompa 1 | RU4-FOC1 | 11P7/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3475000 | 3475000 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-12 | 2026-11-17 | 2102364736 | 8202239129 |  | 26_[CR] Perbaikan Belt Finfan 140E607 FB | RU4-GTO | 140E607F-B/00 | 60 | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 3450000 | 0 | MA7-ROT |  | ABDULFM |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-05-29 | 2102355144 | 8202241848 |  | 26_[CR] Perbaikan Belt Finfan 140E6 | RU4-GTO | 140E607B-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 3450000 | 3450000 | MA7-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-05-29 | 2102364735 | 8202239349 |  | 26_[CR] Perbaikan Belt Finfan 120E602 B | RU4-GTO | 120E602B/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 3285500 | 3285500 | MA7-ROT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-05-29 | 2102364734 | 8202239347 |  | 26_[CR] Perbaikan Belt Finfan 120E602 A | RU4-GTO | 120E602A/00 | 50 | REL CSER GMPS MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 3285500 | 3285500 | MA7-ROT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-02-24 | 2026-04-27 | 2026-02-09 | 2026-11-24 | 2102364081 | 8202239118 |  | 26_[CR] Perbaikan Belt Finfan 102E517A2 | RU4-RFCC | 102E517A-K2/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 4782103 | 4782103 | MA6-ROT |  | LUQMANULH | 2026-02-09 | 2026-02-25 | PT02 | 5 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-21 | 2026-05-18 | 2026-10-29 | 2102368635 | 8202243251 |  | 26_[CR] Perbaikan Belt Finfan 101E532 C1 | RU4-RFCC | 101E532C-K1/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | ABDULFM | 2026-05-18 | 2026-05-18 | PT02 | 5 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-10 | 2026-04-08 | 2026-05-29 | 2102367034 | 8202242231 |  | 26_[CR] Perbaikan bearing 21P10A | RU4-LOC1 | 21P10A/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 93294125 | 93294125 | MA1-ROT |  | WAHYUCATUR |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-07-30 | 2102367270 | 8202242545 |  | 26_[CR] Perbaikan bearing 21P10A | RU4-LOC1 | 21P10/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 20542172 | 17607576 | MA1-ROT |  | AGHANIAKBAR |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-03 | 2026-05-22 | 2026-10-29 | 2102368915 | 8202243387 |  | 26_[CR] Perbaikan ALOP 36P101B | RU4-TRML | 36P101B-P2/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 90440000 | 90440000 | MA3-ROT |  | FARIZSETYANA |  | 2026-05-22 | PT02 | 4 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-03-22 | 2026-03-25 | 2026-03-25 | 2026-06-29 | 2102364644 | 8202241833 |  | 26_[CR] Perbaikan ALOP 057P101AP2 | RU4-UTL | 057P101A-P2/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-09-29 | 2102366174 | 8202242277 |  | 26_[CR] Perbaikan 54P202D | RU4-UTL | 54P202D/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-03-22 | 2026-03-25 | 2026-03-25 | 2026-06-29 | 2102363989 | 8202241842 |  | 26_[CR] Perbaikan 53P1BT | RU4-UTL | 53P1B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 17448314 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-05-12 | 2026-03-25 | 2026-06-29 | 2102363988 | 8202241841 |  | 26_[CR] Perbaikan 53P1AT | RU4-UTL | 53P1A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 17448314 | 0 | MA5-ROT |  | YUNITAMR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-11-19 | 2102366175 | 8202242276 |  | 26_[CR] Perbaikan 52B3KT | RU4-UTL | 52B3K-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 13103784 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-04-21 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102366779 | 8202242602 |  | 26_[CR] Perbaikan 14K652 | RU4-FOC1 | 14K652/00 | 60 | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 78522377 | 78522377 | MA1-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369322 | 8202243815 |  | 26_[CR] Perbaikan 101P530B - Glass LO Ke | RU4-RFCC | 101P530B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369323 | 8202243830 |  | 26_[CR] Perbaikan 101F503 - Fillter SAF | RU4-RFCC | 101F503A14/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 15505500 | 0 | MA6-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368247 | 8202242911 |  | 26_[CR] Penggantian V-Belt 89E203KD | RU4-KPC | 89E203KD/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 3375000 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 4 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368246 | 8202242910 |  | 26_[CR] Penggantian V-Belt 89E203KA | RU4-KPC | 89E203KA/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 3375000 | 3175000 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 4 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368245 | 8202242909 |  | 26_[CR] Penggantian V-Belt 89E202KB | RU4-KPC | 86E202KB/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 3375000 | 3175000 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 4 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-12-30 | 2102366232 | 8202241394 |  | 26_[CR] Penggantian V-Belt 82E202B | RU4-KPC | 82E202KB/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2891761 | 2891762 | MA4-ROT |  | ABDULFM |  | 2026-03-09 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-06 | 2026-03-06 | 2102366231 | 8202241388 |  | 26_[CR] Penggantian V-Belt 82E202A | RU4-KPC | 82E202KA/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2891761 | 2891761 | MA4-ROT |  | ABDULFM |  | 2026-03-09 | PT02 | 5 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-31 | 2026-04-23 | 2026-03-31 | 2026-10-29 | 2102363936 | 8202241966 |  | 26_[CR] Penggantian sproket 24E2A (rusak | RU4-LOC1 | 24E2A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 13500000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-31 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-21 | 2026-05-18 | 2026-06-29 | 2102368596 | 8202243248 |  | 26_[CR] Penggantian Sililca Gel 101F503K | RU4-RFCC | 101F503K2/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 3854227 | 3854227 | MA6-ROT |  | WAHYUCATUR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-27 | 2026-03-03 | 2026-05-29 | 2102364652 | 8202239346 |  | 26_[CR] Penggantian Silica Gel/Breather | RU4-RFCC | 101A510A/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 57813405 | 57813405 | MA6-ROT |  | LUQMANULH | 2026-03-03 | 2026-03-03 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-10 | 2026-04-27 | 2026-03-10 | 2026-06-09 | 2102366227 | 8202241535 |  | 26_[CR] Penggantian Silica Gel 101-F-503 | RU4-RFCC | 101F503K2/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 3854227 | 3854227 | MA6-ROT |  | LUQMANULH | 2026-03-10 | 2026-03-10 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-06 | 2026-04-20 | 2026-03-06 | 2026-06-29 | 2102364906 | 8202241348 |  | 26_[CR] Penggantian Sight Glass 140P609A | RU4-GTO | 140P609A/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 72500000 | 72500000 | MA7-ROT |  | FARIZSETYANA | 2026-06-03 | 2026-03-09 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-07-30 | 2102365221 | 8202241663 |  | 26_[CR] Penggantian shim coupling 21P-7B | RU4-LOC1 | 21P7B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-07-30 | 2102365220 | 8202241662 |  | 26_[CR] Penggantian shim coupling 21P-7A | RU4-LOC1 | 21P7A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102369040 | 8202243749 |  | 26_[CR] Penggantian pulley fin-fan 91E40 | RU4-SRU | 91E409A2M/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-11-18 | 2102364742 | 8202239411 |  | 26_[CR] Penggantian pompa 39P210A | RU4-TRML | 39P210A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 5 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-13 | 2026-05-12 | 2026-03-13 | 2026-06-29 | 2102366574 | 8202241681 |  | 26_[CR] Penggantian MLOP 54P1B | RU4-UTL | 54P1B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-13 | 2026-05-12 | 2026-03-13 | 2026-05-29 | 2102366573 | 8202241680 |  | 26_[CR] Penggantian MLOP 54P1A | RU4-UTL | 54P1A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-11-30 | 2102367149 | 8202242749 |  | 26_[CR] Penggantian Membran kopling 63P5 | RU4-RFCUTL | 63P502A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-05-12 | 2026-05-19 | 2026-05-12 | 2026-08-31 | 2102368514 | 8202243151 |  | 26_[CR] Penggantian membran coupling 22P | RU4-LOC1 | 22P4B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-10-22 | 2102369919 | 8202243988 |  | 26_[CR] Penggantian Membran 023P105A | RU4-LOC2 | 023P105A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-11-30 | 2102355283 | 8202242149 |  | 26_[CR] Penggantian mechseal pompa 157P5 | RU4-RFCUTL | 157P502A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 9921900 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-23 | 2026-03-12 | 2026-09-29 | 2102365884 | 8202241639 |  | 26_[CR] Penggantian mech seal OB 25P-1A | RU4-LOC1 | 25P1A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 86332734 | 86332734 | MA1-ROT |  | MALBARSN |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-12-29 | 2102365714 | 8202239431 |  | 26_[CR] Penggantian Mech Seal 14K652 Spa | RU4-FOC1 | 14K652/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 19995573 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-04-24 | 2026-04-28 | 2026-04-27 | 2026-07-29 | 2102367228 | 8202242705 |  | 26_[CR] Penggantian LO Filter STG 510G60 | RU4-UTL | 510G601T/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 103500000 | 51750000 | MA5-ROT |  | ABDULFM |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-15 | 2026-04-08 | 2026-09-29 | 2102365123 | 8202242203 |  | 26_[CR] penggantian hose oil cooler 52P2 | RU4-UTL | 52P2A/01 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-04-17 | 2026-04-21 | 2026-04-17 | 2026-07-23 | 2102367468 | 8202242551 |  | 26_[CR] Penggantian hose LO 52P2B | RU4-UTL | 52P2B/01 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 6 | 0 | MA5-ROT |  | YUNITAMR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-16 | 2026-03-16 | 2026-12-30 | 2102366224 | 8202241630 |  | 26_[CR] Penggantian Gland Mech Seal 91K4 | RU4-SRU | 91K401A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | ABDULFM |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-12 | 2026-03-03 | 2026-05-29 | 2102364544 | 8202239343 |  | 26_[CR] Penggantian gelas pelumas 23P-14 | RU4-LOC1 | 23P14/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 5533846 | 5533846 | MA1-ROT |  | YMOHAMMAD |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-04-29 | 2102366612 | 8202241827 |  | 26_[CR] Penggantian gelas pelumas 22P-2B | RU4-LOC1 | 22P2B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 2766923 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-05-29 | 2102366610 | 8202241826 |  | 26_[CR] Penggantian gelas pelumas 21P-6B | RU4-LOC1 | 21P6B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 2766923 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-05-29 | 2102366611 | 8202241825 |  | 26_[CR] Penggantian gelas pelumas 21P-13 | RU4-LOC1 | 21P13B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 5533846 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-05-29 | 2102366549 | 8202241824 |  | 26_[CR] Penggantian gelas pelumas 21P-10 | RU4-LOC1 | 21P10/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 2766923 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-03-17 | 2026-11-24 | 2102366496 | 8202242385 |  | 26_[CR] Penggantian filter lube oil 51G2 | RU4-UTL | 51G201T/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 31144212 | 7313218 | MA5-ROT |  | ABDULFM |  | 2026-04-20 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-07-30 | 2102367148 | 8202243217 |  | 26_[CR] Penggantian Filter Lube Oil 51G1 | RU4-UTL | 51G1/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 18993631 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-05-29 | 2102364401 | 8202241852 |  | 26_[CR] Penggantian Filter Lube Oil 11 K | RU4-FOC1 | 11K401A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 36801000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-05-29 | 2102364402 | 8202241853 |  | 26_[CR] Penggantian Filter Lube Oil 11 K | RU4-FOC1 | 11K401A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 36801000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-07-30 | 2102367575 | 8202243214 |  | 26_[CR] Penggantian Filter LO 11K401(Bar | RU4-FOC1 | 11K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 36801000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-07-30 | 2102367332 | 8202243219 |  | 26_[CR] Penggantian Filter Intake DPA A | RU4-RFCUTL | 156K502A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 46552430 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369614 | 8202243801 |  | 26_[CR] Penggantian desicant breather 41 | RU4-TRML | 41P4A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 4913172 | 4913172 | MA1-ROT |  | ABDULFM |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-06-29 | 2102366396 | 8202241682 |  | 26_[CR] Penggantian Cyclone Pompa 46P101 | RU4-TRML | 46P101C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-05-20 | 2026-05-21 | 2026-05-20 | 2026-10-29 | 2102366225 | 8202243331 |  | 26_[CR] Penggantian Cyclone 47P503B-ROT | LOC1-UP4 | 47P503B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-03-12 | 2026-06-08 | 2026-03-12 | 2026-09-29 | 2102366189 | 8202241638 |  | 26_[CR] Penggantian cyclone 22P-2A | RU4-LOC1 | 22P2A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | EDWINK |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-09-29 | 2102366223 | 8202241637 |  | 26_[CR] Penggantian cyclone 21P-10A | RU4-LOC1 | 21P10A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-26 | 2026-06-22 | 2026-05-26 | 2026-12-30 | 2102368621 | 8202243512 |  | 26_[CR] Penggantian coupling assy 560K60 | RU4-UTL | 560K601A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 50 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-06-03 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368620 | 8202243615 |  | 26_[CR] Penggantian coupling assy 560K60 | RU4-UTL | 560K601B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-18 | 2026-06-22 | 2026-06-19 | 2026-12-22 | 2102369164 | 8202243934 |  | 26_[CR] Penggantian coupling 101P503B-T | RU4-RFCC | 101P503B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-08-27 | 2102366852 | 8202242146 |  | 26_[CR] Penggantian cooler pompa 47P-101 | RU4-TRML | 47P101A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-03-11 | 2026-03-11 | 2102366494 | 8202242564 |  | 26_[CR] Penggantian cooler pompa 21P-8 | RU4-LOC1 | 21P8/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 65000000 | 65000000 | MA1-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-10-29 | 2102368216 | 8202242736 |  | 26_[CR] Penggantian cooler 41P4B | RU4-TRML | 41P4B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-04-28 | PT02 | 4 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-24 | 2026-03-25 | 2026-06-29 | 2102366602 | 8202241828 |  | 26_[CR] Penggantian cooler 25P1A | RU4-LOC1 | 25P1A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 65000000 | 65000000 | MA1-ROT |  | AGHANIAKBAR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-12 | 2026-05-19 | 2026-05-12 | 2026-09-29 | 2102368056 | 8202243156 |  | 26_[CR] Penggantian Blade Fin Fan 86E207 | RU4-KPC | 86E207KC/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-05-19 | PT02 | 5 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-23 | 2026-04-20 | 2026-02-19 | 2026-05-18 | 2102364566 | 8202239066 |  | 26_[CR] Penggantian Belt Finfan Aus 106E | RU4-RFCGTO | 106E502A-K1/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 6763510 | 6763510 | MA7-ROT |  | FARIZSETYANA | 2026-06-04 | 2026-02-23 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-02-23 | 2026-04-20 | 2026-02-19 | 2026-05-18 | 2102364565 | 8202239058 |  | 26_[CR] Penggantian Belt Finfan Aus 105E | RU4-RFCGTO | 105E510B-K1/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 6763510 | 6763510 | MA7-ROT |  | FARIZSETYANA | 2026-06-04 | 2026-02-23 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-05 | 2026-12-08 | 2102368726 | 8202243252 |  | 26_[CR] Penggantian Belt Finfan 104E509E | RU4-RFCC | 104E509E-K1/00 | 60 | REL CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | ABDULFM | 2026-05-05 | 2026-05-20 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-06-29 | 2102368208 | 8202242917 |  | 26_[CR] Penggantian Belt Finfan 104E509C | RU4-RFCC | 104E509C-K1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368209 | 8202242916 |  | 26_[CR] Penggantian Belt Finfan 104E509B | RU4-RFCC | 104E509B-K1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-12 | 2026-06-12 | 2102369975 | 8202244020 |  | 26_[CR] Penggantian Belt Finfan 104E509B | RU4-RFCC | 104E509B-K2/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 5664338 | 0 | MA6-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-12 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-22 | 2026-06-17 | 2026-12-22 | 2102369104 | 8202243650 |  | 26_[CR] Penggantian Belt Finfan 104E509A | RU4-RFCC | 104E509A-K1/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10307020 | 10307020 | MA6-ROT |  | SAPBATCH | 2026-06-17 | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-10 | 2026-04-27 | 2026-03-10 | 2026-06-09 | 2102366226 | 8202241533 |  | 26_[CR] Penggantian Belt Finfan 104-E-50 | RU4-RFCC | 104E509E2/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | LUQMANULH | 2026-03-10 | 2026-03-10 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-05-04 | 2026-06-03 | 2026-05-05 | 2026-10-28 | 2102367682 | 8202242931 |  | 26_[CR] Penggantian belt finfan 102E520C | RU4-RFCC | 102E520C-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-05-04 | 2026-06-03 | 2026-04-29 | 2026-10-28 | 2102367607 | 8202242930 |  | 26_[CR] Penggantian belt finfan 102E520B | RU4-RFCC | 102E520B-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-05-05 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-05-03 | 2026-06-03 | 2026-05-04 | 2026-07-30 | 2102368333 | 8202242908 |  | 26_[CR] Penggantian Belt Finfan 102E520A | RU4-RFCC | 102E520A-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-04-08 | 2026-06-03 | 2026-04-08 | 2026-11-30 | 2102367059 | 8202242184 |  | 26_[CR] Penggantian belt finfan 102E520A | RU4-RFCC | 102E520A-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-05-04 | 2026-06-03 | 2026-05-05 | 2026-10-28 | 2102367489 | 8202242929 |  | 26_[CR] Penggantian belt finfan 102E520A | RU4-RFCC | 102E520A-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-05-04 | 2026-06-03 | 2026-05-05 | 2026-10-28 | 2102367488 | 8202242928 |  | 26_[CR] Penggantian belt finfan 102E519B | RU4-RFCC | 102E519B-K1/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 0 | MA6-ROT |  | FARIZSETYANA |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369167 | 8202243652 |  | 26_[CR] Penggantian Belt Finfan 102E519A | RU4-RFCC | 102E519A-K2/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 13550000 | 13550000 | MA6-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369166 | 8202243651 |  | 26_[CR] Penggantian Belt Finfan 102E518A | RU4-RFCC | 102E518A-K1/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 13550000 | 13550000 | MA6-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-22 | 2026-05-04 | 2026-07-30 | 2102368310 | 8202242913 |  | 26_[CR] Penggantian Belt Finfan 102E517B | RU4-RFCC | 102E517B-K1/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 4782103 | 4782103 | MA6-ROT |  | SAPBATCH | 2026-05-04 | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-27 | 2026-03-12 | 2026-12-29 | 2102365242 | 8202241597 |  | 26_[CR] Penggantian Belt Finfan 102E517A | RU4-RFCC | 102E517A-K1/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 4782103 | 4782103 | MA6-ROT |  | LUQMANULH | 2026-03-12 | 2026-03-12 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-02-24 | 2026-03-12 | 2026-02-09 | 2026-11-17 | 2102363884 | 8202239117 |  | 26_[CR] Penggantian belt finfan 102-E-52 | RU4-RFCC | 102E520D-K2/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 10970000 | 10970000 | MA6-ROT |  | YMOHAMMAD |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368311 | 8202242912 |  | 26_[CR] Penggantian Belt Finfan 101E532I | RU4-RFCC | 101E532I-K2/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-06-29 | 2102368338 | 8202242902 |  | 26_[CR] Penggantian Belt Finfan 101E532H | RU4-RFCC | 101E532H1/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-02-24 | 2026-06-07 | 2026-03-25 | 2026-06-25 | 2102363883 | 8202239116 |  | 26_[CR] Penggantian belt finfan 101-E-53 | RU4-RFCC | 101E532F-K2/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 5664338 | 5664338 | MA6-ROT |  | SAPBATCH | 2026-03-25 | 2026-02-25 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369369 | 8202243654 |  | 26_[CR] Penggantian Belt Fin-Fan 91E409B | RU4-SRU | 91E409B1M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 3285500 | 3285500 | MA1-ROT |  | ABDULFM |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369410 | 8202243655 |  | 26_[CR] Penggantian Belt Fin-Fan 91E409B | RU4-SRU | 91E409B2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 3285500 | 3285500 | MA1-ROT |  | ABDULFM |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369216 | 8202243653 |  | 26_[CR] Penggantian Belt Fin-Fan 91E409A | RU4-SRU | 91E409A1M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 3285500 | 3285500 | MA1-ROT |  | ABDULFM |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-31 | 2026-03-12 | 2026-11-25 | 2102366383 | 8202241610 |  | 26_[CR] Penggantian belt fin fan 24E-23A | RU4-LOC1 | 24E23K-A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 2000296 | 0 | MA1-ROT |  | ABDULFM |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-10-29 | 2102366382 | 8202241608 |  | 26_[CR] Penggantian belt fin fan 24E-12A | RU4-LOC1 | 24E12K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 2000296 | 2000296 | MA1-ROT |  | ABDULFM |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-12-22 | 2102366219 | 8202241385 |  | 26_[CR] Penggantian belt fin fan 23E-8A | RU4-LOC1 | 23E8K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 2000296 | 2000296 | MA1-ROT |  | ABDULFM |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-12-30 | 2102365886 | 8202241381 |  | 26_[CR] penggantian belt fin fan 23E-4A | RU4-LOC1 | 23E4K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 5365000 | 5365000 | MA1-ROT |  | ABDULFM |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-12-30 | 2102365887 | 8202241384 |  | 26_[CR] Penggantian belt fin fan 23E-1A | RU4-LOC1 | 23E1K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 1272509 | 1272509 | MA1-ROT |  | ABDULFM |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-11-26 | 2102366384 | 8202241611 |  | 26_[CR] Penggantian belt fin fan 21E-30E | RU4-LOC1 | 21E30KE/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 3470000 | 3470000 | MA1-ROT |  | ABDULFM |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-12-22 | 2102365885 | 8202241380 |  | 26_[CR] Penggantian belt fin fan 21E-30A | RU4-LOC1 | 21E30KA/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 2000296 | 2000296 | MA1-ROT |  | ABDULFM |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368347 | 8202242906 |  | 26_[CR] Penggantian Belt Fin Fan 024E-12 | RU4-LOC2 | 024E123K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1514588 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368348 | 8202242907 |  | 26_[CR] Penggantian Belt Fin Fan 024E-12 | RU4-LOC2 | 024E125K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1514588 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102368346 | 8202242905 |  | 26_[CR] Penggantian Belt Fin Fan 024E-11 | RU4-LOC2 | 024E112K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1370939 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-08-27 | 2102368344 | 8202242903 |  | 26_[CR] Penggantian Belt Fin Fan 023E-10 | RU4-LOC2 | 023E101K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 936667 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-08-27 | 2102368345 | 8202242904 |  | 26_[CR] Penggantian Belt Fin Fan 023E-10 | RU4-LOC2 | 023E108K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 837651 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-12-28 | 2102366526 | 8202241770 |  | 26_[CR] Penggantian Belt 16K1 | RU4-FOC1 | 16K1/01 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369929 | 8202244013 |  | 26_[CR] Penggantian Belt 14K621B | RU4-FOC1 | 14K621B/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 1030000 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-06 | 2026-12-14 | 2102368766 | 8202243263 |  | 26_[CR] Penggantian Belt 14K621 | RU4-FOC1 | 14K621B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1565000 | 1565000 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-12 | 2026-11-25 | 2102364403 | 8202239120 |  | 26_[CR] Penggantian Belt 14E610AB | RU4-FOC1 | 14E610A-B/00 | 60 | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 355464 | 355464 | MA1-ROT |  | ABDULFM |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-10-28 | 2102367509 | 8202242934 |  | 26_[CR] Penggantian Belt 14E605B | RU4-FOC1 | 14E5K-B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3525955 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-19 | 2026-05-06 | 2026-11-23 | 2102368746 | 8202243232 |  | 26_[CR] Penggantian Belt 14E605B | RU4-FOC1 | 14E5K-B/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2635000 | 2635000 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-11 | 2026-06-11 | 2102369926 | 8202244005 |  | 26_[CR] Penggantian Belt 14E605A | RU4-FOC1 | 14E5K-A/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 2990000 | 0 | MA1-ROT |  | ABDULFM |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-17 | 2026-03-09 | 2026-11-30 | 2102366523 | 8202241767 |  | 26_[CR] Penggantian Belt 14E2F | RU4-FOC1 | 14E2K-F/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1919300 | 1919300 | MA1-ROT |  | ABDULFM |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-17 | 2026-03-09 | 2026-12-21 | 2102366525 | 8202241769 |  | 26_[CR] Penggantian Belt 14E2E | RU4-FOC1 | 14E2K-E/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1919300 | 1919300 | MA1-ROT |  | ABDULFM |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-06 | 2026-12-15 | 2102368739 | 8202243253 |  | 26_[CR] Penggantian Belt 13E5A | RU4-FOC1 | 13E5K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1116544 | 1116544 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-02-24 | 2026-04-09 | 2026-02-12 | 2026-11-16 | 2102364406 | 8202239125 |  | 26_[CR] Penggantian Belt 12E2B | RU4-FOC1 | 12E2K-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3381755 | 3381755 | MA1-ROT |  | AGHANIAKBAR |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369951 | 8202244017 |  | 26_[CR] Penggantian Belt 11E61B | RU4-FOC1 | 11E61K-B/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 1740000 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-12 | 2026-11-24 | 2102364404 | 8202239123 |  | 26_[CR] Penggantian Belt 11E61A | RU4-FOC1 | 11E61K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 24012000 | 1512000 | MA1-ROT |  | ABDULFM |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-12 | 2026-11-23 | 2102364405 | 8202239124 |  | 26_[CR] Penggantian Belt 11E60B | RU4-FOC1 | 11E60K-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3470000 | 3470000 | MA1-ROT |  | ABDULFM |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369950 | 8202244015 |  | 26_[CR] Penggantian Belt 11E605A | RU4-FOC1 | 14E5K-A/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 2990000 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369924 | 8202244001 |  | 26_[CR] Penggantian Belt 11E54B | RU4-FOC1 | 11E54K-B/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 3075463 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-06 | 2026-11-24 | 2102368790 | 8202243269 |  | 26_[CR] Penggantian Belt 11E54A | RU4-FOC1 | 11E54K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1030000 | 1030000 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369940 | 8202244014 |  | 26_[CR] Penggantian Belt 11E54A | RU4-FOC1 | 11E54K-A/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 3075463 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-02-24 | 2026-05-21 | 2026-02-12 | 2026-11-24 | 2102364407 | 8202239127 |  | 26_[CR] Penggantian Belt 11E53B | RU4-FOC1 | 11E53AK-B/00 | 60 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 1740000 | 1740000 | MA1-ROT |  | YMOHAMMAD |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369925 | 8202244003 |  | 26_[CR] Penggantian Belt 11E53A | RU4-FOC1 | 11E53AK-A/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 1740000 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-05-19 | 2026-06-03 | 2026-05-06 | 2026-12-14 | 2102368791 | 8202243270 |  | 26_[CR] Penggantian Belt 11E52F | RU4-FOC1 | 11E52K-F/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2960000 | 2960000 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-19 | 2026-06-03 | 2026-05-06 | 2026-11-17 | 2102368794 | 8202243273 |  | 26_[CR] Penggantian Belt 11E52E | RU4-FOC1 | 11E52K-E/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2960000 | 2960000 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-07-30 | 2102368747 | 8202243233 |  | 26_[CR] Penggantian Belt 11E52D | RU4-FOC1 | 11E52K-D/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2960000 | 2960000 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-05-18 | 2026-06-03 | 2026-05-06 | 2026-12-07 | 2102368764 | 8202243261 |  | 26_[CR] Penggantian Belt 11E52C | RU4-FOC1 | 11E52K-C/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2960000 | 2960000 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-11 | 2026-05-05 | 2026-10-28 | 2102367574 | 8202242935 |  | 26_[CR] Penggantian Belt 11E52A | RU4-FOC1 | 11E52K-A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | ABDULFM |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-05-19 | 2026-06-03 | 2026-05-08 | 2026-12-08 | 2102368887 | 8202243279 |  | 26_[CR] Penggantian Belt 11E52A | RU4-FOC1 | 11E52K-A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-08 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-06 | 2026-12-01 | 2102368793 | 8202243272 |  | 26_[CR] Penggantian Belt 11E50T | RU4-FOC1 | 11E50K-T/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3171368 | 3171367 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-05 | 2026-05-04 | 2026-07-30 | 2102367571 | 8202242921 |  | 26_[CR] Penggantian Belt 11E50Q | RU4-FOC1 | 11E50K-Q/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3075463 | 3075463 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-18 | 2026-06-02 | 2026-05-06 | 2026-11-30 | 2102368765 | 8202243262 |  | 26_[CR] Penggantian Belt 11E50Q | RU4-FOC1 | 11E50K-Q/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2960000 | 2960000 | MA1-ROT |  | AGHANIAKBAR |  | 2026-05-20 | PT02 | 1 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369928 | 8202244008 |  | 26_[CR] Penggantian Belt 11E50O | RU4-FOC1 | 11E50K-O/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 3075463 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-05-03 | 2026-06-02 | 2026-05-04 | 2026-07-30 | 2102367573 | 8202242919 |  | 26_[CR] Penggantian Belt 11E50N | RU4-FOC1 | 11E50K-N/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2960000 | 2960000 | MA1-ROT |  | AGHANIAKBAR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-06 | 2026-12-08 | 2102368792 | 8202243271 |  | 26_[CR] Penggantian Belt 11E50N | RU4-FOC1 | 11E50K-N/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3171368 | 3171368 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102367570 | 8202242922 |  | 26_[CR] Penggantian Belt 11E50M | RU4-FOC1 | 11E50K-M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2000296 | 2000296 | MA1-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-07-30 | 2102367572 | 8202242920 |  | 26_[CR] Penggantian Belt 11E50K | RU4-FOC1 | 11E50K-K/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2000296 | 2000296 | MA1-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-06 | 2026-11-24 | 2102368760 | 8202243257 |  | 26_[CR] Penggantian Belt 11E50K | RU4-FOC1 | 11E50K-K/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2000296 | 2000296 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-11 | 2026-06-11 | 2102369869 | 8202244000 |  | 26_[CR] Penggantian Belt 11E50K | RU4-FOC1 | 11E50K-K/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 1939034 | 0 | MA1-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-11 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-06 | 2026-11-17 | 2102368749 | 8202243256 |  | 26_[CR] Penggantian Belt 11E50H | RU4-FOC1 | 11E50K-H/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2000296 | 2000296 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-06 | 2026-12-08 | 2102368748 | 8202243255 |  | 26_[CR] Penggantian Belt 11E50G | RU4-FOC1 | 11E50K-G/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2000296 | 2000296 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-06 | 2026-11-23 | 2102368763 | 8202243260 |  | 26_[CR] Penggantian Belt 11E50F | RU4-FOC1 | 11E50K-F/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3171368 | 0 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-18 | 2026-05-20 | 2026-05-06 | 2026-12-15 | 2102368762 | 8202243259 |  | 26_[CR] Penggantian Belt 11E50E | RU4-FOC1 | 11E50K-E/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 3171368 | 0 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-05-18 | 2026-06-03 | 2026-05-06 | 2026-11-17 | 2102368761 | 8202243258 |  | 26_[CR] Penggantian Belt 11E50 S | RU4-FOC1 | 11E50K-S/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 2960000 | 2960000 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-06 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-17 | 2026-03-09 | 2026-12-29 | 2102366524 | 8202241768 |  | 26_[CR] Penggantian Belt 11 E50B | RU4-FOC1 | 11E50K-B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 4000592 | 2000296 | MA1-ROT |  | ABDULFM |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-03 | 2026-06-03 | 2102369546 | 8202243998 |  | 26_[CR] Penggantian Belt 107E504K1K2 | RU4-RFCGTO | 107E504A-K1/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 5437428 | 0 | MA7-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-03 | 2026-06-03 | 2102369547 | 8202243999 |  | 26_[CR] Penggantian Belt 105E504K1K2 | RU4-RFCGTO | 105E504A-K1/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 10160936 | 0 | MA7-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 003
| K401 | 2026-06-22 |  | 2026-06-12 | 2026-06-12 | 2102369974 | 8202244019 |  | 26_[CR] Penggantian Belt 102E518B1 | RU4-RFCC | 102E518B-K1/00 | 50 | CRTD CSER MACM PRC | 4RR |  | 149050000 | 0 | MA6-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-12 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369548 | 8202243892 |  | 26_[CR] Penggantian Belt 024E125M1&M2 | RU4-LOC2 | 024E125K01/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1514588 | 1514588 | MA4-ROT |  | ABDULFM |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369445 | 8202243890 |  | 26_[CR] Penggantian Belt 024E123M1 | RU4-LOC2 | 024E123K01/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1514588 | 0 | MA4-ROT |  | ABDULFM |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-14 | 2026-05-22 | 2026-05-18 | 2026-09-29 | 2102367851 | 8202243211 |  | 26_[CR] Penggantian bearing&mech seal 21 | RU4-LOC1 | 21P8/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 80148927 | 0 | MA1-ROT |  | AGHANIAKBAR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-22 | 2026-05-18 | 2026-08-13 | 2102356285 | 8202243213 |  | 26_[CR] Penggantian bearing&mech seal 21 |  |  | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 43934117 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 045
| K401 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-07-29 | 2102367705 | 8202242768 |  | 26_[CR] Penggantian bearing 11P3 | RU4-FOC1 | 11P3/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 28654143 | 28648208 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-05 | 2026-05-04 | 2026-08-27 | 2102368510 | 8202242901 |  | 26_[CR] Penggantian bearing 11P2A | RU4-FOC1 | 11P2A/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 7054650 | 7054650 | MA1-ROT |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-04-28 | 2026-05-21 | 2026-04-29 | 2026-11-30 | 2102367726 | 8202242796 |  | 26_[CR] Penggantian bearing & mechseal 2 | RU4-LOC1 | 24P9A/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 128274125 | 128274125 | MA1-ROT |  | YMOHAMMAD |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-17 | 2026-05-22 | 2026-12-30 | 2102368083 | 8202243376 |  | 26_[CR] Penggantian Alop Pompa 54P202D | RU4-UTL | 54P202D/00 | 60 WAMA | REL CSER PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | EDWINK |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-05-16 | 2026-06-03 | 2026-05-18 | 2026-08-13 | 2102367330 | 8202243218 |  | 26_[CR] Penggantian Air Intake Filter DP | RU4-RFCUTL | 156K502B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 46552430 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102367948 | 8202243885 |  | 26_[CR] Pengadaan Spare Buffer Tank 105P | RU4-RFCGTO | 105P501A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-ROT |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-13 | 2026-06-03 | 2026-04-21 | 2026-12-16 | 2102366546 | 8202242387 |  | 26_[CR] Pengadaan precut sim untuk aligm | RU4-SRU | 91K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-10 | 2026-04-08 | 2026-09-09 | 2102367142 | 8202242230 |  | 26_[CR] Pengadaan pompa pelumas 91K401AP | RU4-SRU | 91K401APM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 158260000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-13 | 2026-03-12 | 2026-12-30 | 2102365805 | 8202241647 |  | 26_[CR] Pengadaan parts pompa 11P4 Spare | RU4-FOC1 | 11P4A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368918 | 8202243744 |  | 26_[CR] Pengadaan kopling 11P17B | RU4-FOC1 | 11P17B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 51500000 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-13 | 2026-03-12 | 2026-10-29 | 2102365715 | 8202241650 |  | 26_[CR] Pengadaan gasket casing pompa 11 | RU4-FOC1 | 11P7A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 10000000 | 0 | MA1-ROT |  | YUNITAMR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-16 | 2026-02-26 | 2026-12-30 | 2102364598 | 8202239187 |  | 26_[CR] Pengadaan 2 Unit MAC Workshop | RU4-WS | 037BD101-B3/00 | 50 WAMA | CLSD CSER MACM NCMP PRC | 4RR | D14/26/B6/RT-15-C2H | 2000000000 | 0 | WS-KAB |  | WAHYUCATUR |  |  | PT02 | 4 | 2 | 2026-03-16 | PM |  | 045
| K401 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-08-27 | 2102368170 | 8202242893 |  | 26_[CR] Penambahan LO Console 57P102AT | RU4-UTL | 57P102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-30 | PM |  | 003
| K401 | 2026-05-26 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368171 | 8202243516 |  | 26_[CR] Penambahan LO Console 530P601AT | RU4-UTL | 530P601A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 221226000 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-26 | 2026-05-25 | 2026-11-30 | 2102365748 | 8202243439 |  | 26_[CR] Pelumasan speedvariator 24S1B bo | RU4-LOC1 | 24S1B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 1 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-04-29 | 2026-04-30 | 2026-04-29 | 2026-06-29 | 2102367591 | 8202242833 |  | 26_[CR] Membrane coupling 054WS105P3 | RU4-UTL | 054WS105P3/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-21 | 2026-05-04 | 2026-08-31 | 2102368513 | 8202242900 |  | 26_[CR] Membran coupling 22P-2B patah | RU4-LOC1 | 22P2B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 11189544 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-08-27 | 2102367728 | 8202242975 |  | 26_[CR] Membran coupling 054P102BT | RU4-UTL | 054P102B-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 45 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-05 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-20 | 2026-03-12 | 2026-04-29 | 2102365157 | 8202241664 |  | 26_[CR] Mechanical seal 23P-3B bocor | RU4-LOC1 | 23P3/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 17809950 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-22 | 2026-03-25 | 2026-03-25 | 2026-06-29 | 2102363866 | 8202241845 |  | 26_[CR] Mechanical Seal 023P117 Bocor | RU4-LOC2 | 023P117A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 4 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-06-29 | 2102363865 | 8202241844 |  | 26_[CR] Mechanical Seal 021P109B Bocor | RU4-LOC2 | 021P109B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 123912865 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-21 | 2026-03-13 | 2026-07-30 | 2102366289 | 8202241688 |  | 26_[CR] Mech Seal Leak 85P210B | RU4-KPC | 85P210B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 4504200 | 0 | MA4-ROT |  | YUNITAMR |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-21 | 2026-06-17 | 2026-12-30 | 2102368903 | 8202243743 |  | 26_[CR] Mech Seal IB 87P202A leak | RU4-KPC | 87P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 429900000 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369004 | 8202243746 |  | 26_[CR] Mech Seal 87P206B Bocor | RU4-KPC | 87P206B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 5696046 | 5696046 | MA4-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-23 |  | 2026-04-15 | 2026-04-15 | 2102368014 | 8202244047 |  | 26_[CR] Low Performance pada 120P603 | RU4-GTO | 120P603A/00 | 50 WAMA WENG | CRTD CSER MACM PRC | 4RR |  | 6 | 0 | MA7-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-05-29 | 2102366287 | 8202241854 |  | 26_[CR] High Temp Rod Packing Case 84K20 | RU4-KPC | 84K202C/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-29 | 2026-06-18 | 2026-06-17 | 2026-12-22 | 2102368354 | 8202243544 |  | 26_[CR] High Temp Loader Valve 84K202B | RU4-KPC | 84K202B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 211571180 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-27 | 2026-06-11 | 2026-04-28 | 2026-11-30 | 2102366853 | 8202242748 |  | 26_[CR] Gearbox 47P-101B noise & vibrasi | RU4-TRML | 47P101B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 96312786 | 86158994 | MA3-ROT |  | ABDULFM |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-23 | 2026-04-08 | 2026-06-29 | 2102366962 | 8202242233 |  | 26_[CR] Ganti Catridge Filter 91K401B RO | RU4-SRU | 91K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 55201500 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-10 | PT02 | 3 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-23 | 2026-03-25 | 2026-06-29 | 2102364611 | 8202241837 |  | 26_[CR] Ganti Catridge Filter 91K401B | RU4-SRU | 91K401B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 96978000 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-07 | 2026-12-08 | 2102368860 | 8202243277 |  | 26_[CR] Ganti Belt 91E408B2 ROT-MA1 | RU4-SRU | 91E408B2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 3248353 | 3248354 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102366540 | 8202242567 |  | 26_[CR] Ganti Belt 91E408B1 ROT-MA1 | RU4-SRU | 91E408B1M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 3248354 | 3248354 | MA1-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-07 | 2026-12-15 | 2102368829 | 8202243276 |  | 26_[CR] Ganti Belt 91E408B1 ROT-MA1 | RU4-SRU | 91E408B1M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 3248353 | 3248353 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-12-22 | 2102365771 | 8202241599 |  | 26_[CR] Ganti Belt 91E408A2-ROT MA1 | RU4-SRU | 91E408A2M/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 3248354 | 0 | MA1-ROT |  | ABDULFM |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-02-24 | 2026-04-09 | 2026-02-12 | 2026-12-14 | 2102364822 | 8202239130 |  | 26_[CR] Ganti Belt 91E408A2 ROT-MA1 | RU4-SRU | 91E408A2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 6496707 | 6496707 | MA1-ROT |  | AGHANIAKBAR |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-07 | 2026-12-07 | 2102368828 | 8202243275 |  | 26_[CR] Ganti Belt 91E408A2 ROT-MA1 | RU4-SRU | 91E408A2M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 3248353 | 3248353 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-10 | 2026-11-24 | 2102364248 | 8202239119 |  | 26_[CR] Ganti Belt 91E408A1 ROT-MA1 | RU4-SRU | 91E408A1M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 3248354 | 3248354 | MA1-ROT |  | ABDULFM |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-11-30 | 2102366529 | 8202242565 |  | 26_[CR] Ganti Belt 91E408A1 ROT-MA1 | RU4-SRU | 91E408A1M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 3248354 | 3248354 | MA1-ROT |  | ABDULFM |  | 2026-04-24 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-07 | 2026-12-07 | 2102368827 | 8202243274 |  | 26_[CR] Ganti Belt 91E408A1 ROT-MA1 | RU4-SRU | 91E408A1M/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 3248353 | 3248354 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-05-19 | 2026-05-20 | 2026-05-07 | 2026-12-01 | 2102368861 | 8202243278 |  | 26_[CR] Ganti Belt 91E402A ROT-MA1 | RU4-SRU | 91E402AM/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-6-C2H | 3248353 | 3248353 | MA1-ROT |  | ABDULFM |  | 2026-05-20 | PT02 | 3 | 3 | 2026-05-07 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-24 | 2026-03-25 | 2026-05-29 | 2102366588 | 8202241822 |  | 26_[CR] Casing Bocor 021P111 | RU4-LOC2 | 021P111/00 | 60 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 74008450 | 74008450 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-25 | PT02 | 4 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102368916 | 8202243649 |  | 26_[CR] Belt fin-fan 3360-14-40 putus | RU4-RFCGTO | 107E504A-K1/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 2718714 | 0 | MA7-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-11-26 | 2102366264 | 8202241607 |  | 26_[CR] Belt Fin Fan 024E116M4 Rusak | RU4-LOC2 | 024E116K04/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 1370939 | 1370939 | MA2-ROT |  | ABDULFM |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-12-30 | 2102366124 | 8202241312 |  | 26_[CR] Belt Fin Fan 024E-125M2 Rusak | RU4-LOC2 | 024E125K02/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1514588 | 1514589 | MA2-ROT |  | HARINOTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-11-26 | 2102366123 | 8202241310 |  | 26_[CR] Belt Fin Fan 024E-123M2 Rusak | RU4-LOC2 | 024E123K02/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1514588 | 1514588 | MA2-ROT |  | HARINOTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-11-19 | 2102366122 | 8202241309 |  | 26_[CR] Belt Fin Fan 024E-116M2 Rusak | RU4-LOC2 | 024E116K02/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1370939 | 1370939 | MA2-ROT |  | HARINOTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-17 | 2026-04-09 | 2026-09-29 | 2102366887 | 8202242217 |  | 26_[CR] Belt Fin Fan 023E-101M4 Rusak | RU4-LOC2 | 023E101-3/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1052569 | 1052569 | MA2-ROT |  | ABDULFM |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-03-06 | 2026-04-09 | 2026-03-06 | 2026-12-22 | 2102366125 | 8202241313 |  | 26_[CR] Belt Fin Fan 023E-101M3 Rusak | RU4-LOC2 | 023E101-3/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 918214 | 918214 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-11-24 | 2102366120 | 8202241306 |  | 26_[CR] Belt Fin Fan 023E-101M2 Rusak | RU4-LOC2 | 023E101K02/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 936667 | 0 | MA2-ROT |  | HARINOTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-12-22 | 2102366121 | 8202241308 |  | 26_[CR] Belt Fin Fan 021E-130M3 Rusak | RU4-LOC2 | 021E130K03/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 3474087 | 0 | MA2-ROT |  | HARINOTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-11-25 | 2102365758 | 8202241304 |  | 26_[CR] Belt Fin Fan 021E-130 M2 Rusak | RU4-LOC2 | 021E130K02/00 | 60 | REL CNF CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 1494840 | 0 | MA4-ROT |  | ABDULFM | 2026-02-27 | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-12 | 2026-03-06 | 2026-12-22 | 2102365759 | 8202241305 |  | 26_[CR] Belt Fin Fan 021E-130 M10 Rusak | RU4-LOC2 | 021E130K10/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 3474087 | 3474087 | MA2-ROT |  | HARINOTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-13 | 2026-05-07 | 2026-03-13 | 2026-08-31 | 2102366288 | 8202241690 |  | 26_[CR] Bearing Housing Noise 88E202B | RU4-KPC | 88E202KB/00 | 60 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 65900000 | 71687100 | MA4-ROT |  | EDWINK |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-24 | 2026-04-28 | 2026-03-25 | 2026-10-28 | 2102364495 | 8202241868 |  | 26_[CR] 88P214 Mech Seal Bocor | RU4-KPC | 88P214/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 99561256 | 99561256 | MA4-ROT |  | EDWINK |  | 2026-03-25 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-28 | 2026-05-04 | 2026-04-29 | 2026-11-30 | 2102367788 | 8202242798 |  | 26_[CR] 88E215KB/00 V Belt Rusak | RU4-KPC | 88E215KB/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 1565000 | 1565000 | MA4-ROT |  | ABDULFM |  | 2026-04-29 | PT02 | 5 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369474 | 8202243657 |  | 26_[CR] 88E206KB Vbelt rusak | RU4-KPC | 88E206KB/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2223967 | 0 | MA4-ROT |  | ABDULFM |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-06 | 2026-02-26 | 2026-08-26 | 2102364724 | 8202239179 |  | 26_[CR] 87P206A mech seal bocor | RU4-KPC | 87P206A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 17202507 | 17201981 | MA4-ROT |  | AGHANIAKBAR |  | 2026-02-26 | PT02 | 4 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369356 | 8202243832 |  | 26_[CR] 87P202C Mech Seal IB Bocor | RU4-KPC | 87P202C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 210132300 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-14 | 2026-04-08 | 2026-11-30 | 2102367455 | 8202242183 |  | 26_[CR] 87P202A Mseal OB Bocor | RU4-KPC | 87P202A/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 10967701 | 10967700 | MA4-ROT |  | ABDULFM |  | 2026-04-08 | PT02 | 5 | 3 | 2026-04-08 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-21 | 2026-06-17 | 2026-12-22 | 2102369480 | 8202243659 |  | 26_[CR] 84E202KD Vbelt rusak | RU4-KPC | 84E202KD/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 3175000 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-05 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369437 | 8202243656 |  | 26_[CR] 84E202KA Vbelt rusak | RU4-KPC | 84E202KA/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 3175000 | 0 | MA4-ROT |  | ABDULFM |  | 2026-06-18 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-19 | 2026-06-17 | 2026-12-31 | 2102369303 | 8202243814 |  | 26_[CR] 84E202 jack bolt rusak/macet | RU4-KPC | 84E202KA/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-ROT |  | ABDULFM |  | 2026-06-18 | PT02 | 5 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-20 | 2026-03-25 | 2026-05-29 | 2102355233 | 8202241849 |  | 26_[CR] 82K201A Indikasi Low Flow | RU4-KPC | 82K201A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 131023514 | 131023514 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 4 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-20 | 2026-03-25 | 2026-08-31 | 2102364630 | 8202241836 |  | 26_[CR] 81A201K1A Penggantian Intake Fil | RU4-KPC | 81A201K1A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 39955856 | 39955856 | MA4-ROT |  | FARIZSETYANA |  | 2026-03-25 | PT02 | 5 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-28 | 2026-05-04 | 2026-04-29 | 2026-11-30 | 2102367787 | 8202242797 |  | 26_[CR] 80E202KF/00 V Belt Rusak | RU4-KPC | 80E202KF/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2891761 | 2891761 | MA4-ROT |  | ABDULFM |  | 2026-04-29 | PT02 | 5 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-29 | 2026-04-29 | 2026-11-30 | 2102355006 | 8202242122 |  | 26_[CR] 48P201B Mech Seal Bocor | RU4-TRML | 48P201B/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 101916698 | 0 | MA4-ROT |  | FARIZSETYANA |  | 2026-04-29 | PT02 | 4 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-04-27 | 2026-06-19 | 2026-04-29 | 2026-11-30 | 2102367719 | 8202242769 |  | 26_[CR] 140P602A low performance | RU4-GTO | 140P602A/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 200000000 | 0 | MA7-ROT |  | FARIZSETYANA |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-04-27 | 2026-05-21 | 2026-04-27 | 2026-07-27 | 2102368261 | 8202242738 |  | 26_[CR] 11P-2B Vibrasi tinggi | RU4-FOC1 | 11P2B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 14830454 | 7054650 | MA1-ROT |  | YMOHAMMAD |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-05-11 | 2026-05-19 | 2026-05-11 | 2026-08-03 | 2102368266 | 8202243128 |  | 26_[CR] 048K-101B : Liquid bocor | RU4-TRML | 048K101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-08 | 2026-03-13 | 2026-10-29 | 2102366308 | 8202241685 |  | 26_[CR] 041P104B Mech Seal Bocor | RU4-TRML | 041P104B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-3-C2H | 0 | 0 | MA2-ROT |  | YUNITAMR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-22 | 2026-05-19 | 2026-03-25 | 2026-05-29 | 2102366630 | 8202241823 |  | 26_[CR] 024P111A High Vibration | RU4-LOC2 | 024P111A/00 | 60 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 300330801 | 23330800 | MA2-ROT |  | ABDULFM |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-08-27 | 2102369114 | 8202243370 |  | 26_[CR] 023P118 Mech Seal Bocor | RU4-LOC2 | 023P118/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 6928350 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-04-06 | 2026-05-18 | 2026-04-16 | 2026-07-15 | 2102366753 | 8202242123 |  | 26_[CR] 021P112A Pompa Noise | RU4-LOC2 | 021P112A/00 | 60 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 3566700 | 3566700 | MA2-ROT |  | ABDULFM |  | 2026-04-07 | PT02 | 4 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-22 | 2026-03-16 | 2026-12-07 | 2102366759 | 8202242976 |  | 26_[CR] 018POP101A kopling rusak | RU4-FOC2 | 018POP101A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 275000 | 275000 | MA2-ROT |  | ABDULFM |  | 2026-05-11 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-05-25 | 2026-06-18 | 2026-05-25 | 2026-11-30 | 2102367436 | 8202243440 |  | 26_[CR] 018P702A mech seal bocor | RU4-FOC2 | 018P102A/00 | 60 | CLSD CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | ABDULFM |  | 2026-05-26 | PT02 | 3 | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-12-30 | 2102368888 | 8202243384 |  | 26_[CR] 017P103B coupling rontok | RU4-FOC2 | 017P103B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 17136000 | 17136000 | MA2-ROT |  | ABDULFM |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-04-21 | 2026-11-25 | 2102366622 | 8202242388 |  | 26_[CR] 015P-102B coupling goyang | RU4-FOC2 | 015P102B/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 23552000 | 0 | MA2-ROT |  | ABDULFM |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-05-16 | 2026-05-22 | 2026-05-18 | 2026-10-29 | 2102367755 | 8202243229 |  | 26_[CR] 014P103B Bearing Defect | RU4-FOC2 | 014P103B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 55117000 | 55117000 | MA2-ROT |  | AGHANIAKBAR |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-03 | 2026-02-10 | 2026-02-10 | 2102364094 | 8202239350 |  | 26_[CR] 014K102B 2nd stage: High temp ds | RU4-FOC2 | 014K102B/00 | 50 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 429777954 | 365616000 | MA2-ROT |  | ABDULFM |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-10 | PM |  | 003
| K401 | 2026-05-26 | 2026-06-20 | 2026-06-17 | 2026-12-22 | 2102368002 | 8202243515 |  | 26_[CR] 014K102A stage 2 terdapat bocora | RU4-FOC2 | 014K102A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 346772183 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-30 | 2026-03-09 | 2026-12-22 | 2102366220 | 8202241386 |  | 26_[CR] 014E108K02 belt rusak 2RB X 105 | RU4-FOC2 | 014E108K02/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1298879 | 1298879 | MA2-ROT |  | YUNITAMR |  | 2026-03-09 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-07-29 | 2102367487 | 8202242766 |  | 26_[CR] 013P105 No Flow | RU4-FOC2 | 013P105A/00 | 50 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 152558 | 152558 | MA2-ROT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-04-27 | 2026-06-15 | 2026-04-27 | 2026-07-30 | 2102368253 | 8202242744 |  | 26_[CR] 013P104 A Bocoran cooler O/B | RU4-FOC2 | 013P104A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-04-30 | PT02 | 3 | 3 | 2026-04-27 | PM |  | 003
| K401 | 2026-05-03 | 2026-05-05 | 2026-05-04 | 2026-10-29 | 2102368251 | 8202242915 |  | 26_[CR] 013K101A : Pelumas bocor | RU4-FOC2 | 013K101A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 5027530 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-11-26 | 2102366197 | 8202241605 |  | 26_[CR] 013E111K01 belt rusak TIMING BEL | RU4-FOC2 | 013E111K01/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3635469 | 3635470 | MA2-ROT |  | ABDULFM |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-23 | 2026-05-22 | 2026-03-25 | 2026-05-29 | 2102364003 | 8202241856 |  | 26_[CR] 012P103A : Cooler i/b buntu | RU4-FOC2 | 012P103A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-30 | 2026-03-12 | 2026-10-29 | 2102366195 | 8202241601 |  | 26_[CR] 012E102K01 belt rusak 2RB X 105 | RU4-FOC2 | 012E102K01/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1298879 | 1298879 | MA2-ROT |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-13 | 2026-05-21 | 2026-03-13 | 2026-06-29 | 2102364835 | 8202241705 |  | 26_[CR] 011P127B horizontal mech seal bo | RU4-FOC2 | 011P127B/00 | 60 WAMA | REL CSER GMPS MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 123774165 | 1763565 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-18 | 2026-06-17 | 2026-12-30 | 2102369062 | 8202243780 |  | 26_[CR] 011P121A gear box unbalance | RU4-FOC2 | 011P121A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 190681351 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-12 | 2026-03-05 | 2026-12-30 | 2102365249 | 8202239480 |  | 26_[CR] 011P117B high vibrasi | RU4-FOC2 | 011P117B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 68258350 | 68258350 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-09 | 2026-03-25 | 2026-07-01 | 2102364627 | 8202241832 |  | 26_[CR] 011P112A mech seal i/b bocor | RU4-FOC2 | 011P112A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 98786250 | 98256000 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-19 | 2026-06-17 | 2026-12-30 | 2102369348 | 8202243831 |  | 26_[CR] 011P110C Mech seal in/out bocor | RU4-FOC2 | 011P110C/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 101737396 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-16 | 2026-03-25 | 2026-05-29 | 2102365222 | 8202241830 |  | 26_[CR] 011P109A pompa high vibrasi | RU4-FOC2 | 011P109A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 134465850 | 38688350 | MA2-ROT |  | ABDULFM |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-09-03 | 2102366795 | 8202242384 |  | 26_[CR] 011P106C membrane kopling pecah | RU4-FOC2 | 011P106C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 36 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-22 | 2026-06-11 | 2026-12-29 | 2102369315 | 8202243779 |  | 26_[CR] 011P106C High Vibrasi Accelerati | RU4-FOC2 | 011P106C/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 19361867 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-11 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-19 | 2026-06-17 | 2026-12-22 | 2102369032 | 8202243748 |  | 26_[CR] 011P105A - pelumas o/b pompa boc | RU4-FOC2 | 011P105A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 6913496 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-17 | PM |  | 003
| K401 | 2026-03-22 | 2026-04-24 | 2026-03-25 | 2026-06-29 | 2102364055 | 8202241840 |  | 26_[CR] 011P103BT high vibrasi governor | RU4-FOC2 | 011P103B-T/00 | 60 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 11470118 | 11120118 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-25 | PT02 | 3 | 3 | 2026-03-25 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-21 | 2026-02-24 | 2026-09-16 | 2102364845 | 8202242377 |  | 26_[CR] 011P-112 B Mech seal i/b bocor | RU4-FOC2 | 011P112A/00 | 60 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | ABDULFM |  | 2026-04-20 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-03-03 | 2026-06-21 | 2026-03-03 | 2026-12-30 | 2102363905 | 8202239339 |  | 26_[CR] 011P-110B :Bocor di m/s OB di St | RU4-FOC2 | 011P110B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 71463900 | 10967700 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-03 | 2026-04-20 | 2026-03-03 | 2026-05-29 | 2102363904 | 8202239338 |  | 26_[CR] 011P-106A high vibrasi velocity | RU4-FOC2 | 011P106A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 19361867 | 19361867 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-12-30 | 2102368623 | 8202243379 |  | 26_[CR] 011P-102B mech seal i/b bocor | RU4-FOC2 | 011P102B/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 176212500 | 176212500 | MA2-ROT |  | ABDULFM |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-10-29 | 2102365232 | 8202241302 |  | 26_[CR] 011E125K10 belt rusak | RU4-FOC2 | 011E125K10/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3209123 | 0 | MA2-ROT |  | ABDULFM |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-03 | 2026-05-12 | 2026-07-30 | 2102368529 | 8202243142 |  | 26_[CR] 011E125K07 5RB X 158 belt rusak | RU4-FOC2 | 011E125K07/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3209123 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-06 | 2026-02-23 | 2026-08-27 | 2102364054 | 8202239012 |  | 26_[CR] 011E125K07 (bearing Fan macet) | RU4-FOC2 | 011E125K07/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 14007883 | 14007883 | MA2-ROT |  | YMOHAMMAD |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-09-29 | 2102366920 | 8202242218 |  | 26_[CR] 011E125K05 belt rusak 5RB X 158 | RU4-FOC2 | 011E125K05/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/25/B6/RTC-2-C2H | 3209123 | 3209123 | MA2-ROT |  | ABDULFM |  | 2026-04-09 | PT02 | 3 | 3 | 2026-04-09 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-24 | 2026-04-14 | 2026-11-26 | 2102367747 | 8202242395 |  | 26_[CR] 011E124K03 belt rusak | RU4-FOC2 | 011E124K03/00 | 60 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3525955 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 003
| K401 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-11-26 | 2102366196 | 8202241602 |  | 26_[CR] 011E124K01 belt rusak TIMING BEL | RU4-FOC2 | 011E124K01/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3635469 | 3635469 | MA2-ROT |  | ABDULFM |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-05-19 | 2102367746 | 8202242394 |  | 26_[CR] 011E121K05 belt rusak | RU4-FOC2 | 011E121K05/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765778 | 1765778 | MA2-ROT |  | YUNITAMR |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-05-12 | 2102367745 | 8202242393 |  | 26_[CR] 011E121K03 belt rusak | RU4-FOC2 | 011E121K03/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765778 | 1765779 | MA2-ROT |  | YUNITAMR |  | 2026-04-14 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-24 | 2026-03-13 | 2026-05-29 | 2102366527 | 8202241677 |  | 26_[CR] 011E113K02: belt rusak TIMING BE | RU4-FOC2 | 011E113K02/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3525955 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-08-27 | 2102364833 | 8202241706 |  | 26_[CR] 011E113K02 noise | RU4-FOC2 | 011E113K02/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 3525955 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-05-12 | 2026-06-03 | 2026-05-12 | 2026-07-30 | 2102368528 | 8202243141 |  | 26_[CR] 011E110K42: 3RB X 128 belt rusak | RU4-FOC2 | 011E110K38/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765779 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-05-19 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-20 | 2026-03-13 | 2026-05-29 | 2102364836 | 8202241704 |  | 26_[CR] 011E110K29 Blade nyenggol body | RU4-FOC2 | 011E110K29/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765779 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-15 | 2026-03-13 | 2026-05-29 | 2102366528 | 8202241675 |  | 26_[CR] 011E110K25 belt rusak 3RB X 128 | RU4-FOC2 | 011E110K25/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765779 | 1765779 | MA2-ROT |  | YUNITAMR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-13 | PM |  | 003
| K401 | 2026-02-24 | 2026-02-25 | 2026-02-12 | 2026-11-25 | 2102364651 | 8202239128 |  | 26_[CR] 011E110K09 : belt rusak 3RB X 12 | RU4-FOC2 | 011E110K09/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1765778 | 0 | MA2-ROT |  | ABDULFM |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-12 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-17 | 2026-04-01 | 2026-10-05 | 2102367196 | 8202242152 |  | 26_[CR] 011E-110 K42 blade macet | RU4-FOC2 | 011E110K38/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 14324714 | 10798759 | MA2-ROT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-11-12 | 2102367926 | 8202242503 |  | 26_[BONPINJAM]Perbaikan Proximity Switch | RU4-RFCC | 101A512/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 107000000 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-04-17 | PT02 | 8 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369996 | 8202243992 |  | 26_[BON PNJM]Penggantian Proximity Switc | RU4-RFCUTL | 156ZE650A/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 742500000 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-21 | 2026-05-04 | 2026-12-29 | 2102368499 | 8202242947 |  | 26_[BON PNJM] Perbaikan Solenoid Valve 9 | RU4-SRU | 93XV068/00 | 60 | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 21450000 | 42900000 | MA1-INT |  | YMOHAMMAD |  | 2026-05-04 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-29 | 2102369997 | 8202243994 |  | 26_[BON PNJM] Penggantian Proximity Swit | RU4-RFCUTL | 156VE661B/00 | 50 | CRTD CSER MACM PRC | 4IR |  | 742500000 | 0 | MA5-INT |  | FATAHALFI |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 003
| K401 | 2026-04-09 | 2026-05-21 | 2026-04-15 | 2026-10-07 | 2102367644 | 8202242293 |  | 26_[BON PINJAM]Perbaikan 93XV063 INT-MA1 | RU4-SRU | 93XV063/00 | 60 WAMA | REL GMPS MANC PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 90450000 | 111900000 | MA1-INT |  | YMOHAMMAD |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-17 | 2026-04-15 | 2026-10-22 | 2102367640 | 8202242291 |  | 26_[BON PINJAM]Perbaikan 91LT112 INT-MA1 | RU4-SRU | 91LT112/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 30598949 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-04-09 | 2026-04-17 | 2026-04-15 | 2026-11-12 | 2102367641 | 8202242292 |  | 26_[BON PINJAM] Perbaikan 91LI563 INT-MA | RU4-SRU | 91LT563/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 30598949 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-03-12 | 2026-05-21 | 2026-03-12 | 2026-11-26 | 2102364765 | 8202241623 |  | 26_[BD]Kerusakan Kompresor 260K101/102B | RU4-LOC3 | 260K101B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | MA4-ROT |  | WAHYUCATUR |  | 2026-03-12 | PT02 | 4 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-12-30 | 2102368840 | 8202243383 |  | 26_(SL) Perbaikan Filter 103P506, 103P51 | RU4-RFCC | 103P506/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-12-C2H | 90000000 | 90000000 | MA6-ROT |  | ABDULFM |  | 2026-05-22 | PT02 | 8 | 3 | 2026-05-22 | PM |  | 003
| K401 | 2026-02-06 | 2026-03-06 | 2026-02-06 | 2026-12-30 | 2102356275 | 8202238710 |  | 26_(BON PNJM) Perbaikan thermoskin boile | RU4-UTL | 520B301/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 150848000 | 150848000 | MA5-INT |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-02-06 | 2026-03-06 | 2026-02-09 | 2026-09-08 | 2102363872 | 8202238730 |  | 26_(BON PINJAM) Perbaikan Part Pneumix 1 | RU4-RFCC | 101A525A/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 625147041 | 353028333 | MA6-INT |  | YMOHAMMAD |  | 2026-02-18 | PT02 | 3 | 3 | 2026-02-09 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-05-05 | 2102367045 | 8202242110 |  | 26_(BON PINJAM) Penggantian BEACON & HOR | RU4-RFCC | 153-CWR0108-28/00 | 50 | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 117600000 | 117600000 | MA5-INT |  | FARIZSETYANA |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-19 | 2026-06-18 | 2026-06-29 | 2102369846 | 8202243753 |  | 26_(BON PINJAM) Penggantian 22HV013 | RU4-LOC1 | 22HV013/00 | 50 | REL MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 285000000 | 0 | MA1-INT |  | FARIZSETYANA |  | 2026-06-19 | PT02 | 4 | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-19 | 2026-06-18 | 2026-06-29 | 2102369845 | 8202243752 |  | 26_(BON PINJAM) Penggantian 22HV012 | RU4-LOC1 | 22HV012/00 | 50 | CRTD MACM PRC | 4IR | D14/26/B6/RT-7-C2H | 285000000 | 0 | MA1-INT |  | FARIZSETYANA |  |  | PT02 | 4 | 2 | 2026-06-18 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-21 | 2026-06-18 | 2026-06-29 | 2102369844 | 8202243751 |  | 26_(BON PINJAM) Penggantian 21HV702 | RU4-LOC1 | 25HS013/00 | 50 | REL MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 457200000 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-06-19 | PT02 | 4 | 3 | 2026-06-18 | PM |  | 003
| K401 | 2026-04-06 | 2026-06-19 | 2026-04-06 | 2026-05-05 | 2102367048 | 8202242101 |  | 26_(BON PINJAM) License Scada Point DCS | RU4-UTL | 05AUX1/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-INT |  | FARIZSETYANA |  | 2026-04-07 | PT02 | 6 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-03-30 | 2026-05-21 | 2026-03-30 | 2026-12-30 | 2102365154 | 8202241914 |  | 26_(Bon Pinjam) barang kimap G375903804 |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-LIS |  | WAHYUCATUR |  | 2026-03-30 | PT02 | 5 | 3 | 2026-03-30 | PM |  | 045
| K401 | 2026-02-27 | 2026-05-25 | 2026-02-27 | 2026-12-30 | 2102364798 | 8202239261 |  | 26_'018LT 034 rusak | RU4-FOC2 | 018LTC034/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 003
| K401 | 2026-04-06 | 2026-05-19 | 2026-04-06 | 2026-07-13 | 2102367193 | 8202242073 |  | 26_ perbaikan motor 054WS105P3M | RU4-UTL | 054WS105/00 | 60 | TECO CNF CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 4335350 | 4335350 | MA5-LIS |  | AHMADZAENURI | 2026-05-19 | 2026-04-06 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-30 | 2026-04-15 | 2026-07-20 | 2102367935 | 8202242446 |  | 26_ perbaikan motor 054WS101P1M | RU4-UTL | 054WS101P1M/00 | 60 | CLSD CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 699100 | 699100 | MA5-LIS |  | AHMADZAENURI |  | 2026-04-15 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K401 | 2026-02-06 | 2026-03-11 | 2026-03-11 | 2026-12-30 | 2102356193 | 8202238709 |  | 26_ New Chiller 81 kondisi Termowell rus | RU4-KPC | 81A201/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 1 | 0 | MA4-INT |  | WAHYUCATUR |  | 2026-03-11 | PT02 | 5 | 3 | 2026-03-11 | PM |  | 045
| K401 | 2026-05-16 | 2026-06-19 | 2026-05-18 | 2026-10-29 | 2102367533 | 8202243225 |  | 26_ [CR] Perbaikan Pompa 110P502 | RU4-RFCUTL | 110P502B/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 5483850 | 0 | MA5-ROT |  | AGHANIAKBAR |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-05-06 | 2026-05-26 | 2026-04-16 | 2026-11-09 | 2102368081 | 8202243049 |  | 26_ [CR] Perbaikan Bocoran Steam 153P501 | RU4-RFCUTL | 153P501A-T/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-13-C2H | 14846041 | 0 | MA5-ROT |  | YUNITAMR |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-16 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2102365789 | 8202241775 |  | 26_ [CR] Perbaikan 24P2B | RU4-LOC1 | 24P2B/00 | 50 WASR | CRTD NMAT PRC | 4RR |  | 1000000000 | 0 | MA1-ROT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-03-16 | PM |  | 004
| K401 | 2026-03-16 | 2026-03-17 | 2025-12-10 | 2025-12-10 |  | 8202241779 | 8202240949 | 25_[CR] Perbaikan mechanical seal 10P3 | RU4-FOC1 | 10P2/00 | 50 | CLSD NCMP NMAT PRC | 4RR | D14/26/B6/RT-9-C2H | 0 | 0 | WS-PMP |  | AGHANIAKBAR |  |  | PT02 | 3 | 2 | 2026-03-17 | PM |  | 003
| K401 | 2026-05-04 | 2026-05-04 | 2026-04-30 | 2026-04-30 | 2102368617 | 8202242943 |  | 24_Pengadaan material TDR FOC-1 | RU4-FOC1 | 11FT701/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-05-04 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-24 | 2026-04-07 | 2026-11-30 | 2102364995 | 8202242164 |  | 220PSV028 rusak (220P105) | RU4-LOC3 | 220PSV028/00 | 50 WAMA | REL CSER MANC PRC SETC | 4MR | D14/26/B6/RT-9-C2H | 1 | 0 | MA4-STA |  | TEGARPRAMUDY |  | 2026-04-07 | PT02 | 4 | 3 | 2026-04-07 | PM |  | 045
| K201 | 2026-06-19 | 2026-06-19 | 2026-05-19 | 2026-06-18 | 2102365205 | 8202243959 |  | 212-P-15C Rusak | RU2-HCC | 212-P-15C/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 89111444 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 003
| K201 | 2026-04-01 | 2026-04-10 | 2026-04-01 | 2026-04-01 | 2102366379 | 8202242003 |  | 212-P 9C Mech Seal Bocor | RU2-HCC | 212-P-9C/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 5885999 | 2157695 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-04-01 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K201 | 2026-04-15 |  | 2026-06-16 | 2026-06-17 | 2102366378 | 8202242454 |  | 212-P 9A Mech Seal Bocor | RU2-HCC | 212-P-9A/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/RT-D2H | 431800 | 0 | MA2-ROT |  |  |  |  | PT02 | 5 | 2 | 2026-06-16 | PM |  | 003
| K201 | 2026-03-09 | 2026-05-26 | 2026-03-09 | 2026-12-29 | 2102366361 | 8202241453 |  | 212-C1 Module Protech GII | RU2-HCC | 212-C-1/00 | 60 | REL CSER GMPS MACM PRC SETC | 2IR | D12/26/B6/NR-D2H | 467300000 | 467300000 | MA2-INT |  | ADEMULYADI |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 005
| K201 | 2026-05-11 | 2026-06-08 | 2026-04-23 | 2026-04-23 | 2102368291 | 8202243112 |  | 212 PM-16B Motor short | RU2-HCC | 212-PM-16B/00 | 50 | REL CSER MSPT PRC SETC | 2ER | D12/26/B6/NR-D2H | 33537489 | 0 | MA2-LIS |  | SATRIAAGUNG |  | 2026-06-08 | PT02 | 3 | 3 | 2026-04-23 | PM |  | 003
| K201 | 2026-04-01 | 2026-05-31 | 2026-04-01 | 2026-04-01 | 2102363524 | 8202241999 |  | 211-PT-65 B Coupling Rusak | RU2-HCC | 211-P-65B/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 14521242 | 14521242 | MA2-ROT |  | SAPBATCH | 2026-04-01 | 2026-04-01 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K201 | 2026-04-01 | 2026-06-01 | 2026-04-01 | 2026-04-01 | 2102365206 | 8202242001 |  | 211-PT 4B Overhaul | RU2-HCC | 211-P-4B/00 | 60 | CLSD CNF CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 111010250 | 111010250 | MA2-ROT |  | SAPBATCH | 2026-04-02 | 2026-04-01 | PT02 | 5 | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-04-01 | 2026-06-22 | 2026-04-01 | 2026-04-01 | 2102363980 | 8202242000 |  | 211-PT 17A vibrasi tinggi | RU2-HCC | 211-P-17A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 7382182 | 0 | MA2-ROT |  | NURFADHILLA |  | 2026-04-01 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K201 | 2026-03-17 | 2026-06-15 | 2026-03-17 | 2026-04-02 | 2102364817 | 8202241791 |  | 211-P-9C Mechseal DE Side Bocor | RU2-HCC | 211-P-9C/00 | 60 | REL CSER GMPS MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 9552975 | 9491092 | MA2-ROT |  | NURFADHILLA |  | 2026-03-17 | PT02 | 5 | 3 | 2026-03-17 | PM |  | 003
| K201 | 2026-04-10 | 2026-06-18 | 2026-05-20 | 2026-05-21 | 2102364819 | 8202242336 |  | 211-P-19A Mech.seal bocor | RU2-HCC | 211-P-19A/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 3572162 | 0 | MA2-ROT |  | MDSYAHPUTRA |  | 2026-04-10 | PT02 | 5 | 3 | 2026-05-20 | PM |  | 003
| K201 | 2026-04-30 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2102367700 | 8202242887 |  | 211-H2 Rusak | RU2-HCC | 211-H-2/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 100000000 | 0 | MA2-STA |  | CHANRARD |  | 2026-05-04 | PT02 | 5 | 3 | 2026-05-04 | PM |  | 003
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102365052 | 8202243462 |  | 211 PM-19A Motor Vibrasi | RU2-HCC | 211-PM-19A/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 1780000 | 0 | MA2-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-08-03 | 2026-08-03 | 2102365050 | 8202243461 |  | 211 PM-18A Motor Vibrasi | RU2-HCC | 211-PM-18A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 890000 | 0 | MA2-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-08-03 | 2026-08-03 | 2102365051 | 8202243460 |  | 211 PM-17A Motor Vibrasi | RU2-HCC | 211-PM-17A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 2349660 | 0 | MA2-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-08-03 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102365039 | 8202243459 |  | 211 PM-15B motor vibrasi | RU2-HCC | 211-PM-15B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 906237 | 0 | MA2-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K202 | 2026-03-10 | 2026-03-11 | 2026-02-06 | 2026-02-06 | 2102362625 | 8202241504 |  | 2102350964#KEBUTUHAN MATERIAL DRIP SAM | RU2S-KIL | 18PL946506-A1A1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 496356 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-03-11 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-02-13 | 2026-04-20 | 2026-02-26 | 2026-11-26 | 2102355071 | 8202238916 |  | 2102350946#[CR] 014E102B K04 Ganti bel | RU4-FOC2 | 014E102B-K04/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 1298879 | 1298879 | MA2-ROT |  | FARIZSETYANA |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-18 | 2026-03-12 | 2026-02-02 | 2026-12-30 | 2102354873 | 8202238923 |  | 2102350943#Pengadaan Material Alat IP5 | RU4-FOC2 | 010AOC1/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-2-C2H | 100000 | 0 | WS-INT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-03-04 | 2026-03-04 | 2026-02-02 | 2026-06-29 | 2102351039 | 8202239421 |  | 2102350941#Pemb. On Call LTSA Honeywell | RU6-POC | 38-E-101/00 | 50 | REL GMPS NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 48800000 | 48800000 | MA3-STA |  | DANDARWANI |  | 2026-03-04 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-03-06 | 2026-05-26 | 2026-02-02 | 2026-02-02 | 2102351490 | 8202241342 |  | 2102350911#RK0285 TSA Alat Sulfur WDXRF | RU2-LAB |  | 50 | REL GMPS NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 300000000 | 32650000 | WS-IN1 |  | DEDISUKMANA |  | 2026-03-13 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-03-06 |  | 2026-02-02 | 2026-02-02 | 2102351491 | 8202241339 |  | 2102350910#TSA Alat ICP & Spektro UV-V | RU2-LAB |  | 01 | CRTD NMAT PRC | 2IR | D12/09/B6/RT1-LABNH | 0 | 0 | WS-IN1 |  |  |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-09 | 2026-02-09 | 2026-02-02 | 2026-03-11 | 2102351037 | 8202238783 |  | 2102350901 Pengg. Bearing 32-K-101-P1A-T | RU6-HSC | 32-K-101-P1-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA3-ROT |  | DANDARWANI |  | 2026-02-09 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-12 | 2026-06-18 | 2026-02-02 | 2026-12-30 | 2102354876 | 8202238886 |  | 2102350891#Tagihan Termin II UP Bordes | RU4-TRML | 68JT1/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 1183199000 | 1183199000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-04 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-10 | 2026-06-08 | 2026-02-02 | 2026-02-02 | 2102354548 | 8202241514 |  | 2102350885#Service dan Refill Media 80 |  |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 045
| K601 | 2026-02-26 | 2026-02-27 | 2026-02-02 | 2026-12-16 | 2102351033 | 8202239198 |  | 2102350809#Perbaikan mechseal 42-P-102 | RU6-ITP | 42-P-102B/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 7252381 | 0 | MA4-ROT |  | DANDARWANI |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-10 |  | 2026-02-02 | 2026-02-02 | 2102356198 | 8202241521 |  | 2102350777#Perbaikan 38PT310B dan 38PT |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  |  |  |  | PT02 | 5 | 2 | 2026-02-02 | PM |  | 045
| K501 | 2026-02-24 | 2026-02-24 | 2026-02-02 | 2026-08-30 | 2102360701 | 8202239131 |  | 2102350755#Perbaikan MS BPP 1 (3) | RU5-D&W | G-202-06B/00 | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 69398000 | 0 | MA1-ROT |  | YONZHETG |  | 2026-02-24 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-24 | 2026-02-24 | 2026-02-02 | 2026-08-30 | 2102360559 | 8202239133 |  | 2102350754#Perbaikan MS BPP 1 (2) | RU5-D&W | G-201-02A/00 | 50 | REL NMAT PRC SETC | 5RR | D15/26/B6/RT-C2H | 246245000 | 0 | MA1-ROT |  | YONZHETG |  | 2026-02-24 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-03-08 | 2026-06-03 | 2026-12-02 | 2026-12-02 | 2102360558 | 8202241354 |  | 2102350719#KOMPRESOR K-19-01B VIBRASI | RU5-E15112 | K-19-01B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 531638038 | 0 | MA2-ROT |  | HIMMATUSS |  | 2026-05-04 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K401 | 2026-02-10 | 2026-05-25 | 2026-02-24 | 2026-09-29 | 2102356144 | 8202238822 |  | 2102350717#26_Penggantian PI range 25 kg | RU4-TRML | 71P10A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 4879625 | 0 | MA3-INT |  | DWIHIZZKI |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-02-10 | 2026-05-25 | 2026-02-24 | 2026-09-29 | 2102356147 | 8202238823 |  | 2102350716#26_Penggantian PI range 25 kg | RU4-TRML | 71P13A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 4879625 | 0 | MA3-INT |  | DWIHIZZKI |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-02-10 | 2026-05-25 | 2026-02-24 | 2026-09-29 | 2102356141 | 8202238821 |  | 2102350715#26_Penggantian PI range 25 kg | RU4-TRML | 71P1A/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4IR | D14/26/B6/RT-4-C2H | 7319437 | 0 | MA3-INT |  | DWIHIZZKI |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-24 | 2026-04-15 | 2026-10-12 | 2102356424 | 8202242469 |  | 2102350692#Perbaikan Motor 91K401BPM - | RU4-SRU | 91K401BPM/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-6-C2H | 926800 | 926800 | MA1-LIS |  | TEGARPRAMUDY |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K201 | 2026-03-03 | 2026-03-03 | 2026-02-02 | 2026-02-02 | 2102351728 | 8202239399 |  | 2102350679#Perbaikan panel Capstan | RU2-ITP | 990-HVM-1007/00 | 50 | REL MACM PRC SETC | 2MR | D12/26/B6/NR-D2H | 886200000 | 0 | MA4-LIS |  | DJOKOTRIONO |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 004
| K201 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102351781 | 8202243969 |  | 2102350646#Pompa Rusak | RU2-HCC | 211-P-34B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 938000 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-02-09 | 2026-05-05 | 2026-02-18 | 2026-12-30 | 2102357129 | 8202238784 |  | 2102350634#Corrective Maintenance MAC | RU4-WS | 037BD101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 156611000 | 0 | WS-KAB |  | FARIZSETYANA |  | 2026-02-18 | PT02 | 5 | 3 | 2026-02-18 | PM |  | 045
| K201 | 2026-02-20 | 2026-05-08 | 2026-02-20 | 2026-02-20 | 2102351998 | 8202238985 |  | 2102350625#211-PT 4B Jumper Line | RU2-HCC | 211-P-4B/00 | 60 | REL CSER GMPS MANC PRC SETC | 2MR | D12/26/B6/RT-D2H | 131270468 | 135338495 | MA2-STA |  | NURFADHILLA |  | 2026-02-25 | PT02 | 5 | 3 | 2026-02-20 | PM |  | 003
| K201 | 2026-04-29 | 2026-05-08 | 2026-10-10 | 2026-10-12 | 2102352140 | 8202242811 |  | 2102350621#Material Perbaikan Equipmen | RU2-HSC | 300-PT-7B/00 | 50 | CRTD CSER MACM PRC RELR | 2RR | D12/25/B6/RT-D2H | 881983250 | 0 | MA2-ROT |  | ADEMULYADI |  |  | PT02 | 5 | 2 | 2026-10-10 | PM |  | 003
| K401 | 2026-03-10 | 2026-06-21 | 2026-06-10 | 2026-12-22 | 2102357432 | 8202241531 |  | 2102350603#26_023LT-011 Rusak | RU4-LOC2 | 023LT011/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-8-C2H | 95860000 | 0 | MA2-INT |  | WAHYUCATUR |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-10 | PM |  | 003
| K501 | 2026-02-27 | 2026-03-02 | 2026-03-02 | 2026-04-07 | 2102358760 | 8202239263 |  | 2102350586#TSA PLC SCHNEIDER (1) | RU5-D&W | K-235-01C-INST/00 | 50 | REL NMAT PRC SETC | 5IR | D15/26/B6/RT-C2H | 111350000 | 0 | MA1-INT |  | ANTONIUSAD |  | 2026-03-02 | PT02 | 3 | 3 | 2026-03-02 | PM |  | 045
| K501 | 2026-04-07 | 2026-05-06 | 2026-04-07 | 2026-05-22 | 2102358765 | 8202242154 |  | 2102350584#Perb. LPD 2" Suction P13 A | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/26/B6/RT-C2H | 70829698 | 0 | MA4-STA |  | FAUZANR |  | 2026-05-06 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-02-25 | 2026-04-02 | 2026-02-25 | 2026-07-20 | 2102351027 | 8202239152 |  | 2102350548#Sarfas UCO | RU6-DHC | 22-R-101/00 | 50 | REL CSER GMCO MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 375369298 | 0 | MA2-STA |  | SHELFIANCBP |  | 2026-02-25 | PT02 | 6 | 3 | 2026-02-25 | PM |  | 004
| K201 | 2026-04-06 | 2026-05-26 | 2026-04-06 | 2026-04-06 | 2102350889 | 8202242111 |  | 2102350538#Perbaikan Trafo T-2-13 | RU2-UTL | 905-TRF-2-13/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1774000000 | 0 | MA3-LIS |  | ERLANGGA |  | 2026-04-07 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 005
| K601 | 2026-03-12 | 2026-03-12 | 2026-02-02 | 2026-02-02 | 2102351026 | 8202241633 |  | 2102350524#Indikasi valve bypass pasin | RU6-POC | 38-V-103/00 | 50 | REL CSER MANC PRC SETC | 6MR | D16/26/B6/NR-C2H | 12045504 | 0 | MA3-STA |  | DANDARWANI |  | 2026-03-12 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-10 | 2026-02-02 | 2026-06-29 | 2102351024 | 8202238820 |  | 2102350515#Perbaikan 12-VSHH-601 | RU6-DHC | 12-K-501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | DANDARWANI |  | 2026-02-10 | PT02 | 2 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2102351224 | 8202239464 |  | 2102350510#Line cold bottom corrosive | RU2-HCC | 212-V-103/00 | 50 | CRTD CSER MACM PRC | 2MR | D12/26/B6/RT-D2H | 6685762 | 0 | MA2-STA |  | CHANRARD |  |  | PT02 | 3 | 2 | 2026-03-04 | PM |  | 003
| K401 | 2026-03-05 | 2026-04-24 | 2026-03-05 | 2026-12-30 | 2102354689 | 8202240695 |  | 2102350493#Penggantian Gasket dan Boltin | RU4-GTO | 140D602B/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-14-C2H | 38098426 | 0 | MA7-STA |  | TEGARPRAMUDY |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K501 | 2026-04-02 | 2026-04-28 | 2026-12-02 | 2026-12-02 | 2102358945 | 8202242022 |  | 2102350438#FIN FAN EA-1-21M V-BELT RUS | RU5-E15111 | EF-1-21M/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 3259628 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K501 | 2026-02-26 | 2026-03-03 | 2026-05-04 | 2026-05-04 | 2102358946 | 8202239194 |  | 2102350436#FINFAN EA-1-21R VBELT RETAK | RU5-E15111 | EF-1-21R/00 | 60 | CLSD CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-02-26 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-10 | 2026-03-10 | 2026-02-02 | 2026-02-02 | 2102354589 | 8202241532 |  | 2102350416#Perbaikan Pneumix 101A525B | RU4-RFCC | 101A525B/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-09 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102354511 | 8202238768 |  | 2102350407#[TGH] Termin 12 UP Tenaga B | RU4-WS | 037BD101-44K1M/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 356596250 | 356596250 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-03-13 | 2026-06-09 | 2026-12-02 | 2026-12-02 | 2102351227 | 8202241699 |  | 2102350401#TSA Penggantian Mech Seal A | RU2-HCC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 2100000000 | 0 | MA2-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K202 | 2026-04-23 | 2026-04-23 | 2026-02-02 | 2026-02-02 | 2102351446 | 8202242695 |  | 2102350388#Tidak dapat start pada 900- | RU2S-KIL | 900-06GE-7-G/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 2399984 | 2399984 | MAS-LIS |  | JUNIANTO |  | 2026-04-23 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-10 | 2026-03-10 | 2026-02-02 | 2026-02-02 | 2102355247 | 8202241537 |  | 2102350374#Perbaikan HMI Sootblower HM | RU4-RFCC | 101F503/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | YMOHAMMAD |  |  | PT02 | 8 | 2 | 2026-03-10 | PM |  | 003
| K501 | 2026-04-10 | 2026-04-13 | 2026-12-02 | 2026-12-02 | 2102359140 | 8202242317 |  | 2102350369#Perb. Pompa Feed G-220-01D | RU5-TBL | G-220-01D/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 2309870 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K501 | 2026-04-24 | 2026-04-28 | 2026-12-02 | 2026-12-02 | 2102359088 | 8202242727 |  | 2102350367#POMPA G-202-02B COUPLING ASSY | RU5-D&W | G-202-02B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 1 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K201 | 2026-03-05 | 2026-03-06 | 2026-12-02 | 2026-12-02 | 2102351430 | 8202239983 |  | 2102350363#TSA Scada System OEM ABB | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 500000000 | 0 | MA3-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K401 | 2026-03-03 | 2026-06-18 | 2026-02-02 | 2026-12-30 | 2102355192 | 8202239396 |  | 2102350325#TGH5_25 Upgrade DCS OM 60 & N |  | 60EE0131A/00 | 60 | REL CSER GMPS NMAT PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 2393700000 | 2393700000 | MA3-INT |  | FARIZSETYANA |  | 2026-03-11 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-17 | 2026-04-24 | 2026-03-17 | 2026-12-30 | 2102355195 | 8202241794 |  | 2102350288#Pengambilan Material H84040 | RU4-TRML | 70P11/00 | 50 WAMA | REL CSER MACM PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 73900000 | 0 | MA3-STA |  | TEGARPRAMUDY |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-02-24 | 2026-03-26 | 2026-02-26 | 2026-12-30 | 2102355606 | 8202239089 |  | 2102350279#[TGH] PM rotating eqp termi |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 432200000 | 0 | MA2-ROT |  | AGHANIAKBAR |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 045
| K201 | 2026-03-09 | 2026-05-26 | 2026-12-02 | 2026-12-02 | 2102351817 | 8202241489 |  | 2102350223#LTSA Online Leak Sealing Al | RU2-HCC | 701-E-3/00 | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 671510000 | MA2-STA |  | ADEMULYADI |  | 2026-03-10 | PT02 | 5 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2102351436 | 8202243632 |  | 2102350208#211-EG-4H Coupling Rusak | RU2-HCC | 211-EG-4H/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/RT-D2H | 20388889 | 0 | MA2-ROT |  | MAULANAHARUN |  |  | PT02 | 5 | 2 | 2026-06-04 | PM |  | 003
| K401 | 2026-03-16 | 2026-04-24 | 2026-03-16 | 2026-12-30 | 2102355949 | 8202241772 |  | 2102350199#Penggantian modul switch ge | RU4-SRU | 93K401BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-LIS |  | YMOHAMMAD |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K201 | 2026-04-01 | 2026-05-08 | 2026-05-04 | 2026-05-04 | 2102351435 | 8202242005 |  | 2102350191#Perbaikan Motor 140-PM-23 B | RU2-HOC | 140-PM-23B/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 906237 | 906237 | MA1-LIS |  | NURFADHILLA |  | 2026-04-01 | PT02 | 3 | 3 | 2026-05-04 | PM |  | 003
| K401 | 2026-02-06 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102356576 | 8202238696 |  | 2102350172#[TGH] Penggantian mech seal | RU4-LOC1 | 23P8/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 159553500 | 159553500 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K501 | 2026-04-07 | 2026-06-02 | 2026-04-07 | 2026-04-07 | 2102359474 | 8202242128 |  | 2102350140#Tag-1 TSA PM Oil Spil Monit | RU5-TBL | 34-LT-170/00 | 01 | CLSD CSER NCMP NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  | RIANDAADI |  |  | PT02 | 3 | 2 | 2026-06-02 | PM |  | 045
| K201 | 2026-03-06 | 2026-05-26 | 2026-09-09 | 2026-09-09 | 2102352021 | 8202241343 |  | 2102350124#LTSA CEMS 110 H-1AB | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 1040000000 | 169860000 | MA1-INT |  | ADEMULYADI |  | 2026-03-10 | PT02 | 3 | 3 | 2026-09-09 | PM |  | 045
| K201 | 2026-03-06 | 2026-06-10 | 2026-03-10 | 2026-03-10 | 2102352025 | 8202241341 |  | 2102350123#TSA PLC SCHNEIDER | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA1-INT |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 045
| K201 | 2026-03-05 | 2026-06-09 | 2026-07-24 | 2026-07-24 | 2102352023 | 8202240011 |  | 2102350122#LTSA PM & MECH SEAL JOHN CR | RU2-HOC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 500000000 | 500000000 | MA1-ROT |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-07-24 | PM |  | 045
| K201 | 2026-03-05 | 2026-03-06 | 2026-12-02 | 2026-12-02 | 2102352029 | 8202240002 |  | 2102350120#PREVENTIVE MAINTENANCE MOTO | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 500000000 | 500000000 | MA1-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-05 | 2026-04-16 | 2026-12-02 | 2026-12-02 | 2102352092 | 8202240013 |  | 2102350115#LTSA HVAC GEDUNG ELECTRICAL | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1100000000 | 630047000 | MA3-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-05 | 2026-05-26 | 2026-05-21 | 2026-05-21 | 2102352074 | 8202240012 |  | 2102350114#LTSA CM SW, CW PUMP | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA3-ROT |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 045
| K201 | 2026-03-05 | 2026-06-15 | 2026-06-15 | 2026-12-30 | 2102352095 | 8202239981 |  | 2102350113#RK0028 LTSA DEG | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 1456237169 | 822034353 | MA3-ROT |  | AHILMANSYAH |  | 2026-03-06 | PT02 | 3 | 3 | 2026-06-15 | PM |  | 045
| K201 | 2026-03-06 | 2026-05-26 | 2026-03-10 | 2026-03-10 | 2102352079 | 8202241340 |  | 2102350112#RK0104 TSA DCS OEM SCHNEIDER | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 500000000 | 0 | MA3-INT |  | DEDISUKMANA |  | 2026-03-11 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 045
| K201 | 2026-03-05 | 2026-04-15 | 2026-12-02 | 2026-12-02 | 2102352091 | 8202239973 |  | 2102350111#PSA UPS DAN DC CHARGER MFR. | RU2-UTL |  | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 800000000 | 0 | MA3-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-05 | 2026-03-06 | 2026-03-11 | 2026-03-11 | 2102352020 | 8202239994 |  | 2102350109#TSA G. CRANE & DECOKING SYS | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 386523566 | 177677267 | MA1-ROT |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K201 | 2026-03-13 | 2026-05-26 | 2026-12-02 | 2026-12-02 | 2102352071 | 8202241701 |  | 2102350108#KONTRAK SRING HANGER & SUPP | RU2-HOC |  | 50 | REL GMCO NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1000000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-03-13 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-05 | 2026-05-26 | 2026-12-02 | 2026-12-02 | 2102351856 | 8202239992 |  | 2102350107#RK0370 LTSA SOOTBLOWER HEATER | RU2-HOC |  | 50 | REL GMCO GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 300000000 | 300000000 | MA1-LIS |  | DEDISUKMANA |  | 2026-03-11 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-12 | 2026-05-26 | 2026-03-16 | 2026-12-30 | 2102351858 | 8202241620 |  | 2102350103#RK0041 LTSA THERMAL INSULATIO | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 0 | 0 | MA1-STA |  | DEDISUKMANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 045
| K201 | 2026-03-05 | 2026-05-26 | 2026-03-16 | 2026-03-16 | 2102352070 | 8202239990 |  | 2102350102#RK0292 LTSA ELEVATOR 140-PX-5 | RU2-HOC |  | 60 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 120854000 | 114190000 | MA1-LIS |  | DEDISUKMANA |  | 2026-03-13 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 045
| K201 | 2026-03-10 | 2026-03-11 | 2026-11-02 | 2026-11-02 | 2102352026 | 8202241559 |  | 2102350101#LTSA CLEANING DENGAN HIGH P | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-11-02 | PM |  | 045
| K201 | 2026-03-10 | 2026-03-11 | 2026-02-02 | 2026-02-02 | 2102351859 | 8202241556 |  | 2102350100#LTASA PIPING BORDES HOC | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 639800000 | 639400000 | MA1-STA |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-03-05 | 2026-06-22 | 2026-12-02 | 2026-12-02 | 2102352077 | 8202239965 |  | 2102350098#RK0098 LTSA TRANSFORMATOR, SW | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1300000000 | 335397000 | MA3-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-12 | 2026-05-26 | 2026-03-12 | 2026-12-31 | 2102352072 | 8202241614 |  | 2102350097#RK0283 LTSA THERMAL INSULATIO | RU2-UTL | 925-PIPING/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 700000000 | 276828000 | MA3-STA |  | DEDISUKMANA |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K201 | 2026-03-05 | 2026-05-26 | 2026-12-10 | 2026-12-10 | 2102352073 | 8202239988 |  | 2102350096#RK0022 TSA PEMELIHARAAN MECHS | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2RR | D12/26/B6/RT-D2H | 500000000 | 478787000 | MA3-ROT |  | DEDISUKMANA |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-10 | PM |  | 045
| K201 | 2026-03-10 | 2026-03-11 | 2026-12-02 | 2026-12-02 | 2102352094 | 8202241558 |  | 2102350095#PERBAIKAN STEAM LEAKS NON T | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 500000000 | 239500000 | MA3-STA |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-10 | 2026-03-11 | 2026-10-02 | 2026-10-02 | 2102352075 | 8202241557 |  | 2102350094#PERBAIKAN DAN PENGGANTIAN P | RU2-UTL |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 389407000 | 191309000 | MA3-STA |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-10-02 | PM |  | 045
| K501 | 2026-04-23 | 2026-04-28 | 2026-12-02 | 2026-12-02 | 2102359527 | 8202242701 |  | 2102350071#PM Rutin G-20-06C LPG Trans | RU5-TBL | G-20-06C/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 44235737 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K501 | 2026-04-23 | 2026-05-12 | 2026-12-02 | 2026-12-02 | 2102359525 | 8202242702 |  | 2102350070#PM Rutin G-20-06B LPG Trans | RU5-TBL | G-20-06B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 429355160 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102352130 | 8202243968 |  | 2102350064#Mechanical Seal Sebelah Dal | RU2-HCC | 211-P-2A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 99641286 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K501 | 2026-03-31 | 2026-04-07 | 2026-07-01 | 2026-07-29 | 2102359470 | 8202241961 |  | 2102350063#PERBAIKAN LCP SOOTBLOWER F-20 | RU5-D&W | SB-201-01A/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 34 | 0 | MA1-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 4 | 3 | 2026-07-01 | PM |  | 003
| K501 | 2026-04-23 | 2026-04-28 | 2026-12-02 | 2026-12-02 | 2102359531 | 8202242703 |  | 2102350058#PM Rutin G-20-25B LPG Feed | RU5-TBL | G-20-25B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 49678526 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K501 | 2026-04-02 | 2026-04-28 | 2026-12-02 | 2026-12-02 | 2102359529 | 8202242029 |  | 2102350057#PM Rutin G-20-25A LPG Feed | RU5-TBL | G-20-25A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 49678525 | 0 | MA4-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K401 | 2026-03-10 | 2026-03-17 | 2026-03-17 | 2026-11-26 | 2102357030 | 8202241541 |  | 2102350054#D26_Perbaikan 101FI203/101FI2 | RU4-RFCC | 101FT203/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 003
| K201 | 2026-03-05 | 2026-05-26 | 2026-12-02 | 2026-12-02 | 2102352027 | 8202239984 |  | 2102350039#RK0291 KONTRAK PERFORMANCE DC | RU2-HOC |  | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1500000000 | 0 | MA1-LIS |  | ADEMULYADI |  | 2026-03-06 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 045
| K201 | 2026-03-10 | 2026-03-11 | 2026-07-31 | 2026-07-31 | 2102351857 | 8202241550 |  | 2102350038#LTSA CLEANING BURNER RUTIN | RU2-HOC |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 363710000 | 222930000 | MA1-STA |  | ADEMULYADI |  | 2026-03-11 | PT02 | 3 | 3 | 2026-07-31 | PM |  | 045
| K201 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102352170 | 8202243966 |  | 2102350022#Pompa Jamed | RU2-HCC | 702-P-2/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 4051894 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102352138 | 8202243964 |  | 2102350021#Mechseal Bocor | RU2-HCC | 212-P-19B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 4051894 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K201 | 2026-05-22 | 2026-06-04 | 2026-06-01 | 2026-06-03 | 2102352171 | 8202243404 |  | 2102350020#High Vibrasi | RU2-HCC | 840-P-1B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 3804161 | 0 | MA2-ROT |  | MAULANAHARUN |  | 2026-05-22 | PT02 | 3 | 3 | 2026-06-01 | PM |  | 003
| K501 | 2026-03-09 | 2026-04-06 | 2026-07-01 | 2026-08-28 | 2102359633 | 8202241485 |  | 2102349939#Perbaikan Card Power MCFA | RU5-TBL | 101-5-CTRL-FIRE/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 2 | 0 | HSSE |  | RIANDAADI |  | 2026-04-06 | PT02 | 5 | 3 | 2026-07-01 | PM |  | 003
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351258 | 8202243476 |  | 2102349916#Perbaikan Motor 140 PM-1B | RU2-HOC | 140-PM-1B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 2146000 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K501 | 2026-05-11 | 2026-05-29 | 2026-05-11 | 2026-06-30 | 2102359707 | 8202243125 |  | 2102349903#Perb. Line 4" Discharge Pom | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 25632175 | 0 | MA4-STA |  | BERNANDOP |  | 2026-05-29 | PT02 | 5 | 3 | 2026-05-11 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-27 | 2026-02-06 | 2026-04-06 | 2102361954 | 8202238844 |  | 2102349900#Perbaikan Motor 16-E-120G-M | RU6-RCC | 16-E-120G-M/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 203508 | 203508 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-27 | 2026-02-06 | 2026-04-06 | 2102361950 | 8202238842 |  | 2102349893#Perbaikan Motor 16-E-119G-M | RU6-RCC | 16-E-119G-M/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 203508 | 203508 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-12-30 | 2102355405 | 8202242362 |  | 2102349890#Perbaikan Indikator Mati SA | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-12-C2H | 4 | 0 | MA6-INT |  | WAHYUCATUR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K601 | 2026-02-11 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361918 | 8202238850 |  | 2102349884#Perbaikan Motor 16-K-102-P1 | RU6-RCC | 16-K-102-P1A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 657457 | 657457 | MA1-LIS |  | AGUNGK79 |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-11 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361916 | 8202238848 |  | 2102349883#Perbaikan Motor 16-E-120P-M | RU6-RCC | 16-E-120P-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1330108 | 203507 | MA1-LIS |  | AGUNGK79 |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361914 | 8202238839 |  | 2102349882#Perbaikan Motor 16-E-117B-M | RU6-RCC | 16-E-117B-M/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 203508 | 203508 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-04-15 | 2026-04-23 | 2026-04-15 | 2026-10-06 | 2102355434 | 8202242468 |  | 2102349878#Pengadaan bearing motor 11P | RU4-FOC1 | 11P6AM/00 | 60 | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 2712239 | 2712239 | MA1-LIS |  | FARIZSETYANA |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K601 | 2026-02-10 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361912 | 8202238846 |  | 2102349874#Perbaikan Motor 16-E-120N-M | RU6-RCC | 16-E-120N-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1330108 | 203508 | MA1-LIS |  | AGUNGK79 |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-27 | 2026-02-06 | 2026-04-06 | 2102361910 | 8202238843 |  | 2102349873#Perbaikan Motor 16-E-120D-M | RU6-RCC | 16-E-120D-M/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 203508 | 203508 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-11 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361847 | 8202238859 |  | 2102349868#Perbaikan Motor 19-P-112A-M | RU6-RCC | 19-P-112A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 391248 | 391248 | MA1-LIS |  | AGUNGK79 |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-11 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361845 | 8202238849 |  | 2102349867#Perbaikan Motor 16-E-121A-M | RU6-RCC | 16-E-121A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1216319 | 1216319 | MA1-LIS |  | AGUNGK79 |  | 2026-02-12 | PT02 | 1 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-27 | 2026-02-06 | 2026-04-06 | 2102361843 | 8202238841 |  | 2102349866#Perbaikan Motor 16-E-117M-M | RU6-RCC | 16-E-117M-M/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 203508 | 0 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361841 | 8202238840 |  | 2102349865#Perbaikan Motor 16-E-117C-M | RU6-RCC | 16-E-117C-M/00 | 50 | REL CSER GMPS MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 203508 | 203508 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-03-04 | 2026-05-04 | 2026-03-05 | 2026-09-05 | 2102359975 | 8202239455 |  | 2102349858#POMPA G-1-35B INDIKASI BOCO | RU5-E15111 | G-1-35B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 7809000 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K601 | 2026-02-11 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361805 | 8202238851 |  | 2102349857#Perbaikan Motor 19-P-106B-M | RU6-RCC | 19-P-106B-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 496603 | 496603 | MA1-LIS |  | AGUNGK79 |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361803 | 8202238835 |  | 2102349856#Perbaikan Motor 15-E-110AD | RU6-RCC | 15-E-110AD-M/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 319400 | 0 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-03-31 | 2026-04-07 | 2026-08-03 | 2026-09-30 | 2102360191 | 8202241963 |  | 2102349846#Perbaikan O2 analyzer HHP B | RU5-UTL | HHP-5-INST/00 | 50 | REL CSER MACM PRC SETC | 5IR | D15/26/B6/RT-C2H | 438473006 | 0 | MA1-INT |  | ANTONIUSAD |  | 2026-04-07 | PT02 | 1 | 3 | 2026-08-03 | PM |  | 004
| K601 | 2026-02-10 | 2026-02-12 | 2026-02-06 | 2026-04-06 | 2102361802 | 8202238838 |  | 2102349839#Perbaikan Motor 15-E-110Y-M | RU6-RCC | 15-E-110Y-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361800 | 8202238837 |  | 2102349838#Perbaikan Motor 15-E-110D-M | RU6-RCC | 15-E-110D-M/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2H | 319400 | 0 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-12 | 2026-02-24 | 2026-02-06 | 2026-04-02 | 2102361758 | 8202238889 |  | 2102349837#Perbaikan Motor 15-E-110AE | RU6-RCC | 15-E-110AE-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1446000 | 1126600 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-02-24 | 2026-03-04 | 2026-02-02 | 2026-12-30 | 2102355813 | 8202239100 |  | 2102349835#[TGH] Tagihan 6 LTSA Fire T | RU4-WS | FL50/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 15890967 | 13507322 | WS-KAB |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-12 | 2026-02-24 | 2026-02-06 | 2026-04-02 | 2102361756 | 8202238888 |  | 2102349818#Perbaikan Motor 15-E-108A | RU6-RCC | 15-E-108A-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1446000 | 1445999 | MA1-LIS |  | DINDINS |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K201 | 2026-04-01 | 2026-06-15 | 2026-04-01 | 2026-04-01 | 2102351497 | 8202241998 |  | 2102349809#300-P-71A Pompa Vibrasi Tin | RU2-HSC | 300-P-71A/00 | 60 | REL CSER GMPS MACM PRC SETC | 2RR | D12/26/B6/NR-D2H | 26046022 | 26046022 | MA2-ROT |  | NURFADHILLA |  | 2026-04-01 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K501 | 2026-05-11 | 2026-05-29 | 2026-05-11 | 2026-06-30 | 2102360260 | 8202243126 |  | 2102349793#Perb. Line 13-10" Prod L.Re | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 45633276 | 0 | MA4-STA |  | BERNANDOP |  | 2026-05-29 | PT02 | 5 | 3 | 2026-05-11 | PM |  | 003
| K201 | 2026-04-27 | 2026-06-09 | 2026-06-02 | 2026-06-02 | 2102351681 | 8202242779 |  | 2102349777#Perbaikan Overhead Crane Wo | RU2-WS | OHC-1/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | WS-LI2 |  | ADEMULYADI |  | 2026-05-07 | PT02 | 3 | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102357600 | 8202243160 |  | 2102349743#[BONPNJM] Pengadaan Fitting | RU4-RFCUTL | 150BD2A/00 | 50 WENG | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-12-30 | 2102357602 | 8202243159 |  | 2102349742#[BONPNJM] Perbaikan Tubing | RU4-RFCUTL | 150BD2A/00 | 50 WAMA WENG | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-13-C2H | 0 | 0 | MA5-INT |  | WAHYUCATUR |  | 2026-05-12 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 045
| K201 | 2026-06-22 | 2026-06-22 | 2026-08-03 | 2026-08-03 | 2102351721 | 8202244038 |  | 2102349702#Perbaikan MEM-16 | RU2-ITP | 930-ME-18/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 1007321 | 0 | MA4-LIS |  | STEVANEKOPP |  | 2026-06-22 | PT02 | 5 | 3 | 2026-08-03 | PM |  | 003
| K202 | 2026-03-05 | 2026-03-05 | 2026-02-02 | 2026-02-02 | 2102352374 | 8202239468 |  | 2102349612#PELAKSANAAN SERVICE BV DAN | RU2S-KIL |  | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/NRZ-D2H | 580000000 | 0 | MAS-ME2 |  | JUNIANTO |  | 2026-03-05 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-11 |  | 2026-02-02 | 2026-12-30 | 2102355670 | 8202238867 |  | 2102349579#Perbaikan Analyzer/GC SRU-I | RU4-SRU | 91AIT360/00 | 50 | CRTD NMAT PRC | 4IR |  | 29000000000 | 0 | MA1-INT |  |  |  |  | PT02 | 4 | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2102360574 | 8202242129 |  | 2102349550#Penarikan Kabel HMI MFP ke |  | HMIFGDS/00 | 01 | CLSD CSER NCMP NMAT PRC | 5IR | D15/09/B6/RT1-K3NH | 0 | 0 | ENG-INT |  | RIANDAADI |  |  | PT02 | 5 | 2 | 2026-04-07 | PM |  | 045
| K401 | 2026-02-06 | 2026-03-06 | 2026-02-10 | 2026-10-28 | 2102355555 | 8202238695 |  | 2102349538#[CR] Penggantian V-Belt 80E | RU4-KPC | 80E202KF/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 2891761 | 0 | MA4-ROT |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 5 | 3 | 2026-02-10 | PM |  | 003
| K201 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 2102351786 | 8202243954 |  | 2102349529#Pengambilan Part Burner WHB | RU2-HOC | 170-B-1/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 32863750 | 0 | MA1-STA |  | STEVANEKOPP |  | 2026-06-18 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-15 | 2026-02-03 | 2026-12-30 | 2102355558 | 8202241709 |  | 2102349517#[TGH] Penggantian Mech Seal | RU4-KPC | 84P201A/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 474180000 | 474180000 | MA4-ROT |  | YUNITAMR |  | 2026-03-16 | PT02 | 5 | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-03-13 | 2026-04-15 | 2026-02-03 | 2026-12-30 | 2102355611 | 8202241710 |  | 2102349516#[TGH] Penggantian Mech Seal | RU4-KPC | 84P211B/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 202860000 | 202860000 | WS-PMP |  | YUNITAMR |  | 2026-03-16 | PT02 | 5 | 3 | 2026-02-03 | PM |  | 003
| K601 | 2026-02-26 | 2026-03-02 | 2026-02-06 | 2026-03-31 | 2102361461 | 8202239177 |  | 2102349503#Perbaikan 15-P-901B | RU6-RCC | 15-P-901B/00 | 50 | REL GMPS NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 54306000 | 54306000 | MA1-ROT |  | DANDARWANI |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102361427 | 8202238845 |  | 2102349494#Perbaikan Motor 16-E-120H-M | RU6-RCC | 16-E-120H-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1330108 | 203507 | MA1-LIS |  | AGUNGK79 |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-12 | 2026-02-06 | 2026-02-19 | 2102361426 | 8202238836 |  | 2102349493#Perbaikan Motor 15-E-110AF- | RU6-RCC | 15-E-110AF-M/00 | 50 | REL CSER MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 0 | 0 | MA1-LIS |  | DANDARWANI |  | 2026-02-12 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K501 | 2026-06-09 | 2026-06-11 | 2026-06-09 | 2026-07-22 | 2102360615 | 8202243719 |  | 2102349487#Perb. LPD 2" Suction P1 A H | RU5-TBL | PIPE-TANK-PUMP/00 | 50 | REL CSER MACM PRC SETC | 5MR | D15/10/B6/RT1-FJNH | 260366756 | 0 | MA4-STA |  | BERNANDOP |  | 2026-06-11 | PT02 | 5 | 3 | 2026-06-09 | PM |  | 003
| K201 | 2026-03-05 | 2026-03-13 | 2026-04-24 | 2026-04-29 | 2102351990 | 8202239653 |  | 2102349475#Pengadaan Mechanical Seal | RU2-HOC | 140-P-5A/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 1 | 0 | MA1-ROT |  | STEVANEKOPP |  | 2026-03-13 | PT02 | 3 | 3 | 2026-04-24 | PM |  | 003
| K401 | 2026-03-03 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102356021 | 8202239351 |  | 2102349455#(TGH) Termin 11 UP Tenaga B | RU4-WS | 037BD101-SCP/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 406388400 | 406388400 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K202 | 2026-04-03 | 2026-04-25 | 2026-02-02 | 2026-02-02 | 2102352378 | 8202242057 |  | 2102349437#PENGECEKAN FILTER SERVO GE- | RU2S-KIL | 900-06GE-6/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 53636499 | 7800000 | MAS-LIS |  | JUNIANTO |  | 2026-04-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102357234 | 8202239450 |  | 2102349417#[TGH] Tagihan Perbaikan 002 | RU4-LOC2 | 002P101A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 64246400 | 64246400 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-25 | 2026-03-05 | 2026-12-22 | 2102356627 | 8202239481 |  | 2102349408#Perbaikan motor pompa 70P1B | RU4-TRML | 70P1BM/00 | 50 WAMA | REL CSER MACM PRC SETC | 4ER | D14/26/B6/RT-4-C2H | 0 | 0 | MA3-LIS |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K201 | 2026-03-03 | 2026-04-06 | 2026-02-02 | 2026-02-02 | 2102352155 | 8202239360 |  | 2102349396#Pengambilan Breaker 3 Phase | RU2-UTL | 560-TRF-AS1/00 | 60 | REL CSER GMPS MACM PRC SETC | 2ER | D12/09/B6/RT1-PWGNH | 5400000 | 5400000 | MA3-LIS |  | ADEMULYADI |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-03-12 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102352380 | 8202241626 |  | 2102349393#PENGECEKAN LINE FUEL BOILER | RU2S-KIL |  | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-D2H | 2338959 | 2338959 | MAS-ME1 |  | JUNIANTO |  | 2026-03-12 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K501 | 2026-03-03 | 2026-05-04 | 2026-03-06 | 2026-09-06 | 2102360691 | 8202239410 |  | 2102349343#EA-1-21B V-BELT RUSAK | RU5-E15111 | EA-1-21B/00 | 60 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 19060642 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-10-22 | 2102357823 | 8202242140 |  | 2102349309# Pengadaan Module Converter |  |  | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 2 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-07 | PM |  | 045
| K401 | 2026-02-25 | 2026-06-03 | 2026-02-25 | 2026-08-31 | 2102357826 | 8202239139 |  | 2102349276#[CR] Mechanical Seal 021P10 | RU4-LOC2 | 021P108/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 6741300 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-25 | PM |  | 003
| K201 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102350957 | 8202243963 |  | 2102349249#211-PM 24B Vibrasi Tinggi | RU2-HCC | 211-P-24B/00 | 50 | REL CSER MACM PRC SETC | 2MR | D12/26/B6/RT-D2H | 37518786 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-06-19 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-02-23 | 2026-04-07 | 2026-02-02 | 2026-12-30 | 2102354786 | 8202239041 |  | 2102349244#Re-Integrasi CEMS 052B101/1 | RU4-UTL | 052B101/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-5-C2H | 250000000 | 0 | MA5-INT |  | SAMSUDINH |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-04-10 | 2026-04-13 | 2026-02-06 | 2026-07-03 | 2102361286 | 8202242341 |  | 2102349216#Perbaikan 12-K-501A | RU6-DHC | 12-K-501A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 0 | 0 | MA2-INT |  | DANDARWANI |  | 2026-04-13 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-05-26 | 2026-05-26 | 2026-05-25 | 2026-12-30 | 2102355104 | 8202243499 |  | 2102349206#[CR] penggantian Accu FT-42 | RU4-K3LL | FT42/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 43493808 | 0 | WS-KAB |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 045
| K401 | 2026-05-26 | 2026-05-26 | 2026-05-25 | 2026-12-30 | 2102355102 | 8202243498 |  | 2102349205#[CR] Perbaikan FT-39 | RU4-K3LL | FT39/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 28009892 | 0 | WS-KAB |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 045
| K201 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2102351280 | 8202239048 |  | 2102349188#Pengadaan Push Button Switc | RU2-ITP | 970-PM-1C/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/10/B6/RT1-PWGNH | 0 | 0 | MA4-LIS |  | STEVANEKOPP |  | 2026-02-23 | PT02 | 8 | 3 | 2026-02-23 | PM |  | 003
| K401 | 2026-02-06 | 2026-04-24 | 2026-02-04 | 2026-11-24 | 2102355533 | 8202238697 |  | 2102349134#[CR] Bocoran packing rod 2n | RU4-LOC3 | 220K101/00 | 60 WAMA | REL CSER GMPS MANC PRC SETC | 4RR | D14/26/B6/RT-9-C1H | 75140253 | 62901225 | MA4-ROT |  | YMOHAMMAD |  | 2026-02-13 | PT02 | 1 | 3 | 2026-02-04 | PM |  | 003
| K201 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2102351285 | 8202239047 |  | 2102349118#Perbaikan Pushbutton switch | RU2-UTL | 925-PM-7A/00 | 50 | REL CSER MSPT PRC SETC | 2ER | D12/10/B6/RT1-PWGNH | 0 | 0 | MA3-LIS |  | STEVANEKOPP |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-23 | PM |  | 003
| K201 | 2026-02-23 | 2026-02-23 | 2026-02-02 | 2026-02-02 | 2102351284 | 8202239046 |  | 2102349117#Perbaikan Pushbutton switch | RU2-UTL | 925-PM-6A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/10/B6/RT1-PWGNH | 0 | 0 | MA3-LIS |  | STEVANEKOPP |  | 2026-02-23 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-31 | 2026-02-02 | 2026-12-30 | 2102357102 | 8202239071 |  | 2102349055#[CR] 87P202C Mech Seal IB B | RU4-KPC | 87P202C/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 114896000 | 114896000 | WS-PMP |  | WAHYUCATUR |  | 2026-03-31 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-05-04 | 2026-05-11 | 2026-07-01 | 2026-07-01 | 2102350927 | 8202242968 |  | 2102348978#Pengadaan Ampere Meter 200 | RU2-ITP | 200-PM-7B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA4-LIS |  | AZIZFATONI |  | 2026-05-11 | PT02 | 3 | 3 | 2026-07-01 | PM |  | 003
| K601 | 2026-02-10 | 2026-02-10 | 2026-02-06 | 2026-07-17 | 2102362383 | 8202238814 |  | 2102348977#Penggantian control valve 5 | RU6-UTL | 52-TV-219B/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 886918 | 0 | MA4-INT |  | DANDARWANI |  | 2026-02-10 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102354974 | 8202239441 |  | 2102348884#[TGH] Penagihan perbaikan 1 | RU4-RFCUTL | 166P512B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 170801550 | 170801550 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 4 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102354971 | 8202239448 |  | 2102348875#[TGH] 166P501A, penagihan p | RU4-RFCUTL | 166P501A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 59389500 | 59389500 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 4 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102362280 | 8202239101 |  | 2102348867#Perbaikan Motor 16-E-119A-M | RU6-RCC | 16-E-119A-M/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2 | 1330108 | 0 | MA1-LIS |  | AGUNGK79 |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K601 | 2026-02-24 | 2026-02-24 | 2026-02-06 | 2026-04-06 | 2102362248 | 8202239099 |  | 2102348866#Perbaikan Motor 15-E-110AE- | RU6-RCC | 15-E-110AE-M/00 | 50 | REL CSER MSPT PRC SETC | 6ER | D16/26/B6/RT-C2 | 1330108 | 0 | MA1-LIS |  | AGUNGK79 |  | 2026-02-24 | PT02 | 3 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-04-07 | 2026-03-06 | 2026-12-30 | 2102354972 | 8202239442 |  | 2102348862#[TGH] 166P501B, penagihan p | RU4-RFCUTL | 166P501B/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 54187500 | 54187500 | WS-PMP |  | YUNITAMR |  | 2026-03-06 | PT02 | 4 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-02 | 2026-06-18 | 2026-02-02 | 2026-12-30 | 2102354799 | 8202239278 |  | 2102348852#Perbaikan Pipa Metode Wrapp |  |  | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 1032011000 | 1032011000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-02 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102355646 | 8202239440 |  | 2102348851#[TGH] Penagihan perbaikan p | RU4-RFCUTL | 166P512A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 169614100 | 169614100 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 4 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102355579 | 8202239444 |  | 2102348840#[TGH] TAGIHAN_PM Pompa 100P | RU4-GTO | 100P621B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 61528950 | 61528950 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102355750 | 8202239445 |  | 2102348830#[TGH] Pompa under perform 2 | RU4-LOC3 | 200P104A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 65159300 | 65159300 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102355565 | 8202239443 |  | 2102348786#[TGH] Penagihan Pompa CPI 0 | RU4-UTL | 005P101A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 64246400 | 64246400 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102355644 | 8202239447 |  | 2102348759#[TGH] TAGIHAN_PM Pompa 148P | RU4-RFCGTO | 148P503A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 83249000 | 83249000 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K401 | 2026-03-04 | 2026-03-09 | 2026-02-03 | 2026-12-28 | 2102355641 | 8202239446 |  | 2102348758#[TGH] TAGIHAN_PM Pompa 148P | RU4-RFCGTO | 148P502A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 73491000 | 73491000 | WS-PMP |  | WAHYUCATUR |  | 2026-03-09 | PT02 | 3 | 3 | 2026-02-03 | PM |  | 003
| K401 | 2026-02-24 | 2026-05-05 | 2026-02-02 | 2026-12-30 | 2102357633 | 8202239122 |  | 2102348750#Perbaikan Density DMA4500M | RU4-FOC2 | 30BD12EE0012A/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 850000000 | 0 | WS-INT |  | FARIZSETYANA |  | 2026-03-02 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-04-27 | 2026-04-27 | 2026-06-10 | 2026-06-10 | 2102361970 | 8202242755 |  | 2102348724#Pembuatan jumperline kerose | RU6-ITP | 42-PIPE/00 | 50 | REL CSER MANC PRC SETC | 6MR | D16/26/B6/RT-C2H | 70437553 | 0 | MA4-STA |  | DANDARWANI |  | 2026-04-27 | PT02 | 5 | 3 | 2026-06-10 | PM |  | 003
| K401 | 2026-02-10 | 2026-04-21 | 2026-04-21 | 2026-12-21 | 2102358280 | 8202238832 |  | 2102348649#26_140FT032 Transmitter Rusak | RU4-GTO | 140FT032/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | FARIZSETYANA |  | 2026-04-21 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-03-10 | 2026-04-15 | 2026-03-10 | 2026-12-30 | 2102356146 | 8202241534 |  | 2102348547#[TGH] Penagihan TSA MS 11P4 | RU4-FOC1 | 11P4A/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 173929000 | 0 | WS-PMP |  | YUNITAMR |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-10 |  | 2026-02-02 | 2026-02-02 | 2102358229 | 8202238833 |  | 2102348358#3 PSU tidak dapat charging |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 5 | 2 | 2026-02-02 | PM |  | 045
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351717 | 8202243484 |  | 2102348268#Perbaikan Motor 925-PM-6B | RU2-UTL | 925-PM-6B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 21998702 | 0 | MA3-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-06 | 2026-02-02 | 2026-12-30 | 2102356993 | 8202239467 |  | 2102348133#Termin 4 -Pemeliharaan & Per. | RU4-UTL | 51E1/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 164466500 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351790 | 8202243485 |  | 2102348100#701 EM-9B suara kasar | RU2-HCC | 701-EM-9B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 248128 | 0 | MA2-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K202 | 2026-03-25 | 2026-05-21 | 2026-02-02 | 2026-02-02 | 2102352426 | 8202241873 |  | 2102348057#Gagal start 900-06GE-5 (3x) | RU2S-KIL | 900-06GE-5/00 | 50 | REL CSER GMPS MANC PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 230000 | 230000 | MAS-ME1 |  | JUNAIDIT |  | 2026-03-30 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-03-03 | 2026-04-16 | 2026-02-02 | 2026-12-30 | 2102352429 | 8202239398 |  | 2102347991#SARANA BANTU NAVIGASI (SBNP | RU2S-KIL | 10PL946503-A1A1/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/NRZ-D2H | 1100000000 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K601 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-04-01 | 2102361238 | 8202238800 |  | 2102347906#11-P-111 A | RU6-HSC | 11-P-111A/00 | 50 WAMA | REL CSER MANC PRC SETC | 6RR | D16/26/B6/RT-C2H | 28420531 | 0 | MA1-ROT |  | PANDUA |  | 2026-02-09 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 003
| K202 | 2026-05-19 | 2026-06-05 | 2026-05-19 | 2026-05-19 | 2102352437 | 8202243295 |  | 2102347846#BAS JETTY I TIDAK MENYALA | RU2S-KIL | 946-BAS-01/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/NRZ-C1H | 0 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-06-05 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 003
| K401 | 2026-02-23 | 2026-05-05 | 2026-02-02 | 2026-12-30 | 2102355216 | 8202239067 |  | 2102347839#[CR] 84P202A Mech Seal Leak | RU4-KPC | 84P202A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 203175000 | 203175000 | WS-PMP |  | FARIZSETYANA |  | 2026-03-31 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K601 | 2026-03-04 | 2026-03-11 | 2026-02-06 | 2026-03-31 | 2102362602 | 8202239439 |  | 2102347809#Perbaikan mech seal pompa | RU6-ITP | 42-P-402A/00 | 50 | REL CSER MSPT PRC SETC | 6RR | D16/26/B6/RT-C2H | 11880 | 0 | MA4-ROT |  | PANDUA |  | 2026-03-04 | PT02 | 5 | 3 | 2026-02-06 | PM |  | 003
| K401 | 2026-02-12 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102357947 | 8202238902 |  | 2102347697#[CR] Perbaikan bocoran mech | RU4-FOC1 | 17P1B/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 74353750 | 74353750 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-05-25 |  | 2026-08-03 | 2026-08-03 | 2102352044 | 8202243486 |  | 2102347695#212-EM-18B motor trip | RU2-HCC | 212-EM-18B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 88000 | 0 | MA2-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-08-03 | PM |  | 003
| K201 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2102352048 | 8202243634 |  | 2102347686#701-P-3B Pompa Jammed | RU2-HCC | 701-P-3B/00 | 50 | CRTD CSER MACM PRC | 2RR | D12/26/B6/RT-D2H | 83432000 | 0 | MA2-ROT |  |  |  |  | PT02 | 3 | 2 | 2026-06-04 | PM |  | 003
| K202 | 2026-03-31 | 2026-04-17 | 2026-02-02 | 2026-02-02 | 2102352442 | 8202241994 |  | 2102347684#DISPENSER FUEL OIL TK-F-132 | RU2S-KIL | 946-FI-501/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 183400000 | 183400000 | MAS-INT |  | JUNIANTO |  | 2026-03-31 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-31 | 2026-02-02 | 2026-12-30 | 2102357898 | 8202239075 |  | 2102347679#[CR] Pompa 021P-108 jammed | RU4-LOC2 | 021P108/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 119609000 | 119609000 | WS-PMP |  | WAHYUCATUR |  | 2026-03-31 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-04-20 | 2026-04-23 | 2026-12-21 | 2026-12-21 | 2102352041 | 8202242585 |  | 2102347668#Mechanical Cleaning | RU2-HSC | 100-E-7A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 300000000 | 0 | MA2-STA |  | STEVANEKOPP |  | 2026-04-21 | PT02 | 5 | 3 | 2026-12-21 | PM |  | 003
| K601 | 2026-04-30 | 2026-04-30 | 2026-02-06 | 2026-07-03 | 2102362348 | 8202242846 |  | 2102347667#Perbaikan instrumentasi 13- | RU6-DHC | 13-K-101-LP/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 2 | 0 | MA2-INT |  | DANDARWANI |  | 2026-04-30 | PT02 | 4 | 3 | 2026-02-06 | PM |  | 003
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102352045 | 8202243487 |  | 2102347664#212-PM-24B motor high vibra | RU2-HCC | 212-PM-24B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 88000 | 0 | MA2-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K202 | 2026-02-13 | 2026-03-08 | 2026-02-02 | 2026-02-02 | 2102352452 | 8202238921 |  | 2102347501#Penggantian expansion joint | RU2S-KIL | 10PL90001A-A1A1/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/25/B6/RTZ-C1H | 245948 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-03-08 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-03-31 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102352454 | 8202241995 |  | 2102347495#Perbaikan Isolasi Pipa 20 I | RU2S-KIL | 12PL946Y23-A1A1/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 1948606 | 1948606 | MAS-ME1 |  | JUNIANTO |  | 2026-03-31 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K301 | 2026-04-20 | 2026-04-24 | 2026-04-21 | 2026-04-21 | 2102353261 | 8202242597 |  | 2102347470#Pengadaan Material Level Gl | RU3-CDL | CDU-6-D-3/00 | 50 WAMA | REL CSER MACM PRC SETC | 3MR | D13/26/B6/RT-1-C2H | 0 | 0 | MA3-STA |  | ALEPDALITAN |  | 2026-04-21 | PT02 | 5 | 3 | 2026-04-21 | PM |  | 003
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-08-03 | 2102362210 | 8202244025 |  | 2102347467#Perbaikan bocoran HE 62-E-2 | RU6-UTL | 62-E-201B/00 | 50 | REL CSER MACM PRC SETC | 6MR | D16/26/B6/RT-C2H | 2943661 | 0 | MA4-STA |  | DANDARWANI |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-22 | PM |  | 004
| K202 | 2026-03-06 | 2026-06-09 | 2026-02-02 | 2026-02-02 | 2102352464 | 8202241320 |  | 2102347379#CLEANING TANKI 946-TK-12 | RU2S-KIL | 946-TK-12/00 | 50 | REL CSER GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 3326600 | 3312689 | MAS-ME1 |  | JUNAIDIT |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-04-21 | 2102351163 | 8202242623 |  | 2102347288#Perbaikan kabel power dari | RU2-UTL | 560-SWGTR-3WTP/00 | 50 | REL NMAT PRC SETC | 2ER | D12/26/B6/RT-D2H | 1480000000 | 0 | MA3-LIS |  | STEVANEKOPP |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 004
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351201 | 8202243488 |  | 2102347257#Perbaikan Bearing 140 EM - | RU2-HOC | 140-EM-8D/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 2847386 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K401 | 2026-02-23 | 2026-04-28 | 2026-02-02 | 2026-12-30 | 2102354105 | 8202239056 |  | 2102347247#[CR] 86P202B Seal Leak | RU4-KPC | 86P202B/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 179025000 | 179025000 | WS-PMP |  | AGHANIAKBAR |  | 2026-03-31 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-31 | 2026-02-02 | 2026-12-30 | 2102354103 | 8202239060 |  | 2102347246#[CR] 86P202A Seal leak | RU4-KPC | 86P202A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 179025000 | 179025000 | WS-PMP |  | WAHYUCATUR |  | 2026-03-31 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-31 | 2026-02-02 | 2026-12-30 | 2102354067 | 8202239073 |  | 2102347244#[CR] 84P201B Seal Leak | RU4-KPC | 84P201B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 237090000 | 237090000 | WS-PMP |  | WAHYUCATUR |  | 2026-03-31 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351206 | 8202243489 |  | 2102347152#Perbaikan Motor 220 PM-2B | RU2-HOC | 220-PM-2B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 616350 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K401 | 2026-05-19 |  | 2026-05-20 | 2026-05-20 | 2102354295 | 8202243309 |  | 2102347149#[CR] Perbaikan Pompa 30P101 | RU4-TRML | 30P101A/00 | 01 WASR | CRTD CSER NMAT PRC | 4RR |  | 0 | 0 | MA3-ROT |  |  |  |  | PT02 | 4 | 2 | 2026-05-20 | PM |  | 003
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351247 | 8202243490 |  | 2102346888#Perbaikan Bearing Motor 110 | RU2-HOC | 110-PM-9B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-15 | 2026-03-12 | 2026-12-30 | 2102356619 | 8202241616 |  | 2102346826#[PV] Pemeliharaan FT-30 | RU4-K3LL | FT30/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 115986800 | 115986800 | WS-KAB |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-03-12 | 2026-04-15 | 2026-03-12 | 2026-12-30 | 2102356694 | 8202241625 |  | 2102346821#[PV] Pemeliharaan FT-41 | RU4-K3LL | FT41/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 7897396 | 7897396 | WS-KAB |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-30 | 2026-03-12 | 2026-12-30 | 2102356693 | 8202241498 |  | 2102346820#[PV] Pemeliharaan FT-40 | RU4-K3LL | FT40/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 7897396 | 7897396 | WS-KAB |  | AGHANIAKBAR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-12 | 2026-04-15 | 2026-03-12 | 2026-12-30 | 2102356617 | 8202241624 |  | 2102346802#[PV] Pemeliharaan FT-28 | RU4-K3LL | FT28/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 6306538 | 6306538 | WS-KAB |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-12-30 |  | 8202241730 | 8202238967 | 2102346801#[PV] Pemeliharaan FT-27 | RU4-K3LL | FT27/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C1H | 6306538 | 6306538 | WS-KAB |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351335 | 8202243491 |  | 2102346766#Perbaikan 140 PM-27B | RU2-HOC | 140-PM-27B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 112171 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K401 | 2026-04-07 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102356467 | 8202242137 |  | 2102346716#[CR] Perbaikan Pompa 20P2 | RU4-LOC1 | 20P2/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 58994950 | 58994950 | WS-PMP |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-05-19 |  | 2026-05-20 | 2026-05-20 | 2102356915 | 8202243308 |  | 2102346713#[CR] Perbaikan Pompa 40P101 | RU4-TRML | 40P101A/00 | 01 WASR | CRTD CSER NMAT PRC | 4RR |  | 0 | 0 | MA3-ROT |  |  |  |  | PT02 | 5 | 2 | 2026-05-20 | PM |  | 003
| K201 | 2026-05-25 |  | 2026-09-01 | 2026-09-01 | 2102351361 | 8202243492 |  | 2102346657#Perbaikan Motor 110 PM-3A | RU2-HOC | 110-PM-3A/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 503661 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-09-01 | PM |  | 003
| K201 | 2026-05-26 |  | 2026-08-03 | 2026-08-03 | 2102351362 | 8202243532 |  | 2102346656#Perbaikan Motor 140 PM-23A | RU2-HOC | 140-PM-23A/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 906237 | 0 | MA1-LIS |  |  |  |  | PT02 | 3 | 2 | 2026-08-03 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-26 | 2026-05-21 | 2026-11-19 | 2102351456 | 8202243403 |  | 2102346473#Positioner Control PDCV 54 | RU2-UTL | 550-STK-PDT-54/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 005
| K201 | 2026-05-18 |  | 2026-05-18 | 2026-11-16 | 2102351552 | 8202243265 |  | 2102346227#Instrumentasi Area HCC Rusa | RU2-HCC | 212-H-1/00 | 01 | CRTD CSER MACM PRC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-18 | PM |  | 005
| K401 | 2026-03-11 | 2026-04-15 | 2026-03-12 | 2026-12-30 | 2102357605 | 8202241592 |  | 2102346202#[PV] Perbaikan Minor & Valv | RU4-K3LL | FT29/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/XX/B6/RT-C2NH | 31864185 | 31864185 | WS-KAB |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-03-11 | 2026-04-15 | 2026-03-12 | 2026-12-30 | 2102357607 | 8202241590 |  | 2102346201#[PV] Penggantian Ban dan La | RU4-K3LL | FT39/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 92734733 | 92734373 | WS-KAB |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 003
| K401 | 2026-04-01 | 2026-05-26 | 2026-04-02 | 2026-12-30 | 2102354903 | 8202242014 |  | 2102345941#[CR] Perbaikan FT 28 | RU4-K3LL | FT28/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 13420499 | 13420499 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-05-18 | 2026-05-26 | 2026-05-18 | 2026-11-17 | 2102351820 | 8202243266 |  | 2102345321#Perbaikan O2 Analyzer 310-A | RU2-HSC | 310-AT-383/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-18 | PM |  | 005
| K201 | 2026-05-18 | 2026-05-26 | 2026-05-18 | 2026-11-17 | 2102351821 | 8202243267 |  | 2102345320#Perbaikan Control Valve 310 | RU2-HSC | 310-BV-9A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-18 | PM |  | 005
| K401 | 2026-03-10 | 2026-04-24 | 2026-03-10 | 2026-12-30 | 2102356217 | 8202241536 |  | 2102345067#[CR] Perbaikan pompa bocor | RU4-LOC3 | 260P156B/00 | 60 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 149100000 | 0 | WS-PMP |  | YMOHAMMAD |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-13 | 2026-06-19 | 2026-02-02 | 2026-12-30 | 2102357108 | 8202238908 |  | 2102344976#[CR] Mechanical Seal 87P204 | RU4-KPC | 87P204A/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 200641050 | 200641050 | WS-PMP |  | AGHANIAKBAR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102354054 | 8202239449 |  | 2102344866#[CR] Pompa under perform 20 | RU4-LOC3 | 200P101B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 62179200 | 62179200 | WS-PMP |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K201 | 2026-05-26 |  | 2026-08-07 | 2026-08-07 | 2102352061 | 8202243533 |  | 2102344705#Perbaikan Motor 200-PM-6B | RU2-HSC | 200-PM-6B/00 | 50 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 2146000 | 0 | MA2-LIS |  |  |  |  | PT02 | 5 | 2 | 2026-08-07 | PM |  | 003
| K202 | 2026-02-25 | 2026-03-09 | 2026-02-02 | 2026-02-02 | 2102352506 | 8202239172 |  | 2102344671#Perbaikan Solenoid Metering | RU2S-KIL | 946-S-1800B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/NRZ-C1H | 11532 | 11532 | MAS-ME1 |  | JUNIANTO |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-05-22 | 2026-05-22 | 2026-06-01 | 2026-06-03 | 2102352120 | 8202243405 |  | 2102344660#MATERIAL Penggantian Membra | RU2-UTL | 920-P-2D/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 0 | 0 | MA3-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-06-01 | PM |  | 003
| K201 | 2026-05-22 | 2026-05-22 | 2026-06-03 | 2026-06-04 | 2102352115 | 8202243406 |  | 2102344604#211-P-15B High Vibration | RU2-HCC | 211-P-15B/00 | 50 | REL CSER MACM PRC SETC | 2RR | D12/26/B6/RT-D2H | 7333398 | 0 | MA2-ROT |  | STEVANEKOPP |  | 2026-05-22 | PT02 | 3 | 3 | 2026-06-03 | PM |  | 003
| K201 | 2026-03-09 |  | 2026-02-02 | 2026-02-02 | 2102352112 | 8202241487 |  | 2102344579#Fire Proofing Area HSC - Pr | RU2-HSC |  | 01 | CRTD NMAT PRC | 2MR | D12/09/B6/RT1-100NH | 0 | 0 | MA2-STA |  |  |  |  | PT02 | 5 | 2 | 2026-02-02 | PM |  | 045
| K401 | 2026-04-07 | 2026-04-17 | 2026-02-09 | 2026-12-30 | 2102356803 | 8202242134 |  | 2102344491#[CR] 48P202 Saat Jalan Vibr | RU4-TRML | 48P202/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 102464950 | 102464950 | WS-PMP |  | WAHYUCATUR |  | 2026-04-17 | PT02 | 5 | 3 | 2026-02-09 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-26 | 2026-05-21 | 2026-06-04 | 2102351065 | 8202243397 |  | 2102344350#Perbaikan Press Tansmitter | RU2-UTL | 550-TRF-BMHI/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 8290000 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 005
| K401 | 2026-06-18 | 2026-06-21 | 2026-06-18 | 2027-06-30 | 2102354003 | 8202243949 |  | 2102344204#Perbaikan AC 10SS1 | RU4-LOC1 | 20SS1AHU1/00 | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 2000000000 | 0 | MA5-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-06-18 | PM |  | 003
| K601 | 2026-02-26 | 2026-05-29 | 2026-03-02 | 2026-05-06 | 2102363260 | 8202239176 |  | 2102344166#Perbaikan 22-P-901B | RU6-DHC | 22-P-901B/00 | 60 | TECO CNF GMPS NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 216384000 | 216384000 | MA2-ROT |  | SAPBATCH | 2026-05-29 | 2026-03-02 | PT02 | 3 | 3 | 2026-05-29 | PM |  | 003
| K601 | 2026-04-23 | 2026-04-24 | 2026-02-06 | 2026-07-03 | 2102363206 | 8202242683 |  | 2102344078#Penambahan control valve pa | RU6-DHC | 12-FV-002/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 17698453 | 0 | MA2-INT |  | DANDARWANI |  | 2026-04-24 | PT02 | 2 | 3 | 2026-02-06 | PM |  | 003
| K202 | 2026-03-30 | 2026-04-07 | 2026-02-02 | 2026-02-02 | 2102352517 | 8202241953 |  | 2102344040#Fire Truck 717 AFT 3 | RU2S-LKKK | 717-AFT-3/00 | 50 | REL CSER MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 5355968 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-03-31 | PT02 | 8 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-26 | 2026-05-22 | 2026-02-26 | 2026-11-30 | 2102357124 | 8202239200 |  | 2102343859#[CR] Perbaikan Pompa 54P202 | RU4-UTL | 54P202A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102357121 | 8202238862 |  | 2102343856#Penggantian Transmitter 153 | RU4-RFCUTL | 153TT001/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102357594 | 8202238863 |  | 2102343830#Perbaikan 14-WI-002 |  |  | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 045
| K401 | 2026-02-24 | 2026-03-04 | 2026-02-02 | 2026-12-30 | 2102357795 | 8202239109 |  | 2102343808#[CR] Perbaikan FT-42 | RU4-WS | FL53/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 210277398 | 178735788 | WS-KAB |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102357793 | 8202238865 |  | 2102343781#TSA Sparing HB66 | RU4-TRML | 66HB101/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  | YMOHAMMAD |  |  | PT02 | 4 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102357740 | 8202238864 |  | 2102343767#Seal Piston Bocor 105-FV-04 | RU4-RFCGTO | 105FY-U105/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-29 | 2026-02-02 | 2026-02-02 | 2102357974 | 8202238868 |  | 2102343757#Tagihan PM Field Instrument | RU4-RFCC | 30BD12EE0102A/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA6-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-05-29 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102358020 | 8202238869 |  | 2102343744#Penggantian Remote Display | RU4-FOC1 | 14LSL030A/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102353714 | 8202238871 |  | 2102343727#Perbaikan PSU 14K602A | RU4-FOC1 | 20UCPSK602A/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102353297 | 8202238870 |  | 2102343699#014S111 reverse jet CCR rus | RU4-FOC2 | 014S111/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-04-07 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102353713 | 8202242138 |  | 2102343686#[CR] Pompa noise 200P101B | RU4-LOC3 | 200P101B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-9-C2H | 57878900 | 57878900 | WS-PMP |  | FARIZSETYANA |  | 2026-05-13 | PT02 | 5 | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354010 | 8202238936 |  | 2102343650#Kerusakan solenoid 105UV604 | RU4-RFCGTO | 105F502/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354012 | 8202238937 |  | 2102343641#Perbaikan 13FT021 | RU4-FOC1 | 13FT021/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-11 | 2026-05-25 | 2026-04-22 | 2026-12-30 | 2102357794 | 8202238866 |  | 2102343598#penggantian Control Valve | RU4-SRU | 93XV058/00 | 60 | CLSD CSER MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 1 | 0 | MA1-INT |  | YMOHAMMAD |  | 2026-04-22 | PT02 | 5 | 3 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354236 | 8202238940 |  | 2102343571#Penggantian 154LI008B | RU4-RFCUTL | 154LI008B/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354234 | 8202238938 |  | 2102343563#Transmitter 024LT-008B rusa | RU4-LOC2 | 024LT008B/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354660 | 8202238941 |  | 2102343505#Temp Indicator Penunjukkan | RU4-GTO | 140TT067C/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-09 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354949 | 8202241470 |  | 2102343490#39P202A under perform | RU4-TRML | 39P202A/00 | 50 | CRTD NMAT PRC | 4RR |  | 48608000 | 0 | WS-PMP |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-09 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354816 | 8202241461 |  | 2102343455#[BD] Pompa 054P101A jammed | RU4-UTL | 054P101A/00 | 50 | CRTD NMAT PRC | 4RR |  | 255378000 | 0 | WS-PMP |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354769 | 8202238943 |  | 2102343452#penggantian level Transmite |  |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA3-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 045
| K401 | 2026-02-10 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102355032 | 8202238806 |  | 2102343397#85P210A underperform | RU4-KPC | 85P210A/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 134373950 | 134373950 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102355033 | 8202238944 |  | 2102343395#K89_V1_501X.PV Alrm HH 89K2 | RU4-KPC | 89K201/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | YMOHAMMAD |  |  | PT02 | 5 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-12-30 | 2102355384 | 8202241358 |  | 2102343367#[CR] Fabrikasi Casing Pompa | RU4-RFCC | 102P510A/00 | 50 | CRTD NMAT PRC | 4RR |  | 492217000 | 0 | WS-PMP |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-03-10 | PM |  | 003
| K401 | 2026-02-18 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102355274 | 8202238945 |  | 2102343356#Pengadaan LT Displacer RFCC | RU4-REL |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA6-INT |  | YMOHAMMAD |  |  | PT02 | 8 | 2 | 2026-05-25 | PM |  | 045
| K201 | 2026-03-09 | 2026-05-26 | 2026-03-10 | 2026-11-06 | 2102351349 | 8202241495 |  | 2102343208#RK0371 LTSA CLEANING SEPARATO | RU2-ITP |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 700000000 | 462800000 | MA4-STA |  | DEDISUKMANA |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 045
| K201 | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-12-31 | 2102351402 | 8202239452 |  | 2102343179# LTSA PEMELIHARAAN THERMAL | RU2-HOC | 140-PIPING/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 200000000 | 0 | MA1-STA |  | STEVANEKOPP |  | 2026-03-04 | PT02 | 3 | 3 | 2026-03-04 | PM |  | 003
| K201 | 2026-04-13 | 2026-06-09 | 2026-05-14 | 2026-12-29 | 2102351404 | 8202242357 |  | 2102343172#CLEANING BURNER RUTIN AREA | RU2-HOC | 140-V-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 200000000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-04-17 | PT02 | 3 | 3 | 2026-05-14 | PM |  | 003
| K201 | 2026-03-30 |  | 2026-02-02 | 2026-02-02 | 2102351400 | 8202241920 |  | 2102343165#REVITALISASI STRUCTURE DRIL | RU2-HOC | 140-V-1A/00 | 01 | CRTD NMAT PRC | 2MR | D12/XX/B6/RT-D2NH | 0 | 0 | MA1-STA |  |  |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-11-18 | 2102351501 | 8202243310 |  | 2102343057#Pengambilan Pressure Gauge | RU2-HSC | 301-C-1/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 005
| K401 | 2026-02-24 | 2026-03-12 | 2026-02-24 | 2026-12-30 | 2102357485 | 8202239135 |  | 2102343032#Pengadaan coupling multilug | RU4-K3LL | FT27/00 | 50 | CRTD CSER MACM PRC | 4MR | D14/XX/B6/RT-C2NH | 4462351842 | 0 | MA3-STA |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-02-24 | PM |  | 045
| K201 | 2026-05-21 | 2026-05-26 | 2026-05-21 | 2026-06-04 | 2102351503 | 8202243398 |  | 2102343013#Perbaikan Level glass 550-T | RU2-UTL | 550-TK-701/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 9801000 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 005
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-11-18 | 2102351504 | 8202243314 |  | 2102343012#Perbaikan Pressure Transmit | RU2-UTL | 940-B-3/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 005
| K201 | 2026-06-05 | 2026-06-18 | 2026-06-15 | 2026-12-31 | 2102351601 | 8202243664 |  | 2102342987#Pemeliharaan rutin AC dalam | RU2-UTL | UTL-AC-ES/00 | 50 | CRTD NMAT PRC | 2IR | D12/26/B6/RT-D2H | 1987600000 | 0 | WS-IN1 |  | STEVANEKOPP |  |  | PT02 | 3 | 2 | 2026-06-15 | PM |  | 004
| K201 | 2026-03-09 | 2026-06-17 | 2026-03-11 | 2026-03-11 | 2102351540 | 8202241484 |  | 2102342948#RK0024(PSA) METERING SYSTEM D | RU2-ITP |  | 60 | REL GMPS NMAT PRC SETC | 2IR | D12/26/B6/RT-D2H | 500000000 | 500000000 | MA4-INT |  | ADEMULYADI |  | 2026-03-10 | PT02 | 3 | 3 | 2026-03-11 | PM |  | 045
| K201 | 2026-05-21 | 2026-05-26 | 2026-05-21 | 2026-11-19 | 2102351628 | 8202243399 |  | 2102342848#Perbaikan alarm low dischar | RU2-UTL | 510-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 22266225 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 005
| K401 | 2026-03-30 | 2026-04-20 | 2026-02-02 | 2026-02-02 | 2102358007 | 8202241939 |  | 2102342842#Control Valve Macet 100TV63 | RU4-GTO | 100V632/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA7-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-04-20 | PM |  | 003
| K401 | 2026-03-30 | 2026-04-20 | 2026-02-02 | 2026-02-02 | 2102358067 | 8202241940 |  | 2102342824#Tagihan Termin 1 TSA PT. Sp |  |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | WS-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-04-20 | PM |  | 045
| K501 | 2026-04-02 | 2026-04-28 | 2026-06-02 | 2026-06-02 | 2102359077 | 8202242023 |  | 2102342796#Perbaikan pompa G-5-09A | RU5-E15111 | G-5-09A/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 932600 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 4 | 3 | 2026-06-02 | PM |  | 003
| K401 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2102358112 | 8202243511 |  | 2102342777#[PV] Fabrikasi Impeller Spa | RU4-RFCC | 101P522A/00 | 50 | CRTD NMAT PRC | 4RR |  | 491318000 | 0 | WS-PMP |  |  |  |  | PT02 | 8 | 2 | 2026-05-26 | PM |  | 003
| K401 | 2026-02-24 | 2026-03-11 | 2026-02-02 | 2026-12-30 | 2102353752 | 8202239102 |  | 2102342727#[CR] Perbaikan FT-27 | RU4-WS | FL50/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 24790031 | 21071527 | WS-KAB |  | YUNITAMR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-02-24 | 2026-03-04 | 2026-02-02 | 2026-12-30 | 2102353753 | 8202239103 |  | 2102342725#[CR] Perbaikan FT-39 | RU4-WS | FL52/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 109898936 | 93414096 | WS-KAB |  | WAHYUCATUR |  | 2026-03-04 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-30 | 2026-04-20 | 2026-02-02 | 2026-02-02 | 2102358154 | 8202241947 |  | 2102342717#052T101 Conductivity Analiz | RU4-UTL | 052T101/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-04-20 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-11-18 | 2102351692 | 8202243315 |  | 2102342712#Perbaikan Temp. Switch 220T | RU2-HOC | 220-C-1B/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA1-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 005
| K401 | 2026-03-30 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102353837 | 8202241948 |  | 2102342578#Perbaikan Positioner 14FV50 | RU4-FOC1 | 14FV506/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-30 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354567 | 8202241949 |  | 2102342475#Kerusakan pada 39LT220 Sump | RU4-TRML | 39LT220/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA4-INT |  | YMOHAMMAD |  |  | PT02 | 5 | 2 | 2026-05-25 | PM |  | 003
| K401 | 2026-03-06 |  | 2026-02-02 | 2026-02-02 | 2102356359 | 8202241297 |  | 2102342300#LTSA_PEMELIHARAAN OXYGEN AN | RU4-RFCC | 102FT-U102/00 | 01 | CRTD NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  |  |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-06-21 | 2026-06-22 | 2026-06-19 | 2026-12-30 | 2102353892 | 8202243986 |  | 2102342172#RK_26-RT ONLINE CHEMICAL CL |  |  | 50 | REL CSER NMAT PRC SETC | 4MR | D14/26/B6/RT-10-C2H | 0 | 0 | MA4-STA |  | WAHYUCATUR |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 045
| K401 | 2026-03-30 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102353898 | 8202241954 |  | 2102342155#Penggantian pressure gauge |  |  | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 045
| K401 | 2026-03-30 | 2026-04-20 | 2026-02-02 | 2026-02-02 | 2102353970 | 8202241955 |  | 2102342154#Tagihan Termin I Upgrade DC |  |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR | D14/09/B6/RTNH | 0 | 0 | MA3-INT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-04-20 | PM |  | 045
| K401 | 2026-03-30 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102353899 | 8202241951 |  | 2102342139#Penggantian thermodial di U |  |  | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 045
| K401 | 2026-03-09 | 2026-05-25 | 2026-03-02 | 2026-12-30 | 2102353578 | 8202241459 |  | 2102342109#[BK] 84P203B Jammed | RU4-KPC | 84P203B/00 | 50 | CRTD NMAT PRC | 4RR |  | 494969000 | 0 | WS-PMP |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-03-02 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-11-18 | 2102351803 | 8202243316 |  | 2102342095#Perbaikan 940-PSH 1127 940- | RU2-UTL | 940-PSH-1127/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 005
| K401 | 2026-03-30 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354100 | 8202241956 |  | 2102342069#Penggantian Power supply VM | RU4-LOC1 | 24K2/00 | 01 | CLSD NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-05-25 | PM |  | 045
| K401 | 2026-03-31 | 2026-04-20 | 2026-02-02 | 2026-02-02 | 2102354348 | 8202241959 |  | 2102342006#82PDI207A stariner rusak | RU4-KPC | 82P201A/00 | 01 | CRTD CSER NMAT PRC | 4MR |  | 0 | 0 | MA4-STA |  | DWIHIZZKI |  |  | PT02 | 5 | 2 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-31 | 2026-05-25 | 2026-02-02 | 2026-02-02 | 2102354683 | 8202241960 |  | 2102341980#Penggantian modul 93FT-055 | RU4-SRU | 93FT255/00 | 01 | CLSD NCMP NMAT PRC | 4IR |  | 0 | 0 | MA1-INT |  | YMOHAMMAD |  |  | PT02 | 5 | 2 | 2026-05-25 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-26 | 2026-05-21 | 2026-11-19 | 2102351836 | 8202243400 |  | 2102341839#Perbaikan Flow Transmitter | RU2-UTL | 520-PIPING/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 005
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-05-29 | 2102351891 | 8202243311 |  | 2102341771#Penggantian Torque Tube Lev | RU2-HSC | 200-LT-65/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 51100000 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 005
| K201 | 2026-05-21 | 2026-05-22 | 2026-05-21 | 2026-11-19 | 2102351893 | 8202243401 |  | 2102341728#Pengambilan Breaker area 17 | RU2-HOC | 170-WHB-PIPING/00 | 01 | CRTD CSER MACM PRC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA1-LIS |  | DONITGN |  |  | PT02 | 3 | 2 | 2026-05-21 | PM |  | 005
| K401 | 2026-04-01 | 2026-05-26 | 2026-04-02 | 2026-12-30 | 2102354025 | 8202242013 |  | 2102341225#[CR] Perbaikan FT-28 | RU4-K3LL | FT28/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 57017638 | 57017638 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-04-01 | 2026-05-26 | 2026-04-02 | 2026-12-30 | 2102354026 | 8202242011 |  | 2102341224#[CR] Perbaikan FT-29 | RU4-K3LL | FT29/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 4421058 | 4421058 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-04-01 | 2026-05-26 | 2026-04-02 | 2026-12-30 | 2102354028 | 8202242015 |  | 2102341223#[CR] Perbaikan FT-41 | RU4-K3LL | FT41/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 66702472 | 66702472 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-04-01 | 2026-05-26 | 2026-04-02 | 2026-12-30 | 2102354027 | 8202242012 |  | 2102341222#[CR] Perbaikan FT-40 | RU4-K3LL | FT40/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 21503610 | 21503610 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-02-27 | 2026-03-05 | 2026-02-27 | 2026-10-29 | 2102354426 | 8202239247 |  | 2102341008#[CR] Penggantian Blade 11E5 | RU4-FOC1 | 11E50JM/00 | 60 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 113673760 | 0 | MA1-ROT |  | YMOHAMMAD |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 003
| K401 | 2026-04-01 | 2026-05-26 | 2026-04-02 | 2026-12-30 | 2102354840 | 8202242010 |  | 2102341003#[CR] Perbaikan FT-34 | RU4-K3LL | FT34/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 10955513 | 10955513 | WS-KAB |  | WAHYUCATUR |  | 2026-04-02 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-26 | 2026-05-21 | 2026-06-04 | 2102351213 | 8202243395 |  | 2102340865#Pressure switch rusak | RU2-HCC | 840-P-2/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 16490443 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 005
| K401 | 2026-05-04 | 2026-06-22 | 2026-02-02 | 2026-02-02 | 2102355587 | 8202242965 |  | 2102340811#[BD] Pompa 057P101A Jammed | RU4-UTL | 057P101A/01 | 50 | CRTD NMAT PRC | 4RR |  | 665392750 | 0 | MA5-ROT |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-02-02 | PM |  | 003
| K501 | 2026-02-23 | 2026-03-04 | 2026-12-01 | 2026-12-30 | 2102358907 | 8202239020 |  | 2102340472#Perbaikan Panel Listrik (T6) |  |  | 60 | CLSD NMAT PRC SETC | 5ER | D15/26/B6/RT-C2H | 215284000 | 0 | MA3-LIS |  | GHAGASP |  | 2026-02-23 | PT02 | 8 | 3 | 2026-03-04 | PM |  | 045
| K202 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2102352571 | 8202243978 |  | 2102340471#Perbaikan lantai ruangan la | RU2S-KIL | GDG-LAB/00 | 50 | REL NMAT PRC SETC | 2MS | D12/26/B6/NRZ-C2H | 128500000 | 0 | MAS-ME1 |  | JUNAIDIT |  | 2026-06-19 | PT02 | 4 | 3 | 2026-06-19 | PM |  | 003
| K501 | 2026-04-24 | 2026-04-28 | 2026-12-02 | 2026-12-02 | 2102359154 | 8202242726 |  | 2102340159#Perbaikan pompa G-202-02B | RU5-D&W | G-202-02B/00 | 50 | REL CSER MACM PRC SETC | 5RR | D15/26/B6/RT-C2H | 0 | 0 | MA1-ROT |  | ANDREAYR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-12-02 | PM |  | 003
| K401 | 2026-02-19 | 2026-05-13 | 2026-02-02 | 2026-12-30 | 2102353943 | 8202238966 |  | 2102340045#Perbaikan Pompa 38P110B | RU4-TRML | 38P110B/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 100 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-19 | 2026-05-13 | 2026-02-02 | 2026-12-30 | 2102353941 | 8202238965 |  | 2102340044#Perbaikan Pompa 38P110A | RU4-TRML | 38P110A/00 | 50 | REL CSER NMAT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 100 | 0 | MA3-ROT |  | FARIZSETYANA |  | 2026-03-06 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-11-18 | 2102351417 | 8202243313 |  | 2102340040#Penggantian Press Gauge | RU2-HSC | 301-P-4/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/XX/B6/RT-D2NH | 0 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 005
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-11-18 | 2102351416 | 8202243312 |  | 2102340009#Penggantian Press Gauge | RU2-HSC | 300-V-6/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA2-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 5 | 3 | 2026-05-19 | PM |  | 005
| K401 | 2026-03-06 | 2026-03-13 | 2026-03-06 | 2026-12-30 | 2102354592 | 8202241347 |  | 2102339841#perbaikan coupling 91K-401A | RU4-SRU | 91K401A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-03-13 | PT02 | 4 | 3 | 2026-03-06 | PM |  | 003
| K202 | 2026-04-22 | 2026-04-22 | 2026-02-02 | 2026-02-02 | 2102352584 | 8202242670 |  | 2102339748#Perbaikan Cooling Tower CT1 | RU2S-KIL | 900-07CT-1A/00 | 50 | REL GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 346152 | 346152 | MAS-ME1 |  | JUNIANTO |  | 2026-04-22 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K201 | 2026-05-19 | 2026-05-26 | 2026-05-19 | 2026-05-19 | 2102351591 | 8202243317 |  | 2102339689#Perbaikan sensor temperatur | RU2-UTL | 905-TE-1032A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 0 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-19 | PM |  | 005
| K401 | 2026-03-05 | 2026-04-28 | 2026-03-05 | 2026-12-30 | 2102355204 | 8202239470 |  | 2102339658#Penambahan line flushing ke | RU4-TRML | 33T3/00 | 50 | REL NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 100000 | 0 | MA3-STA |  | WAHYUCATUR |  | 2026-03-05 | PT02 | 4 | 3 | 2026-03-05 | PM |  | 045
| K401 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-12-30 | 2102355710 | 8202241360 |  | 2102339554#[CPI]Perbaikan Pompa 38P113 | RU4-TRML | 38P113A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 595800000 | 0 | WS-PMP |  | FARIZSETYANA |  | 2026-03-10 | PT02 | 5 | 3 | 2026-03-10 | PM |  | 003
| K201 | 2026-05-21 | 2026-05-26 | 2026-05-21 | 2026-11-19 | 2102351865 | 8202243402 |  | 2102338900#Perbaikan 905-TG-1 | RU2-UTL | 905-TE-1025A/00 | 50 | REL CSER MACM PRC SETC | 2IR | D12/26/B6/RT-D2H | 102371244 | 0 | MA3-INT |  | STEVANEKOPP |  | 2026-05-26 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 005
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102352054 | 8202243454 |  | 2102338656#Perbaikan Motor | RU2-HSC | 200-PM-2A/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 2349660 | 0 | MA2-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 5 | 3 | 2026-09-01 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102352055 | 8202243453 |  | 2102338655#Perbaikan Motor | RU2-HSC | 310-CM-1/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 3110000 | 0 | MA2-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 5 | 3 | 2026-05-25 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102352052 | 8202243455 |  | 2102338646#Perbaikan Motor 140 PC-51 | RU2-HOC | 140-PC-51/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 559255 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2102352056 | 8202243452 |  | 2102338601#Perbaikan 550-PM-104 | RU2-UTL | 550-PM-104/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA3-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102352057 | 8202243450 |  | 2102338496#Perbaikan Kontaktor MCC 940 | RU2-UTL | 940-EF-55AI/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 5636800 | 0 | MA3-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102351015 | 8202243448 |  | 2102338476#Pengambilan Contactor Gantr | RU2-HOC | 140-PC-51/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 0 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102351017 | 8202243446 |  | 2102338402#Perbaikan 140 PM-20B | RU2-HOC | 140-PM-20B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 5533750 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K401 | 2026-03-27 | 2026-06-03 | 2026-03-27 | 2026-07-29 | 2102353429 | 8202241905 |  | 2102338213#[CR] Penggantian shear pin | RU4-LOC2 | 024E102A/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 795675 | 636540 | MA2-ROT |  | FARIZSETYANA |  | 2026-03-27 | PT02 | 3 | 3 | 2026-03-27 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102351185 | 8202243443 |  | 2102337930#Motor 140 PM-6B High Vibrat | RU2-HOC | 140-PM-6B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 453119 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K201 | 2026-05-25 | 2026-05-25 | 2026-09-01 | 2026-09-01 | 2102351252 | 8202243437 |  | 2102337658#Perbaikan 110 EM-7B | RU2-HOC | 110-EM-7B/00 | 50 | REL CSER MACM PRC SETC | 2ER | D12/26/B6/RT-D2H | 2942440 | 0 | MA1-LIS |  | STEVANEKOPP |  | 2026-05-25 | PT02 | 3 | 3 | 2026-09-01 | PM |  | 003
| K202 | 2026-06-19 | 2026-06-22 | 2026-06-19 | 2026-06-19 | 2102352147 | 8202243965 |  | 2102336852#PM 900-06AC-1 dan 900-09AC- | RU2S-KIL | 900-09AC-4/01 | 50 | REL CSER MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 0 | 0 | MAS-ME1 |  | JUNIANTO |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-19 | PM |  | 003
| K201 | 2026-03-30 | 2026-05-19 | 2026-03-30 | 2026-12-31 | 2102364326 | 8202241935 |  | 2102335874#TSA 7 Alat Peralatan Lab RU | RU2-LAB | LAB-GAS-21/00 | 50 | CRTD NMAT PRC | 2IR | D12/25/B6/RT-D2H | 500000000 | 0 | WS-IN1 |  | ADEMULYADI |  |  | PT02 | 3 | 2 | 2026-03-30 | PM |  | 045
| K202 | 2026-04-22 | 2026-04-23 | 2026-02-02 | 2026-02-02 | 2102352180 | 8202242671 |  | 2102335804#Hydrant Fire Ground | RU2S-LKKK |  | 50 | REL PRC SETC | 2MS | D12/26/B6/RTZ-C2H | 0 | 0 | MAS-ME2 |  | JUNAIDIT |  | 2026-04-22 | PT02 | 8 | 3 | 2026-02-02 | PM |  | 045
| K201 | 2026-05-22 | 2026-05-26 | 2026-05-25 | 2026-05-25 | 2102364325 | 8202243431 |  | 2102335309#KONTRAK SCAFFOLDING AREA HO | RU2-HOC | 140-V-1A/00 | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 2153675000 | 0 | MA1-STA |  | ADEMULYADI |  | 2026-05-22 | PT02 | 3 | 3 | 2026-05-25 | PM |  | 003
| K201 | 2026-03-06 | 2026-05-12 | 2026-12-11 | 2026-12-11 | 2102364323 | 8202241338 |  | 2102335130#SERTIFIKASI T.U.METERING | RU2-ITP |  | 50 | REL NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 2100000000 | 0 | MA4-INT |  | ADEMULYADI |  | 2026-03-11 | PT02 | 5 | 3 | 2026-12-11 | PM |  | 045
| K201 | 2026-03-06 | 2026-06-17 | 2026-12-11 | 2026-12-11 | 2102364321 | 8202241337 |  | 2102335127#RK0025 TSA ATG | RU2-ITP |  | 50 | REL GMPS NMAT PRC SETC | 2MR | D12/26/B6/RT-D2H | 1200000000 | 406226000 | MA4-INT |  | ADEMULYADI |  | 2026-03-11 | PT02 | 5 | 3 | 2026-12-11 | PM |  | 045
| K202 | 2026-03-05 | 2026-03-09 | 2026-02-02 | 2026-02-02 | 2102352203 | 8202240697 |  | 2102334740# Motor 946-P-4C tidak bisa | RU2S-KIL | 946-P-4C-M/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/NRZ-C3H | 2107860 | 2107860 | MAS-LIS |  | JUNIANTO |  | 2026-03-06 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-04-23 | 2026-05-19 | 2026-02-02 | 2026-02-02 | 2102352208 | 8202242692 |  | 2102334318#Kebocoran Seal 946-P-1B | RU2S-KIL | 946-P-1B/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/RTZ-C1H | 94000000 | 94000000 | MAS-ME1 |  | JUNAIDIT |  | 2026-04-23 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K701 | 2026-04-05 | 2026-04-05 | 2026-01-02 | 2026-01-02 | 2102358566 | 8202242058 |  | 2102332327#Perbaikan Atap Dalam Kilang | RU7-CDU |  | 50 | REL NMAT PRC SETC | 7RT | D17/26/B6/RT-1-D2H | 1 | 0 | MA-STA |  | YAYANHER |  | 2026-04-05 | PT02 | 5 | 3 | 2026-01-02 | PM |  | 004
| K202 | 2026-02-25 | 2026-04-17 | 2026-02-02 | 2026-02-02 | 2102352240 | 8202239171 |  | 2102332210#101-P-6A indikasi High Vibr | RU2S-KIL | 101-P-6A/00 | 50 | REL CSER GMPS MACM PRC SETC | 2RS | D12/26/B6/NRZ-C1H | 18623100 | 14411627 | MAS-ME1 |  | JUNIANTO |  | 2026-02-25 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-03-06 | 2026-03-16 | 2026-02-02 | 2026-02-02 | 2102352245 | 8202241324 |  | 2102331423#900-02-P-LAGON WTP | RU2S-KIL | 4RW900081A-GALV/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C1H | 2600804 | 2600804 | MAS-ME1 |  | JUNIANTO |  | 2026-03-06 | PT02 | 4 | 3 | 2026-02-02 | PM |  | 003
| K202 | 2026-06-03 | 2026-06-05 | 2026-06-03 | 2026-06-03 | 2102352252 | 8202243605 |  | 2102331037#Emergency Isolation Valve 1 | RU2S-KIL | 101-D-2/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/RTZ-C2H | 55035000 | 55035000 | MAS-ME1 |  | JUNIANTO |  | 2026-06-04 | PT02 | 5 | 3 | 2026-06-03 | PM |  | 003
| K202 | 2026-04-14 | 2026-04-16 | 2026-02-02 | 2026-02-02 | 2102352269 | 8202242434 |  | 2102328975#946-P-1B-MCC/00 | RU2S-KIL | 946-P-1B-MCC/00 | 50 | REL CSER GMPS MACM PRC SETC | 2ES | D12/26/B6/RTZ-C1H | 6712000 | 6712000 | MAS-LIS |  | JUNIANTO |  | 2026-04-14 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-30 | 2026-03-04 | 2026-03-04 | 2102366039 | 8202239999 |  | 2102324681#Perbaikan limit switch 260P |  | 260PV345/00 | 01 | CLSD NCMP NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA4-INT |  | WAHYUCATUR |  |  | PT02 | 5 | 2 | 2026-03-30 | PM |  | 003
| K202 | 2026-03-06 | 2026-03-09 | 2026-02-02 | 2026-02-02 | 2102352306 | 8202241322 |  | 2102323756#Pompa Telaga Suri Perdana | RU2S-LKKK |  | 50 | REL GMPS MANC PRC SETC | 2MS | D12/26/B6/RTZ-C3H | 346152 | 346152 | MAS-ME2 |  | JUNIANTO |  | 2026-03-06 | PT02 | 8 | 3 | 2026-02-02 | PM |  | 045
| K202 | 2026-02-26 | 2026-03-09 | 2026-02-02 | 2026-02-02 | 2102352323 | 8202239222 |  | 2102321478#Penggantian V-Belt 101-E-6- | RU2S-KIL | 101-E-6F/00 | 50 | REL CSER GMPS MACM PRC SETC | 2MS | D12/26/B6/NRZ-C1H | 1589188 | 1589188 | MAS-ME1 |  | JUNIANTO |  | 2026-02-26 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-12-30 | 2102366688 | 8202242118 |  | 21_Perbaikan Analyzer 180AT603 | RU4-GTO | 140E607C-A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-04-13 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-03-09 | 2102366380 | 8202241762 |  | 180TT630 RUSAK | RU4-GTO | 180TT630/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-03-09 | 2102366348 | 8202241760 |  | 180TI641B rusak | RU4-GTO | 180TI641B/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-03-09 | 2102366347 | 8202241759 |  | 180TI641A rusak | RU4-GTO | 180TI641A/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-12-28 | 2102366349 | 8202241761 |  | 180TI628 RUSAK | RU4-GTO | 180TT628/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-12-21 | 2102366344 | 8202241757 |  | 180PT619 rusak | RU4-GTO | 180PT619/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-12-21 | 2102366342 | 8202241755 |  | 180PT613B rusak | RU4-GTO | 180PT613B/00 | 50 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-09 | 2026-12-29 | 2102366345 | 8202241758 |  | 180PI627 rusak | RU4-GTO | 180PT627/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-16 | 2026-03-10 | 2026-12-29 | 2102366381 | 8202241753 |  | 120TG019 FAULT | RU4-GTO | 120TT019/00 | 60 | REL CSER NMAT PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 0 | 0 | MA7-INT |  | WAHYUCATUR |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-10 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-12-30 | 2102367102 | 8202242161 |  | 11-P-115 AB | RU6-HSC | 11-P-115A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 5177613 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-04-07 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K401 | 2026-06-22 | 2026-06-22 | 2026-06-17 | 2026-06-17 | 2102370008 | 8202244018 |  | 100PCV632 membran sobek dan spring patah | RU4-GTO |  | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA7-INT |  | YMOHAMMAD |  |  | PT02 | 3 | 2 | 2026-06-22 | PM |  | 045
| K401 | 2026-06-11 |  | 2026-06-09 | 2026-06-09 | 2102369830 | 8202243804 |  | 024LT004 penunjukkan error | RU4-LOC2 | 024LT004/00 | 01 | CRTD CSER NMAT PRC | 4IR | D14/XX/B6/RT-C2NH | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-09 | PM |  | 003
| K401 | 2026-03-09 |  | 2026-03-03 | 2026-03-03 | 2102365199 | 8202241473 |  | 014PV009 error tidak mengontrol | RU4-FOC2 | 014PV009/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-03-03 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-09 | 2026-03-04 | 2026-03-04 | 2102365804 | 8202241471 |  | 014PV009 : Hunting | RU4-FOC2 | 014PV009/00 | 01 | CLSD CSER NCMP NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-04-09 | PM |  | 045
| K401 | 2026-03-17 |  | 2026-03-12 | 2026-03-12 | 2102366604 | 8202241805 |  | 014FV029 passing | RU4-FOC2 | 014FV029/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-03-12 | PM |  | 003
| K401 | 2026-05-20 |  | 2026-05-18 | 2026-05-18 | 2102369085 | 8202243340 |  | 011PCV001 - Control Valve Rusak | RU4-FOC2 | 011PCV001/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-18 | PM |  | 003
| K401 | 2026-05-20 | 2026-05-20 | 2026-05-18 | 2026-05-18 | 2102369048 | 8202243339 |  | 011PCV-002 rusak | RU4-FOC2 | 011PCV002/00 | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  | TYFFANIM |  |  | PT02 | 3 | 2 | 2026-05-18 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-21 | 2026-05-12 | 2026-12-30 | 2102369016 | 8202243727 |  | [TGH]T18(TKDN)-Perb Peralatan Kilang UTL | RU4-UTL | 051E101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 233726700 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-12-30 | 2102366149 | 8202241973 |  | [TGH]PM IAS termin 29 bulan januari 2026 |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 392100000 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-31 | PT02 | 3 | 3 | 2026-03-31 | PM |  | 045
| K401 | 2026-06-18 | 2026-06-21 | 2026-05-22 | 2026-12-30 | 2102369229 | 8202243930 |  | [TGH] Termin 3 Pek. PM Compressor IR | RU4-UTL | 56K201/00 | 50 | CRTD NMAT PRC | 4RR |  | 329959800 | 0 | MA5-ROT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-05-22 | PM |  | 003
| K401 | 2026-05-22 | 2026-06-22 | 2026-05-12 | 2026-12-30 | 2102368964 | 8202243420 |  | [TGH] Termin 15 UP Tenaga Bantu WS | RU4-WS | 037BD101/00 | 50 | CRTD NMAT PRC | 4RR |  | 655763950 | 0 | WS-PMP |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-05-12 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-11 | 2026-04-17 | 2026-12-30 | 2102368046 | 8202243031 |  | [TGH] Termin 14 UP Tenaga Bantu WS | RU4-WS | 037BD101/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 458996600 | 458996600 | WS-PMP |  | WAHYUCATUR |  | 2026-05-11 | PT02 | 3 | 3 | 2026-04-17 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-07 | 2026-04-28 | 2026-12-30 | 2102368508 | 8202243034 |  | [TGH] Termin 14 PM Recip. Komp FOC II | RU4-FOC2 | 011P114A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 50003800 | 50003800 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 045
| K401 | 2026-03-03 | 2026-06-19 | 2026-02-02 | 2026-12-30 | 2102364980 | 8202239368 |  | [TGH] Termin 13 UP Tenaga Bantu WS | RU4-WS | 037BD101-B11/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 628956650 | 628956650 | WS-PMP |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-05-06 | 2026-05-07 | 2026-04-28 | 2026-12-30 | 2102368507 | 8202243033 |  | [TGH] Termin 13 PM Recip. Komp FOC II | RU4-FOC2 | 014K102A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 69874250 | 69874250 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-07 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 045
| K401 | 2026-04-28 | 2026-05-12 | 2026-04-20 | 2026-12-30 | 2102368152 | 8202242785 |  | [TGH] Termin 1&2 Perb Peralatan Kilang | RU4-UTL | 054P106A/00 | 50 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 281127300 | 281127300 | MA5-ROT |  | AGHANIAKBAR |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 045
| K401 | 2026-02-27 | 2026-03-16 | 2026-03-16 | 2026-12-30 | 2102364877 | 8202239241 |  | [TGH] Termin 1 LTSA Steam Turbine | RU4-UTL | 53P1A-T/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 329800000 | 329800000 | WS-PMP |  | FARIZSETYANA |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-21 | 2026-06-03 | 2026-12-30 | 2102369509 | 8202243872 |  | [TGH] Term-7 Perb Diesel Enginer Cummins | RU4-UTL | 52B203/00 | 50 | CRTD NMAT PRC | 4RR |  | 473639550 | 0 | MA5-ROT |  | WAHYUCATUR |  |  | PT02 | 3 | 2 | 2026-06-03 | PM |  | 045
| K401 | 2026-02-12 | 2026-03-27 | 2026-03-27 | 2026-12-30 | 2102363996 | 8202238892 |  | [TGH] Tagihan Termin 11 PM Reciprocating | RU4-FOC2 | 013K101A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 68676600 | 68676600 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-27 | PT02 | 3 | 3 | 2026-03-27 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-26 | 2026-04-29 | 2026-12-30 | 2102368552 | 8202243494 |  | [TGH] Tagihan SootBlower 025F101 Termin3 | RU4-LOC2 | 025F101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 124388150 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 6 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-26 | 2026-04-29 | 2026-12-30 | 2102368551 | 8202243483 |  | [TGH] Tagihan SootBlower 025F101 Termin2 | RU4-LOC2 | 025F101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 125231350 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 6 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-05-25 | 2026-05-26 | 2026-04-29 | 2026-12-30 | 2102368550 | 8202243482 |  | [TGH] Tagihan SootBlower 025F101 Termin1 | RU4-LOC2 | 025F101/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 128135800 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-26 | PT02 | 6 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-03-10 | 2026-04-15 | 2026-03-10 | 2026-12-30 | 2102366315 | 8202241510 |  | [TGH] Tagihan Mech Seal 023P104 | RU4-LOC2 | 023P104/00 | 60 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 115912800 | 115912800 | WS-PMP |  | YUNITAMR |  | 2026-03-10 | PT02 | 4 | 3 | 2026-03-10 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-05 | 2026-04-01 | 2026-12-30 | 2102367585 | 8202242990 |  | [TGH] Tagihan Mech Seal 021P104 | RU4-LOC2 | 021P104/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 113016000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-05-05 | PT02 | 5 | 3 | 2026-04-01 | PM |  | 003
| K401 | 2026-06-12 | 2026-06-12 | 2026-06-02 | 2026-06-02 | 2102369399 | 8202243834 |  | [TGH] Tagihan 5 Pemeliharaan MAC |  |  | 50 | CRTD NMAT PRC | 4RR |  | 90386010 | 0 | WS-KAB |  | ABDULFM |  |  | PT02 | 3 | 2 | 2026-06-02 | PM |  | 045
| K401 | 2026-02-27 | 2026-03-03 | 2026-02-27 | 2026-12-30 | 2102364875 | 8202239238 |  | [TGH] Tagihan 4 Pemeliharaan MAC | RU4-WS | 037BD101/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 146617290 | 146617290 | WS-KAB |  | WAHYUCATUR |  | 2026-02-27 | PT02 | 3 | 3 | 2026-02-27 | PM |  | 045
| K401 | 2026-06-10 | 2026-06-21 | 2026-05-12 | 2026-12-30 | 2102369015 | 8202243728 |  | [TGH] T3-Perb Peralatan Kilang Area UTL | RU4-UTL | 52B1/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 64719000 | 0 | MA5-ROT |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-05-12 | PM |  | 045
| K401 | 2026-02-24 | 2026-03-16 | 2026-03-04 | 2026-12-30 | 2102364591 | 8202239093 |  | [TGH] Refurbishment 024K101 & 024K102T | RU4-LOC2 | 024K101/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 496593000 | 496593000 | WS-PMP |  | FARIZSETYANA |  | 2026-03-04 | PT02 | 6 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367551 | 8202243174 |  | [TGH] PM Sootblower Paket 8 FOC II |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 112092900 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367550 | 8202243173 |  | [TGH] PM Sootblower Paket 7 FOC II |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 112860450 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367539 | 8202243172 |  | [TGH] PM Sootblower Paket 6 FOC II |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 114710900 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367538 | 8202243171 |  | [TGH] PM Sootblower Paket 5 FOC II |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 111219100 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367537 | 8202243170 |  | [TGH] PM Sootblower Paket 4 FOC II |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 141503750 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367536 | 8202243168 |  | [TGH] PM Sootblower Paket 3 FOC II |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 112509400 | 112509400 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-12-30 | 2102367535 | 8202243122 |  | [TGH] PM Sootblower Paket 2 FOC II |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 116872450 | 116872450 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 045
| K401 | 2026-04-06 | 2026-04-14 | 2026-04-02 | 2026-12-30 | 2102367311 | 8202242114 |  | [TGH] PM Reciprocating Kompresor FOC 2 | RU4-FOC2 | 014K102C/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 68610300 | 68610300 | MA2-ROT |  | AGHANIAKBAR |  | 2026-04-08 | PT02 | 3 | 3 | 2026-04-02 | PM |  | 003
| K401 | 2026-04-27 | 2026-04-27 | 2026-04-14 | 2026-12-30 | 2102367936 | 8202242729 |  | [TGH] PM Air Compressor IR Termin 2 | RU4-UTL | 56K201/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 137802000 | 137802000 | MA5-ROT |  | WAHYUCATUR |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-14 | PM |  | 004
| K401 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-12-30 | 2102364950 | 8202243121 |  | [TGH] perbaikan soot blower FOC 2 paket | RU4-FOC2 | 011F101A01/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 93475350 | 93475350 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-11 | PT02 | 3 | 3 | 2026-05-11 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-21 | 2026-04-06 | 2026-12-30 | 2102366506 | 8202242062 |  | [TGH] Perbaikan pompa foam FT-39 | RU4-K3LL | FT39/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 53852806 | 53852806 | WS-KAB |  | WAHYUCATUR |  | 2026-04-06 | PT02 | 5 | 3 | 2026-04-06 | PM |  | 045
| K401 | 2026-05-11 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102368045 | 8202243118 |  | [TGH] Perbaikan pompa CPI 20P-2 | RU4-LOC1 | 20P2/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 62280350 | 62280350 | WS-PMP |  | FARIZSETYANA |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-04-27 | 2026-06-18 | 2026-04-13 | 2026-12-30 | 2102367873 | 8202242732 |  | [TGH] Perbaikan pompa 70P2C | RU4-K3LL | 70P2C/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 948515000 | 948515000 | WS-PMP |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-04-27 | 2026-06-18 | 2026-04-13 | 2026-12-30 | 2102367872 | 8202242731 |  | [TGH] Perbaikan pompa 70P2B dan 70P2BG | RU4-K3LL | 70P2B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-4-C2H | 1030837500 | 1030837500 | MA3-ROT |  | FARIZSETYANA |  | 2026-04-27 | PT02 | 3 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-06-08 | 2026-06-20 | 2026-05-26 | 2026-12-30 | 2102369347 | 8202243672 |  | [TGH] Perbaikan 10P2 | RU4-FOC1 | 10P2/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 66178450 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-20 | PT02 | 3 | 3 | 2026-05-26 | PM |  | 003
| K401 | 2026-05-11 | 2026-06-22 | 2026-05-05 | 2026-05-05 | 2102368717 | 8202243123 |  | [TGH] Perbaikan 103P514A TSA Krone (Tagi | RU4-RFCC | 103P514A/00 | 50 | CRTD NMAT PRC | 4RR |  | 229385250 | 0 | WS-PMP |  | SAMSUDINH |  |  | PT02 | 3 | 2 | 2026-05-05 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102364715 | 8202239038 |  | [TGH] Penggantian Mechanical Seal 051P10 | RU4-UTL | 051P103A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 80082750 | 80082750 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102364716 | 8202239040 |  | [TGH] Penggantian Mech Seal 54P202D | RU4-UTL | 54P202D/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 91681850 | 91681850 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-06-17 | 2026-06-21 | 2026-06-19 | 2026-12-30 | 2102369504 | 8202243873 |  | [TGH] Penggantian mech seal 54P202C | RU4-UTL | 54P202C/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 77206350 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-06-09 | 2026-06-21 | 2026-06-19 | 2026-12-30 | 2102369505 | 8202243718 |  | [TGH] Penggantian mech seal 54P202A | RU4-UTL | 54P202A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 154411850 | 0 | WS-PMP |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-04-06 | 2026-05-05 | 2026-04-06 | 2026-12-30 | 2102366454 | 8202242060 |  | [TGH] Penggantian Cylinder Head |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 165750000 | 165750000 | WS-KAB |  | FARIZSETYANA |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 045
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102368570 | 8202243167 |  | [TGH] Penagihan pompa 019P124B Paket 9 | RU4-FOC2 | 019P124B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 67484750 | 67484750 | WS-PMP |  | FARIZSETYANA |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-02-12 | 2026-03-30 | 2026-02-02 | 2026-12-31 | 2102364176 | 8202238891 |  | [TGH] Penagihan pemeliharaan 12K1 dan 13 | RU4-FOC1 | 12K1A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 584131250 | 435398900 | MA1-ROT |  | AGHANIAKBAR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 045
| K401 | 2026-03-13 | 2026-04-15 | 2026-03-09 | 2026-12-31 | 2102366674 | 8202241713 |  | [TGH] Penagihan LTSA Mseal 87P204A | RU4-KPC | 87P204A/00 | 60 | REL GMCO GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 144219500 | 144219500 | WS-PMP |  | YUNITAMR |  | 2026-03-16 | PT02 | 5 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-02-26 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102364705 | 8202239203 |  | [TGH] Pemasangan Mech Seal john crane | RU4-FOC1 | 11P17A/00 | 50 | REL CSER GMPS MACM PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 92092400 | 92092400 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-12-30 | 2102364103 | 8202241315 |  | [TGH] Kontrak PM Rotating Eqp termin 28 |  |  | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 441900000 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 045
| K401 | 2026-03-12 | 2026-04-15 | 2026-03-12 | 2026-12-30 | 2102366456 | 8202241615 |  | [TGH] Assessment Unit FT-40 & FT-41 | RU4-K3LL | FT40/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 13740701 | 13740701 | WS-KAB |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-02-23 | 2026-04-07 | 2026-02-02 | 2026-12-30 | 2102363998 | 8202239035 |  | [TGH] 011P112A mech seal bocor OB | RU4-FOC2 | 011P112A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 86290300 | 86290300 | WS-PMP |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-02-23 | 2026-03-03 | 2026-02-02 | 2026-12-30 | 2102363999 | 8202239037 |  | [TGH] 011P112A mech seal bocor IB | RU4-FOC2 | 011P112A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 86290300 | 86290300 | WS-PMP |  | WAHYUCATUR |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-02 | PM |  | 003
| K401 | 2026-05-05 | 2026-05-11 | 2026-04-21 | 2026-12-30 | 2102368250 | 8202242989 |  | [TGH] 011P106B Mech seal bocor | RU4-FOC2 | 011P106B/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 186284000 | 0 | MA2-ROT |  | WAHYUCATUR |  | 2026-05-05 | PT02 | 3 | 3 | 2026-04-21 | PM |  | 003
| K401 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367909 | 8202243166 |  | [TGH] Perbaikan Pompa CPI 48P202 |  |  | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-10-C2H | 40022150 | 40022150 | WS-PMP |  | WAHYUCATUR |  | 2026-05-13 | PT02 | 5 | 3 | 2026-05-13 | PM |  | 045
| K401 | 2026-03-12 | 2026-06-18 | 2026-02-24 | 2026-12-30 | 2102364828 | 8202241636 |  | [RKAP25] Pengecetan 540T401-402 | RU4-UTL | 540A601T/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/NR-5-C2H | 600600000 | 600600000 | MA5-STA |  | WAHYUCATUR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-02-24 | PM |  | 045
| K401 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-11-30 | 2102368319 | 8202242835 |  | [PV] Pengadaan Material 14K602A | RU4-FOC1 | 14K602A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 45221100 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-29 | PM |  | 003
| K401 | 2026-02-24 | 2026-03-16 | 2026-03-04 | 2026-12-30 | 2102364612 | 8202239091 |  | [PGH]Refurbishment rotor 240K101 & 240K1 | RU4-LOC3 | 240K102/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 319984000 | 319984000 | WS-PMP |  | FARIZSETYANA |  | 2026-03-04 | PT02 | 5 | 3 | 2026-03-04 | PM |  | 003
| K401 | 2026-04-28 | 2026-05-12 | 2026-04-28 | 2026-12-22 | 2102367929 | 8202242804 |  | [MSP]_Perbaikan Part Pneumix 101A525A/B | RU4-RFCC | 101A525A/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 0 | 0 | MA6-INT |  | FARIZSETYANA |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-03-16 | 2026-04-28 | 2026-03-09 | 2026-12-28 | 2102366341 | 8202241765 |  | [MSP]_48PG601A rusak | RU4-GTO | 48PI001A/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-3-C2H | 1128493 | 0 | MA7-INT |  | FATAHALFI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-16 | 2026-04-28 | 2026-03-16 | 2026-12-30 | 2102366346 | 8202241764 |  | [MSP]_180PI622 rusak | RU4-GTO | 180PT622/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-14-C2H | 1370895 | 0 | MA7-INT |  | FATAHALFI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-28 | 2026-03-16 | 2026-12-30 | 2102366257 | 8202241464 |  | [MSP]_140PG102 rusak | RU4-GTO | 140PI102/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 1328614 | 0 | MA7-INT |  | FATAHALFI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-28 | 2026-03-16 | 2026-12-30 | 2102366259 | 8202241463 |  | [MSP]_140PG100F rusak | RU4-GTO | 140PI100F/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 1128493 | 0 | MA7-INT |  | FATAHALFI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-28 | 2026-03-16 | 2026-12-30 | 2102366258 | 8202241462 |  | [MSP]_140PG077A rusak | RU4-GTO | 140PI077A/00 | 60 | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 1128493 | 0 | MA7-INT |  | FATAHALFI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-03-09 | 2026-04-28 | 2026-03-16 | 2026-12-30 | 2102366145 | 8202241468 |  | [MSP]_120PG068 rusak | RU4-GTO | 120PI068/00 | 60 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-15-C2H | 1355534 | 0 | MA7-INT |  | FATAHALFI |  | 2026-03-16 | PT02 | 3 | 3 | 2026-03-16 | PM |  | 003
| K401 | 2026-05-20 | 2026-06-19 | 2026-05-20 | 2026-09-29 | 2102368625 | 8202243332 |  | [CR] Perbaikan Turbin 54P1AT | RU4-UTL | 54P1A-T/00 | 50 WAMA | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-20 | PM |  | 003
| K401 | 2026-03-03 | 2026-05-21 | 2026-03-03 | 2026-04-06 | 2102365009 | 8202239385 |  | [CR] Perbaikan Pompa ALOP 057P101AP1 | RU4-UTL | 057P101A/01 | 60 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-5-C2H | 1 | 0 | MA5-ROT |  | YMOHAMMAD |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-03 | PM |  | 003
| K401 | 2026-04-27 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367856 | 8202242734 |  | [CR] Perbaikan pompa 166P502A ROT-MA7 | RU4-RFCUTL | 166P502A/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 58878500 | 58878500 | WS-PMP |  | FARIZSETYANA |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-04-27 | 2026-05-13 | 2026-05-13 | 2026-12-30 | 2102367855 | 8202242733 |  | [CR] Perbaikan pompa 166P501B ROT-MA7 | RU4-RFCUTL | 166P501B/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-14-C2H | 53872000 | 53872000 | WS-PMP |  | FARIZSETYANA |  | 2026-05-13 | PT02 | 3 | 3 | 2026-05-13 | PM |  | 003
| K401 | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-12-30 | 2102366455 | 8202241729 |  | [CR] Perbaikan FT-30 (Overhaull) | RU4-K3LL | FT30/00 | 50 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 1154657000 | 1154657000 | WS-KAB |  | WAHYUCATUR |  | 2026-03-17 | PT02 | 3 | 3 | 2026-03-17 | PM |  | 045
| K401 | 2026-03-11 | 2026-04-15 | 2026-03-12 | 2026-12-30 |  | 8202241591 | 8202239102 | [CR] Perbaikan FT-27 | RU4-WS | FL50/00 | 60 | REL GMPS NMAT PRC SETC | 4RR | D14/26/B6/RT-15-C2H | 60305447 | 60305447 | WS-KAB |  | YUNITAMR |  | 2026-03-12 | PT02 | 3 | 3 | 2026-03-12 | PM |  | 045
| K401 | 2026-06-02 | 2026-06-20 | 2026-06-08 | 2026-12-30 | 1102332174 | 8202243576 |  | [CR] Perbaikan Dump Truck R 9260CT | RU4-WS | 037BD101-HIJ/00 | 50 WASR | CRTD NMAT PRC | 4MR | D14/26/B6/RT-15-C2H | 750000000 | 0 | WS-KAB |  | FARIZSETYANA |  |  | PT02 | 5 | 2 | 2026-06-08 | PM |  | 045
| K401 | 2026-06-09 | 2026-06-22 | 2026-05-11 | 2026-05-11 | 2102368942 | 8202243715 |  | [CR] Penggantian Valve 13K1B | RU4-FOC1 | 13K1B/00 | 50 WAMA | CRTD CSER MACM PRC | 4RR |  | 976492000 | 0 | MA1-ROT |  | FARIZSETYANA |  |  | PT02 | 3 | 2 | 2026-05-11 | PM |  | 003
| K401 | 2026-06-10 | 2026-06-22 | 2026-06-19 | 2026-12-22 | 2102369601 | 8202243741 |  | [CR] Penggantian Teflon Coupling024S101C | RU4-LOC2 | 024S101C/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 5077000 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 3 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-06-09 | 2026-06-22 | 2026-06-19 | 2026-12-22 | 2102369551 | 8202243720 |  | [CR] Penggantian Mech Seal OB 022P104B | RU4-LOC2 | 022P104B/00 | 50 | REL CSER MACM PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 331774650 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-06-22 | PT02 | 4 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-06-11 | 2026-06-21 | 2026-06-19 | 2026-12-30 | 2102369492 | 8202243776 |  | [CR] Penggantian mech seal 24P-13A | RU4-LOC1 | 24P13A/00 | 50 | REL NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 80979500 | 0 | MA1-ROT |  | WAHYUCATUR |  | 2026-06-21 | PT02 | 4 | 3 | 2026-06-19 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-06 | 2026-05-04 | 2026-05-04 | 2102364905 | 8202242109 |  | [CR] Penggantian Kompressor 81A201K1A | RU4-KPC | 81A201K1A/00 | 01 | CRTD CSER MACM PRC | 4RR |  | 16500000000 | 0 | MA4-ROT |  | AGHANIAKBAR |  |  | PT02 | 5 | 2 | 2026-05-04 | PM |  | 004
| K401 | 2026-03-17 | 2026-03-30 | 2026-03-30 | 2026-09-29 | 2102366752 | 8202241819 |  | [CR] Mech seal 24P-5 netes/bocor | RU4-LOC1 | 24P5/00 | 50 WAMA | REL CSER MSPT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | FARIZSETYANA |  | 2026-03-30 | PT02 | 3 | 3 | 2026-03-30 | PM |  | 003
| K401 | 2026-05-21 | 2026-06-03 | 2026-05-21 | 2026-11-30 | 2102369113 | 8202243359 |  | [CR] 023P110A Mech Seal Bocor | RU4-LOC2 | 023P110A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-8-C2H | 102722400 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-05-21 | PT02 | 3 | 3 | 2026-05-21 | PM |  | 003
| K401 | 2026-05-18 | 2026-06-03 | 2026-05-18 | 2026-10-29 | 2102368866 | 8202243245 |  | [CR] 011P118A Mech. Seal bocor | RU4-FOC2 | 011P118A/00 | 50 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 61256500 | 0 | MA2-ROT |  | FARIZSETYANA |  | 2026-05-18 | PT02 | 3 | 3 | 2026-05-18 | PM |  | 003
| K401 | 2026-03-05 | 2026-05-21 | 2026-03-05 | 2026-11-24 | 2102364628 | 8202239477 |  | [CR] 011K101C cly 1 suct temp 150 DegC | RU4-FOC2 | 011K101C/00 | 60 WAMA | REL CSER MANC PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 15056726 | 0 | MA2-ROT |  | YMOHAMMAD |  | 2026-03-05 | PT02 | 3 | 3 | 2026-03-05 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-24 | 2026-04-06 | 2026-12-29 | 2102367315 | 8202242090 |  | [BON PNJM]_Perbaikan LT Displacer 21LT01 | RU4-LOC1 | 21LT013/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 30598949 | 30598949 | MA1-INT |  | TEGARPRAMUDY |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-24 | 2026-04-06 | 2026-12-29 | 2102367317 | 8202242091 |  | [BON PNJM]_Perbaikan LT Displacer 21LT01 | RU4-LOC1 | 21LT014/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 30598949 | 30598949 | MA1-INT |  | TEGARPRAMUDY |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-06 | 2026-04-24 | 2026-04-06 | 2026-12-29 | 2102367318 | 8202242092 |  | [BON PNJM]_Perbaikan LT Displacer 21LT01 | RU4-LOC1 | 21LT015/00 | 50 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-7-C2H | 30598949 | 30598949 | MA1-INT |  | TEGARPRAMUDY |  | 2026-04-06 | PT02 | 3 | 3 | 2026-04-06 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-12-29 | 2102367987 | 8202242561 |  | [BON PNJM]_Perbaikan Control Valve Assy | RU4-SRU | 91KV311B/00 | 50 | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 144000000 | 144000000 | MA1-INT |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-04-20 | 2026-05-21 | 2026-04-20 | 2026-12-29 | 2102367988 | 8202242562 |  | [BON PNJM]_Perbaikan Control Valve Assy | RU4-SRU | 91KV311C/00 | 50 WAMA | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 144000000 | 0 | MA1-INT |  | YMOHAMMAD |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-12-29 | 2102368091 | 8202242563 |  | [BON PNJM]_Perbaikan Control Valve Assy | RU4-SRU | 91KV312C/00 | 50 | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 811000000 | 811000000 | MA1-INT |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-12-29 | 2102367989 | 8202242566 |  | [BON PNJM]_Perbaikan Control Valve Assy | RU4-SRU | 91KV332A/00 | 50 | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 660000000 | 660000000 | MA1-INT |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-04-20 | 2026-05-06 | 2026-04-20 | 2026-12-29 | 2102368090 | 8202242568 |  | [BON PNJM]_Perbaikan Control Valve Assy | RU4-SRU | 91KV332C/00 | 50 | REL MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-INT |  | WAHYUCATUR |  | 2026-04-20 | PT02 | 3 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-04-21 | 2026-05-21 | 2026-04-28 | 2026-06-29 | 2102368092 | 8202242635 |  | [BON PNJM]_Perbaikan Control Valve Assy | RU4-SRU | 94FV111/00 | 60 WAMA | REL GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 120500000 | 120500000 | MA1-INT |  | YMOHAMMAD |  | 2026-04-28 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K401 | 2026-04-13 | 2026-04-24 | 2026-04-13 | 2026-12-29 | 2102367701 | 8202242371 |  | [BON PNJM]_85PV240 positioner rusak | RU4-KPC | 85PV240/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 23454546 | 23454546 | MA4-INT |  | TEGARPRAMUDY |  | 2026-04-14 | PT02 | 4 | 3 | 2026-04-13 | PM |  | 003
| K401 | 2026-04-20 | 2026-05-21 | 2026-04-20 | 2026-12-29 | 2102367927 | 8202242572 |  | [BON PINJM]_Perbaikan Panel HMI SB 101F5 | RU4-RFCC | 101F503/00 | 50 WAMA | REL CSER MACM PRC SETC | 4IR | D14/26/B6/RT-12-C2H | 46122318 | 0 | MA6-INT |  | YMOHAMMAD |  | 2026-04-20 | PT02 | 8 | 3 | 2026-04-20 | PM |  | 003
| K401 | 2026-02-23 | 2026-02-23 | 2026-01-02 | 2026-01-02 |  | 8202239049 |  | (DELETED) | RU4-UTL | 051G102/00 | 01 | CLSD CSER DLFL NCMP NMAT PRC SETC | 4ER | D14/26/B6/RT-5-C2H | 0 | 0 | MA5-LIS |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-02-23 | PM |  | 045
| K401 | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 |  | 8202239736 |  | (DELETED) | RU4-LOC3 | 260PV345/00 | 01 | CLSD CSER DLFL NCMP NMAT PRC SETC | 4IR | D14/25/B6/RTC-9-C2H | 0 | 0 | MA4-INT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-09 | 2026-03-05 | 2026-03-05 |  | 8202239795 |  | (DELETED) | RU4-TRML | 36M105A/00 | 01 | CLSD CSER DLFL NCMP NMAT PRC SETC | 4RR | D14/25/B6/RTC-3-C2H | 0 | 0 | MA3-ROT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-09 | 2026-01-02 | 2026-01-02 |  | 8202240610 |  | (DELETED) | RU4-SRU | 91K401A/00 | 01 | CLSD DLFL NCMP NMAT PRC SETC | 4RR | D14/26/B6/RT-1-C2H | 0 | 0 | MA1-ROT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-09 | 2026-01-02 | 2026-01-02 |  | 8202241211 |  | (DELETED) | RU4-SRU | 91K401A/00 | 01 | CLSD DLFL NCMP NMAT PRC SETC | 4RR | D14/26/B6/RT-7-C2H | 0 | 0 | MA1-ROT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-09 | 2026-01-13 | 2026-01-13 |  | 8202241268 |  | (DELETED) | RU4-FOC2 | 013S105BM/00 | 01 | CLSD CSER DLFL NCMP NMAT PRC SETC | 4RR | D14/26/B6/RT-2-C2H | 0 | 0 | MA2-ROT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-03 | 2026-06-18 | 2026-02-19 | 2026-12-30 | 2102364626 | 8202239333 |  | TGH4_UP Floating Hose SPM 2024-2026 | RU4-TRML | SPM/00 | 50 | REL CSER GMPS NMAT PRC SETC | 4MR | D14/26/B6/RT-3-C2H | 839043000 | 839043000 | MA3-STA |  | FARIZSETYANA |  | 2026-03-03 | PT02 | 3 | 3 | 2026-02-19 | PM |  | 045
| K401 | 2026-06-22 |  | 2026-06-02 | 2026-06-02 | 2102369502 | 8202244030 |  | TGH1_UP Fire Proofing ME II Tahun 2025 | RU4-RFCC | 102A501/00 | 50 | CRTD CSER NMAT PRC | 4MR |  | 1467097000 | 0 | MA6-STA |  |  |  |  | PT02 | 8 | 2 | 2026-06-02 | PM |  | 045
| K601 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-09-16 |  | 8202244004 | 8202242227 | Tgh ke 6 Pemeliharaan Rutin MA 2 | RU6-DHC | 12-R-101/00 | 50 | REL NMAT PRC SETC | 6MR | D16/26/B6/RT-C2H | 68226000 | 0 | MA2-STA |  | DANDARWANI |  | 2026-06-22 | PT02 | 5 | 3 | 2026-06-22 | PM |  | 003
| K301 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-12-31 |  | 8202243993 | 8202238248 | Tag 13 Pek IPAL Domestik | RU3-LKKK | 33-SH-IPAL/00 | 50 | REL NMAT PRC SETC | 3MR | D13/26/B6/RT-2-D2H | 40688650 | 0 | GEN-STA |  | RRAMADHANI |  | 2026-06-22 | PT02 |  | 3 | 2026-06-22 | PM |  | 003
| K401 | 2026-06-02 |  | 2026-05-26 | 2026-05-26 | 2102369349 | 8202243569 |  | perbaikan transmitter 154FT755A | RU4-RFCUTL |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-26 | PM |  | 045
| K601 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-12-08 | 2102361723 | 8202243882 |  | Perbaikan Positioner Ctrl Vlv 42-HV-412 | RU6-ITP | 42-T-101F/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 32209 | 0 | MA4-INT |  | DANDARWANI |  | 2026-06-17 | PT02 | 4 | 3 | 2026-06-17 | PM |  | 003
| K501 | 2026-03-05 | 2026-04-16 | 2026-03-06 | 2026-06-06 | 2102366115 | 8202240702 |  | perbaikan pompa G-5-02A | RU5-E15111 | G-5-02A/00 | 50 | REL CSER MANC PRC SETC | 5RR | D15/26/B6/RT-C2H | 2521519 | 0 | MA2-ROT |  | ANDREAYR |  | 2026-03-06 | PT02 | 3 | 3 | 2026-03-06 | PM |  | 003
| K601 | 2026-04-15 | 2026-04-17 | 2026-04-15 | 2026-07-21 | 2102366316 | 8202242470 |  | Perbaikan AC No. 6 di SS17 | RU6-HSC | SS-17/00 | 50 WAMA | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 0 | 0 | WS-INT |  | DANDARWANI |  | 2026-04-17 | PT02 | 5 | 3 | 2026-04-15 | PM |  | 003
| K401 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2102369017 | 8202243189 |  | Perbaikan 520 FT 701 |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA5-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-13 | PM |  | 045
| K601 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-06-30 | 2102368525 | 8202242815 |  | Perbaikan 20-E-108D | RU6-RCC | 20-E-108D/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1637695 | 1478752 | MA1-LIS |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-06-30 | 2102368524 | 8202242814 |  | Perbaikan 20-E-104B | RU6-RCC | 20-E-104B/00 | 50 | REL CSER GMPS MACM PRC SETC | 6ER | D16/26/B6/RT-C2H | 1637695 | 1478751 | MA1-LIS |  | DANDARWANI |  | 2026-04-29 | PT02 | 3 | 3 | 2026-04-28 | PM |  | 003
| K601 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-06-04 | 2102367521 | 8202242142 |  | Penggantian Positioner CV 31-LIC-005 | RU6-HSC | 31-LV-005/00 | 50 | REL CSER MACM PRC SETC | 6IR | D16/26/B6/RT-C2H | 144709392 | 0 | MA3-INT |  | DANDARWANI |  | 2026-04-07 | PT02 | 5 | 3 | 2026-04-07 | PM |  | 003
| K601 | 2026-05-05 | 2026-05-05 | 2026-04-09 | 2026-08-26 | 2102367707 | 8202242991 |  | pengadaan filter element 11-P-132 AB | RU6-HSC | 11-P-132A/00 | 50 WAMA | REL CSER MACM PRC SETC | 6RR | D16/26/B6/RT-C2H | 2 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-05-05 | PT02 | 5 | 3 | 2026-04-09 | PM |  | 005
| K501 | 2026-04-06 |  | 2026-05-29 | 2026-05-29 | 2102366358 | 8202242069 |  | Pek. TSA PM Metering System All Area OM | RU5-TBL | 22-716B/00 | 01 | CRTD CSER NMAT PRC | 5IR | D15/26/B6/RT-C2H | 0 | 0 | MA4-INT |  |  |  |  | PT02 | 3 | 2 | 2026-05-29 | PM |  | 045
| K401 | 2026-06-22 |  | 2026-06-19 | 2026-06-19 | 2102370163 | 8202243989 |  | optimalisasi program digitalisasi aset |  |  | 01 | CRTD CSER NMAT PRC | 4IR |  | 0 | 0 | MA2-INT |  |  |  |  | PT02 | 3 | 2 | 2026-06-19 | PM |  | 045
| K401 | 2026-04-15 | 2026-04-24 | 2026-04-15 | 2026-10-14 | 2102366885 | 8202242475 |  | erbaikan motor 12P2M | RU4-FOC1 | 12P2M/00 | 50 WAMA | REL CSER GMPS MACM PRC SETC | 4ER | D14/26/B6/RT-1-C2H | 3029200 | 3029200 | MA1-LIS |  | TEGARPRAMUDY |  | 2026-04-16 | PT02 | 3 | 3 | 2026-04-15 | PM |  | 045
| K601 | 2026-02-27 | 2026-03-03 | 2026-02-26 | 2026-04-17 | 2102365031 | 8202239250 |  | 23-P-901B tagihan LTSA | RU6-HSC | 23-P-901B/00 | 50 | REL NMAT PRC SETC | 6RR | D16/26/B6/RT-C2H | 55956000 | 0 | MA1-ROT |  | DANDARWANI |  | 2026-03-03 | PT02 | 5 | 3 | 2026-02-26 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-09 | 2026-03-06 | 2026-03-06 |  | 8202241033 |  | (DELETED) | RU4-KPC | 84E202D/00 | 01 | CLSD CSER DLFL NCMP NMAT PRC SETC | 4RR | D14/25/B6/RTC-10-C2H | 0 | 0 | MA4-ROT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-09 | 2026-01-02 | 2026-01-02 |  | 8202241086 |  | (DELETED) | RU4-SRU | 91LV112/00 | 01 | CLSD DLFL NCMP NMAT PRC SETC | 4IR | D14/26/B6/RT-6-C2H | 0 | 0 | MA1-INT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003
| K401 | 2026-03-05 | 2026-03-09 | 2026-01-07 | 2026-01-07 |  | 8202241227 |  | (DELETED) | RU4-KPC | 86K201/00 | 01 | CLSD CSER DLFL MACM NCMP PRC SETC | 4IR | D14/26/B6/RT-10-C2H | 545915667 | 0 | MA4-INT |  | T_YUDIPRAS |  |  | PT02 |  | 2 | 2026-03-09 | PM |  | 003